{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":5,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Schedule","index":1,"n_rows":1359,"n_cols":45,"rows_kept":1359,"cut":false,"hidden":false,"merged":[[0,35,0,36],[0,37,0,38],[0,39,0,40],[2,43,2,44],[1,23,1,27],[1,30,2,30],[1,36,2,36],[1,37,2,37],[1,38,2,38],[1,39,2,39],[1,40,2,40],[1,41,2,41],[1,42,2,42],[1,34,2,34],[1,1,2,1],[1,3,2,3],[1,33,2,33],[1,32,2,32],[1,31,2,31],[1,29,2,29],[1,28,2,28],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22],[1,17,2,17],[1,4,2,4],[1,15,2,15],[1,16,2,16],[1,2,2,2]]}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day\n(character of timely closure)","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In annual timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"PLC\n(ÖBB)"]
[null,80,"20612F2A6935E.01","Frankfurt - Aschaffenburg","< >","Laufach","Wiesthal",2021,2021,20,20,"2021-05-22T23:45:00","23:45:00","2021-05-23T06:00:00","06:00:00","6 h","continuous","Tunnel","T",null,null,null,null,"","","","","","Tunnelprüfung Begehung Gewährleistung nach Neubau",null,"N","20612F2A6935E.01","2020-06-08T16:03:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C093D6C.05","Frankfurt - Aschaffenburg","< >","Lohr Bahnhof","Lohr Bahnhof",2021,2021,38,39,"2021-09-26T22:00:00","22:00:00","2021-09-27T05:00:00","05:00:00","7 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307362.05","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF702A18E2AC.04","Frankfurt - Aschaffenburg",">","Aschaffenburg Hbf Ausfahrt","Aschaffenburg Hbf",2021,2021,39,40,"2021-09-30T08:00:00","08:00:00","2021-10-05T08:59:00","08:59:00","5 d, 01 h","continuous","Track & Rail",null,"ST",null,null,null,"C,,C","R,R,R",",B,","0,0,0","O,,O","Gleiserneuerung mit BR GE Aschaffenburg - Steinerts",null,"N","305404.04","2019-05-24T07:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C570F4C.03","Frankfurt - Aschaffenburg","< >","Lohr Bahnhof","Lohr Bahnhof",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-04T06:00:00","06:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307371.03","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C570F4C.04","Frankfurt - Aschaffenburg","< >","Lohr Bahnhof","Lohr Bahnhof",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-05T05:00:00","05:00:00","3 d, 07 h","continuous","Switch",null,"ST",null,null,null,"","","","0,,0","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307371.04","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF702A74702C.01","Frankfurt - Aschaffenburg","<","Aschaffenburg Hbf Ausfahrt","Kleinostheim",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-08T05:00:00","05:00:00","6 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,"C,,C","R,R,R",",B,","0,0,0","O,,O","Gleiserneuerung mit BR GE Aschaffenburg - Steinerts",null,"N","305416.01","2019-05-24T07:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF702A7D97EC.04","Frankfurt - Aschaffenburg","<","Aschaffenburg Hbf Ausfahrt","Kleinostheim",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-08T05:00:00","05:00:00","6 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,"C,,C","R,R,R",",B,","0,0,0","O,,O","Gleiserneuerung mit BR GE Aschaffenburg - Steinerts",null,"N","305417.04","2019-05-24T07:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C70FFEC.01","Frankfurt - Aschaffenburg",">","Partenstein","Lohr Bahnhof",2021,2021,39,40,"2021-10-02T01:00:00","01:00:00","2021-10-04T05:00:00","05:00:00","2 d, 04 h","continuous","Switch",null,"LT",null,null,null,"","","","0,0,0","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307374.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C70FFEC.02","Frankfurt - Aschaffenburg","< >","Nantenbach","Lohr Bahnhof",2021,2021,39,40,"2021-10-02T01:00:00","01:00:00","2021-10-04T05:00:00","05:00:00","2 d, 04 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307374.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C70FFEC.03","Frankfurt - Aschaffenburg","< >","Rohrbach","Nantenbach",2021,2021,39,40,"2021-10-02T01:00:00","01:00:00","2021-10-04T05:00:00","05:00:00","2 d, 04 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307374.03","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CA35A8C.03","Frankfurt - Aschaffenburg","<","Rohrbach","Nantenbach",2021,2021,40,40,"2021-10-04T05:00:00","05:00:00","2021-10-05T05:00:00","05:00:00","1 d","continuous","Switch",null,"LT",null,null,null,"","","","","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307380.03","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CA35A8C.05","Frankfurt - Aschaffenburg","<","Nantenbach","Partenstein",2021,2021,40,40,"2021-10-04T05:00:00","05:00:00","2021-10-05T05:00:00","05:00:00","1 d","continuous","Switch",null,"LT",null,null,null,"","","","0,0,0","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307380.05","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AEBE9DD3547.01","Frankfurt - Aschaffenburg","< >","Rohrbach","Lohr Bahnhof",2021,2021,45,45,"2021-11-13T22:00:00","22:00:00","2021-11-14T06:00:00","06:00:00","8 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Belastungsstopfgang W73W10, W73W11, W73W12 in Lohr Bahnhof",null,"N","20AEBE9DD3547.01","2019-10-24T08:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"222EA801EB096.04","Mannheim - Darmstadt",">","Darmstadt-Eberstadt","Bickenbach (Bergstr)",2021,2021,3,4,"2021-01-23T00:30:00","00:30:00","2021-01-27T20:00:00","20:00:00","4 d, 20 h","continuous","Track & Rail",null,"LT",null,null,null,"","","","","","Untergrundverbesserung BBM.21.0074 Bettungsreinigung FDE-FBI",null,"N","50125","2020-06-17T10:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"226054B4C593F.02","Mannheim - Darmstadt","<","Heddesheim/Hirschberg","Hemsbach",2021,2021,7,7,"2021-02-15T01:00:00","01:00:00","2021-02-19T21:00:00","21:00:00","4 d, 20 h","continuous","Switch",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,O,","Weichenerneuerung im Bf Weinheim, SEV",null,"N","306034.02","2020-07-21T12:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21C8E96E2E83F.01","Mannheim - Darmstadt","< >","Ladenburg","Ladenburg",2021,2021,8,9,"2021-02-27T01:30:00","01:30:00","2021-03-01T04:30:00","04:30:00","2 d, 03 h","continuous","Bridge","T",null,null,null,null,"","","","","","Durchlassarbeiten Restarbeiten TE RLD in Ladenburg",null,"N","65040","2020-06-16T09:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7069FE4EAC.01","Mannheim - Darmstadt",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2021,2021,22,23,"2021-06-04T21:00:00","21:00:00","2021-06-08T04:00:00","04:00:00","3 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,",",B,","0,0,0",",O,","Schienenerneuerung 4000_HD-Wieblingen-HD-Hbf SE2_GMT, SEV",null,"N","306185.01","2019-05-24T07:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"200BA4756C2E7.01","Mannheim - Darmstadt","< >","Darmstadt Hbf","Darmstadt Hbf",2021,2021,48,49,"2021-11-30T07:00:00","07:00:00","2021-12-07T07:00:00","07:00:00","7 d","continuous","Track & Rail",null,"ST",null,null,null,"","","",",,0","","Gleiserneuerung mit BR BK.21.0470 // GE Darmstadt Hbf Gleis 14 in Darmstadt Hbf",null,"N","205738.01","2019-06-07T11:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"200BA4756C2E7.02","Mannheim - Darmstadt","< >","Darmstadt Hbf","Darmstadt Hbf",2021,2021,48,49,"2021-11-30T07:00:00","07:00:00","2021-12-07T07:00:00","07:00:00","7 d","continuous","Track & Rail",null,"ST",null,null,null,"","","",",,0","","Gleiserneuerung mit BR BK.21.0470 // GE Darmstadt Hbf Gleis 14 in Darmstadt Hbf",null,"N","205738.02","2019-06-07T11:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2241AA62F97F6.01","Darmstadt - Aschaffenburg","<","Darmstadt-Kranichstein","Darmstadt Gbf",2021,2021,2,4,"2021-01-16T23:00:00","23:00:00","2021-01-25T03:00:00","03:00:00","8 d, 04 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten BBM.21.0041 BK.21.0083 Erneurung KBW VzG 3557 Darmstadt",null,"N","305588.02","2020-06-30T11:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2245CC74FCB76.02","Darmstadt - Aschaffenburg","< >","Darmstadt Gbf","Darmstadt Nord",2021,2021,6,7,"2021-02-12T23:40:00","23:40:00","2021-02-15T12:10:00","12:10:00","2 d, 13 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten BBM.21.0080 BK.21.0083 Erneurung KBW VzG 3557",null,"N","305588.03","2020-07-03T07:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2245CC74FCB76.03","Darmstadt - Aschaffenburg",">","Darmstadt Hbf","Darmstadt Nord",2021,2021,7,45,"2021-02-15T12:10:00","12:10:00","2021-11-09T23:45:00","23:45:00","267 d, 12 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten BBM.21.0080 BK.21.0083 Erneurung KBW VzG 3557",null,"Y","305588.04","2020-07-03T07:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8AE189A1FD.01","Karlsruhe - Stuttgart","< >","Stuttgart Hbf","Stuttgart-Zuffenhausen",2021,2021,6,7,"2021-02-13T21:00:00","21:00:00","2021-02-18T05:00:00","05:00:00","1 d, 16 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8AE189A1FD.01","2019-10-04T09:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20BE8A921C56D.02","Karlsruhe - Stuttgart","< >","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2021,2021,24,26,"2021-06-18T23:30:00","23:30:00","2021-06-28T04:30:00","04:30:00","4 d, 10 h","periodical","Switch","T",null,null,null,null,",C,C",",R,R",",B,",",0,0",",O,O","Weicheneinbau Anbindung Tiefbahnhof in TSFE in Stg-Feuerbach Hp",null,"N","206822.02","2019-10-17T14:45:00","Unclassified","5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8BAD54F55D.01","Karlsruhe - Stuttgart","< >","Stuttgart Hbf","Stuttgart-Zuffenhausen",2021,2021,45,45,"2021-11-08T21:00:00","21:00:00","2021-11-12T05:00:00","05:00:00","1 d, 08 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8BAD54F55D.01","2019-10-04T10:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8BAEF278BD.01","Karlsruhe - Stuttgart","< >","Stuttgart Hbf","Stuttgart-Zuffenhausen",2021,2021,45,46,"2021-11-14T21:00:00","21:00:00","2021-11-19T05:00:00","05:00:00","1 d, 16 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8BAEF278BD.01","2019-10-04T10:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"223BCBC91AB03.04","Stuttgart - München","< >","Ebersbach (Fils)","Göppingen",2021,2021,4,4,"2021-01-25T22:00:00","22:00:00","2021-01-26T04:30:00","04:30:00","7 h","continuous","Maintenance","T",null,null,null,null,"","","","","","Schienenschleifen  Weichen Handschleifen 4700 in Uhingen",null,"N","63025","2020-06-26T10:25:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20A48D4B8865D.01","Stuttgart - München","< >","Stuttgart-Bad Cannstatt","Geislingen (Steige)",2021,2021,5,6,"2021-02-04T21:00:00","21:00:00","2021-02-08T05:00:00","05:00:00","1 d, 08 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schienenschleifen TPG TS - TG",null,"N","20A48D4B8865D.01","2019-09-20T13:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20A48E63D153D.01","Stuttgart - München","< >","Geislingen (Steige)","Ulm Hbf",2021,2021,6,6,"2021-02-09T21:00:00","21:00:00","2021-02-12T05:00:00","05:00:00","1 d","periodical","Maintenance","T",null,null,null,null,"","","","","","Schienenschleifen TPG TG - TU",null,"N","20A48E63D153D.01","2019-09-20T13:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22746B890A42D.01","Stuttgart - München","<","Ulm Hbf","Beimerstetten",2021,2021,8,9,"2021-02-28T23:30:00","23:30:00","2021-03-02T04:30:00","04:30:00","1 d, 05 h","continuous","Signal",null,"LT",null,null,null,",C,C","R,R,","","0,0,0","O,,O","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW in Ulm Hbf",null,"N","106505.01","2020-08-04T08:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22746E147EB8D.01","Stuttgart - München",">","Ulm-Örlingen","Ulm Hbf Em Nord",2021,2021,9,10,"2021-03-02T23:30:00","23:30:00","2021-03-14T04:30:00","04:30:00","11 d, 05 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW in Ulm Hbf",null,"N","306048.01","2020-08-04T08:28:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22746B890A42D.02","Stuttgart - München","<","Ulm Hbf","Beimerstetten",2021,2021,10,12,"2021-03-14T23:30:00","23:30:00","2021-03-25T04:30:00","04:30:00","10 d, 05 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW in Ulm Hbf",null,"N","106505.02","2020-08-04T08:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A7A645E6E43.01","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2021,2021,13,13,"2021-04-03T05:00:00","05:00:00","2021-04-04T05:00:00","05:00:00","1 d","continuous","Miscellaneous",null,"ST",null,null,null,"","","",",,0","","Bahnsteigarbeiten barrierefreie Erschließung in Beimerstetten",null,"N","206757.01","2020-09-08T13:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21DA937EA4E8D.03","Stuttgart - München",">","Ulm-Örlingen","Ulm Hbf Em Nord",2021,2021,15,16,"2021-04-12T23:30:00","23:30:00","2021-04-20T04:30:00","04:30:00","7 d, 05 h","continuous","Signal",null,"LT",null,null,null,"","","","0,0,0","","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW in Ulm Hbf",null,"N","206012.03","2020-04-20T15:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22C5EC585140D.04","Stuttgart - München","<","Ulm Hbf","Ulm-Örlingen",2021,2021,16,16,"2021-04-20T23:30:00","23:30:00","2021-04-23T04:30:00","04:30:00","2 d, 05 h","continuous","Signal",null,"LT",null,null,null,",,C","R,,","","0,0,0","O,,","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW in Ulm Hbf",null,"N","206617.04","2020-09-29T08:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20319C0C6352D.02","Stuttgart - München","< >","Ulm Hbf Em Nord","Ulm Hbf",2021,2021,23,24,"2021-06-12T23:30:00","23:30:00","2021-06-14T04:30:00","04:30:00","1 d, 05 h","continuous","Signal","T",null,null,null,null,",C,C","R,R,","","0,0,","O,,","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW, SEV in Ulm Hbf",null,"N","206616.02","2020-06-30T13:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20319C0C6352D.04","Stuttgart - München","< >","Ulm Hbf","Ulm Hbf",2021,2021,23,24,"2021-06-12T23:30:00","23:30:00","2021-06-14T13:30:00","13:30:00","1 d, 14 h","continuous","Signal",null,"ST",null,null,null,",C,",",R,","",",0,0","","Arbeiten an LST-Anlagen Pfa 2.6 BTO, Bz M21 und Vorarbeiten ESTW, SEV in Ulm Hbf",null,"N","206616.04","2020-06-30T13:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706C6FEAEC.03","Stuttgart - München","< >","Ulm Hbf","Ulm Hbf",2021,2021,29,32,"2021-07-19","00:00:00","2021-08-09T04:00:00","04:00:00","21 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,",,C","","",",,0","","Gleiserneuerung und WE in Ulm Hbf",null,"N","306239.03","2019-07-03T10:09:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2085C59A0387D.01","Stuttgart - München","< >","Geislingen West","Amstetten (Württ)",2021,2021,32,33,"2021-08-13T07:00:00","07:00:00","2021-08-17T17:00:00","17:00:00","2 d, 02 h","periodical","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Bahnsteigarbeiten unter Deckung TSP Bündel in Geislingen (St)",null,"N","206756.01","2019-08-30T10:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706E56AC4C.01","Stuttgart - München",">","Ulm Hbf Em Nord","Ulm Hbf",2021,2021,32,33,"2021-08-13T20:00:00","20:00:00","2021-08-16T04:00:00","04:00:00","2 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,","O,,","Gleiserneuerung und WE in Ulm Hbf",null,"N","306285.01","2019-07-03T10:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706E1388CC.03","Stuttgart - München","< >","Amstetten (Württ)","Geislingen (Steige)",2021,2021,32,33,"2021-08-13T22:00:00","22:00:00","2021-08-16T22:00:00","22:00:00","3 d","continuous","Bridge","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,,","Brückenarbeiten Durchlasserneuerung, SEV",null,"N","306279.03","2019-05-24T07:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706D7043EC.03","Stuttgart - München","< >","Göppingen","Eislingen (Fils)",2021,2021,32,34,"2021-08-13T22:00:00","22:00:00","2021-08-27T04:00:00","04:00:00","13 d, 06 h","continuous","Switch","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Weichenerneuerung Bahnhofsbündel, SEV in Göppingen",null,"N","306264.03","2019-05-24T07:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706E68FBCC.01","Stuttgart - München","< >","Göppingen","Göppingen",2021,2021,32,35,"2021-08-13T22:00:00","22:00:00","2021-09-03T04:00:00","04:00:00","20 d, 06 h","continuous","Switch","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Weichenerneuerung Bahnhofsbündel in Göppingen",null,"N","306287.01","2019-07-05T07:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706E5FD40C.01","Stuttgart - München","< >","Geislingen West","Ulm Hbf",2021,2021,32,35,"2021-08-13T22:00:00","22:00:00","2021-09-03T04:00:00","04:00:00","20 d, 06 h","continuous","Track & Rail","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Schienenauswechslung Geislingen-Westerstetten, Amstetten-Beimerstetten, Beimerstetten-Ulm, SEV",null,"N","306286.01","2019-07-04T12:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2085C59A0387D.02","Stuttgart - München","< >","Geislingen West","Amstetten (Württ)",2021,2021,33,33,"2021-08-20T08:00:00","08:00:00","2021-08-22T16:00:00","16:00:00","1 d","periodical","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Bahnsteigarbeiten unter Deckung TSP Bündel in Geislingen (St)",null,"N","206756.02","2019-08-30T10:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706F61B3AC.01","Stuttgart - München","< >","Uhingen","Göppingen",2021,2021,34,34,"2021-08-26T22:00:00","22:00:00","2021-08-27T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"C,,C","","","","","sonstige Arbeiten Erneuerung WHZ Göppingen in Göppingen",null,"N","306309.01","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706F6ADB6C.01","Stuttgart - München","< >","Eislingen (Fils)","Gingen (Fils) Süd",2021,2021,34,35,"2021-08-27T22:00:00","22:00:00","2021-09-03T22:00:00","22:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","sonstige Arbeiten LST-, OL-, Oberbau- und Abnahmearbeiten, SEV",null,"N","306310.01","2019-07-04T12:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"205BA6EC9F7DD.01","Stuttgart - München","< >","Göppingen","Süßen",2021,2021,34,35,"2021-08-27T22:00:00","22:00:00","2021-09-03T22:00:00","22:00:00","7 d","continuous","Bridge","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,O,","Brückenarbeiten Neubau EÜ Mühlbachstraße km 46,092 in Eislingen (Fils)",null,"N","206683.01","2019-08-01T11:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70628AF56C.01","Stuttgart - München","< >","Günzburg","Günzburg",2021,2021,4,5,"2021-01-29T22:30:00","22:30:00","2021-02-02T05:15:00","05:15:00","3 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","","0,,0","","sonstige Arbeiten Nacharbeiten Fußgängersteg, Oberleitung in Günzburg",null,"N","306019.01","2019-05-24T07:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2275F2432D2C3.01","Stuttgart - München","< >","Ulm Hbf","Nersingen",2021,2021,9,9,"2021-03-06T22:00:00","22:00:00","2021-03-07T06:00:00","06:00:00","8 h","continuous","Maintenance","T",null,null,null,null,"","","","","","Durcharbeitung von Weichen Weichen DUA Bf MNM in Neu-Ulm",null,"N","63067","2020-08-05T09:28:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A8F8D063FC3.02","Stuttgart - München","< >","Günzburg","Günzburg",2021,2021,14,16,"2021-04-09T22:00:00","22:00:00","2021-04-24T05:20:00","05:20:00","14 d, 07 h","continuous","Switch",null,"ST",null,null,null,"C,,C","","","0,,0","","Weichenerneuerung mit PSS 32 - 35 in Günzburg",null,"N","306100.02","2020-09-09T11:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A8F8D063FC3.03","Stuttgart - München","< >","Günzburg","Günzburg",2021,2021,14,15,"2021-04-09T22:20:00","22:20:00","2021-04-12T05:20:00","05:20:00","2 d, 07 h","continuous","Switch",null,"ST",null,null,null,",,C","R,,","","0,,","","Weichenerneuerung mit PSS 32 - 35 in Günzburg",null,"N","306100.03","2020-09-09T11:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A76AE5785A0.05","Stuttgart - München",">","Westheim (Schwab)","Augsburg Hirblinger Straße",2021,2021,15,16,"2021-04-17T15:00:00","15:00:00","2021-04-19T05:00:00","05:00:00","1 d, 14 h","continuous","Switch",null,"LT",null,null,null,"","","","","","Weichenerneuerung Weiche 4/5, 7, 9, 15, 16 u. 18 in Augsb-Oberhausen Bft",null,"N","70593","2020-09-08T09:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706806C46C.04","Stuttgart - München","< >","Günzburg","Günzburg",2021,2021,18,19,"2021-05-07T22:00:00","22:00:00","2021-05-10T05:00:00","05:00:00","2 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,",,C","","","","","Gleiserneuerung mit BR, PSS und TE Gl 12, W 14 in Günzburg",null,"N","306142.04","2019-07-11T14:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706806C46C.05","Stuttgart - München",">","Günzburg","Neuoffingen",2021,2021,18,19,"2021-05-07T22:30:00","22:30:00","2021-05-10T04:50:00","04:50:00","2 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,",C,C","R,,","","0,0,0","O,,","Gleiserneuerung mit BR, PSS und TE Gl 12, W 14 in Günzburg",null,"N","306142.05","2019-07-11T14:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7068B1AA6C.01","Stuttgart - München",">","Günzburg","Neuoffingen",2021,2021,19,20,"2021-05-14T22:30:00","22:30:00","2021-05-17T04:50:00","04:50:00","2 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,,","Gleiserneuerung mit BR, PSS und TE Gl 12 in Günzburg",null,"N","306156.01","2019-05-24T07:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20C0181B8EE58.03","Stuttgart - München","<","Augsburg Hirblinger Straße","Westheim (Schwab)",2021,2021,28,29,"2021-07-18T07:00:00","07:00:00","2021-07-19T03:00:00","03:00:00","20 h","continuous","Track & Rail",null,"LT",null,null,null,"","","",",,0","","Gleiserneuerung mit BR Erstellung Stürtzwand Holzbachbrücke u. GE Gleis 170",null,"N","207921.03","2019-10-09T12:08:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20C021FE3A758.01","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hirblinger Straße",2021,2021,29,30,"2021-07-25T11:00:00","11:00:00","2021-07-26T03:00:00","03:00:00","16 h","continuous","Track & Rail","T",null,null,null,null,",,C","R,R,","","0,0,","O,,","Gleiserneuerung mit BR Erstellung Stürtzwand Holzbachbrücke u. GE Gleis 170",null,"N","207922.01","2019-10-09T12:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706C6FEAEC.05","Stuttgart - München","< >","Ulm Hbf","Ulm Hbf",2021,2021,31,32,"2021-08-07","00:00:00","2021-08-09T04:00:00","04:00:00","2 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,"","","",",,0","","Gleiserneuerung und WE in Ulm Hbf",null,"N","306239.05","2019-07-03T10:09:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20CA837F421C4.03","Stuttgart - München","< >","Freihalden Üst","Dinkelscherben",2021,2021,33,34,"2021-08-20T23:05:00","23:05:00","2021-08-23T05:00:00","05:00:00","2 d, 06 h","continuous","Bridge","T",null,null,null,null,",C,C","R,R,","","0,0,","","Brückenarbeiten  km 35,545 + 35,029",null,"N","207925.03","2020-06-05T20:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70760A1BCC.01","Stuttgart - München",">","Günzburg","Neuoffingen",2021,2021,47,48,"2021-11-26T23:30:00","23:30:00","2021-11-29T05:30:00","05:30:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,","O,,","sonstige Arbeiten Nacharbeiten Fußgängersteg, Oberleitung in Günzburg",null,"N","306458.01","2019-05-24T08:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70760A1BCC.02","Stuttgart - München",">","Unterfahlheim","Günzburg",2021,2021,47,48,"2021-11-26T23:30:00","23:30:00","2021-11-29T05:30:00","05:30:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,","O,O,","sonstige Arbeiten Nacharbeiten Fußgängersteg, Oberleitung in Günzburg",null,"N","306458.02","2019-05-24T08:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF707637E28C.01","Stuttgart - München","<","Nersingen","Ulm Hbf",2021,2021,48,48,"2021-11-29","00:00:00","2021-12-04T05:00:00","05:00:00","5 d, 05 h","continuous","Track & Rail",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,","O,,","Schienenauswechslung SE2 in Neu-Ulm",null,"N","306463.01","2019-07-12T11:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2077917AD887D.01","Stuttgart - München",">","Günzburg","Burgau (Schwab)",2021,2021,48,49,"2021-12-03","00:00:00","2021-12-06T05:00:00","05:00:00","3 d, 05 h","continuous","Switch",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,0","O,,O","Weichenerneuerung in Neuoffingen",null,"N","206745.01","2020-02-24T12:56:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70764EC5EC.01","Stuttgart - München","<","Neuoffingen","Günzburg",2021,2021,48,49,"2021-12-03T22:30:00","22:30:00","2021-12-06T05:20:00","05:20:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,","O,,","sonstige Arbeiten Nacharbeiten Fußgängersteg, Oberleitung in Günzburg",null,"N","306465.01","2019-05-24T08:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70764EC5EC.02","Stuttgart - München","<","Günzburg","Unterfahlheim",2021,2021,48,49,"2021-12-03T22:30:00","22:30:00","2021-12-06T05:20:00","05:20:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,",",B,","0,0,","O,,","sonstige Arbeiten Nacharbeiten Fußgängersteg, Oberleitung in Günzburg",null,"N","306465.02","2019-05-24T08:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"222D4DD36FA72.02","Karlsruhe - Mannheim","< >","Schwetzingen","Schwetzingen",2021,2021,1,7,"2021-01-10","00:00:00","2021-02-20T23:59:00","23:59:00","42 d","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,","","Gleiserneuerung mit BR 3601_MA-Friedrichsfeld-Heidelberg_GMT in N-Edingen/F-feld",null,"N","306004.02","2020-06-16T11:25:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706AC7B92C.01","Karlsruhe - Mannheim",">","Mannheim-Rheinau","Schwetzingen",2021,2021,24,31,"2021-06-20T22:00:00","22:00:00","2021-08-03T04:00:00","04:00:00","43 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","0,,0","","Bahnsteigarbeiten 2. Baustufe S-Bahn Rhein-Neckar, Abschnitt Mannheim - Karlsruhe, SEV",null,"N","306201.01","2019-05-24T07:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706AC7B92C.02","Karlsruhe - Mannheim","< >","Schwetzingen","Mannheim-Rheinau",2021,2021,30,31,"2021-07-28T22:00:00","22:00:00","2021-08-03T04:00:00","04:00:00","5 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,",,C","R,R,",",B,","0,0,","O,O,","Bahnsteigarbeiten 2. Baustufe S-Bahn Rhein-Neckar, Abschnitt Mannheim - Karlsruhe, SEV",null,"N","306201.02","2019-05-24T07:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706AC7B92C.03","Karlsruhe - Mannheim","<","Schwetzingen","Mannheim-Rheinau",2021,2021,31,37,"2021-08-03T04:00:00","04:00:00","2021-09-13T04:00:00","04:00:00","41 d","continuous","Miscellaneous",null,"LT",null,null,null,"","","","0,,0","","Bahnsteigarbeiten 2. Baustufe S-Bahn Rhein-Neckar, Abschnitt Mannheim - Karlsruhe, SEV",null,"N","306201.03","2019-05-24T07:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706DBE15CC.02","Karlsruhe - Mannheim","< >","Philippsburg Molzau","Philippsburg Molzau",2021,2021,31,34,"2021-08-07T21:00:00","21:00:00","2021-08-23T05:00:00","05:00:00","2 d","periodical","Miscellaneous","T",null,null,null,null,"","R,,","","0,,","O,,","sonstige Arbeiten ETCS KorA Ausrüstung ESG IH KAR VzG 4020 Nord Teil 3",null,"N","306272.02","2019-05-24T07:59:00","Unclassified","6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706E96C28C.03","Karlsruhe - Mannheim","< >","Philippsburg Molzau","Philippsburg Molzau",2021,2021,32,33,"2021-08-09T23:00:00","23:00:00","2021-08-21T05:00:00","05:00:00","2 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,"","R,,","","0,,","O,,","sonstige Arbeiten ETCS KorA Ausrüstung ESG IH KAR VzG 4020 Nord Teil 3",null,"N","306290.03","2019-07-15T10:59:00","Unclassified","1,2,3,4,5",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF707032BF4C.04","Karlsruhe - Mannheim","< >","Hockenheim","Hockenheim",2021,2021,36,40,"2021-09-06","00:00:00","2021-10-06T23:59:00","23:59:00","31 d","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,0","","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT",null,"N","306329.04","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF707032BF4C.05","Karlsruhe - Mannheim","< >","Schwetzingen","Schwetzingen",2021,2021,36,40,"2021-09-06","00:00:00","2021-10-06T23:59:00","23:59:00","31 d","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,0","","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT",null,"N","306329.05","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70709C086C.01","Karlsruhe - Mannheim",">","Oftersheim","Hockenheim",2021,2021,36,37,"2021-09-08T22:00:00","22:00:00","2021-09-16T06:00:00","06:00:00","7 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306338.01","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7070AE57EC.01","Karlsruhe - Mannheim","< >","Hockenheim","Hockenheim",2021,2021,36,37,"2021-09-08T22:00:00","22:00:00","2021-09-16T06:00:00","06:00:00","2 d, 16 h","periodical","Track & Rail","T",null,null,null,null,",,C","R,R,","","0,,","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306340.01","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7070AE57EC.02","Karlsruhe - Mannheim","< >","Hockenheim","Schwetzingen",2021,2021,36,37,"2021-09-08T22:00:00","22:00:00","2021-09-16T06:00:00","06:00:00","2 d, 16 h","periodical","Track & Rail","T",null,null,null,null,",,C","R,R,","","0,,","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306340.02","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF707163EC4C.01","Karlsruhe - Mannheim",">","Schwetzingen","Oftersheim",2021,2021,37,38,"2021-09-18T22:00:00","22:00:00","2021-09-20T06:00:00","06:00:00","1 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,"","R,R,","","0,,0","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306356.01","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF707163EC4C.02","Karlsruhe - Mannheim","<","Hockenheim","Schwetzingen",2021,2021,37,38,"2021-09-18T22:00:00","22:00:00","2021-09-20T06:00:00","06:00:00","1 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,"","R,R,","","0,,0","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306356.02","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7071B95F4C.03","Karlsruhe - Mannheim",">","Schwetzingen","Oftersheim",2021,2021,38,39,"2021-09-25","00:00:00","2021-09-27T06:00:00","06:00:00","2 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,",,C","R,R,","","0,,0","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306364.03","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7071B95F4C.04","Karlsruhe - Mannheim",">","Schwetzingen","Hockenheim",2021,2021,38,39,"2021-09-25","00:00:00","2021-09-27T06:00:00","06:00:00","2 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,","","0,,0","O,O,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306364.04","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70724BDB4C.03","Karlsruhe - Mannheim","< >","Waghäusel","Waghäusel",2021,2021,39,40,"2021-10-02T22:00:00","22:00:00","2021-10-05T06:00:00","06:00:00","2 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,0","","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306374.03","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70724BDB4C.04","Karlsruhe - Mannheim",">","Hockenheim","Philippsburg Molzau",2021,2021,39,40,"2021-10-02T22:00:00","22:00:00","2021-10-05T06:00:00","06:00:00","2 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,,","Schienenerneuerung 4020_Schwetzingen-Waghäusel_SE2_GMT, SEV",null,"N","306374.04","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2235FAADEB02A.04","Strasbourg - Karlsruhe","< >","Graben-Neudorf","Karlsruhe Hbf",2021,2021,5,6,"2021-02-05T22:00:00","22:00:00","2021-02-08T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,",,C","R,R,","","0,0,","O,,","sonstige Arbeiten ETCS KorA Ausrüstung ESG IH KAR VzG 4020 Nord Teil 1, SEV",87,"N","306011.04","2020-06-22T10:27:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2287A0F726F12.01","Strasbourg - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2021,2021,10,12,"2021-03-08","00:00:00","2021-03-23T23:59:00","23:59:00","16 d","continuous","Maintenance",null,"ST",null,null,null,"","","","0,,0","","Durcharbeitung von Gleisen SFS 4080 Belastungsstopfgänge",87,"N","306063.01","2020-08-17T13:07:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A78881D8852.01","Strasbourg - Karlsruhe","< >","Karlsruhe Hbf","Forchheim (b Karlsruhe)",2021,2021,13,14,"2021-04-04T23:00:00","23:00:00","2021-04-05T23:00:00","23:00:00","1 d","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme ETCS KorA: IBN ESTW Dammerstock / SEV",87,"N","206851.01","2020-09-08T11:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"224B098A04C0A.02","Strasbourg - Karlsruhe","< >","Forchheim (b Karlsruhe)","Durmersheim Nord",2021,2021,19,20,"2021-05-13T00:01:00","00:01:00","2021-05-17T04:30:00","04:30:00","4 d, 04 h","continuous","Catenary","T",null,null,null,null,",,C","R,R,R",",B,","0,0,0","O,O,O","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"N","306018.02","2020-09-09T12:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706B86754C.01","Strasbourg - Karlsruhe",">","Karlsruhe Hbf Bft Südeinfahrt","Bashaide",2021,2021,26,35,"2021-07-02T23:00:00","23:00:00","2021-08-30T05:00:00","05:00:00","58 d, 06 h","continuous","Catenary",null,"LT",null,null,null,",,C","R,R,R",",B,","0,0,0","O,O,","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"Y","306219.01","2019-08-01T12:07:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AD489F9A526.03","Strasbourg - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Karlsruhe Hbf Bft Südeinfahrt",2021,2021,26,35,"2021-07-02T23:00:00","23:00:00","2021-08-30T05:00:00","05:00:00","58 d, 06 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten KaBa PfA 1 Bashaide Teil 1 - Ergänzung zu J(XEI)",87,"N","20AD489F9A526.03","2019-09-26T20:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706C8E6F6C.03","Strasbourg - Karlsruhe","< >","Graben-Neudorf","Philippsburg Molzau",2021,2021,29,31,"2021-07-19T23:00:00","23:00:00","2021-08-07T05:00:00","05:00:00","3 d, 18 h","periodical","Miscellaneous","T",null,null,null,null,"","R,,","","0,,","O,,","sonstige Arbeiten ETCS KorA Ausrüstung ESG IH KAR VzG 4020 Nord Teil 3",87,"N","306241.03","2019-08-07T14:27:00","Unclassified","1,2,3,4,5",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AECB9CA03E6.01","Strasbourg - Karlsruhe",">","Durmersheim","Ötigheim",2021,2021,31,35,"2021-08-08T04:01:00","04:01:00","2021-08-30T04:00:00","04:00:00","22 d","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","Bahnsteigarbeiten Erneuerung Bahnsteig in Bietighm(Baden) Hp",87,"N","20AECB9CA03E6.01","2019-09-27T14:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AECD201A946.01","Strasbourg - Karlsruhe","<","Ötigheim","Durmersheim",2021,2021,35,38,"2021-08-30T04:00:00","04:00:00","2021-09-21T18:00:00","18:00:00","22 d, 14 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","Bahnsteigarbeiten Erneuerung Bahnsteig in Bietighm(Baden) Hp",87,"N","20AECD201A946.01","2019-09-27T14:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706FCF90AC.01","Strasbourg - Karlsruhe","<","Bashaide","Karlsruhe Hbf Bft Südeinfahrt",2021,2021,35,45,"2021-08-30T23:00:00","23:00:00","2021-11-08T04:30:00","04:30:00","69 d, 05 h","continuous","Catenary",null,"LT",null,null,null,",,C","R,R,R",",B,","0,0,0","O,O,","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"Y","306320.01","2019-08-01T12:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7072875DAC.01","Strasbourg - Karlsruhe","<","Durmersheim","Bashaide",2021,2021,39,43,"2021-10-03T22:00:00","22:00:00","2021-10-29T05:00:00","05:00:00","25 d, 07 h","continuous","Catenary",null,"LT",null,null,null,",,C","R,R,R",",B,","0,0,0","O,O,","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"N","306380.01","2019-08-01T12:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B49544F109D.01","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Mühlacker",2021,2021,2,3,"2021-01-16T22:00:00","22:00:00","2021-01-21T05:00:00","05:00:00","1 d, 11 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B49544F109D.01","2019-10-01T14:16:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B49544F109D.02","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Mühlacker",2021,2021,3,4,"2021-01-22T22:00:00","22:00:00","2021-01-27T05:00:00","05:00:00","1 d, 11 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B49544F109D.02","2019-10-01T14:16:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2255F0B7BD6AA.02","Karlsruhe - Stuttgart","< >","Wilferdingen-Singen","Pforzheim Hbf",2021,2021,5,6,"2021-02-06T02:00:00","02:00:00","2021-02-08T04:00:00","04:00:00","2 d, 02 h","continuous","Miscellaneous","T",null,null,null,null,",,C","R,R,","","0,0,","O,O,","Kabelarbeiten Erneuerung F-Kabel TWL-TPH, SEV",null,"N","106518.02","2020-07-14T09:37:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2293346156812.02","Karlsruhe - Stuttgart","< >","Vaihingen (Enz)","Vaihingen (Enz)",2021,2021,11,18,"2021-03-18","00:00:00","2021-05-03T23:59:00","23:59:00","47 d","continuous","Maintenance",null,"ST",null,null,null,"","","","0,,0","","Durcharbeitung von Gleisen SFS 4080 Belastungsstopfgänge",null,"N","306071.02","2020-08-25T12:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20716BDBBF1BD.02","Karlsruhe - Stuttgart","< >","Wilferdingen-Singen","Pforzheim Hbf",2021,2021,18,19,"2021-05-08T02:00:00","02:00:00","2021-05-10T04:00:00","04:00:00","2 d, 02 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Kabelarbeiten Erneuerung F-Kabel TWL-TPH // unter Deckung EÜ Bilfingen",null,"N","20716BDBBF1BD.02","2019-08-16T10:36:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8AE189A1FD.02","Karlsruhe - Stuttgart","< >","Stuttgart-Zuffenhausen","Sachsenheim",2021,2021,6,7,"2021-02-13T21:00:00","21:00:00","2021-02-18T05:00:00","05:00:00","1 d, 16 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8AE189A1FD.02","2019-10-04T09:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20D468CBA373D.01","Karlsruhe - Stuttgart","< >","Sachsenheim","Tamm (Württ)",2021,2021,9,9,"2021-03-02T22:00:00","22:00:00","2021-03-06T04:30:00","04:30:00","1 d, 02 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schienenschleifen  Weichen 4800+4900 in Bietigheim-Biss",null,"N","20D468CBA373D.01","2019-10-23T11:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B4897BB33A0.01","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2021,2021,18,19,"2021-05-09T22:30:00","22:30:00","2021-05-10T04:30:00","04:30:00","6 h","continuous","Bridge","T",null,null,null,null,"","R,R,R",",B,","0,0,0",",O,O","Brückenarbeiten Oberleitungsarbeiten Richtseilwechsel Mast 10-12/Mast 10-12a in Kornwestheim Pbf",null,"N","206811.01","2019-10-01T13:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706944266C.01","Karlsruhe - Stuttgart","< >","Kornwestheim Karlshöhe","Kornwestheim Pbf",2021,2021,20,23,"2021-05-22T01:45:00","01:45:00","2021-06-07T04:00:00","04:00:00","16 d, 02 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ Kornwestheim, Strecke 4800, km 10,71 in Kornwestheim Pbf",null,"N","306168.01","2020-04-23T12:17:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7073B2702C.05","Karlsruhe - Stuttgart","<","Stuttgart-Zuffenhausen","Kornwestheim Pbf",2021,2021,42,43,"2021-10-23T01:45:00","01:45:00","2021-10-25T04:00:00","04:00:00","2 d, 02 h","continuous","Switch",null,"LT",null,null,null,"C,,C",",,R","",",,0",",,O","Weichenerneuerung Stuttgart-Feuerbach, Erneuerung Weichen  101, 102, 103, 115 in Stg-Feuerbach Hp",null,"N","306405.05","2019-07-02T08:54:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8BAD54F55D.02","Karlsruhe - Stuttgart","< >","Stuttgart-Zuffenhausen","Sachsenheim",2021,2021,45,45,"2021-11-08T21:00:00","21:00:00","2021-11-12T05:00:00","05:00:00","1 d, 08 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8BAD54F55D.02","2019-10-04T10:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B8BAEF278BD.02","Karlsruhe - Stuttgart","< >","Stuttgart-Zuffenhausen","Sachsenheim",2021,2021,45,46,"2021-11-14T21:00:00","21:00:00","2021-11-19T05:00:00","05:00:00","1 d, 16 h","periodical","Maintenance","T",null,null,null,null,"","","","","","Schleifen von Schienen",null,"N","20B8BAEF278BD.02","2019-10-04T10:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"224B137FAAB6A.01","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt",2021,2021,5,49,"2021-02-06T23:00:00","23:00:00","2021-12-11T23:59:00","23:59:00","308 d, 01 h","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,0","","Bahnsteigarbeiten Modernisierung Bahnhof Rastatt - Logistik + Umschlag",87,"N","306026.01","2020-07-06T22:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"224B137FAAB6A.02","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt",2021,2021,8,49,"2021-02-22T08:00:00","08:00:00","2021-12-11T23:59:00","23:59:00","292 d, 16 h","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,0","","Bahnsteigarbeiten Modernisierung Bahnhof Rastatt - Logistik + Umschlag",87,"N","306026.02","2020-07-06T22:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2261C4714CD1C.01","Strasbourg - Karlsruhe","< >","Appenweier-Muhrhaag","Appenweier Nord",2021,2021,10,11,"2021-03-12T23:35:00","23:35:00","2021-03-15T04:15:00","04:15:00","2 d, 05 h","continuous","Bridge",null,"ST",null,null,null,",,C","","","","","Brückenarbeiten Rückbau PU, SEV in Appenweier",87,"N","106495.01","2020-07-22T12:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AD42E6DAC58.01","Strasbourg - Karlsruhe",">","Rastatt","Rastatt-Süd",2021,2021,13,13,"2021-03-29T00:15:00","00:15:00","2021-04-02T00:15:00","00:15:00","4 d","continuous","Bridge",null,"LT",null,null,null,",C,C","R,,","","0,0,0","O,,","Brückenarbeiten Verschwenkung zur Umfahrung Tunnel Rastatt",87,"N","106528.01","2019-09-26T13:37:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AD42E6DAC58.02","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt-Süd",2021,2021,13,14,"2021-04-02T00:15:00","00:15:00","2021-04-06T03:00:00","03:00:00","4 d, 03 h","continuous","Bridge","T",null,null,null,null,"C,C,C",",R,",",B,",",0,","O,O,","Brückenarbeiten Verschwenkung zur Umfahrung Tunnel Rastatt",87,"N","206789.02","2019-09-26T13:37:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A7B733DE032.03","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt",2021,2021,13,35,"2021-04-02T23:00:00","23:00:00","2021-08-30","00:00:00","149 d, 01 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","","0,,0","","Bahnsteigarbeiten Modernisierung Bahnhof Rastatt - Bph 2+3 / SEV",87,"N","306053.03","2020-09-08T14:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A7B733DE032.01","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt",2021,2021,21,26,"2021-05-24T23:00:00","23:00:00","2021-07-01T04:30:00","04:30:00","37 d, 05 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","","0,,0","","Bahnsteigarbeiten Modernisierung Bahnhof Rastatt - Bph 2+3 / SEV",87,"N","306053.01","2020-09-08T14:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706A49134C.01","Strasbourg - Karlsruhe","< >","Rastatt","Rastatt",2021,2021,35,45,"2021-08-30","00:00:00","2021-11-08T04:30:00","04:30:00","70 d, 04 h","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,0","","Bahnsteigarbeiten Modernisierung Bahnhof Rastatt - halbseitiger Umb Bstg 3 (Gl 4)",87,"Y","306191.01","2020-03-30T17:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2261C5356021C.04","Strasbourg - Karlsruhe","< >","Appenweier Nord","Appenweier Kurve",2021,2021,12,13,"2021-03-27T00:30:00","00:30:00","2021-03-29T04:30:00","04:30:00","2 d, 04 h","continuous","Bridge","T",null,null,null,null,"",",R,",",B,",",0,","O,,","Brückenarbeiten Rückbau PU in Appenweier",87,"N","106496.04","2020-07-22T12:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22C47D59AA756.01","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2021,2021,16,18,"2021-04-23T07:00:00","07:00:00","2021-05-05T17:00:00","17:00:00","12 d, 10 h","continuous","Switch",null,"ST",null,null,null,"","","","0,,","","Weichenerneuerung Logistikgleise für  Bf. Jossa WE12, 28, 31, 34",null,"N","307144.01","2020-09-28T08:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20A0344BDFA67.02","Gemünden - Würzburg - Nürnberg","<","Karlstadt (Main)","Gemünden (Main)",2021,2021,28,29,"2021-07-16T22:00:00","22:00:00","2021-07-19T10:00:00","10:00:00","2 d, 12 h","continuous","Switch",null,"LT",null,null,null,"","","","","","Weichenerneuerung mit PSS Weichenerneuerung Gemünden W173 + 174",null,"N","20A0344BDFA67.02","2019-09-17T15:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C3EA54C.01","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2021,2021,39,43,"2021-09-27T07:00:00","07:00:00","2021-10-25T18:00:00","18:00:00","28 d, 11 h","continuous","Switch",null,"ST",null,null,null,"","","","0,,","","Weichenerneuerung mit PSS Weichenerneuerung Bf Gemünden W272 + 273",null,"N","307368.01","2019-09-18T20:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C5EB06C.02","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2021,2021,39,40,"2021-10-01T07:00:00","07:00:00","2021-10-05T17:00:00","17:00:00","4 d, 10 h","continuous","Switch",null,"ST",null,null,null,"","","","0,,","","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307372.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C67D82C.01","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Langenprozelten",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-04T04:50:00","04:50:00","2 d, 07 h","continuous","Track & Rail","T",null,null,null,null,",,C","R,R,","","0,0,","O,O,","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307373.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C67D82C.02","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Langenprozelten",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-04T04:50:00","04:50:00","2 d, 07 h","continuous","Track & Rail","T",null,null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307373.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C67D82C.03","Gemünden - Würzburg - Nürnberg","< >","Langenprozelten","Gemünden (Main)",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-04T04:50:00","04:50:00","21 h","periodical","Track & Rail","T",null,null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307373.03","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C3EA54C.02","Gemünden - Würzburg - Nürnberg","< >","Langenprozelten","Gemünden (Main)",2021,2021,39,40,"2021-10-01T22:00:00","22:00:00","2021-10-04T06:00:00","06:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,"","","","0,,","","Weichenerneuerung mit PSS Weichenerneuerung Bf Gemünden W272 + 273",null,"N","307368.02","2019-09-18T20:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C67D82C.04","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2021,2021,39,41,"2021-10-01T22:00:00","22:00:00","2021-10-14T05:00:00","05:00:00","12 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307373.04","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704C67D82C.05","Gemünden - Würzburg - Nürnberg",">","Langenprozelten","Gemünden (Main)",2021,2021,39,41,"2021-10-01T22:00:00","22:00:00","2021-10-14T05:00:00","05:00:00","12 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,O,","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307373.05","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CA35A8C.01","Gemünden - Würzburg - Nürnberg","<","Langenprozelten","Nantenbach",2021,2021,40,40,"2021-10-04T05:00:00","05:00:00","2021-10-05T05:00:00","05:00:00","1 d","continuous","Switch",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,O,","Weichenerneuerung Bf. Lohr W73W10, W73W11, W73W12",null,"N","307380.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CB1162C.02","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Langenprozelten",2021,2021,40,41,"2021-10-04T22:00:00","22:00:00","2021-10-12T04:50:00","04:50:00","2 d, 07 h","periodical","Track & Rail","T",null,null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS GE Langenprozelten - Gemünden km 40,403-38,380",null,"N","307381.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704D09966C.01","Gemünden - Würzburg - Nürnberg","<","Gemünden (Main)","Langenprozelten",2021,2021,41,42,"2021-10-16","00:00:00","2021-10-18T06:00:00","06:00:00","2 d, 06 h","continuous","Switch",null,"LT",null,null,null,"","R,R,","","0,0,","O,O,","Weichenerneuerung mit PSS Weichenerneuerung Bf Gemünden W276 + 278",null,"N","307390.01","2019-08-07T16:28:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704D29A18C.01","Gemünden - Würzburg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2021,2021,42,43,"2021-10-20T05:00:00","05:00:00","2021-10-25T05:00:00","05:00:00","5 d","continuous","Switch",null,"ST",null,null,null,"","","","0,,","","Weichenerneuerung mit PSS Weichenerneuerung Bf Gemünden W234 + 237 + 238",null,"N","307393.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704D29A18C.04","Gemünden - Würzburg - Nürnberg","< >","Langenprozelten","Gemünden (Main)",2021,2021,42,43,"2021-10-20T22:00:00","22:00:00","2021-10-25T05:00:00","05:00:00","21 h","periodical","Switch","T",null,null,null,null,",,C","R,R,","","0,0,0","O,O,","Weichenerneuerung mit PSS Weichenerneuerung Bf Gemünden W234 + 237 + 238",null,"N","307393.04","2019-05-24T07:51:00","Unclassified","3,4,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AEBE9DD3547.02","Gemünden - Würzburg - Nürnberg","< >","Nantenbach","Langenprozelten",2021,2021,45,45,"2021-11-13T22:00:00","22:00:00","2021-11-14T06:00:00","06:00:00","8 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung Belastungsstopfgang W73W10, W73W11, W73W12 in Lohr Bahnhof",null,"N","20AEBE9DD3547.02","2019-10-24T08:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2077509ACB2BE.03","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2021,2021,31,32,"2021-08-06","00:00:00","2021-08-10T02:10:00","02:10:00","4 d, 02 h","continuous","Track & Rail",null,null,null,"P",null,"","","","","","Gleiserneuerung Gl.030,003,033,103 in Hersbruck (re P)",54,"N","2077509ACB2BE.03","2020-11-19T08:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2077509ACB2BE.05","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2021,2021,31,34,"2021-08-08","00:00:00","2021-08-28T04:35:00","04:35:00","20 d, 05 h","continuous","Track & Rail",null,null,null,"P",null,"","","","","","Gleiserneuerung Gl.030,003,033,103 in Hersbruck (re P)",54,"N","2077509ACB2BE.05","2020-11-19T08:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20775B6D1F45E.01","Nürnberg - Plzen","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2021,2021,32,34,"2021-08-10T02:10:00","02:10:00","2021-08-24T04:45:00","04:45:00","14 d, 03 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,,","","0,,0",",,O","Gleiserneuerung Gl.030,003,033,103 in Hersbruck (re P)",54,"N","207816.01","2020-11-19T10:33:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20775B6D1F45E.02","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2021,2021,32,34,"2021-08-10T02:10:00","02:10:00","2021-08-24T04:45:00","04:45:00","14 d, 03 h","continuous","Track & Rail",null,"ST",null,null,null,",,C","R,,R","","0,,0",",,O","Gleiserneuerung Gl.030,003,033,103 in Hersbruck (re P)",54,"N","207816.02","2020-11-19T10:33:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"204E579BEFA5E.01","Nürnberg - Plzen","< >","Pegnitz","Neuhaus (Pegnitz)",2021,2021,34,35,"2021-08-24T22:00:00","22:00:00","2021-08-30T05:00:00","05:00:00","5 d, 07 h","continuous","Bridge","T",null,null,null,null,",,C","R,,R","","0,,0","","Brückenarbeiten EÜ-Erneuerung Pegnitzbrücke km 60,119",54,"N","207762.01","2019-07-23T08:03:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20777D20896FE.01","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2021,2021,36,37,"2021-09-06T05:00:00","05:00:00","2021-09-13T04:35:00","04:35:00","7 d","continuous","Bridge","T",null,null,null,null,",,C","R,,R","","0,,0",",,O","Brückenarbeiten EÜ-Erneuerung km 28,249+28,142+ Du-Erneu.km 30,748 in Hersbruck (re P)",54,"N","207820.01","2019-08-20T14:42:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"227EF1DD23FA5.01","Stuttgart - München",">","München-Lochhausen","München-Pasing",2021,2021,12,12,"2021-03-22T22:00:00","22:00:00","2021-03-27T05:40:00","05:40:00","4 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,",C,","R,R,R","","0,0,0","O,O,","Gleiserneuerung MP-MLO 5503+5543 und MP Gl 204, 205, 305, 308, 310, 405",null,"N","107678.01","2020-08-11T13:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"227EF1DD23FA5.02","Stuttgart - München","< >","München-Pasing","München-Lochhausen",2021,2021,12,12,"2021-03-22T22:45:00","22:45:00","2021-03-27T05:20:00","05:20:00","1 d, 09 h","periodical","Track & Rail","T",null,null,null,null,"","R,R,R","","0,0,0",",O,O","Gleiserneuerung MP-MLO 5503+5543 und MP Gl 204, 205, 305, 308, 310, 405",null,"N","107678.02","2020-08-11T13:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FB477DFEAD7A.02","Stuttgart - München",">","München-Pasing","München Hbf",2021,2021,17,18,"2021-04-30T22:50:00","22:50:00","2021-05-03T04:50:00","04:50:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,",,C","R,R,","","0,0,0","O,O,","sonstige Arbeiten Neubau 2. SBSS West Oberirischer Bereich BK21-Bürle-001, Ol-Arbeiten, Verbau LSW Brücke in MLR",null,"N","207685.02","2020-07-06T15:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2005F539CDADA.01","Stuttgart - München",">","München-Pasing","München Hbf",2021,2021,22,23,"2021-06-05T22:50:00","22:50:00","2021-06-10T04:50:00","04:50:00","4 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,",C,C","R,R,R",",B,","0,0,0","O,O,","sonstige Arbeiten Neubau 2. SBSS West Oberirischer Bereich BK21-Bürle-001,  LSW Brücke WL West in MLR",null,"N","207695.01","2020-01-31T09:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"208A56225F658.01","Stuttgart - München","< >","Mering Üst","Olching",2021,2021,28,29,"2021-07-16T22:30:00","22:30:00","2021-07-24T05:30:00","05:30:00","14 h","periodical","Bridge","T",null,null,null,null,"","","","","","Brückenprüfung Erneuerung SÜ Merianstr., Km 21,43",null,"N","207844.01","2019-09-02T13:37:00","Unclassified",5,1,null,null,null,null,"Published",null,"Y"]
[null,80,"208A56225F658.03","Stuttgart - München","< >","Mering Üst","Olching",2021,2021,28,29,"2021-07-17T22:10:00","22:10:00","2021-07-25T05:30:00","05:30:00","15 h","periodical","Bridge","T",null,null,null,null,"","","","","","Brückenprüfung Erneuerung SÜ Merianstr., Km 21,43",null,"N","207844.03","2019-09-02T13:37:00","Unclassified",6,1,null,null,null,null,"Published",null,"Y"]
[null,80,"208A56225F658.04","Stuttgart - München","< >","Mering Üst","Olching",2021,2021,28,30,"2021-07-18T22:30:00","22:30:00","2021-07-26T04:40:00","04:40:00","12 h","periodical","Bridge","T",null,null,null,null,"","","","","","Brückenprüfung Erneuerung SÜ Merianstr., Km 21,43",null,"N","207844.04","2019-09-02T13:37:00","Unclassified",7,1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049AE848C.03","Stuttgart - München","< >","München-Pasing","München Hbf",2021,2021,29,36,"2021-07-24T22:50:00","22:50:00","2021-09-06T04:50:00","04:50:00","3 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,",,C","R,R,R","","0,0,0","O,,","sonstige Arbeiten Neubau 2.SBSS Oberirdischer Bereich Abschnitt West Bündel 0028",null,"N","307295.03","2019-05-24T07:51:00","Unclassified","6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"226A44F0789F1.01","München - Rosenheim - Salzburg ","< >","Rottau","Übersee",2021,2021,12,12,"2021-03-22T22:30:00","22:30:00","2021-03-26T04:30:00","04:30:00","1 d","periodical","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ Sichlerweg, Km 37,333",81,"N","70242","2020-07-28T08:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20DE875011FBA.04","München - Rosenheim - Salzburg ","< >","München Hbf","München Heimeranplatz",2021,2021,27,27,"2021-07-05T16:00:00","16:00:00","2021-07-10T10:30:00","10:30:00","4 d, 19 h","continuous","Switch","T",null,null,null,null,",C,C",",R,R",",,B",",0,0",",O,","Weichenerneuerung WE MH W 243+244 und GE MHB Gl 782",81,"N","207955.04","2020-06-08T11:24:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20975494FABBA.02","München - Rosenheim - Salzburg ",">","München Ost Pbf","München-Trudering",2021,2021,33,34,"2021-08-21T22:00:00","22:00:00","2021-08-23T04:00:00","04:00:00","1 d, 06 h","continuous","Switch",null,"LT",null,null,null,"","R,R,R","","0,0,0","","Weichenerneuerung mit PSS Weiche 236, verschoben von 2019 in München Ost Pbf",81,"N","207866.02","2019-09-11T11:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20975E28E047A.01","München - Rosenheim - Salzburg ","< >","München Ost Pbf","München-Trudering",2021,2021,34,36,"2021-08-27T04:00:00","04:00:00","2021-09-06T04:00:00","04:00:00","10 d","continuous","Switch","T",null,null,null,null,",C,C","R,R,R",",,B","0,0,0","O,,","Weichenerneuerung mit PSS Weiche 275,276,233,234,235,215,216+217, verschoben von 2019 in München Ost Pbf",81,"N","207869.01","2019-09-11T12:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20DE8D83F01FA.03","München - Rosenheim - Salzburg ","< >","München Hbf","München Heimeranplatz",2021,2021,36,36,"2021-09-10T23:00:00","23:00:00","2021-09-11T07:00:00","07:00:00","8 h","continuous","Switch","T",null,null,null,null,",,C",",R,R",",,B",",0,0",",O,","Weichenerneuerung WE MH W 243+244 und GE MHB Gl 782 Qualistopfgang",81,"N","207956.03","2019-10-30T13:41:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704E5C552C.01","München - Rosenheim - Salzburg ","< >","München Hbf","München Hbf",2021,2021,45,47,"2021-11-09T02:00:00","02:00:00","2021-11-23T04:00:00","04:00:00","14 d, 02 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","","","","sonstige Arbeiten Neubau 2.SBSS Oberirdischer Bereich Abschnitt West Bündel 0028",81,"N","307426.01","2019-05-24T07:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"207751530B2D8.01","München - Rosenheim - Salzburg ","< >","Rottau","Übersee",2021,2021,45,46,"2021-11-13T22:30:00","22:30:00","2021-11-15T04:30:00","04:30:00","1 d, 06 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ Sichlerweg, Km 37,333",81,"N","207815.01","2019-11-05T14:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704E5C552C.02","München - Rosenheim - Salzburg ","< >","München Hbf","München Hbf",2021,2021,47,49,"2021-11-23T04:00:00","04:00:00","2021-12-11T23:59:00","23:59:00","18 d, 20 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","","","","sonstige Arbeiten Neubau 2.SBSS Oberirdischer Bereich Abschnitt West Bündel 0028",81,"N","307426.02","2019-05-24T07:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22420086357D9.03","Nürnberg - Regensburg","< >","Neumarkt (Oberpf)","Seubersdorf",2021,2021,3,3,"2021-01-23T21:30:00","21:30:00","2021-01-24T05:30:00","05:30:00","8 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Maststellen + Auslegermontage",null,"N","70119","2020-06-30T16:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225486CA2D076.02","Nürnberg - Regensburg",">","Neumarkt (Oberpf)","Seubersdorf",2021,2021,5,6,"2021-02-05","00:00:00","2021-02-08T04:40:00","04:40:00","3 d, 05 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Kettenwerkszug (Zulauf- u. Weichenkettenwerk) für Üst Deining",null,"N","107003.02","2020-07-13T10:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225486CA2D076.04","Nürnberg - Regensburg","<","Seubersdorf","Neumarkt (Oberpf)",2021,2021,6,7,"2021-02-12T00:25:00","00:25:00","2021-02-15T05:00:00","05:00:00","3 d, 05 h","continuous","Catenary",null,"LT",null,null,null,",C,C","R,R,R","","0,0,0","O,O,O","Oberleitungsarbeiten Kettenwerkszug (Zulauf- u. Weichenkettenwerk) für Üst Deining",null,"N","107003.04","2020-07-13T10:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225486CA2D076.01","Nürnberg - Regensburg","< >","Neumarkt (Oberpf)","Seubersdorf",2021,2021,6,7,"2021-02-14T19:10:00","19:10:00","2021-02-15T04:10:00","04:10:00","9 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Kettenwerkszug (Zulauf- u. Weichenkettenwerk) für Üst Deining",null,"N","107003.01","2020-07-13T10:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225488B7E4A16.01","Nürnberg - Regensburg","< >","Neumarkt (Oberpf)","Seubersdorf",2021,2021,7,9,"2021-02-21T00:35:00","00:35:00","2021-03-01T04:10:00","04:10:00","2 d, 07 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Kettenwerkszug (Zulauf- u. Weichenkettenwerk) für Üst Deining",null,"N","107006.01","2020-07-13T10:25:00","Unclassified","1,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"227F0ADCC4CD9.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg-Prüfening               (NRH)",2021,2021,9,9,"2021-03-06T22:25:00","22:25:00","2021-03-07T05:25:00","05:25:00","7 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Regulierung OL in Regensburg Bbf Bft",null,"N","107667.01","2020-08-11T15:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2287C5D57A8D9.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg-Prüfening               (NRH)",2021,2021,10,10,"2021-03-11T21:40:00","21:40:00","2021-03-12T04:00:00","04:00:00","6 h","continuous","Bridge","T",null,null,null,null,",C,C","R,,","","0,,","O,,","Brückenarbeiten Regulierung OL für Neubau SÜ Klenzebrücke km 1,996",null,"N","107007.01","2020-08-17T15:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2287C7FE52DF9.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg-Prüfening               (NRH)",2021,2021,10,11,"2021-03-13T22:20:00","22:20:00","2021-03-15T04:00:00","04:00:00","1 d, 06 h","continuous","Bridge","T",null,null,null,null,",C,C","R,,","","0,,","O,,","Brückenarbeiten Aufbau Traggerüst + Einheben Träger + Restarbeiten OL für Neubau SÜ Klenzebrücke km 1,996",null,"N","107668.01","2020-08-17T15:37:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A8F1CEEEB0.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Obertraubling",2021,2021,11,11,"2021-03-20T22:20:00","22:20:00","2021-03-21T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,","O,,","Brückenarbeiten Abbruch WL Nord, Vorbereitung Ausbau Schutzgerüst in Regensbg Ost",null,"N","107676.01","2020-08-19T13:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7043200D0C.01","Regensburg - Wels",">","Girching","Vilshofen (Niederbay)",2021,2021,13,14,"2021-04-01T23:30:00","23:30:00","2021-04-06T06:00:00","06:00:00","4 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",C,C","R,,","","0,,0","O,,O","Arbeiten an Lärmschutzanlagen LSW Pleinting Wand 2, Vilshofen Wände 2 u. 6",81,"N","307104.01","2019-05-24T07:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7043200D0C.03","Regensburg - Wels",">","Girching","Vilshofen (Niederbay)",2021,2021,14,20,"2021-04-09T23:30:00","23:30:00","2021-05-17T06:00:00","06:00:00","13 d, 15 h","periodical","Miscellaneous",null,"LT",null,null,null,",C,C","R,,","","0,,","O,,","Arbeiten an Lärmschutzanlagen LSW Pleinting Wand 2, Vilshofen Wände 2 u. 6",81,"N","307104.03","2019-05-24T07:49:00","Unclassified","5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20389C784F038.02","Regensburg - Wels","<","Passau Hbf","Passau Gbf",2021,2021,18,19,"2021-05-07T22:00:00","22:00:00","2021-05-10T05:00:00","05:00:00","2 d, 07 h","continuous","Switch",null,"ST",null,null,null,",C,C","R,,","","0,,0","O,,","Weichenerneuerung Weiche 85, 87, 88 u. 89 in Passau Hbf",81,"N","207727.02","2019-07-08T09:38:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"207A4507820BE.03","Nürnberg - Regensburg","< >","Nürnberg Hbf","Nürnberg Hbf",2021,2021,20,21,"2021-05-22T22:00:00","22:00:00","2021-05-24T05:00:00","05:00:00","1 d, 07 h","continuous","Switch",null,"ST",null,null,null,",C,",",R,","",",0,0",",O,O","Weichenerneuerung W 255 in Nürnberg Hbf",null,"N","207822.03","2019-08-22T12:37:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7046D525CC.03","Nürnberg - Regensburg",">","Postbauer-Heng","Neumarkt (Oberpf)",2021,2021,21,25,"2021-05-27T01:00:00","01:00:00","2021-06-21T05:00:00","05:00:00","25 d, 04 h","continuous","Track & Rail",null,"LT",null,null,null,",C,C","R,R,","","0,0,0","O,O,O","Gleiserneuerung mit BR, PSS und TE GE/PSS Postbauer-Heng - Neumarkt Km 72,862- 65,251",null,"N","307210.03","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704769286C.03","Regensburg - Wels",">","Osterhofen (Niederbay)","Girching",2021,2021,22,25,"2021-06-05T21:00:00","21:00:00","2021-06-26T05:00:00","05:00:00","20 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,",C,C","R,,","","0,,0","O,,O","Gleiserneuerung Ge Osterhofen-Girching, km 36,382-34,100",81,"N","307227.03","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704769286C.05","Regensburg - Wels","< >","Osterhofen (Niederbay)","Girching",2021,2021,23,24,"2021-06-07T21:00:00","21:00:00","2021-06-19T04:00:00","04:00:00","2 d, 22 h","periodical","Track & Rail","T",null,null,null,null,",C,C","R,,","","0,,","O,,","Gleiserneuerung Ge Osterhofen-Girching, km 36,382-34,100",81,"N","307227.05","2019-05-24T07:50:00","Unclassified","1,2,3,4,5",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70478DC76C.01","Nürnberg - Regensburg","< >","Neumarkt (Oberpf)","Postbauer-Heng",2021,2021,23,23,"2021-06-07T22:00:00","22:00:00","2021-06-10T05:00:00","05:00:00","21 h","periodical","Track & Rail","T",null,null,null,null,"C,,C","R,,","","0,0,","O,,","Gleiserneuerung mit BR, PSS und TE G.016177684 Ge/PSS Postbauer-Heng - Neumarkt Km 72,862- 65,251",null,"N","307231.01","2019-05-24T07:50:00","Unclassified","1,2,3",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704769286C.04","Regensburg - Wels","< >","Osterhofen (Niederbay)","Girching",2021,2021,23,24,"2021-06-12T20:30:00","20:30:00","2021-06-20T04:30:00","04:30:00","1 d","periodical","Track & Rail","T",null,null,null,null,",C,C","R,,","","0,,","O,,","Gleiserneuerung Ge Osterhofen-Girching, km 36,382-34,100",81,"N","307227.04","2019-05-24T07:50:00","Unclassified","6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7047BA078C.03","Nürnberg - Regensburg","<","Seubersdorf","Deining Üst",2021,2021,24,26,"2021-06-17T05:00:00","05:00:00","2021-07-03T05:00:00","05:00:00","16 d","continuous","Track & Rail",null,"LT",null,null,null,"","","","","","Schwellenerneuerung Brückenschwellenauswechslung Deining",null,"N","307236.03","2020-08-18T15:19:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"207740D4A68F8.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg-Prüfening               (NRH)",2021,2021,29,30,"2021-07-25T22:00:00","22:00:00","2021-07-26T04:00:00","04:00:00","6 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Neubau Klenzebrücke, Km 1,996",null,"N","207814.01","2019-08-20T10:47:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049E3EC6C.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg Hbf",2021,2021,30,31,"2021-07-29T23:00:00","23:00:00","2021-08-02T23:00:00","23:00:00","4 d","continuous","Track & Rail",null,"ST",null,null,null,"","","",",,0",",,O","Gleiserneuerung Reg Hbf Gl 3, 4, 108",null,"N","307301.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049E3EC6C.02","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg Hbf",2021,2021,31,31,"2021-08-02T23:00:00","23:00:00","2021-08-06T23:00:00","23:00:00","4 d","continuous","Track & Rail",null,"ST",null,null,null,"","","",",,0",",,O","Gleiserneuerung Reg Hbf Gl 3, 4, 108",null,"N","307301.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AA2F9F3C0D8.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Obertraubling",2021,2021,34,34,"2021-08-28T22:20:00","22:20:00","2021-08-29T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,",,C","R,,R",",,B","0,,0","O,,","Brückenarbeiten Erneuerung Autobahnbrücke Burgweinting Bw 59 in Regensbg Ost",null,"N","207895.01","2019-09-24T10:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AA307C1B058.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Obertraubling",2021,2021,35,35,"2021-09-04T22:20:00","22:20:00","2021-09-05T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,",,C","R,,R",",,B","0,,0","O,,","Brückenarbeiten Erneuerung Autobahnbrücke Burgweinting Bw 59 in Regensbg Ost",null,"N","207896.01","2019-09-24T10:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21B49D11B2AB8.01","Nürnberg - Regensburg",">","Beratzhausen","Undorf",2021,2021,36,36,"2021-09-12T07:00:00","07:00:00","2021-09-12T19:00:00","19:00:00","12 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","21B49D11B2AB8.01","2020-03-25T12:54:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B5C60B39ED8.03","Nürnberg - Regensburg","< >","Seubersdorf","Neumarkt (Oberpf)",2021,2021,38,41,"2021-09-26T00:20:00","00:20:00","2021-10-11T04:10:00","04:10:00","15 d, 04 h","continuous","Track & Rail",null,null,null,"P",null,"","","","","","Schienenerneuerung Se2, Km 58,750 - Km 60,400",null,"N","20B5C60B39ED8.03","2019-10-02T09:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20B5C4C9A5B58.04","Nürnberg - Regensburg","<","Seubersdorf","Neumarkt (Oberpf)",2021,2021,39,40,"2021-10-02T06:00:00","06:00:00","2021-10-04T05:00:00","05:00:00","1 d, 23 h","continuous","Track & Rail",null,"LT",null,null,null,"","","","","","Schienenerneuerung Se2, Km 58,750 - Km 60,400",null,"N","20B5C4C9A5B58.04","2019-10-02T09:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20AA38EE15D18.01","Nürnberg - Regensburg","< >","Regensburg Hbf","Obertraubling",2021,2021,42,42,"2021-10-23T22:20:00","22:20:00","2021-10-24T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,",,C","R,,R",",,B","0,,0","O,,","Brückenarbeiten Erneuerung Autobahnbrücke Burgweinting Bw 59 in Regensbg Ost",null,"N","207897.01","2019-09-24T11:24:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7046768B0C.02","Regensburg - Wels","<","Regensburg Ost","Regensburg Hbf",2021,2021,44,45,"2021-11-06T00:30:00","00:30:00","2021-11-11T00:30:00","00:30:00","5 d","continuous","Track & Rail",null,"LT",null,null,null,",C,C","R,,",",,B","0,0,0","O,,","Gleiserneuerung Regensburg Ost-Regensburg Hbf_ km 135,626-137,331",81,"N","307199.02","2019-10-30T10:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2009147D0366D.02","Regensburg - Wels","<","Obertraubling","Regensburg Hbf",2021,2021,44,45,"2021-11-06T01:00:00","01:00:00","2021-11-08T05:00:00","05:00:00","8 h","periodical","Track & Rail",null,"LT",null,null,null,"","","","","","Gleiserneuerung Regensburg Ost-Regensburg Hbf_ km 135,626-137,331",81,"N","2009147D0366D.02","2019-11-04T10:40:00","Unclassified","1,6",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704E6D1E0C.01","Regensburg - Wels","< >","Sünching","Mangolding",2021,2021,44,45,"2021-11-07T01:30:00","01:30:00","2021-11-11T00:30:00","00:30:00","3 d, 23 h","continuous","Bridge","T",null,null,null,null,"C,C,C","R,R,",",B,B","0,0,","O,O,","Brückenarbeiten Erneuerung EÜ km 103,721 Str. 5830 Pa-Otr",81,"N","307428.01","2019-11-28T13:36:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21B6177DF00D8.01","Nürnberg - Regensburg","< >","Regensburg-Prüfening               (NRH)","Beratzhausen",2021,2021,48,49,"2021-12-03T23:30:00","23:30:00","2021-12-06T21:00:00","21:00:00","2 d, 22 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","21B6177DF00D8.01","2020-03-26T13:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21B6177DF00D8.05","Nürnberg - Regensburg","< >","Regensburg-Prüfening               (NRH)","Beratzhausen",2021,2021,49,49,"2021-12-06T21:00:00","21:00:00","2021-12-07T04:30:00","04:30:00","8 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","21B6177DF00D8.05","2020-03-26T13:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21B61E1D79AB8.01","Nürnberg - Regensburg","<","Regensburg-Prüfening               (NRH)","Beratzhausen",2021,2021,49,49,"2021-12-07T04:30:00","04:30:00","2021-12-11T18:30:00","18:30:00","4 d, 14 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","21B61E1D79AB8.01","2020-03-26T13:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2221D350A8960.02","Regensburg - München","< >","Neufahrn (b Freising) Nord","Langenbach (Oberbay)",2021,2021,4,4,"2021-01-29T20:30:00","20:30:00","2021-01-31T04:15:00","04:15:00","16 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Fahrdrahtwechsel nach Bstg Arbeiten in Freising",null,"N","70054","2020-06-08T14:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"227747F48FB40.02","Regensburg - München",">","Neufahrn (Niederbay)","Landshut (Bay) Hbf",2021,2021,9,10,"2021-03-05T09:00:00","09:00:00","2021-03-08T12:00:00","12:00:00","3 d, 03 h","continuous","Switch",null,"LT",null,null,null,"","","","","","Weicheneinbau Neubau Überleitverbindung - Ol Arbeiten in Artlkofen Üst",null,"N","307206.02","2020-08-06T07:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"227747F48FB40.01","Regensburg - München","<","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,10,11,"2021-03-12T09:00:00","09:00:00","2021-03-15T12:00:00","12:00:00","3 d, 03 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weicheneinbau Neubau Überleitverbindung - Ol Arbeiten in Artlkofen Üst",null,"N","307206.01","2020-08-06T07:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2005F13AFCDBA.04","Regensburg - München","<","München-Neulustheim","München-Moosach",2021,2021,18,19,"2021-05-07T23:00:00","23:00:00","2021-05-10T04:00:00","04:00:00","2 d, 05 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","sonstige Arbeiten Neubau 2. SBSS West Oberirischer Bereich BK21-Bürle-001, Einbau W 762 im IH-Korridor Stammstrecke in Mü-Laim Pbf",null,"N","2005F13AFCDBA.04","2019-06-03T13:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70437706AC.03","Regensburg - München",">","Köfering","Eggmühl",2021,2021,21,21,"2021-05-28T01:00:00","01:00:00","2021-05-29T13:00:00","13:00:00","1 d, 12 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Weichenerneuerung Köfering Weichen 1, 2, 3",null,"N","307113.03","2019-07-18T14:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70444CA62C.02","Regensburg - München","<","Eggmühl","Obertraubling",2021,2021,21,22,"2021-05-29T13:00:00","13:00:00","2021-05-31T05:00:00","05:00:00","1 d, 16 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weichenerneuerung Köfering Weichen 1, 2, 3",null,"N","307137.02","2019-07-18T15:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704722F7AC.01","Regensburg - München","<","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,22,23,"2021-06-04T23:00:00","23:00:00","2021-06-08T05:00:00","05:00:00","3 d, 06 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307219.01","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704722F7AC.02","Regensburg - München","< >","Neufahrn (Niederbay)","Landshut (Bay) Hbf",2021,2021,22,22,"2021-06-05T03:00:00","03:00:00","2021-06-05T17:00:00","17:00:00","14 h","continuous","Switch","T",null,null,null,null,",,C","R,,","","0,,","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307219.02","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7047C32F4C.01","Regensburg - München",">","Neufahrn (Niederbay)","Landshut (Bay) Hbf",2021,2021,23,24,"2021-06-10T23:00:00","23:00:00","2021-06-14T05:00:00","05:00:00","3 d, 06 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307237.01","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7047C32F4C.02","Regensburg - München","< >","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,23,23,"2021-06-11T03:00:00","03:00:00","2021-06-11T17:00:00","17:00:00","14 h","continuous","Switch","T",null,null,null,null,"","","","","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307237.02","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70481BAF8C.02","Regensburg - München","<","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,24,24,"2021-06-16T14:00:00","14:00:00","2021-06-18T22:00:00","22:00:00","2 d, 08 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307248.02","2019-07-18T16:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70481BAF8C.04","Regensburg - München","< >","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,24,25,"2021-06-18T22:00:00","22:00:00","2021-06-21T06:00:00","06:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,",,C","R,,","","0,,","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307248.04","2019-07-18T16:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2038C943624D8.01","Regensburg - München","< >","Köfering","Obertraubling",2021,2021,24,25,"2021-06-18T22:00:00","22:00:00","2021-06-21T06:00:00","06:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,","","Brückenarbeiten Erneuerung EÜ Köfering, Km 126,988",null,"N","207728.01","2020-06-10T12:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2061991D62B18.02","Regensburg - München","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2021,2021,24,26,"2021-06-18T22:00:00","22:00:00","2021-07-01T05:00:00","05:00:00","12 d, 07 h","continuous","Track & Rail","T",null,null,null,null,"","","","0,,0","","Gleiserneuerung Gleis 429 u. RüLü Weiche 487 in Landshut/B Hbf",null,"N","207784.02","2020-06-02T15:35:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70481BAF8C.03","Regensburg - München",">","Neufahrn (Niederbay)","Landshut (Bay) Hbf",2021,2021,25,25,"2021-06-23T14:00:00","14:00:00","2021-06-25T22:00:00","22:00:00","2 d, 08 h","continuous","Switch",null,"LT",null,null,null,",,C","R,,","","0,,0","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307248.03","2019-07-18T16:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2038C943624D8.02","Regensburg - München","< >","Köfering","Obertraubling",2021,2021,25,26,"2021-06-25T08:00:00","08:00:00","2021-06-28T06:00:00","06:00:00","2 d, 22 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ Köfering, Km 126,988",null,"N","2038C943624D8.02","2020-06-10T12:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70488805EC.01","Regensburg - München","< >","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,25,26,"2021-06-25T22:00:00","22:00:00","2021-06-28T06:00:00","06:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,",,C","R,,","","0,,","","Weicheneinbau Neubau Überleitverbindung Artlkofen km 85,7",null,"N","307261.01","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7048DA6BAC.02","Regensburg - München","< >","Landshut (Bay) Hbf","Neufahrn (Niederbay)",2021,2021,26,26,"2021-07-04T01:00:00","01:00:00","2021-07-04T11:00:00","11:00:00","10 h","continuous","Switch","T",null,null,null,null,",,C","R,,","","0,,","","Weicheneinbau Neubau Überleitverbindung Artlkofen",null,"N","307271.02","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049AE848C.01","Regensburg - München","< >","München Kanal","München Hbf",2021,2021,29,36,"2021-07-24T22:50:00","22:50:00","2021-09-06T04:50:00","04:50:00","3 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,",,C",",,R",",,B",",,0","","sonstige Arbeiten Neubau 2.SBSS Oberirdischer Bereich Abschnitt West Bündel 0028",null,"N","307295.01","2019-05-24T07:51:00","Unclassified","6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704BF5674C.03","Regensburg - München","<","Köfering","Obertraubling",2021,2021,37,39,"2021-09-19T01:00:00","01:00:00","2021-10-03T05:00:00","05:00:00","14 d, 04 h","continuous","Track & Rail",null,"LT",null,null,null,",,C","R,,","","0,,0","","Gleiserneuerung mit BR und PSS Gleiserneuerung und Einbau PSS Köfering - Obertraubling km 125,857 - km 130,206",null,"N","307360.03","2019-07-10T11:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704116334C.03","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Freimann",2021,2021,9,9,"2021-03-06T12:00:00","12:00:00","2021-03-06T23:59:00","23:59:00","12 h","continuous","Signal","T",null,null,null,null,"","R,R,","","0,,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307592.03","2020-07-02T12:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2221A14732C2F.01","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,9,13,"2021-03-06T12:00:00","12:00:00","2021-03-29T15:00:00","15:00:00","8 d, 12 h","periodical","Signal","T",null,null,null,null,"","R,R,R",",B,B","0,,0","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","307050.01","2020-06-08T10:52:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2221A14732C2F.03","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,10,10,"2021-03-08T15:00:00","15:00:00","2021-03-09T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307050.03","2020-06-08T10:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2221A14732C2F.05","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2021,2021,11,13,"2021-03-15T15:00:00","15:00:00","2021-03-30T06:00:00","06:00:00","1 d, 21 h","periodical","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307050.05","2020-06-08T10:52:00","Unclassified",1,1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A705D9732F.01","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,13,14,"2021-04-01T15:00:00","15:00:00","2021-04-05T14:00:00","14:00:00","3 d, 23 h","continuous","Signal","T",null,null,null,null,"","R,R,",",B,","0,0,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307103.01","2020-08-19T11:27:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A705D9732F.03","Stuttgart - München","< >","München Nord Richtungsgruppe Süd","München-Milbertshofen",2021,2021,14,14,"2021-04-05T14:00:00","14:00:00","2021-04-06T09:00:00","09:00:00","19 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307103.03","2020-08-19T11:27:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A71F7DC7EF.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,14,15,"2021-04-10T12:00:00","12:00:00","2021-04-12T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,"","R,R,R",",B,B","0,,0","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307067.02","2020-08-19T11:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A71F7DC7EF.04","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,15,15,"2021-04-12T15:00:00","15:00:00","2021-04-13T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307067.04","2020-08-19T11:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A7398B65CF.02","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,15,22,"2021-04-17T12:00:00","12:00:00","2021-05-31T15:00:00","15:00:00","14 d, 21 h","periodical","Signal","T",null,null,null,null,"","R,R,",",B,","0,,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307094.02","2020-08-19T11:40:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A70A642B6F.04","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,15,15,"2021-04-18T00:45:00","00:45:00","2021-04-18T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70375, 70376","2020-08-19T11:28:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A7398B65CF.04","Stuttgart - München",">","München-Milbertshofen","München-Freimann",2021,2021,16,18,"2021-04-19T15:00:00","15:00:00","2021-05-04T06:00:00","06:00:00","1 d, 21 h","periodical","Signal",null,"LT",null,null,null,"","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307094.04","2020-08-19T11:40:00","Unclassified",1,1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A776AB492F.01","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,17,17,"2021-05-02T00:45:00","00:45:00","2021-05-02T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70376","2020-08-19T11:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A79588496F.01","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,18,19,"2021-05-08T12:00:00","12:00:00","2021-05-11T06:00:00","06:00:00","2 d, 18 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70376","2020-08-19T12:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A7398B65CF.05","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,19,22,"2021-05-10T15:00:00","15:00:00","2021-06-01T06:00:00","06:00:00","2 d, 12 h","periodical","Signal",null,"LT",null,null,null,"","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307094.05","2020-08-19T11:40:00","Unclassified",1,1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A79588496F.04","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,19,19,"2021-05-16T00:45:00","00:45:00","2021-05-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70376","2020-08-19T12:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A7A62E110F.01","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,21,21,"2021-05-24T15:00:00","15:00:00","2021-05-25T22:00:00","22:00:00","1 d, 07 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70376","2020-08-19T12:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"228A7A62E110F.04","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,21,21,"2021-05-26T06:00:00","06:00:00","2021-05-28T22:00:00","22:00:00","2 d","periodical","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","70376","2020-08-19T12:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20D902860D26D.01","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,21,22,"2021-05-29T12:00:00","12:00:00","2021-06-01T06:00:00","06:00:00","2 d, 18 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","20D902860D26D.01","2019-10-28T10:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20D902860D26D.04","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,22,22,"2021-06-01T06:00:00","06:00:00","2021-06-01T22:00:00","22:00:00","16 h","periodical","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","20D902860D26D.04","2019-10-28T10:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70420D648C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2021,2021,22,24,"2021-06-05T12:00:00","12:00:00","2021-06-14T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,"","R,R,",",B,","0,0,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307075.02","2019-07-05T14:35:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70420D648C.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,23,24,"2021-06-07T15:00:00","15:00:00","2021-06-15T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,"C,,","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307075.03","2019-07-05T14:35:00","Unclassified",1,1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7043AAE7EC.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2021,2021,24,26,"2021-06-19T12:00:00","12:00:00","2021-06-28T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,"C,,","R,R,",",B,","0,0,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307119.02","2019-07-05T15:08:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7043AAE7EC.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,25,26,"2021-06-21T15:00:00","15:00:00","2021-06-29T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,"C,,","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307119.03","2019-07-05T15:08:00","Unclassified",1,1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7044C9C56C.01","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2021,2021,26,27,"2021-07-03T12:00:00","12:00:00","2021-07-05T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,"","R,R,",",B,","0,,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307152.01","2019-07-05T15:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7044C9C56C.03","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2021,2021,27,27,"2021-07-05T15:00:00","15:00:00","2021-07-06T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307152.03","2019-07-05T15:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704526D98C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2021,2021,27,29,"2021-07-10T12:00:00","12:00:00","2021-07-19T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,"","R,R,",",B,","0,,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307162.02","2019-07-05T15:16:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704526D98C.01","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2021,2021,28,28,"2021-07-12T15:00:00","15:00:00","2021-07-13T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307162.01","2019-07-05T15:16:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704526D98C.04","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,29,29,"2021-07-19T15:00:00","15:00:00","2021-07-20T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"C,,","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307162.04","2019-07-05T15:16:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704940A78C.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,29,30,"2021-07-24T12:00:00","12:00:00","2021-07-26T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,"","R,R,R",",B,B","0,,0","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307283.02","2019-07-08T09:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704940A78C.03","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2021,2021,30,30,"2021-07-26T15:00:00","15:00:00","2021-07-27T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307283.03","2019-07-08T09:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70497C29EC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2021,2021,30,32,"2021-07-31T12:00:00","12:00:00","2021-08-09T15:00:00","15:00:00","2 d, 20 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307289.02","2019-07-08T09:46:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70497C29EC.01","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2021,2021,30,32,"2021-07-31T12:00:00","12:00:00","2021-08-10T06:00:00","06:00:00","5 d, 12 h","periodical","Signal",null,"LT",null,null,null,"","R,R,R",",B,B","0,,0","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307289.01","2019-07-08T09:46:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049A6E36C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2021,2021,32,34,"2021-08-14T12:00:00","12:00:00","2021-08-23T15:00:00","15:00:00","2 d, 20 h","continuous","Signal","T",null,null,null,null,"","R,R,",",B,","0,,","O,O,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307294.02","2020-07-01T16:48:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7049A6E36C.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,32,34,"2021-08-14T12:00:00","12:00:00","2021-08-24T06:00:00","06:00:00","5 d, 12 h","periodical","Signal",null,"LT",null,null,null,"C,,","R,,","","0,,","O,,","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"Y","307294.03","2020-07-01T16:48:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22437608A6C6D.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2021,2021,36,39,"2021-09-11T12:00:00","12:00:00","2021-09-27T15:00:00","15:00:00","4 d, 06 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","22437608A6C6D.02","2020-07-01T16:50:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22437608A6C6D.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2021,2021,36,39,"2021-09-11T12:00:00","12:00:00","2021-09-28T06:00:00","06:00:00","8 d, 06 h","periodical","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen ESTW Milbertshofen",null,"N","22437608A6C6D.03","2020-07-01T16:50:00","Unclassified","1,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CC1DF0C.01","Stuttgart - München","<","München-Johanneskirchen","München-Freimann",2021,2021,40,41,"2021-10-07","00:00:00","2021-10-11T22:00:00","22:00:00","4 d, 22 h","continuous","Switch",null,"LT",null,null,null,"","R,R,",",B,","0,0,","O,O,","Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"Y","307383.01","2019-07-04T17:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CDBCFAC.02","Stuttgart - München","< >","München-Johanneskirchen","München-Freimann",2021,2021,41,41,"2021-10-11T22:00:00","22:00:00","2021-10-17T04:00:00","04:00:00","5 d, 06 h","continuous","Switch","T",null,null,null,null,"C,,","R,R,",",B,","0,0,","O,O,","Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"Y","307385.02","2019-07-04T17:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704DC2380C.03","Stuttgart - München","< >","München-Freimann","München-Johanneskirchen",2021,2021,43,44,"2021-10-30T00:30:00","00:30:00","2021-11-03T03:30:00","03:30:00","4 d, 03 h","continuous","Switch","T",null,null,null,null,"","R,R,",",B,","0,0,","O,O,","Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"Y","307410.03","2019-07-05T10:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2264A57E561CB.01","Gemünden - Bamberg - Nürnberg","< >","Haßfurt","Haßfurt",2021,2021,2,21,"2021-01-11T22:30:00","22:30:00","2021-05-24T05:00:00","05:00:00","132 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","",",,0","","Bahnsteigarbeiten Haßfurt Neubau Mittelbahnsteig Gl.2/3 in Haßfurt",null,"Y","307021.01","2020-11-25T13:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"222BD5085718B.01","Gemünden - Bamberg - Nürnberg","< >","Gädheim","Haßfurt",2021,2021,3,3,"2021-01-23T21:05:00","21:05:00","2021-01-24T11:00:00","11:00:00","14 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,","O,,O","Brückenarbeiten Neubau SÜ km 38,4 und km 76,6 NHT-NGAE",null,"N","107654.01","2020-06-15T11:08:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C28582090B.02","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Schweinfurt Hbf",2021,2021,13,13,"2021-04-02T15:00:00","15:00:00","2021-04-03T19:50:00","19:50:00","1 d, 05 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307105.02","2020-08-31T15:41:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2264AB70668CB.01","Gemünden - Bamberg - Nürnberg","<","Zeil","Gädheim",2021,2021,13,14,"2021-04-02T22:30:00","22:30:00","2021-04-05T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Bahnsteigarbeiten Haßfurt Neubau Mittelbahnsteig Gl. 2/3 in Haßfurt",null,"N","307106.01","2020-07-24T12:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C28582090B.05","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2021,2021,13,13,"2021-04-03T19:50:00","19:50:00","2021-04-04T09:50:00","09:50:00","14 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307105.05","2020-08-31T15:41:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C28FF97A8B.01","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Waigolshausen",2021,2021,13,14,"2021-04-04T09:50:00","09:50:00","2021-04-05T15:00:00","15:00:00","1 d, 05 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307109.01","2020-08-31T15:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C2A804DFCB.02","Gemünden - Bamberg - Nürnberg","< >","Waigolshausen","Schweinfurt Hbf",2021,2021,14,14,"2021-04-09T22:05:00","22:05:00","2021-04-10T04:05:00","04:05:00","6 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307114.02","2020-08-31T15:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2264AB70668CB.03","Gemünden - Bamberg - Nürnberg","<","Zeil","Gädheim",2021,2021,14,15,"2021-04-09T22:30:00","22:30:00","2021-04-12T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Bahnsteigarbeiten Haßfurt Neubau Mittelbahnsteig Gl. 2/3 in Haßfurt",null,"N","307106.03","2020-07-24T12:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C2A804DFCB.04","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Schweinfurt Hbf",2021,2021,14,14,"2021-04-10T04:05:00","04:05:00","2021-04-11T10:00:00","10:00:00","1 d, 06 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307114.04","2020-08-31T15:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C2A804DFCB.05","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Waigolshausen",2021,2021,14,15,"2021-04-11T10:00:00","10:00:00","2021-04-12T16:00:00","16:00:00","1 d, 06 h","continuous","Bridge",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307114.05","2020-08-31T15:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2264ACD29860B.01","Gemünden - Bamberg - Nürnberg","<","Zeil","Gädheim",2021,2021,15,16,"2021-04-16T22:30:00","22:30:00","2021-04-19T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Bahnsteigarbeiten Haßfurt Neubau Mittelbahnsteig Gl. 2/3 in Haßfurt",null,"N","307134.01","2020-07-24T12:38:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"229C2E1C2102B.02","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Schweinfurt Hbf",2021,2021,15,15,"2021-04-17T05:00:00","05:00:00","2021-04-17T20:00:00","20:00:00","15 h","continuous","Bridge",null,"LT",null,null,null,",,C","R,,","","0,,0",",,O","Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","307136.02","2020-08-31T16:03:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70469CB0AC.01","Gemünden - Bamberg - Nürnberg","< >","Haßfurt","Haßfurt",2021,2021,21,32,"2021-05-25T22:30:00","22:30:00","2021-08-13T05:00:00","05:00:00","79 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,",,C","","",",,0","","Bahnsteigarbeiten Haßfurt (Teil 2) - Neubau Mittelbstg. Gleis 2/3, Verziehung Gleis 3",null,"Y","307203.01","2019-05-24T07:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"200B61C4D60BE.01","Gemünden - Bamberg - Nürnberg","< >","Gädheim","Haßfurt",2021,2021,33,33,"2021-08-21T21:00:00","21:00:00","2021-08-22T15:00:00","15:00:00","18 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,","O,,O","Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Einbau Schutzeinrichtung",null,"N","207704.01","2020-05-15T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704A9B076C.04","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2021,2021,34,35,"2021-08-26T22:00:00","22:00:00","2021-09-02T05:00:00","05:00:00","6 d, 07 h","continuous","Track & Rail","T",null,null,null,null,"C,,C","R,,","","0,,","O,,O","Gleiserneuerung Schweinfurt Hbf - Waigolshausen km 58,201 - 59,400",null,"N","307322.04","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704AB3716C.02","Gemünden - Bamberg - Nürnberg","< >","Waigolshausen","Schweinfurt Hbf",2021,2021,34,35,"2021-08-26T22:30:00","22:30:00","2021-09-02T04:00:00","04:00:00","6 d, 05 h","continuous","Bridge","T",null,null,null,null,"C,,C","R,,","","0,,","O,,O","Brückenarbeiten Erneuerung EÜ km 60,242 über A 70",null,"N","307325.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704ABC992C.01","Gemünden - Bamberg - Nürnberg","< >","Waigolshausen","Seligenstadt (b Würzburg)",2021,2021,34,35,"2021-08-26T22:45:00","22:45:00","2021-08-30T04:15:00","04:15:00","3 d, 06 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,",",,O","Brückenarbeiten Erneuerung EÜ Prosselsheim km 82,180",null,"N","307326.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704AC43A4C.01","Gemünden - Bamberg - Nürnberg","<","Zeil","Gädheim",2021,2021,34,35,"2021-08-27T22:30:00","22:30:00","2021-08-30T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",,C","R,,","","0,,0","O,,O","Bahnsteigarbeiten Haßfurt (Teil 2) - Neubau Mittelbstg. Gleis 2/3, Verziehung Gleis 3",null,"N","307327.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"204739424AA1E.02","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2021,2021,34,34,"2021-08-27T23:00:00","23:00:00","2021-08-29T06:00:00","06:00:00","14 h","periodical","Miscellaneous","T",null,null,null,null,",,C","R,,","","0,,","O,,","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.3 in Bamberg",null,"N","207751.02","2020-05-07T14:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"200B62A2A927E.01","Gemünden - Bamberg - Nürnberg","< >","Gädheim","Haßfurt",2021,2021,34,34,"2021-08-28T21:00:00","21:00:00","2021-08-29T09:00:00","09:00:00","12 h","continuous","Bridge","T",null,null,null,null,",,C","R,,","","0,,","O,,","Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Aushub Überbauteile",null,"N","207705.01","2020-05-15T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22577D68E4764.01","Gemünden - Bamberg - Nürnberg","< >","Wernfeld","Gemünden (Main)",2021,2021,7,8,"2021-02-16T08:00:00","08:00:00","2021-02-23T16:00:00","16:00:00","1 d, 16 h","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307037.01","2020-07-15T11:10:00","Unclassified","1,2,3,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22577D68E4764.02","Gemünden - Bamberg - Nürnberg","< >","Eußenheim","Wernfeld",2021,2021,8,9,"2021-02-24T08:00:00","08:00:00","2021-03-04T16:00:00","16:00:00","2 d","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307037.02","2020-07-15T11:10:00","Unclassified","1,2,3,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225A50A85FC24.01","Gemünden - Bamberg - Nürnberg","< >","Thüngen (Unterfr)","Wernfeld",2021,2021,10,10,"2021-03-08T08:00:00","08:00:00","2021-03-09T16:00:00","16:00:00","16 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307063.01","2020-07-17T09:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225A50A85FC24.02","Gemünden - Bamberg - Nürnberg","< >","Thüngen (Unterfr)","Eußenheim",2021,2021,10,11,"2021-03-10T08:00:00","08:00:00","2021-03-16T16:00:00","16:00:00","1 d, 08 h","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307063.02","2020-07-17T09:46:00","Unclassified","1,2,3,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225A50A85FC24.03","Gemünden - Bamberg - Nürnberg","< >","Arnstein (Unterfr)","Eußenheim",2021,2021,11,11,"2021-03-17T08:00:00","08:00:00","2021-03-18T16:00:00","16:00:00","16 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307063.03","2020-07-17T09:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"225A518E04D24.01","Gemünden - Bamberg - Nürnberg","< >","Arnstein (Unterfr)","Thüngen (Unterfr)",2021,2021,12,13,"2021-03-22T08:00:00","08:00:00","2021-04-01T16:00:00","16:00:00","2 d, 16 h","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Ol-Vollinspektion",null,"N","307078.01","2020-07-17T09:49:00","Unclassified","1,2,3,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A93E9D00A44.01","Gemünden - Bamberg - Nürnberg","< >","Thüngen (Unterfr)","Mühlhausen (Wern)",2021,2021,14,14,"2021-04-06T08:00:00","08:00:00","2021-04-08T16:00:00","16:00:00","1 d","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Vollinstandsetzung in Arnstein (Ufr)",null,"N","307111.01","2020-09-09T15:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22B481075A2E4.01","Gemünden - Bamberg - Nürnberg","< >","Mühlhausen (Wern)","Arnstein (Unterfr)",2021,2021,15,15,"2021-04-12T08:00:00","08:00:00","2021-04-14T16:00:00","16:00:00","1 d","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Vollinspektion Ol",null,"N","307125.01","2020-09-17T09:13:00","Unclassified","1,2,3",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22B481075A2E4.02","Gemünden - Bamberg - Nürnberg","< >","Mühlhausen (Wern)","Mühlhausen (Wern)",2021,2021,15,16,"2021-04-15T08:00:00","08:00:00","2021-04-19T16:00:00","16:00:00","16 h","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Vollinspektion Ol",null,"N","307125.02","2020-09-17T09:13:00","Unclassified","1,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22B481075A2E4.03","Gemünden - Bamberg - Nürnberg","< >","Waigolshausen","Mühlhausen (Wern)",2021,2021,16,16,"2021-04-20T08:00:00","08:00:00","2021-04-22T16:00:00","16:00:00","1 d","periodical","Catenary","T",null,null,null,null,"","R,,","","0,,","O,,","Oberleitungsarbeiten Vollinspektion Ol",null,"N","307125.03","2020-09-17T09:13:00","Unclassified","2,3,4",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20A18B5B8CFA7.01","Gemünden - Bamberg - Nürnberg","< >","Wernfeld","Gemünden (Main)",2021,2021,34,35,"2021-08-26T22:00:00","22:00:00","2021-09-02T05:00:00","05:00:00","6 d, 07 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung mit PSS Weichenerneuerung Gemünden W103,106,182,183,184",null,"N","20A18B5B8CFA7.01","2020-05-26T11:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20DF232B3A527.02","Gemünden - Bamberg - Nürnberg","< >","Wernfeld","Gemünden (Main)",2021,2021,35,35,"2021-09-01T22:00:00","22:00:00","2021-09-02T05:00:00","05:00:00","7 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung mit PSS Weichenerneuerung Gemünden W103,106,182,183,184 in Gemünden (Main)",null,"N","20DF232B3A527.02","2020-05-26T12:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20A209D5A6EC7.03","Gemünden - Bamberg - Nürnberg","< >","Wernfeld","Gemünden (Main)",2021,2021,46,46,"2021-11-20T23:00:00","23:00:00","2021-11-21T05:00:00","05:00:00","6 h","periodical","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung mit PSS Weichenerneuerung Gemünden W103,106,182,183,184 in Gemünden (Main)",null,"N","20A209D5A6EC7.03","2019-12-03T14:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2065C5CB2D21E.04","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Nürnberg Großmarkt",2021,2021,31,32,"2021-08-08T21:00:00","21:00:00","2021-08-09T05:00:00","05:00:00","8 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Vollinspektion_Anm.3460 in Fürth (Bay) Hbf",null,"N","2065C5CB2D21E.04","2019-08-08T10:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22634731AB8CB.01","Gemünden - Bamberg - Nürnberg","<","Bamberg","Breitengüßbach",2021,2021,1,12,"2021-01-09T22:30:00","22:30:00","2021-03-26T04:00:00","04:00:00","75 d, 05 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","sonstige Arbeiten NBS 02/21 + 07/21U Neubau Streckengleis",null,"N","307013.01","2020-07-23T13:35:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"222EB0928298B.01","Gemünden - Bamberg - Nürnberg","< >","Unterleiterbach","Bamberg",2021,2021,3,4,"2021-01-22T22:00:00","22:00:00","2021-01-25T22:00:00","22:00:00","3 d","continuous","Bridge","T",null,null,null,null,"C,C,C","R,R,","","0,0,","O,,","Brückenarbeiten NBS 06/21 U Abbruch SÜ BAB 73 km 6,573",null,"N","307019.01","2020-06-17T10:16:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704038F2AC.01","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Hirschaid",2021,2021,3,3,"2021-01-23T20:00:00","20:00:00","2021-01-24T20:00:00","20:00:00","1 d","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten SÜ FO 17 km 39,457 ( SÜ B505 km 55,504)_Anm.IB21-Mos-106-Ä1",null,"N","307020.01","2019-12-11T14:43:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2261DA19C5BCB.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach",2021,2021,4,4,"2021-01-30T22:30:00","22:30:00","2021-01-31T08:30:00","08:30:00","10 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten NBS 02/21U Neubau Streckengleise",null,"N","70234","2020-07-22T14:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2261DA19C5BCB.03","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach",2021,2021,4,5,"2021-01-31T22:30:00","22:30:00","2021-02-01T05:00:00","05:00:00","7 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten NBS 02/21U Neubau Streckengleise",null,"N","70234","2020-07-22T14:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7040E55F4C.01","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Hirschaid",2021,2021,7,7,"2021-02-20T22:00:00","22:00:00","2021-02-21T06:00:00","06:00:00","8 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten SÜ FO 17 km 39,457 (SÜ B505 km 55,504)_Anm.IB21-Mos-106_Ä1",null,"N","307040.01","2019-12-11T14:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70411DD46C.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Forchheim (Oberfr)",2021,2021,8,9,"2021-02-27T22:00:00","22:00:00","2021-03-01T05:00:00","05:00:00","14 h","periodical","Bridge","T",null,null,null,null,",,C","R,R,","","0,0,","O,,O","Brückenarbeiten EÜ Maximilianstraße km 51,230_Anm.IB21-Mos-105_Ä1",null,"N","307047.01","2019-12-11T15:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF70412E9D4C.01","Gemünden - Bamberg - Nürnberg","< >","Hirschaid","Forchheim (Oberfr)",2021,2021,8,9,"2021-02-28T22:00:00","22:00:00","2021-03-01T05:00:00","05:00:00","7 h","periodical","Miscellaneous","T",null,null,null,null,"","","",",,0","","sonstige Arbeiten VDE 8.1 PA 19 VP 19.2300",null,"N","307049.01","2020-01-28T11:28:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2291A8CBD038B.04","Gemünden - Bamberg - Nürnberg","<","Fürth (Bay) Hbf","Vach",2021,2021,12,12,"2021-03-22T23:10:00","23:10:00","2021-03-26T23:00:00","23:00:00","4 d","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Ju-Mos-121 Interimslösung Einbau Weichen in Fürth-Untfarrnb Hp",null,"N","107646.04","2020-08-24T10:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2261D6CA5660B.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Unterleiterbach",2021,2021,12,13,"2021-03-26T04:00:00","04:00:00","2021-03-29T04:00:00","04:00:00","3 d","continuous","Bridge","T",null,null,null,null,"C,C,C","R,R,",",B,","0,0,","","Brückenarbeiten NBS 07/21U Anbindung Richtungsgleise",null,"N","307086.01","2020-07-22T13:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2291A8CBD038B.01","Gemünden - Bamberg - Nürnberg","< >","Vach","Fürth (Bay) Hbf",2021,2021,12,13,"2021-03-26T22:00:00","22:00:00","2021-03-29T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,"C,C,C","R,R,",",B,","0,0,","O,,","Oberleitungsarbeiten Ju-Mos-121 Interimslösung Einbau Weichen in Fürth-Untfarrnb Hp",null,"N","107646.01","2020-08-24T10:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"223BC63F15C2B.01","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Hirschaid",2021,2021,12,13,"2021-03-26T22:00:00","22:00:00","2021-03-29T04:00:00","04:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten VDE 8.1 PA 19 Streckenbau",null,"N","307085.01","2020-06-26T10:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22963EEBA454B.01","Gemünden - Bamberg - Nürnberg","< >","Bad Staffelstein","Bamberg",2021,2021,12,12,"2021-03-27T21:00:00","21:00:00","2021-03-28T06:00:00","06:00:00","9 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen NBS 11/21U IBN Richtungsgleise NHAL-NUL",null,"N","307092.01","2020-08-27T14:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22634731AB8CB.03","Gemünden - Bamberg - Nürnberg",">","Breitengüßbach","Bamberg",2021,2021,13,13,"2021-03-29T04:00:00","04:00:00","2021-04-02T16:00:00","16:00:00","4 d, 12 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,0",",,O","sonstige Arbeiten NBS 02/21 + 07/21U Neubau Streckengleis",null,"N","307013.03","2020-07-23T13:35:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2203037F45EBE.04","Gemünden - Bamberg - Nürnberg","< >","Vach","Erlangen",2021,2021,35,35,"2021-09-03T21:00:00","21:00:00","2021-09-04T04:00:00","04:00:00","7 h","continuous","Switch","T",null,null,null,null,"","","","","","Weicheneinbau W 28W417+418_Ju-Bk21-Mos-003-Ä1 in Eltersdorf",null,"N","2203037F45EBE.04","2020-05-18T09:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFD16568727E.01","Gemünden - Bamberg - Nürnberg","< >","Vach","Fürth (Bay) Hbf",2021,2021,35,35,"2021-09-03T21:00:00","21:00:00","2021-09-04T04:00:00","04:00:00","7 h","continuous","Switch","T",null,null,null,null,",C,C","R,R,",",B,","0,0,","O,,","Weicheneinbau WEB W 902,903+906+907 u.Errichtung Ol _Ju-Bk-21-Mos-001_Ä2 in Fürth-Untfarrnb Hp",null,"N","207691.01","2020-05-15T15:22:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704B0BF1AC.03","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Bamberg",2021,2021,35,35,"2021-09-03T21:00:00","21:00:00","2021-09-04T04:00:00","04:00:00","7 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten VDE 8.1 PA 19 VP 19.2300_Anm.IB21-Mos-101",null,"N","80001","2019-12-12T08:38:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704B0BF1AC.01","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Bamberg",2021,2021,35,37,"2021-09-03T21:00:00","21:00:00","2021-09-14T04:00:00","04:00:00","10 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,",",B,","0,0,","O,,","sonstige Arbeiten VDE 8.1 PA 19 VP 19.2300_Anm.IB21-Mos-101",null,"N","307335.01","2019-12-12T08:38:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704B0BF1AC.02","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2021,2021,35,37,"2021-09-03T21:00:00","21:00:00","2021-09-14T04:00:00","04:00:00","10 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,",",B,","0,0,","O,,","sonstige Arbeiten VDE 8.1 PA 19 VP 19.2300_Anm.IB21-Mos-101",null,"N","307335.02","2019-12-12T08:38:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704A6D40AC.01","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2021,2021,35,38,"2021-09-03T21:00:00","21:00:00","2021-09-21T04:00:00","04:00:00","17 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,","","sonstige Arbeiten VDE 8.1 PA 21 Streckenbau_Anm.IB21-Mos-103",null,"N","307316.01","2019-12-12T07:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704A6D40AC.02","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2021,2021,35,38,"2021-09-03T21:00:00","21:00:00","2021-09-21T04:00:00","04:00:00","17 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten VDE 8.1 PA 21 Streckenbau_Anm.IB21-Mos-103",null,"N","307316.02","2019-12-12T07:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFD16568727E.04","Gemünden - Bamberg - Nürnberg","<","Fürth (Bay) Hbf","Vach",2021,2021,35,37,"2021-09-04T04:00:00","04:00:00","2021-09-14T04:00:00","04:00:00","10 d","continuous","Switch",null,"LT",null,null,null,"C,C,C","R,R,",",B,","0,0,0","O,,O","Weicheneinbau WEB W 902,903+906+907 u.Errichtung Ol _Ju-Bk-21-Mos-001_Ä2 in Fürth-Untfarrnb Hp",null,"N","207691.04","2020-05-15T15:22:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20472458EFA5E.02","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,35,35,"2021-09-04T06:00:00","06:00:00","2021-09-04T23:00:00","23:00:00","17 h","continuous","Miscellaneous",null,"ST",null,null,null,",C,C","R,R,","","0,0,0","","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.6 in Bamberg",null,"N","207749.02","2020-05-08T06:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20301CF51953E.04","Gemünden - Bamberg - Nürnberg",">","Eltersdorf","Vach",2021,2021,35,35,"2021-09-04T21:00:00","21:00:00","2021-09-05T13:00:00","13:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Kreuzungsbauwerk km 15,627_Ju-Bk-21-Mos-002_Ä1",null,"N","20301CF51953E.04","2020-05-15T14:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20472458EFA5E.04","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,35,36,"2021-09-05T06:00:00","06:00:00","2021-09-06T23:00:00","23:00:00","1 d, 10 h","periodical","Miscellaneous",null,"ST",null,null,null,",,C","","","","","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.6 in Bamberg",null,"N","207749.04","2020-05-08T06:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2047277B8C65E.02","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,36,36,"2021-09-07T06:00:00","06:00:00","2021-09-10T23:00:00","23:00:00","2 d, 20 h","periodical","Miscellaneous",null,"ST",null,null,null,"","","","0,,","","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.6 in Bamberg",null,"N","207750.02","2019-08-14T09:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20474DCCC19FE.04","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Bamberg",2021,2021,36,36,"2021-09-08T23:00:00","23:00:00","2021-09-10T06:00:00","06:00:00","14 h","periodical","Miscellaneous","T",null,null,null,null,"C,C,C","R,,","","0,,","O,,","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.3 in Bamberg",null,"N","207753.04","2020-05-07T14:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFE4F5A2771E.01","Gemünden - Bamberg - Nürnberg","<","Vach","Erlangen Paul-Gossen-Straße",2021,2021,36,36,"2021-09-10T01:30:00","01:30:00","2021-09-11T21:00:00","21:00:00","1 d, 20 h","continuous","Switch",null,"LT",null,null,null,"C,C,C","R,R,",",B,","0,0,0","O,,O","Weicheneinbau W 28W417+418_Ju-Bk21-Mos-003-Ä1 in Eltersdorf",null,"N","207692.01","2020-05-18T09:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"20301CF51953E.01","Gemünden - Bamberg - Nürnberg","<","Vach","Eltersdorf",2021,2021,36,36,"2021-09-10T22:00:00","22:00:00","2021-09-11T14:00:00","14:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Kreuzungsbauwerk km 15,627_Ju-Bk-21-Mos-002_Ä1",null,"N","20301CF51953E.01","2020-05-15T14:57:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFE4F5A2771E.04","Gemünden - Bamberg - Nürnberg","< >","Vach","Erlangen",2021,2021,36,36,"2021-09-11T21:00:00","21:00:00","2021-09-12T06:00:00","06:00:00","9 h","continuous","Switch","T",null,null,null,null,",C,C","R,R,",",B,","0,0,","O,,","Weicheneinbau W 28W417+418_Ju-Bk21-Mos-003-Ä1 in Eltersdorf",null,"N","207692.04","2020-05-18T09:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFD172E3FC3E.01","Gemünden - Bamberg - Nürnberg","< >","Vach","Fürth (Bay) Hbf",2021,2021,36,36,"2021-09-11T21:00:00","21:00:00","2021-09-12T06:00:00","06:00:00","9 h","continuous","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Errichtung Ol über neuer Wv 904-905_Ju-Bk-21-Mos-001 in Fürth-Untfarrnb Hp",null,"N","1FFD172E3FC3E.01","2020-05-15T15:33:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFE53F08235E.01","Gemünden - Bamberg - Nürnberg","<","Vach","Eltersdorf",2021,2021,36,37,"2021-09-12T06:00:00","06:00:00","2021-09-14T05:00:00","05:00:00","1 d, 23 h","continuous","Switch",null,"LT",null,null,null,"C,C,C","R,R,",",B,","0,0,0","O,,O","Weicheneinbau W28W417+418_Ju-Bk21-Mos-003-Ä1 in Eltersdorf",null,"N","207693.01","2020-06-04T15:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2047522ED97BE.03","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Bamberg",2021,2021,37,37,"2021-09-13T21:00:00","21:00:00","2021-09-14T04:00:00","04:00:00","7 h","continuous","Miscellaneous","T",null,null,null,null,"C,,C","R,R,","","0,0,","","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.3 in Bamberg",null,"N","207754.03","2019-07-18T12:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2047277B8C65E.04","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,37,38,"2021-09-14T06:00:00","06:00:00","2021-09-23T23:00:00","23:00:00","7 d, 02 h","periodical","Miscellaneous",null,"ST",null,null,null,",,C","","","0,,0","","Bahnsteigarbeiten Herstellung Bstgverlängerung Gl.6 in Bamberg",null,"N","207750.04","2019-08-14T09:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704BA3018C.05","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,37,46,"2021-09-14T07:00:00","07:00:00","2021-11-18T18:00:00","18:00:00","65 d, 11 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS und WE Pressig - Ludwigstadt + Ol Erneuerung Bf NPR_ NFDF-NPR",null,"N","307351.05","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704BAAA2AC.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,37,46,"2021-09-14T07:00:00","07:00:00","2021-11-18T18:00:00","18:00:00","65 d, 11 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS und WE Pressig - Ludwigstadt + Ol Erneuerung Bf NPR_ NFDF-NPR",null,"N","307352.01","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704BAAA2AC.02","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bamberg",2021,2021,37,46,"2021-09-14T07:00:00","07:00:00","2021-11-18T18:00:00","18:00:00","65 d, 11 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,","","Gleiserneuerung mit BR und PSS und WE Pressig - Ludwigstadt + Ol Erneuerung Bf NPR_ NFDF-NPR",null,"N","307352.02","2019-05-24T07:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704CBA3DEC.01","Gemünden - Bamberg - Nürnberg",">","Breitengüßbach","Bamberg",2021,2021,40,48,"2021-10-05T22:00:00","22:00:00","2021-12-01T01:00:00","01:00:00","56 d, 03 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,C,C","R,R,","","0,0,0","O,,O","sonstige Arbeiten ABS/NBS Nürnberg - Ebensfeld - Erfurt, BA 23, hier: Aufbau neue Gleise Hallstadt(e) - Breitengüßbach",null,"N","307382.01","2019-07-17T20:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704F3CA30C.02","Gemünden - Bamberg - Nürnberg","< >","Breitengüßbach","Bamberg",2021,2021,48,49,"2021-12-01T01:00:00","01:00:00","2021-12-06T04:00:00","04:00:00","5 d, 03 h","continuous","Miscellaneous","T",null,null,null,null,"C,C,C","R,R,","","0,0,","","sonstige Arbeiten ABS/NBS Nürnberg - Ebensfeld - Erfurt, BA 23, hier: NHAL - NBG, Herstellung Anbindung Richtungsgleis NBG - NHAL (ABS)",null,"N","307450.02","2019-05-24T07:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"206B6576265FE.01","Gemünden - Bamberg - Nürnberg","<","Vach","Eltersdorf",2021,2021,48,48,"2021-12-03T22:00:00","22:00:00","2021-12-04T14:00:00","14:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Kreuzungsbauwerk km 15,627_Ju-Bk-21-Mos-002",null,"N","206B6576265FE.01","2019-08-12T07:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"206B6576265FE.04","Gemünden - Bamberg - Nürnberg",">","Eltersdorf","Vach",2021,2021,48,48,"2021-12-04T22:00:00","22:00:00","2021-12-05T14:00:00","14:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten Kreuzungsbauwerk km 15,627_Ju-Bk-21-Mos-002",null,"N","206B6576265FE.04","2019-08-12T07:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF704F5E34CC.02","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Unterleiterbach",2021,2021,48,49,"2021-12-05T21:00:00","21:00:00","2021-12-06T04:00:00","04:00:00","7 h","continuous","Signal","T",null,null,null,null,"","","","0,,","","Arbeiten an LST-Anlagen ABS/NBS Nürnberg - Ebensfeld - Erfurt, BA 23, hier: Inbetriebnahme Richtungsgleis NBG-NHAL ABS  (Dreigleisigkeit)",null,"N","307454.02","2019-05-24T07:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22978E394AFC8.01","Regensburg - Plzen","< >","Bodenwöhr Nord","Bodenwöhr Nord",2021,2021,12,19,"2021-03-23T07:00:00","07:00:00","2021-05-10T07:00:00","07:00:00","48 d","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,","","Bahnsteigarbeiten Erneuerung am Gl.4 in Bodenwöhr Nord",54,"Y","307633.01","2020-08-28T11:47:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFCF5375071E.02","Regensburg - Plzen","< >","Bodenwöhr Nord","Bodenwöhr Nord",2021,2021,19,27,"2021-05-11T07:00:00","07:00:00","2021-07-05T07:00:00","07:00:00","55 d","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,","","Bahnsteigarbeiten Erneuerung am Gl.2 in Bodenwöhr Nord",54,"Y","307634.02","2019-05-28T09:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFCF639DAF7E.03","Regensburg - Plzen","< >","Bodenwöhr Nord","Bodenwöhr Nord",2021,2021,27,29,"2021-07-05T07:00:00","07:00:00","2021-07-23T07:00:00","07:00:00","18 d","continuous","Miscellaneous",null,"ST",null,null,null,"C,,","","","","","Bahnsteigarbeiten Erneuerung am Gl.1 in Bodenwöhr Nord",54,"Y","307635.03","2020-04-29T08:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFCF8EE824DE.01","Regensburg - Plzen","< >","Bodenwöhr Nord","Bodenwöhr Nord",2021,2021,33,34,"2021-08-21","00:00:00","2021-08-27T23:59:00","23:59:00","7 d","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,0","","Bahnsteigarbeiten Einhub Brückenbauwerk PÜ u. Abbruch+Auffüllung PU in Bodenwöhr Nord",54,"N","307636.01","2020-03-30T10:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FFCFB5E1DDBE.02","Regensburg - Plzen","< >","Bodenwöhr Nord","Bodenwöhr Nord",2021,2021,38,43,"2021-09-21T07:00:00","07:00:00","2021-10-25T07:00:00","07:00:00","34 d","continuous","Miscellaneous",null,"ST",null,null,null,"","","","0,,","","Bahnsteigarbeiten Erneuerung am Gl.4 in Bodenwöhr Nord",54,"Y","307638.02","2020-03-30T11:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"2235FAADEB02A.05","Karlsruhe - Mannheim","< >","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2021,2021,5,6,"2021-02-05T22:00:00","22:00:00","2021-02-08T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,",,C","R,R,","","0,0,","O,,","sonstige Arbeiten ETCS KorA Ausrüstung ESG IH KAR VzG 4020 Nord Teil 1, SEV",null,"N","306011.05","2020-06-22T10:27:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"22A78881D8852.02","Strasbourg - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Dammerstock",2021,2021,13,14,"2021-04-04T23:00:00","23:00:00","2021-04-05T23:00:00","23:00:00","1 d","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme ETCS KorA: IBN ESTW Dammerstock / SEV",87,"N","206851.02","2020-09-08T11:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706B86754C.03","Strasbourg - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Dammerstock",2021,2021,26,35,"2021-07-02T23:00:00","23:00:00","2021-08-30T05:00:00","05:00:00","58 d, 06 h","continuous","Catenary",null,"LT",null,null,null,",,C","R,,","","0,,","O,,","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"N","306219.03","2019-08-01T12:07:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF706FCF90AC.03","Strasbourg - Karlsruhe","<","Karlsruhe-Dammerstock","Karlsruhe Gbf",2021,2021,35,45,"2021-08-30T23:00:00","23:00:00","2021-11-08T05:00:00","05:00:00","69 d, 06 h","continuous","Catenary",null,"LT",null,null,null,",,C","R,,","","0,,","O,,","Oberleitungsarbeiten KaBa PfA 1 Bashaide, SEV",87,"N","306320.03","2019-08-01T12:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"1FF7071E7260C.01","Strasbourg - Karlsruhe","<","Karlsruhe-Dammerstock","Karlsruhe Gbf",2021,2021,38,39,"2021-09-25T06:00:00","06:00:00","2021-09-27T04:00:00","04:00:00","1 d, 22 h","continuous","Switch",null,"LT",null,null,null,"","","","0,,","","Weichenerneuerung Karlsruhe Hbf WE // BBP-EINTRAG ENTFÄLLT",87,"N","306368.01","2019-05-24T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Published",null,"Y"]
[null,80,"21E444BBE78AC.04","Frankfurt - Aschaffenburg","< >","Nantenbach","Rohrbach",2022,2022,23,38,"2022-06-10T22:00:00","22:00:00","2022-09-24T19:00:00","19:00:00","105 d, 21 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307216.04","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444F167D4C.04","Frankfurt - Aschaffenburg","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-25T07:00:00","07:00:00","2022-10-08T19:00:00","19:00:00","7 d","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307336.04","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444FAD8D2C.04","Frankfurt - Aschaffenburg","< >","Nantenbach","Rohrbach",2022,2022,40,42,"2022-10-09T07:00:00","07:00:00","2022-10-17T04:00:00","04:00:00","7 d, 21 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307355.04","2020-06-08T10:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441A88D0AC.03","Mannheim - Darmstadt","< >","Darmstadt Hbf","Hemsbach",2022,2022,1,1,"2022-01-08T23:00:00","23:00:00","2022-01-09T05:00:00","05:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","305056.03","2020-04-27T06:40:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E446E1CB06C.02","Mannheim - Darmstadt","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,4,5,"2022-01-28T22:00:00","22:00:00","2022-01-31T05:30:00","05:30:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306107.02","2020-08-11T15:44:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441E34C1AC.01","Mannheim - Darmstadt","< >","Darmstadt-Eberstadt","Bickenbach (Bergstr)",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-03-28T05:00:00","05:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","305193.01","2020-06-08T11:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441E34C1AC.03","Mannheim - Darmstadt",">","Bickenbach Nord","Zwingenberg (Bergstr)",2022,2022,13,13,"2022-03-28T05:00:00","05:00:00","2022-04-02T05:00:00","05:00:00","5 d","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","305193.03","2020-06-08T11:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441E5960AC.01","Mannheim - Darmstadt","< >","Darmstadt-Eberstadt","Zwingenberg (Bergstr)",2022,2022,13,13,"2022-03-28T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","1 d","periodical","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","305199.01","2020-04-27T06:41:00","Unclassified","1,2,3",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447749044C.04","Mannheim - Darmstadt",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-10T05:30:00","05:30:00","8 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306384.04","2020-04-27T07:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447799E36C.01","Mannheim - Darmstadt","< >","Heidelberg-Wieblingen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-10T05:30:00","05:30:00","2 d, 20 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306394.01","2020-04-27T07:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441E9C842C.01","Mannheim - Darmstadt","<","Bensheim","Bensheim-Auerbach",2022,2022,14,15,"2022-04-06T06:00:00","06:00:00","2022-04-15T21:00:00","21:00:00","9 d, 15 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","305209.01","2020-06-15T13:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E441E9C842C.03","Mannheim - Darmstadt","< >","Zwingenberg (Bergstr)","Heppenheim Nord",2022,2022,14,15,"2022-04-06T22:00:00","22:00:00","2022-04-13T04:45:00","04:45:00","1 d, 23 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","305209.03","2020-06-15T13:06:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44ADCE3B2C.01","Mannheim - Darmstadt","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,33,36,"2022-08-15T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","7 d, 07 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306034.01","2020-07-15T10:25:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4427A2B26C.01","Mannheim - Darmstadt","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,38,"2022-09-10T14:00:00","14:00:00","2022-09-19T05:00:00","05:00:00","3 d, 06 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"Y","305540.01","2020-04-27T06:43:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44289CF0EC.01","Mannheim - Darmstadt","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,38,40,"2022-09-24T20:00:00","20:00:00","2022-10-03T09:00:00","09:00:00","3 d, 02 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"Y","305576.01","2020-04-27T06:43:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44294C6ACC.01","Mannheim - Darmstadt","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,40,47,"2022-10-08T14:00:00","14:00:00","2022-11-21T05:00:00","05:00:00","11 d, 09 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"Y","305599.01","2020-04-27T06:43:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A342F38C.01","Karlsruhe - Stuttgart",">","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2022,2022,21,23,"2022-05-27T21:00:00","21:00:00","2022-06-10T21:00:00","21:00:00","14 d","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306735.01","2020-06-14T16:22:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A342F38C.02","Karlsruhe - Stuttgart","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,21,23,"2022-05-27T23:00:00","23:00:00","2022-06-10T05:00:00","05:00:00","3 d, 12 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","306735.02","2020-06-14T16:22:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A38309CC.02","Karlsruhe - Stuttgart","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,21,22,"2022-05-28T23:00:00","23:00:00","2022-06-03T05:00:00","05:00:00","1 d, 12 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306742.02","2020-06-15T07:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447B0BD8AC.01","Stuttgart - München","< >","Eislingen (Fils)","Gingen (Fils) Süd",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306503.01","2020-06-13T23:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447A287D8C.03","Stuttgart - München","< >","Geislingen (Steige)","Amstetten (Württ)",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306475.03","2020-06-08T00:04:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447B02B0EC.01","Stuttgart - München","< >","Eislingen (Fils)","Göppingen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306770.01","2020-06-08T00:09:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447BD0AF4C.01","Stuttgart - München","< >","Eislingen (Fils)","Süßen",2022,2022,16,17,"2022-04-22T21:00:00","21:00:00","2022-04-25T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306527.01","2020-06-13T23:59:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A2E5DF6C.01","Stuttgart - München","< >","Beimerstetten","Neu-Ulm",2022,2022,21,22,"2022-05-26","00:00:00","2022-05-30T04:00:00","04:00:00","4 d, 04 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","306724.01","2020-04-27T07:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4470D9114C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,7,8,"2022-02-18T21:00:00","21:00:00","2022-02-25T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306185.01","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44424A6D6C.02","Stuttgart - München","< >","Westheim (Schwab)","Augsburg Hbf",2022,2022,20,24,"2022-05-17T21:00:00","21:00:00","2022-06-17T05:00:00","05:00:00","10 d, 08 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","307181.02","2020-05-06T10:56:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A1C0E76C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-03T21:00:00","21:00:00","14 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306688.01","2020-04-27T07:13:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44C1D09B4C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306544.01","2020-04-27T07:20:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B56AC74C.01","Karlsruhe - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2022,2022,12,13,"2022-03-25T22:00:00","22:00:00","2022-03-29T05:00:00","05:00:00","3 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306229.01","2020-06-08T11:24:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B6E09E6C.01","Karlsruhe - Mannheim","<","Schwetzingen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,13,13,"2022-03-29T05:00:00","05:00:00","2022-04-01T12:00:00","12:00:00","3 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306256.01","2020-06-08T11:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B73F392C.01","Karlsruhe - Mannheim","< >","Mannheim Ziehbrunnen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-06T06:00:00","06:00:00","1 d, 16 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","306300.01","2020-06-08T11:53:00","Unclassified","1,2,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44726D6CEC.01","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2022,2022,9,11,"2022-03-04T23:00:00","23:00:00","2022-03-17T05:59:00","05:59:00","12 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306235.01","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4476A7460C.01","Karlsruhe - Mannheim","<","Waghäusel","Hockenheim",2022,2022,12,14,"2022-03-25T23:00:00","23:00:00","2022-04-07T05:00:00","05:00:00","12 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306363.01","2020-04-27T07:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E446EADA5CC.03","Strasbourg - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,87,"N","306321.03","2020-04-27T07:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44724EE86C.01","Strasbourg - Karlsruhe","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306231.01","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44724EE86C.02","Strasbourg - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306231.02","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44724EE86C.05","Strasbourg - Karlsruhe","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,9,10,"2022-03-06T21:00:00","21:00:00","2022-03-07T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,87,"N","306231.05","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4472EC12CC.02","Strasbourg - Karlsruhe","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306251.02","2020-06-08T16:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4472EC12CC.03","Strasbourg - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306251.03","2020-06-08T16:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4472EC12CC.05","Strasbourg - Karlsruhe","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,13,13,"2022-03-30T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,87,"N","306251.05","2020-06-08T16:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447762F4EC.02","Strasbourg - Karlsruhe","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,13,14,"2022-03-31T05:00:00","05:00:00","2022-04-04T05:00:00","05:00:00","4 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306387.02","2020-06-08T16:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447762F4EC.03","Strasbourg - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2022,2022,13,14,"2022-03-31T05:00:00","05:00:00","2022-04-04T05:00:00","05:00:00","4 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306387.03","2020-06-08T16:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4478759D6C.02","Strasbourg - Karlsruhe",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,14,"2022-04-04T05:00:00","05:00:00","2022-04-06T21:00:00","21:00:00","2 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306422.02","2020-06-08T16:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4478759D6C.04","Strasbourg - Karlsruhe","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,14,"2022-04-06T21:00:00","21:00:00","2022-04-07T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,87,"N","306422.04","2020-06-08T16:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44794CC38C.01","Strasbourg - Karlsruhe",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,17,"2022-04-07T05:00:00","05:00:00","2022-04-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306447.01","2020-06-08T16:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44794CC38C.03","Strasbourg - Karlsruhe","< >","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,17,17,"2022-04-30T21:00:00","21:00:00","2022-05-01T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,87,"N","306447.03","2020-06-08T16:32:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447D88234C.01","Strasbourg - Karlsruhe",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,17,18,"2022-05-01T05:00:00","05:00:00","2022-05-04T23:59:00","23:59:00","3 d, 19 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,87,"Y","306577.01","2020-07-30","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E446CCE858C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:00:00","21:00:00","2022-01-21T05:00:00","05:00:00","2 d, 08 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306069.01","2020-04-27T07:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E446CD626AC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:00:00","21:00:00","2022-01-21T05:00:00","05:00:00","2 d, 08 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306070.01","2020-04-27T07:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447B1FAECC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306505.01","2020-05-26T08:42:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447B28D68C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306506.01","2020-05-26T10:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447B31FE4C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306507.01","2020-05-26T08:47:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B3C5A2CC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306347.01","2020-04-27T07:17:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B3CD43EC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","306342.01","2020-04-27T07:17:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B3D4E50C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","306188.01","2020-04-27T07:17:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44B4FB63AC.01","Karlsruhe - Stuttgart","<","Bietigheim-Bissingen","Sachsenheim",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-04-01T20:59:00","20:59:00","7 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306220.01","2020-06-04T14:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44A59A9F2C.02","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,23,24,"2022-06-10T21:00:00","21:00:00","2022-06-17T05:00:00","05:00:00","6 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","306802.02","2020-06-15T08:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440FC428C.01","Gemünden - Würzburg - Nürnberg","< >","Fürth (Bay) Gbf","Nürnberg Hbf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307143.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440FC428C.02","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Jansenbrücke","Nürnberg Jansenbrücke",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307143.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440FC428C.03","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307143.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440FC428C.05","Gemünden - Würzburg - Nürnberg","< >","Fürth (Bay) Hbf","Mainbernheim",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307143.05","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C2F62EC.01","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,26,26,"2022-06-29","00:00:00","2022-07-02T05:00:00","05:00:00","3 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307234.01","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C2F62EC.03","Nürnberg - Plzen","<","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,26,28,"2022-07-02T05:00:00","05:00:00","2022-07-17","00:00:00","14 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,54,"Y","307234.03","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C7EBB6C.01","Nürnberg - Plzen","< >","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,28,30,"2022-07-17","00:00:00","2022-07-28T05:00:00","05:00:00","11 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307246.01","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CAE08CC.03","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2022,2022,29,30,"2022-07-22T23:00:00","23:00:00","2022-07-25T11:00:00","11:00:00","2 d, 12 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,54,"N","307253.03","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C7EBB6C.02","Nürnberg - Plzen","<","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,30,31,"2022-07-28T05:00:00","05:00:00","2022-08-06T05:00:00","05:00:00","9 d","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,54,"Y","307246.02","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D0E2A2C.04","Nürnberg - Plzen","< >","Neuhaus (Pegnitz)","Pegnitz",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T06:00:00","06:00:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"Y","307266.04","2020-06-12T14:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D15CB4C.04","Nürnberg - Plzen","< >","Pegnitz","Neuhaus (Pegnitz)",2022,2022,31,37,"2022-08-01T06:00:00","06:00:00","2022-09-12T05:00:00","05:00:00","41 d, 23 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"Y","307267.04","2020-06-12T15:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C7EBB6C.04","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,31,32,"2022-08-06T05:00:00","05:00:00","2022-08-08T05:00:00","05:00:00","2 d","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307246.04","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D72DF6C.03","Nürnberg - Plzen",">","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,32,34,"2022-08-08T05:00:00","05:00:00","2022-08-23","00:00:00","14 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,54,"Y","307280.03","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D72DF6C.04","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,34,35,"2022-08-23","00:00:00","2022-09-02T05:00:00","05:00:00","10 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307280.04","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E1AB82C.02","Nürnberg - Plzen",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,35,37,"2022-08-29T06:00:00","06:00:00","2022-09-12T05:00:00","05:00:00","13 d, 23 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,54,"Y","307302.02","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E4E996C.02","Nürnberg - Plzen",">","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,35,36,"2022-09-02T05:00:00","05:00:00","2022-09-08","00:00:00","5 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,54,"Y","307310.02","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E4E996C.03","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,36,37,"2022-09-08","00:00:00","2022-09-12T05:00:00","05:00:00","4 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307310.03","2020-04-27T06:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4450DEBA2C.04","Nürnberg - Plzen","< >","Schnabelwaid","Pegnitz",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307393.04","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44501FFE0C.02","Nürnberg - Plzen","< >","Marktredwitz","Schirnding Grenze",2022,2022,42,46,"2022-10-21T22:35:00","22:35:00","2022-11-16T04:20:00","04:20:00","25 d, 06 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,54,"N","307370.02","2020-06-15T14:42:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4450CF77EC.02","Nürnberg - Plzen","< >","Schnabelwaid","Kirchenlaibach",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,54,"N","307391.02","2020-06-15T13:25:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F9119CC.01","Stuttgart - München",">","München-Pasing","München Hbf",2022,2022,11,12,"2022-03-18T23:00:00","23:00:00","2022-03-21T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307089.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443FC3746C.01","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,12,13,"2022-03-25T23:00:00","23:00:00","2022-03-28T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307097.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44400CB26C.02","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,13,14,"2022-04-01T23:00:00","23:00:00","2022-04-04T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307109.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44407F234C.02","Stuttgart - München","<","München Hbf","München-Pasing",2022,2022,14,15,"2022-04-08T23:00:00","23:00:00","2022-04-11T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307127.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BD0C82C.03","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,23,33,"2022-06-11T23:00:00","23:00:00","2022-08-15T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307219.03","2020-04-27T06:52:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BE9322C.02","Stuttgart - München","< >","München-Pasing","München Hbf",2022,2022,24,33,"2022-06-13T23:00:00","23:00:00","2022-08-18T05:00:00","05:00:00","7 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307223.02","2020-04-27T06:52:00","Unclassified","1,2,3",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444012CCEC.01","München - Rosenheim - Salzburg ","< >","München Ost Pbf","München Süd",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T06:00:00","06:00:00","1 d","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,81,"N","307110.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440ACEA0C.01","München - Rosenheim - Salzburg ","<","München Ost Pbf","München Süd",2022,2022,14,15,"2022-04-09T05:00:00","05:00:00","2022-04-11T05:00:00","05:00:00","2 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,81,"N","307133.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44426150CC.02","München - Rosenheim - Salzburg ","<","München Ost Pbf","München Süd",2022,2022,20,24,"2022-05-20T22:00:00","22:00:00","2022-06-16T04:00:00","04:00:00","26 d, 06 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,81,"Y","307184.02","2020-06-15T08:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444B6D998C.03","München - Rosenheim - Salzburg ",">","Rückstetten","Teisendorf",2022,2022,20,21,"2022-05-20T23:30:00","23:30:00","2022-05-28T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,81,"Y","307206.03","2020-06-09T08:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444B753AAC.05","München - Rosenheim - Salzburg ","<","Teisendorf","Rückstetten",2022,2022,21,24,"2022-05-27T23:30:00","23:30:00","2022-06-16T05:30:00","05:30:00","19 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,81,"Y","307207.05","2020-06-09T08:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44426150CC.04","München - Rosenheim - Salzburg ",">","München Süd","München Ost Pbf",2022,2022,24,28,"2022-06-15T23:00:00","23:00:00","2022-07-14T04:00:00","04:00:00","28 d, 05 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,81,"Y","307184.04","2020-06-15T08:58:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4450F7242C.01","München - Rosenheim - Salzburg ","< >","München Ost Pbf","München Süd",2022,2022,43,44,"2022-10-29T10:00:00","10:00:00","2022-11-03T20:00:00","20:00:00","5 d, 10 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,81,"N","307396.01","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F1707CC.03","Nürnberg - Regensburg",">","Deining Üst","Seubersdorf",2022,2022,10,13,"2022-03-11T22:00:00","22:00:00","2022-03-28T05:00:00","05:00:00","16 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307070.03","2020-06-06T17:00:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444020888C.02","Nürnberg - Regensburg",">","Beratzhausen","Undorf",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T05:00:00","05:00:00","2 d, 07 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307112.02","2020-06-04T16:34:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440B48B2C.01","Nürnberg - Regensburg","< >","Undorf","Parsberg",2022,2022,14,14,"2022-04-09T01:00:00","01:00:00","2022-04-10T16:00:00","16:00:00","1 d, 15 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","307134.01","2020-06-06T16:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444032D80C.02","Regensburg - Wels","<","Radldorf (Niederbay)","Mangolding",2022,2022,14,15,"2022-04-10","00:00:00","2022-04-11T04:00:00","04:00:00","1 d, 04 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,81,"N","307115.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440B48B2C.02","Nürnberg - Regensburg","<","Undorf","Parsberg",2022,2022,14,15,"2022-04-10T16:00:00","16:00:00","2022-04-11T12:00:00","12:00:00","20 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307134.02","2020-06-06T16:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444117B9CC.01","Nürnberg - Regensburg","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307146.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44411F5AEC.02","Nürnberg - Regensburg","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307147.02","2020-06-06T16:30:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4441DB09CC.01","Nürnberg - Regensburg",">","Undorf","Regensburg Bbf",2022,2022,18,19,"2022-05-02T22:00:00","22:00:00","2022-05-12T22:00:00","22:00:00","10 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307167.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44421CA6AC.01","Regensburg - Wels","< >","Mangolding","Radldorf (Niederbay)",2022,2022,19,20,"2022-05-13T13:00:00","13:00:00","2022-05-16T05:00:00","05:00:00","2 d, 16 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,81,"N","307176.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44421CA6AC.02","Regensburg - Wels","< >","Mangolding","Radldorf (Niederbay)",2022,2022,20,20,"2022-05-16T22:00:00","22:00:00","2022-05-19T05:00:00","05:00:00","21 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,81,"N","307176.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F10ED4C.01","Regensburg - München",">","München-Moosach","München-Neulustheim",2022,2022,9,10,"2022-03-05T07:00:00","07:00:00","2022-03-13T22:00:00","22:00:00","2 d, 12 h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307069.01","2020-04-27T06:49:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44412E9D2C.01","Regensburg - München","<","München-Neulustheim","München-Moosach",2022,2022,15,16,"2022-04-15T02:40:00","02:40:00","2022-04-18T22:40:00","22:40:00","3 d, 20 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307149.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44417961CC.03","Regensburg - München","< >","München Hbf","München Kanal",2022,2022,16,17,"2022-04-22T23:00:00","23:00:00","2022-04-25T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307154.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4441B66ACC.01","Regensburg - München","< >","München Kanal","München Hbf",2022,2022,17,18,"2022-04-29T23:00:00","23:00:00","2022-05-02T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307161.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4441E1244C.01","Regensburg - München","<","München Hbf","München-Moosach",2022,2022,18,19,"2022-05-06T23:00:00","23:00:00","2022-05-09T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307168.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444268F1EC.01","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,20,21,"2022-05-20T22:00:00","22:00:00","2022-05-23T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307185.01","2020-05-26T14:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444268F1EC.05","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,21,21,"2022-05-27T22:00:00","22:00:00","2022-05-29T14:00:00","14:00:00","1 d, 16 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307185.05","2020-05-26T14:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444B5E574C.01","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,22,23,"2022-06-03T23:00:00","23:00:00","2022-06-07T05:00:00","05:00:00","3 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307205.01","2020-05-26T16:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444B5E574C.03","Regensburg - München","< >","Landshut (Bay) Hbf","Moosburg",2022,2022,22,22,"2022-06-04T03:00:00","03:00:00","2022-06-04T17:00:00","17:00:00","14 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307205.03","2020-05-26T16:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BA60EAC.03","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,23,24,"2022-06-10T23:00:00","23:00:00","2022-06-13T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307213.03","2020-05-26T16:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BD0C82C.01","Regensburg - München","< >","München Kanal","München Hbf",2022,2022,23,33,"2022-06-11T23:00:00","23:00:00","2022-08-15T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307219.01","2020-04-27T06:52:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BA60EAC.05","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-15T23:00:00","23:00:00","2022-06-19T05:00:00","05:00:00","3 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307213.05","2020-05-26T16:39:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BEF4CAC.01","Regensburg - München","< >","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-16T03:00:00","03:00:00","2022-06-16T17:00:00","17:00:00","14 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307224.01","2020-05-26T16:41:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BF5672C.01","Regensburg - München","< >","München-Neulustheim","München Hbf",2022,2022,24,33,"2022-06-16T23:00:00","23:00:00","2022-08-20T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307225.01","2020-04-27T06:52:00","Unclassified","4,5",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444BFD084C.04","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-19T05:00:00","05:00:00","2022-06-19T22:00:00","22:00:00","17 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307226.04","2020-05-26T16:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C46464C.04","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,26,27,"2022-07-01T22:00:00","22:00:00","2022-07-04T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307237.04","2020-05-26T17:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C5A1C6C.03","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,27,27,"2022-07-08T22:00:00","22:00:00","2022-07-10T05:00:00","05:00:00","1 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307240.03","2020-05-26T17:15:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CB5A9EC.01","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,28,29,"2022-07-15T22:00:00","22:00:00","2022-07-18T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307254.01","2020-05-26T17:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CB5A9EC.03","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,29,30,"2022-07-23T22:00:00","22:00:00","2022-07-25T05:00:00","05:00:00","1 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307254.03","2020-05-26T17:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D080FAC.01","Regensburg - München",">","Moosburg","Langenbach (Oberbay)",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307265.01","2020-05-27T16:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D01F52C.01","Regensburg - München","< >","Moosburg","Landshut (Bay) Hbf",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307264.01","2020-05-26T17:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D469F4C.01","Regensburg - München","< >","Freising","Landshut (Bay) Hbf",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307274.01","2020-05-28T14:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D375D0C.03","Regensburg - München","< >","Landshut (Bay) Hbf","Freising",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T10:00:00","10:00:00","12 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307272.03","2020-05-26T17:42:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444DE5504C.01","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307294.01","2020-05-26T13:12:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E0A79CC.03","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,2,2,"2022-01-16T00:45:00","00:45:00","2022-01-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307028.03","2020-06-06T17:31:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E1E4FEC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,3,5,"2022-01-22T12:00:00","12:00:00","2022-01-31T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307031.02","2020-04-27T06:48:00","Unclassified","1,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E246A6C.02","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,4,4,"2022-01-24T15:00:00","15:00:00","2022-01-25T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307032.02","2020-04-27T06:48:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E39C72C.02","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,5,5,"2022-01-31T15:00:00","15:00:00","2022-02-01T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307035.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E584BAC.02","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2022,2022,5,6,"2022-02-05T12:00:00","12:00:00","2022-02-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307040.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E584BAC.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,6,6,"2022-02-07T15:00:00","15:00:00","2022-02-08T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307040.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E678DEC.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,6,7,"2022-02-12T12:00:00","12:00:00","2022-02-14T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307042.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E678DEC.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,7,7,"2022-02-14T15:00:00","15:00:00","2022-02-15T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307042.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E87990C.02","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307047.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E87990C.03","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307047.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EA0030C.01","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307051.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EA0030C.03","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307051.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EB86D0C.02","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307055.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EB86D0C.03","Stuttgart - München","< >","München-Johanneskirchen","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307055.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EB86D0C.04","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-02-28T15:00:00","15:00:00","2022-03-08T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","307055.04","2020-04-27T06:49:00","Unclassified",1,1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F04B84C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-03-05T12:00:00","12:00:00","2022-03-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307067.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F4DF64C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,10,13,"2022-03-12T12:00:00","12:00:00","2022-03-28T15:00:00","15:00:00","6 d, 09 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307079.02","2020-04-27T06:49:00","Unclassified","1,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443F4DF64C.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,11,12,"2022-03-14T15:00:00","15:00:00","2022-03-22T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307079.03","2020-04-27T06:49:00","Unclassified",1,1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443FD5C3EC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Freimann",2022,2022,12,12,"2022-03-27T12:00:00","12:00:00","2022-03-27T21:00:00","21:00:00","9 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"Y","307100.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443FD5C3EC.03","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,13,13,"2022-03-28T15:00:00","15:00:00","2022-03-29T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307100.03","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C9EC68C.01","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-21T06:00:00","06:00:00","2022-07-22T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307251.01","2020-06-07T13:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444C9EC68C.03","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-23T06:00:00","06:00:00","2022-07-23T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307251.03","2020-06-07T13:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CCF9A8C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,29,29,"2022-07-24T06:00:00","06:00:00","2022-07-24T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307258.03","2020-06-07T13:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CCF9A8C.04","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,30,30,"2022-07-25T06:00:00","06:00:00","2022-07-28T22:00:00","22:00:00","3 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307258.04","2020-06-07T13:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444CE98B2C.04","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,30,30,"2022-07-30T06:00:00","06:00:00","2022-07-30T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307261.04","2020-06-07T13:11:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D2386EC.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,30,31,"2022-07-31T06:00:00","06:00:00","2022-08-07T22:00:00","22:00:00","2 d","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307269.03","2020-06-07T13:16:00","Unclassified","6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444D5D82AC.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,32,32,"2022-08-08T06:00:00","06:00:00","2022-08-08T14:00:00","14:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307277.03","2020-06-07T13:20:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444DECF16C.03","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,33,33,"2022-08-19T06:00:00","06:00:00","2022-08-21T22:00:00","22:00:00","2 d","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307295.03","2020-06-07T13:25:00","Unclassified","5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E487EEC.03","Stuttgart - München","< >","München-Daglfing","München-Freimann",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-05T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307309.03","2020-06-07T13:50:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E7DE6CC.03","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,36,37,"2022-09-09T22:00:00","22:00:00","2022-09-12T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307316.03","2020-06-07T13:45:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444E9F788C.05","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,37,37,"2022-09-16T22:00:00","22:00:00","2022-09-17T04:00:00","04:00:00","6 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307321.05","2020-06-07T13:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444F4A5E8C.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,39,39,"2022-10-02T00:45:00","00:45:00","2022-10-02T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307342.02","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444F4A5E8C.05","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,39,39,"2022-10-02T06:00:00","06:00:00","2022-10-02T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307342.05","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E445038680C.01","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,40,41,"2022-10-09T14:00:00","14:00:00","2022-10-11T04:00:00","04:00:00","1 d, 14 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307373.01","2020-06-29T15:05:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44502925CC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,41,41,"2022-10-16T00:45:00","00:45:00","2022-10-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307371.02","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E445030C6EC.01","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,41,41,"2022-10-16T06:00:00","06:00:00","2022-10-16T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307372.01","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44510C80EC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,44,45,"2022-11-06T00:45:00","00:45:00","2022-11-09T15:00:00","15:00:00","3 d, 14 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307399.02","2020-06-06T18:55:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E445104DFCC.01","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,44,44,"2022-11-06T06:00:00","06:00:00","2022-11-06T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","307398.01","2020-06-06T18:56:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4450D7190C.02","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,45,45,"2022-11-07T04:00:00","04:00:00","2022-11-07T20:00:00","20:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307392.02","2020-06-07T14:19:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4451ACB88C.05","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,45,45,"2022-11-08T21:00:00","21:00:00","2022-11-11T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307417.05","2020-06-07T16:29:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44518692EC.01","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,46,46,"2022-11-14T04:00:00","04:00:00","2022-11-15T20:00:00","20:00:00","1 d, 16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307413.01","2020-06-07T16:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44518692EC.02","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-16T21:00:00","21:00:00","2022-11-17T04:00:00","04:00:00","7 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307413.02","2020-06-07T16:18:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4451B8ED8C.05","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,46,46,"2022-11-17T04:00:00","04:00:00","2022-11-18T13:00:00","13:00:00","1 d, 09 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307419.05","2020-06-07T16:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4451B8ED8C.03","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-18T21:00:00","21:00:00","2022-11-20T03:00:00","03:00:00","1 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307419.03","2020-06-07T16:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44522B5E6C.02","Stuttgart - München",">","München-Freimann","München-Daglfing",2022,2022,46,47,"2022-11-20T03:00:00","03:00:00","2022-11-21T19:00:00","19:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307431.02","2020-06-07T15:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44522B5E6C.03","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,47,47,"2022-11-21T21:00:00","21:00:00","2022-11-23T13:00:00","13:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307431.03","2020-06-07T15:51:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44525C326C.02","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,47,47,"2022-11-25T21:00:00","21:00:00","2022-11-27T03:00:00","03:00:00","1 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307437.02","2020-06-08T15:02:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E445263D38C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,47,48,"2022-11-27T03:00:00","03:00:00","2022-11-28T21:00:00","21:00:00","1 d, 18 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307438.03","2020-06-08T15:09:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E445270088C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,48,49,"2022-12-02T21:00:00","21:00:00","2022-12-05T19:00:00","19:00:00","2 d, 22 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307440.03","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4452962E2C.03","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,49,49,"2022-12-09T21:00:00","21:00:00","2022-12-10T23:59:00","23:59:00","1 d, 03 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","307445.03","2020-04-27T06:53:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443DE5DACC.02","Gemünden - Bamberg - Nürnberg",">","Hirschaid","Forchheim (Oberfr)",2022,2022,1,5,"2022-01-07T21:00:00","21:00:00","2022-02-04T21:00:00","21:00:00","28 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307025.02","2020-06-10T19:14:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E4C16AC.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Forchheim (Oberfr)",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307038.01","2020-05-25T13:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E4C16AC.02","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307038.02","2020-05-25T13:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443E6DA86C.01","Gemünden - Bamberg - Nürnberg","< >","Breitengüßbach","Bamberg",2022,2022,7,8,"2022-02-18T21:00:00","21:00:00","2022-02-21T21:00:00","21:00:00","3 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","307043.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E443EAC380C.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach",2022,2022,8,9,"2022-02-25T21:00:00","21:00:00","2022-03-01T09:00:00","09:00:00","3 d, 12 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","307053.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444086C46C.01","Gemünden - Bamberg - Nürnberg","< >","Vach","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","307128.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44408E658C.01","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Vach",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307129.01","2020-07-23T12:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44408E658C.03","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307129.03","2020-07-23T12:10:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44409DA7CC.01","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307131.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44409DA7CC.02","Gemünden - Bamberg - Nürnberg","< >","Hirschaid","Erlangen",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307131.02","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440A548EC.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bad Staffelstein",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307132.01","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444109FE2C.01","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Forchheim (Oberfr)",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307144.01","2020-07-31T10:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444109FE2C.02","Gemünden - Bamberg - Nürnberg","< >","Vach","Bamberg",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307144.02","2020-07-31T10:52:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4440FC428C.04","Gemünden - Bamberg - Nürnberg","< >","Vach","Strullendorf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","307143.04","2020-04-27T06:49:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444259AFAC.01","Gemünden - Bamberg - Nürnberg",">","Bamberg","Strullendorf",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-02T05:00:00","05:00:00","12 d, 08 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307183.01","2020-06-10T18:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E444259AFAC.02","Gemünden - Bamberg - Nürnberg",">","Hirschaid","Forchheim (Oberfr)",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-02T05:00:00","05:00:00","12 d, 08 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","307183.02","2020-06-10T18:46:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E44724EE86C.04","Karlsruhe - Mannheim","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","306231.04","2020-04-27T07:01:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E4472EC12CC.04","Karlsruhe - Mannheim","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","306251.04","2020-06-08T16:23:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,80,"21E447762F4EC.05","Karlsruhe - Mannheim","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,13,14,"2022-03-31T05:00:00","05:00:00","2022-04-04T05:00:00","05:00:00","4 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","306387.05","2020-06-08T16:26:00","Unclassified","1,2,3,4,5,6,7",1,null,null,null,null,"Planned",null,"Y"]
[null,54,"V-020500/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Choceň",2021,2021,43,43,"2021-10-25T18:00:00",null,"2021-10-30T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025294/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Choceň",2021,2021,44,45,"2021-11-01T18:00:00",null,"2021-11-09T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019440/20","Choceň - Hranice na Moravě","< >","Bezpráví","Brandýs nad Orlicí",2021,2021,41,43,"2021-10-16T18:00:00",null,"2021-10-30T06:00:00",null,"12 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025284/20","Choceň - Hranice na Moravě","< >","Bezpráví","Brandýs nad Orlicí",2021,2021,44,45,"2021-11-01T18:00:00",null,"2021-11-09T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022000/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,23,23,"2021-06-10T18:00:00",null,"2021-06-12T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022002/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,36,36,"2021-09-10T18:00:00",null,"2021-09-12T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025712/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,53,21,"2021-01-01",null,"2021-05-26T23:59:59",null,"146 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019302/20","Plzen - Praha","< >","Praha-Krč","Tunel odb.",2021,2021,32,32,"2021-08-10",null,"2021-08-12T23:59:59",null,"3 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019308/20","Plzen - Praha","< >","Praha-Krč","Tunel odb.",2021,2021,34,35,"2021-08-24",null,"2021-09-04T23:59:59",null,"7 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019413/20","Plzen - Praha","< >","Praha-Krč","Tunel odb.",2021,2021,48,48,"2021-11-29",null,"2021-12-01T23:59:59",null,"3 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019416/20","Plzen - Praha","< >","Praha-Krč","Tunel odb.",2021,2021,49,49,"2021-12-06",null,"2021-12-08T23:59:59",null,"3 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025499/20","Plzen - Praha","< >","Praha-Krč","Tunel odb.",2021,2021,50,50,"2021-12-13",null,"2021-12-16T23:59:59",null,"4 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019521/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","Předměřice nad Labem",2021,2021,25,25,"2021-06-21",null,"2021-06-21T23:59:59",null,"1 x 8 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. PZS v km 24,864. .","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019505/20","Choceň - Hranice na Moravě","< >","Les odb.","Třebovice v Čechách",2021,2021,9,10,"2021-03-01",null,"2021-03-12T23:59:59",null,"12 days","continuous","Track & Rail","T","LT","","","","","","","","","200. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019491/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Bezpráví",2021,2021,41,48,"2021-10-16",null,"2021-12-04T23:59:59",null,"50 days","continuous","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019460/20","Choceň - Hranice na Moravě","< >","Choceň","Brandýs nad Orlicí",2021,2021,41,43,"2021-10-16T18:00:00",null,"2021-10-25T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019443/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","",2021,2021,25,27,"2021-06-21T18:00:00",null,"2021-07-05T06:00:00",null,"12 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2,4 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019451/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","",2021,2021,27,30,"2021-07-06T18:00:00",null,"2021-07-28T06:00:00",null,"18 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2,4 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025250/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","",2021,2021,32,33,"2021-08-09T18:00:00",null,"2021-08-16T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2,4 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021991/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,2,3,"2021-01-17",null,"2021-01-20T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021991/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,2,3,"2021-01-17",null,"2021-01-20T23:59:59",null,"4 x 10 hours","periodical","Catenary","","ST","","","","","","B","","","4,6,6a jen TV, 2,2a + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019437/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2021,18,18,"2021-05-04T18:00:00",null,"2021-05-08T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025257/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2021,18,19,"2021-05-09T18:00:00",null,"2021-05-15T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025258/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2021,19,21,"2021-05-13T18:00:00",null,"2021-05-27T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025267/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2021,20,22,"2021-05-23T18:00:00",null,"2021-05-31T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019135/20","Plzen - Praha","< >","Praha-Radotín","Odb Barrandov",2021,2021,12,15,"2021-03-23T18:00:00",null,"2021-04-13T06:00:00",null,"15 x 4 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021986/20","Praha - Choceň","< >","Kostěnice","Pardubice hlavní nádraží",2021,2021,13,17,"2021-04-01",null,"2021-04-30T23:59:59",null,"30 days","continuous","Signal","","LT","","","","","","B","","","zab. zař. TZZ .","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021986/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,13,17,"2021-04-01",null,"2021-04-30T23:59:59",null,"30 days","continuous","Signal","","ST","","","","","","B","","","zab. zař. SZZ celá.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021986/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,13,17,"2021-04-01",null,"2021-04-30T23:59:59",null,"30 days","continuous","Signal","","LT","","","","","","B","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021986/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2021,2021,13,17,"2021-04-01",null,"2021-04-30T23:59:59",null,"30 days","continuous","Signal","","LT","","","","","","B","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021770/18","Praha - Choceň","< >","Praha-Libeň","Praha-Vysočany",2021,2021,45,45,"2021-11-13",null,"2021-11-14T23:59:59",null,"2 days","continuous","Miscellaneous","","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021220/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Hostivař",2021,2021,11,20,"2021-03-15T18:00:00",null,"2021-05-19T06:00:00",null,"13 x 4 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019439/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Ústí nad Orlicí",2021,2021,18,20,"2021-05-04",null,"2021-05-20T23:59:59",null,"17 days","continuous","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019436/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Ústí nad Orlicí",2021,2021,20,39,"2021-05-21",null,"2021-09-27T23:59:59",null,"130 days","continuous","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019435/20","Choceň - Hranice na Moravě","< >","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2021,39,41,"2021-09-28",null,"2021-10-15T23:59:59",null,"18 days","continuous","Catenary","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019423/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Ústí nad Orlicí",2021,2021,39,40,"2021-09-28T18:00:00",null,"2021-10-07T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019433/20","Choceň - Hranice na Moravě","< >","Brandýs nad Orlicí","Ústí nad Orlicí",2021,2021,39,40,"2021-10-03T18:00:00",null,"2021-10-04T06:00:00",null,"1 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019092/20","Plzen - Praha","< >","Odb Barrandov","Praha-Radotín",2021,2021,2,3,"2021-01-11",null,"2021-01-24T23:59:59",null,"3 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019095/20","Plzen - Praha","< >","Odb Barrandov","Praha-Radotín",2021,2021,3,3,"2021-01-21",null,"2021-01-22T23:59:59",null,"2 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019096/20","Plzen - Praha","< >","Odb Barrandov","Praha-Radotín",2021,2021,5,5,"2021-02-01",null,"2021-02-03T23:59:59",null,"3 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022308/20","Plzen - Praha","< >","Odb Barrandov","Praha-Radotín",2021,2021,9,9,"2021-03-03",null,"2021-03-04T23:59:59",null,"2 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025341/20","Ostr. - Dětmarovice - Č. Těšín","< >","Dětmarovice","Petrovice u Karviné",2021,2021,5,5,"2021-02-01",null,"2021-02-05T23:59:59",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025346/20","Ostr. - Dětmarovice - Č. Těšín","< >","Dětmarovice","Petrovice u Karviné",2021,2021,8,8,"2021-02-22",null,"2021-02-26T23:59:59",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021222/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","",2021,2021,30,31,"2021-07-31",null,"2021-08-03T23:59:59",null,"4 days","continuous","Switch","","ST","","","D","","","","","","4a,6,8,12a,14a,16a,18a jen TV, 10a + TV, výh.: 16. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017965/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,40,40,"2021-10-06",null,"2021-10-08T23:59:59",null,"3 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2/2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021216/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","",2021,2021,13,14,"2021-04-02",null,"2021-04-05T23:59:59",null,"4 days","continuous","Switch","","ST","","","D","","","B","","","10a bez TV, 2,1,3a,3b,5,7,13c jen TV, výh.: 19ab. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021213/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","",2021,2021,13,14,"2021-04-02",null,"2021-04-05T23:59:59",null,"4 days","continuous","Switch","","ST","","","D","","","B","","","10c,19c bez TV, 2,1,3a,3b,5,7,13c jen TV, výh.: 4ab,5ab. \nzáhlaví a zhlaví směr Opatovice-Pohřebačka a směr odb. Plačice.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021213/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Krč",2021,2021,15,16,"2021-04-12",null,"2021-04-22T23:59:59",null,"11 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021209/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Krč",2021,2021,33,34,"2021-08-22",null,"2021-08-24T23:59:59",null,"3 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021209/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Vršovice",2021,2021,33,34,"2021-08-22",null,"2021-08-24T23:59:59",null,"3 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021208/18","Plzen - Praha","< >","Praha-Hostivař","Praha-Zahradní Město",2021,2021,36,37,"2021-09-12",null,"2021-09-14T23:59:59",null,"3 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021208/18","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,36,37,"2021-09-12",null,"2021-09-14T23:59:59",null,"3 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021201/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Malešice",2021,2021,15,40,"2021-04-12",null,"2021-10-04T23:59:59",null,"176 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-021198/18","Plzen - Praha","< >","Praha-Hostivař","Praha-Zahradní Město",2021,2021,53,34,"2021-01-01",null,"2021-08-24T23:59:59",null,"236 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025211/19","Praha - Choceň","< >","Záboří nad Labem","Kolín",2021,2021,37,37,"2021-09-18",null,"2021-09-19T23:59:59",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ 1.+2.TK, SZZ, DOZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025209/19","Praha - Choceň","< >","Přelouč","Řečany nad Labem",2021,2021,36,36,"2021-09-11",null,"2021-09-12T23:59:59",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ 1. + 2.TK + úvazky ve stanicích a na CDP Praha - etapizace.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-025099/19","Hranice na Moravě - Ostrava","< >","Ostrava hlavní nádraží","",2021,2021,22,23,"2021-06-01",null,"2021-06-10T23:59:59",null,"10 days","continuous","Switch","","ST","","","D","","","","","","403-411,11a,822-825 jen TV, výh.: 405,406,407,408,412. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020971/20","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,41,41,"2021-10-16",null,"2021-10-17T23:59:59",null,"2 days","continuous","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024105/18","Nürnberg - Plzen","< >","Tachov","Planá u Mariánských Lázní",2021,2021,37,37,"2021-09-13",null,"2021-09-17T23:59:59",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024104/18","Nürnberg - Plzen","< >","Svojšín","Bor",2021,2021,42,43,"2021-10-19",null,"2021-10-27T23:59:59",null,"9 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024103/18","Nürnberg - Plzen","< >","Svojšín","Bor",2021,2021,18,19,"2021-05-03",null,"2021-05-14T23:59:59",null,"12 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024096/18","Nürnberg - Plzen","< >","Planá u Mariánských Lázní","Chodová Planá",2021,2021,17,17,"2021-04-26",null,"2021-04-30T23:59:59",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024095/18","Regensburg - Plzen","< >","Nýřany","Heřmanova Huť",2021,2021,31,35,"2021-08-03",null,"2021-08-30T23:59:59",null,"28 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024093/18","Nürnberg - Plzen","< >","Pňovany","Cebiv",2021,2021,37,39,"2021-09-14",null,"2021-09-27T23:59:59",null,"14 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024090/18","Regensburg - Plzen","< >","Staňkov","Blížejov",2021,2021,20,22,"2021-05-20",null,"2021-06-03T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024090/18","Regensburg - Plzen","< >","Blížejov","",2021,2021,20,22,"2021-05-20",null,"2021-06-03T23:59:59",null,"15 days","continuous","Track & Rail","","ST","","","","","","B","","","celá bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024090/18","Regensburg - Plzen","< >","Blížejov","Domažlice",2021,2021,20,22,"2021-05-20",null,"2021-06-03T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-024053/18","Plzen - Praha","< >","Praha-Zahradní Město","Praha-Vršovice",2021,2021,29,38,"2021-07-25",null,"2021-09-20T23:59:59",null,"58 days","continuous","Miscellaneous","","LT","","","","","","","","","101. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023772/18","Choceň - Hranice na Moravě","< >","Blatec","Olomouc hlavní nádraží",2021,2021,30,32,"2021-07-31",null,"2021-08-11T23:59:59",null,"12 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023770/18","Choceň - Hranice na Moravě","< >","Přerov","Věžky",2021,2021,17,17,"2021-04-26",null,"2021-04-30T23:59:59",null,"5 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023768/18","Choceň - Hranice na Moravě","< >","Olomouc hlavní nádraží","Olomouc-Nová Ulice",2021,2021,26,29,"2021-07-01",null,"2021-07-20T23:59:59",null,"20 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023727/18","Hranice na Moravě - Ostrava","< >","Ostrava pravé nádraží","",2021,2021,39,40,"2021-10-01",null,"2021-10-10T23:59:59",null,"10 days","continuous","Signal","","ST","","","D","","","","","","224.-262. + TV. \nzab. zař. KB 1.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023670/18","Ostrava - Český Těšín","< >","Ostrava-Kunčice","Ostrava-Vítkovice",2021,2021,26,39,"2021-07-01",null,"2021-09-29T23:59:59",null,"91 days","continuous","Bridge","T","LT","","","","","","B","","","1,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023561/18","Hranice na Moravě - Žilina","< >","Hranice na Moravě město","Hranice na Moravě",2021,2021,41,45,"2021-10-16",null,"2021-11-14T23:59:59",null,"30 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023559/18","Hranice na Moravě - Žilina","< >","Hranice na Moravě","Hranice na Moravě město",2021,2021,37,41,"2021-09-16",null,"2021-10-15T23:59:59",null,"30 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023492/18","Praha - Choceň","< >","Poříčany","Český Brod",2021,2021,8,17,"2021-02-23",null,"2021-04-30T23:59:59",null,"67 days","continuous","Miscellaneous","","LT","","","","","","","","","0. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019080/20","Plzen - Praha","< >","Tunel odb.","Praha-Radotín",2021,2021,2,36,"2021-01-11",null,"2021-09-08T23:59:59",null,"241 days","continuous","Miscellaneous","","LT","","","","","","","","","4. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020970/20","Praha - Choceň","< >","Poříčany","Pečky",2021,2021,40,40,"2021-10-09",null,"2021-10-10T23:59:59",null,"2 days","continuous","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020969/20","Praha - Choceň","< >","Poříčany","Sadská",2021,2021,25,26,"2021-06-24",null,"2021-06-30T23:59:59",null,"7 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020965/20","Praha - Choceň","< >","Kolín","Velim",2021,2021,8,8,"2021-02-27T18:00:00",null,"2021-02-28T06:00:00",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020967/20","Praha - Choceň","< >","Kolín","Velim",2021,2021,9,10,"2021-03-06T18:00:00",null,"2021-03-08T06:00:00",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020957/20","Praha - Choceň","< >","Pečky","Velim",2021,2021,36,37,"2021-09-07T18:00:00",null,"2021-09-13T06:00:00",null,"6 x 6 hours","periodical","Catenary","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020877/20","Praha - Choceň","< >","Pečky","Velim",2021,2021,13,47,"2021-04-01T18:00:00",null,"2021-11-24T06:00:00",null,"39 x 4 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020924/20","Praha - Choceň","< >","Pečky","Velim",2021,2021,15,48,"2021-04-14T18:00:00",null,"2021-11-30T06:00:00",null,"17 x 4 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020681/20","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,35,36,"2021-09-01T18:00:00",null,"2021-09-07T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019073/20","Plzen - Praha","< >","Praha-Libeň","Praha-Malešice",2021,2021,36,38,"2021-09-08",null,"2021-09-21T23:59:59",null,"14 days","continuous","Bridge","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023419/18","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,31,33,"2021-08-05",null,"2021-08-18T23:59:59",null,"14 days","continuous","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023419/18","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,31,33,"2021-08-05",null,"2021-08-18T23:59:59",null,"14 days","continuous","Miscellaneous","","ST","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023362/19","Choceň - Hranice na Moravě","< >","Česká Třebová","",2021,2021,24,24,"2021-06-14",null,"2021-06-20T23:59:59",null,"7 days","continuous","Track & Rail","","ST","","","D","","","","","","101T bez TV, 101,102,104. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023354/18","Ostr. - Dětmarovice - Č. Těšín","< >","Petrovice u Karviné","Dětmarovice",2021,2021,30,50,"2021-08-01",null,"2021-12-15T23:59:59",null,"137 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023353/18","Ostr. - Dětmarovice - Č. Těšín","< >","Petrovice u Karviné","Dětmarovice",2021,2021,9,13,"2021-03-01",null,"2021-03-31T23:59:59",null,"31 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023348/18","Ostr. - Dětmarovice - Č. Těšín","< >","Dětmarovice","Petrovice u Karviné",2021,2021,13,30,"2021-04-01",null,"2021-07-31T23:59:59",null,"122 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023346/19","Choceň - Hranice na Moravě","< >","Česká Třebová","",2021,2021,19,21,"2021-05-10",null,"2021-05-29T23:59:59",null,"20 days","continuous","Switch","","ST","","","D","","","","","","215-222 bez TV, 201-222 jen TV, výh.: 230,231,232,233,234,235,236.. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023203/18","Praha - Choceň","< >","Kolín","Ratboř",2021,2021,39,41,"2021-10-01",null,"2021-10-15T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022303/20","Praha - Hr. Králové - Choceň","< >","Chlumec nad Cidlinou","Městec Králové",2021,2021,40,41,"2021-10-04",null,"2021-10-15T23:59:59",null,"10 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023182/19","Ostr. - Dětmarovice - Č. Těšín","< >","Závada odb.","Koukolná odb.",2021,2021,13,19,"2021-04-01",null,"2021-05-15T23:59:59",null,"45 days","continuous","Miscellaneous","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-023170/18","Praha - Hr. Králové - Choceň","< >","Nymburk hlavní nádraží","Veleliby",2021,2021,31,35,"2021-08-03",null,"2021-09-01T23:59:59",null,"30 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020745/20","Praha - Choceň","< >","Pečky","Velim",2021,2021,32,35,"2021-08-15T18:00:00",null,"2021-08-31T06:00:00",null,"16 x 4 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022945/20","Choceň - Hranice na Moravě","< >","Prosenice","Dluhonice výhybna",2021,2021,48,49,"2021-12-01T18:00:00",null,"2021-12-11T06:00:00",null,"10 x 6 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. traťová kolej 1S,2S.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022935/20","Choceň - Hranice na Moravě","< >","Prosenice","Přerov",2021,2021,48,49,"2021-12-01T18:00:00",null,"2021-12-11T06:00:00",null,"10 x 6 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. TZZ 1.,2.TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022908/20","Choceň - Hranice na Moravě","< >","Lipník nad Bečvou","Prosenice",2021,2021,48,50,"2021-12-02",null,"2021-12-16T23:59:59",null,"15 days","continuous","Signal","","LT","","","","","","","","","zab. zař. taraťová kolej 1. a 2..","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020862/20","Praha - Choceň","< >","Velim","Pečky",2021,2021,30,32,"2021-08-01T18:00:00",null,"2021-08-14T06:00:00",null,"13 x 4 hours","periodical","Others","T","LT","","","","","","B","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022874/18","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Střítež nad Bečvou",2021,2021,39,41,"2021-10-01",null,"2021-10-14T23:59:59",null,"14 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022825/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,35,35,"2021-09-01T18:00:00",null,"2021-09-04T06:00:00",null,"3 x 7 hours","periodical","Catenary","T","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022828/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,36,37,"2021-09-09T18:00:00",null,"2021-09-18T06:00:00",null,"9 x 7 hours","periodical","Catenary","T","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022837/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,38,38,"2021-09-22T18:00:00",null,"2021-09-25T06:00:00",null,"3 x 7 hours","periodical","Catenary","T","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022840/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,39,40,"2021-10-01T18:00:00",null,"2021-10-04T06:00:00",null,"3 x 7 hours","periodical","Catenary","T","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020843/20","Praha - Choceň","< >","Poříčany","Pečky",2021,2021,26,28,"2021-07-01T18:00:00",null,"2021-07-14T06:00:00",null,"13 x 4 hours","periodical","Others","T","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022808/20","Plzen - Praha","< >","Praha-Malešice","Praha-Hostivař",2021,2021,44,46,"2021-11-01",null,"2021-11-16T23:59:59",null,"16 x 9 hours","periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005400/19","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,19,19,"2021-05-10T18:00:00",null,"2021-05-15T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020749/20","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,19,22,"2021-05-15T18:00:00",null,"2021-05-31T06:00:00",null,"17 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020766/20","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,22,24,"2021-06-01T18:00:00",null,"2021-06-19T06:00:00",null,"18 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022780/20","Praha - Choceň","< >","Kutná Hora hlavní nádraží","Kolín",2021,2021,13,13,"2021-03-30",null,"2021-03-31T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015918/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Opava východ",2021,2021,8,8,"2021-02-22",null,"2021-02-26T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017830/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Opava východ",2021,2021,15,15,"2021-04-12",null,"2021-04-16T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017835/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Opava východ",2021,2021,49,49,"2021-12-06",null,"2021-12-10T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010846/19","Choceň - Hranice na Moravě","< >","Chornice","Třebovice v Čechách",2021,2021,16,17,"2021-04-19",null,"2021-04-28T23:59:59",null,"10 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010691/19","Plzen - Praha","< >","Praha-Radotín","Tunel odb.",2021,2021,36,52,"2021-09-09",null,"2021-12-31T23:59:59",null,"114 days","continuous","Miscellaneous","","LT","","","","","","","","","3. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010691/19","Plzen - Praha","< >","Praha-Radotín","Odb Barrandov",2021,2021,36,52,"2021-09-09",null,"2021-12-31T23:59:59",null,"114 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010684/19","Plzen - Praha","< >","Praha-Radotín","Dobřichovice",2021,2021,35,36,"2021-09-05",null,"2021-09-08T23:59:59",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. \nzhlaví dobřichovické 2. TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010683/19","Plzen - Praha","< >","Odb Barrandov","Praha-Radotín",2021,2021,10,36,"2021-03-13",null,"2021-09-08T23:59:59",null,"180 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010678/19","Plzen - Praha","< >","Praha-Radotín","Dobřichovice",2021,2021,10,11,"2021-03-12",null,"2021-03-15T23:59:59",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. \nzhlaví dobřichovické 2. TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006828/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,14,20,"2021-04-10",null,"2021-05-22T23:59:59",null,"9 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006829/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,19,22,"2021-05-15",null,"2021-06-05T23:59:59",null,"8 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006847/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,22,23,"2021-06-06",null,"2021-06-11T23:59:59",null,"6 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004331/20","Plzen - Praha","< >","Beroun","Zdice",2021,2021,7,7,"2021-02-19",null,"2021-02-20T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004329/20","Plzen - Praha","< >","Zdice","Beroun",2021,2021,7,7,"2021-02-16",null,"2021-02-17T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010665/19","Praha - Choceň","< >","Řečany nad Labem","Přelouč",2021,2021,35,36,"2021-09-05T18:00:00",null,"2021-09-06T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010664/19","Praha - Choceň","< >","Přelouč","Řečany nad Labem",2021,2021,35,35,"2021-09-04T18:00:00",null,"2021-09-05T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010653/19","Praha - Choceň","< >","Záboří nad Labem","Řečany nad Labem",2021,2021,36,36,"2021-09-08T18:00:00",null,"2021-09-10T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010661/19","Praha - Choceň","< >","Řečany nad Labem","Záboří nad Labem",2021,2021,36,36,"2021-09-06T18:00:00",null,"2021-09-07T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010652/19","Praha - Choceň","< >","Řečany nad Labem","Záboří nad Labem",2021,2021,36,36,"2021-09-07T18:00:00",null,"2021-09-08T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006772/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,20,21,"2021-05-23",null,"2021-05-26T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006776/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,24,24,"2021-06-14",null,"2021-06-17T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006780/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,28,28,"2021-07-12",null,"2021-07-15T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010555/19","Praha - Choceň","< >","Záboří nad Labem","Kolín vjezd.náv.L",2021,2021,37,37,"2021-09-14T18:00:00",null,"2021-09-15T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010554/19","Praha - Choceň","< >","Kolín vjezd.náv.L","Záboří nad Labem",2021,2021,37,37,"2021-09-13T18:00:00",null,"2021-09-14T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010426/18","Praha - Hr. Králové - Choceň","< >","Nový Bydžov","Chlumec nad Cidlinou",2021,2021,14,14,"2021-04-08",null,"2021-04-11T23:59:59",null,"4 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010426/18","Praha - Hr. Králové - Choceň","< >","Chlumec nad Cidlinou","",2021,2021,14,14,"2021-04-08",null,"2021-04-11T23:59:59",null,"4 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví novobydžovské","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010329/19","Plzen - Praha","< >","Ejpovice","Chrást u Plzně",2021,2021,42,43,"2021-10-20",null,"2021-10-26T23:59:59",null,"7 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010327/19","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","Prosenice",2021,2021,53,17,"2021-01-01",null,"2021-04-29T23:59:59",null,"119 days","continuous","Miscellaneous","","LT","","","","","","","","","2S + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010324/19","Regensburg - Plzen","< >","Stod","Holýšov",2021,2021,39,41,"2021-10-01",null,"2021-10-15T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-009856/19","Praha - Choceň","< >","Zámrsk","Choceň",2021,2021,10,13,"2021-03-11",null,"2021-04-04T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019010/20","Choceň - Hranice na Moravě","< >","Třebovice v Čechách","Česká Třebová",2021,2021,15,15,"2021-04-17",null,"2021-04-17T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019008/20","Choceň - Hranice na Moravě","< >","Česká Třebová","Třebovice v Čechách",2021,2021,15,15,"2021-04-17",null,"2021-04-17T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019007/20","Choceň - Hranice na Moravě","< >","Rudoltice v Čechách","Třebovice v Čechách",2021,2021,15,15,"2021-04-16",null,"2021-04-16T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019006/20","Choceň - Hranice na Moravě","< >","Třebovice v Čechách","Rudoltice v Čechách",2021,2021,15,15,"2021-04-16",null,"2021-04-16T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019005/20","Choceň - Hranice na Moravě","< >","Rudoltice v Čechách","Třebovice v Čechách",2021,2021,15,15,"2021-04-15",null,"2021-04-15T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019004/20","Choceň - Hranice na Moravě","< >","Třebovice v Čechách","Rudoltice v Čechách",2021,2021,15,15,"2021-04-15",null,"2021-04-15T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004215/20","Plzen - Praha","< >","Beroun","Zdice",2021,2021,10,10,"2021-03-08",null,"2021-03-09T23:59:59",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004211/20","Plzen - Praha","< >","Zdice","Beroun",2021,2021,10,10,"2021-03-10",null,"2021-03-12T23:59:59",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004191/20","Plzen - Praha","< >","Zdice","Hořovice",2021,2021,39,39,"2021-09-30",null,"2021-09-30T23:59:59",null,"1 x 16 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004194/20","Plzen - Praha","< >","Hořovice","Kařízek",2021,2021,39,39,"2021-10-02",null,"2021-10-02T23:59:59",null,"1 x 16 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004190/20","Plzen - Praha","< >","Hořovice","Zdice",2021,2021,39,39,"2021-09-29",null,"2021-09-29T23:59:59",null,"1 x 16 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004192/20","Plzen - Praha","< >","Kařízek","Hořovice",2021,2021,39,39,"2021-10-01",null,"2021-10-01T23:59:59",null,"1 x 16 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018994/20","Choceň - Hranice na Moravě","< >","Krasíkov","Rudoltice v Čechách",2021,2021,15,15,"2021-04-14",null,"2021-04-14T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018993/20","Choceň - Hranice na Moravě","< >","Rudoltice v Čechách","Krasíkov",2021,2021,15,15,"2021-04-14",null,"2021-04-14T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018992/20","Choceň - Hranice na Moravě","< >","Krasíkov","Rudoltice v Čechách",2021,2021,15,15,"2021-04-13",null,"2021-04-13T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018991/20","Choceň - Hranice na Moravě","< >","Rudoltice v Čechách","Krasíkov",2021,2021,15,15,"2021-04-13",null,"2021-04-13T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018990/20","Choceň - Hranice na Moravě","< >","Hoštejn","Krasíkov",2021,2021,15,15,"2021-04-12",null,"2021-04-12T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018989/20","Choceň - Hranice na Moravě","< >","Krasíkov","Hoštejn",2021,2021,15,15,"2021-04-12",null,"2021-04-12T23:59:59",null,"1 x 8 hours","periodical","Switch","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-009532/19","Choceň - Hranice na Moravě","< >","Olomouc hlavní nádraží","Velká Bystřice",2021,2021,9,13,"2021-03-01",null,"2021-03-30T23:59:59",null,"30 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-009423/19","Plzen - Praha","< >","Praha-Vršovice","Praha-Krč",2021,2021,41,42,"2021-10-12",null,"2021-10-21T23:59:59",null,"10 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006763/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,20,20,"2021-05-21",null,"2021-05-22T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006765/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,23,23,"2021-06-09",null,"2021-06-13T23:59:59",null,"5 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006770/20","Choceň - Hranice na Moravě","< >","Přerov","Dluhonice výhybna",2021,2021,30,30,"2021-07-28",null,"2021-07-29T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006766/19","Ostrava - Český Těšín","< >","Havířov","Albrechtice u Českého Těšína",2021,2021,5,7,"2021-02-02",null,"2021-02-15T23:59:59",null,"14 days","continuous","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-008237/19","Praha - Choceň","< >","Přelouč","Pardubice hlavní nádraží",2021,2021,33,35,"2021-08-19",null,"2021-09-03T23:59:59",null,"16 days","continuous","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-008237/19","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,33,35,"2021-08-19",null,"2021-09-03T23:59:59",null,"16 days","continuous","Miscellaneous","","ST","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-008216/20","Plzen - Praha","< >","Praha-Krč","Praha-Vršovice",2021,2021,5,8,"2021-02-03",null,"2021-02-26T23:59:59",null,"24 days","continuous","Catenary","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004183/20","Plzen - Praha","< >","Zdice","Hořovice",2021,2021,37,38,"2021-09-17T18:00:00",null,"2021-09-20T06:00:00",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004182/20","Plzen - Praha","< >","Hořovice","Zdice",2021,2021,37,37,"2021-09-16T18:00:00",null,"2021-09-19T06:00:00",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004178/20","Plzen - Praha","< >","Zdice","Hořovice",2021,2021,33,33,"2021-08-17T18:00:00",null,"2021-08-18T06:00:00",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004180/20","Plzen - Praha","< >","Hořovice","Kařízek",2021,2021,33,33,"2021-08-20T18:00:00",null,"2021-08-21T06:00:00",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004177/20","Plzen - Praha","< >","Hořovice","Zdice",2021,2021,33,33,"2021-08-16T18:00:00",null,"2021-08-17T06:00:00",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004179/20","Plzen - Praha","< >","Kařízek","Hořovice",2021,2021,33,33,"2021-08-19T18:00:00",null,"2021-08-20T06:00:00",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004129/20","Hranice na Moravě - Žilina","< >","Jablůnka","Valašské Meziříčí",2021,2021,12,13,"2021-03-22",null,"2021-03-31T23:59:59",null,"10 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004128/20","Hranice na Moravě - Žilina","< >","Jablůnka","Valašské Meziříčí",2021,2021,28,31,"2021-07-15",null,"2021-08-03T23:59:59",null,"20 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022431/18","Hranice na Moravě - Žilina","< >","Vsetín","Hovězí",2021,2021,37,39,"2021-09-16",null,"2021-09-30T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006725/20","Hranice na Moravě - Ostrava","< >","Ostrava hlavní nádraží","",2021,2021,26,27,"2021-07-02",null,"2021-07-08T23:59:59",null,"7 days","continuous","Switch","","ST","","","D","","","","","","6a bez TV, 4a,6a,6,8,10,10b jen TV, výh.: 93,94,96,101. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006724/20","Hranice na Moravě - Žilina","< >","Lhotka nad Bečvou","Hustopeče nad Bečvou",2021,2021,1,4,"2021-01-04",null,"2021-01-29T23:59:59",null,"26 days","continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ, PZZ.",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006724/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Lhotka nad Bečvou",2021,2021,1,4,"2021-01-04",null,"2021-01-29T23:59:59",null,"26 days","continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ, PZZ.",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006723/20","Ostrava - Český Těšín","< >","Ostrava-Vítkovice","Odra odb.",2021,2021,35,36,"2021-09-02",null,"2021-09-10T23:59:59",null,"9 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006618/20","Hranice na Moravě - Žilina","< >","Lhotka nad Bečvou","Hustopeče nad Bečvou",2021,2021,15,15,"2021-04-14",null,"2021-04-14T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006623/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Lhotka nad Bečvou",2021,2021,16,16,"2021-04-19",null,"2021-04-20T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003998/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Jablůnka",2021,2021,17,28,"2021-05-01",null,"2021-07-14T23:59:59",null,"75 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003976/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Jablůnka",2021,2021,9,11,"2021-03-01",null,"2021-03-19T23:59:59",null,"11 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003982/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Jablůnka",2021,2021,10,11,"2021-03-08",null,"2021-03-15T23:59:59",null,"8 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003985/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Jablůnka",2021,2021,11,11,"2021-03-20",null,"2021-03-21T23:59:59",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003924/20","Hranice na Moravě - Žilina","< >","Hustopeče nad Bečvou","",2021,2021,35,36,"2021-09-01",null,"2021-09-06T23:59:59",null,"6 x 6 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020648/20","Plzen - Praha","< >","Praha-Hostivař","Praha-Malešice",2021,2021,34,40,"2021-08-28",null,"2021-10-04T23:59:59",null,"38 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020647/20","Plzen - Praha","< >","Praha-Malešice","Praha-Zahradní Město",2021,2021,40,43,"2021-10-05",null,"2021-10-29T23:59:59",null,"25 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006615/20","Hranice na Moravě - Žilina","< >","Hustopeče nad Bečvou","Lhotka nad Bečvou",2021,2021,14,15,"2021-04-11",null,"2021-04-12T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006621/20","Hranice na Moravě - Žilina","< >","Lhotka nad Bečvou","Valašské Meziříčí",2021,2021,15,15,"2021-04-17",null,"2021-04-18T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006619/20","Hranice na Moravě - Žilina","< >","Lhotka nad Bečvou","Hustopeče nad Bečvou",2021,2021,15,15,"2021-04-15",null,"2021-04-16T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006617/20","Hranice na Moravě - Žilina","< >","Hustopeče nad Bečvou","Lhotka nad Bečvou",2021,2021,15,15,"2021-04-13",null,"2021-04-13T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006440/20","Plzen - Praha","< >","Beroun","Zdice",2021,2021,42,42,"2021-10-23T18:00:00",null,"2021-10-24T06:00:00",null,"1 x 5 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. TZZ 1. a 2. TK .","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006435/20","Plzen - Praha","< >","Rokycany","Ejpovice",2021,2021,42,47,"2021-10-23T18:00:00",null,"2021-11-28T06:00:00",null,"11 x 5 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. TZZ 1. a 2. TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022317/20","Praha - Hr. Králové - Choceň","< >","Chlumec nad Cidlinou","Dobšice nad Cidlinou",2021,2021,13,14,"2021-04-02",null,"2021-04-05T23:59:59",null,"4 days","continuous","Track & Rail","","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022316/20","Praha - Hr. Králové - Choceň","< >","Praskačka","Chlumec nad Cidlinou",2021,2021,13,14,"2021-04-02",null,"2021-04-05T23:59:59",null,"4 days","continuous","Track & Rail","","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022036/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Kostěnice",2021,2021,48,48,"2021-11-29",null,"2021-12-05T23:59:59",null,"7 x 8 hours","periodical","Catenary","","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020393/20","Praha - Hr. Králové - Choceň","< >","Újezd u Chocně","Čermná nad Orlicí",2021,2021,17,17,"2021-04-28T18:00:00",null,"2021-04-30T06:00:00",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-003914/20","Choceň - Hranice na Moravě","< >","Blatec","Olomouc hlavní nádraží",2021,2021,18,19,"2021-05-08",null,"2021-05-14T23:59:59",null,"7 x 10 hours","periodical","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022029/20","Praha - Choceň","< >","Kostěnice","Pardubice hlavní nádraží",2021,2021,47,47,"2021-11-22",null,"2021-11-28T23:59:59",null,"7 x 8 hours","periodical","Catenary","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006322/20","Hranice na Moravě - Žilina","< >","Valašské Meziříčí","Jablůnka",2021,2021,48,48,"2021-12-01",null,"2021-12-05T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020387/20","Praha - Hr. Králové - Choceň","< >","Borohrádek","",2021,2021,15,16,"2021-04-12",null,"2021-04-25T23:59:59",null,"14 days","continuous","Miscellaneous","","ST","","","D","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020387/20","Praha - Hr. Králové - Choceň","< >","Borohrádek","",2021,2021,15,16,"2021-04-12",null,"2021-04-25T23:59:59",null,"14 days","continuous","Miscellaneous","","ST","","","D","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006323/20","Hranice na Moravě - Žilina","< >","Jablůnka","Valašské Meziříčí",2021,2021,49,49,"2021-12-06",null,"2021-12-10T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006265/20","Hranice na Moravě - Žilina","< >","Vsetín","Valašská Polanka",2021,2021,44,48,"2021-11-01",null,"2021-11-30T23:59:59",null,"30 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022021/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,34,35,"2021-08-29T18:00:00",null,"2021-08-31T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022024/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,34,35,"2021-08-26T18:00:00",null,"2021-09-03T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022028/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,35,35,"2021-09-01T18:00:00",null,"2021-09-02T06:00:00",null,"1 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022021/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,34,35,"2021-08-29T18:00:00",null,"2021-08-31T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví TK 2 směr Přelouč + TV","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022024/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,34,35,"2021-08-26T18:00:00",null,"2021-09-03T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví TK 2 směr Přelouč + TV","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022028/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,35,35,"2021-09-01T18:00:00",null,"2021-09-02T06:00:00",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví TK 2 směr Přelouč + TV","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006234/20","Hranice na Moravě - Žilina","< >","Valašská Polanka","Vsetín",2021,2021,39,43,"2021-10-01",null,"2021-10-31T23:59:59",null,"31 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018365/20","Ostr. - Dětmarovice - Č. Těšín","< >","Bohumín","Bohumín st.hr.",2021,2021,22,22,"2021-06-01",null,"2021-06-04T23:59:59",null,"4 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018008/20","Ostrava - Český Těšín","< >","Vratimov","Ostrava-Kunčice",2021,2021,17,17,"2021-04-26",null,"2021-04-30T23:59:59",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-018006/20","Ostrava - Český Těšín","< >","Vratimov","Ostrava-Kunčice",2021,2021,16,16,"2021-04-20",null,"2021-04-25T23:59:59",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","2 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017997/20","Ostrava - Český Těšín","< >","Havířov","Albrechtice u Českého Těšína",2021,2021,46,48,"2021-11-16",null,"2021-11-30T23:59:59",null,"15 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017995/20","Ostrava - Český Těšín","< >","Havířov","Albrechtice u Českého Těšína",2021,2021,44,46,"2021-11-01",null,"2021-11-15T23:59:59",null,"15 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017994/20","Ostrava - Český Těšín","< >","Český Těšín","Albrechtice u Českého Těšína",2021,2021,42,43,"2021-10-20",null,"2021-10-30T23:59:59",null,"11 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020154/20","Choceň - Hranice na Moravě","< >","Třebovice v Čechách","Moravská Třebová",2021,2021,46,46,"2021-11-15",null,"2021-11-19T23:59:59",null,"5 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020096/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2021,2021,22,46,"2021-05-31",null,"2021-11-18T23:59:59",null,"172 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020056/20","Praha - Choceň","< >","Záboří nad Labem","Kolín",2021,2021,37,37,"2021-09-16T18:00:00",null,"2021-09-17T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020054/20","Praha - Choceň","< >","Záboří nad Labem","Kolín",2021,2021,37,37,"2021-09-15T18:00:00",null,"2021-09-16T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020047/20","Praha - Choceň","< >","Přelouč","Řečany nad Labem",2021,2021,35,35,"2021-09-04T18:00:00",null,"2021-09-05T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-020046/20","Praha - Choceň","< >","Přelouč","Řečany nad Labem",2021,2021,35,36,"2021-09-05T18:00:00",null,"2021-09-06T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022018/20","Praha - Choceň","< >","Přelouč","Pardubice hlavní nádraží",2021,2021,32,33,"2021-08-14T18:00:00",null,"2021-08-17T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022018/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,32,33,"2021-08-14T18:00:00",null,"2021-08-17T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví TK 1 směr Přelouč + TV","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022015/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,15,15,"2021-04-13T18:00:00",null,"2021-04-15T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022013/20","Praha - Choceň","< >","Kostěnice","Pardubice hlavní nádraží",2021,2021,12,12,"2021-03-27",null,"2021-03-28T23:59:59",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","B","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022013/20","Praha - Choceň","< >","Pardubice hlavní nádraží","",2021,2021,12,12,"2021-03-27",null,"2021-03-28T23:59:59",null,"2 x 8 hours","periodical","Catenary","","ST","","","","","","B","","","4,6,6a jen TV, 2,2a + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017993/20","Ostrava - Český Těšín","< >","Český Těšín","Albrechtice u Českého Těšína",2021,2021,39,42,"2021-10-01",null,"2021-10-19T23:59:59",null,"19 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017990/20","Choceň - Hranice na Moravě","< >","Přerov","",2021,2021,14,15,"2021-04-10",null,"2021-04-15T23:59:59",null,"6 days","continuous","Catenary","","ST","","","D","","","","","","18.,20. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006227/20","Hranice na Moravě - Žilina","< >","Vsetín","Valašská Polanka",2021,2021,36,36,"2021-09-08T18:00:00",null,"2021-09-11T06:00:00",null,"3 x 6 hours","periodical","Bridge","T","LT","","","","","","","","","1,2 + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019887/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","Hněvčeves",2021,2021,16,16,"2021-04-19",null,"2021-04-23T23:59:59",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-019782/20","Praha - Hr. Králové - Choceň","< >","Praskačka","Chlumec nad Cidlinou",2021,2021,14,14,"2021-04-06",null,"2021-04-08T23:59:59",null,"6 x 10 hours","periodical","Track & Rail","","LT","","","","","","B","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022011/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,22,22,"2021-06-01T18:00:00",null,"2021-06-04T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022009/20","Praha - Choceň","< >","Přelouč","Pardubice hlavní nádraží",2021,2021,21,22,"2021-05-30T18:00:00",null,"2021-05-31T06:00:00",null,"1 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022010/20","Praha - Choceň","< >","Přelouč","Pardubice hlavní nádraží",2021,2021,22,22,"2021-06-02T18:00:00",null,"2021-06-03T06:00:00",null,"1 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022004/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,35,35,"2021-09-03T18:00:00",null,"2021-09-05T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-022005/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,37,37,"2021-09-17T18:00:00",null,"2021-09-19T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2,1 bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-002063/20","Choceň - Hranice na Moravě","< >","Přerov","",2021,2021,14,14,"2021-04-06",null,"2021-04-09T23:59:59",null,"4 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","18.,20. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017982/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,20,20,"2021-05-17",null,"2021-05-18T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","0/1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017984/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,35,35,"2021-09-01",null,"2021-09-02T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","0/1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017967/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná-Doly",2021,2021,14,16,"2021-04-06",null,"2021-04-20T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017960/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná-Doly",2021,2021,10,10,"2021-03-11",null,"2021-03-12T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017961/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná-Doly",2021,2021,10,39,"2021-03-13",null,"2021-10-01T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017964/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná-Doly",2021,2021,39,39,"2021-10-02",null,"2021-10-02T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","T","LT","","","","","","","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017952/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,9,10,"2021-03-06",null,"2021-03-10T23:59:59",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1/0 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017957/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,39,40,"2021-10-03",null,"2021-10-05T23:59:59",null,"3 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1/0 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005607/20","Choceň - Hranice na Moravě","< >","Uničov","Olomouc hlavní nádraží",2021,2021,44,46,"2021-11-01",null,"2021-11-19T23:59:59",null,"19 days","continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. aktivace DOZ.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005572/20","Choceň - Hranice na Moravě","< >","Šternberk","Olomouc hlavní nádraží",2021,2021,36,39,"2021-09-09",null,"2021-10-03T23:59:59",null,"25 days","continuous","Catenary","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017947/20","Ostr. - Dětmarovice - Č. Těšín","< >","Louky nad Olší","Karviná hlavní nádraží",2021,2021,9,9,"2021-03-01",null,"2021-03-05T23:59:59",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2/2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005381/19","Hranice na Moravě - Žilina","< >","Hranice na Moravě město","Hranice na Moravě",2021,2021,17,17,"2021-04-26",null,"2021-04-30T23:59:59",null,"5 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005380/19","Hranice na Moravě - Žilina","< >","Hranice na Moravě","Hranice na Moravě město",2021,2021,16,16,"2021-04-21",null,"2021-04-25T23:59:59",null,"5 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005313/20","Ostr. - Dětmarovice - Č. Těšín","< >","Dětmarovice","Petrovice u Karviné",2021,2021,2,3,"2021-01-11",null,"2021-01-19T23:59:59",null,"4 x 10 hours","periodical","Others","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005324/20","Ostr. - Dětmarovice - Č. Těšín","< >","Dětmarovice","Petrovice u Karviné",2021,2021,3,3,"2021-01-20",null,"2021-01-21T23:59:59",null,"2 x 10 hours","periodical","Others","","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005306/19","Hranice na Moravě - Žilina","< >","Hostašovice","Valašské Meziříčí",2021,2021,26,28,"2021-07-01",null,"2021-07-16T23:59:59",null,"16 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZZ v km 61,937 a 64,219 a 65,880.",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007768/20","Praha - Choceň","< >","Kutná Hora hlavní nádraží","Kolín",2021,2021,9,9,"2021-03-03",null,"2021-03-06T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007767/20","Praha - Choceň","< >","Řečany nad Labem","Pečky",2021,2021,17,17,"2021-04-29T18:00:00",null,"2021-04-30T06:00:00",null,"3 x 5 hours","periodical","Catenary","T","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007767/20","Praha - Choceň","< >","Kolín","Kutná Hora hlavní nádraží",2021,2021,17,17,"2021-04-29T18:00:00",null,"2021-04-30T06:00:00",null,"1 x 5 hours","periodical","Catenary","T","LT","","","","","","","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007766/20","Praha - Choceň","< >","Řečany nad Labem","Pečky",2021,2021,15,17,"2021-04-18",null,"2021-04-29T23:59:59",null,"12 days","continuous","Catenary","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007766/20","Praha - Choceň","< >","Kolín","Nymburk hlavní nádraží",2021,2021,15,17,"2021-04-18",null,"2021-04-29T23:59:59",null,"12 days","continuous","Catenary","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007766/20","Praha - Choceň","< >","Kolín","Kutná Hora hlavní nádraží",2021,2021,15,17,"2021-04-18",null,"2021-04-29T23:59:59",null,"12 days","continuous","Catenary","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007765/20","Praha - Choceň","< >","Kolín","Kutná Hora hlavní nádraží",2021,2021,15,15,"2021-04-17T18:00:00",null,"2021-04-18T06:00:00",null,"1 x 5 hours","periodical","Catenary","T","LT","","","","","","","","","1.,2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007765/20","Praha - Choceň","< >","Řečany nad Labem","Pečky",2021,2021,15,15,"2021-04-17T18:00:00",null,"2021-04-18T06:00:00",null,"3 x 5 hours","periodical","Catenary","T","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007761/20","Praha - Choceň","< >","Kolín","Kutná Hora hlavní nádraží",2021,2021,12,13,"2021-03-28",null,"2021-03-29T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005286/19","Hranice na Moravě - Žilina","< >","Valašské Klobouky","Horní Lideč",2021,2021,40,42,"2021-10-05",null,"2021-10-19T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007757/20","Praha - Choceň","< >","Řečany nad Labem","Pečky",2021,2021,9,10,"2021-03-07",null,"2021-03-10T23:59:59",null,"12 x 10 hours","periodical","Catenary","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007750/20","Praha - Choceň","< >","Kolín","Kutná Hora hlavní nádraží",2021,2021,8,9,"2021-02-28",null,"2021-03-02T23:59:59",null,"3 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007707/20","Nürnberg - Plzen","< >","Pňovany","Stříbro",2021,2021,42,42,"2021-10-21",null,"2021-10-22T23:59:59",null,"2 x 6 hours","periodical","Maintenance","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007709/20","Nürnberg - Plzen","< >","Pňovany","Stříbro",2021,2021,43,43,"2021-10-25",null,"2021-10-27T23:59:59",null,"3 x 6 hours","periodical","Maintenance","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007713/20","Nürnberg - Plzen","< >","Svojšín","Planá u Mariánských Lázní",2021,2021,43,43,"2021-10-29",null,"2021-10-29T23:59:59",null,"1 x 6 hours","periodical","Maintenance","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007714/20","Nürnberg - Plzen","< >","Svojšín","Planá u Mariánských Lázní",2021,2021,44,44,"2021-11-01",null,"2021-11-04T23:59:59",null,"4 x 6 hours","periodical","Maintenance","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007638/20","Plzen - Praha","< >","Ejpovice","Rokycany",2021,2021,42,43,"2021-10-20",null,"2021-10-26T23:59:59",null,"7 x 12 hours","periodical","Track & Rail","","LT","","","","","","B","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007638/20","Plzen - Praha","< >","Ejpovice","",2021,2021,42,43,"2021-10-20",null,"2021-10-26T23:59:59",null,"7 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","2.,4. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007631/20","Plzen - Praha","< >","Rokycany","Ejpovice",2021,2021,41,42,"2021-10-13",null,"2021-10-19T23:59:59",null,"7 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-002017/20","Choceň - Hranice na Moravě","< >","Přerov","",2021,2021,11,14,"2021-03-18",null,"2021-04-05T23:59:59",null,"19 days","continuous","Catenary","","ST","","","D","","","","","","18.,20. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005212/19","Choceň - Hranice na Moravě","< >","Zábřeh na Moravě","Hoštejn",2021,2021,40,41,"2021-10-04",null,"2021-10-13T23:59:59",null,"10 days","continuous","Signal","","LT","","","","","","","","","zab. zař. 2.TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005212/19","Choceň - Hranice na Moravě","< >","Hoštejn","Zábřeh na Moravě",2021,2021,40,41,"2021-10-04",null,"2021-10-13T23:59:59",null,"10 days","continuous","Signal","","LT","","","","","","","","","zab. zař. 1.TK.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007449/20","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2021,2021,41,42,"2021-10-11",null,"2021-10-20T23:59:59",null,"10 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007449/20","Nürnberg - Plzen","< >","Lipová u Chebu","",2021,2021,41,42,"2021-10-11",null,"2021-10-20T23:59:59",null,"10 x 10 hours","periodical","Track & Rail","","ST","","","","","","B","","","1,2,3,4 + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007449/20","Nürnberg - Plzen","< >","Lipová u Chebu","",2021,2021,41,42,"2021-10-11",null,"2021-10-20T23:59:59",null,"10 x 10 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví plzeňské.",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007449/20","Nürnberg - Plzen","< >","Lipová u Chebu","",2021,2021,41,42,"2021-10-11",null,"2021-10-20T23:59:59",null,"10 x 10 hours","periodical","Track & Rail","","ST","","","","","","B","","","zhlaví chebské.",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005144/19","Praha - Choceň","< >","Poříčany","Pečky",2021,2021,28,30,"2021-07-15",null,"2021-07-28T23:59:59",null,"14 days","continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005142/19","Praha - Choceň","< >","Pečky","Poříčany",2021,2021,26,28,"2021-07-01",null,"2021-07-14T23:59:59",null,"14 days","continuous","Miscellaneous","","LT","","","","","","B","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005141/19","Praha - Choceň","< >","Velim","Pečky",2021,2021,32,35,"2021-08-15",null,"2021-08-31T23:59:59",null,"17 days","continuous","Miscellaneous","","LT","","","","","","B","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005140/19","Praha - Choceň","< >","Pečky","Velim",2021,2021,30,32,"2021-07-29",null,"2021-08-14T23:59:59",null,"17 days","continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005139/19","Praha - Choceň","< >","Český Brod","Poříčany",2021,2021,7,8,"2021-02-20",null,"2021-02-23T23:59:59",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-005111/19","Praha - Choceň","< >","Český Brod","Poříčany",2021,2021,17,26,"2021-05-01",null,"2021-06-30T23:59:59",null,"61 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-007448/20","Nürnberg - Plzen","< >","Cheb","Františkovy Lázně",2021,2021,31,35,"2021-08-02",null,"2021-08-31T23:59:59",null,"30 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ",80,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004333/20","Plzen - Praha","< >","Karlštejn","Beroun",2021,2021,12,13,"2021-03-26T18:00:00",null,"2021-03-29T06:00:00",null,"6 x 2 hours","periodical","Others","","LT","","","D","","","","","","1.,2. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-004333/20","Plzen - Praha","< >","Beroun","",2021,2021,12,13,"2021-03-26T18:00:00",null,"2021-03-29T06:00:00",null,"6 x 2 hours","periodical","Others","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006943/19","Hranice na Moravě - Ostrava","< >","Suchdol nad Odrou","Fulnek",2021,2021,22,24,"2021-06-01",null,"2021-06-16T23:59:59",null,"16 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006941/19","Hranice na Moravě - Ostrava","< >","Suchdol nad Odrou","Fulnek",2021,2021,23,23,"2021-06-07",null,"2021-06-09T23:59:59",null,"3 days","continuous","Signal","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006939/19","Hranice na Moravě - Ostrava","< >","Studénka","",2021,2021,35,38,"2021-09-01",null,"2021-09-20T23:59:59",null,"20 days","continuous","Track & Rail","","ST","","","","","","B","","","105b,105c,107 jen TV, 105,105a + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-006868/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","Prosenice",2021,2021,44,48,"2021-11-02",null,"2021-12-01T23:59:59",null,"30 days","continuous","Track & Rail","","LT","","","","","","","","","2S + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017521/20","Hranice na Moravě - Ostrava","< >","Ostrava pravé nádraží","",2021,2021,42,43,"2021-10-18",null,"2021-10-27T23:59:59",null,"10 days","continuous","Track & Rail","","ST","","","D","","","","","","246.,248. bez TV, 240.-250. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017519/20","Hranice na Moravě - Ostrava","< >","Ostrava pravé nádraží","",2021,2021,39,40,"2021-10-01",null,"2021-10-10T23:59:59",null,"10 days","continuous","Track & Rail","","ST","","","D","","","","","","210.,212. bez TV, 206.-214. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017481/20","Hranice na Moravě - Ostrava","< >","Suchdol nad Odrou","Heřmánky",2021,2021,26,27,"2021-06-29",null,"2021-07-07T23:59:59",null,"9 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017374/20","Choceň - Hranice na Moravě","< >","Štěpánov","",2021,2021,15,15,"2021-04-17",null,"2021-04-18T23:59:59",null,"2 x 5 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017278/20","Hranice na Moravě - Žilina","< >","Valašská Polanka","Horní Lideč",2021,2021,35,39,"2021-09-03",null,"2021-09-30T23:59:59",null,"28 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017277/20","Hranice na Moravě - Žilina","< >","Horní Lideč","Valašská Polanka",2021,2021,31,35,"2021-08-04",null,"2021-09-02T23:59:59",null,"30 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017253/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,20,21,"2021-05-22T18:00:00",null,"2021-05-28T06:00:00",null,"6 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017259/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,25,26,"2021-06-23T18:00:00",null,"2021-06-29T06:00:00",null,"6 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017265/20","Choceň - Hranice na Moravě","< >","Dluhonice výhybna","",2021,2021,29,30,"2021-07-24T18:00:00",null,"2021-07-30T06:00:00",null,"6 x 7 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017142/20","Choceň - Hranice na Moravě","< >","Prosenice","Lipník nad Bečvou",2021,2021,26,29,"2021-07-02",null,"2021-07-21T23:59:59",null,"20 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017139/20","Choceň - Hranice na Moravě","< >","Lipník nad Bečvou","Prosenice",2021,2021,23,26,"2021-06-12",null,"2021-07-01T23:59:59",null,"20 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-017138/20","Choceň - Hranice na Moravě","< >","Bohuňovice","Olomouc hlavní nádraží",2021,2021,53,3,"2021-01-01",null,"2021-01-20T23:59:59",null,"20 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ, PZZ .","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016714/20","Hranice na Moravě - Žilina","< >","Vsetín","",2021,2021,36,36,"2021-09-09",null,"2021-09-09T23:59:59",null,"1 x 5 hours","periodical","Others","","ST","","","D","","","","","","celá jen TV, 1,2 + TV. ",56,"N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016704/20","Choceň - Hranice na Moravě","< >","Zábřeh na Moravě","Postřelmov",2021,2021,45,46,"2021-11-10",null,"2021-11-16T23:59:59",null,"7 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016701/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","Předměřice nad Labem",2021,2021,20,20,"2021-05-19",null,"2021-05-19T23:59:59",null,"1 x 8 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. PZS v km 24,239.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016700/20","Praha - Hr. Králové - Choceň","< >","Hradec Králové hlavní nádraží","Předměřice nad Labem",2021,2021,20,20,"2021-05-18",null,"2021-05-18T23:59:59",null,"1 x 8 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. PZS v km 23,902.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016272/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,12,12,"2021-03-25",null,"2021-03-26T23:59:59",null,"2 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","2.,4. bez TV, sudá jen TV, výh.: 7,8. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016269/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,12,12,"2021-03-22",null,"2021-03-24T23:59:59",null,"3 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","1.,3.,5. bez TV, lichá jen TV, výh.: 5,6,9. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016268/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,11,11,"2021-03-18",null,"2021-03-18T23:59:59",null,"1 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","1.,3.,5. bez TV, celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016267/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,11,11,"2021-03-17",null,"2021-03-17T23:59:59",null,"1 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","1.,3.,5. bez TV, celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016266/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,11,11,"2021-03-16",null,"2021-03-16T23:59:59",null,"1 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","5. bez TV, lichá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016265/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,11,11,"2021-03-15",null,"2021-03-15T23:59:59",null,"1 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","5. bez TV, lichá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016263/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,10,10,"2021-03-13",null,"2021-03-14T23:59:59",null,"2 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","1.,5.,7.,4.,8. bez TV, celá jen TV, výh.: 5,6,9,8. \nzhlaví ze směru Havířov od náv. Se4 po S1,S3,S5.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016260/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,10,10,"2021-03-08",null,"2021-03-10T23:59:59",null,"3 x 12 hours","periodical","Catenary","","ST","","","D","","","","","","1.,5.,7. bez TV, celá jen TV. \nzhlaví ze směru Havířov od nám. výh.4 po náv.S2 až S14.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016259/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,6,6,"2021-02-09",null,"2021-02-09T23:59:59",null,"1 x 6 hours","periodical","Catenary","","ST","","","D","","","","","","5. bez TV, lichá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016254/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,9,9,"2021-03-01",null,"2021-03-05T23:59:59",null,"5 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","2.-14. + TV, výh.: 7,8,10,11. \nzhlaví ze směru Havířovod nám. výh.4 po náv.S2 až S14.","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016253/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,6,6,"2021-02-11",null,"2021-02-11T23:59:59",null,"1 x 5 hours","periodical","Catenary","","ST","","","D","","","","","","5. bez TV, lichá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016252/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,6,6,"2021-02-11",null,"2021-02-11T23:59:59",null,"1 x 5 hours","periodical","Catenary","","ST","","","D","","","","","","2.,4. bez TV, sudá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-016239/20","Ostrava - Český Těšín","< >","Ostrava-Bartovice","",2021,2021,6,6,"2021-02-09",null,"2021-02-09T23:59:59",null,"1 x 6 hours","periodical","Catenary","","ST","","","D","","","","","","2.,4. bez TV, sudá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015669/20","Ostrava - Český Těšín","< >","Havířov","Albrechtice u Českého Těšína",2021,2021,2,3,"2021-01-13",null,"2021-01-22T23:59:59",null,"10 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015528/20","Ostrava - Český Těšín","< >","Ostrava-Svinov","Odra odb.",2021,2021,32,32,"2021-08-10",null,"2021-08-13T23:59:59",null,"4 x 10 hours","periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015587/20","Ostrava - Český Těšín","< >","Polanka nad Odrou výh.","Odra odb.",2021,2021,34,34,"2021-08-23",null,"2021-08-23T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015586/20","Praha - Choceň","< >","Pardubice hlavní nádraží","Přelouč",2021,2021,32,32,"2021-08-09",null,"2021-08-15T23:59:59",null,"7 days","continuous","Track & Rail","","LT","","","","","","B","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015585/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","Ostrava-Svinov",2021,2021,33,33,"2021-08-22",null,"2021-08-22T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","D","","","","","","2 jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015585/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Polanka nad Odrou výh.",2021,2021,33,33,"2021-08-22",null,"2021-08-22T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","D","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015585/20","Ostrava - Český Těšín","< >","Polanka nad Odrou výh.","Odra odb.",2021,2021,33,33,"2021-08-22",null,"2021-08-22T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","D","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015585/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","",2021,2021,33,33,"2021-08-22",null,"2021-08-22T23:59:59",null,"1 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","1.,3. jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015580/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","Ostrava-Svinov",2021,2021,33,33,"2021-08-21",null,"2021-08-21T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","","","","","","","1 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015580/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Polanka nad Odrou výh.",2021,2021,33,33,"2021-08-21",null,"2021-08-21T23:59:59",null,"1 x 10 hours","periodical","Catenary","T","LT","","","","","","","","","2 jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015578/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","Ostrava-Svinov",2021,2021,33,33,"2021-08-19",null,"2021-08-20T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015532/20","Ostrava - Český Těšín","< >","Ostrava-Svinov","Odra odb.",2021,2021,32,32,"2021-08-15",null,"2021-08-15T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","D","","","","","","traťová jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015577/20","Ostrava - Český Těšín","< >","Ostrava-Vítkovice","Odra odb.",2021,2021,33,33,"2021-08-18",null,"2021-08-18T23:59:59",null,"2 x 10 hours","periodical","Catenary","","LT","","","D","","","","","","traťová jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015577/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","Ostrava-Svinov",2021,2021,33,33,"2021-08-18",null,"2021-08-18T23:59:59",null,"1 x 10 hours","periodical","Catenary","","LT","","","D","","","","","","1 jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015577/20","Hranice na Moravě - Ostrava","< >","Ostrava-Svinov","Polanka nad Odrou výh.",2021,2021,33,33,"2021-08-18",null,"2021-08-18T23:59:59",null,"1 x 10 hours","periodical","Catenary","","LT","","","D","","","","","","2 + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015532/20","Ostrava - Český Těšín","< >","Odra odb.","",2021,2021,32,32,"2021-08-15",null,"2021-08-15T23:59:59",null,"1 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015577/20","Hranice na Moravě - Ostrava","< >","Polanka nad Odrou výh.","",2021,2021,33,33,"2021-08-18",null,"2021-08-18T23:59:59",null,"1 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-015518/20","Ostrava - Český Těšín","< >","Polanka nad Odrou výh.","Odra odb.",2021,2021,31,32,"2021-08-02",null,"2021-08-09T23:59:59",null,"8 x 10 hours","periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-014984/20","Praha - Hr. Králové - Choceň","< >","Poděbrady","Libice nad Cidlinou",2021,2021,44,45,"2021-11-05",null,"2021-11-10T23:59:59",null,"6 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-014990/20","Praha - Hr. Králové - Choceň","< >","Poděbrady","Libice nad Cidlinou",2021,2021,46,47,"2021-11-16",null,"2021-11-25T23:59:59",null,"10 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-014959/20","Praha - Hr. Králové - Choceň","< >","Libice nad Cidlinou","Poděbrady",2021,2021,39,40,"2021-09-28",null,"2021-10-08T23:59:59",null,"11 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-014970/20","Praha - Hr. Králové - Choceň","< >","Libice nad Cidlinou","Poděbrady",2021,2021,42,43,"2021-10-18",null,"2021-10-27T23:59:59",null,"10 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-014980/20","Praha - Hr. Králové - Choceň","< >","Libice nad Cidlinou","Poděbrady",2021,2021,44,44,"2021-11-01",null,"2021-11-04T23:59:59",null,"4 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-012314/20","Praha - Choceň","< >","Chrudim","Moravany",2021,2021,20,20,"2021-05-17",null,"2021-05-23T23:59:59",null,"7 days","continuous","Maintenance","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011658/19","Choceň - Hranice na Moravě","< >","Svitavy","Česká Třebová",2021,2021,25,25,"2021-06-22",null,"2021-06-24T23:59:59",null,"3 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011664/19","Choceň - Hranice na Moravě","< >","Svitavy","Česká Třebová",2021,2021,40,40,"2021-10-05",null,"2021-10-07T23:59:59",null,"3 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011126/19","Praha - Hr. Králové - Choceň","< >","Nymburk město","Veleliby",2021,2021,39,46,"2021-10-02",null,"2021-11-15T23:59:59",null,"45 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011125/19","Praha - Choceň","< >","Pečky","Plaňany",2021,2021,18,20,"2021-05-03",null,"2021-05-17T23:59:59",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011105/19","Praha - Choceň","< >","Přelouč","Prachovice",2021,2021,41,41,"2021-10-11",null,"2021-10-15T23:59:59",null,"5 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011012/19","Praha - Choceň","< >","Kostěnice","Pardubice hlavní nádraží",2021,2021,11,11,"2021-03-21",null,"2021-03-21T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011011/19","Praha - Choceň","< >","Pardubice hlavní nádraží","Kostěnice",2021,2021,11,11,"2021-03-20",null,"2021-03-20T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011008/19","Praha - Choceň","< >","Moravany","Kostěnice",2021,2021,11,11,"2021-03-18",null,"2021-03-18T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011007/19","Praha - Choceň","< >","Kostěnice","Moravany",2021,2021,11,11,"2021-03-17",null,"2021-03-17T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011005/19","Praha - Choceň","< >","Moravany","Kostěnice",2021,2021,11,11,"2021-03-16",null,"2021-03-16T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011004/19","Praha - Choceň","< >","Kostěnice","Moravany",2021,2021,11,11,"2021-03-15",null,"2021-03-15T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011003/19","Praha - Choceň","< >","Uhersko","Moravany",2021,2021,10,10,"2021-03-14",null,"2021-03-14T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-011002/19","Praha - Choceň","< >","Moravany","Uhersko",2021,2021,10,10,"2021-03-13",null,"2021-03-13T23:59:59",null,"1 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,54,"V-010997/19","Praha - Choceň","< >","Choceň","Zámrsk",2021,2021,10,14,"2021-03-12",null,"2021-04-05T23:59:59",null,"2 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","N","","2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,561812005,"Hranice na Moravě - Žilina","< >","Púchov","Považská Bystrica",2021,2021,1,38,"2021-01-01","00:00:00","2021-09-16",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,561812006,"Hranice na Moravě - Žilina","< >","Púchov","Považská Bystrica",2021,2021,38,51,"2021-09-16","00:00:00","2021-12-15",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562012001,"Hranice na Moravě - Žilina","< >","Považská Bystrica","Považská Bystrica",2021,2021,37,38,"2021-09-09","00:00:00","2021-09-16",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 1,3",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101001,"Hranice na Moravě - Žilina","< >","Púchov","Lúky pod Makytou",2021,2021,26,27,"2021-06-28","00:00:00","2021-07-05",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101002,"Hranice na Moravě - Žilina","< >","Púchov","Lúky pod Makytou",2021,2021,25,26,"2021-06-23","00:00:00","2021-06-28",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101003,"Hranice na Moravě - Žilina","< >","Lúky pod Makytou","Lúky pod Makytou št. hr.",2021,2021,9,21,"2021-03-01","00:00:00","2021-05-30",1,null,"periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1 (at need)",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101004,"Hranice na Moravě - Žilina","< >","Lúky pod Makytou","Lúky pod Makytou št. hr.",2021,2021,22,23,"2021-06-01","00:00:00","2021-06-10",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101005,"Hranice na Moravě - Žilina","< >","Lúky pod Makytou","Lúky pod Makytou št. hr.",2021,2021,26,27,"2021-06-28","00:00:00","2021-07-05",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101006,"Hranice na Moravě - Žilina","< >","Lúky pod Makytou","Lúky pod Makytou št. hr.",2021,2021,23,26,"2021-06-11","00:00:00","2021-06-28",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101007,"Český Těšín - Žilina","< >","Čadca št. hr.","Čadca",2021,2021,1,5,"2021-01-07","00:00:00","2021-02-07",1,null,"periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101008,"Žilina - Košice","< >","Poprad-Tatry","Svit",2021,2021,25,26,"2021-06-22","00:00:00","2021-06-28",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101009,"Žilina - Košice","< >","Poprad-Tatry","Svit",2021,2021,9,25,"2021-03-01","00:00:00","2021-06-21",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101010,"Žilina - Košice","< >","Svit","Svit",2021,2022,45,16,"2021-11-11","00:00:00","2022-04-20",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 2,4,6",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101011,"Žilina - Košice","< >","Svit","Výh. Lučivná",2021,2021,34,38,"2021-08-29","00:00:00","2021-09-21",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101012,"Žilina - Košice","< >","Svit","Výh. Lučivná",2021,2021,33,34,"2021-08-17","00:00:00","2021-08-28",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101013,"Žilina - Košice","< >","Svit","Výh. Lučivná",2021,2021,38,45,"2021-09-22","00:00:00","2021-11-10",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101014,"Žilina - Košice","< >","Svit","Štrba",2021,2021,26,27,"2021-06-29","00:00:00","2021-07-08",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101015,"Žilina - Košice","< >","Svit","Štrba",2021,2021,27,28,"2021-07-09","00:00:00","2021-07-16",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,56,562101016,"Žilina - Košice","< >","Svit","Svit",2022,2022,16,26,"2022-04-21","00:00:00","2022-06-29",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 1,3,5",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101017,"Žilina - Košice","< >","Svit","Svit",2022,2022,26,27,"2022-06-30","00:00:00","2022-07-07",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 2,4,6",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101018,"Žilina - Košice","< >","Svit","Výh. Lučivná",2022,2022,16,26,"2022-04-21","00:00:00","2022-06-29",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101019,"Žilina - Košice","< >","Svit","Výh. Lučivná",2022,2022,26,27,"2022-06-30","00:00:00","2022-07-07",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101020,"Žilina - Košice","< >","Svit","Štrba",2022,2022,27,27,"2022-07-08","00:00:00","2022-07-10",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562101021,"Žilina - Košice","< >","Svit","Štrba",2022,2022,28,28,"2022-07-11","00:00:00","2022-07-13",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,54551,"Salzburg - Wels","< >","Steindorf bei Straßwalchen","",2020,2021,49,27,"30.11.2020","08:00","10.07.2021","07:00","221 days + 22,0 h","continuous","Track & Rail","","ST","","","","C","","B","5,0,3","","Abtrag Gleise 406 +408 sowie Bstg 1\nNeuerrichtung Unterführung und Bstg 1","","Y","","16.12.2020","Unclassified",null,null,"",0,3,"","Published","","Y",1105,""]
[null,81,"60075A","Salzburg - Wels","< >","Steindorf bei Straßwalchen","Neumarkt am Wallersee",2020,2021,49,27,"30.11.2020","08:00","10.07.2021","07:00","221 days + 22,0 h","continuous","Miscellaneous","","LT","","","","C","","B","5,0,3","","Abtrag Gleise 406 +408 sowie Bstg 1\nNeuerrichtung Unterführung und Bstg 1","","Y","","10.12.2020","Unclassified",null,null,"",0,3,"","Published","","Y",1105,""]
[null,81,59938,"Linz - Wien","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2021,2021,5,8,"07.02.2021","01:00","22.02.2021","05:00","5x 4,0 h","periodical","Maintenance","T","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","","12.01.2021","Medium",null,null,"100%","","","","Published","","Y",90285,90288]
[null,81,59142,"Linz - Wien","< >","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,7,8,"20.02.2021","00:00","22.02.2021","04:00","2 days + 4,0 h","continuous","Catenary","","LT","","","","C","","B","","","Errichten von 4 Mastfundamente in herkömmlicher Art (Schalen, betonieren)\n2wege Bagger,","","Y","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1056,90784]
[null,81,58842,"Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2021,2021,8,8,"22.02.2021","23:00","26.02.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","","","","Drainagespülen Wachberg II mit OBW+Niederflurwagen","","Y","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",91055,1042]
[null,81,58854,"Linz - Wien","< >","Loosdorf","Pöchlarn",2021,2021,8,8,"27.02.2021","23:00","28.02.2021","04:30","5,5 h","continuous","Maintenance","T","LT","","","","C","","","","","Sonderinspektion Wachbergtunnel alt mit OBW;","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1040,1042]
[null,81,58843,"Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2021,2021,9,9,"01.03.2021","23:00","05.03.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","","","","Drainagespülen Melker Tunnel mit OBW+Niederflurwagen","","Y","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",91055,1042]
[null,81,58844,"Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2021,2021,10,10,"08.03.2021","23:00","12.03.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","","","","Drainagespülen Melker Tunnel mit OBW+Niederflurwagen","","Y","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",91055,1042]
[null,81,58872,"Linz - Wien","< >","Tullnerfeld-Ost","Abzw Knoten Hadersdorf",2021,2021,10,13,"12.03.2021","00:40","01.04.2021","05:10","21x 4,5 h","periodical","Maintenance","T","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","05.01.2021","Unclassified",null,null,"","","","","Published","","Y",90862,90280]
[null,81,58899,"Linz - Wien","< >","St.Valentin","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,11,12,"15.03.2021","00:00","26.03.2021","24:00","12 days","continuous","Track & Rail","T","LT","","","","C","","B","","","Tausch verharztes Schotterbett Siebergtunnel\nOstportal km 152,991 - km 153,028\nWestportal km 159,488 - km 159,525","","Y","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1061,90784]
[null,81,59250,"Linz - Wien","< >","Sbl Spw 2","St.Valentin",2021,2021,11,12,"15.03.2021","08:00","26.03.2021","20:00","11 days + 12,0 h","continuous","Track & Rail","T","LT","","","","C","","B","5,12,5","","GN Gleis 3 und 4 Portale Siebergtunnel","","Y","","16.12.2020","Unclassified",null,null,"",12,5,"","Published","","Y",90777,1061]
[null,81,60434,"München - Rosenheim - Salzburg ","< >","Teisendorf","Freilassing",2021,2021,12,12,"22.03.2021","21:20","23.03.2021","05:20","8,0 h","continuous","Switch","T","LT","","","","","","","","","Weichenerneuerung Inbetriebnahme WE Freilassing Umrüstung EKW-DKW in Freilassing",80,"N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",20203,13400]
[null,81,58873,"Linz - Wien","< >","Tullnerfeld-Ost","Abzw Knoten Hadersdorf",2021,2021,14,17,"06.04.2021","00:40","26.04.2021","05:10","21x 4,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",90862,90280]
[null,81,58845,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,14,14,"06.04.2021","23:00","09.04.2021","04:30","3x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,57751,"Linz - Wien","< >","Sbl Spw 2","Sbl Spw 5",2021,2021,15,17,"12.04.2021","22:30","02.05.2021","05:00","20x 6,5 h","periodical","Maintenance","T","LT","","","","C","","B","5,5,0","","Spülen und Fräsen Siebergtunnel","","N","","12.01.2021","Unclassified",null,null,"",5,0,"","Published","","Y",90776,90783]
[null,81,58846,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,15,15,"12.04.2021","23:00","16.04.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,57494,"Wels - Linz","< >","Linz Hbf Westbrücke","Untergaumberg",2021,2021,15,18,"16.04.2021","22:00","03.05.2021","04:30","16 days + 6,5 h","continuous","Track & Rail","T","LT","","","","","","","","","Herstellung Gleisanschluss \nWN W 418, 419","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",5914,5485]
[null,81,58847,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,16,16,"19.04.2021","23:00","23.04.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,58848,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,17,17,"26.04.2021","23:00","30.04.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,59143,"Linz - Wien","< >","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,18,18,"03.05.2021","22:40","08.05.2021","05:00","5x 6,3 h","periodical","Catenary","","LT","","","","","","","0,0,7","","Rammfundierung und Maststellen (28Stk) + Mastbolzen","","Y","","16.12.2020","Unclassified",null,null,"",0,7,"","Published","","Y",1056,90784]
[null,81,58892,"Linz - Wien","< >","Tullnerfeld","Abzww Knoten Wagram Nord",2021,2021,18,19,"03.05.2021","23:30","12.05.2021","05:00","9x 5,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1295,91052]
[null,81,58893,"Linz - Wien","< >","Tullnerfeld","Abzww Knoten Wagram Nord",2021,2021,20,20,"17.05.2021","23:30","21.05.2021","05:00","4x 5,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1295,91052]
[null,81,58304,"Wels - Linz","< >","Wels Hbf","",2021,2021,20,21,"21.05.2021","22:30","25.05.2021","04:00","3 days + 5,5 h","continuous","Switch","","ST","","","","C","","B","2,1,0","","WN W 67  und W 124","","N","","05.01.2021","Unclassified",null,null,"",1,0,"","Published","","Y",1081,""]
[null,81,"60450A","Wels - Linz","< >","Wels Hbf","Marchtrenk",2021,2021,20,21,"21.05.2021","22:30","25.05.2021","04:00","3 days + 5,5 h","continuous","Switch","","LT","","","","C","","B","2,1,0","","WN W 67  und W 124","","N","","05.01.2021","Unclassified",null,null,"",1,0,"","Published","","Y",1081,1079]
[null,81,57947,"Wels - Linz","< >","Pasching","Sbl Lz 3",2021,2021,21,23,"24.05.2021","21:30","12.06.2021","05:00","15x 7,5 h","periodical","Others","","LT","S","","","","","","","","Erneuerung Bstg","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1076,90513]
[null,81,58894,"Linz - Wien","< >","Tullnerfeld","Abzww Knoten Wagram Nord",2021,2021,21,21,"25.05.2021","23:30","30.05.2021","05:00","5x 5,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1295,91052]
[null,81,57716,"Wels - Linz","< >","Wels Hbf","",2021,2021,22,23,"04.06.2021","22:30","07.06.2021","04:30","2 days + 6,0 h","continuous","Switch","","ST","","","","C","","B","2,1,0","","WN W 65,66","","N","","05.01.2021","Unclassified",null,null,"",1,0,"","Published","","Y",1081,""]
[null,81,"60449A","Wels - Linz","< >","Wels Hbf","Marchtrenk",2021,2021,22,23,"04.06.2021","22:30","07.06.2021","04:30","2 days + 6,0 h","continuous","Switch","","LT","","","","C","","B","2,1,0","","WN W 65,66","","N","","05.01.2021","Unclassified",null,null,"",1,0,"","Published","","Y",1081,1079]
[null,81,54552,"Salzburg - Wels","< >","Steindorf bei Straßwalchen","Friedburg",2021,2021,27,37,"10.07.2021","05:00","13.09.2021","20:00","65 days + 15,0 h","continuous","Track & Rail","T","LT","","","","C","","B","","","GN mit Einsatz AHM, Ausbau AB W 1L,2L,1Fe und 1Bo sowie W 301\nEinschub Tragwerk Hainbachbrücke, Herstellung Unterbau Umbau Bf Friedburg - Gleis 722neu, Errichtung neuer Bstg. WN,","","Y","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1105,2041]
[null,81,57968,"Linz - Wien","< >","Üst Ams 2","",2021,2021,27,28,"10.07.2021","23:00","17.07.2021","04:00","6 days + 5,0 h","continuous","Catenary","T","ST","","","","C","","B","20,6,0","","Erneuerung der Oberleitung in der Üst Amstetten 2","","Y","","16.12.2020","Unclassified",null,null,"",6,0,"","Published","","Y",90044,""]
[null,81,58943,"Linz - Wien","< >","Amstetten","",2021,2021,27,28,"10.07.2021","23:00","17.07.2021","04:00","6 days + 5,0 h","continuous","Switch","T","ST","","","","","","","","","Weichenreinigung W 201,202,211,212,213","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1049,""]
[null,81,58946,"Linz - Wien","< >","Amstetten","",2021,2021,28,29,"17.07.2021","04:00","22.07.2021","04:00","5 days","continuous","Switch","T","ST","","","","","","","","","Weichenreinigung W 205,211,213","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1049,""]
[null,81,60035,"Wels - Linz","< >","Linz Wegscheid","Linz Hbf Westbrücke",2021,2021,29,29,"19.07.2021","07:00","25.07.2021","17:00","6 days + 10,0 h","continuous","Signal","","LT","","","","","","","5,1,1","","Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;","","N","","16.12.2020","Unclassified",null,null,"",1,1,"","Published","","Y",1600,5914]
[null,81,60032,"Wels - Linz","< >","Linz Hbf Westbrücke","Linz Wegscheid",2021,2021,30,30,"26.07.2021","07:00","01.08.2021","17:00","6 days + 10,0 h","continuous","Signal","","LT","","","","","","","5,1,1","","Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;","","N","","16.12.2020","Unclassified",null,null,"",1,1,"","Published","","Y",5914,1600]
[null,81,58947,"Linz - Wien","< >","Ybbs a.d.Donau","Abzw Knoten Karlsbach",2021,2021,31,34,"02.08.2021","23:00","23.08.2021","04:00","20 days + 5,0 h","continuous","Switch","T","LT","","","","","","","","","Weichentausch W1,2,3,4,5,6,54,57\nWeichenausbau: 58,59","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1045,90380]
[null,81,59147,"Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,35,36,"30.08.2021","22:40","10.09.2021","05:00","9x 6,3 h","periodical","Catenary","","LT","","","","","","","0,0,7","","Vorarmieren Oberleitungsmaste\nEinbau Trenner St. Peter-Seitenstetten","","Y","","16.12.2020","Unclassified",null,null,"",0,7,"","Published","","Y",91010,90784]
[null,81,58852,"Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2021,2021,35,35,"30.08.2021","23:00","03.09.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","","","","Drainagespülen Melker Tunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",91055,1042]
[null,81,58849,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,36,36,"06.09.2021","23:00","10.09.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,57959,"Linz - Wien","< >","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,36,38,"11.09.2021","00:00","20.09.2021","04:00","9 days + 4,0 h","continuous","Catenary","","LT","S","","","C","","B","10,0,0","","Erneuerung der Oberleitung auf Sgl 1 von km 145,100 bis km 147,200","","N","","16.12.2020","Unclassified",null,null,"",0,0,"","Published","","Y",1056,90784]
[null,81,59148,"Linz - Wien","< >","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,36,38,"11.09.2021","00:00","20.09.2021","04:00","9 days + 4,0 h","continuous","Catenary","","LT","","","","C","","B","","","Abtrag OL-Kette, alter Ausleger, alte Fundamente + verfüllen\nZiehen Altmasten\nZu Beginn der Sperre freischalten Bf. Sp 106 für 1 Stunde\nzusätzlich: 17/18.+18/19.22:40 - 05:00freischalten SpSG106 \n19/20. 22:40 - 05:00 freischalten SpSG106+206","","Y","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1056,90784]
[null,81,58850,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,37,37,"13.09.2021","23:00","17.09.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,58003,"Salzburg - Wels","< >","Attnang-Puchheim","Sbl At 1",2021,2021,37,38,"17.09.2021","22:00","20.09.2021","05:00","2 days + 7,0 h","continuous","Bridge","","LT","","","","C","","B","5,2,2","","Neubau Brücke","","N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",1091,90065]
[null,81,58851,"Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,38,38,"20.09.2021","23:00","24.09.2021","04:30","4x 5,5 h","periodical","Maintenance","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",1042,1045]
[null,81,58004,"Salzburg - Wels","< >","Attnang-Puchheim","Sbl At 1",2021,2021,38,39,"24.09.2021","22:00","27.09.2021","05:00","2 days + 7,0 h","continuous","Bridge","","LT","","","","C","","B","5,2,2","","Neubau Brücke","","N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",1091,90065]
[null,81,58853,"Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,39,39,"27.09.2021","22:30","01.10.2021","05:00","4x 6,5 h","periodical","Maintenance","T","LT","","","","C","","","","","Drainagespülen Grüntunnel mit OBW+Niederflurwagen","","N","","12.01.2021","Unclassified",null,null,"","","","","Published","","Y",91010,90784]
[null,81,58868,"Linz - Wien","< >","Loosdorf","Pöchlarn",2021,2021,39,39,"02.10.2021","23:30","03.10.2021","04:30","5,0 h","continuous","Maintenance","T","LT","","","","","","","","","Sonderinspektion Wachbergtunnel alt mit OBW","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1040,1042]
[null,81,57750,"Linz - Wien","< >","Sbl Spw 2","Sbl Spw 5",2021,2021,40,42,"04.10.2021","22:30","24.10.2021","05:00","20x 6,5 h","periodical","Maintenance","T","LT","","","","C","","B","5,5,0","","Spülen und Fräsen Siebergtunnel","","N","","12.01.2021","Unclassified",null,null,"",5,0,"","Published","","Y",90776,90783]
[null,81,58875,"Linz - Wien","< >","Tullnerfeld-Ost","Abzw Knoten Hadersdorf",2021,2021,40,42,"05.10.2021","00:40","22.10.2021","05:10","18x 4,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",90862,90280]
[null,81,58874,"Linz - Wien","< >","Tullnerfeld-Ost","Abzw Knoten Hadersdorf",2021,2021,44,46,"03.11.2021","00:40","20.11.2021","05:10","18x 4,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",90862,90280]
[null,81,57496,"Salzburg - Wels","< >","Steindorf bei Straßwalchen","Straßwalchen",2021,2021,45,47,"13.11.2021","08:00","26.11.2021","17:00","13 days + 9,0 h","continuous","Track & Rail","","LT","","","","C","","B","5,2,2","","GN mit PLV","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",1105,1104]
[null,81,57497,"Salzburg - Wels","< >","Steindorf bei Straßwalchen","",2021,2021,45,47,"13.11.2021","08:00","26.11.2021","17:00","13 days + 9,0 h","continuous","Track & Rail","","ST","","","","C","","B","5,2,2","","GN mit PLV","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",1105,""]
[null,81,58895,"Linz - Wien","< >","Tullnerfeld","Abzww Knoten Wagram Nord",2021,2021,47,49,"22.11.2021","23:30","10.12.2021","05:00","18x 5,5 h","periodical","Maintenance","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",1295,91052]
[null,81,57498,"Salzburg - Wels","< >","Seekirchen am Wallersee","Steindorf bei Straßwalchen",2021,2021,47,48,"27.11.2021","22:00","01.12.2021","22:00","4 days","continuous","Switch","","LT","","","","C","","B","5,3,3","","Schotterbetttausch W 201-204 Gl 1+2","","Y","","16.12.2020","Unclassified",null,null,"",3,3,"","Published","","Y",1110,1105]
[null,81,57499,"Salzburg - Wels","< >","Steindorf bei Straßwalchen","Seekirchen am Wallersee",2021,2021,48,49,"01.12.2021","22:00","06.12.2021","05:00","4 days + 7,0 h","continuous","Switch","","LT","","","","C","","B","5,3,3","","Tausch Schotterbett in der ÜSt Steindorf b.Stw 2","","Y","","16.12.2020","Unclassified",null,null,"",3,3,"","Published","","Y",1105,1110]
[null,81,58888,"Linz - Wien","< >","Wien Meidling","W.Mat.-Oswaldgasse",2021,2023,49,15,"12.12.2021","00:00","16.04.2023","24:00","491 days","continuous","Track & Rail","T","LT","","","","C","","B","","","zweigleisiger Ausbau - Sperre Oswaldschleife","","N","","07.01.2021","Major",null,null,"100%","","","","Planned","","Y",3107,1274]
[null,81,59529,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,4,5,"28.01.2022","23:00","31.01.2022","05:00","2 days + 6,0 h","continuous","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59530,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,5,6,"04.02.2022","23:00","07.02.2022","05:00","2 days + 6,0 h","continuous","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59531,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,5,6,"05.02.2022","20:00","07.02.2022","06:00","2x 10,0 h","periodical","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59532,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,6,7,"12.02.2022","20:00","14.02.2022","06:00","2x 10,0 h","periodical","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59533,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,7,8,"19.02.2022","20:00","21.02.2022","06:00","2x 10,0 h","periodical","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59534,"Salzburg - Wels","< >","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,8,9,"21.02.2022","22:00","28.02.2022","05:00","7x 7,0 h","periodical","Catenary","","LT","","","","C","","B","3,2,2","","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y","",1105]
[null,81,59339,"Salzburg - Wels","< >","Lambach","Stadl-Paura",2022,2022,11,11,"15.03.2022","07:00","18.03.2022","17:00","3 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","GN","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1086,1881]
[null,81,59414,"Wels - Linz","< >","Linz Hbf","Linz Gaumberg",2022,2022,12,12,"21.03.2022","00:00","24.03.2022","24:00","4 days","continuous","Track & Rail","","LT","","","","","","","","","Anbindung Gleis 2 (Gleis 4Neu)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1073,5984]
[null,81,59415,"Wels - Linz","< >","Linz Gaumberg","Linz Hbf",2022,2022,12,13,"25.03.2022","00:00","29.03.2022","06:00","4 days + 5,0 h","continuous","Track & Rail","","LT","","","","","","","","","Anbindung Gleis 1 (Gleis 3Neu)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",5984,1073]
[null,81,59416,"Wels - Linz","< >","Linz Hbf","Marchtrenk",2022,2022,12,13,"25.03.2022","22:00","29.03.2022","05:00","4x 7,0 h","periodical","Signal","","LT","","","","","","","","","IB ESTW Hörsching","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1073,1079]
[null,81,59586,"Wels - Linz","< >","Hörsching","",2022,2022,12,13,"26.03.2022","22:00","29.03.2022","05:00","2 days + 6,0 h","continuous","Signal","","ST","S","","","","","","","","IB ESTW Hörsching - aufgehobene Signalabhängigkeit\nmit Sicherheitserprobung","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1077,""]
[null,81,59869,"Wels - Linz","< >","Sbl Lz 3","Hörsching",2022,2022,12,12,"26.03.2022","22:00","27.03.2022","05:00","6,0 h","continuous","Signal","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 1 (Gl 2 Lz-Hoe)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90513,1077]
[null,81,59870,"Wels - Linz","< >","Hörsching","Marchtrenk",2022,2022,12,12,"27.03.2022","05:00","27.03.2022","22:00","17,0 h","continuous","Signal","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 2 (Gl 2 Lz-Mak)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1077,1079]
[null,81,59871,"Wels - Linz","< >","Hörsching","Sbl Lz 3",2022,2022,12,13,"27.03.2022","22:00","28.03.2022","17:00","19,0 h","continuous","Signal","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 3 (Gl 1 Hoe-Lz)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1077,90513]
[null,81,59872,"Wels - Linz","< >","Hörsching","Sbl Hoe 1",2022,2022,13,13,"28.03.2022","17:00","29.03.2022","05:00","12,0 h","continuous","Signal","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 4 (Gl 1 Hoe-Mak)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1077,90329]
[null,81,59671,"Linz - Wien","< >","Sbl Spw 5","Sbl Spw 2",2022,2022,12,14,"21.03.2022","22:30","10.04.2022","05:00","15x 6,5 h","periodical","Tunnel","T","LT","","","","C","","B","6,4,0","","Kanalspülen","","N","","16.12.2020","Unclassified",null,null,"",4,0,"","Planned","","Y",90782,90776]
[null,81,59587,"Salzburg - Wels","< >","Gunskirchen","",2022,2022,12,12,"26.03.2022","22:00","27.03.2022","05:00","6,0 h","continuous","Signal","","ST","S","","","C","","B","","","IB ESTW Bf Gunskirchen - aufgehobenen Signalabhängigkeit mit Sicherheitserprobung","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1085,""]
[null,81,59232,"Linz - Wien","< >","Prinzersdorf","",2022,2022,14,17,"09.04.2022","00:00","25.04.2022","04:00","16 days + 4,0 h","continuous","Switch","","ST","","","","C","","B","","","Weichentausch W 52,53,54,55,56,57","","Y","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1037,""]
[null,81,59226,"Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,15,17,"15.04.2022","01:00","25.04.2022","04:00","10 days + 3,0 h","continuous","Miscellaneous","T","LT","","","","C","","B","","","Sankt Peter-Seitenstetten: Schotterbettreinigung W 6,7,52,54,  \nErrichtung Grabenmauer km 145,260-146,500\nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",91010,1061]
[null,81,59228,"Linz - Wien","< >","St.Peter-Seitenstetten","Üst Spw 13",2022,2022,17,18,"25.04.2022","01:00","05.05.2022","04:00","10 days + 3,0 h","continuous","Miscellaneous","","LT","","","","C","","B","","","Errichtung Grabenmauer km 145,260-146,500\nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1056,90269]
[null,81,59861,"Wels - Linz","< >","Marchtrenk","Wels Hbf",2022,2022,17,19,"25.04.2022","08:00","11.05.2022","18:00","16 days + 10,0 h","continuous","Track & Rail","","LT","","","","C","","B","10,2,3","","GN","","Y","","16.12.2020","Unclassified",null,null,"",2,3,"","Planned","","Y",1079,1081]
[null,81,59328,"Wels - Linz","< >","Üst Lz 2","Hörsching",2022,2022,17,19,"25.04.2022","21:30","12.05.2022","05:00","15x 7,5 h","periodical","Others","","LT","S","","","","","","","","Erneuerung Bstg in Pasching","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90515,1077]
[null,81,58903,"München - Rosenheim - Salzburg ","< >","Traunstein","Freilassing",2022,2022,21,31,"25.05.2022","00:00","06.08.2022","24:00","74 days","continuous","Track & Rail","","LT","","","","","","","1,3,1","","GN Traunstein - Lauter, ÜST Rückstetten - Teisendorf, Üst Rumgraben - Traunstein\nNeubau ÜST Straß",80,"N","","16.12.2020","Unclassified",null,null,"",3,1,"","Planned","","Y",20314,13400]
[null,81,59673,"Wels - Linz","< >","Marchtrenk","",2022,2022,27,33,"09.07.2022","08:00","16.08.2022","18:00","38 days + 10,0 h","continuous","Track & Rail","","ST","","","","C","","B","","","Verschwenkung Gleis 4 - Errichtung prov. Bahnsteig 1\nEinbau W 49P","","Y","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,""]
[null,81,59855,"Wels - Linz","< >","Marchtrenk","",2022,2022,32,32,"12.08.2022","21:00","14.08.2022","05:00","1 day + 8,0 h","continuous","Switch","","ST","","","","C","","B","2,2,2","","Einbau W 49P - Ausbau W7","","Y","","16.12.2020","Unclassified",null,null,"",2,2,"","Planned","","Y",1079,""]
[null,81,59867,"Wels - Linz","< >","Wels Hbf","",2022,2022,32,32,"12.08.2022","21:00","13.08.2022","05:00","8,0 h","continuous","Signal","","ST","","","","C","","B","","","IB ESTW Migration - Phase 7 (Gleis 1 We-Mak)","","Y","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1081,""]
[null,81,59864,"Wels - Linz","< >","Marchtrenk","Wels Hbf",2022,2022,32,32,"13.08.2022","09:00","13.08.2022","17:00","8,0 h","continuous","Signal","","LT","S","","","C","","B","","","IB ESTW Marchtrenk - Phase 2 (Gleis 2 Mak-We)","","Y","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,1081]
[null,81,59863,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2022,2022,32,32,"13.08.2022","21:00","14.08.2022","05:00","8,0 h","continuous","Signal","","LT","S","","","C","","B","10,8,5","","IB ESTW Marchtrenk - Phase 3 (Gleis 2 Mak-Hoe)","","Y","","16.12.2020","Unclassified",null,null,"",8,5,"","Planned","","Y",1079,90330]
[null,81,59589,"Wels - Linz","< >","Marchtrenk","",2022,2022,32,33,"13.08.2022","22:00","16.08.2022","05:00","2 days + 7,0 h","continuous","Signal","","ST","S","","","","","","","","IB ESTW Marchtrenk - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,""]
[null,81,59862,"Wels - Linz","< >","Marchtrenk","Hörsching",2022,2022,32,32,"14.08.2022","09:00","14.08.2022","17:00","8,0 h","continuous","Signal","","LT","S","","","C","","B","10,8,5","","IB ESTW Marchtrenk - Phase 4 (Gleis 1 Mak-Hoe)","","Y","","16.12.2020","Unclassified",null,null,"",8,5,"","Planned","","Y",1079,1077]
[null,81,60030,"Wels - Linz","< >","Marchtrenk","",2022,2022,32,33,"14.08.2022","17:00","15.08.2022","05:00","12,0 h","continuous","Switch","","ST","S","","","","","","","","Einbau Weiche 34P","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,""]
[null,81,59866,"Wels - Linz","< >","Wels Vbf-Terminal","Marchtrenk",2022,2022,33,33,"15.08.2022","09:00","15.08.2022","17:00","8,0 h","continuous","Signal","T","LT","S","","","","","","","","IB ESTW Marchtrenk - Phase 6 (Überwurfgleis Wei)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1968,1079]
[null,81,59868,"Wels - Linz","< >","Wels Vbf-Terminal","Marchtrenk",2022,2022,33,33,"15.08.2022","09:00","15.08.2022","17:00","8,0 h","continuous","Signal","T","LT","S","","","","","","","","IB ESTW Marchtrenk - Phase 6 (Überwurfgleis Wei)","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1968,1079]
[null,81,59227,"Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,28,29,"11.07.2022","04:00","18.07.2022","04:00","7 days","continuous","Switch","T","LT","","","","C","","B","0,9,0","","SpW1: Schotterbettreinigung W104,105,106,107,108","","N","","16.12.2020","Unclassified",null,null,"",9,0,"","Planned","","Y",91010,1061]
[null,81,59221,"Linz - Wien","< >","Amstetten","Abzw Knoten St.Peter-Seitenstetten West",2022,2022,29,30,"18.07.2022","01:00","27.07.2022","04:00","9 days + 3,0 h","continuous","Switch","T","LT","","","","C","","B","0,9,0","","Üst Ams2: Weichentausch W401,402,403,404 inkl. Schottertausch\nKtn. Spo: Schotterbettreinigung W10, Abtrag W13,14\nWest200","","N","","16.12.2020","Unclassified",null,null,"",9,0,"","Planned","","Y",1049,90784]
[null,81,60055,"Wels - Linz","< >","Abzw Mak 1","Wels Vbf-Einfgr",2022,2022,33,49,"16.08.2022","00:00","07.12.2022","24:00","114 days + 1,0 h","continuous","Track & Rail","T","LT","","","","","","","","","4gleisiger Ausbau Linz - Wels\nIm Bf Wels Vbf Rückbau der \nGleise  924, 104-504, 106-506, 508","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90533,5839]
[null,81,59672,"Linz - Wien","< >","Sbl Spw 5","Sbl Spw 2",2022,2022,40,42,"03.10.2022","22:30","23.10.2022","05:00","15x 6,5 h","periodical","Tunnel","T","LT","","","","C","","B","6,4,0","","Kanalspülen","","N","","16.12.2020","Unclassified",null,null,"",4,0,"","Planned","","Y",90782,90776]
[null,81,59329,"Salzburg - Wels","< >","Gunskirchen","",2022,2022,41,42,"14.10.2022","08:00","17.10.2022","04:30","2 days + 20,5 h","continuous","Track & Rail","","ST","","","","C","","B","","","GN","","Y","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1085,""]
[null,81,59845,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2022,2022,41,42,"14.10.2022","22:00","17.10.2022","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","","","","","","LM 22 - Einbau  Hib","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,90330]
[null,81,59846,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2022,2022,43,44,"30.10.2022","22:00","02.11.2022","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","","","","","","LM 22 Einbau  Hib","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",1079,90330]
[null,81,58804,"Wels - Linz","< >","Marchtrenk","",2022,2022,44,45,"04.11.2022","22:00","07.11.2022","04:00","2 days + 6,0 h","continuous","Bridge","","ST","","","","C","","B","15,5,10","","LM 22 - Einbau Hib","","N","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,""]
[null,81,59485,"Salzburg - Wels","< >","Straßwalchen","Steindorf bei Straßwalchen",2022,2022,44,46,"04.11.2022","22:00","14.11.2022","05:00","9 days + 7,0 h","continuous","Track & Rail","","LT","S","","","C","","B","15,5,5","","GN mit PLV","","N","","16.12.2020","Unclassified",null,null,"",5,5,"","Planned","","Y",1104,1105]
[null,81,58792,"Wels - Linz","< >","Sbl Hoe 2","Marchtrenk",2023,2023,7,7,"17.02.2023","22:00","18.02.2023","24:00","1 day + 2,0 h","continuous","Track & Rail","","LT","","","","C","","B","15,5,10","","LM19 - Hebung Gleis mit OL um ca. 20cm","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",90330,1079]
[null,81,58793,"Wels - Linz","< >","Marchtrenk","Hörsching",2023,2023,7,8,"19.02.2023","00:00","20.02.2023","04:00","1 day + 4,0 h","continuous","Track & Rail","","LT","","","","C","","B","15,5,10","","LM19 - Hebung Gleis mit OL um ca. 20cm","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,1077]
[null,81,58795,"Wels - Linz","< >","Sbl Hoe 2","Marchtrenk",2023,2023,8,9,"24.02.2023","22:00","27.02.2023","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","C","","B","15,5,10","","Einbau Hib LM19","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",90330,1079]
[null,81,58809,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2023,2023,9,10,"03.03.2023","22:00","06.03.2023","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","C","","B","15,5,10","","Einbau Hib LM19","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,90330]
[null,81,58799,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2023,2023,10,11,"10.03.2023","22:00","13.03.2023","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","C","","B","15,5,10","","LM 21 Einbau Hib\nLM 22 Ausbau  Hib","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,90330]
[null,81,58798,"Wels - Linz","< >","Marchtrenk","Sbl Hoe 2",2023,2023,11,12,"17.03.2023","22:00","20.03.2023","04:00","2 days + 6,0 h","continuous","Bridge","","LT","","","","C","","B","15,5,10","","LM 21 - Einbau Hib\nLM 22 - Ausbau  Hib","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,90330]
[null,81,58806,"Wels - Linz","< >","Marchtrenk","",2023,2023,27,28,"07.07.2023","22:00","10.07.2023","04:00","2 days + 6,0 h","continuous","Bridge","","ST","","","","C","","B","15,5,10","","LM 21 Ausbau  Hib","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,""]
[null,81,58807,"Wels - Linz","< >","Marchtrenk","",2023,2023,28,29,"14.07.2023","22:00","17.07.2023","04:00","2 days + 6,0 h","continuous","Bridge","","ST","","","","C","","B","15,5,10","","LM 21 Ausbau  Hib","","Y","","16.12.2020","Unclassified",null,null,"",5,10,"","Planned","","Y",1079,""]
[null,81,59202,"Regensburg - Wels","< >","Grieskirchen-Gallspach","Obertrattnach-M Hofk",2021,2021,8,9,"26.02.2021","20:00","01.03.2021","05:00","2 days + 9,0 h","continuous","Track & Rail","","LT","S","","","","","","5,2,5","","Gleissanierung im Bereich von 5 Durchlässen",80,"N","","16.12.2020","Unclassified",null,null,"",2,5,"","Published","","Y",1726,1727]
[null,81,59203,"Regensburg - Wels","< >","Grieskirchen-Gallspach","Obertrattnach-M Hofk",2021,2021,9,10,"05.03.2021","20:00","08.03.2021","05:00","2 days + 9,0 h","continuous","Track & Rail","","LT","S","","","","","","5,2,5","","Gleissanierung im Bereich von 5 Durchlässen\n\nverschoben SAE von 2020 auf  2022 - \n30.04.20 vorgezogen auf 2021 (Anlagenzustand)",80,"N","","16.12.2020","Unclassified",null,null,"",2,5,"","Published","","Y",1726,1727]
[null,81,57906,"Regensburg - Wels","< >","Üst Neu 1","Riedau",2021,2021,10,11,"12.03.2021","07:00","15.03.2021","12:00","3 days + 5,0 h","continuous","Track & Rail","","LT","S","","","","","","5,2,2","","Schotterbetttausch auf Brücke",80,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",90588,1733]
[null,81,57905,"Regensburg - Wels","< >","Üst Neu 1","Riedau",2021,2021,11,12,"19.03.2021","07:00","22.03.2021","12:00","3 days + 5,0 h","continuous","Track & Rail","","LT","S","","","","","","5,2,2","","Schotterbetttausch auf Brücke",80,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",90588,1733]
[null,81,59244,"Regensburg - Wels","< >","Andorf","",2021,2021,18,20,"08.05.2021","07:00","22.05.2021","17:00","14 days + 10,0 h","continuous","Track & Rail","","ST","S","","","","","","","","GN",80,"N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",1736,""]
[null,81,"60417A","Regensburg - Wels","< >","Abzww Str 20602","Schärding",2021,2021,23,25,"07.06.2021","07:15","27.06.2021","17:00","20 days + 9,8 h","continuous","Miscellaneous","T","LT","","","","C","","B","","","Gesamtsperre",80,"N","","05.01.2021","Unclassified",null,null,"","","","","Published","","Y",90740,1740]
[null,81,57908,"Regensburg - Wels","< >","Üst Neu 1","Neumarkt-Kallham",2021,2021,23,25,"10.06.2021","07:00","26.06.2021","17:00","17x 10,0 h","periodical","Others","","LT","","","","","","","5,0,1","","Erneuerung Bahnsteig",80,"N","","16.12.2020","Unclassified",null,null,"",0,1,"","Published","","Y",90588,1729]
[null,81,57907,"Regensburg - Wels","< >","Neumarkt-Kallham","Üst Neu 1",2021,2021,26,29,"03.07.2021","07:00","21.07.2021","17:00","19x 10,0 h","periodical","Others","","LT","","","","","","","5,0,1","","Erneuerung Bahnsteig",80,"N","","16.12.2020","Unclassified",null,null,"",0,1,"","Published","","Y",1729,90588]
[null,81,"60645A","Regensburg - Wels","< >","Abzww Str 20602","Schärding",2022,2022,39,40,"26.09.2022","08:00","09.10.2022","18:00","13 days + 10,0 h","continuous","Track & Rail","T","LT","","","","C","","B","","","GA",80,"Y","","14.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90740,1740]
[null,81,60234,"Parndorf - Hegyeshalom","< >","Zurndorf","",2021,2021,9,9,"06.03.2021","23:30","07.03.2021","04:30","5,0 h","continuous","Signal","T","ST","","","","C","","B","","","Versetzen von Signalen",55,"Y","","07.01.2021","Unclassified",null,null,"","","","","Published","","Y",2978,""]
[null,81,59626,"Wien - Parndorf","< >","Grillgasse","",2021,2021,11,11,"15.03.2021","08:00","19.03.2021","14:20","5x 6,3 h","periodical","Miscellaneous","","ST","","","","C","","B","20,2,5","","Barrierefreiheit","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2961,""]
[null,81,60127,"Wien - Parndorf","< >","Wien Zvbf-Einfgr","Abzww Zur",2021,2021,12,12,"27.03.2021","18:00","28.03.2021","17:00","22,0 h","continuous","Track & Rail","","LT","","","","","","","","","Vorarbeiten für Gleisneulage Gl 260+270 und Weichenneulage DKW 175/176 sowie W 170","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",4530,90997]
[null,81,60128,"Wien - Parndorf","< >","Wien Zvbf-Einfgr","Abzww Zur",2021,2021,13,13,"29.03.2021","07:00","02.04.2021","17:00","5x 10,0 h","periodical","Track & Rail","","LT","","","","","","","","","Vorarbeiten für Gleisneulage Gl 260+270 und Weichenneulage DKW 175/176 sowie W 170","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",4530,90997]
[null,81,59628,"Wien - Parndorf","< >","Grillgasse","",2021,2021,13,13,"29.03.2021","23:30","04.04.2021","04:30","6x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,0,5","","Vorarbeiten","","N","","07.01.2021","Unclassified",null,null,"",0,5,"","Published","","Y",2961,""]
[null,81,59288,"Wien - Parndorf","< >","Wien Zvbf-Einfgr","Abzww Zur",2021,2021,13,14,"03.04.2021","07:00","06.04.2021","17:00","3 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Gleisneulage Gl 260+270 und Weichenneulage DKW 175/176 sowie W 170","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",4530,90997]
[null,81,59627,"Wien - Parndorf","< >","Grillgasse","",2021,2021,14,16,"05.04.2021","08:00","25.04.2021","14:20","21x 6,3 h","periodical","Miscellaneous","","ST","","","","","","","20,2,5","","Barrierefreiheit","","N","","12.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2961,""]
[null,81,60129,"Wien - Parndorf","< >","Wien Zvbf-Einfgr","Abzww Zur",2021,2021,14,14,"07.04.2021","07:00","09.04.2021","17:00","3x 10,0 h","periodical","Track & Rail","","LT","","","","","","","","","Nacharbeiten für Gleisneulage Gl 260+270 und Weichenneulage DKW 175/176 sowie W 170","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",4530,90997]
[null,81,60130,"Wien - Parndorf","< >","Wien Zvbf-Einfgr","Abzww Zur",2021,2021,14,14,"10.04.2021","07:00","11.04.2021","17:00","1 day + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Nacharbeiten für Gleisneulage Gl 260+270 und Weichenneulage DKW 175/176 sowie W 170","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",4530,90997]
[null,81,59292,"Wien - Parndorf","< >","Kledering","Lanzendorf-Rannersdorf",2021,2021,15,15,"12.04.2021","07:00","18.04.2021","17:00","6 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Gleisneulage Gl 542, 532, 533, 521 sowie Weichenneulage W536 +537","","N","","16.12.2020","Unclassified",null,null,"","","","","Published","","Y",2963,2964]
[null,81,59649,"Parndorf - Hegyeshalom","< >","Parndorf Ort","Zurndorf",2021,2021,15,15,"12.04.2021","07:50","16.04.2021","12:30","5x 4,7 h","periodical","Catenary","","LT","","","","C","","B","20,2,2","","Tragseiltausch",55,"Y","","07.01.2021","Unclassified",null,null,"",2,2,"","Published","","Y",2975,2978]
[null,81,59174,"Parndorf - Bratislava","< >","Parndorf","Kittsee",2021,2021,15,15,"12.04.2021","07:50","16.04.2021","12:30","5x 4,7 h","periodical","Maintenance","T","LT","","","","C","","B","","","Instandsetzungsarbeiten",56,"N","","07.01.2021","Unclassified",null,null,"","","","","Published","","Y",2976,3002]
[null,81,59651,"Parndorf - Hegyeshalom","< >","Parndorf","Zurndorf",2021,2021,16,16,"21.04.2021","08:00","23.04.2021","15:00","3x 7,0 h","periodical","Catenary","","LT","","","","","","","20,2,2","","Tragseiltausch",55,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",2976,2978]
[null,81,59652,"Parndorf - Hegyeshalom","< >","Parndorf","Zurndorf",2021,2021,17,17,"26.04.2021","08:00","30.04.2021","15:00","5x 7,0 h","periodical","Catenary","","LT","","","","","","","20,2,2","","Tragseiltausch",55,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",2976,2978]
[null,81,59632,"Wien - Parndorf","< >","Grillgasse","",2021,2021,17,17,"26.04.2021","23:30","30.04.2021","04:30","4x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,2,5","","Barrierefreiheit","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2961,""]
[null,81,59653,"Parndorf - Hegyeshalom","< >","Parndorf","Zurndorf",2021,2021,18,18,"03.05.2021","08:00","04.05.2021","15:00","2x 7,0 h","periodical","Catenary","","LT","","","","","","","20,2,2","","Tragseiltausch",55,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",2976,2978]
[null,81,59629,"Wien - Parndorf","< >","Grillgasse","",2021,2021,18,18,"03.05.2021","23:30","07.05.2021","04:30","4x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,0,5","","Vorarbeiten","","N","","07.01.2021","Unclassified",null,null,"",0,5,"","Published","","Y",2961,""]
[null,81,59650,"Parndorf - Hegyeshalom","< >","Parndorf Ort","Zurndorf",2021,2021,18,19,"07.05.2021","23:00","11.05.2021","04:30","4x 5,5 h","periodical","Catenary","","LT","","","","","","","20,2,2","","Tragseiltausch",55,"N","","16.12.2020","Unclassified",null,null,"",2,2,"","Published","","Y",2975,2978]
[null,81,59633,"Wien - Parndorf","< >","Grillgasse","",2021,2021,19,20,"10.05.2021","23:30","22.05.2021","04:30","12x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,0,5","","Barrierefreiheit","","N","","07.01.2021","Unclassified",null,null,"",0,5,"","Published","","Y",2961,""]
[null,81,59455,"Wien - Parndorf","< >","Kledering","Himberg",2021,2021,20,21,"23.05.2021","21:15","25.05.2021","04:30","2x 7,2 h","periodical","Bridge","","LT","","","","","","","20,3,5","","Ausheben Steg","","N","","07.01.2021","Unclassified",null,null,"",3,5,"","Published","","Y",2963,2966]
[null,81,59630,"Wien - Parndorf","< >","Grillgasse","",2021,2021,21,22,"25.05.2021","23:30","06.06.2021","04:30","12x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,0,5","","Vorarbeiten","","N","","07.01.2021","Unclassified",null,null,"",0,5,"","Published","","Y",2961,""]
[null,81,59631,"Wien - Parndorf","< >","Grillgasse","",2021,2021,23,24,"12.06.2021","23:30","14.06.2021","04:30","2x 5,0 h","periodical","Miscellaneous","","ST","","","","","","","20,0,5","","Vorarbeiten","","N","","07.01.2021","Unclassified",null,null,"",0,5,"","Published","","Y",2961,""]
[null,81,58273,"Wien - Parndorf","< >","Grillgasse","",2021,2021,25,33,"26.06.2021","08:00","20.08.2021","17:00","55 days + 9,0 h","continuous","Miscellaneous","","ST","","","","C","","B","20,2,5","","Barrierefreiheit","","Y","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2961,""]
[null,81,58272,"Wien - Parndorf","< >","Grillgasse","",2021,2021,33,35,"20.08.2021","17:00","05.09.2021","16:00","15 days + 23,0 h","continuous","Miscellaneous","","ST","","","","C","","B","20,2,5","","Barrierefreiheit","","Y","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2961,""]
[null,81,59175,"Parndorf - Bratislava","< >","Kittsee","Parndorf",2021,2021,38,38,"20.09.2021","07:50","24.09.2021","12:30","5x 4,7 h","periodical","Maintenance","T","LT","","","","C","","B","","","Instandsetzungsarbeiten",56,"N","","08.01.2021","Unclassified",null,null,"","","","","Published","","Y",3002,2976]
[null,81,59769,"Wien - Parndorf","< >","Himberg","",2021,2021,41,42,"15.10.2021","23:20","18.10.2021","04:30","2 days + 5,2 h","continuous","Catenary","","ST","","","","C","","B","20,2,5","","Bohrpfahlherstellung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2966,""]
[null,81,59770,"Wien - Parndorf","< >","Himberg","",2021,2021,42,43,"23.10.2021","23:20","27.10.2021","04:30","3 days + 5,2 h","continuous","Bridge","","ST","","","","C","","B","20,2,5","","Einbau Hilfsbrücke","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Published","","Y",2966,""]
[null,81,59824,"Wien - Parndorf","< >","Himberg","",2022,2022,14,16,"08.04.2022","22:00","19.04.2022","04:00","10 days + 6,0 h","continuous","Track & Rail","","ST","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,""]
[null,81,59360,"Wien - Parndorf","< >","Wien Zvbf","Kledering",2022,2022,15,16,"16.04.2022","07:00","19.04.2022","14:00","3 days + 7,0 h","continuous","Switch","","LT","","","","","","","","","Weichenneulage W 450, DKW 453/454, DKW 455/456","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",2962,2963]
[null,81,59825,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2022,2022,16,21,"19.04.2022","05:00","23.05.2022","05:00","34 days","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,59826,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2022,2022,21,24,"23.05.2022","05:00","13.06.2022","05:00","21 days","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,59827,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2022,2022,22,23,"04.06.2022","22:00","07.06.2022","05:00","2 days + 7,0 h","continuous","Switch","","LT","","","","C","","B","30,2,5","","Unterbausanierung W 56","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,59829,"Wien - Parndorf","< >","Lanzendorf-Rannersdorf","Himberg",2022,2022,36,40,"09.09.2022","05:00","03.10.2022","05:00","24 days","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2964,2966]
[null,81,59828,"Wien - Parndorf","< >","Lanzendorf-Rannersdorf","Himberg",2022,2022,36,37,"09.09.2022","22:00","12.09.2022","05:00","2 days + 7,0 h","continuous","Switch","","LT","","","","C","","B","30,2,5","","Unterbausanierung W 2 in Himberg","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2964,2966]
[null,81,59354,"Wien - Parndorf","< >","Abzww Zur","Wien Zvbf",2022,2022,37,38,"12.09.2022","07:00","25.09.2022","17:00","13 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Gleisneulage","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90997,2962]
[null,81,59830,"Wien - Parndorf","< >","Lanzendorf-Rannersdorf","Himberg",2022,2022,40,43,"03.10.2022","05:00","24.10.2022","05:00","21 days","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2964,2966]
[null,81,59823,"Wien - Parndorf","< >","Wien Zvbf","Abzww Zur",2022,2022,45,46,"07.11.2022","07:00","20.11.2022","17:00","13 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Gleisneulage","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",2962,90997]
[null,81,59356,"Wien - Parndorf","< >","Abzww Zur","Wien Zvbf",2022,2022,48,49,"28.11.2022","07:00","11.12.2022","17:00","13 days + 10,0 h","continuous","Track & Rail","","LT","","","","","","","","","Gleisneulage","","N","","16.12.2020","Unclassified",null,null,"","","","","Planned","","Y",90997,2962]
[null,81,59831,"Wien - Parndorf","< >","Himberg","",2023,2023,14,14,"09.04.2023","00:00","09.04.2023","06:00","6,0 h","continuous","Signal","T","ST","","","","C","","B","","","Inbetriebnahme ESTW neu","","Y","","07.01.2021","Unclassified",null,null,"","","","","Planned","","Y",2966,""]
[null,81,59833,"Wien - Parndorf","< >","Himberg","",2023,2023,36,41,"09.09.2023","07:00","13.10.2023","22:00","34 days + 15,0 h","continuous","Track & Rail","","ST","","","","C","","B","30,2,5","","Unterbausanierung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,""]
[null,81,59834,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2023,2023,41,43,"13.10.2023","22:00","25.10.2023","22:00","12 days","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Anschwenkungen","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,59835,"Wien - Parndorf","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,43,44,"25.10.2023","22:00","01.11.2023","01:00","6 days + 4,0 h","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Anschwenkungen Sgl 2 an Gleis 4-neu","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2964,2968]
[null,81,59832,"Wien - Parndorf","< >","Himberg","",2023,2023,44,44,"01.11.2023","00:00","01.11.2023","06:00","6,0 h","continuous","Signal","T","ST","","","","C","","B","","","Inbetriebnahme ESTW neu","","Y","","07.01.2021","Unclassified",null,null,"","","","","Planned","","Y",2966,""]
[null,81,59836,"Wien - Parndorf","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,44,44,"01.11.2023","06:00","03.11.2023","05:00","1 day + 23,0 h","continuous","Switch","","LT","","","","C","","B","30,2,5","","Einbau W 1-neu und anbinden an Bgl 2","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2964,2968]
[null,81,59837,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2023,2023,44,45,"01.11.2023","06:00","06.11.2023","05:00","4 days + 23,0 h","continuous","Track & Rail","","LT","","","","C","","B","30,2,5","","Anschwenken Bgl 2 an Sgl 1 Ri Gn","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,59838,"Wien - Parndorf","< >","Himberg","Gramatneusiedl",2023,2023,45,46,"06.11.2023","05:00","18.11.2023","17:30","12 days + 12,5 h","continuous","Signal","","LT","","","","C","","B","30,2,5","","Hauptverkabelung","","N","","07.01.2021","Unclassified",null,null,"",2,5,"","Planned","","Y",2966,2968]
[null,81,"57913","Wels - Traun - Linz","< >","Marchtrenk","Rutzing",{"$f":"YEAR(L1079)","v":2021},{"$f":"YEAR(N1079)","v":2021},{"$f":"WEEKNUM(L1079,2)","v":43},{"$f":"WEEKNUM(N1079,2)","v":44},"2021-10-23","07:00","2021-10-29","17:00","6 days + 10,0 h","continuous","Track & Rail",null,"LT+ST",null,null,null,null,null,null,null,null,"Gleissanierung - WN W 1F, W 1S",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,81,"59413","Wels - Linz","< >","Linz Hbf","Marchtrenk",2022,2022,13,14,"2022-03-21","00:00","2022-03-29","06:00","8 days + 5,0 h","continuous","Signal",null,"LT",null,null,null,"C,C,C",null,null,"10,8,5",null,"Umbau Linz Westkopf mit IB ESTW Hoersching, Marchtrenk, Gunskirchen\nSWT Linz Hbf und Wels Hbf",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,"59417","Wels - Traun - Linz","< >","Linz Hbf","Linz Wegscheid",2022,2022,46,51,"2022-11-07","07:00","2022-12-14","18:00","37 days + 11,0 h","continuous","Miscellaneous",null,"LT",null,null,null,"C,,C",null,null,null,null,"Umbau Westkopf Abschnitt Ri Pyhrnbahn",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,"59518","Wels - Traun - Linz","< >","Linz Wegscheid","St.Martin bei Traun",2022,2022,47,49,"2022-11-14","08:00","2022-11-28","01:00","13 days + 17,0 h","continuous","Signal",null,"LT",null,null,null,null,null,null,"5,1,2",null,"Migration Linz Wegscheid BFZ Linz",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,"59536","Wels - Traun - Linz","< >","Linz Oed","Linz Wegscheid",2022,2022,47,47,"2022-11-14","07:00","2022-11-16","24:00","2 days + 17,0 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Tausch Oberleitungskette",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,"59537","Wels - Traun - Linz","< >","Linz Oed","Linz Wegscheid",2022,2022,49,51,"2022-11-28","07:00","2022-12-14","24:00","16 days + 17,0 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Tausch Oberleitungskette",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Planned",null,"Y"]
[null,81,"59574","Wels - Traun - Linz","< >","Marchtrenk","Traun",2021,2021,48,44,"2021-11-23","07:00","2021-10-29","17:00","6 days + 10,0 h","continuous","Miscellaneous","T","LT",null,null,null,"C,C,C",null,null,null,null,"Gesamtsperre",null,"Y",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,81,"60033","Wels - Traun - Linz","< >","Linz Wegscheid","Traun",2021,2021,33,33,"2021-08-09","07:00","2021-08-15","17:00","6 days + 10,0 h","continuous","Signal",null,"LT",null,null,null,null,null,null,"5,1,1",null,"Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,81,"60034","Wels - Traun - Linz","< >","Traun","Linz Wegscheid",2021,2021,32,32,"2021-08-02","07:00","2021-08-08","17:00","6 days + 10,0 h","continuous","Signal",null,"LT",null,null,null,null,null,null,"5,1,1",null,"Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,81,"60036","Wels - Traun - Linz","< >","Linz Hbf","Traun",2021,2021,30,33,"2021-07-19","07:00","2021-08-15","17:00","27 days + 10,0 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"; Vorarbeiten Migration Linz Wegscheid",null,"N",null,"2021-01-11","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118001,"Győr - Budapest","< >","Herceghalom","Bicske",2021,2021,3,3,"2021-01-19","08:25:00","2021-01-19","16:10:00",0.32291666666666674,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118002,"Győr - Budapest","< >","Herceghalom","Bicske",2021,2021,3,3,"2021-01-20","08:25:00","2021-01-20","16:10:00",0.32291666666666674,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118003,"Győr - Budapest","< >","Herceghalom","Bicske",2021,2021,3,3,"2021-01-21","08:25:00","2021-01-21","12:35:00",0.17361111111111116,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118004,"Győr - Budapest","< >","Herceghalom","Bicske",2021,2021,3,3,"2021-01-21","12:35:00","2021-01-21","16:10:00",0.14930555555555558,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118005,"Győr - Budapest","< >","Herceghalom","Bicske",2021,2021,3,3,"2021-01-22","08:25:00","2021-01-22","16:10:00",0.32291666666666674,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118006,"Győr - Budapest","< >","Biatorbágy","Herceghalom",2021,2021,3,3,"2021-01-23","08:10:00","2021-01-23","16:00:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118007,"Győr - Budapest","< >","Biatorbágy","Herceghalom",2021,2021,3,3,"2021-01-24","08:10:00","2021-01-24","16:00:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118008,"Győr - Budapest","< >","Bicske","Szárliget",2021,2021,4,4,"2021-01-25","08:20:00","2021-01-25","16:05:00",0.32291666666666657,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118009,"Győr - Budapest","< >","Bicske","Szárliget",2021,2021,4,4,"2021-01-26","08:20:00","2021-01-26","16:05:00",0.32291666666666657,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118010,"Győr - Budapest","< >","Bicske","Szárliget",2021,2021,4,4,"2021-01-27","08:20:00","2021-01-27","16:05:00",0.32291666666666657,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118011,"Győr - Budapest","< >","Bicske","Szárliget",2021,2021,4,4,"2021-01-28","08:20:00","2021-01-28","16:05:00",0.32291666666666657,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118012,"Győr - Budapest","< >","Komárom","Ács",2021,2021,4,4,"2021-01-29","07:00:00","2021-01-29","15:00:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118013,"Győr - Budapest","< >","Biatorbágy","Herceghalom",2021,2021,4,4,"2021-01-30","08:10:00","2021-01-30","16:00:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118014,"Győr - Budapest","< >","Biatorbágy","Herceghalom",2021,2021,4,4,"2021-01-31","08:10:00","2021-01-31","16:00:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118015,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-01","08:05:00","2021-02-01","15:45:00",0.31944444444444442,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118016,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-02","08:05:00","2021-02-02","15:45:00",0.31944444444444442,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118017,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-03","08:05:00","2021-02-03","12:10:00",0.17013888888888884,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118018,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-03","12:10:00","2021-02-03","15:45:00",0.14930555555555558,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118019,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-04","08:05:00","2021-02-04","15:45:00",0.31944444444444442,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118020,"Győr - Budapest","< >","Tatabánya","Tata",2021,2021,5,5,"2021-02-05","08:05:00","2021-02-05","15:45:00",0.31944444444444442,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118021,"Győr - Budapest","< >","Ács","Nagyszentjános",2021,2021,6,6,"2021-02-08","07:05:00","2021-02-08","15:15:00",0.34027777777777773,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118022,"Győr - Budapest","< >","Ács","Nagyszentjános",2021,2021,6,6,"2021-02-09","07:05:00","2021-02-09","15:15:00",0.34027777777777773,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118023,"Győr - Budapest","< >","Ács","Nagyszentjános",2021,2021,6,6,"2021-02-10","07:05:00","2021-02-10","15:15:00",0.34027777777777773,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118024,"Győr - Budapest","< >","Ács","Nagyszentjános",2021,2021,6,6,"2021-02-11","07:05:00","2021-02-11","15:15:00",0.34027777777777773,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118025,"Győr - Budapest","< >","Nagyszentjános","Győrszentiván",2021,2021,9,9,"2021-03-01","07:00:00","2021-03-01","14:50:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118026,"Győr - Budapest","< >","Nagyszentjános","Győrszentiván",2021,2021,9,9,"2021-03-02","07:00:00","2021-03-02","14:50:00",0.3263888888888889,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118027,"Győr - Budapest","< >","Győrszentiván","Győr",2021,2021,9,9,"2021-03-03","06:45:00","2021-03-03","14:45:00",0.33333333333333337,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118028,"Győr - Budapest","< >","Győrszentiván","Győr",2021,2021,9,9,"2021-03-04","06:45:00","2021-03-04","14:45:00",0.33333333333333337,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118029,"Győr - Budapest","< >","Szárliget","Tatabánya",2021,2021,11,12,"2021-03-19","22:50:00","2021-03-22","05:00:00","2 day 6 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118030,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,14,16,"2021-04-08","00:00:00","2021-04-25","23:59:00","18 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118031,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,17,17,"2021-04-26","21:30:00","2021-04-27","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118032,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,17,17,"2021-04-27","21:30:00","2021-04-28","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118033,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,17,17,"2021-04-28","21:30:00","2021-04-29","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118034,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,17,17,"2021-04-29","21:30:00","2021-04-30","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118035,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,18,18,"2021-05-03","21:30:00","2021-05-04","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118036,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,18,18,"2021-05-04","21:30:00","2021-05-05","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118037,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,18,18,"2021-05-05","21:30:00","2021-05-06","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118038,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,18,18,"2021-05-06","21:30:00","2021-05-07","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118039,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,18,18,"2021-05-07","21:30:00","2021-05-08","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118040,"Győr - Budapest","< >","Almásfüzitő felső","Komárom-Rendező",2021,2021,18,18,"2021-05-08","00:00:00","2021-05-09","23:59:00","2 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118041,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,19,19,"2021-05-10","21:30:00","2021-05-11","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118042,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,19,19,"2021-05-11","21:30:00","2021-05-12","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118043,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,19,19,"2021-05-12","21:30:00","2021-05-13","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118044,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,19,19,"2021-05-13","21:30:00","2021-05-14","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118045,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,19,19,"2021-05-14","21:30:00","2021-05-15","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118046,"Győr - Budapest","< >","Almásfüzitő felső","Komárom-Rendező",2021,2021,19,19,"2021-05-15","00:00:00","2021-05-16","23:59:00","2 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118047,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,20,20,"2021-05-17","21:30:00","2021-05-18","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118048,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,20,20,"2021-05-18","21:30:00","2021-05-19","05:30:00",0.33333333333090731,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118049,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,20,20,"2021-05-19","21:30:00","2021-05-20","05:30:00",0.33333333333090731,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118050,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,20,20,"2021-05-20","21:30:00","2021-05-21","05:30:00",0.33333333333090631,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118051,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,20,20,"2021-05-21","21:30:00","2021-05-22","05:30:00",0.33333333333090631,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118052,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,21,21,"2021-05-24","21:30:00","2021-05-25","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118053,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,21,21,"2021-05-25","21:30:00","2021-05-26","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118054,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,21,21,"2021-05-26","21:30:00","2021-05-27","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118055,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,21,21,"2021-05-27","21:30:00","2021-05-28","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118056,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,21,21,"2021-05-28","21:30:00","2021-05-29","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118057,"Győr - Budapest","< >","Nagyszentjános","Győrszentiván",2021,2021,21,21,"2021-05-28","22:30:00","2021-05-31","04:00:00",2.2291666666666665,"periodical","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118058,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,22,22,"2021-05-31","21:30:00","2021-06-01","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118059,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,22,22,"2021-06-02","21:30:00","2021-06-03","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118060,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,22,22,"2021-06-03","21:30:00","2021-06-04","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118061,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,22,22,"2021-06-04","21:30:00","2021-06-05","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118062,"Győr - Budapest","< >","Nagyszentjános\nGyőrszentiván","Győrszentiván\nGönyű",2021,2021,22,22,"2021-06-04","23:00:00","2021-06-07","04:00:00","2 day 5 h","periodical","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118063,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,24,24,"2021-06-15","21:30:00","2021-06-16","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118064,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,24,24,"2021-06-16","21:30:00","2021-06-17","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118065,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,24,24,"2021-06-17","21:30:00","2021-06-18","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118066,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,24,24,"2021-06-18","21:30:00","2021-06-19","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118067,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,25,25,"2021-06-24","21:30:00","2021-06-25","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118068,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,25,25,"2021-06-25","21:30:00","2021-06-26","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118069,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,25,25,"2021-06-28","21:30:00","2021-06-29","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118070,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,27,27,"2021-07-05","21:30:00","2021-07-06","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118071,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,27,27,"2021-07-06","21:30:00","2021-07-07","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118072,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,27,27,"2021-07-07","21:30:00","2021-07-08","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118073,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,27,27,"2021-07-08","21:30:00","2021-07-09","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118074,"Győr - Budapest","< >","Tata\nAlmásfüzitő","Almásfüzitő-felső\nAlmásfüzitő-felső",2021,2021,27,27,"2021-07-10","00:00:00","2021-07-11","23:59:00","2 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118075,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,28,28,"2021-07-12","21:30:00","2021-07-13","05:30:00",0.33333333333090731,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118076,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,28,28,"2021-07-13","21:30:00","2021-07-14","05:30:00",0.33333333333090631,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118077,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,28,28,"2021-07-14","21:30:00","2021-07-15","05:30:00",0.33333333333090631,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118078,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,28,28,"2021-07-15","21:30:00","2021-07-16","05:30:00",0.33333333333090631,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118079,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,29,29,"2021-07-19","21:30:00","2021-07-20","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118080,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,29,29,"2021-07-20","21:30:00","2021-07-21","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118081,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,29,29,"2021-07-21","21:30:00","2021-07-22","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118082,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,31,31,"2021-08-05","21:30:00","2021-08-06","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118083,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,35,35,"2021-09-02","21:30:00","2021-09-03","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118084,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-06","21:30:00","2021-09-07","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118085,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-07","21:30:00","2021-09-08","05:30:00",0.33333333333090798,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118086,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-08","21:30:00","2021-09-09","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118087,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-09","21:30:00","2021-09-10","05:30:00",0.33333333333090731,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118088,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-10","21:30:00","2021-09-11","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118089,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,36,36,"2021-09-11","21:30:00","2021-09-12","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118090,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,37,37,"2021-09-13","21:30:00","2021-09-14","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118091,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,37,37,"2021-09-14","21:30:00","2021-09-15","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118092,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,37,37,"2021-09-15","21:30:00","2021-09-16","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118093,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,37,37,"2021-09-16","21:30:00","2021-09-17","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118094,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,37,37,"2021-09-17","21:30:00","2021-09-18","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118095,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-20","21:30:00","2021-09-21","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118096,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-21","21:30:00","2021-09-22","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118097,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-22","21:30:00","2021-09-23","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118098,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-23","21:30:00","2021-09-24","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118099,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-24","21:30:00","2021-09-25","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118100,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,38,"2021-09-25","21:30:00","2021-09-26","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118101,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,38,39,"2021-09-26","21:30:00","2021-09-27","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118102,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,39,39,"2021-09-27","21:30:00","2021-09-28","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118103,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,39,39,"2021-09-28","21:30:00","2021-09-29","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118104,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,39,39,"2021-09-29","21:30:00","2021-09-30","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118105,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,39,39,"2021-09-30","21:30:00","2021-10-01","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118106,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,39,39,"2021-10-01","21:30:00","2021-10-02","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118107,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,40,40,"2021-10-04","21:30:00","2021-10-05","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118108,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,40,40,"2021-10-05","21:30:00","2021-10-06","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118109,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,40,40,"2021-10-06","21:30:00","2021-10-07","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118110,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,40,40,"2021-10-07","21:30:00","2021-10-08","05:30:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118111,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,40,40,"2021-10-08","21:30:00","2021-10-09","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118112,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-11","21:30:00","2021-10-12","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118113,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-12","21:30:00","2021-10-13","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118114,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-13","21:30:00","2021-10-14","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118115,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-14","21:30:00","2021-10-15","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118116,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-15","21:30:00","2021-10-16","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118117,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-16","21:30:00","2021-10-17","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118118,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,41,41,"2021-10-17","21:30:00","2021-10-18","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118119,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,42,42,"2021-10-18","21:30:00","2021-10-19","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118120,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,42,42,"2021-10-19","21:30:00","2021-10-20","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118121,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,42,42,"2021-10-20","21:30:00","2021-10-21","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118122,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,42,42,"2021-10-21","21:30:00","2021-10-22","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118123,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,42,43,"2021-10-24","21:30:00","2021-10-25","05:30:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118124,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,43,43,"2021-10-25","21:30:00","2021-10-26","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118125,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,43,43,"2021-10-26","21:30:00","2021-10-27","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118126,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,43,43,"2021-10-27","21:30:00","2021-10-28","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118127,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,43,43,"2021-10-28","21:30:00","2021-10-29","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118128,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,43,43,"2021-10-29","21:30:00","2021-10-30","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118129,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,44,44,"2021-11-02","21:30:00","2021-11-03","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118130,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,44,44,"2021-11-03","21:30:00","2021-11-04","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118131,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,44,44,"2021-11-04","21:30:00","2021-11-05","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118132,"Győr - Budapest","< >","Szárliget","Tatabánya",2021,2021,44,44,"2021-11-05","22:50:00","2021-11-08","05:00:00",2.2569444444444442,"periodical","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118133,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,45,45,"2021-11-08","21:30:00","2021-11-09","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118134,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,45,45,"2021-11-09","21:30:00","2021-11-10","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118135,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,45,45,"2021-11-10","21:30:00","2021-11-11","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118136,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,45,45,"2021-11-11","21:30:00","2021-11-12","05:30:00",0.33333333333090831,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118137,"Győr - Budapest","< >","Szárliget","Tatabánya",2021,2021,45,46,"2021-11-12","22:50:00","2021-11-15","05:00:00","2 day 6 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118138,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,46,49,"2021-11-16","21:30:00","2021-12-11","05:30:00","24 day 8 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118139,"Győr - Budapest","< >","Ferencváros","Kelenföld",2021,2021,49,49,"2021-12-11","05:30:00","2021-12-11","21:30:00",0.66666666666909202,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118140,"Szolnok - Cluj","< >","Püspökladány","Biharkeresztes",2021,2021,18,34,"2021-05-03","00:00:00","2021-08-29","23:59:00","119 day","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"modernization",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118141,"Budapest - Újszász - Szajol","< >","Tápiószecső","Nagykáta",2021,2021,4,4,"2021-01-30","08:05:00","2021-01-30","15:50:00",0.32291666666666663,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118142,"Budapest - Újszász - Szajol","< >","Tápiószecső","Nagykáta",2021,2021,4,4,"2021-01-31","08:05:00","2021-01-31","15:50:00",0.32291666666666663,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118143,"Budapest - Újszász - Szajol","< >","Mende","Sülysáp",2021,2021,5,5,"2021-02-06","08:00:00","2021-02-06","16:00:00",0.33333333333330994,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118144,"Budapest - Újszász - Szajol","< >","Mende","Sülysáp",2021,2021,5,5,"2021-02-07","08:00:00","2021-02-07","16:00:00",0.33333333333330795,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118145,"Budapest - Újszász - Szajol","< >","Rákos","Rákoshegy",2021,2021,7,7,"2021-02-20","08:00:00","2021-02-20","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118146,"Budapest - Újszász - Szajol","< >","Tápiószele","Tápiógyörgye",2021,2021,14,14,"2021-04-10","08:00:00","2021-04-10","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118147,"Budapest - Újszász - Szajol","< >","Tápiószele","Tápiógyörgye",2021,2021,14,14,"2021-04-11","08:00:00","2021-04-11","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118148,"Budapest - Újszász - Szajol","< >","Gyömrő","Mende",2021,2021,16,16,"2021-04-24","08:00:00","2021-04-24","16:00:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118149,"Budapest - Újszász - Szajol","< >","Gyömrő","Mende",2021,2021,16,16,"2021-04-25","08:00:00","2021-04-25","16:00:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118150,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-03","22:50:00","2021-05-04","01:20:00",0.10416666666666674,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118151,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-04","02:30:00","2021-05-04","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118152,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-04","22:50:00","2021-05-05","01:20:00",0.10416666666666674,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118153,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-05","02:30:00","2021-05-05","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118154,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-05","22:50:00","2021-05-06","01:20:00",0.10416666666666674,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118155,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,18,18,"2021-05-06","02:30:00","2021-05-06","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118156,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,18,18,"2021-05-06","22:55:00","2021-05-07","01:30:00",0.10763888888888884,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118157,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,18,18,"2021-05-07","02:25:00","2021-05-07","04:50:00",0.10069444444444443,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118158,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,19,19,"2021-05-10","22:55:00","2021-05-11","01:30:00",0.10763888888888884,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118159,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,19,19,"2021-05-11","02:25:00","2021-05-11","04:50:00",0.10069444444444443,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118160,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,19,19,"2021-05-11","22:55:00","2021-05-12","01:30:00",0.10763888888888884,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118161,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,19,19,"2021-05-12","02:25:00","2021-05-12","04:50:00",0.10069444444444443,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118162,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,19,19,"2021-05-12","23:10:00","2021-05-13","01:40:00",0.10416666666666663,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118163,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,19,19,"2021-05-13","02:20:00","2021-05-13","04:40:00",9.7222222222222224E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118164,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,19,19,"2021-05-13","23:10:00","2021-05-14","01:40:00",0.10416666666666663,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118165,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,19,19,"2021-05-14","02:20:00","2021-05-14","04:40:00",9.7222222222222224E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118166,"Szolnok - Arad","< >","Sülysáp","Tápiószecső",2021,2021,19,19,"2021-05-15","00:00:00","2021-05-15","23:59:00",0.99930555555555556,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118167,"Szolnok - Arad","< >","Sülysáp","Tápiószecső",2021,2021,19,19,"2021-05-16","00:00:00","2021-05-16","23:59:00",0.99930555555555556,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118168,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,20,20,"2021-05-17","23:10:00","2021-05-18","01:40:00",0.10416666666666663,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118169,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,20,20,"2021-05-18","02:20:00","2021-05-18","04:40:00",9.7222222222222224E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118170,"Szolnok - Arad","< >","Rákos\n\nRákos","Rákoshegy\n\nPécel",2021,2021,34,35,"2021-08-27","00:00:00","2021-09-01","04:00:00","5 day 6 h","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"modernization",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118171,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-13","21:55:00","2021-09-14","01:25:00",0.14583333333333315,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118172,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-14","02:30:00","2021-09-14","05:00:00",0.10416666666666667,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118173,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-14","21:55:00","2021-09-15","01:25:00",0.14583333333333315,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118174,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-15","02:30:00","2021-09-15","05:00:00",0.10416666666666667,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118175,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-15","21:55:00","2021-09-16","01:25:00",0.14583333333333315,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118176,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,37,37,"2021-09-15","22:00:00","2021-09-16","01:30:00",0.14583333333333337,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118177,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-16","02:30:00","2021-09-16","05:00:00",0.10416666666666667,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118178,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-16","21:55:00","2021-09-17","01:25:00",0.14583333333333315,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118179,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,37,37,"2021-09-16","22:00:00","2021-09-17","01:30:00",0.14583333333333337,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118180,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,37,37,"2021-09-17","02:30:00","2021-09-17","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118181,"Szolnok - Arad","< >","Békéscsaba","Szabadkígyós",2021,2021,37,37,"2021-09-17","02:30:00","2021-09-17","05:00:00",0.10416666666666667,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118182,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,37,37,"2021-09-17","22:00:00","2021-09-18","01:30:00",0.14583333333333337,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118183,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,37,37,"2021-09-18","02:30:00","2021-09-18","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118184,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,38,38,"2021-09-20","22:00:00","2021-09-21","01:30:00",0.14583333333333337,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118185,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,38,38,"2021-09-21","02:30:00","2021-09-21","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118186,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,38,38,"2021-09-21","22:00:00","2021-09-22","01:30:00",0.14583333333333337,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118187,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-21","22:15:00","2021-09-22","01:40:00",0.14236111111111105,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118188,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-22","02:25:00","2021-09-22","04:40:00",9.3750000000000014E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118189,"Szolnok - Arad","< >","Szabadkígyós","Kétegyháza",2021,2021,38,38,"2021-09-22","02:30:00","2021-09-22","04:50:00",9.7222222222222196E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118190,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-22","22:15:00","2021-09-23","01:40:00",0.14236111111111105,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118191,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-23","02:25:00","2021-09-23","04:40:00",9.3750000000000014E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118192,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-23","22:15:00","2021-09-24","01:40:00",0.14236111111111105,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118193,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-24","02:25:00","2021-09-24","04:40:00",9.3750000000000014E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118194,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-24","22:15:00","2021-09-25","01:40:00",0.14236111111111105,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118195,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,38,38,"2021-09-25","02:25:00","2021-09-25","04:40:00",9.3750000000000014E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118196,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,39,39,"2021-09-27","22:15:00","2021-09-28","01:40:00",0.14236111111111105,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118197,"Szolnok - Arad","< >","Lőkösháza","Lőkösháza oh.",2021,2021,39,39,"2021-09-27","23:35:00","2021-09-28","00:55:00",5.555555555555558E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118198,"Szolnok - Arad","< >","Kétegyháza","Lőkösháza",2021,2021,39,39,"2021-09-28","02:25:00","2021-09-28","04:40:00",9.3750000000000014E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118199,"Szolnok - Arad","< >","Lőkösháza","Lőkösháza oh.",2021,2021,39,39,"2021-09-28","03:00:00","2021-09-28","04:50:00",7.6388888888888867E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118200,"Szolnok - Arad","< >","Lőkösháza","Lőkösháza oh.",2021,2021,39,39,"2021-09-28","23:35:00","2021-09-29","00:55:00",5.555555555555558E-2,"continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure of a single track line. Diversionary route of RFC 7.",53,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118201,"Budapest - Újszász - Szajol","< >","Újszász","Szolnok D elág.",2021,2021,41,41,"2021-10-11","08:00:00","2021-10-17","23:59:00","7 day 16 h","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"modernization",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118202,"Budapest - Újszász - Szajol",">","Tápiógyörgye","Újszász",2021,2021,45,45,"2021-11-13","08:00:00","2021-11-13","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118203,"Budapest - Újszász - Szajol","<","Tápiógyörgye","Újszász",2021,2021,45,45,"2021-11-14","08:00:00","2021-11-14","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118204,"Budapest - Újszász - Szajol",">","Újszász","Szolnok",2021,2021,46,46,"2021-11-20","08:00:00","2021-11-20","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118205,"Budapest - Újszász - Szajol","<","Újszász","Szolnok",2021,2021,46,46,"2021-11-21","08:00:00","2021-11-21","16:00:00",0.33333333333333398,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118206,"Budapest - Újszász - Szajol",">","Rákoshegy","Maglód",2021,2021,47,47,"2021-11-27","08:00:00","2021-11-27","16:00:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118207,"Budapest - Újszász - Szajol","<","Rákoshegy","Maglód",2021,2021,47,47,"2021-11-28","08:00:00","2021-11-28","16:00:00",0.33333333333333331,"continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118208,"Budapest - Újszász - Szajol","<","Tápiógyörgye","Újszász",2021,2021,11,12,"2021-03-19","22:00:00","2021-03-22","04:00:00","2 day 6 h","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Bridge",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118209,"Budapest - Újszász - Szajol","<","Tápiógyörgye","Újszász",2021,2021,12,13,"2021-03-26","22:00:00","2021-03-29","04:00:00","2 day 6 h","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Bridge",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118210,"Budapest - Újszász - Szajol","<","Nagykáta","Tápiószele",2021,2021,24,34,"2021-06-19","00:00:00","2021-08-29","23:59:00","72 day","continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Bridge",null,"N",null,"2020-10-26","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118211,"Budapest - Cegléd - Szolnok","<","Pilis","Albertirsa",2021,2021,6,6,"2021-02-13","08:10:00","2021-02-13","15:50:00","0 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118212,"Budapest - Cegléd - Szolnok",">","Pilis","Albertirsa",2021,2021,6,6,"2021-02-14","08:10:00","2021-02-14","15:50:00","1 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118213,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc I vg.","Pestszentlőrinc I vg.",2021,2021,11,11,"2021-03-16","00:00:00","2021-03-21","23:59:00","6 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118214,"Budapest - Cegléd - Szolnok",">","Vecsés","Üllő",2021,2021,14,19,"2021-04-06","00:00:00","2021-05-15","23:59:00","40 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118215,"Budapest - Cegléd - Szolnok","<","Vecsés","Üllő",2021,2021,19,24,"2021-05-16","00:00:00","2021-06-18","23:59:00","34 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118216,"Budapest - Cegléd - Szolnok",">","Üllő","Monor",2021,2021,35,39,"2021-08-30","00:00:00","2021-09-29","23:59:00","31 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,55,210118217,"Budapest - Cegléd - Szolnok","<","Üllő","Monor",2021,2021,39,43,"2021-09-30","00:00:00","2021-10-29","23:59:00","30 day","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,"2020-12-21","Unclassified",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118001,"Arad - Brașov","< >","Mintia ","Branisca",2020,2022,44,27,"2020-10-30",null,"2022-06-30",null,608,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118002,"Arad - Brașov","< >","Branisca","Ilia",2020,2022,2,27,"2020-01-07",null,"2022-06-30",null,905,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118003,"Arad - Brașov","< >","Ilia","Gurasada",2020,2022,39,27,"2020-09-25",null,"2022-06-30",null,643,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118004,"Arad - Brașov","< >","Gurasada","Campuri",2021,2021,10,10,"2021-03-05",null,"2021-03-05",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118005,"Arad - Brașov","< >","Gurasada","Ilteu",2018,2022,47,38,"2018-11-22",null,"2022-09-16",null,1394,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118006,"Arad - Brașov","< >","Ilteu","Savarsin",2019,2021,6,49,"2019-02-06",null,"2021-12-02",null,1030,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118007,"Arad - Brașov","< >","Varadia","Batuta",2019,2022,9,17,"2019-02-27",null,"2022-04-22",null,1150,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118008,"Arad - Brașov","< >","Barzava","Barzava Noua",2019,2022,25,17,"2019-06-19",null,"2022-04-22",null,1038,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118009,"Arad - Brașov","< >","Savarsin","Varadia",2020,2021,40,49,"2020-10-01",null,"2021-12-02",null,427,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118010,"Arad - Brașov","< >","Savarsin"," Varadia",2021,2021,48,49,"2021-11-26",null,"2021-12-02",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118011,"Arad - Brașov","< >","Ilteu","Varadia",2021,2021,16,17,"2021-04-13",null,"2021-04-19",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118012,"Arad - Brașov","< >","Varadia","Barzava Noua",2021,2022,38,17,"2021-09-15",null,"2022-04-22",null,219,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118013,"Arad - Brașov","< >","Barzava","Milova",2017,2022,40,19,"2017-09-25",null,"2022-05-03",null,1681,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118014,"Arad - Brașov","< >","Conop","Milova",2019,2022,9,19,"2019-03-01",null,"2022-05-03",null,1159,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118015,"Arad - Brașov","< >","Conop","Radna",2021,2021,9,9,"2021-02-22",null,"2021-02-26",null,4,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118016,"Arad - Brașov","< >","Paulis","Glogovat",2021,2021,12,13,"2021-03-20",null,"2021-03-22",null,2,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118017,"Arad - Brașov","< >","Milova","Paulis",2021,2021,19,19,"2021-05-05",null,"2021-05-07",null,2,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118018,"Arad - Brașov","< >","Milova","Paulis",2021,2021,29,30,"2021-07-18",null,"2021-07-21",null,3,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118019,"Arad - Brașov","< >","Braşov","Stupini",2020,2023,36,11,"01.09.2020",null,"2023-03-10",null,920,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118020,"Arad - Brașov","< >","Stupini","Bod",2020,2023,35,25,"2020-08-26",null,"2023-06-14",null,1022,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118021,"Arad - Brașov","< >","Stupini","Bod",2021,2021,29,30,"2021-07-15",null,"2021-07-20",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118022,"Arad - Brașov","< >","Feldioara","Apata",2021,2022,30,8,"21.07.2021",null,"15.02.2022",null,209,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118023,"Arad - Brașov","< >","Augustin","Rupea",2021,2024,10,13,"2021-03-01",null,"2024-03-27",null,1122,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118024,"Arad - Brașov","< >","Mureni","Vanatori",2021,2022,49,32,"01.12.2021",null,"07.08.2022",null,249,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118025,"Arad - Brașov","< >","Vanatori","Albesti",2021,2022,11,32,"08.03.2021",null,"07.08.2022",null,517,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118026,"Arad - Brașov","< >","Albesti","Sighisoara",2021,2022,9,32,"22.02.2021",null,"07.08.2022",null,531,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118027,"Arad - Brașov","< >","Albesti","Sighisoara",2021,2021,44,49,"30.10.2021",null,"30.11.2021",null,31,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Major",null,null,null,null,null,null,"Published",null,"Y"]
[null,53,210118028,"Arad - Brașov","< >","Simeria","Deva",2022,2023,42,13,"2022-10-11",null,"2023-03-20",null,160,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118029,"Arad - Brașov","< >","Mintia","Branisca",2021,2022,29,27,"2021-07-16",null,"2022-06-30",null,349,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118030,"Arad - Brașov","< >","Mintia","Ilia",2022,2022,26,27,"2022-06-25",null,"2022-06-30",null,5,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118031,"Arad - Brașov","< >","Branisca","Ilia",2021,2022,36,27,"2021-09-02",null,"2022-06-30",null,301,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118032,"Arad - Brașov","< >","Ilia","Gurasada",2020,2022,39,33,"2020-09-25",null,"2022-08-14",null,688,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118033,"Arad - Brașov","< >","Gurasada","Ilteu",2018,2022,47,38,"2018-11-22",null,"2022-09-16",null,1394,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118034,"Arad - Brașov","< >","Varadia","Batuta",2019,2022,9,17,"2019-02-27",null,"2022-04-22",null,1150,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118035,"Arad - Brașov","< >","Barzava","Barzava Noua",2019,2022,25,17,"2019-06-19",null,"2022-04-22",null,1038,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118036,"Arad - Brașov","< >","Varadia","Barzava Noua",2021,2022,38,17,"2021-09-15",null,"2022-04-22",null,219,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118037,"Arad - Brașov","< >","Barzava Noua","Milova",2022,2022,16,17,"2022-04-16",null,"2022-04-22",null,6,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118038,"Arad - Brașov","< >","Barzava","Milova",2017,2022,40,48,"2017-09-25",null,"2022-11-23",null,1885,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118039,"Arad - Brașov","< >","Conop","Milova",2019,2022,9,19,"2019-03-01",null,"2022-05-03",null,1159,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118040,"Arad - Brașov","< >","Barzava","Radna",2022,2022,18,19,"2022-04-27",null,"2022-05-03",null,6,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118041,"Arad - Brașov","< >","Barzava","Radna",2022,2022,48,48,"2022-11-21",null,"2022-11-23",null,2,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118042,"Arad - Brașov","< >","Brasov","Stupini",2022,2023,17,11,"21.04.2022",null,"10.03.2023",null,323,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118043,"Arad - Brașov","< >","Stupini","Bod",2020,2023,35,25,"2020-08-26",null,"2023-06-14",null,1022,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118044,"Arad - Brașov","< >","Stupini","Bod",2022,2022,44,45,"2022-10-30",null,"2022-11-04",null,6,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118045,"Arad - Brașov","< >","Bod","Feldioara",2022,2023,8,19,"2022-02-16",null,"2023-05-05",null,443,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118046,"Arad - Brașov","< >","Bod","Feldioara",2022,2022,44,45,"30.10.2022",null,"04.11.2022",null,6,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118047,"Arad - Brașov","< >","Feldioara","Apata",2021,2023,30,36,"21.07.2021",null,"30.08.2023",null,770,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118048,"Arad - Brașov","< >","Augustin","Rupea",2021,2024,10,13,"2021-03-01",null,"2024-03-27",null,1122,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118049,"Arad - Brașov","< >","Cata","Beia",2022,2023,33,8,"08.08.2022",null,"15.02.2023",null,191,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118050,"Arad - Brașov","< >","Beia","Mureni",2022,2023,46,8,"10.11.2022",null,"15.02.2023",null,97,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118051,"Arad - Brașov","< >","Mureni","Vanatori",2021,2023,49,8,"01.12.2021",null,"15.02.2023",null,441,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118052,"Arad - Brașov","< >","Vanatori","Albesti",2021,2023,49,8,"01.12.2021",null,"15.02.2023",null,441,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118053,"Arad - Brașov","< >","Albesti","Sighisoara",2021,2022,49,32,"01.12.2021",null,"07.08.2022",null,249,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,"N",null,"2021-01-11","High",null,null,null,null,null,null,"Planned",null,"Y"]
[null,53,210118054,"Arad - Brașov","< >","Sighisoara Station",null,2022,2022,32,32,"02.08.2022",null,"07.08.2022",null,6,"continuous","Track & Rail","T","ST",null,null,null,null,null,null,null,null,null,null,"N",null,"2021-01-11","Medium",null,null,null,null,null,null,"Planned",null,"Y"]

{"sheet":"Graphic Overview","index":2,"n_rows":1063,"n_cols":375,"rows_kept":1063,"cut":false,"hidden":false,"merged":[[3,306,3,312],[3,313,3,319],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,271,3,277],[3,278,3,284],[3,285,3,291],[3,292,3,298],[3,299,3,305],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,282,2,312],[2,313,2,342],[2,343,2,373],[3,159,3,165],[3,166,3,172],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,194,3,200],[3,201,3,207],[3,341,3,347],[3,348,3,354],[3,355,3,361],[3,362,3,368],[3,369,3,373],[3,215,3,221],[3,222,3,228],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,229,3,235],[3,208,3,214],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,138,3,144],[3,145,3,151],[3,33,3,39],[2,129,2,159],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[3,68,3,74],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128],[3,257,3,263],[3,264,3,270],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,103,3,109],[3,110,3,116],[3,152,3,158],[3,236,3,242],[3,243,3,249],[3,250,3,256]]}
[null,"Rhine-Danube, Overview"]
[]
[null,null,null,null,null,null,2021,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-12-12","2022-07-29T18:00:00","229 d, 18 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-09-26T22:00:00","2021-09-27T05:00:00","7 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-09-30T08:00:00","2021-10-05T08:59:00","5 d, 01 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-05T05:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Partenstein - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Nantenbach - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Nantenbach - Partenstein",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Weinheim (Bergstr) - Weinheim (Bergstr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-01T01:00:00","2021-02-05T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-08T05:00:00","2021-02-12T21:00:00","4 d, 16 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-15T01:00:00","2021-02-19T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Neu-Edingen/Mhm-Friedrichsfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-05-27","2021-06-18T23:59:00","23 d","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Heidelberg-Wieblingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-06-04T21:00:00","2021-06-08T04:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Nord - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-01-15T23:30:00","2021-01-18T01:30:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-13T00:30:00","2021-02-15T13:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-15T13:00:00","2021-11-09T23:45:00","267 d, 11 h","DB Netz AG"]
[]
[null,"Dieburg - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-22T09:00:00","2021-11-15T23:59:00","10 d, 15 h","DB Netz AG"]
[]
[null,"Dieburg - Messel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Messel - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt-Kranichstein - Babenhausen (Hess)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-24T23:30:00","2021-11-07T05:30:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-01T08:00:00","2021-11-16T06:00:00","14 d, 22 h","DB Netz AG"]
[]
[null,"Mainaschaff Abzw - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T21:00:00","2021-11-16T05:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T22:00:00","2021-11-16T06:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T23:45:00","2021-11-17T04:45:00","7 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-15T06:00:00","2021-11-30T06:00:00","15 d","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-22T05:00:00","2021-11-26T22:00:00","4 d, 17 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Stuttgart Hbf - Stuttgart-Zuffenhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Ebersbach (Fils) - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-25T22:00:00","2021-01-26T04:30:00","7 h","DB Netz AG"]
[]
[null,"Stuttgart-Bad Cannstatt - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-04T21:00:00","2021-02-08T05:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Geislingen (Steige) - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-09T21:00:00","2021-02-12T05:00:00","1 d","DB Netz AG"]
[]
[null,"Ulm Hbf - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-02-28T23:30:00","2021-03-02T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-02T23:30:00","2021-03-14T04:30:00","11 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm-Örlingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-14T23:00:00","2021-03-25T04:30:00","10 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-15T22:00:00","2021-03-22T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Ulm-Örlingen - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-25T23:30:00","2021-03-27T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19","2021-08-09T04:00:00","21 d, 04 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-02T01:00:00","2021-08-13T22:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Ulm Hbf Em Nord - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T20:00:00","2021-08-16T04:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Amstetten (Württ) - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-16T22:00:00","3 d","DB Netz AG"]
[]
[null,"Göppingen - Eislingen (Fils)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-27T04:00:00","13 d, 06 h","DB Netz AG"]
[]
[null,"Geislingen West - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Uhingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-26T22:00:00","2021-08-27T04:00:00","6 h","DB Netz AG"]
[]
[null,"Eislingen (Fils) - Gingen (Fils) Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-27T22:00:00","2021-09-03T22:00:00","7 d","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-29T22:30:00","2021-02-02T05:15:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:00:00","2021-04-24T05:20:00","14 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:20:00","2021-04-12T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:00:00","2021-05-10T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:30:00","2021-05-10T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-14T22:30:00","2021-05-17T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-07","2021-08-09T04:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Burgau (Schwab)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Unterfahlheim - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Nersingen - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-29","2021-12-04T05:00:00","5 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Mannheim Hbf Ost - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-02-06T02:35:00","2021-02-08T04:35:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Mannheim-Rheinau - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-06-20T22:00:00","2021-08-03T04:00:00","43 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-07-28T22:00:00","2021-08-03T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-08-03T04:00:00","2021-09-13T04:00:00","41 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-07T21:00:00","2021-08-23T05:00:00","2 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-09T23:00:00","2021-08-21T05:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Schwetzingen - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Oftersheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-08T22:00:00","2021-09-16T06:00:00","7 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Waghäusel - Waghäusel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Graben-Neudorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-03-08","2021-03-23T23:59:00","16 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Forchheim (b Karlsruhe) - Durmersheim Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-05-13T00:01:00","2021-05-17T04:30:00","4 d, 04 h","DB Netz AG"]
[]
[null,"Karlsruhe Hbf Bft Südeinfahrt - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-07-19T23:00:00","2021-08-07T05:00:00","3 d, 18 h","DB Netz AG"]
[]
[null,"Durmersheim Nord - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-20T23:00:00","2021-08-23T05:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bashaide - Karlsruhe Hbf Bft Südeinfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-30T23:00:00","2021-11-08T04:30:00","69 d, 05 h","DB Netz AG"]
[]
[null,"Durmersheim - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-03T22:00:00","2021-10-29T05:00:00","25 d, 07 h","DB Netz AG"]
[]
[null,"Durmersheim - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-29T23:00:00","2021-11-02T04:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Pforzheim Hbf - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Vaihingen (Enz) - Vaihingen (Enz)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-03-18","2021-05-03T23:59:00","47 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-07","2021-05-11T23:59:00","5 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-08T02:00:00","2021-05-10T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Sachsenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Sachsenheim - Tamm (Württ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-03-02T22:00:00","2021-03-06T04:30:00","1 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Karlshöhe - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-22T01:45:00","2021-06-07T04:00:00","16 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Pbf - Kornwestheim Karlshöhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-07T08:00:00","2021-09-07T16:00:00","8 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-10-23T01:45:00","2021-10-25T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-06T23:00:00","2021-12-11T23:59:00","308 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-22T08:00:00","2021-12-11T23:59:00","292 d, 16 h","DB Netz AG"]
[]
[null,"Appenweier-Muhrhaag - Appenweier Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-12T23:35:00","2021-03-15T04:15:00","2 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-29T00:15:00","2021-04-02T00:15:00","4 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T00:15:00","2021-04-06T03:00:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-08-30","149 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-05-24T23:00:00","2021-07-01T04:30:00","37 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-08-30","2021-11-08T04:30:00","70 d, 04 h","DB Netz AG"]
[]
[null,"Appenweier Nord - Appenweier Kurve",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-03-27T00:30:00","2021-03-29T04:30:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-04-23T07:00:00","2021-05-05T17:00:00","12 d, 10 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-04T00:45:00","2021-07-04T06:45:00","6 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-09T23:00:00","2021-07-17T05:00:00","7 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-10T22:00:00","2021-07-11T06:45:00","9 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-07-11T22:00:00","2021-07-14T04:40:00","20 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-25T00:45:00","2021-07-25T06:45:00","6 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-09-27T07:00:00","2021-10-25T18:00:00","28 d, 11 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T07:00:00","2021-10-05T17:00:00","4 d, 10 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-01T22:00:00","2021-10-04T04:50:00","21 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-04T22:00:00","2021-10-12T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-16","2021-10-18T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-20T05:00:00","2021-10-25T05:00:00","5 d","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-20T22:00:00","2021-10-25T05:00:00","21 h","DB Netz AG"]
[]
[null,"München-Lochhausen - München-Pasing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-22T22:00:00","2021-03-27T05:40:00","4 d, 08 h","DB Netz AG"]
[]
[null,"München-Pasing - München-Lochhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-03-22T22:45:00","2021-03-27T05:20:00","1 d, 09 h","DB Netz AG"]
[]
[null,"München-Pasing - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Rosenheim - Rosenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-03-10T00:40:00","2021-03-14T02:40:00","4 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-09T02:00:00","2021-11-23T04:00:00","14 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-23T04:00:00","2021-12-11T23:59:00","18 d, 20 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-05","2021-02-08T04:50:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-12T00:25:00","2021-02-15T05:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-14T19:10:00","2021-02-15T04:10:00","9 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical continuous","2021-02-21T00:25:00","2021-03-01T04:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-06T22:20:00","2021-03-07T05:20:00","7 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-07T22:00:00","2021-03-08T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-11T21:40:00","2021-03-12T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-13T22:20:00","2021-03-15T04:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-19T16:00:00","2021-03-21T16:00:00","2 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-03-20T22:20:00","2021-03-21T05:10:00","7 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-04-01T23:30:00","2021-04-06T06:00:00","4 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-04-09T23:30:00","2021-05-17T06:00:00","13 d, 15 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-21T23:30:00","2021-05-25T06:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Postbauer-Heng - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-05-27T01:00:00","2021-06-21T05:00:00","25 d, 04 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-05T21:00:00","2021-06-26T05:00:00","20 d, 08 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-07T21:00:00","2021-06-19T04:00:00","2 d, 22 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Postbauer-Heng",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical","2021-06-07T22:00:00","2021-06-10T05:00:00","21 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-12T20:30:00","2021-06-20T04:30:00","1 d","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-06-19","2021-07-04T23:50:00","16 d","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-26T23:30:00","2021-06-28T06:00:00","1 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-07-02T23:30:00","2021-08-02T06:00:00","11 d, 09 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-07-29T23:00:00","2021-08-02T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-08-02T23:00:00","2021-08-06T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Ost",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-06T00:30:00","2021-11-11T00:30:00","5 d","DB Netz AG"]
[]
[null,"Sünching - Mangolding",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-07T01:30:00","2021-11-11T00:30:00","3 d, 23 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-05T09:00:00","2021-03-07T12:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-12T09:00:00","2021-03-15T12:00:00","3 d, 03 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T01:00:00","2021-05-02T05:00:00","6 d, 04 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T04:00:00","2021-05-02T02:00:00","5 d, 22 h","DB Netz AG"]
[]
[null,"Köfering - Eggmühl",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-28T01:00:00","2021-05-29T13:00:00","1 d, 12 h","DB Netz AG"]
[]
[null,"Eggmühl - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-29T13:00:00","2021-05-31T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-04T23:00:00","2021-06-08T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-05T03:00:00","2021-06-05T17:00:00","14 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-10T23:00:00","2021-06-14T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-11T03:00:00","2021-06-11T17:00:00","14 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-16T14:00:00","2021-06-18T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-18T22:00:00","2021-06-21T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-23T14:00:00","2021-06-25T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-25T22:00:00","2021-06-28T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-07-04T01:00:00","2021-07-04T11:00:00","10 h","DB Netz AG"]
[]
[null,"München Kanal - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Köfering - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-09-19T01:00:00","2021-10-03T05:00:00","14 d, 04 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T22:00:00","2021-10-23T05:00:00","11 d, 07 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-23T22:00:00","2021-11-01T04:00:00","8 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-11-01T22:00:00","2021-11-07T05:00:00","5 d, 07 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Richtungsgruppe Süd - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-05T14:00:00","2021-04-06T09:00:00","19 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-10T12:00:00","2021-04-12T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-12T15:00:00","2021-04-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-04-17T12:00:00","2021-05-31T15:00:00","14 d, 21 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-04-19T15:00:00","2021-05-04T06:00:00","1 d, 21 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-05-10T15:00:00","2021-06-01T06:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-05T12:00:00","2021-06-14T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-07T15:00:00","2021-06-15T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-19T12:00:00","2021-06-28T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-21T15:00:00","2021-06-29T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-03T12:00:00","2021-07-05T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-05T15:00:00","2021-07-06T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-10T12:00:00","2021-07-19T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-12T15:00:00","2021-07-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19T15:00:00","2021-07-20T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-24T12:00:00","2021-07-26T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-26T15:00:00","2021-07-27T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-31T12:00:00","2021-08-09T15:00:00","2 d, 20 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-31T12:00:00","2021-08-10T06:00:00","5 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-14T12:00:00","2021-09-13T15:00:00","7 d, 02 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-08-14T12:00:00","2021-09-14T06:00:00","13 d, 18 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-07","2021-10-11T22:00:00","4 d, 22 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-11T22:00:00","2021-10-17T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"München-Freimann - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-30T00:30:00","2021-11-03T03:30:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-01-25T22:30:00","2021-05-24T05:00:00","118 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T15:00:00","2021-04-03T20:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T22:30:00","2021-04-05T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-03T20:00:00","2021-04-04T10:00:00","14 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-04T10:00:00","2021-04-05T15:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:00:00","2021-04-10T04:00:00","6 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:30:00","2021-04-12T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-10T04:00:00","2021-04-11T10:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-11T10:00:00","2021-04-12T16:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-16T22:30:00","2021-04-19T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-17T05:00:00","2021-04-17T20:00:00","15 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-05-25T22:30:00","2021-08-13T05:00:00","79 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-02T05:00:00","9 d, 11 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-03T18:00:00","11 d","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:00:00","2021-09-02T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:30:00","2021-09-02T04:00:00","6 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Seligenstadt (b Würzburg)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:45:00","2021-08-30T04:15:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-27T22:30:00","2021-08-30T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Wernfeld - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-16T08:00:00","2021-02-23T16:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Eußenheim - Wernfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-24T08:00:00","2021-03-04T16:00:00","2 d","DB Netz AG"]
[]
[null,"Eußenheim - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-08T08:00:00","2021-03-09T16:00:00","16 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-10T08:00:00","2021-03-16T16:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-17T08:00:00","2021-03-18T16:00:00","16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-22T08:00:00","2021-04-01T16:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-06T08:00:00","2021-04-08T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-12T08:00:00","2021-04-14T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-15T08:00:00","2021-04-19T16:00:00","16 h","DB Netz AG"]
[]
[null,"Waigolshausen - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-20T08:00:00","2021-04-22T16:00:00","1 d","DB Netz AG"]
[]
[null,"Nürnberg Rbf Einfahrt - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-02-22T06:00:00","2021-12-11T23:59:00","292 d, 18 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-13T06:00:00","2021-03-14T04:00:00","22 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-20T06:00:00","2021-03-21T04:00:00","22 h","DB Netz AG"]
[]
[null,"Bamberg - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-27T22:00:00","2021-03-01T05:00:00","14 h","DB Netz AG"]
[]
[null,"Hirschaid - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-28T22:00:00","2021-03-01T05:00:00","7 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Vach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-22T23:00:00","2021-03-26T23:00:00","4 d","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T04:00:00","2021-03-29T04:00:00","3 d","DB Netz AG"]
[]
[null,"Vach - Fürth (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bad Staffelstein - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T21:00:00","2021-03-28T06:00:00","9 h","DB Netz AG"]
[]
[null,"Hirschaid - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T23:00:00","2021-04-01T04:00:00","4 d, 05 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-04T04:00:00","7 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-10-05T22:00:00","2021-12-01T01:00:00","56 d, 03 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-01T01:00:00","2021-12-06T04:00:00","5 d, 03 h","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-05T21:00:00","2021-12-06T04:00:00","7 h","DB Netz AG"]
[]
[null,"Bodenwöhr Nord - Bodenwöhr Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Plzen","continuous","2021-03-23T07:00:00","2021-05-10T07:00:00","48 d","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-10T07:00:00","2021-06-18T21:00:00","39 d, 14 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe-Dammerstock",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-08-30T23:00:00","2021-11-08T05:00:00","69 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-08","2021-09-29T23:59:00","22 d","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-25T06:00:00","2021-09-27T04:00:00","1 d, 22 h","DB Netz AG"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","30.11.2020","10.07.2021","221 days + 22,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Linz - Wien","cont.","20.02.2021","22.02.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","08.03.2021","16.03.2021","8 days + 9,5 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.03.2021","15.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","12 days","ÖBB Infra"]
[]
[null,"Sbl Spw 2 - St.Valentin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","11 days + 12,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","19.03.2021","22.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","22.03.2021","03.04.2021","12 days + 8,5 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","26.03.2021","29.03.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.04.2021","16.04.2021","4 days","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","12.04.2021","21.04.2021","9 days + 9,5 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - Untergaumberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","16.04.2021","03.05.2021","16 days + 6,5 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","21.05.2021","25.05.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","22.05.2021","24.05.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","04.06.2021","07.06.2021","2 days + 5,5 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Lambach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","09.07.2021","12.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Üst Ams 2 - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","7 days + 4,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","6 days + 5,0 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Sbl Gun 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","16.07.2021","19.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","17.07.2021","22.07.2021","5 days","ÖBB Infra"]
[]
[null,"Gunskirchen - Wels Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","23.07.2021","26.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Ybbs a.d.Donau - Abzw Knoten Karlsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","03.08.2021","23.08.2021","20 days","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","17.09.2021","20.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.09.2021","27.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","01.10.2021","04.10.2021","2 days + 19,0 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","15.10.2021","18.10.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","18.10.2021","22.10.2021","4 days + 10,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","23.10.2021","26.10.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","30.10.2021","02.11.2021","3 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","30.10.2021","02.11.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","05.11.2021","08.11.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Seekirchen am Wallersee - Steindorf bei Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","20.11.2021","24.11.2021","4 days","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Seekirchen am Wallersee",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.11.2021","29.11.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Meidling - W.Mat.-Oswaldgasse",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Linz - Wien","cont.","12.12.2021","16.04.2023","491 days","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","26.02.2021","01.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","05.03.2021","08.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.03.2021","15.03.2021","3 days + 16,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.03.2021","22.03.2021","3 days + 17,0 h","ÖBB Infra"]
[]
[null,"Andorf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.05.2021","15.05.2021","7 days + 10,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.10.2021","11.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","15.10.2021","18.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.11.2021","15.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.11.2021","22.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Parndorf Ort - Zurndorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Parndorf - Hegyeshalom","cont.","12.04.2021","16.04.2021","4 days + 4,7 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","08.03.2021","12.03.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.03.2021","14.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","19.03.2021","21.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","03.04.2021","06.04.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","10.04.2021","11.04.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - Lanzendorf-Rannersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.04.2021","18.04.2021","6 days + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","13.05.2021","16.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","22.05.2021","25.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","29.05.2021","30.05.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.06.2021","20.06.2021","13 days + 10,0 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","26.06.2021","20.08.2021","55 days + 9,0 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","05.07.2021","16.07.2021","10 days + 20,5 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","16.07.2021","06.08.2021","21 days + 12,5 h","ÖBB Infra"]
[]
[null,"Abzww Str 11815 - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.08.2021","16.09.2021","39 days + 20,5 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","20.08.2021","05.09.2021","15 days + 23,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Wien - Parndorf","cont.","01.09.2021","31.12.2022","487 days","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","15.10.2021","18.10.2021","2 days + 5,2 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","18.10.2021","31.10.2021","13 days + 11,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","23.10.2021","27.10.2021","3 days + 5,2 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","28.05.2021","02.06.2021","5 days + 15,0 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Inzersdorf Ort-Ost - Oberlaa",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","22.03.2021","29.03.2021","6 days + 20,0 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","29.10.2021","03.11.2021","4 days + 7,5 h","ÖBB Infra"]
[]
[null,"Linz Oed - Linz Wegscheid",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-26","2021-08-01","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-19","2021-07-25","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-02","2021-08-08","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-09","2021-08-15","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Rutzing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Rutzing - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":62,"n_cols":21,"rows_kept":62,"cut":false,"hidden":true,"merged":[[0,2,0,3],[0,0,0,1]]}
["IM",null,"Section",null,"Direction","Duration","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","International Coordination","In yearly timetable","Classification","Status","Automatic process"]
["GySEV",43,"Strasbourg - Karlsruhe",1,"< >","continuous","Signal","T","LT","S","W","D","C,,","R,,",",B,","O,,",43,"Y","Major","Planned","Y"]
["CFR",53,"Appenweier - Karlsruhe (div.)",2,">","periodical","Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,",53,"N","High","Coordination","N"]
["SŽCZ",54,"Karlsruhe - Bruchsal",3,"<","periodical continuous","Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",54,null,"Medium","Consultation"]
["MÁV",55,"Bruchsal - Mannheim",4,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",55,null,"Minor","Published"]
["ŽSR",56,"Karlsruhe - Mannheim",5,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",56,null,"Unclassified","Canceled"]
["DB Netz AG",80,"Mannheim - Darmstadt",6,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",80]
["ÖBB-Infra",81,"Mannheim - Gr. Gerau - Fr.",7,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",81]
["SNCF Reseau",87,"Darmstadt - Frankfurt",8,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,87]
[null,null,"Frankfurt - Aschaffenburg",9,null,null,"Others",null,null,null,null,null,null,null,null,null,54.81]
[null,null,"Darmstadt - Aschaffenburg",10,null,null,null,null,null,null,null,null,null,null,null,null,80.81]
[null,null,"Aschaffenburg - Gemünden",11,null,null,null,null,null,null,null,null,null,null,null,null,"54,80"]
[null,null,"Gemünden - Bamberg - Nürnberg",12,null,null,null,null,null,null,null,null,null,null,null,null,"55,56"]
[null,null,"Gemünden - Würzburg - Nürnberg",13,null,null,null,null,null,null,null,null,null,null,null,null,"54,81"]
[null,null,"Nürnberg - Regensburg",14,null,null,"Signal",null,null,null,null,null,null,null,null,null,"56,81"]
[null,null,"Regensburg - München",15,null,null,"Switch",null,null,null,null,null,null,null,null,null,"55,81"]
[null,null,"Regensburg - Wels",16,null,null,"Catenary",null,null,null,null,null,null,null,null,null,"43,55"]
[null,null,"Bruchsal - Mühlacker",17,null,null,"Track & Rail",null,null,null,null,null,null,null,null,null,"43,81"]
[null,null,"Karlsruhe - Stuttgart",18,null,null,"Tunnel"]
[null,null,"Stuttgart - München",19,null,null,"Bridge"]
[null,null,"München - Rosenheim - Salzburg ",20,null,null,"Miscellaneous*"]
[null,null,"München - Mühld. - Freilassing",21,null,null,"Maintenance"]
[null,null,"Nürnberg - Plzen",22,null,null,"Others**"]
[null,null,"Regensburg - Plzen",23]
[null,null,"Plzen - Praha",24]
[null,null,"Praha - Choceň",25]
[null,null,"Praha - Hr. Králové - Choceň",26]
[null,null,"Choceň - Hranice na Moravě",27]
[null,null,"Hranice na Moravě - Žilina",28]
[null,null,"Hranice na Moravě - Ostrava",29]
[null,null,"Ostrava - Český Těšín",30]
[null,null,"Ostr. - Dětmarovice - Č. Těšín",31]
[null,null,"Český Těšín - Žilina",32]
[null,null,"Žilina - Košice",33]
[null,null,"Košice - Čierna nad Tisou",34]
[null,null,"Čierna nad Tisou - Chop",35]
[null,null,"Košice - Haniska pri Košiciach",36]
[null,null,"Haniska pri Košic. - Maťovce",37]
[null,null,"Salzburg - Wels",38]
[null,null,"Wels - Linz",39]
[null,null,"Wels - Traun - Linz",40]
[null,null,"Linz - Wien",41]
[null,null,"Wien - Parndorf",42]
[null,null,"Parndorf - Bratislava",43]
[null,null,"Parndorf - Hegyeshalom",44]
[null,null,"Wien - Sopron",45]
[null,null,"Sopron - Győr",46]
[null,null,"Bratislava - Hegyeshalom",47]
[null,null,"Hegyeshalom - Györ",48]
[null,null,"Györ - Budapest",49]
[null,null,"Budapest - Újszász - Szolnok",50]
[null,null,"Budapest - Cegléd - Szolnok",51]
[null,null,"Szolnok - Arad",52]
[null,null,"Szolnok - Cluj",53]
[null,null,"Cluj - Coșlariu",54]
[null,null,"Arad - Brașov",55]
[null,null,"Brașov - Bucuresti",56]
[null,null,"Arad - Craiova",57]
[null,null,"Craiova - Bucuresti",58]
[null,null,"Bucuresti - Constanţa",59]
[null,null,"Ploiești triaj - Fetești",60]
[null,null,"Simeria - Filiasi",61]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}