{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":7,"defined_names":5,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Schedule","index":1,"n_rows":1648,"n_cols":45,"rows_kept":1648,"cut":false,"hidden":false,"merged":[[2,43,2,44],[1,23,1,27],[1,30,2,30],[1,36,2,36],[1,37,2,37],[1,38,2,38],[1,39,2,39],[1,40,2,40],[1,41,2,41],[1,42,2,42],[1,34,2,34],[1,4,2,4],[1,15,2,15],[0,35,0,36],[0,37,0,38],[0,39,0,40],[1,16,2,16],[1,2,2,2],[1,1,2,1],[1,3,2,3],[1,33,2,33],[1,32,2,32],[1,31,2,31],[1,29,2,29],[1,28,2,28],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22],[1,17,2,17]]}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day\n(character of timely closure)","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In annual timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"PLC\n(ÖBB)"]
[null,80,"21E441A88D0AC.03","Bruchsal - Mannheim","< >","Darmstadt Hbf","Hemsbach",2022,2022,1,1,"2022-01-08T23:00:00","23:00:00","2022-01-09T05:00:00","05:00:00","6 h","continuous","Signal","T",null,null,null,null,",,X","X,X,","","0,,","X,X,","Arbeiten an LST-Anlagen ETCS Kor Rhine-Alpine TP Mitte",null,"N","305056.03","2020-04-27T06:40:00",null,"1,2,3,4,5,6,7",1]
[null,80,"227953E139FC6.01","Bruchsal - Mannheim","< >","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,2,3,"2022-01-14T23:45:00","23:45:00","2022-01-17T04:20:00","04:20:00","2 d, 05 h","continuous","Miscellaneous","T",null,null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Kabelarbeiten ETCS Str 3601 RGCH-RMF+RMF-RGCH / SEV",null,"N","106065.01","2021-03-31T11:48:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22275E9244167.05","Bruchsal - Mannheim",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,4,5,"2022-01-30T13:00:00","13:00:00","2022-01-31T05:00:00","05:00:00","16 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,X,","Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","105037.05","2020-06-12T09:32:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441DD319AC.02","Bruchsal - Mannheim","< >","Bickenbach Nord","Bickenbach Nord",2022,2022,11,13,"2022-03-20","00:00:00","2022-04-02T18:00:00","18:00:00","13 d, 18 h","continuous","Switch",null,"ST",null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Weichenerneuerung mit PSS Bf Bickenbach, Weichen 1-3 und Gleis 12",null,"N","305179.02","2020-04-27T06:41:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E34C1AC.01","Bruchsal - Mannheim","< >","Darmstadt-Eberstadt","Bickenbach (Bergstr)",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-03-28T05:00:00","05:00:00","2 d, 08 h","continuous","Switch","T",null,null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Weichenerneuerung mit PSS Bf Bickenbach, Weichen 1-3 und Gleis 12",null,"N","305193.01","2020-06-08T11:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44727CAF2C.01","Bruchsal - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,12,14,"2022-03-25T22:00:00","22:00:00","2022-04-07T23:00:00","23:00:00","13 d, 01 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","X,,","","0,0,","X,,","Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE",null,"N","306237.01","2021-04-19T11:11:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E34C1AC.03","Bruchsal - Mannheim",">","Bickenbach Nord","Zwingenberg (Bergstr)",2022,2022,13,13,"2022-03-28T05:00:00","05:00:00","2022-04-02T05:00:00","05:00:00","5 d","continuous","Switch",null,"LT",null,null,null,",X,X","X,X,","","0,0,","X,X,","Weichenerneuerung mit PSS Bf Bickenbach, Weichen 1-3 und Gleis 12",null,"N","305193.03","2020-06-08T11:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"222770DCCE8E7.03","Bruchsal - Mannheim","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,13,13,"2022-03-28T21:00:00","21:00:00","2022-03-29T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,","","0,,","X,X,","Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","105039.03","2020-06-12T10:42:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E5960AC.01","Bruchsal - Mannheim","< >","Darmstadt-Eberstadt","Zwingenberg (Bergstr)",2022,2022,13,13,"2022-03-28T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","1 d","periodical","Switch","T",null,null,null,null,",X,X","X,X,","","0,,","X,X,","Weichenerneuerung mit PSS Bf Bickenbach, Weichen 1-3 und Gleis 12",null,"N","305199.01","2020-04-27T06:41:00",null,"1,2,3",1]
[null,80,"2221A2B0422A7.01","Bruchsal - Mannheim","< >","Darmstadt-Eberstadt","Zwingenberg (Bergstr)",2022,2022,13,13,"2022-03-31T21:00:00","21:00:00","2022-04-02T05:00:00","05:00:00","16 h","periodical","Switch","T",null,null,null,null,",X,X","X,X,","","0,,","X,X,","Weichenerneuerung mit PSS Bf Bickenbach, Weichen 1-3 und Gleis 12",null,"N","105031.01","2020-06-08T10:58:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E904F2C.03","Bruchsal - Mannheim","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,14,16,"2022-04-04T18:00:00","18:00:00","2022-04-18T18:00:00","18:00:00","14 d","continuous","Track & Rail",null,"ST",null,null,null,"","X,,","","0,,","X,,","Gleiserneuerung mit BR, PSS und TE GE Bensheim - Bensheim-Auerbach",null,"N","305207.03","2020-06-15T12:20:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E9C842C.01","Bruchsal - Mannheim","<","Bensheim","Bensheim-Auerbach",2022,2022,14,15,"2022-04-06T06:00:00","06:00:00","2022-04-15T21:00:00","21:00:00","9 d, 15 h","continuous","Track & Rail",null,"LT",null,null,null,",X,X","X,X,","","0,,","X,X,","Gleiserneuerung mit BR, PSS und TE GE Bensheim - Bensheim-Auerbach",null,"N","305209.01","2020-06-15T13:06:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E441E9C842C.03","Bruchsal - Mannheim","< >","Zwingenberg (Bergstr)","Heppenheim Nord",2022,2022,14,15,"2022-04-06T22:00:00","22:00:00","2022-04-13T04:45:00","04:45:00","1 d, 23 h","periodical","Track & Rail","T",null,null,null,null,",X,X","X,X,","","0,,","X,X,","Gleiserneuerung mit BR, PSS und TE GE Bensheim - Bensheim-Auerbach",null,"N","305209.03","2020-06-15T13:06:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44ADCE3B2C.01","Bruchsal - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,33,36,"2022-08-15T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","7 d, 07 h","periodical","Track & Rail","T",null,null,null,null,",,X","X,X,",",x,","0,0,0","X,X,","Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","306034.01","2020-07-15T10:25:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E442AC0BB4C.03","Bruchsal - Mannheim","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,47,"2022-11-07T06:00:00","06:00:00","2022-11-24T18:00:00","18:00:00","17 d, 12 h","continuous","Switch",null,"ST",null,null,null,",X,","X,X,",",x,","0,0,","X,X,","Weichenerneuerung Weichen 326, 331 und 332",null,"N","305652.03","2020-04-27T06:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E442B9C754C.02","Bruchsal - Mannheim","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T04:00:00","04:00:00","2 d","continuous","Switch",null,"ST",null,null,null,"X,,X","X,X,","","0,0,","X,X,","Weichenerneuerung Weichen 326, 331 und 332",null,"N","305683.02","2020-04-27T06:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"222606F589C6C.02","Darmstadt - Aschaffenburg","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2022,2022,8,8,"2022-02-21T04:30:00","04:30:00","2022-02-26","00:00:00","4 d, 20 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","","","","","Gleiserneuerung BK.22.0651  GE Gl 004 NAH(IB) in Aschaffenbg Hbf",null,"N","105035.02","2020-06-11T11:25:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E442AD4916C.02","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,46,"2022-11-09T05:00:00","05:00:00","2022-11-14T05:00:00","05:00:00","5 d","continuous","Switch",null,"ST",null,null,null,",,X","","","","","Weichenerneuerung Weichen 326, 331 und 332",null,"N","305655.02","2020-04-27T06:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A342F38C.01","Karlsruhe - Stuttgart",">","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2022,2022,21,23,"2022-05-27T21:00:00","21:00:00","2022-06-10T21:00:00","21:00:00","14 d","continuous","Signal",null,"LT",null,null,null,",X,X",",X,X",",x,x",",0,0",",X,X","Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","306735.01","2020-06-14T16:22:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A342F38C.02","Karlsruhe - Stuttgart","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,21,23,"2022-05-27T23:00:00","23:00:00","2022-06-10T05:00:00","05:00:00","3 d, 12 h","periodical","Signal","T",null,null,null,null,",X,X",",X,X",",x,x",",0,0",",X,X","Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","306735.02","2020-06-14T16:22:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A38309CC.02","Karlsruhe - Stuttgart","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,21,22,"2022-05-28T23:00:00","23:00:00","2022-06-03T05:00:00","05:00:00","1 d, 12 h","periodical","Track & Rail","T",null,null,null,null,",X,",",X,X",",x,x",",0,0",",X,X","Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","306742.02","2020-06-15T07:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447B0BD8AC.01","Stuttgart - München","< >","Eislingen (Fils)","Gingen (Fils) Süd",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,X,","sonstige Arbeiten Rückbau Altbestand - Rückbau alte Signalfundamente+Kabel, SEV",null,"N","306503.01","2020-06-13T23:58:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447A287D8C.03","Stuttgart - München","< >","Geislingen (Steige)","Amstetten (Württ)",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,X,","Durchlassarbeiten Erneuerung Durchlass Str 4700 km 65,954",null,"N","306475.03","2020-06-08T00:04:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447B02B0EC.01","Stuttgart - München","< >","Eislingen (Fils)","Göppingen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,X,","Schienenerneuerung SE2 Eislingen-Göppingen",null,"N","306770.01","2020-06-08T00:09:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447BD0AF4C.01","Stuttgart - München","< >","Eislingen (Fils)","Süßen",2022,2022,16,17,"2022-04-22T21:00:00","21:00:00","2022-04-25T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,X,","sonstige Arbeiten Rückbau Altbestand - Rückbau alte Signalfundamente + Kabel, SEV",null,"N","306527.01","2020-06-13T23:59:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A2E5DF6C.01","Stuttgart - München","< >","Beimerstetten","Neu-Ulm",2022,2022,21,22,"2022-05-26","00:00:00","2022-05-30T04:00:00","04:00:00","4 d, 04 h","continuous","Signal","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,,","Arbeiten an LST-Anlagen ESTW Ulm in Ulm Hbf",null,"N","306724.01","2020-04-27T07:13:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4470D9114C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,7,8,"2022-02-18T21:15:00","21:15:00","2022-02-25T21:15:00","21:15:00","7 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,",",x,","0,0,","X,X,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916, SEV in Günzburg",null,"N","306185.01","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"229ECC9518EEA.01","Stuttgart - München","< >","Günzburg","Neuoffingen",2022,2022,7,8,"2022-02-18T21:15:00","21:15:00","2022-02-25T21:15:00","21:15:00","7 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,",",x,","0,0,","X,X,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","106081.01","2020-09-02T16:09:00",null,"1,2,3,4,5,6,7",1]
[null,80,"229ECC9518EEA.02","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,7,8,"2022-02-18T21:15:00","21:15:00","2022-02-25T21:15:00","21:15:00","7 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,",",x,","0,0,","X,X,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","106081.02","2020-09-02T16:09:00",null,"1,2,3,4,5,6,7",1]
[null,80,"229ECC9518EEA.03","Stuttgart - München","< >","Unterfahlheim","Günzburg",2022,2022,7,8,"2022-02-18T21:15:00","21:15:00","2022-02-25T21:15:00","21:15:00","7 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,",",x,","0,0,","X,X,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","106081.03","2020-09-02T16:09:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44424A6D6C.02","Stuttgart - München","< >","Westheim (Schwab)","Augsburg Hbf",2022,2022,20,24,"2022-05-17T21:00:00","21:00:00","2022-06-17T05:00:00","05:00:00","10 d, 08 h","periodical","Bridge","T",null,null,null,null,"","X,X,X","","0,0,","X,X,X","Brückenarbeiten Sanierung Kreuzungsbauwerk Augsburg Oberhausen",null,"N","307181.02","2020-05-06T10:56:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A1C0E76C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-03T21:00:00","21:00:00","14 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,",",x,","0,0,","X,X,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","306688.01","2020-04-27T07:13:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44C1D09B4C.01","Stuttgart - München","< >","Günzburg","Günzburg",2022,2022,47,47,"2022-11-26T21:00:00","21:00:00","2022-11-27T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,,","Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","306544.01","2021-06-10T12:11:00",null,"1,2,3,4,5,6,7",1]
[null,80,"227953E139FC6.03","Karlsruhe - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,2,3,"2022-01-14T23:45:00","23:45:00","2022-01-17T04:20:00","04:20:00","2 d, 05 h","continuous","Miscellaneous",null,"ST",null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Kabelarbeiten ETCS Str 3601 RGCH-RMF+RMF-RGCH / SEV",null,"N","106065.03","2021-03-31T11:48:00",null,"1,2,3,4,5,6,7",1]
[null,80,"228D6B4D0A086.03","Karlsruhe - Mannheim","< >","Mannheim Ziehbrunnen","Schwetzingen",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,X,",",x,","0,0,","X,X,","Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","106078.03","2020-08-21T15:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44752539EC.01","Karlsruhe - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,14,15,"2022-04-07T23:00:00","23:00:00","2022-04-15T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","X,,","","0,0,","X,,","Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE",null,"N","306361.01","2021-04-19T11:16:00",null,"1,2,3,4,5,6,7",1]
[null,80,"228D6B4D0A086.01","Karlsruhe - Mannheim","< >","Mannheim-Rheinau","Waghäusel",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,X,",",x,","0,0,","X,X,","Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","106078.01","2020-08-21T15:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"228D6B4D0A086.02","Karlsruhe - Mannheim","< >","Schwetzingen","Oftersheim",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","106078.02","2020-08-21T15:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447238050C.01","Karlsruhe - Mannheim","< >","Schwetzingen","Schwetzingen",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","X,X,","","0,0,0","X,,X","Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","306228.01","2021-03-04T10:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447238050C.04","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2022,2022,9,11,"2022-03-04T23:00:00","23:00:00","2022-03-17T05:59:00","05:59:00","12 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","X,X,X","","0,0,0","X,,X","Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","306228.04","2021-03-04T10:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44726D6CEC.01","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2022,2022,9,11,"2022-03-04T23:00:00","23:00:00","2022-03-17T05:59:00","05:59:00","12 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,,X","Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","306235.01","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44762D340C.05","Karlsruhe - Mannheim","< >","Hockenheim","Hockenheim",2022,2022,12,14,"2022-03-25T23:00:00","23:00:00","2022-04-07T05:00:00","05:00:00","12 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","X,X,X","","0,0,0","X,,X","Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","306348.05","2020-04-27T07:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4476A7460C.01","Karlsruhe - Mannheim","<","Waghäusel","Hockenheim",2022,2022,12,14,"2022-03-25T23:00:00","23:00:00","2022-04-07T05:00:00","05:00:00","12 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,X,X","","0,0,0","X,,X","Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","306363.01","2020-04-27T07:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44795464AC.02","Karlsruhe - Mannheim","< >","Waghäusel","Waghäusel",2022,2022,17,23,"2022-04-29T08:00:00","08:00:00","2022-06-07T12:00:00","12:00:00","39 d, 04 h","continuous","Bridge",null,"ST",null,null,null,"","X,,","","0,,","X,,","Brückenarbeiten Sanierung SÜ Mannheimer Straße km 30,731",null,"N","306448.02","2020-06-02T14:43:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44795464AC.03","Karlsruhe - Mannheim","< >","Waghäusel","Waghäusel",2022,2022,17,23,"2022-04-29T08:00:00","08:00:00","2022-06-07T12:00:00","12:00:00","39 d, 04 h","continuous","Bridge",null,"ST",null,null,null,"","X,,","","0,,","X,,","Brückenarbeiten Sanierung SÜ Mannheimer Straße km 30,731",null,"N","306448.03","2020-06-02T14:43:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E446EADA5CC.03","Karlsruhe - Mannheim","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,","","0,0,","X,X,","Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 2",null,"N","306321.03","2020-04-27T07:00:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44724EE86C.01","Karlsruhe - Mannheim","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",,x","0,0,0","X,,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306231.01","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44724EE86C.02","Karlsruhe - Mannheim","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",,x","0,0,0","X,,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306231.02","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44724EE86C.05","Karlsruhe - Mannheim","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,9,10,"2022-03-06T21:00:00","21:00:00","2022-03-07T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X","","0,0,0","X,,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","306231.05","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4472EC12CC.02","Karlsruhe - Mannheim","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",x,x","0,0,0","X,X,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306251.02","2020-06-08T16:23:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4472EC12CC.03","Karlsruhe - Mannheim","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",x,x","0,0,0","X,X,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306251.03","2020-06-08T16:23:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4473600A4C.01","Karlsruhe - Mannheim","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,10,11,"2022-03-07T21:00:00","21:00:00","2022-03-17T05:00:00","05:00:00","9 d, 08 h","continuous","Bridge",null,"ST",null,null,null,",,X","X,,","","0,,","X,,","Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 3a",null,"N","306265.01","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22C4A6B4B1186.02","Karlsruhe - Mannheim","<","Bashaide","Karlsruhe-Dammerstock",2022,2022,10,11,"2022-03-12T07:30:00","07:30:00","2022-03-14T05:30:00","05:30:00","1 d, 22 h","continuous","Switch",null,"LT",null,null,null,",,X","X,X,X","","0,0,","X,X,X","Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","106113.02","2020-09-28T12:04:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22C4A6B4B1186.04","Karlsruhe - Mannheim","<","Bashaide","Karlsruhe Hbf",2022,2022,10,11,"2022-03-12T23:30:00","23:30:00","2022-03-14T05:30:00","05:30:00","1 d, 06 h","continuous","Switch",null,"LT",null,null,null,",,X","X,X,X","","0,0,","X,X,X","Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","106113.04","2020-09-28T12:04:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4472EC12CC.05","Karlsruhe - Mannheim","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,13,13,"2022-03-30T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X","","0,0,0","X,,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","306251.05","2020-06-08T16:23:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44794CC38C.01","Karlsruhe - Mannheim",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,17,"2022-04-07T05:00:00","05:00:00","2022-04-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,X","","0,0,0","X,X,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306447.01","2020-06-08T16:32:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447ABE06CC.01","Karlsruhe - Mannheim","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,15,17,"2022-04-13T21:00:00","21:00:00","2022-04-26T05:00:00","05:00:00","12 d, 08 h","continuous","Bridge",null,"ST",null,null,null,"","X,,","","0,,","X,,","Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 3b",null,"N","306747.01","2020-04-27T07:03:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44794CC38C.03","Karlsruhe - Mannheim","< >","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,17,17,"2022-04-30T21:00:00","21:00:00","2022-05-01T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X","","0,0,0","X,X,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","306447.03","2020-06-08T16:32:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447D88234C.01","Karlsruhe - Mannheim",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,17,18,"2022-05-01T05:00:00","05:00:00","2022-05-04T23:59:00","23:59:00","3 d, 19 h","continuous","Bridge",null,"LT",null,null,null,"","","","","","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306577.01","2020-07-30",null,"1,2,3,4,5,6,7",1]
[null,80,"21E446CCE858C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:00:00","21:00:00","2022-01-21T05:00:00","05:00:00","2 d, 08 h","periodical","Miscellaneous","T",null,null,null,null,",,X","X,X,X",",x,","0,0,0","X,X,","Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","306069.01","2020-04-27T07:00:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E446CD626AC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:00:00","21:00:00","2022-01-21T05:00:00","05:00:00","2 d, 08 h","periodical","Bridge","T",null,null,null,null,",,X","X,X,X",",x,","0,0,0","X,X,","Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","306070.01","2020-04-27T07:00:00",null,"1,2,3,4,5,6,7",1]
[null,80,"229C2B72D2FAA.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:00:00","21:00:00","2022-01-21T05:00:00","05:00:00","2 d, 08 h","periodical","Miscellaneous","T",null,null,null,null,"","","","","","Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","229C2B72D2FAA.01","2020-08-31T16:10:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447B1FAECC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,X,X",",x,","0,0,0","X,X,","Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","306505.01","2020-05-26T08:42:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447B28D68C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,X,X",",x,","0,0,0","X,X,","Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","306506.01","2020-05-26T10:10:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E447B31FE4C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X",",x,","0,0,0","X,X,","Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","306507.01","2020-05-26T08:47:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44B3C5A2CC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,,X","X,X,X",",x,","0,0,0","X,X,X","Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","306347.01","2020-04-27T07:17:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44B3CD43EC.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,,X","X,X,X",",x,","0,0,0","X,X,","Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","306342.01","2020-04-27T07:17:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44B3D4E50C.01","Karlsruhe - Stuttgart","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Bridge","T",null,null,null,null,"X,,X","X,X,X",",x,","0,0,0","X,X,X","Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","306188.01","2020-04-27T07:17:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44B4FB63AC.01","Karlsruhe - Stuttgart","<","Bietigheim-Bissingen","Sachsenheim",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-04-01T20:59:00","20:59:00","7 d","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,X,X",",x,x","0,0,0","X,X,X","sonstige Arbeiten PSS Bietigheim-Sachsenheim",null,"N","306220.01","2020-06-04T14:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A2DE3E4C.02","Karlsruhe - Stuttgart","< >","Vaihingen (Enz)","Vaihingen (Enz)",2022,2022,21,24,"2022-05-27T17:00:00","17:00:00","2022-06-17T16:00:00","16:00:00","20 d, 23 h","continuous","Track & Rail",null,"ST",null,null,null,"",",X,X",",x,x",",,0",",X,X","Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","306723.02","2021-04-07T10:04:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44A59A9F2C.02","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,23,24,"2022-06-12T21:00:00","21:00:00","2022-06-17T05:00:00","05:00:00","4 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,X,X",",x,x","0,0,0","X,X,X","Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","306802.02","2021-04-27T14:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440FC428C.01","Gemünden - Würzburg - Nürnberg","< >","Fürth (Bay) Gbf","Nürnberg Hbf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307143.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440FC428C.02","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Jansenbrücke","Nürnberg Jansenbrücke",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307143.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440FC428C.03","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307143.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440FC428C.05","Gemünden - Würzburg - Nürnberg","< >","Fürth (Bay) Hbf","Mainbernheim",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307143.05","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C2F62EC.01","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,26,26,"2022-06-29","00:00:00","2022-07-02T05:00:00","05:00:00","3 d, 05 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"N","307234.01","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C2F62EC.03","Nürnberg - Plzen","<","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,26,28,"2022-07-02T05:00:00","05:00:00","2022-07-17","00:00:00","14 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X",",,x","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"Y","307234.03","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C7EBB6C.01","Nürnberg - Plzen","< >","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,28,30,"2022-07-17","00:00:00","2022-07-28T05:00:00","05:00:00","11 d, 05 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"N","307246.01","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CAE08CC.03","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2022,2022,29,30,"2022-07-22T23:00:00","23:00:00","2022-07-25T11:00:00","11:00:00","2 d, 12 h","continuous","Switch","T",null,null,null,null,"","","","","","Weichenerneuerung We Lauf rdP W 601, 602",null,"N","307253.03","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C7EBB6C.02","Nürnberg - Plzen","<","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,30,31,"2022-07-28T05:00:00","05:00:00","2022-08-06T05:00:00","05:00:00","9 d","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X","","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"Y","307246.02","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D0E2A2C.04","Nürnberg - Plzen","< >","Neuhaus (Pegnitz)","Pegnitz",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T06:00:00","06:00:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,",",,X","Gleiserneuerung Neuhaus-Pegnitz (Ri+Gri), WE/GE Bf Pegnitz, GE Bf Neuhaus",null,"Y","307266.04","2020-06-12T14:48:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D15CB4C.01","Nürnberg - Plzen","< >","Neuhaus (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,30,39,"2022-07-29T22:00:00","22:00:00","2022-09-28T06:00:00","06:00:00","60 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,",,X","","","",",,X","Gleiserneuerung Neuhaus-Pegnitz (Ri+Gri), WE/GE Bf Pegnitz, GE Bf Neuhaus",null,"N","307267.01","2020-06-12T15:30:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D15CB4C.04","Nürnberg - Plzen","< >","Pegnitz","Neuhaus (Pegnitz)",2022,2022,31,37,"2022-08-01T06:00:00","06:00:00","2022-09-12T05:00:00","05:00:00","41 d, 23 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X",",,x","0,,",",,X","Gleiserneuerung Neuhaus-Pegnitz (Ri+Gri), WE/GE Bf Pegnitz, GE Bf Neuhaus",null,"Y","307267.04","2020-06-12T15:30:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C7EBB6C.04","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,31,32,"2022-08-06T05:00:00","05:00:00","2022-08-08T05:00:00","05:00:00","2 d","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,0","X,,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"N","307246.04","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D72DF6C.03","Nürnberg - Plzen",">","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,32,34,"2022-08-08T05:00:00","05:00:00","2022-08-23","00:00:00","14 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X",",,x","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"Y","307280.03","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D72DF6C.04","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,34,35,"2022-08-23","00:00:00","2022-09-02T05:00:00","05:00:00","10 d, 05 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,0","X,,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"N","307280.04","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E1AB82C.02","Nürnberg - Plzen",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,35,37,"2022-08-29T06:00:00","06:00:00","2022-09-12T05:00:00","05:00:00","13 d, 23 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X",",,x","0,,0",",,X","Gleiserneuerung Neuhaus-Pegnitz (Ri+Gri), WE/GE Bf Pegnitz, GE Bf Neuhaus",null,"Y","307302.02","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E4E996C.02","Nürnberg - Plzen",">","Lauf (rechts Pegnitz)","Neunkirchen a Sand",2022,2022,35,36,"2022-09-02T05:00:00","05:00:00","2022-09-08","00:00:00","5 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X","","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"Y","307310.02","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E4E996C.03","Nürnberg - Plzen","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,36,37,"2022-09-08","00:00:00","2022-09-12T05:00:00","05:00:00","4 d, 05 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,X","","0,,0",",,X","Untergrundverbesserung Heuchlinger Damm   Bahn-km 17,800 bis 18,200 auf der Strecke 5903 Nürnberg",null,"N","307310.03","2020-04-27T06:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444EC8AB6C.03","Nürnberg - Plzen","< >","Neuhaus (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,38,38,"2022-09-19T06:00:00","06:00:00","2022-09-22T06:00:00","06:00:00","3 d","continuous","Track & Rail",null,"ST",null,null,null,",,X","","","","","Gleiserneuerung Neuhaus-Pegnitz (Ri+Gri), WE/GE Bf Pegnitz, GE Bf Neuhaus",null,"N","307327.03","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4450DEBA2C.04","Nürnberg - Plzen","< >","Schnabelwaid","Pegnitz",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Track & Rail","T",null,null,null,null,"X,,X","X,,X","","0,,0","X,,","Gleiserneuerung Ge/We Schnabelwaid Gl 3, 4 u. W 1, 2",null,"N","307393.04","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44501FFE0C.02","Nürnberg - Plzen","< >","Marktredwitz","Schirnding Grenze",2022,2022,42,46,"2022-10-21T22:35:00","22:35:00","2022-11-16T04:20:00","04:20:00","25 d, 06 h","continuous","Track & Rail","T",null,null,null,null,",,X","X,,","","0,,","X,,","Gleiserneuerung WE Marktredwitz-Landesgrenze",null,"N","307370.02","2020-06-15T14:42:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4450CF77EC.02","Nürnberg - Plzen","< >","Schnabelwaid","Kirchenlaibach",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Bridge","T",null,null,null,null,"","","","","","Brückenarbeiten EÜ Speichersdorf  km 93,183",null,"N","307391.02","2020-06-15T13:25:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443F9119CC.01","Stuttgart - München",">","München-Pasing","München Hbf",2022,2022,11,12,"2022-03-18T23:00:00","23:00:00","2022-03-21T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,X,X",",x,","0,0,","X,X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307089.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443FC3746C.01","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,12,13,"2022-03-25T23:00:00","23:00:00","2022-03-28T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,",X,X","X,X,X",",x,","0,0,0","X,X,","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307097.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44400CB26C.02","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,13,14,"2022-04-01T23:00:00","23:00:00","2022-04-04T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,",X,X","X,X,X",",x,","0,0,","X,X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307109.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44407F234C.02","Stuttgart - München","<","München Hbf","München-Pasing",2022,2022,14,15,"2022-04-08T23:00:00","23:00:00","2022-04-11T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307127.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444BD0C82C.03","Stuttgart - München","< >","München Hbf","München-Pasing",2022,2022,23,33,"2022-06-11T23:00:00","23:00:00","2022-08-15T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,",,X","X,X,X","","0,0,","X,X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307219.03","2020-04-27T06:52:00",null,"6,7",1]
[null,80,"21E444BE9322C.02","Stuttgart - München","< >","München-Pasing","München Hbf",2022,2022,24,33,"2022-06-13T23:00:00","23:00:00","2022-08-18T05:00:00","05:00:00","7 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,",,X","X,X,X","","0,0,","X,X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307223.02","2020-04-27T06:52:00",null,"1,2,3",1]
[null,80,"21E443EDE92AC.02","München - Rosenheim - Salzburg ","< >","Grafing Bahnhof","Grafing Bahnhof",2022,2022,9,12,"2022-02-28T04:40:00","04:40:00","2022-03-27T23:59:00","23:59:00","27 d, 19 h","continuous","Miscellaneous",null,"ST",null,null,null,",,X","","",",,0","","Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst",null,"N","307061.02","2021-03-25T10:14:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444012CCEC.01","München - Rosenheim - Salzburg ","< >","München Ost Pbf","München Süd",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T06:00:00","06:00:00","1 d","periodical","Bridge","T",null,null,null,null,"X,X,X","X,X,X","","0,0,0","X,,X","Brückenarbeiten EÜ Balanstraße km 9,054",null,"N","307110.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440ACEA0C.01","München - Rosenheim - Salzburg ","<","München Ost Pbf","München Süd",2022,2022,14,15,"2022-04-09T05:00:00","05:00:00","2022-04-11T05:00:00","05:00:00","2 d","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,X","","0,0,0","X,X,X","Brückenarbeiten EÜ Balanstraße km 9,054",null,"N","307133.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440E86C6C.03","München - Rosenheim - Salzburg ","< >","Grafing Bahnhof","Grafing Bahnhof",2022,2022,15,22,"2022-04-11T04:40:00","04:40:00","2022-05-30T01:40:00","01:40:00","48 d, 21 h","continuous","Miscellaneous",null,"ST",null,null,null,",,X","","",",,0","","Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst",null,"N","307141.03","2020-06-05T13:17:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44426150CC.02","München - Rosenheim - Salzburg ","<","München Ost Pbf","München Süd",2022,2022,20,24,"2022-05-20T22:00:00","22:00:00","2022-06-16T04:00:00","04:00:00","26 d, 06 h","continuous","Bridge",null,"LT",null,null,null,",X,X","X,X,X",",,x","0,0,0","X,X,X","Brückenarbeiten EÜ Pilgesheimer Brücke - km 7,232",null,"Y","307184.02","2020-06-15T08:58:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444B6D998C.03","München - Rosenheim - Salzburg ",">","Rückstetten","Teisendorf",2022,2022,20,21,"2022-05-20T23:30:00","23:30:00","2022-05-28T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,"LT",null,null,null,",X,X","X,X,X",",,x","0,,0","X,X,X","Gleiserneuerung mit BR, PSS und TE GE PSS TE Rückstetten - Teisendorf km 67,700-69,100",null,"Y","307206.03","2020-06-09T08:10:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444B753AAC.05","München - Rosenheim - Salzburg ","<","Teisendorf","Rückstetten",2022,2022,21,24,"2022-05-27T23:30:00","23:30:00","2022-06-16T05:30:00","05:30:00","19 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,",X,X","X,X,X",",,x","0,,0","X,X,X","Gleiserneuerung mit BR, PSS und TE GE PSS TE Teisendorf - Rückstetten km 69,4 -64,7",null,"Y","307207.05","2020-06-09T08:55:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44426150CC.04","München - Rosenheim - Salzburg ",">","München Süd","München Ost Pbf",2022,2022,24,28,"2022-06-15T23:00:00","23:00:00","2022-07-14T04:00:00","04:00:00","28 d, 05 h","continuous","Bridge",null,"LT",null,null,null,",X,X","X,X,X",",,x","0,0,0","X,X,X","Brückenarbeiten EÜ Pilgesheimer Brücke - km 7,232",null,"Y","307184.04","2020-06-15T08:58:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C15724C.02","München - Rosenheim - Salzburg ",">","Bergen Rumgraben","Traunstein",2022,2022,24,28,"2022-06-16T22:00:00","22:00:00","2022-07-13T05:00:00","05:00:00","26 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","","",",0,0","","Stützmauerarbeiten 5703 SW 47,201 rdB Schwergew.mauer-Ern",null,"Y","307230.02","2020-10-06T16:20:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C1B8CCC.02","München - Rosenheim - Salzburg ",">","Bergen Rumgraben","Traunstein",2022,2022,24,28,"2022-06-16T22:00:00","22:00:00","2022-07-13T05:00:00","05:00:00","26 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",X,X","X,X,X","","0,0,0","X,X,X","Gleiserneuerung mit BR, PSS und TE GE PSS TE Rumgraben-Traunstein km 46,3-52,6",null,"Y","307231.02","2020-10-05T12:38:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E8D290C.05","München - Rosenheim - Salzburg ","< >","Grafing Bahnhof","Grafing Bahnhof",2022,2022,37,45,"2022-09-13T06:00:00","06:00:00","2022-11-11T22:00:00","22:00:00","40 d","periodical","Miscellaneous",null,"ST",null,null,null,"","X,,","","0,,","X,,","Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst",null,"N","307318.05","2020-06-05T14:20:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4450F7242C.01","München - Rosenheim - Salzburg ","< >","München Ost Pbf","München Süd",2022,2022,43,44,"2022-10-29T10:00:00","10:00:00","2022-11-03T20:00:00","20:00:00","5 d, 10 h","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,X",",x,","0,0,0","X,X,X","Brückenarbeiten EÜ Balanstraße km 9,054",null,"N","307396.01","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21B6240091198.04","Nürnberg - Regensburg",">","Beratzhausen","Undorf",2021,2021,49,50,"2021-12-12","00:00:00","2021-12-13T10:30:00","10:30:00","1 d, 10 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,X,X","","0,0,0","X,,X","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","107640.04","2021-01-11T10:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"2321A03AE1D7E.01","Regensburg - Wels","< >","Obertraubling","Regensburg Ost",2022,2022,1,1,"2022-01-08T22:05:00","22:05:00","2022-01-09T05:45:00","05:45:00","8 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X",",,x","0,0,0","X,,","Brückenarbeiten Erneuerung SÜ A3 Burgweinting_Aufbau Schutzgerüst Gl.1+2 in Regensbg Ost",null,"N","107914.01","2020-12-01T08:56:00",null,"1,2,3,4,5,6,7",1]
[null,80,"235D6569815D8.01","Nürnberg - Regensburg","< >","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,5,5,"2022-02-05T18:00:00","18:00:00","2022-02-06T12:00:00","12:00:00","18 h","continuous","Catenary","T",null,null,null,null,",X,X","X,X,X","","0,0,0","X,,","Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","107917.01","2021-01-11T10:42:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22101885562B8.01","Nürnberg - Regensburg","<","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,7,8,"2022-02-18T21:35:00","21:35:00","2022-02-23T10:40:00","10:40:00","4 d, 13 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,,X","Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","107857.01","2020-05-27T10:36:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22101885562B8.03","Nürnberg - Regensburg",">","Undorf","Regensburg Bbf",2022,2022,8,9,"2022-02-26T22:35:00","22:35:00","2022-02-28T14:05:00","14:05:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,X,X","Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","107857.03","2020-05-27T10:36:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220D18EABDB18.01","Nürnberg - Regensburg","< >","Deining Üst","Seubersdorf",2022,2022,9,10,"2022-03-03T23:15:00","23:15:00","2022-03-07T04:10:00","04:10:00","3 d, 05 h","continuous","Bridge","T",null,null,null,null,",X,X","X,X,","","0,0,","X,,","Brückenarbeiten Abbruch SÜ Sallmannsdorf, Km 50,811",null,"N","107848.01","2020-05-25T08:14:00",null,"1,2,3,4,5,6,7",1]
[null,80,"221024DAAA898.04","Nürnberg - Regensburg","<","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,9,9,"2022-03-05T17:00:00","17:00:00","2022-03-06T05:00:00","05:00:00","12 h","continuous","Catenary",null,"LT",null,null,null,",X,X","X,X,","","0,0,","X,,","Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","107858.04","2020-05-27T10:29:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443F1707CC.03","Nürnberg - Regensburg",">","Deining Üst","Seubersdorf",2022,2022,10,13,"2022-03-11T22:00:00","22:00:00","2022-03-28T05:00:00","05:00:00","16 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,X,","Gleiserneuerung mit BR und PSS Ge mit BR und PSS, BrSchwellenErn km 52, 587 - 51,100",null,"N","307070.03","2020-06-06T17:00:00",null,"1,2,3,4,5,6,7",1]
[null,80,"221D5FED45D98.01","Regensburg - Wels","< >","Regensburg Hbf","Obertraubling",2022,2022,11,11,"2022-03-19T21:50:00","21:50:00","2022-03-20T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,",,X","X,X,X","","0,0,0","X,,","Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","107865.01","2020-11-12T10:22:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444020888C.02","Nürnberg - Regensburg",">","Beratzhausen","Undorf",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T05:00:00","05:00:00","2 d, 07 h","continuous","Switch",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,,X","Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","307112.02","2020-06-04T16:34:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440B48B2C.01","Nürnberg - Regensburg","< >","Undorf","Parsberg",2022,2022,14,14,"2022-04-09T01:10:00","01:10:00","2022-04-10T16:00:00","16:00:00","1 d, 15 h","continuous","Switch","T",null,null,null,null,",X,X","X,X,","","0,0,","X,,","Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","307134.01","2020-06-06T16:05:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444032D80C.02","Regensburg - Wels","<","Radldorf (Niederbay)","Mangolding",2022,2022,14,15,"2022-04-10","00:00:00","2022-04-11T04:00:00","04:00:00","1 d, 04 h","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,,","","0,0,0",",X,","Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","307115.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440B48B2C.02","Nürnberg - Regensburg","<","Undorf","Parsberg",2022,2022,14,15,"2022-04-10T16:00:00","16:00:00","2022-04-11T12:00:00","12:00:00","20 h","continuous","Switch",null,"LT",null,null,null,",X,X","X,X,","","0,0,0","X,,X","Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","307134.02","2020-06-06T16:05:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444117B9CC.01","Nürnberg - Regensburg","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","Fels-/Hangsanierung FS 37,350-38,200 rdB Parsberg",null,"N","307146.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44411F5AEC.02","Nürnberg - Regensburg","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,X,X","Gleiserneuerung mit BR und PSS Gleiserneuerung Parsberg-Seubersdorf km 37,460-43,494",null,"N","307147.02","2020-06-06T16:30:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4441DB09CC.01","Nürnberg - Regensburg",">","Undorf","Regensburg Bbf",2022,2022,18,19,"2022-05-02T22:00:00","22:00:00","2022-05-12T22:00:00","22:00:00","10 d","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,X,","","0,0,0","X,X,X","Fels-/Hangsanierung FS Los1-3 7,889 - 9,271 ldB Etterzhausen",null,"N","307167.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44421CA6AC.01","Regensburg - Wels","< >","Mangolding","Radldorf (Niederbay)",2022,2022,19,20,"2022-05-13T13:00:00","13:00:00","2022-05-16T05:00:00","05:00:00","2 d, 16 h","continuous","Miscellaneous","T",null,null,null,null,",X,X","X,X,",",x,","0,0,","X,X,","Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","307176.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44421CA6AC.02","Regensburg - Wels","< >","Mangolding","Radldorf (Niederbay)",2022,2022,20,20,"2022-05-16T22:00:00","22:00:00","2022-05-19T05:00:00","05:00:00","21 h","periodical","Miscellaneous","T",null,null,null,null,",,X","X,X,","","0,0,0","X,,","Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","307176.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444FFE6C4C.02","Regensburg - Wels","< >","Obertraubling","Obertraubling",2022,2022,41,42,"2022-10-14T23:00:00","23:00:00","2022-10-23T04:00:00","04:00:00","8 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,"X,,","","","0,,","","Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","307366.02","2020-05-26T12:51:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443F10ED4C.01","Regensburg - München",">","München-Moosach","München-Neulustheim",2022,2022,9,10,"2022-03-05T07:00:00","07:00:00","2022-03-13T22:00:00","22:00:00","2 d, 12 h","periodical","Miscellaneous",null,"LT",null,null,null,"","","","","","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307069.01","2020-04-27T06:49:00",null,"6,7",1]
[null,80,"21E44412E9D2C.01","Regensburg - München","<","München-Neulustheim","München-Moosach",2022,2022,15,16,"2022-04-15T02:40:00","02:40:00","2022-04-18T22:40:00","22:40:00","3 d, 20 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307149.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44417961CC.03","Regensburg - München","< >","München Hbf","München Kanal",2022,2022,16,17,"2022-04-22T23:00:00","23:00:00","2022-04-25T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,",,X",",X,X","",",0,0",",X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307154.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4441B66ACC.01","Regensburg - München","< >","München Kanal","München Hbf",2022,2022,17,18,"2022-04-29T23:00:00","23:00:00","2022-05-02T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,",,X",",X,X","",",0,0",",X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307161.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4441E1244C.01","Regensburg - München","<","München Hbf","München-Moosach",2022,2022,18,19,"2022-05-06T23:00:00","23:00:00","2022-05-09T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"",",X,X","",",0,0",",X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307168.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444268F1EC.01","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,20,21,"2022-05-20T22:00:00","22:00:00","2022-05-23T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,X",",,x","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307185.01","2020-05-26T14:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444268F1EC.05","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,21,21,"2022-05-27T22:00:00","22:00:00","2022-05-29T14:00:00","14:00:00","1 d, 16 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,X",",,x","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307185.05","2020-05-26T14:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444B5E574C.01","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,22,23,"2022-06-03T23:00:00","23:00:00","2022-06-07T05:00:00","05:00:00","3 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,","","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307205.01","2020-05-26T16:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444B5E574C.03","Regensburg - München","< >","Landshut (Bay) Hbf","Moosburg",2022,2022,22,22,"2022-06-04T03:00:00","03:00:00","2022-06-04T17:00:00","17:00:00","14 h","continuous","Miscellaneous","T",null,null,null,null,"X,,X","X,,","","0,,","X,,","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307205.03","2020-05-26T16:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444BA60EAC.03","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,23,24,"2022-06-10T23:00:00","23:00:00","2022-06-13T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,","","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307213.03","2020-05-26T16:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444BD0C82C.01","Regensburg - München","< >","München Kanal","München Hbf",2022,2022,23,33,"2022-06-11T23:00:00","23:00:00","2022-08-15T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,",,X",",X,X","",",,0",",X,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307219.01","2020-04-27T06:52:00",null,"6,7",1]
[null,80,"21E444BA60EAC.05","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-15T23:00:00","23:00:00","2022-06-19T05:00:00","05:00:00","3 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,X",",,x","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307213.05","2020-05-26T16:39:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444BEF4CAC.01","Regensburg - München","< >","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-16T03:00:00","03:00:00","2022-06-16T17:00:00","17:00:00","14 h","continuous","Miscellaneous","T",null,null,null,null,"X,,X","X,,","","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307224.01","2020-05-26T16:41:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444BF5672C.01","Regensburg - München","< >","München-Neulustheim","München Hbf",2022,2022,24,33,"2022-06-16T23:00:00","23:00:00","2022-08-20T05:00:00","05:00:00","5 d","periodical","Miscellaneous","T",null,null,null,null,",X,",",,X","",",,0",",,X","sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","307225.01","2020-04-27T06:52:00",null,"4,5",1]
[null,80,"21E444BFD084C.04","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,24,24,"2022-06-19T05:00:00","05:00:00","2022-06-19T22:00:00","22:00:00","17 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,","",",,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307226.04","2020-05-26T16:48:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C46464C.04","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,26,27,"2022-07-01T22:00:00","22:00:00","2022-07-04T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,X",",,x","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307237.04","2020-05-26T17:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C5A1C6C.03","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,27,27,"2022-07-08T22:00:00","22:00:00","2022-07-10T05:00:00","05:00:00","1 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,X",",,x","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307240.03","2020-05-26T17:15:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CB5A9EC.01","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,28,29,"2022-07-15T22:00:00","22:00:00","2022-07-18T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","X,,","","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307254.01","2020-05-26T17:26:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CB5A9EC.03","Regensburg - München","<","Moosburg","Landshut (Bay) Hbf",2022,2022,29,30,"2022-07-23T22:00:00","22:00:00","2022-07-25T05:00:00","05:00:00","1 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,"X,,X","","","0,,0","X,,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307254.03","2020-05-26T17:26:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D080FAC.01","Regensburg - München",">","Moosburg","Langenbach (Oberbay)",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,,X",",,x","0,,0","X,,","Arbeiten am Bahnübergang Erneuerung BÜ km 53,8",null,"N","307265.01","2020-05-27T16:23:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D01F52C.01","Regensburg - München","< >","Moosburg","Landshut (Bay) Hbf",2022,2022,30,31,"2022-07-29T22:00:00","22:00:00","2022-08-01T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,,X",",,x","0,,0","X,,","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307264.01","2020-05-26T17:31:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D469F4C.01","Regensburg - München","< >","Freising","Landshut (Bay) Hbf",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Arbeiten am Bahnübergang Erneuerung BÜ km 53,8",null,"N","307274.01","2020-05-28T14:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D375D0C.03","Regensburg - München","< >","Landshut (Bay) Hbf","Freising",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T10:00:00","10:00:00","12 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,,X",",,x","0,,0",",,X","sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","307272.03","2020-05-26T17:42:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444DE5504C.01","Regensburg - München",">","Landshut (Bay) Hbf","Moosburg",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,",,X","X,,X",",,x","0,,0","X,,X","Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","307294.01","2020-05-26T13:12:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E6EA48C.02","Regensburg - München","< >","Eggmühl","Eggmühl",2022,2022,36,37,"2022-09-07T01:00:00","01:00:00","2022-09-14T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,"","","","0,,0",",,X","Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","307314.02","2020-05-26T11:28:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E0A79CC.03","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,2,2,"2022-01-16T00:45:00","00:45:00","2022-01-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"","X,,","","0,,","X,,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307028.03","2020-06-06T17:31:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E1E4FEC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,3,5,"2022-01-22T12:00:00","12:00:00","2022-01-31T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307031.02","2020-04-27T06:48:00",null,"1,6,7",1]
[null,80,"21E443E246A6C.02","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,4,4,"2022-01-24T15:00:00","15:00:00","2022-01-25T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307032.02","2020-04-27T06:48:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E39C72C.02","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,5,5,"2022-01-31T15:00:00","15:00:00","2022-02-01T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307035.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E584BAC.02","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2022,2022,5,6,"2022-02-05T12:00:00","12:00:00","2022-02-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307040.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"2293426A4FF4D.02","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2022,2022,5,6,"2022-02-05T12:00:00","12:00:00","2022-02-08T06:00:00","06:00:00","2 d, 18 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2293426A4FF4D.02","2020-08-25T12:56:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E584BAC.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,6,6,"2022-02-07T15:00:00","15:00:00","2022-02-08T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307040.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E678DEC.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,6,7,"2022-02-12T12:00:00","12:00:00","2022-02-14T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307042.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E678DEC.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,7,7,"2022-02-14T15:00:00","15:00:00","2022-02-15T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307042.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E87990C.02","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307047.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E87990C.03","Stuttgart - München","< >","München-Milbertshofen","München-Freimann",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307047.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EA0030C.01","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307051.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EA0030C.03","Stuttgart - München","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307051.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EB86D0C.02","Stuttgart - München",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307055.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EB86D0C.03","Stuttgart - München","< >","München-Johanneskirchen","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307055.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EB86D0C.04","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-02-28T15:00:00","15:00:00","2022-03-08T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307055.04","2020-04-27T06:49:00",null,1,1]
[null,80,"21E443F04B84C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-03-05T12:00:00","12:00:00","2022-03-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307067.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443F4DF64C.02","Stuttgart - München","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,10,13,"2022-03-12T12:00:00","12:00:00","2022-03-28T15:00:00","15:00:00","6 d, 09 h","periodical","Signal","T",null,null,null,null,"X,,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307079.02","2020-04-27T06:49:00",null,"1,6,7",1]
[null,80,"21E443F4DF64C.03","Stuttgart - München","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,11,12,"2022-03-14T15:00:00","15:00:00","2022-03-22T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,"","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307079.03","2020-04-27T06:49:00",null,1,1]
[null,80,"21E443FD5C3EC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Freimann",2022,2022,12,12,"2022-03-27T12:00:00","12:00:00","2022-03-27T21:00:00","21:00:00","9 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","307100.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443FD5C3EC.03","Stuttgart - München",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,13,13,"2022-03-28T15:00:00","15:00:00","2022-03-29T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,"X,,","X,,","","0,,","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307100.03","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C9EC68C.01","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-21T06:00:00","06:00:00","2022-07-22T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"LT",null,null,null,"","X,,","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307251.01","2020-06-07T13:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444C9EC68C.03","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-23T06:00:00","06:00:00","2022-07-23T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,,","","0,,0","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307251.03","2020-06-07T13:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CCF9A8C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,29,29,"2022-07-24T06:00:00","06:00:00","2022-07-24T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,"X,,","","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307258.03","2021-03-16T15:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CCF9A8C.04","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,30,30,"2022-07-25T06:00:00","06:00:00","2022-07-28T22:00:00","22:00:00","2 d, 16 h","periodical","Catenary",null,"LT",null,null,null,"","X,X,","","0,,","X,X,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307258.04","2021-03-16T15:02:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CE98B2C.01","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,30,30,"2022-07-29T06:00:00","06:00:00","2022-07-29T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,"X,,X","","","0,,0","","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307261.01","2021-03-16T14:54:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444CE98B2C.04","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,30,30,"2022-07-30T06:00:00","06:00:00","2022-07-30T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,"X,,","","","0,,","","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307261.04","2021-03-16T14:54:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D2386EC.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,30,31,"2022-07-31T06:00:00","06:00:00","2022-08-07T22:00:00","22:00:00","2 d","periodical","Catenary","T",null,null,null,null,"X,,","","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307269.03","2020-06-07T13:16:00",null,"6,7",1]
[null,80,"21E444D2386EC.04","Stuttgart - München","< >","München-Daglfing","München-Daglfing",2022,2022,31,31,"2022-08-01T06:00:00","06:00:00","2022-08-05T22:00:00","22:00:00","3 d, 08 h","periodical","Catenary",null,"ST",null,null,null,"","X,,","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307269.04","2020-06-07T13:16:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D5D82AC.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,32,32,"2022-08-08T06:00:00","06:00:00","2022-08-08T14:00:00","14:00:00","8 h","continuous","Catenary","T",null,null,null,null,"X,,","","","0,,","","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307277.03","2020-06-07T13:20:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444D7F146C.03","Stuttgart - München","< >","München-Daglfing","München-Daglfing",2022,2022,33,33,"2022-08-16T06:00:00","06:00:00","2022-08-17T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"ST",null,null,null,",,X","X,X,","","0,,0","X,X,X","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307282.03","2021-03-16T15:34:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444DECF16C.03","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,33,33,"2022-08-19T06:00:00","06:00:00","2022-08-21T22:00:00","22:00:00","2 d","periodical","Catenary",null,"LT",null,null,null,",,X","X,X,","","0,,0","X,X,X","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307295.03","2020-06-07T13:25:00",null,"5,6,7",1]
[null,80,"21E444E487EEC.03","Stuttgart - München","< >","München-Daglfing","München-Freimann",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-05T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,"X,X,X","","",",,0","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307309.03","2021-03-16T16:36:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E487EEC.05","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T21:00:00","21:00:00","4 d, 17 h","continuous","Catenary",null,"LT",null,null,null,"","X,,","",",,0","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307309.05","2021-03-16T16:36:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E7DE6CC.03","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,36,37,"2022-09-09T22:00:00","22:00:00","2022-09-12T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,"X,X,X","","",",,0","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307316.03","2020-06-07T13:45:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444E9F788C.05","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,37,37,"2022-09-16T22:00:00","22:00:00","2022-09-17T06:00:00","06:00:00","8 h","continuous","Catenary","T",null,null,null,null,"X,,X","","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","307321.05","2021-03-16T17:13:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444F4A5E8C.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,39,39,"2022-10-02T00:45:00","00:45:00","2022-10-02T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"","","","","","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307342.02","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444F4A5E8C.05","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,39,39,"2022-10-02T06:00:00","06:00:00","2022-10-02T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,",X,","X,,","","0,,","X,,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307342.05","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E445038680C.01","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,40,41,"2022-10-09T14:00:00","14:00:00","2022-10-11T04:00:00","04:00:00","1 d, 14 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,,","","0,,0","X,,X","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307373.01","2021-03-18T09:16:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E445038680C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,41,42,"2022-10-10T21:00:00","21:00:00","2022-10-21T04:00:00","04:00:00","2 d, 08 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","21E445038680C.03","2021-03-18T09:16:00",null,"1,2,3,4",1]
[null,80,"21E44502925CC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,41,41,"2022-10-16T00:45:00","00:45:00","2022-10-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,"X,,","X,,","","0,,","X,,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307371.02","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E445030C6EC.01","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,41,41,"2022-10-16T06:00:00","06:00:00","2022-10-16T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,",X,","X,,","","0,,","X,,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307372.01","2020-04-27T06:53:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44512B056C.02","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,43,43,"2022-10-24T21:00:00","21:00:00","2022-10-28T04:00:00","04:00:00","1 d, 04 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","21E44512B056C.02","2021-03-18T09:20:00",null,"1,2,3,4",1]
[null,80,"21E4450D7190C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,44,46,"2022-11-04T21:00:00","21:00:00","2022-11-14T04:00:00","04:00:00","4 d, 14 h","periodical","Catenary","T",null,null,null,null,"","","","","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","21E4450D7190C.03","2021-03-18T09:30:00",null,"5,6,7",1]
[null,80,"21E44510C80EC.02","Stuttgart - München","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,44,45,"2022-11-06T00:45:00","00:45:00","2022-11-09T15:00:00","15:00:00","3 d, 14 h","continuous","Signal","T",null,null,null,null,"X,,X","X,X,",",x,","0,,","X,X,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307399.02","2020-06-06T18:55:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E445104DFCC.01","Stuttgart - München","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,44,44,"2022-11-06T06:00:00","06:00:00","2022-11-06T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,",X,","X,,","","0,,","X,,","Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","307398.01","2020-06-06T18:56:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4450D7190C.02","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,45,45,"2022-11-07T04:00:00","04:00:00","2022-11-07T21:00:00","21:00:00","17 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,X,","","0,,0","X,X,X","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307392.02","2021-03-18T09:30:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4451ACB88C.05","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,45,45,"2022-11-08T21:00:00","21:00:00","2022-11-11T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,"X,,","","","0,,","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307417.05","2020-06-07T16:29:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44518692EC.01","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,46,46,"2022-11-14T04:00:00","04:00:00","2022-11-15T20:00:00","20:00:00","1 d, 16 h","continuous","Catenary","T",null,null,null,null,"","X,,","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307413.01","2021-03-18T09:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44518692EC.02","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-16T21:00:00","21:00:00","2022-11-17T04:00:00","04:00:00","7 h","continuous","Catenary","T",null,null,null,null,",,X","X,,","","0,,","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307413.02","2021-03-18T09:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4451B8ED8C.05","Stuttgart - München","<","München-Daglfing","München-Johanneskirchen",2022,2022,46,46,"2022-11-17T04:00:00","04:00:00","2022-11-18T14:00:00","14:00:00","1 d, 10 h","continuous","Catenary",null,"LT",null,null,null,"X,,X","","","0,,0","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307419.05","2021-03-18T09:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4451B8ED8C.03","Stuttgart - München","< >","München-Freimann","München-Daglfing",2022,2022,46,47,"2022-11-18T21:00:00","21:00:00","2022-11-21T04:00:00","04:00:00","2 d, 07 h","continuous","Catenary","T",null,null,null,null,",,X","X,X,",",x,","0,,","X,X,","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307419.03","2021-03-18T09:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44525C326C.03","Stuttgart - München",">","München-Johanneskirchen","München-Daglfing",2022,2022,47,47,"2022-11-23T21:00:00","21:00:00","2022-11-25T04:00:00","04:00:00","1 d, 07 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,,","","0,,0","X,,","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307437.03","2021-03-18T10:32:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44525C326C.02","Stuttgart - München",">","München-Freimann","München-Daglfing",2022,2022,47,47,"2022-11-25T21:00:00","21:00:00","2022-11-27T13:00:00","13:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,",,X","X,X,",",x,","0,,","X,X,","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307437.02","2021-03-18T10:32:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E445263D38C.03","Stuttgart - München","< >","München-Daglfing","München-Trudering",2022,2022,47,48,"2022-11-27T20:00:00","20:00:00","2022-11-28T21:00:00","21:00:00","1 d, 01 h","continuous","Catenary","T",null,null,null,null,"X,,","","","","","Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","307438.03","2021-03-18T10:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"200B68B0927FE.01","Gemünden - Bamberg - Nürnberg","< >","Gädheim","Haßfurt",2021,2021,50,50,"2021-12-18T21:00:00","21:00:00","2021-12-19T15:00:00","15:00:00","18 h","continuous","Bridge","T",null,null,null,null,",,X","X,,","","0,,","X,,X","Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Abbruch der Pfeiler",null,"N","107009.01","2019-06-07T08:09:00",null,"1,2,3,4,5,6,7",1]
[null,80,"221AAEFAA6E7E.02","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,13,15,"2022-03-31T07:00:00","07:00:00","2022-04-13T17:00:00","17:00:00","13 d, 10 h","continuous","Track & Rail",null,null,null,"P",null,"","","","","","Gleisauswechslung Gl.9 in Schweinfurt Hbf",null,"N","221AAEFAA6E7E.02","2021-01-13T10:37:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220754535431E.01","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,5,6,"2022-02-06T12:00:00","12:00:00","2022-02-07T16:00:00","16:00:00","1 d, 04 h","continuous","Switch",null,"ST",null,null,null,"","X,,","","0,,","","Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","107844.01","2021-01-27T09:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220754535431E.02","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,6,7,"2022-02-13T12:00:00","12:00:00","2022-02-14T16:00:00","16:00:00","1 d, 04 h","continuous","Switch",null,"ST",null,null,null,"","X,,","","","X,,","Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","107844.02","2021-01-27T09:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220754535431E.03","Gemünden - Würzburg - Nürnberg",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,7,7,"2022-02-14T02:00:00","02:00:00","2022-02-14T16:00:00","16:00:00","14 h","continuous","Switch",null,"LT",null,null,null,"","","","","","Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","107844.03","2021-01-27T09:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220754535431E.04","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,7,8,"2022-02-20T12:00:00","12:00:00","2022-02-21T16:00:00","16:00:00","1 d, 04 h","continuous","Switch",null,"ST",null,null,null,"","X,,","","0,,","","Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","107844.04","2021-01-27T09:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22076D6D78F7E.01","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,10,11,"2022-03-13T06:00:00","06:00:00","2022-03-20T01:00:00","01:00:00","6 d, 19 h","continuous","Switch",null,"ST",null,null,null,"","X,,","","0,,","","Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","107845.01","2020-05-21T10:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22076D6D78F7E.03","Gemünden - Würzburg - Nürnberg","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,11,12,"2022-03-19T23:00:00","23:00:00","2022-03-22T02:00:00","02:00:00","2 d, 03 h","continuous","Switch",null,"ST",null,null,null,"","X,,","","0,,","","Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","107845.03","2020-05-21T10:44:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443DE5DACC.02","Gemünden - Bamberg - Nürnberg",">","Hirschaid","Forchheim (Oberfr)",2022,2022,1,5,"2022-01-07T21:00:00","21:00:00","2022-02-04T21:00:00","21:00:00","28 d","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,X,",",x,","0,0,0","X,,X","sonstige Arbeiten Rie-IB2022 Mos-103 VDE 8.1.1 PA19 Neubau EÜ D.-Bohnhoeffer-Str. km 40,011 und EÜ Sendelbachgraben km 40,167, Streckenbau_ PA21 Erneuerung SÜ B505 km 55.504",null,"N","307025.02","2020-06-10T19:14:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E4C16AC.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Forchheim (Oberfr)",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,",,X","X,X,",",x,","0,0,","X,,","sonstige Arbeiten Rie-IB2022 Mos-103 VDE 8.1.1 PA19 Neubau EÜ D.-Bohnhoeffer-Str. km 40,011 und EÜ Sendelbachgraben km 40,167, Streckenbau_ PA21 Erneuerung SÜ B505 km 55.504",null,"N","307038.01","2020-05-25T13:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E4C16AC.02","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten Rie-IB2022 Mos-103 VDE 8.1.1 PA19 Neubau EÜ D.-Bohnhoeffer-Str. km 40,011 und EÜ Sendelbachgraben km 40,167, Streckenbau_ PA21 Erneuerung SÜ B505 km 55.504",null,"N","307038.02","2020-05-25T13:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220317212303E.01","Gemünden - Bamberg - Nürnberg","<","Strullendorf","Bamberg",2022,2022,5,5,"2022-02-05T06:00:00","06:00:00","2022-02-05T23:59:00","23:59:00","18 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten VI_Anm.2048 in Bamberg",null,"N","220317212303E.01","2020-05-18T11:12:00",null,"1,2,3,4,5,6,7",1]
[null,80,"220317212303E.02","Gemünden - Bamberg - Nürnberg",">","Bamberg","Strullendorf",2022,2022,5,5,"2022-02-06T06:00:00","06:00:00","2022-02-06T23:59:00","23:59:00","18 h","continuous","Catenary",null,"LT",null,null,null,"","","","","","Oberleitungsarbeiten VI_Anm.2048 in Bamberg",null,"N","220317212303E.02","2020-05-18T11:12:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443E6DA86C.01","Gemünden - Bamberg - Nürnberg","< >","Breitengüßbach","Bamberg",2022,2022,7,8,"2022-02-18T21:00:00","21:00:00","2022-02-21T21:00:00","21:00:00","3 d","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,","","0,0,","","Brückenarbeiten Anm_IB_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23, hier: Einhub Süd SÜ BAB 73-93b km 6,573_ Aufbau 3. und 4. Gleis Hallstadt- Breitengüßbach (NBS 02/22IB)",null,"N","307043.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E443EAC380C.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach",2022,2022,8,9,"2022-02-25T21:00:00","21:00:00","2022-03-01T09:00:00","09:00:00","3 d, 12 h","continuous","Bridge","T",null,null,null,null,"X,X,X","X,X,","","0,0,","","Brückenarbeiten Anm_IB_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23, hier: Einhub Süd SÜ BAB 73-93b km 6,573_ Aufbau 3. und 4. Gleis Hallstadt- Breitengüßbach (NBS 02/22IB)",null,"N","307053.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44409606AC.01","Gemünden - Bamberg - Nürnberg","< >","Vach","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten Rie-IB2022 Mos-101 VDE 8.1.1 PA17 NEF Neubau Gleis, Weichen, OLA, LST f. S-Bahnsteige, SWW ESTW-UZ Erlangen",null,"N","307130.01","2020-06-10T16:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44408E658C.01","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Vach",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","","","0,,0","X,,","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307129.01","2020-07-23T12:10:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44408E658C.03","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","","","0,,","X,,","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307129.03","2020-07-23T12:10:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44409DA7CC.01","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","","","0,,","X,,","sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","307131.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44409DA7CC.02","Gemünden - Bamberg - Nürnberg","< >","Hirschaid","Erlangen",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","X,X,","","0,0,","X,,","sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","307131.02","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440A548EC.01","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Bad Staffelstein",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","X,X,","","0,0,","","sonstige Arbeiten Anm_IB_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23, hier: LST-Arbeiten, Belastungsstopfen NHAL - NBG Süd, Schottern Anschlussbereiche NBG (NBS 04_22IB)",null,"N","307132.01","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444109FE2C.01","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Forchheim (Oberfr)",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"X,,X","","","","","sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","307144.01","2020-07-31T10:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444109FE2C.02","Gemünden - Bamberg - Nürnberg","< >","Vach","Bamberg",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"X,X,X","","","","","sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","307144.02","2020-07-31T10:52:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4440FC428C.04","Gemünden - Bamberg - Nürnberg","< >","Vach","Strullendorf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","307143.04","2020-04-27T06:49:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44409606AC.04","Gemünden - Bamberg - Nürnberg","< >","Vach","Bamberg",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,"","","","","","sonstige Arbeiten Rie-IB2022 Mos-101 VDE 8.1.1 PA17 NEF Neubau Gleis, Weichen, OLA, LST f. S-Bahnsteige, SWW ESTW-UZ Erlangen",null,"N","307130.04","2020-06-10T16:21:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444259AFAC.01","Gemünden - Bamberg - Nürnberg",">","Bamberg","Strullendorf",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-02T05:00:00","05:00:00","12 d, 08 h","continuous","Miscellaneous",null,"LT",null,null,null,",,X","X,X,",",x,","0,0,0","X,,X","sonstige Arbeiten Rie-IB2022 Mos-106 VDE 8.1.1 PA19: Bodenverbesserung NFO-NEOS, Beschleunigung Inselbaustelle NFON_ PA21: Herstellung Gleislängsverbau, Verbauarbeiten",null,"N","307183.01","2020-06-10T18:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E444259AFAC.02","Gemünden - Bamberg - Nürnberg",">","Hirschaid","Forchheim (Oberfr)",2022,2022,20,22,"2022-05-20T21:00:00","21:00:00","2022-06-02T05:00:00","05:00:00","12 d, 08 h","continuous","Miscellaneous",null,"LT",null,null,null,"","","","","","sonstige Arbeiten Rie-IB2022 Mos-106 VDE 8.1.1 PA19: Bodenverbesserung NFO-NEOS, Beschleunigung Inselbaustelle NFON_ PA21: Herstellung Gleislängsverbau, Verbauarbeiten",null,"N","307183.02","2020-06-10T18:46:00",null,"1,2,3,4,5,6,7",1]
[null,80,"228218F3BAFE4.02","Nürnberg - Plzen","< >","Schwandorf","Maxhütte-Haidhof",2022,2022,12,13,"2022-03-25T22:20:00","22:20:00","2022-03-29T05:05:00","05:05:00","3 d, 07 h","continuous","Switch","T",null,null,null,null,"X,,X","X,,","","0,,","X,,","Weichenerneuerung mit PSS RÜLü Gl. 206 + WE W205, 229, 230, 231",null,"N","107887.02","2020-12-08T13:12:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E44724EE86C.04","Karlsruhe - Mannheim","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",,x","0,0,","X,,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306231.04","2020-04-27T07:01:00",null,"1,2,3,4,5,6,7",1]
[null,80,"21E4472EC12CC.04","Karlsruhe - Mannheim","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,",,X","X,X,",",x,x","0,0,0","X,X,","Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","306251.04","2020-06-08T16:23:00",null,"1,2,3,4,5,6,7",1]
[null,80,"22C4A6B4B1186.03","Strasbourg - Karlsruhe","<","Karlsruhe-Dammerstock","Karlsruhe Gbf",2022,2022,10,11,"2022-03-12T07:30:00","07:30:00","2022-03-14T05:30:00","05:30:00","1 d, 22 h","continuous","Switch",null,"LT",null,null,null,",,X","X,X,X","","0,0,","X,X,X","Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","106113.03","2020-09-28T12:04:00",null,"1,2,3,4,5,6,7",1]
[null,80,"A5C-001","Gemünden - Würzburg - Nürnberg",">","Würzburg Hbf","Gemünden (Main)",2022,2023,49,49,"2022-12-11","22:00:00","2023-12-04","05:00:00","357d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","A5C-001","2021-06-04","N"]
[null,80,"A94-010","Strasbourg - Karlsruhe",">","Ötigheim","Durmersheim",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-010","2021-06-01","N"]
[null,80,"A94-002","Strasbourg - Karlsruhe",">","Bashaide","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-002","2021-06-01","N"]
[null,80,"A94-011","Strasbourg - Karlsruhe",">","Durmersheim","Bashaide",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-011","2021-06-01","N"]
[null,80,"A94-008","Strasbourg - Karlsruhe","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","A94-008","2021-06-01","N"]
[null,80,"A94-009","Strasbourg - Karlsruhe","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","A94-009","2021-06-01","N"]
[null,80,"A94-012","Strasbourg - Karlsruhe",">","Bashaide","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-012","2021-06-01","N"]
[null,80,"A94-013","Strasbourg - Karlsruhe",">","Ötigheim","Durmersheim",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-013","2021-06-01","N"]
[null,80,"A94-003","Strasbourg - Karlsruhe",">","Durmersheim","Forchheim/Karlsr",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","A94-003","2021-06-01","N"]
[null,80,"AAC-002","Gemünden - Würzburg - Nürnberg",">","Aschaffenbg Hbf","Nantenbach",2022,2023,50,48,"2022-12-17","22:00:00","2023-12-03","05:00:00","350d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","AAC-002","2021-06-04","N"]
[null,80,"AAC-001","Gemünden - Würzburg - Nürnberg",">","Nantenbach","Gemünden (Main)",2022,2023,50,48,"2022-12-17","22:00:00","2023-12-03","05:00:00","350d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","AAC-001","2021-06-04","N"]
[null,80,"AB1-001","Gemünden - Bamberg - Nürnberg",">","Forchheim (Ofr)","Eltersdorf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","AB1-001","2021-06-04","N"]
[null,80,"ABB-007","Strasbourg - Karlsruhe","<>","Karlsruhe Gbf","Dammerstock",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","ABB-007","2021-07-26","N"]
[null,80,"ABB-009","Karlsruhe - Mannheim","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","ABB-009","2021-07-26","N"]
[null,80,"ABB-011","Karlsruhe - Bruchsal","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","ABB-011","2021-07-26","N"]
[null,80,"ABB-006","Karlsruhe - Bruchsal","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","ABB-006","2021-07-26","N"]
[null,80,"ABB-005","Strasbourg - Karlsruhe",">","Karlsruhe Gbf","Dammerstock",2023,2023,11,15,"2023-03-17","21:00:00","2023-04-14","21:00:00","27d, 23h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","ABB-005","2021-06-04","N"]
[null,80,"ABB-012","Strasbourg - Karlsruhe","<>","Karlsruhe Gbf","Dammerstock",2023,2023,13,14,"2023-04-01","09:00:00","2023-04-03","16:00:00","2d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","ABB-012","2021-07-27","N"]
[null,80,"ACF-001","Gemünden - Bamberg - Nürnberg",">","Forchheim (Ofr)","Eltersdorf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","ACF-001","2021-06-04","N"]
[null,80,"ADF-004","Stuttgart - München","<>","Mü-Waldtrudering","München-Daglfing",2023,2023,7,8,"2023-02-18","06:00:00","2023-02-26","22:00:00","8d, 16h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","ADF-004","2021-05-27","N"]
[null,80,"AEF-009","München - Rosenheim - Salzburg ","<>","Rosenheim","Bad Endorf (Obb)",2023,2023,17,17,"2023-04-28","22:00:00","2023-04-30","23:59:00","2d, 1h","continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","AEF-009","2021-06-01","N"]
[null,80,"AEF-020","München - Rosenheim - Salzburg ","<>","Rosenheim","Übersee",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","AEF-020","2021-06-01","N"]
[null,80,"AEF-011","München - Rosenheim - Salzburg ","<>","Prien a Chiemsee","Aschau/Chiemgau",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","AEF-011","2021-06-01","N"]
[null,80,"AEF-022","München - Rosenheim - Salzburg ","<>","Rosenheim","Kolbermoor",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","AEF-022","2021-06-01","N"]
[null,80,"AEF-012","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,18,18,"2023-05-01","18:00:00","2023-05-02","06:00:00","0d, 12h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","AEF-012","2021-06-01","N"]
[null,80,"AEF-003","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,18,18,"2023-05-01","06:00:00","2023-05-01","18:00:00","0d, 12h","continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","AEF-003","2021-06-01","N"]
[null,80,"B8F-001","Strasbourg - Karlsruhe",">","Rastatt-Süd","Achern",2023,2023,22,31,"2023-06-01","23:30:00","2023-07-31","06:00:00","59d, 6h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","B8F-001","2021-06-01","N"]
[null,80,"B8F-002","Strasbourg - Karlsruhe",">","Rastatt-Süd","Achern (F)",2023,2023,31,39,"2023-08-01","23:30:00","2023-09-30","06:00:00","59d, 6h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","B8F-002","2021-06-01","N"]
[null,80,"B8F-004","Strasbourg - Karlsruhe",">","Rastatt-Süd","Achern",2023,2023,5,13,"2023-02-01","23:30:00","2023-03-31","06:00:00","57d, 5h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","B8F-004","2021-06-01","N"]
[null,80,"B8F-003","Strasbourg - Karlsruhe",">","Rastatt-Süd","Achern (F)",2023,2023,13,22,"2023-04-01","23:30:00","2023-05-31","06:00:00","59d, 6h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","B8F-003","2021-06-01","N"]
[null,80,"B95-001","Stuttgart - München","<","Mü Nord Rbf For","Olching",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-001","2021-05-31","N"]
[null,80,"B95-002","Stuttgart - München",">","Olching","Mering Üst",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-002","2021-05-31","N"]
[null,80,"B95-009","Stuttgart - München",">","Olching","Maisach Abzw",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-009","2021-05-31","N"]
[null,80,"B95-012","Stuttgart - München","<","Mü Nord Rbf For","Olching",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-012","2021-05-28","N"]
[null,80,"B95-010","Stuttgart - München",">","Olching","Mering Üst",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-010","2021-05-28","N"]
[null,80,"B95-032","Stuttgart - München",">","Olching","Maisach Abzw",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-032","2021-05-28","N"]
[null,80,"B95-013","Stuttgart - München","<>","Olching","Mü Nord Rbf For",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","05:00:00","1d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-013","2021-05-31","N"]
[null,80,"B95-028","Stuttgart - München","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-028","2021-05-28","N"]
[null,80,"B95-020","Stuttgart - München","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-020","2021-05-28","N"]
[null,80,"B95-011","Stuttgart - München",">","Olching","Mü Nord Rbf For",2023,2023,14,16,"2023-04-04","09:00:00","2023-04-20","16:00:00","16d, 7h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-011","2021-06-16","N"]
[null,80,"B95-023","Stuttgart - München","<>","Mü Nord Rbf For","Olching",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-023","2021-05-31","N"]
[null,80,"B95-003","Stuttgart - München","<","Mü Nord Rbf For","Olching",2023,2023,9,9,"2023-03-03","09:00:00","2023-03-04","16:00:00","1d, 7h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-003","2021-05-27","N"]
[null,80,"B95-004","Stuttgart - München","<>","Olching","Olching",2023,2023,13,17,"2023-04-02","00:00:00","2023-04-30","05:00:00","28d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","B95-004","2021-06-25","N"]
[null,80,"B95-005","Stuttgart - München","<>","Olching","Olching",2023,2023,9,13,"2023-03-05","00:00:00","2023-04-02","05:00:00","28d, 4h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","B95-005","2021-06-25","N"]
[null,80,"B95-033","Stuttgart - München","<>","Mü Nord Rbf For","Olching",2023,2023,17,18,"2023-04-30","05:00:00","2023-05-04","22:00:00","4d, 17h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","B95-033","2021-06-25","N"]
[null,80,"B95-030","Stuttgart - München",">","Olching","Mü Nord Rbf For",2023,2023,44,44,"2023-10-30","06:00:00","2023-10-30","20:00:00","0d, 14h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-030","2021-06-16","N"]
[null,80,"B95-016","Stuttgart - München","<>","Olching","Mü Nord Rbf For",2023,2023,13,14,"2023-04-02","05:00:00","2023-04-04","16:00:00","2d, 11h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","B95-016","2021-06-25","N"]
[null,80,"B95-017","Stuttgart - München","<","Mering Üst","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-017","2021-05-27","N"]
[null,80,"B95-026","Stuttgart - München",">","Olching","Mü Nord Rbf For",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-026","2021-05-27","N"]
[null,80,"B95-024","Stuttgart - München","<","Maisach Abzw","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B95-024","2021-05-27","N"]
[null,80,"B95-031","Stuttgart - München","<>","Olching","Mü Nord Rbf For",2023,2023,9,10,"2023-03-05","00:00:00","2023-03-06","16:00:00","1d, 16h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-031","2021-05-27","N"]
[null,80,"B95-006","Stuttgart - München","<>","Olching","Mü Nord Rbf For",2023,2023,14,17,"2023-04-08","22:00:00","2023-04-24","16:00:00","15d, 18h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","B95-006","2021-05-28","N"]
[null,80,"B99-013","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,16,17,"2023-04-21","06:00:00","2023-04-24","06:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-013","2021-05-31","N"]
[null,80,"B99-002","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,13,14,"2023-03-31","21:40:00","2023-04-03","05:40:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-002","2021-05-31","N"]
[null,80,"B99-015","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,15,15,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-015","2021-05-31","N"]
[null,80,"B99-016","München - Rosenheim - Salzburg ","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,11,11,"2023-03-18","23:00:00","2023-03-19","06:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","B99-016","2021-05-31","N"]
[null,80,"B99-034","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-13","22:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-034","2021-05-31","N"]
[null,80,"B99-039","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,15,16,"2023-04-14","22:00:00","2023-04-17","22:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-039","2021-05-31","N"]
[null,80,"B99-030","München - Rosenheim - Salzburg ","<>","Rosenheim","Bad Endorf (Obb)",2023,2023,13,14,"2023-04-01","21:40:00","2023-04-03","05:40:00","1d, 8h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","B99-030","2021-05-31","N"]
[null,80,"B99-021","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,14,15,"2023-04-06","22:00:00","2023-04-11","06:00:00","4d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-021","2021-05-31","N"]
[null,80,"B99-031","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,12,13,"2023-03-24","21:40:00","2023-03-27","05:40:00","2d, 7h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-031","2021-05-31","N"]
[null,80,"B99-035","München - Rosenheim - Salzburg ","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,12,13,"2023-03-25","21:40:00","2023-03-27","05:40:00","1d, 7h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","B99-035","2021-05-31","N"]
[null,80,"B99-036","München - Rosenheim - Salzburg ","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,7,9,"2023-02-18","00:00:00","2023-02-27","05:00:00","9d, 5h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","B99-036","2021-05-31","N"]
[null,80,"B99-037","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,11,12,"2023-03-17","22:00:00","2023-03-20","06:00:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-037","2021-05-31","N"]
[null,80,"B99-038","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,9,10,"2023-03-03","22:00:00","2023-03-06","06:00:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-038","2021-05-31","N"]
[null,80,"B99-024","München - Rosenheim - Salzburg ",">","Rosenheim","Bad Endorf (Obb)",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-17","06:00:00","3d, 8h","periodical",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-024","2021-05-31","N"]
[null,80,"B99-008","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,16,16,"2023-04-17","22:00:00","2023-04-21","06:00:00","3d, 8h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-008","2021-06-01","N"]
[null,80,"B99-025","München - Rosenheim - Salzburg ","<","Bad Endorf (Obb)","Rosenheim",2023,2023,10,10,"2023-03-06","22:00:00","2023-03-10","06:00:00","3d, 8h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","B99-025","2021-06-01","N"]
[null,80,"BE6-021","München - Rosenheim - Salzburg ","<>","Übersee","Traunstein",2023,2023,43,44,"2023-10-29","00:00:00","2023-10-30","04:00:00","1d, 5h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","BE6-021","2021-06-01","N"]
[null,80,"BE6-009","München - Rosenheim - Salzburg ","<>","Prien a Chiemsee","Traunstein",2023,2023,14,14,"2023-04-03","00:30:00","2023-04-07","04:30:00","4d, 4h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","BE6-009","2021-06-01","N"]
[null,80,"BE6-025","München - Rosenheim - Salzburg ",">","Übersee","Rumgraben",2023,2023,15,17,"2023-04-14","22:00:00","2023-04-24","06:00:00","9d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-025","2021-06-01","N"]
[null,80,"BE6-005","München - Rosenheim - Salzburg ","<","Übersee","Rottau",2023,2023,18,18,"2023-05-02","22:00:00","2023-05-03","06:00:00","0d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-005","2021-06-01","N"]
[null,80,"BE6-014","München - Rosenheim - Salzburg ",">","Übersee","Rumgraben",2023,2023,37,37,"2023-09-11","06:00:00","2023-09-12","22:00:00","1d, 16h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-014","2021-06-01","N"]
[null,80,"BE6-022","München - Rosenheim - Salzburg ",">","Übersee","Traunstein",2023,2023,45,45,"2023-11-10","22:00:00","2023-11-12","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-022","2021-06-01","N"]
[null,80,"BE6-007","München - Rosenheim - Salzburg ","<","Übersee","Rottau",2023,2023,45,45,"2023-11-06","06:00:00","2023-11-06","14:00:00","0d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-007","2021-06-01","N"]
[null,80,"BE6-001","München - Rosenheim - Salzburg ",">","Übersee","Rumgraben",2023,2023,15,17,"2023-04-11","22:00:00","2023-04-28","06:00:00","16d, 8h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-001","2021-06-01","N"]
[null,80,"BE6-015","München - Rosenheim - Salzburg ",">","Übersee","Rumgraben",2023,2023,45,46,"2023-11-12","14:00:00","2023-11-17","14:00:00","5d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-015","2021-06-01","N"]
[null,80,"BE6-008","München - Rosenheim - Salzburg ","<","Rumgraben","Übersee",2023,2023,47,47,"2023-11-23","01:00:00","2023-11-24","10:00:00","1d, 9h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-008","2021-06-01","N"]
[null,80,"BE6-002","München - Rosenheim - Salzburg ","<","Rumgraben","Übersee",2023,2023,46,47,"2023-11-19","14:00:00","2023-11-22","22:00:00","3d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-002","2021-06-01","N"]
[null,80,"BE6-027","München - Rosenheim - Salzburg ","<","Rumgraben","Rottau",2023,2023,46,46,"2023-11-17","22:00:00","2023-11-19","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-027","2021-06-01","N"]
[null,80,"BE6-010","München - Rosenheim - Salzburg ",">","Rumgraben","Traunstein",2023,2023,43,44,"2023-10-27","06:00:00","2023-11-04","22:00:00","8d, 17h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-010","2021-06-01","N"]
[null,80,"BE6-011","München - Rosenheim - Salzburg ",">","Übersee","Rumgraben",2023,2023,17,17,"2023-04-28","22:00:00","2023-04-29","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-011","2021-06-01","N"]
[null,80,"BE6-028","München - Rosenheim - Salzburg ",">","Rottau","Übersee",2023,2023,14,15,"2023-04-07","04:30:00","2023-04-11","06:00:00","4d, 1h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-028","2021-06-01","N"]
[null,80,"BE6-016","München - Rosenheim - Salzburg ","<","Traunstein","Rumgraben",2023,2023,42,43,"2023-10-17","06:00:00","2023-10-26","22:00:00","9d, 16h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-016","2021-06-01","N"]
[null,80,"BE6-003","München - Rosenheim - Salzburg ","<","Übersee","Rottau",2023,2023,17,18,"2023-04-30","22:00:00","2023-05-02","06:00:00","1d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-003","2021-06-01","N"]
[null,80,"BE6-024","München - Rosenheim - Salzburg ","<","Rumgraben","Übersee",2023,2023,40,42,"2023-10-05","06:00:00","2023-10-16","22:00:00","11d, 16h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-024","2021-06-01","N"]
[null,80,"BE6-017","München - Rosenheim - Salzburg ","<","Traunstein","Übersee",2023,2023,41,41,"2023-10-15","06:00:00","2023-10-15","22:00:00","0d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-017","2021-06-01","N"]
[null,80,"BE6-018","München - Rosenheim - Salzburg ",">","Rottau","Übersee",2023,2023,44,44,"2023-11-05","06:00:00","2023-11-05","22:00:00","0d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-018","2021-06-01","N"]
[null,80,"BE6-029","München - Rosenheim - Salzburg ","<","Traunstein","Rumgraben",2023,2023,42,42,"2023-10-21","06:00:00","2023-10-22","22:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-029","2021-06-01","N"]
[null,80,"BE6-019","München - Rosenheim - Salzburg ",">","Rottau","Übersee",2023,2023,45,45,"2023-11-08","22:00:00","2023-11-10","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-019","2021-06-01","N"]
[null,80,"BE6-006","München - Rosenheim - Salzburg ","<","Rumgraben","Rottau",2023,2023,17,17,"2023-04-29","22:00:00","2023-04-30","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-006","2021-06-01","N"]
[null,80,"BE6-012","München - Rosenheim - Salzburg ","<","Rumgraben","Übersee",2023,2023,37,37,"2023-09-13","06:00:00","2023-09-15","22:00:00","2d, 16h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-012","2021-06-01","N"]
[null,80,"BE6-020","München - Rosenheim - Salzburg ","<","Rumgraben","Rottau",2023,2023,45,45,"2023-11-06","14:00:00","2023-11-08","14:00:00","2d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-020","2021-06-01","N"]
[null,80,"BE6-013","München - Rosenheim - Salzburg ","<>","Übersee","Rottau",2023,2023,45,45,"2023-11-09","00:00:00","2023-11-10","05:00:00","1d, 5h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","BE6-013","2021-06-01","N"]
[null,80,"BE6-030","München - Rosenheim - Salzburg ",">","Rumgraben","Traunstein",2023,2023,43,43,"2023-10-28","06:00:00","2023-10-29","22:00:00","1d, 17h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","BE6-030","2021-06-01","N"]
[null,80,"BEC-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Fürth (Bay) Hbf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","BEC-001","2021-06-04","N"]
[null,80,"BF1-001","Nürnberg - Regensburg",">","Deining (Oberpf)","Nürnberg Hbf",2022,2023,50,48,"2022-12-17","23:00:00","2023-12-03","06:00:00","350d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","BF1-001","2021-05-07","N"]
[null,80,"BF9-001","Strasbourg - Karlsruhe","<>","Ottersweier","Appenweier",2023,2023,45,45,"2023-11-06","21:00:00","2023-11-11","02:00:00","4d, 5h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","BF9-001","2021-06-01","N"]
[null,80,"BF9-003","Strasbourg - Karlsruhe","<>","Ottersweier","Baden-Baden",2023,2023,45,46,"2023-11-11","02:00:00","2023-11-13","04:30:00","2d, 2h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","BF9-003","2021-06-01","N"]
[null,80,"C02-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Fürth (Bay) Hbf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","C02-001","2021-06-04","N"]
[null,80,"C10-020","Stuttgart - München","<>","München-Pasing","Mü Donnersbgbr",2023,2023,10,14,"2023-03-10","22:40:00","2023-04-03","04:40:00","23d, 5h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-020","2021-04-21","N"]
[null,80,"C10-002","Stuttgart - München","<>","München-Pasing","Mü Hirschgarten",2023,2023,14,15,"2023-04-06","22:40:00","2023-04-11","04:40:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-002","2021-04-22","N"]
[null,80,"C10-006","Stuttgart - München","<","München-Pasing","Mü Hirschgarten",2023,2023,17,18,"2023-04-28","22:40:00","2023-05-02","04:40:00","3d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-006","2021-04-27","N"]
[null,80,"C10-017","Stuttgart - München",">","München Hbf","München-Pasing",2023,2023,21,22,"2023-05-26","22:40:00","2023-05-30","04:40:00","3d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-017","2021-04-27","N"]
[null,80,"C10-047","Stuttgart - München","<>","München-Pasing","Mü Hirschgarten",2023,2023,21,22,"2023-05-26","22:40:00","2023-05-30","04:40:00","3d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-047","2021-04-27","N"]
[null,80,"C10-018","Stuttgart - München","<>","München-Pasing","Mü Friedenhei Br",2023,2023,40,40,"2023-10-07","10:50:00","2023-10-08","07:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-018","2021-04-28","N"]
[null,80,"C10-043","Stuttgart - München",">","München Hbf","München-Pasing",2023,2023,40,40,"2023-10-06","22:50:00","2023-10-07","10:50:00","0d, 12h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-043","2021-04-28","N"]
[null,80,"C10-019","Stuttgart - München",">","München Hbf","München-Pasing",2023,2023,32,32,"2023-08-12","18:50:00","2023-08-13","00:50:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-019","2021-07-08","N"]
[null,80,"C10-003","Stuttgart - München","<>","München-Pasing","Mü Friedenhei Br",2023,2023,24,24,"2023-06-16","21:20:00","2023-06-17","18:20:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-003","2021-06-17","N"]
[null,80,"C10-031","Stuttgart - München","<>","München Hbf","München-Pasing",2023,2023,40,40,"2023-10-07","10:50:00","2023-10-08","07:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-031","2021-04-28","N"]
[null,80,"C10-035","Stuttgart - München","<>","München-Pasing","Mü Friedenhei Br",2023,2023,48,49,"2023-12-01","22:50:00","2023-12-04","04:50:00","2d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-035","2021-04-28","N"]
[null,80,"C10-009","Stuttgart - München",">","Mü Hirschgarten","München-Pasing",2023,2023,6,12,"2023-02-07","22:40:00","2023-03-20","04:40:00","40d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-009","2021-04-19","N"]
[null,80,"C10-010","Stuttgart - München","<","München-Pasing","München Hbf",2023,2023,32,33,"2023-08-12","03:50:00","2023-08-14","04:50:00","2d, 1h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-010","2021-07-08","N"]
[null,80,"C10-042","Stuttgart - München",">","München Hbf","München-Pasing",2023,2023,24,24,"2023-06-17","18:20:00","2023-06-18","00:20:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-042","2021-06-17","N"]
[null,80,"C10-036","Stuttgart - München","<>","München-Pasing","Mü-Neuhausen",2023,2023,24,25,"2023-06-16","21:20:00","2023-06-19","10:20:00","2d, 13h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-036","2021-06-17","N"]
[null,80,"C10-024","Stuttgart - München",">","München Hbf","München-Pasing",2023,2023,40,41,"2023-10-08","07:50:00","2023-10-09","04:50:00","0d, 21h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-024","2021-04-28","N"]
[null,80,"C10-005","Stuttgart - München","<","München-Pasing","Mü Hirschgarten",2023,2023,15,20,"2023-04-11","22:40:00","2023-05-19","04:40:00","37d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C10-005","2021-06-18","N"]
[null,80,"C10-046","Stuttgart - München","<>","München Hbf","München-Pasing",2023,2023,32,32,"2023-08-12","00:50:00","2023-08-12","18:50:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-046","2021-07-08","N"]
[null,80,"C10-025","Stuttgart - München","<>","München-Pasing","Mü Friedenhei Br",2023,2023,32,32,"2023-08-11","21:50:00","2023-08-12","18:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-025","2021-07-08","N"]
[null,80,"C10-015","Stuttgart - München","<>","München Hbf","München-Pasing",2023,2023,48,49,"2023-12-01","22:50:00","2023-12-04","04:50:00","2d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-015","2021-04-28","N"]
[null,80,"C10-026","Stuttgart - München","<>","München Hbf","München-Pasing",2023,2023,24,24,"2023-06-17","00:20:00","2023-06-17","18:20:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C10-026","2021-06-17","N"]
[null,80,"C15-001","Gemünden - Würzburg - Nürnberg",">","Fürth (Bay) Hbf","Würzburg Hbf",2022,2023,50,48,"2022-12-17","23:00:00","2023-12-03","06:00:00","350d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","C15-001","2021-07-07","N"]
[null,80,"C15-002","Gemünden - Würzburg - Nürnberg","<","Würzburg Hbf","Fürth (Bay) Hbf",2022,2023,49,49,"2022-12-11","22:00:00","2023-12-04","05:00:00","357d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","C15-002","2021-07-07","N"]
[null,80,"C18-005","Strasbourg - Karlsruhe","<>","Baden-Baden","Achern (F)",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-05","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","C18-005","2021-06-01","N"]
[null,80,"C18-004","Strasbourg - Karlsruhe","<>","Baden-Baden","Achern",2023,2023,44,44,"2023-10-31","22:00:00","2023-11-03","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","C18-004","2021-06-01","N"]
[null,80,"C18-003","Strasbourg - Karlsruhe","<>","Baden-Baden","Achern (F)",2023,2023,9,49,"2023-03-01","06:00:00","2023-12-09","23:59:00","283d, 17h","continuous","Signal",null,null,"S",null,null,null,null,null,null,null,null,null,"N","C18-003","2021-06-01","N"]
[null,80,"C18-001","Strasbourg - Karlsruhe",">","Rastatt-Süd","Achern",2023,2023,5,13,"2023-02-01","23:30:00","2023-03-31","06:00:00","57d, 5h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C18-001","2021-06-01","N"]
[null,80,"C18-002","Strasbourg - Karlsruhe",">","Baden-Baden","Achern (F)",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:00:00","50d, 6h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","C18-002","2021-06-01","N"]
[null,80,"C2E-006","Stuttgart - München","<>","Mü Isartor","München Ost Pbf",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C2E-006","2021-04-16","N"]
[null,80,"C2E-002","Stuttgart - München","<>","München Ost Pbf","Mü-Steinhausen",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C2E-002","2021-04-19","N"]
[null,80,"C2E-005","Stuttgart - München","<>","München Ost Pbf","Mü-Riem West",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C2E-005","2021-04-19","N"]
[null,80,"C2E-004","Stuttgart - München","<>","München Ost Pbf","München-Giesing",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C2E-004","2021-04-19","N"]
[null,80,"C2E-003","Stuttgart - München","<>","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C2E-003","2021-04-19","N"]
[null,80,"C45-001","Strasbourg - Karlsruhe","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","C45-001","2021-06-01","N"]
[null,80,"C45-009","Strasbourg - Karlsruhe","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","C45-009","2021-06-01","N"]
[null,80,"C45-005","Strasbourg - Karlsruhe","<>","Bashaide","Durmersheim",2023,2023,13,21,"2023-03-31","21:00:00","2023-05-27","06:00:00","56d, 9h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","C45-005","2021-06-01","N"]
[null,80,"C45-006","Strasbourg - Karlsruhe",">","Bashaide","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C45-006","2021-06-01","N"]
[null,80,"C45-007","Strasbourg - Karlsruhe","<>","Karlsruhe Hbf","Durmersheim Nord",2023,2023,45,45,"2023-11-06","04:30:00","2023-11-07","05:00:00","1d, 0h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","C45-007","2021-06-01","N"]
[null,80,"C45-002","Strasbourg - Karlsruhe",">","Durmersheim","Bashaide",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C45-002","2021-06-01","N"]
[null,80,"C45-008","Strasbourg - Karlsruhe",">","Durmersheim","Forchheim/Karlsr",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C45-008","2021-06-01","N"]
[null,80,"C45-003","Strasbourg - Karlsruhe","<>","Bashaide","Durmersheim Nord",2023,2023,45,46,"2023-11-07","05:00:00","2023-11-18","05:00:00","11d, 0h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","C45-003","2021-06-01","N"]
[null,80,"C45-004","Strasbourg - Karlsruhe",">","Bashaide","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C45-004","2021-06-01","N"]
[null,80,"C5B-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,19,20,"2023-05-14","22:00:00","2023-05-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C5B-001","2021-06-07","N"]
[null,80,"C66-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,33,34,"2023-08-20","22:00:00","2023-08-21","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C66-001","2021-06-07","N"]
[null,80,"C68-001","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C68-001","2021-06-08","N"]
[null,80,"C68-003","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","C68-003","2021-06-08","N"]
[null,80,"C68-002","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C68-002","2021-06-08","N"]
[null,80,"C69-002","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C69-002","2021-06-08","N"]
[null,80,"C69-003","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","C69-003","2021-06-08","N"]
[null,80,"C69-001","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C69-001","2021-06-08","N"]
[null,80,"C6B-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C6B-001","2021-05-20","N"]
[null,80,"C70-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,24,24,"2023-06-12","03:00:00","2023-06-12","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C70-001","2021-05-18","N"]
[null,80,"C71-001","Karlsruhe - Mannheim","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C71-001","2021-06-08","N"]
[null,80,"C8D-007","Mannheim - Darmstadt",">","Darmstadt Hbf","Bickenbach",2023,2023,15,16,"2023-04-15","23:00:00","2023-04-17","04:00:00","1d, 5h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C8D-007","2021-05-26","N"]
[null,80,"C8D-010","Mannheim - Darmstadt","<>","Da-Eberstadt","Pfungstadt",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","C8D-010","2021-05-26","N"]
[null,80,"C8D-013","Mannheim - Darmstadt",">","Darmstadt Hbf","Bickenbach",2023,2023,18,19,"2023-05-06","23:00:00","2023-05-08","04:00:00","1d, 5h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C8D-013","2021-05-26","N"]
[null,80,"C8D-008","Mannheim - Darmstadt","<>","Darmstadt Hbf","Bickenbach Nord",2023,2023,16,18,"2023-04-21","22:00:00","2023-05-01","04:00:00","9d, 6h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","C8D-008","2021-07-14","N"]
[null,80,"C91-001","Gemünden - Bamberg - Nürnberg","<>","Bamberg","Bamberg",2023,2023,2,4,"2023-01-14","22:45:00","2023-01-29","06:45:00","14d, 8h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","C91-001","2021-06-22","N"]
[null,80,"C94-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,46,46,"2023-11-13","03:00:00","2023-11-13","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C94-001","2021-05-18","N"]
[null,80,"C9D-001","Karlsruhe - Mannheim","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C9D-001","2021-06-08","N"]
[null,80,"C9F-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,47,48,"2023-11-26","22:00:00","2023-11-27","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","C9F-001","2021-06-08","N"]
[null,80,"CA4-003","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA4-003","2021-06-14","N"]
[null,80,"CA4-001","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA4-001","2021-06-14","N"]
[null,80,"CA4-002","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA4-002","2021-06-14","N"]
[null,80,"CA6-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,35,36,"2023-09-03","22:00:00","2023-09-04","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA6-001","2021-06-07","N"]
[null,80,"CA9-003","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA9-003","2021-06-08","N"]
[null,80,"CA9-001","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","CA9-001","2021-06-08","N"]
[null,80,"CA9-002","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CA9-002","2021-06-08","N"]
[null,80,"CAA-002","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","CAA-002","2021-06-08","N"]
[null,80,"CAA-001","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CAA-001","2021-06-08","N"]
[null,80,"CAA-003","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CAA-003","2021-06-08","N"]
[null,80,"CAD-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,11,12,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CAD-001","2021-06-07","N"]
[null,80,"CC0-003","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CC0-003","2021-06-14","N"]
[null,80,"CC0-002","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CC0-002","2021-06-14","N"]
[null,80,"CC0-001","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CC0-001","2021-06-14","N"]
[null,80,"CC8-006","Gemünden - Bamberg - Nürnberg","<>","Höflein","Ebelsbach-Eltm",2023,2023,14,14,"2023-04-09","08:00:00","2023-04-09","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","CC8-006","2021-05-11","N"]
[null,80,"CC8-001","Gemünden - Bamberg - Nürnberg","<>","Höflein","Ebelsbach-Eltm",2023,2023,15,15,"2023-04-10","08:00:00","2023-04-10","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","CC8-001","2021-05-11","N"]
[null,80,"CC8-002","Gemünden - Bamberg - Nürnberg","<>","Ebelsbach-Eltm","Höflein",2023,2023,18,19,"2023-05-01","21:00:00","2023-05-12","04:40:00","10d, 7h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","CC8-002","2021-05-11","N"]
[null,80,"CD3-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CD3-001","2021-06-07","N"]
[null,80,"CD7-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,29,30,"2023-07-23","22:00:00","2023-07-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CD7-001","2021-06-07","N"]
[null,80,"CE6-004","Mannheim - Darmstadt",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","04:00:00","1d, 6h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CE6-004","2021-05-08","N"]
[null,80,"CE6-010","Mannheim - Darmstadt","<>","Bickenbach Nord","Bickenbach",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","CE6-010","2021-05-08","N"]
[null,80,"CE6-002","Mannheim - Darmstadt",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","04:00:00","2d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CE6-002","2021-05-08","N"]
[null,80,"CE6-001","Mannheim - Darmstadt","<>","Bickenbach","Bickenbach Nord",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","CE6-001","2021-05-08","N"]
[null,80,"CE8-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,20,20,"2023-05-15","03:00:00","2023-05-15","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CE8-001","2021-05-18","N"]
[null,80,"CF6-001","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,10,10,"2023-03-07","22:00:00","2023-03-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-001","2021-06-09","N"]
[null,80,"CF6-002","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,24,24,"2023-06-13","22:00:00","2023-06-14","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-002","2021-06-09","N"]
[null,80,"CF6-005","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,15,15,"2023-04-11","22:00:00","2023-04-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-005","2021-06-09","N"]
[null,80,"CF6-006","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,2,2,"2023-01-10","22:00:00","2023-01-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-006","2021-06-09","N"]
[null,80,"CF6-003","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,6,6,"2023-02-07","22:00:00","2023-02-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-003","2021-06-09","N"]
[null,80,"CF6-010","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,37,37,"2023-09-12","22:00:00","2023-09-13","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-010","2021-06-09","N"]
[null,80,"CF6-007","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,41,41,"2023-10-10","22:00:00","2023-10-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-007","2021-06-09","N"]
[null,80,"CF6-004","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,32,32,"2023-08-08","22:00:00","2023-08-09","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-004","2021-06-09","N"]
[null,80,"CF6-008","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,46,46,"2023-11-14","22:00:00","2023-11-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-008","2021-06-09","N"]
[null,80,"CF6-009","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,28,28,"2023-07-11","22:00:00","2023-07-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-009","2021-06-09","N"]
[null,80,"CF6-011","Karlsruhe - Stuttgart",">","Wilferdgn-Singen","Mühlacker",2023,2023,19,19,"2023-05-09","22:00:00","2023-05-10","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CF6-011","2021-06-09","N"]
[null,80,"CFA-001","Stuttgart - München",">","Süßen","Ulm Hbf Em Nord",2023,2023,36,37,"2023-09-08","23:00:00","2023-09-13","05:00:00","4d, 6h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CFA-001","2021-06-16","N"]
[null,80,"CFA-002","Stuttgart - München",">","Süßen","Ulm Hbf Em Nord",2023,2023,41,42,"2023-10-13","23:00:00","2023-10-18","05:00:00","4d, 6h","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","CFA-002","2021-06-16","N"]
[null,80,"D03-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D03-001","2021-06-07","N"]
[null,80,"D06-010","Gemünden - Würzburg - Nürnberg","<>","Retzb-Zellingen","Gemünden (Main)",2023,2023,43,44,"2023-10-27","21:00:00","2023-11-01","04:00:00","4d, 8h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","D06-010","2021-06-02","N"]
[null,80,"D0F-003","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","D0F-003","2021-06-08","N"]
[null,80,"D0F-002","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D0F-002","2021-06-08","N"]
[null,80,"D0F-001","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D0F-001","2021-06-08","N"]
[null,80,"D15-046","Karlsruhe - Mannheim",">","Mannheim Hbf Ost","Schwetzingen",2023,2023,7,9,"2023-02-18","21:30:00","2023-02-27","04:30:00","8d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D15-046","2021-05-31","N"]
[null,80,"D15-034","Karlsruhe - Mannheim",">","Mannheim-Rheinau","Schwetzingen",2023,2023,3,5,"2023-01-18","23:30:00","2023-01-30","05:30:00","11d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-034","2021-05-31","N"]
[null,80,"D15-013","Karlsruhe - Mannheim","<","Schwetzingen","Mannheim Hbf Ost",2023,2023,5,7,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D15-013","2021-05-31","N"]
[null,80,"D15-037","Karlsruhe - Mannheim","<","Schwetzingen","Mannheim Hbf",2023,2023,7,9,"2023-02-18","21:30:00","2023-02-27","04:30:00","8d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-037","2021-05-31","N"]
[null,80,"D15-007","Karlsruhe - Mannheim","<","Schwetzingen","Mannheim-Rheinau",2023,2023,5,5,"2023-01-30","23:30:00","2023-02-02","05:30:00","2d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-007","2021-05-31","N"]
[null,80,"D15-019","Karlsruhe - Mannheim","<","Schwetzingen","Mhm-Neckarau",2023,2023,6,7,"2023-02-09","23:30:00","2023-02-18","05:30:00","8d, 6h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-019","2021-05-31","N"]
[null,80,"D15-009","Karlsruhe - Mannheim",">","Mannheim Hbf","Schwetzingen",2023,2023,5,7,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-009","2021-05-31","N"]
[null,80,"D15-053","Karlsruhe - Mannheim","<","Schwetzingen","Mannheim-Rheinau",2023,2023,3,5,"2023-01-18","23:30:00","2023-01-30","05:30:00","11d, 6h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D15-053","2021-05-31","N"]
[null,80,"D15-021","Karlsruhe - Mannheim",">","Mannheim-Rheinau","Schwetzingen",2023,2023,5,5,"2023-01-30","23:30:00","2023-02-02","05:30:00","2d, 6h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D15-021","2021-05-31","N"]
[null,80,"D15-041","Karlsruhe - Mannheim",">","Mannheim Hbf","Schwetzingen",2023,2023,5,6,"2023-02-02","23:30:00","2023-02-09","04:30:00","6d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D15-041","2021-05-31","N"]
[null,80,"D22-001","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D22-001","2021-06-08","N"]
[null,80,"D22-003","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D22-003","2021-06-08","N"]
[null,80,"D22-002","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","D22-002","2021-06-08","N"]
[null,80,"D2B-007","Stuttgart - München","<>","Stg-Bad Cannst","Stg-Untertürkhm",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-21","15:00:00","4d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","D2B-007","2021-06-07","N"]
[null,80,"D2B-009","Stuttgart - München","<","Stg-Obertürkheim","Neckarpark",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","04:00:00","2d, 3h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D2B-009","2021-06-07","N"]
[null,80,"D2C-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,14,"2023-04-03","03:00:00","2023-04-03","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D2C-001","2021-05-18","N"]
[null,80,"D33-003","Regensburg - Wels","<","Osterhofen/Nbay","Girching",2023,2023,19,28,"2023-05-08","22:25:00","2023-07-11","06:00:00","63d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D33-003","2021-04-22","N"]
[null,80,"D33-001","Regensburg - Wels","<","Osterhofen/Nbay","Girching",2023,2023,18,28,"2023-05-07","22:25:00","2023-07-10","06:00:00","63d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D33-001","2021-04-22","N"]
[null,80,"D33-007","Regensburg - Wels","<","Osterhofen/Nbay","Girching",2023,2023,18,27,"2023-05-06","22:25:00","2023-07-09","07:25:00","63d, 9h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D33-007","2021-04-22","N"]
[null,80,"D33-004","Regensburg - Wels","<","Osterhofen/Nbay","Girching",2023,2023,18,27,"2023-05-05","22:25:00","2023-07-08","06:25:00","63d, 8h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D33-004","2021-04-22","N"]
[null,80,"D34-072","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,45,45,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-072","2021-06-01","N"]
[null,80,"D34-062","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-062","2021-06-01","N"]
[null,80,"D34-031","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,38,41,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-031","2021-06-01","N"]
[null,80,"D34-063","Karlsruhe - Mannheim","<","Waghäusel","Oftersheim",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-063","2021-06-01","N"]
[null,80,"D34-056","Karlsruhe - Mannheim",">","Schwetzingen","Waghäusel",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-056","2021-06-01","N"]
[null,80,"D34-033","Karlsruhe - Mannheim",">","Mannheim-Rheinau","Waghäusel",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-033","2021-06-01","N"]
[null,80,"D34-034","Karlsruhe - Mannheim","<","Hockenheim","Schwetzingen",2023,2023,40,41,"2023-10-05","23:30:00","2023-10-11","04:30:00","5d, 5h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-034","2021-06-01","N"]
[null,80,"D34-036","Karlsruhe - Mannheim",">","Schwetzingen","Waghäusel",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-036","2021-06-01","N"]
[null,80,"D34-047","Karlsruhe - Mannheim","<","Waghäusel","Hockenheim",2023,2023,41,42,"2023-10-11","23:30:00","2023-10-17","04:30:00","5d, 5h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-047","2021-06-01","N"]
[null,80,"D34-003","Karlsruhe - Mannheim",">","Schwetzingen","Hockenheim",2023,2023,33,36,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-003","2021-06-01","N"]
[null,80,"D34-004","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-004","2021-06-01","N"]
[null,80,"D34-049","Karlsruhe - Mannheim",">","Schwetzingen","Hockenheim",2023,2023,40,41,"2023-10-05","23:30:00","2023-10-11","04:30:00","5d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-049","2021-06-01","N"]
[null,80,"D34-073","Karlsruhe - Mannheim",">","Schwetzingen","Hockenheim",2023,2023,45,45,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-073","2021-06-01","N"]
[null,80,"D34-067","Karlsruhe - Mannheim",">","Oftersheim","Waghäusel",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-067","2021-06-01","N"]
[null,80,"D34-050","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-050","2021-06-01","N"]
[null,80,"D34-007","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-007","2021-06-01","N"]
[null,80,"D34-027","Karlsruhe - Mannheim",">","Schwetzingen","Waghäusel",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-027","2021-06-01","N"]
[null,80,"D34-039","Karlsruhe - Mannheim","<","Waghäusel","Mannheim-Rheinau",2023,2023,33,36,"2023-08-20","00:30:00","2023-09-04","04:30:00","15d, 4h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-039","2021-06-01","N"]
[null,80,"D34-075","Karlsruhe - Mannheim",">","Waghäusel","Schwetzingen",2023,2023,43,45,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-075","2021-06-01","N"]
[null,80,"D34-040","Karlsruhe - Mannheim","<","Waghäusel","Mannheim-Rheinau",2023,2023,39,41,"2023-09-25","00:30:00","2023-10-09","04:30:00","14d, 4h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-040","2021-06-01","N"]
[null,80,"D34-076","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2023,2023,41,42,"2023-10-11","23:30:00","2023-10-17","04:30:00","5d, 5h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-076","2021-06-01","N"]
[null,80,"D34-016","Karlsruhe - Mannheim","<","Hockenheim","Schwetzingen",2023,2023,33,36,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-016","2021-06-01","N"]
[null,80,"D34-019","Karlsruhe - Mannheim",">","Schwetzingen","Waghäusel",2023,2023,38,41,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-019","2021-06-01","N"]
[null,80,"D34-069","Karlsruhe - Mannheim","<","Waghäusel","Schwetzingen",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-069","2021-06-01","N"]
[null,80,"D34-043","Karlsruhe - Mannheim",">","Hockenheim","Waghäusel",2023,2023,45,45,"2023-11-07","00:30:00","2023-11-08","04:30:00","1d, 4h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-043","2021-06-01","N"]
[null,80,"D34-071","Karlsruhe - Mannheim","<","Waghäusel","Hockenheim",2023,2023,45,45,"2023-11-07","00:30:00","2023-11-08","04:30:00","1d, 4h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D34-071","2021-06-01","N"]
[null,80,"D34-044","Karlsruhe - Mannheim","<","Waghäusel","Hockenheim",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-044","2021-06-01","N"]
[null,80,"D34-081","Karlsruhe - Mannheim",">","Oftersheim","Waghäusel",2023,2023,43,45,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D34-081","2021-06-01","N"]
[null,80,"D36-007","Stuttgart - München",">","Augsb Hirbl Str","Westheim/Schwab",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D36-007","2021-06-01","N"]
[null,80,"D38-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,34,34,"2023-08-21","03:00:00","2023-08-21","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D38-001","2021-05-18","N"]
[null,80,"D3D-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,41,42,"2023-10-15","22:00:00","2023-10-16","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D3D-001","2021-06-07","N"]
[null,80,"D42-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,8,8,"2023-02-20","03:00:00","2023-02-20","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D42-001","2021-05-18","N"]
[null,80,"D43-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D43-001","2021-06-07","N"]
[null,80,"D48-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,43,44,"2023-10-29","22:00:00","2023-10-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D48-001","2021-06-07","N"]
[null,80,"D4E-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D4E-001","2021-06-07","N"]
[null,80,"D51-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,30,30,"2023-07-24","03:00:00","2023-07-24","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D51-001","2021-05-18","N"]
[null,80,"D52-001","Karlsruhe - Mannheim","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,31,32,"2023-08-06","22:00:00","2023-08-07","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D52-001","2021-06-08","N"]
[null,80,"D60-002","Gemünden - Bamberg - Nürnberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,20,21,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-002","2021-06-01","N"]
[null,80,"D60-034","Gemünden - Bamberg - Nürnberg",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-15","05:00:00","2023-05-16","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-034","2021-06-01","N"]
[null,80,"D60-020","Gemünden - Würzburg - Nürnberg","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,24,24,"2023-06-12","05:00:00","2023-06-13","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-020","2021-06-02","N"]
[null,80,"D60-013","Gemünden - Bamberg - Nürnberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,23,24,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-013","2021-06-01","N"]
[null,80,"D60-033","Gemünden - Bamberg - Nürnberg","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,25,25,"2023-06-19","05:00:00","2023-06-20","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-033","2021-06-02","N"]
[null,80,"D60-010","Gemünden - Bamberg - Nürnberg","<","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-15","05:00:00","2023-05-16","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-010","2021-06-01","N"]
[null,80,"D60-017","Gemünden - Bamberg - Nürnberg","<","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,21,21,"2023-05-22","12:00:00","2023-05-22","18:00:00","0d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-017","2021-06-01","N"]
[null,80,"D60-005","Gemünden - Würzburg - Nürnberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,24,24,"2023-06-12","05:00:00","2023-06-13","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-005","2021-06-01","N"]
[null,80,"D60-019","Gemünden - Würzburg - Nürnberg",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D60-019","2021-06-01","N"]
[null,80,"D62-003","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D62-003","2021-06-14","N"]
[null,80,"D62-001","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D62-001","2021-06-14","N"]
[null,80,"D62-002","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D62-002","2021-06-14","N"]
[null,80,"D66-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,27,28,"2023-07-09","22:00:00","2023-07-10","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D66-001","2021-06-07","N"]
[null,80,"D67-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,43,44,"2023-10-29","22:00:00","2023-10-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D67-001","2021-06-08","N"]
[null,80,"D73-001","Darmstadt - Aschaffenburg",">","Aschaffenbg Hbf","Darmstadt Hbf",2022,2023,50,48,"2022-12-17","22:30:00","2023-12-03","05:30:00","350d, 7h","periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","D73-001","2021-06-09","N"]
[null,80,"D81-001","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D81-001","2021-06-14","N"]
[null,80,"D81-003","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D81-003","2021-06-14","N"]
[null,80,"D81-002","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D81-002","2021-06-14","N"]
[null,80,"D85-002","Gemünden - Bamberg - Nürnberg","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,17,21,"2023-04-24","01:00:00","2023-05-26","16:00:00","32d, 15h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D85-002","2021-05-03","N"]
[null,80,"D87-003","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D87-003","2021-06-14","N"]
[null,80,"D87-002","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D87-002","2021-06-14","N"]
[null,80,"D87-001","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D87-001","2021-06-14","N"]
[null,80,"D97-009","Gemünden - Würzburg - Nürnberg","<>","Wiesthal","Nantenbach",2023,2023,43,47,"2023-10-28","23:30:00","2023-11-20","04:30:00","22d, 6h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","D97-009","2021-06-04","N"]
[null,80,"D97-008","Gemünden - Würzburg - Nürnberg",">","Lohr Bahnhof","Partenstein",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D97-008","2021-06-04","N"]
[null,80,"D97-006","Gemünden - Würzburg - Nürnberg","<>","Partenstein","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D97-006","2021-06-04","N"]
[null,80,"D97-007","Gemünden - Würzburg - Nürnberg","<>","Partenstein","Lohr Bahnhof",2023,2023,47,47,"2023-11-25","14:00:00","2023-11-26","12:00:00","0d, 22h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","D97-007","2021-06-04","N"]
[null,80,"D97-010","Gemünden - Würzburg - Nürnberg",">","Lohr Bahnhof","Partenstein",2023,2023,47,47,"2023-11-25","14:00:00","2023-11-26","12:00:00","0d, 22h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D97-010","2021-06-04","N"]
[null,80,"D98-003","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D98-003","2021-06-08","N"]
[null,80,"D98-002","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","D98-002","2021-06-08","N"]
[null,80,"D98-001","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D98-001","2021-06-08","N"]
[null,80,"D9A-004","Karlsruhe - Stuttgart","<>","Karlsruhe Hbf","Karlsr-Durlach",2023,2023,21,22,"2023-05-26","12:00:00","2023-05-30","05:00:00","3d, 17h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","D9A-004","2021-07-13","N"]
[null,80,"D9A-003","Karlsruhe - Bruchsal","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,41,42,"2023-10-13","22:00:00","2023-10-16","12:00:00","2d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","D9A-003","2021-05-17","N"]
[null,80,"D9A-001","Karlsruhe - Bruchsal","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,42,43,"2023-10-22","12:00:00","2023-10-23","12:00:00","1d, 0h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","D9A-001","2021-05-17","N"]
[null,80,"D9A-002","Karlsruhe - Bruchsal","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,42,43,"2023-10-20","22:00:00","2023-10-23","12:00:00","2d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","D9A-002","2021-05-17","N"]
[null,80,"D9B-005","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D9B-005","2021-06-08","N"]
[null,80,"D9B-007","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","D9B-007","2021-06-08","N"]
[null,80,"D9B-006","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","D9B-006","2021-06-08","N"]
[null,80,"DAD-001","Karlsruhe - Mannheim",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,10,10,"2023-03-06","03:00:00","2023-03-06","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DAD-001","2021-05-18","N"]
[null,80,"DAF-003","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DAF-003","2021-06-08","N"]
[null,80,"DAF-002","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DAF-002","2021-06-08","N"]
[null,80,"DAF-001","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","DAF-001","2021-06-08","N"]
[null,80,"DB1-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DB1-001","2021-06-07","N"]
[null,80,"DBB-004","Mannheim - Darmstadt","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","DBB-004","2021-05-11","N"]
[null,80,"DBB-003","Mannheim - Darmstadt",">","Bickenbach","Da-Eberst Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBB-003","2021-05-11","N"]
[null,80,"DBD-001","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBD-001","2021-06-14","N"]
[null,80,"DBD-003","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBD-003","2021-06-14","N"]
[null,80,"DBD-002","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBD-002","2021-06-14","N"]
[null,80,"DBF-001","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBF-001","2021-06-14","N"]
[null,80,"DBF-002","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBF-002","2021-06-14","N"]
[null,80,"DBF-003","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DBF-003","2021-06-14","N"]
[null,80,"DC3-020","Gemünden - Würzburg - Nürnberg","<>","Wiesthal","Laufach",2023,2023,16,17,"2023-04-22","23:30:00","2023-04-24","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-020","2021-06-02","N"]
[null,80,"DC3-015","Gemünden - Würzburg - Nürnberg",">","Partenstein","Lohr Bahnhof",2023,2023,38,41,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DC3-015","2021-06-02","N"]
[null,80,"DC3-012","Gemünden - Würzburg - Nürnberg","<","Laufach","Wiesthal",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DC3-012","2021-06-02","N"]
[null,80,"DC3-005","Gemünden - Würzburg - Nürnberg","<>","Partenstein","Lohr Bahnhof",2023,2023,37,38,"2023-09-16","23:30:00","2023-09-18","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-005","2021-06-02","N"]
[null,80,"DC3-028","Gemünden - Würzburg - Nürnberg","<>","Wiesthal","Laufach",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","DC3-028","2021-06-02","N"]
[null,80,"DC3-021","Gemünden - Würzburg - Nürnberg","<>","Wiesthal","Laufach",2023,2023,15,16,"2023-04-15","23:30:00","2023-04-17","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-021","2021-06-02","N"]
[null,80,"DC3-022","Gemünden - Würzburg - Nürnberg","<>","Lohr Bahnhof","Partenstein",2023,2023,47,48,"2023-11-26","12:00:00","2023-11-27","05:00:00","0d, 17h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","DC3-022","2021-06-02","N"]
[null,80,"DC3-008","Gemünden - Würzburg - Nürnberg","<","Partenstein","Lohr Bahnhof",2023,2023,47,48,"2023-11-26","12:00:00","2023-11-27","05:00:00","0d, 17h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DC3-008","2021-06-02","N"]
[null,80,"DC3-010","Aschaffenburg - Gemünden","<>","Rohrbach","Nantenbach",2023,2023,39,40,"2023-09-30","23:30:00","2023-10-02","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-010","2021-06-02","N"]
[null,80,"DC3-024","Gemünden - Würzburg - Nürnberg","<>","Langenprozelten","Wiesthal",2023,2023,39,40,"2023-09-30","23:30:00","2023-10-02","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-024","2021-06-02","N"]
[null,80,"DC3-017","Gemünden - Würzburg - Nürnberg","<>","Lohr Bahnhof","Partenstein",2023,2023,38,41,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","DC3-017","2021-06-02","N"]
[null,80,"DC3-025","Gemünden - Würzburg - Nürnberg","<>","Langenprozelten","Wiesthal",2023,2023,40,41,"2023-10-07","23:30:00","2023-10-09","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-025","2021-06-02","N"]
[null,80,"DC3-033","Aschaffenburg - Gemünden","<>","Rohrbach","Nantenbach",2023,2023,38,39,"2023-09-23","23:30:00","2023-09-25","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-033","2021-06-02","N"]
[null,80,"DC3-027","Gemünden - Würzburg - Nürnberg","<>","Langenprozelten","Wiesthal",2023,2023,38,39,"2023-09-23","23:30:00","2023-09-25","04:30:00","1d, 5h","periodical","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","DC3-027","2021-06-02","N"]
[null,80,"DCA-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,17,18,"2023-04-30","22:00:00","2023-05-01","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DCA-001","2021-06-07","N"]
[null,80,"DCB-001","Stuttgart - München",">","Süßen","Ulm Hbf Em Nord",2023,2023,44,45,"2023-11-03","23:00:00","2023-11-08","05:00:00","4d, 6h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DCB-001","2021-06-16","N"]
[null,80,"DCB-002","Stuttgart - München",">","Süßen","Ulm Hbf Em Nord",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-17","05:00:00","4d, 6h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DCB-002","2021-06-16","N"]
[null,80,"DCF-001","Mannheim - Darmstadt",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,39,40,"2023-10-01","22:00:00","2023-10-02","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DCF-001","2021-06-07","N"]
[null,80,"DD0-001","Karlsruhe - Mannheim",">","Mannheim Hbf","Molzau",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD0-001","2021-06-08","N"]
[null,80,"DD0-002","Karlsruhe - Mannheim",">","Molzau","Graben-Neudorf",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","DD0-002","2021-06-08","N"]
[null,80,"DD0-003","Karlsruhe - Mannheim",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD0-003","2021-06-08","N"]
[null,80,"DD3-003","Strasbourg - Karlsruhe",">","Karlsruhe Hbf","Bashaide",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD3-003","2021-06-14","N"]
[null,80,"DD3-002","Strasbourg - Karlsruhe",">","Bashaide","Ötigheim",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD3-002","2021-06-14","N"]
[null,80,"DD3-001","Strasbourg - Karlsruhe",">","Ötigheim","Rastatt",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD3-001","2021-06-14","N"]
[null,80,"DD4-001","Karlsruhe - Mannheim",">","N-Edingen/F-feld","Schwetzingen",2023,2023,45,46,"2023-11-12","22:00:00","2023-11-13","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","DD4-001","2021-06-08","N"]
[null,81,"81-58386","Linz - Wien","<","Wien Matzleinsdorf","W.Mat.-Laxenburg",2021,2022,12,16,"27.03.2021","04:00","19.04.2022","03:00","388 days","cont.","BFUM","","LT","","","","","","","","","Umbau der Hst. Wien Matzleinsdorfer Platz","","N","","16.12.2020","N","",3105,5526,"","","","","","","",""]
[null,81,"81-58391","Linz - Wien","<","Wien Matzleinsdorf","W.Mat.-Laxenburg",2021,2021,14,35,"06.04.2021","03:00","05.09.2021","04:00","152 days + 1,0 h","cont.","SP","","LT","","","","C","","B",0,"","Umbau der Hast. Wien Matzleinsdorfer Platz (Bstg-Verlägerung auf 220 m, Errichtung neuer Zugang etc.)","","N","","16.12.2020","N","",3105,5526,0,0,"","","","","",""]
[null,81,"81-54552","Salzburg - Wels","< >","Steindorf bei Straßwalchen","Friedburg",2021,2021,27,36,"10.07.2021","05:00","12.09.2021","20:00","64 days + 15,0 h","cont.","GES","T","LT","","","","C","","B","","","GN mit Einsatz AHM, Ausbau AB W 1L,2L,1Fe und 1Bo sowie W 301\nEinschub Tragwerk Hainbachbrücke, Herstellung Unterbau Umbau Bf Friedburg - Gleis 722neu, Errichtung neuer Bstg. WN,","","Y","","30.03.2021","N","",1105,2041,"","","","","","","",""]
[null,81,"81-57877","Wien - Parndorf","<","Götzendorf","Üst Goe 2",2021,2021,28,31,"16.07.2021","04:30","06.08.2021","17:00","21 days + 12,5 h","cont.","SP","","LT","","","","C","","B",30,"","Bahnsteig Trautmannsdorf nicht nutzbar","","N","","16.12.2020","Y","",2969,90247,2,5,"","","","","",""]
[null,81,"81-58947","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2021,2021,29,33,"25.07.2021","18:00","20.08.2021","17:00","25 days + 23,0 h","cont.","GES","T","LT","","","","","","","","","Weichentausch W1,2,3,4,5,6,54,57\nWeichenausbau: 58,59\nOberbauarbeiten+Sanierung im Sittenbergtunnel","","Y","","22.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-59883","Linz - Wien","< >","Unter Purkersdorf","",2021,2021,30,32,"26.07.2021","00:00","13.08.2021","23:59","19 days","cont.","SP","","ST","","","","C","","B","","","Neulage W34,35; Neulage prov. Gleis 2 von AS R2 - W64(a); Neulage Gleis 4; Abtrag Gleis 4a; Neuerrichtung Übergangssteg;","","N","","03.05.2021","N","",1012,"","","","","","","","",""]
[null,81,"81-57461","Wien - Parndorf",">","Abzww Str 11815","Üst Goe 2",2021,2021,31,37,"07.08.2021","08:00","16.09.2021","04:30","39 days + 20,5 h","cont.","SP","","LT","","","","C","","B",30,"","Gleisneulage","","N","","16.12.2020","Y","",91011,90247,2,5,"","","","","",""]
[null,81,"81-59147","Linz - Wien","<","Abzww St.Peter-Seitenstetten Ost","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,35,36,"30.08.2021","22:40","10.09.2021","05:00","9x 6,3 h","period.","SP","","LT","","","","","","",0,"","Vorarmieren Oberleitungsmaste\nEinbau Trenner St. Peter-Seitenstetten","","Y","","16.12.2020","N","",91010,90784,0,7,"","","","","",""]
[null,81,"81-58852","Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2021,2021,35,35,"30.08.2021","23:00","03.09.2021","04:30","4x 5,5 h","period.","WF","T","LT","","","","C","","","","","Drainagespülen Melker Tunnel mit OBW+Niederflurwagen","","N","","12.01.2021","N","",91055,1042,"","","","","","","",""]
[null,81,"81-60615","Salzburg - Wels",">","Steindorf bei Straßwalchen","",2021,2021,35,36,"04.09.2021","22:00","06.09.2021","05:00","1 day + 7,0 h","cont.","SP","","ST","","","","","","",5,"","Einbau W 59 und 61\nAbtrag W 57alt","","N","","01.03.2021","N","",1105,"",1,3,"","","","","",""]
[null,81,"81-60616","Salzburg - Wels","<","Steindorf bei Straßwalchen","",2021,2021,36,36,"06.09.2021","05:00","07.09.2021","05:00","1 day","cont.","SP","","ST","","","","","","",5,"","Einbau W 60\nAbtrag W 58alt","","N","","01.03.2021","N","",1105,"",1,3,"","","","","",""]
[null,81,"81-58392","Linz - Wien",">","Wien Matzleinsdorf","W.Mat.-Laxenburg",2021,2021,35,49,"05.09.2021","04:00","12.12.2021","03:00","98 days","cont.","SP","","LT","","","","C","","B",0,"","Umbau der Hast. Wien Matzleinsdorfer Platz (Bstg-Verlägerung auf 220 m, Errichtung neuer Zugang etc.)","","N","","16.12.2020","N","",3105,5526,0,0,"","","","","",""]
[null,81,"81-58849","Linz - Wien",">","Pöchlarn","Ybbs a.d.Donau",2021,2021,36,36,"06.09.2021","23:00","10.09.2021","04:30","4x 5,5 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-57959","Linz - Wien","<","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,36,38,"11.09.2021","00:00","20.09.2021","04:00","9 days + 4,0 h","cont.","SP","","LT","S","","","C","","B",10,"","Erneuerung der Oberleitung auf Sgl 1 von km 145,100 bis km 147,200","","N","","16.12.2020","N","",1056,90784,0,0,"","","","","",""]
[null,81,"81-59148","Linz - Wien","<","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,36,37,"11.09.2021","07:00","19.09.2021","18:00","8 days + 11,0 h","cont.","SP","","LT","","","","C","","B","","","Abtrag OL-Kette, alter Ausleger, alte Fundamente + verfüllen\nZiehen Altmasten\nZu Beginn der Sperre freischalten Bf. Sp 106 für 1 Stunde\nzusätzlich: 17/18.+18/19.22:40 - 05:00freischalten SpSG106 \n19/20. 22:40 - 05:00 freischalten SpSG106+206","","Y","","04.03.2021","N","",1056,90784,"","","","","","","",""]
[null,81,"81-58850","Linz - Wien",">","Pöchlarn","Ybbs a.d.Donau",2021,2021,37,37,"13.09.2021","23:00","17.09.2021","04:30","4x 5,5 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-58003","Salzburg - Wels","<","Attnang-Puchheim","Sbl At 1",2021,2021,37,38,"17.09.2021","22:00","20.09.2021","05:00","2 days + 7,0 h","cont.","SP","","LT","","","","C","","B",5,"","Neubau Brücke","","N","","16.12.2020","N","",1091,90065,2,2,"","","","","",""]
[null,81,"81-58851","Linz - Wien",">","Pöchlarn","Ybbs a.d.Donau",2021,2021,38,38,"20.09.2021","23:00","24.09.2021","04:30","4x 5,5 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen Sittenbergtunnel mit OBW+Niederflurwagen","","N","","12.01.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-60418","Linz - Wien","< >","Üst Hdd 1","Tullnerfeld-Ost",2021,2021,38,38,"24.09.2021","00:00","24.09.2021","24:00","1 day","cont.","WF","","LT","","","","","","","","","Feuerwehr Tunnelübung \ngrundsätzlich KEINE betrieblichen Einschränkungen","","N","","12.01.2021","Y","",90285,90862,"","","","","","","",""]
[null,81,"81-58004","Salzburg - Wels",">","Attnang-Puchheim","Sbl At 1",2021,2021,38,39,"24.09.2021","22:00","27.09.2021","05:00","2 days + 7,0 h","cont.","SP","","LT","","","","C","","B",5,"","Neubau Brücke","","N","","16.12.2020","N","",1091,90065,2,2,"","","","","",""]
[null,81,"81-60904","Wien - Sopron","< >","Ebenfurth","Abzww Ebenfurth Süd",2021,2021,38,38,"26.09.2021","01:00","26.09.2021","16:00","15,0 h","cont.","SP","","LT","","","","C","","B",0,"","Schienentausch","","N","","10.05.2021","N","",3199,90142,0,0,"","","","","",""]
[null,81,"81-59171","Wien - Parndorf","< >","Wampersdorf","Gramatneusiedl",2021,2021,38,39,"26.09.2021","09:00","27.09.2021","17:00","2x 8,0 h","period.","WF","T","LT","","","","C","","B","","","Instandsetzungsarbeiten","","Y","","07.01.2021","N","",3197,2968,"","","","","","","",""]
[null,81,"81-60905","Wien - Sopron",">","Ebenfurth","Abzww Ebenfurth Süd",2021,2021,38,39,"26.09.2021","16:00","27.09.2021","04:00","12,0 h","cont.","SP","","LT","","","","","","",0,"","Schienentausch","","N","","10.05.2021","N","",3199,90142,0,0,"","","","","",""]
[null,81,"81-58853","Linz - Wien",">","Abzww St.Peter-Seitenstetten Ost","Abzw Knoten St.Peter-Seitenstetten West",2021,2021,39,39,"27.09.2021","22:30","01.10.2021","05:00","4x 6,5 h","period.","WF","T","LT","","","","C","","","","","Drainagespülen Grüntunnel mit OBW+Niederflurwagen","","N","","12.01.2021","N","",91010,90784,"","","","","","","",""]
[null,81,"81-58868","Linz - Wien","< >","Loosdorf","Pöchlarn",2021,2021,39,39,"02.10.2021","23:30","03.10.2021","04:30","5,0 h","cont.","WF","T","LT","","","","","","","","","Sonderinspektion Wachbergtunnel alt mit OBW","","N","","08.01.2021","N","",1040,1042,"","","","","","","",""]
[null,81,"81-60572","Linz - Wien","<","Enns","Abzw Sv 11",2021,2021,40,40,"04.10.2021","07:50","08.10.2021","15:40","4x 7,8 h","period.","SP","","LT","","","","","","","","","Erneuerungen Oberleitung","","N","","02.03.2021","N","",1064,90821,"","","","","","","",""]
[null,81,"81-57750","Linz - Wien","<","Sbl Spw 2","Sbl Spw 5",2021,2021,40,42,"04.10.2021","22:30","24.10.2021","05:00","20x 6,5 h","period.","WF","T","LT","","","","C","","B",5,"","Spülen und Fräsen Siebergtunnel","","N","","12.01.2021","N","",90776,90783,5,0,"","","","","",""]
[null,81,"81-57900","Linz - Wien",">","Abzw Sv 11","Enns",2021,2021,41,41,"11.10.2021","07:50","13.10.2021","15:40","3x 7,8 h","period.","SP","","LT","","","","","","","","","Erneuerungen Oberleitung","","N","","01.03.2021","N","",90821,1064,"","","","","","","",""]
[null,81,"81-59769","Wien - Parndorf",">","Himberg","",2021,2021,41,42,"15.10.2021","23:20","18.10.2021","04:30","2 days + 5,2 h","cont.","SP","","ST","","","","C","","B",20,"","Bohrpfahlherstellung","","N","","07.01.2021","N","",2966,"",2,5,"","","","","",""]
[null,81,"81-60844","Linz - Wien","< >","Tullnerbach-Pressbaum","",2021,2021,42,44,"23.10.2021","01:30","02.11.2021","04:00","10 days + 3,5 h","cont.","GES","T","ST","","","","C","","B","","","Bauphase 1.1:\nAusbau W 54(alt),55(alt) und Einbau W 58(neu), 59(neu) westlich. Abtrag Fahrleitung+Ober-u. Unterbau im Bereich km 20,406.\nErrichten Unterbau für Hilfsbrücke mit Bohrpfählen, Fertigteilen.\nUmbau Stellwerk, Kabelführung neu, neue Signale;","","N","","26.05.2021","N","",1015,"","","","","","","","",""]
[null,81,"81-58950","Linz - Wien","< >","Tullnerbach-Pressbaum","",2021,2021,42,44,"23.10.2021","02:40","02.11.2021","04:10","10 days + 2,5 h","cont.","GES","T","ST","","","","C","","B","","","Errichten von Bohrpfählen zum Auflegen von 2 Hilfsbrücken. Befahrbarkeit der Hilfsbrücke Vmax60km/h.\nVersetzen der Weichen 54,55. Versetzen der ES FR2.  \nVersetzen der Weichen 3,4. Versetzen der ES FR1.","","N","","01.03.2021","N","",1015,"","","","","","","","",""]
[null,81,"81-60669","Linz - Wien","< >","Unter Purkersdorf","",2021,2021,42,44,"23.10.2021","02:40","02.11.2021","04:10","10 days + 2,5 h","cont.","BFUM","","ST","S","","","","","","","","Umbau der Sicherungsanlage: Einbinden der Weichen 34,35; Inbetriebnahme der neuen Schutzsignale\nSignalabhängigkeit im Bf. Unter Purkersdorf aufgehoben von ES-ES; Blöcke/Üst tauglich.\n\nAchtung: Gesamtsperre Pm(Hilfsbrücken), Umleitung, SEV","","N","","02.03.2021","N","",1012,"","","","","","","","",""]
[null,81,"81-59770","Wien - Parndorf",">","Himberg","",2021,2021,42,43,"23.10.2021","23:20","27.10.2021","04:30","3 days + 5,2 h","cont.","SP","","ST","","","","C","","B",20,"","Einbau Hilfsbrücke","","N","","07.01.2021","N","",2966,"",2,5,"","","","","",""]
[null,81,"81-60313","Regensburg - Wels","< >","Wels Vbf-Terminal","Wels Vbf",2021,2021,43,44,"29.10.2021","22:00","04.11.2021","15:30","5 days + 18,5 h","cont.","SP","","LT","","","","C","","","","","WN DKW 108/109, DKW 110/111, W 116","","Y","","15.06.2021","N","",1968,1080,"","","","","","","",""]
[null,81,"81-57569","Wien - Sopron","< >","Münchendorf","Wampersdorf",2021,2021,43,44,"29.10.2021","22:00","03.11.2021","04:30","4 days + 7,5 h","cont.","GES","T","LT","","","","C","","B","","","Verschwenken alte Trasse und Tausch Weiche 3 in Wampersdorf","","Y","","07.01.2021","N","",3194,3197,"","","","","","","",""]
[null,81,"81-60649","Regensburg - Wels","< >","Wels Vbf-Einfgr","",2021,2021,45,46,"13.11.2021","07:00","19.11.2021","18:00","6 days + 11,0 h","cont.","SP","","ST","","","","C","","","","","GNL, WN 402,407","","Y","","15.06.2021","N","",5839,"","","","","","","","",""]
[null,81,"81-60650","Regensburg - Wels","< >","Wels Vbf-Einfgr","",2021,2021,45,46,"13.11.2021","07:00","17.11.2021","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","C","","","","","GNL, WN 403, 406","","Y","","15.06.2021","N","",5839,"","","","","","","","",""]
[null,81,"81-57496","Salzburg - Wels","<","Steindorf bei Straßwalchen","Straßwalchen",2021,2021,45,47,"13.11.2021","08:00","26.11.2021","17:00","13 days + 9,0 h","cont.","SP","","LT","","","","C","","B",5,"","GN mit PLV","","Y","","16.12.2020","N","",1105,1104,2,2,"","","","","",""]
[null,81,"81-57497","Salzburg - Wels","<","Steindorf bei Straßwalchen","",2021,2021,45,47,"13.11.2021","08:00","26.11.2021","17:00","13 days + 9,0 h","cont.","SP","","ST","","","","C","","B",5,"","GN mit PLV","","Y","","16.12.2020","N","",1105,"",2,2,"","","","","",""]
[null,81,"81-58895","Linz - Wien","< >","Tullnerfeld","Abzww Knoten Wagram Nord",2021,2021,47,49,"22.11.2021","23:30","10.12.2021","05:00","18x 5,5 h","period.","WF","","LT","","","","","","","","","Drainage spülen mit OBW+Niederflurwagen","","N","","08.01.2021","N","",1295,91052,"","","","","","","",""]
[null,81,"81-58888","Linz - Wien","< >","Wien Meidling","W.Mat.-Oswaldgasse",2021,2023,49,21,"12.12.2021","00:00","26.05.2023","24:00","531 days","cont.","GES","T","LT","","","","C","","B","","","zweigleisiger Ausbau - Sperre Oswaldschleife","","N","","25.05.2021","N","100%",3107,1274,"","","","","","","","Major"]
[null,81,"81-59529","Salzburg - Wels","<","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,4,5,"28.01.2022","23:00","31.01.2022","05:00","2 days + 6,0 h","cont.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-59530","Salzburg - Wels","<","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,5,6,"04.02.2022","23:00","07.02.2022","05:00","2 days + 6,0 h","cont.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-59531","Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,5,6,"05.02.2022","20:00","07.02.2022","06:00","2x 10,0 h","period.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-59532","Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,6,7,"12.02.2022","20:00","14.02.2022","06:00","2x 10,0 h","period.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-60721","Linz - Wien","< >","Üst Roh 3","Üst Roh 6",2022,2022,7,7,"14.02.2022","22:00","18.02.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","29.04.2021","N","",90723,90724,"","","","","","","",""]
[null,81,"81-59533","Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,7,8,"19.02.2022","20:00","21.02.2022","06:00","2x 10,0 h","period.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-59534","Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,8,9,"21.02.2022","22:00","28.02.2022","05:00","7x 7,0 h","period.","SP","","LT","","","","C","","B",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","Y","","16.12.2020","N","","",1105,2,2,"","","","","",""]
[null,81,"81-60722","Linz - Wien","< >","Üst Roh 3","Üst Roh 6",2022,2022,8,8,"21.02.2022","22:00","25.02.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","29.04.2021","N","",90723,90724,"","","","","","","",""]
[null,81,"81-60725","Linz - Wien","< >","Loosdorf","Sbl Los 4",2022,2022,8,8,"26.02.2022","22:00","27.02.2022","05:00","7,0 h","cont.","WF","T","LT","","","","C","","B","","","Sonderinspektion \nTUF","","N","","05.04.2021","N","",1040,90503,"","","","","","","",""]
[null,81,"81-60726","Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,10,10,"07.03.2022","22:00","11.03.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",91010,1061,"","","","","","","",""]
[null,81,"81-60740","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,10,11,"11.03.2022","23:30","20.03.2022","05:30","9x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60727","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,11,11,"14.03.2022","22:00","18.03.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-59414","Wels - Linz","< >","Linz Hbf","Linz Gaumberg",2022,2022,11,12,"18.03.2022","22:30","21.03.2022","20:00","2 days + 21,5 h","cont.","SP","","LT","","","","","","","","","Anbindung Gleis 2 (Gleis 4Neu)","","N","","03.05.2021","N","",1073,5984,"","","","","","","",""]
[null,81,"81-59415","Wels - Linz","<","Linz Gaumberg","Linz Hbf",2022,2022,12,13,"21.03.2022","20:00","29.03.2022","06:00","7 days + 9,0 h","cont.","SP","","LT","","","","","","","","","Anbindung Gleis 1 (Gleis 3Neu) \nWN W 348 und W 352","","N","","03.05.2021","N","",5984,1073,"","","","","","","",""]
[null,81,"81-59416","Wels - Linz",">","Linz Hbf","Marchtrenk",2022,2022,12,13,"25.03.2022","22:00","29.03.2022","05:00","4x 7,0 h","period.","SP","","LT","","","","","","","","","IB ESTW Hörsching","","N","","16.12.2020","N","",1073,1079,"","","","","","","",""]
[null,81,"81-59586","Wels - Linz","< >","Hörsching","",2022,2022,12,13,"26.03.2022","22:00","29.03.2022","05:00","2 days + 6,0 h","cont.","SP","","ST","S","","","","","","","","IB ESTW Hörsching - aufgehobene Signalabhängigkeit\nmit Sicherheitserprobung","","N","","16.12.2020","N","",1077,"","","","","","","","",""]
[null,81,"81-59869","Wels - Linz",">","Sbl Lz 3","Hörsching",2022,2022,12,12,"26.03.2022","22:00","27.03.2022","05:00","6,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 1 (Gl 2 Lz-Hoe)","","N","","16.12.2020","N","",90513,1077,"","","","","","","",""]
[null,81,"81-59870","Wels - Linz",">","Hörsching","Marchtrenk",2022,2022,12,12,"27.03.2022","05:00","27.03.2022","22:00","17,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 2 (Gl 2 Lz-Mak)","","N","","16.12.2020","N","",1077,1079,"","","","","","","",""]
[null,81,"81-59871","Wels - Linz","<","Hörsching","Sbl Lz 3",2022,2022,12,13,"27.03.2022","22:00","28.03.2022","17:00","19,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 3 (Gl 1 Hoe-Lz)","","N","","16.12.2020","N","",1077,90513,"","","","","","","",""]
[null,81,"81-59872","Wels - Linz","<","Hörsching","Sbl Hoe 1",2022,2022,13,13,"28.03.2022","17:00","29.03.2022","05:00","12,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 4 (Gl 1 Hoe-Mak)","","N","","16.12.2020","N","",1077,90329,"","","","","","","",""]
[null,81,"81-60728","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,12,12,"21.03.2022","22:00","25.03.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-59671","Linz - Wien",">","Sbl Spw 5","Sbl Spw 2",2022,2022,12,14,"21.03.2022","22:30","10.04.2022","05:00","15x 6,5 h","period.","GES","T","LT","","","","C","","B",6,"","Kanalspülen","","N","","19.01.2021","N","",90782,90776,4,0,"","","","","",""]
[null,81,"81-60741","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,12,12,"21.03.2022","23:30","26.03.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-59587","Salzburg - Wels","< >","Gunskirchen","",2022,2022,12,12,"26.03.2022","22:00","27.03.2022","05:00","6,0 h","cont.","SP","","ST","S","","","C","","B","","","IB ESTW Bf Gunskirchen - aufgehobenen Signalabhängigkeit mit Sicherheitserprobung","","N","","19.01.2021","N","",1085,"","","","","","","","",""]
[null,81,"81-60729","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,13,13,"28.03.2022","22:00","01.04.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-60746","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,13,13,"28.03.2022","23:30","02.04.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60730","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,14,14,"04.04.2022","22:00","08.04.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-60747","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,14,14,"04.04.2022","23:30","09.04.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","05.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60748","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,14,14,"04.04.2022","23:30","09.04.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-59824","Wien - Parndorf",">","Himberg","",2022,2022,14,16,"08.04.2022","22:00","19.04.2022","04:00","10 days + 6,0 h","cont.","SP","","ST","","","","C","","B",30,"","Unterbausanierung","","N","","05.04.2021","Y","",2966,"",2,5,"","","","","",""]
[null,81,"81-59225","Linz - Wien","< >","Abzw Ams 11","Waidhofen a.d.Ybbs",2022,2022,14,16,"09.04.2022","00:00","19.04.2022","04:00","10 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Schotterbettreinigung km 22,350-23,000 Böhlerwerke-Waidhofen;\nErneuerung Oberleitung: km7,045-8,902; km7,808-8,071; \nErneuerung ABWeichen: km11,853-11,850; \nTausch Einzelschw, ZW, MDZ-Einsatz: Kröllendf-Hilm\nSchienenneulage+Schotterbettr: Hilm-Rosenau","","N","","22.06.2021","N","",90046,1437,"","","","","","","",""]
[null,81,"81-59232","Linz - Wien",">","Prinzersdorf","",2022,2022,14,17,"09.04.2022","00:00","25.04.2022","04:00","16 days + 4,0 h","cont.","SP","","ST","","","","C","","B",2,"","Weichentausch W 52,53,54,55,56,57","","Y","","22.06.2021","N","",1037,"",2.5,0,"","","","","",""]
[null,81,"81-60749","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,15,15,"11.04.2022","23:30","16.04.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-59226","Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,15,17,"15.04.2022","01:00","25.04.2022","04:00","10 days + 3,0 h","cont.","GES","T","LT","","","","C","","B","","","Sankt Peter-Seitenstetten: Schotterbettreinigung W 6,7,52,54,  \nErrichtung Grabenmauer km 145,260-146,500\nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","","16.12.2020","N","",91010,1061,"","","","","","","",""]
[null,81,"81-59825","Wien - Parndorf",">","Himberg","Gramatneusiedl",2022,2022,16,21,"19.04.2022","05:00","23.05.2022","05:00","34 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","","05.04.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-60754","Linz - Wien","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,16,17,"19.04.2022","23:30","30.04.2022","05:30","11x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90859,91052,"","","","","","","",""]
[null,81,"81-59228","Linz - Wien","<","St.Peter-Seitenstetten","Üst Spw 13",2022,2022,17,18,"25.04.2022","01:00","05.05.2022","04:00","10 days + 3,0 h","cont.","SP","","LT","","","","C","","B","","","Errichtung Grabenmauer km 145,260-146,500\nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","","16.12.2020","N","",1056,90269,"","","","","","","",""]
[null,81,"81-59861","Wels - Linz","<","Marchtrenk","Wels Hbf",2022,2022,17,19,"25.04.2022","08:00","11.05.2022","18:00","16 days + 10,0 h","cont.","SP","","LT","","","","C","","B",10,"","GN","","Y","","19.01.2021","N","",1079,1081,2,3,"","","","","",""]
[null,81,"81-59328","Wels - Linz",">","Üst Lz 2","Hörsching",2022,2022,17,19,"25.04.2022","21:30","12.05.2022","05:00","15x 7,5 h","period.","SP","","LT","S","","","","","","","","Erneuerung Bstg in Pasching","","N","","19.01.2021","N","",90515,1077,"","","","","","","",""]
[null,81,"81-61100","Linz - Wien","< >","Abzw Ams 11","Ulmerfeld-Hausmening",2022,2022,17,20,"25.04.2022","21:35","21.05.2022","04:30","23x 6,9 h","period.","GES","","LT","","","Do","C","","B","","","Oberleitungsumbau, Bauphase 4-1, Nachtsperren jeweils Mo - Sa","","N","","22.06.2021","N","",90046,1431,"","","","","","","",""]
[null,81,"81-59220","Linz - Wien","< >","Neulengbach","Sbl Nl 1",2022,2022,17,44,"29.04.2022","00:00","31.10.2022","24:00","186 days + 1,0 h","cont.","SP","","LT","","","","","","","","","Gleiseindeckung EK km 39,714 Hst. Ollersbach\ntlw. Tagsperren, bei Bedarf  Doppelgleissperren in der Nacht oder Zugspausen","","N","","16.12.2020","N","",1025,90595,"","","","","","","",""]
[null,81,"81-60755","Linz - Wien","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,18,19,"02.05.2022","23:30","09.05.2022","05:30","7x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90859,91052,"","","","","","","",""]
[null,81,"81-61405","Salzburg - Wels","< >","Wankham","Attnang-Puchheim",2022,2022,18,19,"06.05.2022","00:00","09.05.2022","04:00","3 days + 4,0 h","cont.","SP","","LT","","","","","","","","","GN und WN W 1S, km 106,380 - 105,5","","N","","06.06.2021","N","",1921,1091,"","","","","","","",""]
[null,81,"81-60734","Linz - Wien","< >","St.Pölten-Fbf","Abzw Pb 1",2022,2022,19,19,"12.05.2022","22:00","13.05.2022","05:00","7,0 h","cont.","WF","","LT","","","","","","","","","Drainagespülen\nRobel, Niederflurwagen","","N","","09.06.2021","N","",90676,90625,"","","","","","","",""]
[null,81,"81-60735","Linz - Wien","< >","St.Pölten-Fbf","Prinzersdorf",2022,2022,19,19,"13.05.2022","22:00","15.05.2022","05:00","2x 7,0 h","period.","WF","","LT","","","","C","","B","","","Drainagespülen\nRobel, Niederflurwagen","","N","","09.06.2021","N","",90676,1037,"","","","","","","",""]
[null,81,"81-60736","Linz - Wien","< >","Abzww Knoten Rohr West","Üst Roh 3",2022,2022,20,20,"16.05.2022","22:00","18.05.2022","05:00","2x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","05.04.2021","N","",91055,90723,"","","","","","","",""]
[null,81,"81-60737","Linz - Wien","<","Knoten Rohr","Loosdorf",2022,2022,20,20,"18.05.2022","22:00","19.05.2022","05:00","7,0 h","cont.","WF","","LT","","","","","","","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",5683,1040,"","","","","","","",""]
[null,81,"81-59826","Wien - Parndorf","<","Himberg","Gramatneusiedl",2022,2022,21,24,"23.05.2022","05:00","13.06.2022","05:00","21 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","","05.04.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-59339","Salzburg - Wels","< >","Lambach","Stadl-Paura",2022,2022,22,23,"03.06.2022","21:00","08.06.2022","04:30","4 days + 7,5 h","cont.","SP","","LT","","","","","","","","","GN","","N","","19.05.2021","N","",1086,1881,"","","","","","","",""]
[null,81,"81-61603","Wels - Linz","<","Marchtrenk","",2022,2022,22,23,"03.06.2022","22:00","07.06.2022","05:00","3 days + 7,0 h","cont.","SP","","ST","","","","","","",3,"","WN 33P, 34P, 49P = Einbau Verbindungen Gl 1/3 und 2/4","","N","","21.06.2021","N","",1079,"",3,1,"","","","","",""]
[null,81,"81-59827","Wien - Parndorf","<","Himberg","Gramatneusiedl",2022,2022,22,23,"04.06.2022","22:00","07.06.2022","05:00","2 days + 7,0 h","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung W 56","","N","","05.04.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-59089","Wien - Sopron","< >","Münchendorf","Ebreichsdorf",2022,2022,24,25,"15.06.2022","22:00","20.06.2022","04:00","4 days + 6,0 h","cont.","GES","T","LT","","","","C","","B","","","ziehen Spundwände für Gleisverschwenkung","","Y","","19.04.2021","N","100%",3194,3195,"","","","","","","","Medium"]
[null,81,"81-59346","Linz - Wien","< >","Linz Vbf-Ost Einfahrgr","Linz Vbf-Ost Reihungsgr",2022,2022,25,26,"25.06.2022","12:00","27.06.2022","12:00","2 days","cont.","SP","","LT","","","","","","","","","WN W 118,119","","N","","18.05.2021","N","",5462,4685,"","","","","","","",""]
[null,81,"81-57568","Wien - Sopron",">","Wampersdorf","Ebenfurth",2022,2022,26,30,"01.07.2022","08:00","31.07.2022","05:00","29 days + 21,0 h","cont.","SP","","LT","","","","C","","B",40,"","Einbau Weiche 55 und 58 in Wampersdorf, versetzen Lufttrennung und Einfahrsignal","","Y","","15.01.2021","N","",3197,3199,0,5,"","","","","",""]
[null,81,"81-57571","Wien - Sopron","< >","Wampersdorf","",2022,2023,26,26,"01.07.2022","08:00","02.07.2023","01:00","365 days + 17,0 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","","01.06.2021","N","",3197,"",0,5,"","","","","",""]
[null,81,"81-61537","Wien - Sopron","< >","Wampersdorf","",2022,2023,26,36,"01.07.2022","08:00","04.09.2023","04:00","430 days","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","","06.06.2021","N","",3197,"",0,5,"","","","","",""]
[null,81,"81-58197","Wien - Sopron","< >","Wampersdorf","",2022,2022,26,26,"02.07.2022","22:10","03.07.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-57574","Wien - Sopron","< >","Wampersdorf","",2022,2022,26,26,"02.07.2022","23:10","03.07.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-58199","Wien - Sopron","< >","Wampersdorf","",2022,2022,26,27,"03.07.2022","22:10","04.07.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60106A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,26,27,"03.07.2022","22:10","04.07.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57575","Wien - Sopron","< >","Wampersdorf","",2022,2022,26,27,"03.07.2022","23:10","04.07.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-59673","Wels - Linz","< >","Marchtrenk","",2022,2022,27,33,"09.07.2022","08:00","16.08.2022","18:00","38 days + 10,0 h","cont.","SP","","ST","","","","C","","B","","","Phase 0 - Verschwenkung Gleis 4 - Errichtung prov. Bahnsteig 1","","Y","","07.06.2021","N","",1079,"","","","","","","","",""]
[null,81,"81-59865","Wels - Linz",">","Hörsching","Marchtrenk",2022,2022,32,32,"09.08.2022","21:00","10.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","","","","Phase 1 - IB Sig. Elemente  Gleis 2 zw ES A und AS R2","","N","","07.06.2021","N","",1077,1079,"","","","","","","",""]
[null,81,"81-59589","Wels - Linz","< >","Abzw Mak 1","Sbl Hoe 2",2022,2022,32,33,"10.08.2022","21:00","16.08.2022","16:00","5 days + 19,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Marchtrenk - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","","19.05.2021","N","",90533,90330,"","","","","","","",""]
[null,81,"81-59864","Wels - Linz","<","Marchtrenk","Hörsching",2022,2022,32,32,"10.08.2022","21:00","11.08.2022","05:00","8,0 h","cont.","SP","","LT","S","","","C","","B","","","Phase 2 - IB Sig. Elemente  Gleis  1 zw. AS H1 und ES B","","Y","","07.06.2021","N","",1079,1077,"","","","","","","",""]
[null,81,"81-59855","Wels - Linz",">","Marchtrenk","",2022,2022,32,32,"12.08.2022","21:00","14.08.2022","05:00","1 day + 8,0 h","cont.","SP","","ST","","","","C","","B",2,"","Phase 0 - IB Einbau W 49P - Ausbau W7","","Y","","07.06.2021","N","",1079,"",2,2,"","","","","",""]
[null,81,"81-59863","Wels - Linz",">","Marchtrenk","Wels Hbf",2022,2022,32,32,"12.08.2022","21:00","13.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","C","","B",10,"","Phase 5 - IB Sig. Elemente Gleis 2 zw. AS R und ES Y","","Y","","07.06.2021","N","",1079,1081,8,5,"","","","","",""]
[null,81,"81-60801","Wels - Linz","< >","Marchtrenk","",2022,2022,32,32,"13.08.2022","21:00","14.08.2022","05:00","8,0 h","cont.","SP","","ST","","","","C","","B",2,"","Phase 4 - IB Sig. Elemente Gleis 3 zw. ES X und AS H3\n(Stammgleis)","","Y","","07.06.2021","N","",1079,"",2,2,"","","","","",""]
[null,81,"81-59862","Wels - Linz","<","Wels Hbf","Marchtrenk",2022,2022,33,33,"15.08.2022","21:00","16.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","C","","B",10,"","Phase 6 - IB Sig. Elemente  Gleis 1 von ES Z bis AS R1","","Y","","07.06.2021","N","",1081,1079,8,5,"","","","","",""]
[null,81,"81-60783","Wien - Sopron","< >","Wampersdorf","",2022,2022,27,27,"09.07.2022","23:10","10.07.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Überfahrtsbrücke","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60784","Wien - Sopron","< >","Wampersdorf","",2022,2022,27,28,"10.07.2022","23:10","11.07.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-59227","Linz - Wien","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,28,29,"11.07.2022","04:00","18.07.2022","04:00","7 days","cont.","GES","T","LT","","","","C","","B",0,"","SpW1: Schotterbettreinigung W104,105,106,107,108","","N","","18.01.2021","N","",91010,1061,9,0,"","","","","",""]
[null,81,"81-60785","Wien - Sopron","< >","Wampersdorf","",2022,2022,28,28,"16.07.2022","23:10","17.07.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Überfahrtsbrücke","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60789","Wien - Sopron","< >","Wampersdorf","",2022,2022,28,29,"17.07.2022","23:10","18.07.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-59221","Linz - Wien","< >","Amstetten","Abzw Knoten St.Peter-Seitenstetten West",2022,2022,29,30,"18.07.2022","01:00","27.07.2022","04:00","9 days + 3,0 h","cont.","GES","T","LT","","","","C","","B",4,"","Üst Ams2: Weichentausch W401,402,403,404 inkl. Schottertausch\nAbzww Sp W1: Schotterbettreinigung W10, Abtrag W13,14\nWest200","","N","","22.06.2021","N","",1049,90784,11,0,"","","","","",""]
[null,81,"81-58200","Wien - Sopron","< >","Wampersdorf","",2022,2022,29,29,"23.07.2022","22:10","24.07.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60107A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,29,29,"23.07.2022","22:10","24.07.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57576","Wien - Sopron","< >","Wampersdorf","",2022,2022,29,29,"23.07.2022","23:10","24.07.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-57573","Wien - Sopron","< >","Münchendorf","Ebenfurth",2022,2022,30,30,"30.07.2022","22:00","31.07.2022","04:30","6,5 h","cont.","GES","T","LT","","","","C","","B","","","Inbetriebnahme ESTW Wampersdorf","","Y","","19.04.2021","N","",3194,3199,"","","","","","","",""]
[null,81,"81-58194","Wien - Sopron","< >","Wampersdorf","",2022,2022,30,30,"30.07.2022","23:10","31.07.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf, Inbetriebnahme ESTW Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-57570","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,30,35,"31.07.2022","05:00","04.09.2022","17:00","35 days + 12,0 h","cont.","SP","","LT","","","","C","","B",40,"","Einbau Weiche 56 und 57 in Wampersdorf, versetzen Lufttrennung und Einfahrsignal","","Y","","15.01.2021","N","",3197,3199,0,5,"","","","","",""]
[null,81,"81-61101","Linz - Wien","< >","Abzw Ams 11","Ulmerfeld-Hausmening",2022,2022,31,35,"01.08.2022","21:35","03.09.2022","04:30","29x 6,9 h","period.","GES","","LT","","","Do","C","","B","","","Oberleitungsumbau, Bauphase 5, Nachtsperren jeweils Mo - Sa","","N","","22.06.2021","N","",90046,1431,"","","","","","","",""]
[null,81,"81-61208","Linz - Wien","< >","Unter Purkersdorf","",2022,2022,31,34,"06.08.2022","01:30","22.08.2022","04:00","16 days + 2,5 h","cont.","SP","","ST","","","","C","","B","","","Migration Estw Up neu:\n06.08.22: Softwaretausch Hf/Hdd, EstwUpneu; BFZ\nes stehen nur die Gleise 2+4 im Bf. Up zur Verfügung\nSignalabhängigkeit aufgehoben!\nSchluss/Freimelder erforderlich!\nStr. 123 nicht befahrbar!","","N","","06.06.2021","N","",1012,"","","","","","","","",""]
[null,81,"81-60786","Wien - Sopron","< >","Wampersdorf","",2022,2022,31,31,"06.08.2022","23:10","07.08.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Querfelder","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60790","Wien - Sopron","< >","Wampersdorf","",2022,2022,31,32,"07.08.2022","23:10","08.08.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Querfelder","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60787","Wien - Sopron","< >","Wampersdorf","",2022,2022,32,32,"13.08.2022","23:10","14.08.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Querfelder","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60791","Wien - Sopron","< >","Wampersdorf","",2022,2022,32,33,"14.08.2022","23:10","15.08.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Abtrag Querfelder","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60055","Wels - Linz","< >","Abzw Mak 1","Wels Vbf-Einfgr",2022,2022,33,49,"16.08.2022","00:00","07.12.2022","24:00","114 days + 1,0 h","cont.","GES","T","LT","","","","","","","","","4gleisiger Ausbau Linz - Wels\nIm Bf Wels Vbf Rückbau der \nGleise  924, 104-504, 106-506, 508","","N","","16.12.2020","N","",90533,5839,"","","","","","","",""]
[null,81,"81-58198","Wien - Sopron","< >","Wampersdorf","",2022,2022,33,33,"20.08.2022","22:10","21.08.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60105A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,33,33,"20.08.2022","22:10","21.08.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57577","Wien - Sopron","< >","Wampersdorf","",2022,2022,33,33,"20.08.2022","23:10","21.08.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-58201","Wien - Sopron","< >","Wampersdorf","",2022,2022,33,34,"21.08.2022","22:10","22.08.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60108A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,33,34,"21.08.2022","22:10","22.08.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57580","Wien - Sopron","< >","Wampersdorf","",2022,2022,33,34,"21.08.2022","23:10","22.08.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-58202","Wien - Sopron","< >","Wampersdorf","",2022,2022,34,34,"27.08.2022","22:10","28.08.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60109A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,34,34,"27.08.2022","22:10","28.08.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57578","Wien - Sopron","< >","Wampersdorf","",2022,2022,34,34,"27.08.2022","23:10","28.08.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-58203","Wien - Sopron","< >","Wampersdorf","",2022,2022,34,35,"28.08.2022","22:10","29.08.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60110A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,34,35,"28.08.2022","22:10","29.08.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57581","Wien - Sopron","< >","Wampersdorf","",2022,2022,34,35,"28.08.2022","23:10","29.08.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60567","Salzburg - Wels",">","Schwanenstadt","Sbl Sas 1",2022,2022,35,35,"02.09.2022","20:00","03.09.2022","06:00","10,0 h","cont.","SP","","LT","","","","","","",5,"","Inbetriebnahme ESTW Gl 2-6","","N","","03.02.2021","N","",1090,90735,4,4,"","","","","",""]
[null,81,"81-60568","Salzburg - Wels","<","Schwanenstadt","Sbl Sas 1",2022,2022,35,35,"03.09.2022","20:00","04.09.2022","06:00","10,0 h","cont.","SP","","LT","","","","","","",5,"","Inbetriebnahme ESTW Gl 1,3","","N","","03.02.2021","N","",1090,90735,4,4,"","","","","",""]
[null,81,"81-58204","Wien - Sopron","< >","Wampersdorf","",2022,2022,35,35,"03.09.2022","22:10","04.09.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60111A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,35,35,"03.09.2022","22:10","04.09.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57579","Wien - Sopron","< >","Wampersdorf","",2022,2022,35,35,"03.09.2022","23:10","04.09.2022","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-58205","Wien - Sopron","< >","Wampersdorf","",2022,2022,35,36,"04.09.2022","22:10","05.09.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,"","","","","","","","",""]
[null,81,"81-60112A","Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,35,36,"04.09.2022","22:10","05.09.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","01.02.2021","Y","",3197,3199,"","","","","","","",""]
[null,81,"81-57582","Wien - Sopron","< >","Wampersdorf","",2022,2022,35,36,"04.09.2022","23:10","05.09.2022","04:30","5,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","","19.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-60723","Linz - Wien","< >","Üst Roh 3","Üst Roh 6",2022,2022,36,36,"05.09.2022","22:00","09.09.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen,TUF","","N","","29.04.2021","N","",90723,90724,"","","","","","","",""]
[null,81,"81-59829","Wien - Parndorf","<","Lanzendorf-Rannersdorf","Himberg",2022,2022,36,40,"09.09.2022","05:00","03.10.2022","05:00","24 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","","05.04.2021","Y","",2964,2966,2,5,"","","","","",""]
[null,81,"81-59828","Wien - Parndorf","<","Lanzendorf-Rannersdorf","Himberg",2022,2022,36,37,"09.09.2022","22:00","12.09.2022","05:00","2 days + 7,0 h","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung W 2 in Himberg","","N","","05.04.2021","Y","",2964,2966,2,5,"","","","","",""]
[null,81,"81-59354","Linz - Wien","< >","Abzww Zur","Wien Zvbf",2022,2022,37,38,"12.09.2022","07:00","25.09.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","21.04.2021","N","",90997,2962,"","","","","","","",""]
[null,81,"81-60731","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,37,37,"12.09.2022","22:00","16.09.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-61163","München - Rosenheim - Salzburg",">","Salzburg Hbf","",2022,2022,37,38,"16.09.2022","22:00","19.09.2022","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","","","",3,"","WN 308-309","","N","","25.06.2021","N","",1114,"",1,1,"","","","","",""]
[null,81,"81-60732","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,38,38,"19.09.2022","22:00","23.09.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-60645A","Regensburg - Wels","< >","Abzww Str 20602","Schärding",2022,2022,39,40,"26.09.2022","08:00","09.10.2022","18:00","13 days + 10,0 h","cont.","RES","T","LT","","","","C","","B","","","GA","","Y","","14.12.2020","N","",90740,1740,"","","","","","","",""]
[null,81,"81-60733","Linz - Wien","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,39,39,"26.09.2022","22:00","30.09.2022","05:00","4x 7,0 h","period.","WF","T","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","","01.06.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"81-59830","Wien - Parndorf",">","Lanzendorf-Rannersdorf","Himberg",2022,2022,40,43,"03.10.2022","05:00","24.10.2022","05:00","21 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","","05.04.2021","Y","",2964,2966,2,5,"","","","","",""]
[null,81,"81-59672","Linz - Wien",">","Sbl Spw 5","Sbl Spw 2",2022,2022,40,42,"03.10.2022","22:30","23.10.2022","05:00","15x 6,5 h","period.","GES","T","LT","","","","C","","B",6,"","Kanalspülen","","N","","19.01.2021","N","",90782,90776,4,0,"","","","","",""]
[null,81,"81-60756","Linz - Wien","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,40,42,"03.10.2022","23:30","21.10.2022","05:30","18x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","05.04.2021","N","",90859,91052,"","","","","","","",""]
[null,81,"81-60757","Linz - Wien","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,40,42,"03.10.2022","23:30","21.10.2022","05:30","18x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","10.03.2021","N","",90859,91052,"","","","","","","",""]
[null,81,"81-59329","Salzburg - Wels","< >","Gunskirchen","",2022,2022,41,42,"14.10.2022","08:00","17.10.2022","04:30","2 days + 20,5 h","cont.","SP","","ST","","","","C","","B","","","GN","","Y","","19.01.2021","N","",1085,"","","","","","","","",""]
[null,81,"81-59845","Wels - Linz","<","Marchtrenk","Sbl Hoe 2",2022,2022,41,42,"14.10.2022","22:00","17.10.2022","04:00","2 days + 6,0 h","cont.","SP","","LT","","","","","","","","","LM 22 - Einbau  Hib","","N","","19.01.2021","N","",1079,90330,"","","","","","","",""]
[null,81,"81-59846","Wels - Linz",">","Marchtrenk","Sbl Hoe 2",2022,2022,43,44,"30.10.2022","22:00","02.11.2022","04:00","2 days + 6,0 h","cont.","SP","","LT","","","","","","","","","LM 22 Einbau  Hib","","N","","19.01.2021","N","",1079,90330,"","","","","","","",""]
[null,81,"81-60170","Wien - Sopron",">","Oberlaa","",2022,2022,43,50,"27.10.2022","07:00","16.12.2022","19:00","37x 12,0 h","period.","SP","","ST","","","","","","",10,"","Errichtung Lärmschutzwand","","N","","01.03.2021","N","",1271,"",0,0,"","","","","",""]
[null,81,"81-60875","Wien - Sopron","<","Inzersdorf Ort-Ost","Oberlaa",2022,2022,43,44,"27.10.2022","08:00","02.11.2022","05:00","5 days + 22,0 h","cont.","SP","","LT","","","","","","",10,"","Gleisneulage","","N","","03.05.2021","N","",5362,1271,1,5,"","","","","",""]
[null,81,"81-60742","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,43,44,"28.10.2022","23:30","31.10.2022","05:30","3x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60743","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,44,44,"02.11.2022","23:30","05.11.2022","05:30","3x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","05.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-59485","Salzburg - Wels",">","Straßwalchen","Steindorf bei Straßwalchen",2022,2022,44,46,"04.11.2022","22:00","14.11.2022","05:00","9 days + 7,0 h","cont.","SP","","LT","S","","","C","","B",15,"","GN mit PLV","","N","","19.01.2021","N","",1104,1105,5,5,"","","","","",""]
[null,81,"81-58804","Wels - Linz","< >","Marchtrenk","",2022,2022,44,45,"04.11.2022","22:00","07.11.2022","04:00","2 days + 6,0 h","cont.","SP","","ST","","","","C","","B",15,"","LM 22 - Einbau Hib","","N","","18.05.2021","N","",1079,"",5,10,"","","","","",""]
[null,81,"81-60769","Linz - Wien","< >","Loosdorf","Sbl Los 4",2022,2022,44,44,"05.11.2022","22:00","06.11.2022","05:00","7,0 h","cont.","WF","T","LT","","","","C","","B","","","Sonderinspektion \nTUF","","N","","05.04.2021","N","",1040,90503,"","","","","","","",""]
[null,81,"81-59823","Linz - Wien","< >","Wien Zvbf","Abzww Zur",2022,2022,45,46,"07.11.2022","07:00","20.11.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","21.04.2021","N","",2962,90997,"","","","","","","",""]
[null,81,"81-60744","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,45,45,"07.11.2022","23:30","12.11.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60745","Linz - Wien","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,46,46,"14.11.2022","23:30","16.11.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60976","Salzburg - Wels","< >","Lambach","",2022,2022,46,47,"18.11.2022","23:00","21.11.2022","04:00","2 days + 5,0 h","cont.","SP","","ST","","","","C","","B","","","WN 1 und 4","","Y","","19.05.2021","N","",1086,"","","","","","","","",""]
[null,81,"81-60750","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,47,47,"21.11.2022","23:30","26.11.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60977","Salzburg - Wels","< >","Lambach","",2022,2022,47,48,"25.11.2022","23:00","28.11.2022","04:00","2 days + 5,0 h","cont.","SP","","ST","","","","C","","B","","","WN 3 + 5","","Y","","19.05.2021","N","",1086,"","","","","","","","",""]
[null,81,"81-59356","Linz - Wien","< >","Abzww Zur","Wien Zvbf",2022,2022,48,49,"28.11.2022","07:00","11.12.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","21.04.2021","N","",90997,2962,"","","","","","","",""]
[null,81,"81-60751","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,48,48,"28.11.2022","23:30","03.12.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","05.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60752","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,49,49,"05.12.2022","23:30","07.12.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-60753","Linz - Wien",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,50,50,"12.12.2022","23:30","14.12.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","","29.04.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"81-59849","Wels - Linz","< >","Marchtrenk","",2023,2023,6,7,"10.02.2023","22:00","13.02.2023","04:00","2 days + 6,0 h","cont.","GES","T","ST","","","","C","","B",15,"","LM 21 - Einbau Hib\nLM 22 - Ausbau Hib","","N","","05.02.2021","N","",1079,"",5,10,"","","","","",""]
[null,81,"81-60518","Wels - Linz",">","Üst Lz 2","Linz Hbf",2023,2023,7,8,"17.02.2023","22:00","22.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 01 km 191,248\nschlagen dukdiler Phäle","","N","","28.01.2021","N","",90515,1073,"","","","","","","",""]
[null,81,"81-60519","Wels - Linz",">","Marchtrenk","Sbl Hoe 2",2023,2023,7,8,"17.02.2023","22:00","22.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 19, LM 21, \nAusbau Hib LM 22\nAnheben Oberleitung\nEinbau Weiche 5","","N","","28.01.2021","N","",1079,90330,"","","","","","","",""]
[null,81,"81-60520","Wels - Linz","<","Marchtrenk","Sbl Hoe 2",2023,2023,8,9,"22.02.2023","22:00","27.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 19, LM 21, \nAusbau Hib LM 22\nAnheben Oberleitung","","N","","28.01.2021","N","",1079,90330,"","","","","","","",""]
[null,81,"81-60952","Salzburg - Wels",">","Üst Fm 2","Ederbauer",2023,2023,10,10,"07.03.2023","22:45","08.03.2023","05:00","6,2 h","cont.","SP","","LT","","","","","","",5,"","Errichtung OL-Maste","","N","","29.04.2021","N","",90191,1102,2,2,"","","","","",""]
[null,81,"81-60953","Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,10,10,"08.03.2023","22:45","09.03.2023","05:00","6,2 h","cont.","SP","","LT","","","","","","",7,"","Errichtung OL-Maste","","N","","29.04.2021","N","",1104,90191,3,3,"","","","","",""]
[null,81,"81-61248","Linz - Wien",">","Sbl Spw 5","Sbl Spw 2",2023,2023,12,14,"20.03.2023","22:30","05.04.2023","05:00","16x 6,5 h","period.","GES","T","LT","","","","C","","B",6,"","Kanalspülen","","N","","05.05.2021","N","",90782,90776,4,0,"","","","","",""]
[null,81,"81-60954","Salzburg - Wels",">","Üst Fm 2","Ederbauer",2023,2023,12,12,"21.03.2023","22:45","23.03.2023","05:00","2x 6,2 h","period.","SP","","LT","","","","","","",5,"","Errichtung Joche","","N","","20.04.2021","N","",90191,1102,2,2,"","","","","",""]
[null,81,"81-60955","Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,12,12,"24.03.2023","22:45","26.03.2023","05:00","2x 6,2 h","period.","SP","","LT","","","","","","",7,"","Errichtung Joche","","N","","20.04.2021","N","",1104,90191,3,3,"","","","","",""]
[null,81,"81-61377A","Wien - Sopron","< >","Wien Meidling","Wiener Neustadt Hbf",2023,2023,13,15,"01.04.2023","00:00","11.04.2023","04:30","10 days + 4,5 h","cont.","RES","","LT","","","","C","","","","","Weichnenneulage in Md","","N","","06.06.2021","N","",3107,3126,"","","","","","","",""]
[null,81,"81-60524","Wels - Linz","< >","Marchtrenk","Wels Hbf",2023,2025,13,17,"01.04.2023","08:00","22.04.2025","20:00","753 days","cont.","BFUM","","LT","S","","","","","","","","Langsamfahren Gleis 1 und 2 mit 100 km/h - Errichtung des neuen Überwerfungsbauwerks und der Autobahnbrücken von km 207,600 bis 208,400","","N","","27.01.2021","N","",1079,1081,"","","","","","","",""]
[null,81,"81-60958","Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,13,13,"01.04.2023","22:45","02.04.2023","06:00","7,2 h","cont.","SP","","LT","","","","","","",15,"","OL-Querungen aufziehen","","N","","20.04.2021","N","",1104,90191,3,3,"","","","","",""]
[null,81,"81-60956","Salzburg - Wels",">","Üst Fm 2","Ederbauer",2023,2023,13,14,"02.04.2023","22:45","03.04.2023","05:00","6,2 h","cont.","SP","","LT","","","","","","",15,"","OL-Querungen aufziehen","","N","","20.04.2021","N","",90191,1102,2,2,"","","","","",""]
[null,81,"81-61071","Wien - Parndorf","< >","Kledering","",2023,2023,14,15,"08.04.2023","09:00","11.04.2023","05:00","2 days + 20,0 h","cont.","SP","T","ST","","","","","","","","","Weichenneulage DKW 453/454 und DKW 455/456","","N","","06.06.2021","N","",2963,"","","","","","","","",""]
[null,81,"81-60959","Salzburg - Wels",">","Üst Fm 2","Ederbauer",2023,2023,14,14,"08.04.2023","22:45","09.04.2023","07:00","8,2 h","cont.","SP","","LT","","","","","","",5,"","IB neues Schaltgerüst","","N","","20.04.2021","N","",90191,1102,2,2,"","","","","",""]
[null,81,"81-60788","Wien - Sopron","< >","Wampersdorf","",2023,2023,14,14,"08.04.2023","23:10","09.04.2023","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Einbau Überfahrtsbrücke","","Y","","01.06.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-59831","Wien - Parndorf",">","Himberg","",2023,2023,14,14,"09.04.2023","00:00","09.04.2023","06:00","6,0 h","cont.","GES","","ST","","","","C","","B","","","Imbetriebnahme ESTW neu","","Y","","06.06.2021","Y","",2966,"","","","","","","","",""]
[null,81,"81-60960","Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,14,15,"09.04.2023","22:45","10.04.2023","07:00","8,2 h","cont.","SP","","LT","","","","","","",5,"","IB neues Schaltgerüst","","N","","20.04.2021","N","",1104,90191,3,3,"","","","","",""]
[null,81,"81-60792","Wien - Sopron","< >","Wampersdorf","",2023,2023,14,15,"09.04.2023","23:10","10.04.2023","06:00","6,8 h","cont.","GES","T","ST","","","","C","","B","","","Einbau Überfahrtsbrücke","","Y","","05.04.2021","N","",3197,"","","","","","","","",""]
[null,81,"81-61245","Regensburg - Wels","<","Üst Wa 1","Üst Had 2",2023,2023,15,16,"14.04.2023","20:00","17.04.2023","05:00","2 days + 9,0 h","cont.","SP","","LT","","","","","","",3,"","Sanierung UF / Bstg","","N","","05.05.2021","N","",90925,90272,2,2,"","","","","",""]
[null,81,"81-61059","Linz - Wien","< >","Abzww Zur","Wien Zvbf",2023,2023,16,17,"17.04.2023","07:00","30.04.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","06.06.2021","N","",90997,2962,"","","","","","","",""]
[null,81,"81-60724","Linz - Wien","< >","Abzww Knoten Rohr West","Pöchlarn",2023,2023,18,21,"01.05.2023","00:00","22.05.2023","04:00","21 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Weichentausch Knoten Rohr 3 und 6\nWest 200\nErneuerung Löschwasserleitung Melker Tunnel Gl 3; Sperren zum Tunnelspülen werden mitgenutzt.","","N","","14.05.2021","N","",91055,1042,"","","","","","","",""]
[null,81,"81-61246","Regensburg - Wels",">","Üst Wa 1","Üst Had 2",2023,2023,20,21,"19.05.2023","20:00","22.05.2023","05:00","2 days + 9,0 h","cont.","SP","","LT","","","","","","",3,"","Sanierung UF / Bstg","","N","","05.05.2021","N","",90925,90272,2,2,"","","","","",""]
[null,81,"81-60528","Wels - Linz","<","Marchtrenk","Sbl Hoe 2",2023,2023,21,21,"22.05.2023","22:00","26.05.2023","22:00","4 days","cont.","SP","","LT","","","","","","","","","Ausbau Hib LM 19, LM 21,","","N","","05.02.2021","N","",1079,90330,"","","","","","","",""]
[null,81,"81-60529","Wels - Linz",">","Hörsching","Marchtrenk",2023,2023,21,22,"26.05.2023","22:00","30.05.2023","04:00","3 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Ausbau Hib LM 19, LM 21,","","N","","05.02.2021","N","",1077,1079,"","","","","","","",""]
[null,81,"81-59850","Wels - Linz","< >","Marchtrenk","",2023,2023,22,23,"01.06.2023","22:00","05.06.2023","04:00","3 days + 6,0 h","cont.","GES","T","ST","","","","","","","","","Hib Ausbau LM 21","","N","","05.05.2021","N","",1079,"","","","","","","","",""]
[null,81,"81-60810","Salzburg - Wels","<","Ederbauer","Üst Fm 2",2023,2023,23,24,"07.06.2023","23:00","12.06.2023","05:00","4 days + 6,0 h","cont.","SP","","LT","","","","C","","B",5,"","Ed - Tausch Untergrund W 53 und 54","","Y","","23.04.2021","N","",1102,90191,3,3,"","","","","",""]
[null,81,"81-61061","Linz - Wien","< >","Abzww Zur","Wien Zvbf",2023,2023,24,25,"12.06.2023","07:00","25.06.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","06.06.2021","N","",90997,2962,"","","","","","","",""]
[null,81,"81-60550","Salzburg - Wels",">","Seekirchen am Wallersee","Hallwang-Elixhausen",2023,2023,25,44,"23.06.2023","08:00","30.10.2023","08:00","129 days + 1,0 h","cont.","BFUM","","LT","S","","","","","","","","Schutz La - Sicherung Spundung","","N","","18.02.2021","N","",1110,1112,"","","","","","","",""]
[null,81,"81-61102","Linz - Wien","< >","Abzw Ams 11","Waidhofen a.d.Ybbs",2023,2023,26,36,"30.06.2023","23:00","04.09.2023","04:30","65 days + 5,5 h","cont.","GES","T","LT","","","","C","","B","","","Bahnhof Ul: Montage Schaltgerüst\nAbzw. Ams 11 - Ul und Bf. Ul:, Aufziehen der Spitzenleitungen,  Aufziehen und Ausfertigen der Oberleitung\nStrecke UI bis Hk:  Gleisneulage km 12,925 - km 15,032 im Zeitraum 07.08 bis 25.08.2023","","N","","06.06.2021","N","",90046,1437,"","","","","","","",""]
[null,81,"81-56750","Wien - Parndorf","< >","Götzendorf","Abzww Str 11815",2023,2025,26,27,"01.07.2023","00:00","30.06.2025","24:00","731 days","cont.","BFUM","","LT","","","","","","","","","Bf-Umbau","","N","","16.12.2020","Y","",2969,91011,"","","","","","","",""]
[null,81,"81-58206","Wien - Sopron","< >","Münchendorf","Wampersdorf",2023,2023,26,36,"01.07.2023","22:00","04.09.2023","04:30","64 days + 6,5 h","cont.","GES","T","LT","","","","C","","B","","","Anbindung Bf Ebreichdorf neu an Münchendorf und Wampersdorf","","Y","","07.01.2021","N","",3194,3197,"","","","","","","",""]
[null,81,"81-61520","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,26,26,"01.07.2023","23:10","02.07.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61538","Wien - Sopron",">","Wampersdorf","",2023,2023,26,47,"02.07.2023","08:00","24.11.2023","16:00","145 days + 9,0 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","","06.06.2021","N","",3197,"",0,5,"","","","","",""]
[null,81,"81-61540","Wien - Sopron","< >","Wampersdorf","",2023,2024,26,26,"02.07.2023","08:00","29.06.2024","04:30","362 days + 20,5 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","","06.06.2021","N","",3197,"",0,5,"","","","","",""]
[null,81,"81-61522","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,26,27,"02.07.2023","23:10","03.07.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61018","Parndorf - Hegyeshalom",">","Zurndorf","Nickelsdorf",2023,2023,27,30,"04.07.2023","08:00","30.07.2023","16:00","26 days + 8,0 h","cont.","SP","","LT","","","","C","","B",20,"","Gleisneulage mit Untergrundverstärkung","","Y","","28.05.2021","N","25%",2978,2979,2,0,"","","","","","Minor"]
[null,81,"81-60916","Linz - Wien","<","Tullnerbach-Pressbaum","",2023,2023,27,28,"09.07.2023","04:00","12.07.2023","04:00","3 days","cont.","SP","","ST","","","","C","","B","","","Bauphase 3.1:\nSchwenk von Nord auf Südseiten! Umbau Südseite. Umbau Weichenkopf OST Ri Up! Umbau Fahrleitung; Umbau Signalstandorte!\nDoppelgleissperren in den Nächten!","","N","","03.05.2021","N","",1015,"","","","","","","","",""]
[null,81,"81-60544","Salzburg - Wels",">","Seekirchen am Wallersee","Sbl See 1",2023,2023,29,29,"21.07.2023","08:00","23.07.2023","03:00","1 day + 19,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nEinbau Hib Gl 2","","Y","","01.02.2021","N","",1110,90742,2,5,"","","","","",""]
[null,81,"81-61523","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,29,29,"22.07.2023","23:10","23.07.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-60545","Salzburg - Wels","<","Hallwang-Elixhausen","Seekirchen am Wallersee",2023,2023,29,30,"23.07.2023","03:00","25.07.2023","05:00","2 days + 2,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nEinbau Hib Gl 2","","Y","","28.01.2021","N","",1112,1110,2,5,"","","","","",""]
[null,81,"81-61524","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,29,30,"23.07.2023","23:10","24.07.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-60986","Salzburg - Wels",">","Gunskirchen","",2023,2023,30,31,"29.07.2023","08:00","31.07.2023","05:00","1 day + 21,0 h","cont.","SP","","ST","","","","","","",3,"","Gleisneulage","","N","","29.04.2021","N","",1085,"",2,2,"","","","","",""]
[null,81,"81-61525","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,30,30,"29.07.2023","23:10","30.07.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61526","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,30,31,"30.07.2023","23:10","31.07.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-60985","Salzburg - Wels","<","Gunskirchen","",2023,2023,31,32,"05.08.2023","08:00","07.08.2023","05:00","1 day + 21,0 h","cont.","SP","","ST","","","","","","",3,"","Gleisneulage","","N","","03.05.2021","N","",1085,"",2,2,"","","","","",""]
[null,81,"81-60919","Linz - Wien",">","Abzw Pb 1","Prinzersdorf",2023,2023,32,33,"12.08.2023","01:00","18.08.2023","18:00","6 days + 17,0 h","cont.","SP","","LT","","","","C","","B","","","Weichenneulage Weichen 3,6,9 (Gl 204)","","Y","","03.05.2021","N","",90625,1037,"","","","","","","",""]
[null,81,"81-60797","Linz - Wien","<","Abzw Pb 1","Prinzersdorf",2023,2023,33,35,"18.08.2023","18:00","28.08.2023","04:00","9 days + 10,0 h","cont.","SP","","LT","","","","C","","B","","","Weichen- und Gleisneulage Weichen 2,4,5,7 (Gleis 203)","","Y","","28.04.2021","N","",90625,1037,"","","","","","","",""]
[null,81,"81-61527","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,33,33,"19.08.2023","23:10","20.08.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61528","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,33,34,"20.08.2023","23:10","21.08.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61244","Linz - Wien","< >","St.Valentin-Ennskanalbrücke","St.Valentin",2023,2023,34,35,"26.08.2023","08:00","28.08.2023","08:00","2 days","cont.","SP","","LT","","","","C","","B",7,"","Ausbau W 126/127","","Y","","05.05.2021","N","",5762,1061,3,2,"","","","","",""]
[null,81,"81-61529","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,34,34,"26.08.2023","23:10","27.08.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61530","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,34,35,"27.08.2023","23:10","28.08.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61048","Linz - Wien",">","St.Valentin","Linz Kleinmünchen",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","LT","","","","","","","","","Schotterbetttausch SAZ (Ennsbrücke)","","N","","29.04.2021","N","",1061,90442,"","","","","","","",""]
[null,81,"81-61049","Linz - Wien","<","Linz Kleinmünchen","St.Valentin",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","LT","","","","","","","","","Schotterbetttausch SAZ (Ennsbrücke)","","N","","29.04.2021","N","",90442,1061,"","","","","","","",""]
[null,81,"81-61531","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,35,35,"02.09.2023","23:10","03.09.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61532","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,35,36,"03.09.2023","23:10","04.09.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-59833","Wien - Parndorf",">","Himberg","",2023,2023,36,41,"09.09.2023","07:00","13.10.2023","22:00","34 days + 15,0 h","cont.","SP","","ST","","","","C","","B",30,"","Unterbausanierung","","N","","06.06.2021","Y","",2966,"",2,5,"","","","","",""]
[null,81,"81-61070","Wien - Parndorf","< >","Wien Zvbf","Kledering",2023,2023,36,37,"09.09.2023","10:00","15.09.2023","17:00","6 days + 7,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","06.06.2021","N","",2962,2963,"","","","","","","",""]
[null,81,"81-61063","Linz - Wien","< >","Abzww Zur","Wien Zvbf",2023,2023,39,40,"25.09.2023","07:00","08.10.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","","06.06.2021","N","",90997,2962,"","","","","","","",""]
[null,81,"81-61249","Linz - Wien",">","Sbl Spw 5","Sbl Spw 2",2023,2023,41,43,"09.10.2023","22:30","24.10.2023","05:00","15x 6,5 h","period.","GES","T","LT","","","","C","","B",6,"","Kanalspülen","","N","","05.05.2021","N","",90782,90776,4,0,"","","","","",""]
[null,81,"81-59834","Wien - Parndorf",">","Himberg","Gramatneusiedl",2023,2023,41,43,"13.10.2023","22:00","25.10.2023","22:00","12 days","cont.","SP","","LT","","","","C","","B",30,"","Anschwenkungen","","N","","06.06.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-61533","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,41,41,"14.10.2023","23:10","15.10.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61534","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,41,42,"15.10.2023","23:10","16.10.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61116","Regensburg - Wels",">","Riedau","Andorf",2023,2023,42,43,"16.10.2023","07:00","27.10.2023","17:00","11 days + 10,0 h","cont.","SP","","LT","S","","","C","","B",5,"","GN mit Unterbauverbesserung","","Y","","05.05.2021","N","",1733,1736,2,2,"","","","","",""]
[null,81,"81-61535","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,42,42,"21.10.2023","23:10","22.10.2023","05:45","6,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-61536","Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,42,43,"22.10.2023","23:10","23.10.2023","04:45","5,6 h","cont.","GES","T","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","","06.06.2021","N","",3197,3198,"","","","","","","",""]
[null,81,"81-60522","Wels - Linz",">","Marchtrenk","",2023,2023,43,44,"25.10.2023","08:00","30.10.2023","20:00","5 days + 13,0 h","cont.","SP","","ST","S","","","C","","B",15,"","Anschwenkung Gleis 2 / 4Neu","","Y","","27.01.2021","N","",1079,"",10,5,"","","","","",""]
[null,81,"81-59835","Wien - Parndorf",">","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,43,44,"25.10.2023","22:00","01.11.2023","01:00","6 days + 4,0 h","cont.","SP","","LT","","","","C","","B",30,"","Anschwenkungen Sgl 2 an Gleis 4-neu","","N","","06.06.2021","Y","",2964,2968,2,5,"","","","","",""]
[null,81,"81-60523","Wels - Linz","< >","Marchtrenk","",2023,2023,44,44,"30.10.2023","08:00","02.11.2023","20:00","3 days + 12,0 h","cont.","SP","","ST","S","","","C","","B","","","Einbindung neues Gleis 1 (7alt) von W57ALT an Traunergleis W3ALT\nInbetriebnahme Bahnsteiginsel NEU","","Y","","27.01.2021","N","",1079,"","","","","","","","",""]
[null,81,"81-59832","Wien - Parndorf",">","Himberg","",2023,2023,44,44,"01.11.2023","00:00","01.11.2023","06:00","6,0 h","cont.","GES","","ST","","","","C","","B","","","Imbetriebnahme ESTW neu","","Y","","06.06.2021","Y","",2966,"","","","","","","","",""]
[null,81,"81-59836","Wien - Parndorf","<","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,44,44,"01.11.2023","06:00","03.11.2023","05:00","1 day + 23,0 h","cont.","SP","","LT","","","","C","","B",30,"","Einbau W 1-neu und anbinden an Bgl 2","","N","","06.06.2021","Y","",2964,2968,2,5,"","","","","",""]
[null,81,"81-59837","Wien - Parndorf","<","Himberg","Gramatneusiedl",2023,2023,44,45,"01.11.2023","06:00","06.11.2023","05:00","4 days + 23,0 h","cont.","SP","","LT","","","","C","","B",30,"","Anschwenken Bgl 2 an Sgl 1 Ri Gn","","N","","06.06.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-59838","Wien - Parndorf","<","Himberg","Gramatneusiedl",2023,2023,45,46,"06.11.2023","05:00","18.11.2023","17:30","12 days + 12,5 h","cont.","SP","","LT","","","","C","","B",30,"","Hauptverkabelung","","N","","06.06.2021","Y","",2966,2968,2,5,"","","","","",""]
[null,81,"81-60548","Salzburg - Wels",">","Seekirchen am Wallersee","Sbl See 1",2023,2023,46,46,"17.11.2023","08:00","19.11.2023","03:00","1 day + 19,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nAusbau Hib Gl 2","","Y","","28.01.2021","N","",1110,90742,2,5,"","","","","",""]
[null,81,"81-60549","Salzburg - Wels","<","Hallwang-Elixhausen","Seekirchen am Wallersee",2023,2023,46,47,"19.11.2023","03:00","20.11.2023","05:00","1 day + 2,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nAusbau Hib Gl 2","","Y","","28.01.2021","N","",1112,1110,2,5,"","","","","",""]
[null,81,"81-60515","Salzburg - Wels",">","Neumarkt am Wallersee","Seekirchen am Wallersee",2023,2023,48,49,"01.12.2023","21:00","04.12.2023","05:00","2 days + 8,0 h","cont.","SP","","LT","","","","C","","B",5,"","Tausch Schotterbett in der ÜSt Steindorf b.Stw 3","","Y","","20.04.2021","N","","",1110,3,3,"","","","","",""]
[null,81,"81-60543","Salzburg - Wels","<","Seekirchen am Wallersee","Neumarkt am Wallersee",2023,2023,49,50,"08.12.2023","21:00","11.12.2023","05:00","2 days + 8,0 h","cont.","SP","","LT","","","","C","","B",5,"","Tausch Schotterbett in der ÜSt Steindorf b.Stw 3","","Y","","12.05.2021","N","",1110,"",3,3,"","","","","",""]
[null,81,"81-60551","Salzburg - Wels",">","Seekirchen am Wallersee","Sbl See 1",2024,2024,13,21,"29.03.2024","08:00","20.05.2024","08:00","51 days + 23,0 h","cont.","BFUM","","LT","S","","","","","","","","Schutz La - Sicherung Spundung","","N","","22.02.2021","Y","",1110,90742,"","","","","","","",""]
[null,81,"81-60674","Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,13,14,"30.03.2024","08:00","01.04.2024","08:00","1 day + 23,0 h","cont.","SP","","LT","S","","","","","","","","Verschwenkung Gl 1+2","","N","","22.02.2021","N","",1110,90742,"","","","","","","",""]
[null,81,"81-60779A","Wels - Linz","< >","Linz Hbf","Salzburg Hbf",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","","05.04.2021","N","",1073,1114,"","","","","","","",""]
[null,81,"81-60711A","Linz - Wien","< >","Prinzersdorf","Wien Meidling",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","","03.03.2021","N","",1037,3107,"","","","","","","",""]
[null,81,"81-60780A","Linz - Wien","< >","St.Pölten Hbf","Linz Hbf",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","","12.03.2021","N","",1032,1073,"","","","","","","",""]
[null,81,"81-61882A","Wels - Linz","< >","Linz Hbf","Wels Hbf",2024,2024,14,17,"06.04.2024","06:00","28.04.2024","16:00","22 days + 10,0 h","cont.","RES","T","LT","","","","C","","B","","","Reinvestitionsmaßnahmen in verschiedenen Abschnitten","","Y","","03.05.2021","N","",1073,1081,"","","","","","","",""]
[null,81,"81-62188A","Linz - Wien","< >","Wien Meidling","St.Pölten Hbf",2024,2024,14,17,"06.04.2024","06:00","28.04.2024","16:00","22 days + 10,0 h","cont.","RES","T","LT","","","","C","","B","","","Reinvestitionsmaßnahmen in verschiedenen Abschnitten","","Y","","03.05.2021","N","",3107,1032,"","","","","","","",""]
[null,81,"81-60673","Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,20,21,"18.05.2024","08:00","20.05.2024","08:00","2 days","cont.","SP","","LT","S","","","","","","","","Rückschwenkung Gl 1+2","","N","","01.03.2021","N","",1110,90742,"","","","","","","",""]
[null,81,"81-60552","Salzburg - Wels","<","Hallwang-Elixhausen","Seekirchen am Wallersee",2024,2024,21,28,"21.05.2024","08:00","08.07.2024","08:00","48 days","cont.","SP","","LT","S","","","C","","B",5,"","(Neue ÜST See1)\nHerstellung Bstg 1","","Y","","01.03.2021","N","",1112,1110,2,2,"","","","","",""]
[null,81,"81-59839","Wien - Parndorf","< >","Himberg","",2024,2024,21,23,"24.05.2024","07:00","03.06.2024","05:00","9 days + 22,0 h","cont.","SP","","ST","","","","C","","","","","Umbau AB","","N","","07.01.2021","N","",2966,"","","","","","","","",""]
[null,81,"81-62193A","Linz - Wien","< >","Wien Hbf-Südosttangente (in Wbf)","Gramatneusiedl",2024,2024,26,35,"29.06.2024","09:00","01.09.2024","16:00","64 days + 7,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","","03.05.2021","N","80%",3092,2968,"","","","","","","","Major"]
[null,81,"81-62191A","Wien - Sopron","< >","Wien Meidling","Wiener Neustadt Hbf",2024,2024,26,35,"29.06.2024","09:00","01.09.2024","16:00","64 days + 7,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","","03.05.2021","N","80%",3107,3126,"","","","","","","","Major"]
[null,81,"81-60032","Wels - Traun - Linz","<","Linz Hbf Westbrücke","Linz Wegscheid",2021,2021,29,30,"23.07.2021","07:00","01.08.2021","17:00","9 days + 10,0 h","cont.","SP","","LT","","","","","","",5,"","Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;","","N","","18.02.2021","N","",5914,1600,1,1,"","","","","",""]
[null,81,"81-60034","Wels - Traun - Linz","<","Traun","Linz Wegscheid",2021,2021,31,31,"02.08.2021","07:00","08.08.2021","17:00","6 days + 10,0 h","cont.","SP","","LT","","","","","","",5,"","Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;","","N","","16.12.2020","N","",1602,1600,1,1,"","","","","",""]
[null,81,"81-60033","Wels - Traun - Linz",">","Linz Wegscheid","Traun",2021,2021,32,32,"09.08.2021","07:00","15.08.2021","17:00","6 days + 10,0 h","cont.","SP","","LT","","","","","","",5,"","Herstellung - Fundamente Schaltstation ES-EVS; Querung EVS und ES Teil2; Trogtrasse und Tausch defekter Tröge Bestandstrasse;","","N","","16.12.2020","N","",1600,1602,1,1,"","","","","",""]
[null,81,"81-60509A","Wels - Traun - Linz","< >","Linz Hbf","Selzthal",2021,2021,38,38,"21.09.2021","22:45","22.09.2021","05:30","6,8 h","cont.","RES","","LT","","","","C","","B","","","Gesamtsperre Strecke 10103 - Üst Aj 5","","Y","","01.02.2021","N","",1073,1457,"","","","","","","",""]
[null,81,"81-57913","Wels - Traun - Linz","< >","Marchtrenk","Rutzing",2021,2021,42,43,"23.10.2021","07:00","29.10.2021","17:00","6 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleissanierung - WN W 1F, W 1S","","N","","16.12.2020","N","",1079,5692,"","","","","","","",""]
[null,81,"81-61446","Wels - Traun - Linz","< >","Marchtrenk","Rutzing",2022,2022,32,32,"11.08.2022","21:00","12.08.2022","05:00","8,0 h","cont.","GES","T","LT","","","","C","","B","","","Phase 3 - IB ESTW Marchtrenk ID 59860","","Y","","07.06.2021","N","",1079,5692,"","","","","","","",""]
[null,81,"81-59536","Wels - Traun - Linz",">","Linz Oed","Linz Wegscheid",2022,2022,46,46,"14.11.2022","07:00","16.11.2022","24:00","2 days + 17,0 h","cont.","SP","","LT","","","","","","","","","Tausch Oberleitungskette","","N","","17.05.2021","N","",1591,1600,"","","","","","","",""]
[null,81,"81-59518","Wels - Traun - Linz","<","Linz Wegscheid","St.Martin bei Traun",2022,2022,46,48,"14.11.2022","08:00","28.11.2022","01:00","13 days + 17,0 h","cont.","SP","","LT","","","","","","",5,"","Migration Linz Wegscheid BFZ Linz","","N","","17.05.2021","N","",1600,1601,1,2,"","","","","",""]
[null,81,"81-59590","Wels - Traun - Linz","<","Linz Wegscheid","",2022,2022,47,48,"26.11.2022","22:00","28.11.2022","05:00","1 day + 7,0 h","cont.","SP","","ST","S","","","","","","","","Migration Linz Wegscheid BFZ Linz - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","","17.05.2021","N","",1600,"","","","","","","","",""]
[null,81,"81-59537","Wels - Traun - Linz","<","Linz Oed","Linz Wegscheid",2022,2022,48,50,"28.11.2022","07:00","14.12.2022","24:00","16 days + 17,0 h","cont.","SP","","LT","","","","","","","","","Tausch Oberleitungskette","","N","","16.12.2020","N","",1591,1600,"","","","","","","",""]
[null,81,"81-61258","Wels - Traun - Linz","< >","Marchtrenk","Abzww Traun West",2023,2023,22,23,"01.06.2023","22:00","05.06.2023","04:00","3 days + 6,0 h","cont.","GES","T","LT","","","","","","","","","Sanierung Pumpe Silvia-Tunnel\nLS-Verkabelung und Fundamente herstellen","","N","","05.05.2021","N","",1079,90841,"","","","","","","",""]
[null,81,"81-61885A","Wels - Traun - Linz","< >","Linz Hbf","Selzthal",2024,2024,14,17,"06.04.2024","06:00","28.04.2024","16:00","22 days + 10,0 h","cont.","RES","T","LT","","","","C","","B","","","Reinvestitionsmaßnahmen in verschiedenen Abschnitten","","Y","","03.05.2021","N","",1073,1457,"","","","","","","",""]
[null,81,"81-60052","Wels - Traun - Linz","< >","Abzww Traun West","Marchtrenk",2024,2024,29,37,"16.07.2024","08:00","09.09.2024","18:00","55 days + 10,0 h","cont.","GES","T","LT","","","","C","","B","","","4gleisiger Ausbau Linz - Wels - Umbau Marchtrenk","","Y","","16.12.2020","N","",90841,1079,"","","","","","","",""]
[null,54,"V-026523/19","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,44,49,"2022-11-01",null,"2022-12-09T23:59:59.997",null,"39 days","continuous","Miscellaneous","","LT","","","","","","","","","2 jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026522/19","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,44,49,"2022-10-31",null,"2022-12-07T23:59:59.997",null,"38 days","continuous","Miscellaneous","","LT","","","","","","","","","1 jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026521/19","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,44,44,"2022-10-31",null,"2022-10-31T23:59:59.997",null,"1 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012145/21","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,44,44,"2022-11-01",null,"2022-11-02T23:59:59.997",null,"2 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009849/21","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,36,37,"2022-09-07",null,"2022-09-16T23:59:59.997",null,"10 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026508/19","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,36,36,"2022-09-06",null,"2022-09-06T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026507/19","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,36,36,"2022-09-05",null,"2022-09-05T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024995/19","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,7,9,"2022-02-17",null,"2022-03-04T23:59:59.997",null,"16 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024992/19","Praha - Choceň","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,5,7,"2022-02-01",null,"2022-02-16T23:59:59.997",null,"16 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024987/19","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,20,29,"2022-05-17",null,"2022-07-21T23:59:59.997",null,"66 days","continuous","Miscellaneous","","ST","","","","","","B","","","1.,3. + TV. \nzáhlaví a zhlaví 1. TK směr Choceň\nzáhlaví a zhlaví 1. TK směr Bezpráví.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012267/20","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,44,49,"2022-11-03",null,"2022-12-07T23:59:59.997",null,"35 days","continuous","Miscellaneous","","LT","","","","","","","","","1 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025081/19","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Chotěbuz",2022,2022,22,39,"2022-06-01",null,"2022-09-30T23:59:59.997",null,"122 days","continuous","Bridge","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025073/19","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Fulnek",2022,2022,40,44,"2022-10-04",null,"2022-11-02T23:59:59.997",null,"30 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025065/19","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Fulnek",2022,2022,40,43,"2022-10-04",null,"2022-10-24T23:59:59.997",null,"21 days","continuous","Switch","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025051/19","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín","",2022,2022,44,45,"2022-11-01",null,"2022-11-11T23:59:59.997",null,"11 days","continuous","Track & Rail","","ST","","","","","","B","","","96,96a bez TV, výh.: 60. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024987/19","Choceň - Hranice na Moravě","<>","Choceň","Brandýs nad Orlicí",2022,2022,20,29,"2022-05-17",null,"2022-07-21T23:59:59.997",null,"66 days","continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024986/19","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2022,2022,5,29,"2022-02-01",null,"2022-07-21T23:59:59.997",null,"171 days","continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024986/19","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,5,29,"2022-02-01",null,"2022-07-21T23:59:59.997",null,"171 days","continuous","Miscellaneous","","ST","","","","","","B","","","záhlaví TK 1. směr Brandýs nad Orlicí + TV","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024986/19","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,5,29,"2022-02-01",null,"2022-07-21T23:59:59.997",null,"171 days","continuous","Miscellaneous","","ST","","","","","","B","","","1. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024984/19","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,29,50,"2022-07-22",null,"2022-12-18T23:59:59.997",null,"150 days","continuous","Miscellaneous","","ST","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025051/19","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín","Bohumín st.hr.",2022,2022,44,45,"2022-11-01",null,"2022-11-11T23:59:59.997",null,"11 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025047/19","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Bohumín",2022,2022,25,28,"2022-06-24",null,"2022-07-15T23:59:59.997",null,"22 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025043/19","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2022,2022,19,24,"2022-05-15",null,"2022-06-15T23:59:59.997",null,"32 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024984/19","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2022,2022,29,50,"2022-07-22",null,"2022-12-18T23:59:59.997",null,"150 days","continuous","Miscellaneous","","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024983/19","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Choceň",2022,2022,29,32,"2022-07-22",null,"2022-08-10T23:59:59.997",null,"20 days","continuous","Miscellaneous","","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024983/19","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,29,32,"2022-07-22",null,"2022-08-10T23:59:59.997",null,"20 days","continuous","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví záhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024700/19","Hranice na Moravě - Ostrava","<>","Studénka","",2022,2022,26,28,"2022-07-01",null,"2022-07-15T23:59:59.997",null,"15 days","continuous","Others","","ST","","","","","","B","","","12 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024700/19","Hranice na Moravě - Ostrava","<>","Studénka","Bílovec",2022,2022,26,28,"2022-07-01",null,"2022-07-15T23:59:59.997",null,"15 days","continuous","Others","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025040/19","Ostrava - Detmarovice - Cesky Tesin","<>","Petrovice u Karviné","Dětmarovice",2022,2022,52,9,"2022-01-01",null,"2022-02-28T23:59:59.997",null,"59 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024687/19","Regensburg - Plzen","<>","Domažlice","Poběžovice",2022,2022,40,42,"2022-10-03",null,"2022-10-17T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024686/19","Ostrava - Český Těšín","<>","Ostrava-Bartovice","Havířov",2022,2022,10,13,"2022-03-09",null,"2022-03-28T23:59:59.997",null,"20 days","continuous","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024684/19","Regensburg - Plzen","<>","Vejprnice","Nýřany",2022,2022,33,35,"2022-08-21",null,"2022-09-03T23:59:59.997",null,"14 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024683/19","Regensburg - Plzen","<>","Nýřany","Stod",2022,2022,31,33,"2022-08-01",null,"2022-08-20T23:59:59.997",null,"20 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024681/19","Regensburg - Plzen","<>","Holýšov","Staňkov",2022,2022,31,33,"2022-08-01",null,"2022-08-20T23:59:59.997",null,"20 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012019/21","Plzen - Praha","<>","Tunel odb.","Praha-Radotín",2022,2022,23,26,"2022-06-10",null,"2022-06-30T23:59:59.997",null,"21 x 10 hours","periodical","Miscellaneous","","LT","","","","","","","","","4. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024679/19","Nürnberg - Plzen","<>","Pňovany","Bezdružice",2022,2022,16,20,"2022-04-21",null,"2022-05-18T23:59:59.997",null,"28 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024676/19","Regensburg - Plzen","<>","Nýřany","Heřmanova Huť",2022,2022,36,40,"2022-09-05",null,"2022-10-04T23:59:59.997",null,"30 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011179/21","Plzen - Praha","<>","Ejpovice","Chrást u Plzně",2022,2022,14,14,"2022-04-04",null,"2022-04-08T23:59:59.997",null,"5 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024667/19","Nürnberg - Plzen","<>","Tachov","Planá u Mariánských Lázní",2022,2022,34,34,"2022-08-22",null,"2022-08-26T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024661/19","Nürnberg - Plzen","<>","Svojšín","Bor",2022,2022,39,42,"2022-09-29",null,"2022-10-17T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024660/19","Regensburg - Plzen","<>","Staňkov","Poběžovice",2022,2022,20,24,"2022-05-17",null,"2022-06-13T23:59:59.997",null,"28 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007639/21","Nürnberg - Plzen","<>","Pavlovice","Brod nad Tichou",2022,2022,42,43,"2022-10-21",null,"2022-10-27T23:59:59.997",null,"35 x 10 hours","periodical","Bridge","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007639/21","Nürnberg - Plzen","<>","Pavlovice","",2022,2022,42,43,"2022-10-21",null,"2022-10-27T23:59:59.997",null,"21 x 10 hours","periodical","Bridge","","ST","","","","","","B","","","celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007639/21","Nürnberg - Plzen","<>","Ošelín","",2022,2022,42,43,"2022-10-21",null,"2022-10-27T23:59:59.997",null,"7 x 10 hours","periodical","Bridge","","ST","","","","","","B","","","1 bez TV, celá jen TV. \nzáhlaví a zhlaví svojšínské a pavlovické.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024646/19","Regensburg - Plzen","<>","Kdyně","Domažlice",2022,2022,16,22,"2022-04-22",null,"2022-05-31T23:59:59.997",null,"40 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024645/19","Regensburg - Plzen","<>","Kdyně","Domažlice",2022,2022,16,22,"2022-04-22",null,"2022-05-31T23:59:59.997",null,"40 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024585/19","Choceň - Hranice na Moravě","<>","Prosenice","Dluhonice výhybna",2022,2022,33,38,"2022-08-18",null,"2022-09-19T23:59:59.997",null,"33 days","continuous","Signal","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024585/19","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,33,38,"2022-08-18",null,"2022-09-19T23:59:59.997",null,"33 days","continuous","Signal","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024585/19","Choceň - Hranice na Moravě","<>","Přerov","Dluhonice výhybna",2022,2022,33,38,"2022-08-18",null,"2022-09-19T23:59:59.997",null,"33 days","continuous","Signal","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023683/19","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2022,2022,37,48,"2022-09-13",null,"2022-11-28T23:59:59.997",null,"77 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011987/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,10,10,"2022-03-07T18:00:00",null,"2022-03-11T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011991/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,11,12,"2022-03-15T18:00:00",null,"2022-03-21T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011997/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,14,15,"2022-04-04T18:00:00",null,"2022-04-11T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012004/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,16,16,"2022-04-19T18:00:00",null,"2022-04-22T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012007/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,19,20,"2022-05-09T18:00:00",null,"2022-05-20T06:00:00",null,"10 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009606/21","Plzen - Praha","<>","Odb Barrandov","Praha-Radotín",2022,2022,9,10,"2022-03-03T18:00:00",null,"2022-03-11T06:00:00",null,"8 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009614/21","Plzen - Praha","<>","Odb Barrandov","Praha-Radotín",2022,2022,11,13,"2022-03-15T18:00:00",null,"2022-03-28T06:00:00",null,"12 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009626/21","Plzen - Praha","<>","Odb Barrandov","Praha-Radotín",2022,2022,13,15,"2022-04-03T18:00:00",null,"2022-04-11T06:00:00",null,"8 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009634/21","Plzen - Praha","<>","Odb Barrandov","Praha-Radotín",2022,2022,15,16,"2022-04-13T18:00:00",null,"2022-04-22T06:00:00",null,"9 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009643/21","Plzen - Praha","<>","Odb Barrandov","Praha-Radotín",2022,2022,17,21,"2022-04-28T18:00:00",null,"2022-05-23T06:00:00",null,"23 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009045/21","Praha - Choceň","<>","Tatce","Pečky",2022,2022,12,14,"2022-03-27T18:00:00",null,"2022-04-04T06:00:00",null,"8 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011651/18","Hranice na Moravě - Žilina","<>","Hovězí","Vsetín bývalá Odb Bečva",2022,2022,26,39,"2022-06-28",null,"2022-09-30T23:59:59.997",null,"95 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006411/19","Hranice na Moravě - Žilina","<>","Vsetín","",2022,2022,27,29,"2022-07-05T18:00:00",null,"2022-07-19T06:00:00",null,"14 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","1a + TV. \nzáhlaví a zhlaví 1a / 1 býv odb. Bečva.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011520/18","Hranice na Moravě - Žilina","<>","Vsetín","",2022,2022,29,33,"2022-07-19T18:00:00",null,"2022-08-16T06:00:00",null,"28 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","1a + TV. \nzáhlaví a zhlaví 1a / 1 býv odb. Bečva.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006411/19","Hranice na Moravě - Žilina","<>","Vsetín","Valašská Polanka",2022,2022,27,29,"2022-07-05T18:00:00",null,"2022-07-19T06:00:00",null,"14 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011520/18","Hranice na Moravě - Žilina","<>","Vsetín","Valašská Polanka",2022,2022,29,33,"2022-07-19T18:00:00",null,"2022-08-16T06:00:00",null,"28 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007070/21","Praha - Choceň","<>","Přelouč nákladní nádraží","Heřmanův Městec",2022,2022,13,26,"2022-04-01",null,"2022-06-30T23:59:59.997",null,"91 x 10 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025023/19","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,39,41,"2022-09-29",null,"2022-10-14T23:59:59.997",null,"16 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023737/18","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Nový Jičín město",2022,2022,38,40,"2022-09-19",null,"2022-10-07T23:59:59.997",null,"19 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009043/21","Praha - Choceň","<>","Poříčany","Tatce",2022,2022,9,9,"2022-03-02T18:00:00",null,"2022-03-03T06:00:00",null,"1 x 12 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008980/21","Praha - Choceň","<>","Cerhenice","Velim",2022,2022,10,11,"2022-03-08T18:00:00",null,"2022-03-14T06:00:00",null,"6 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008986/21","Praha - Choceň","<>","Cerhenice","Velim",2022,2022,12,14,"2022-03-24T18:00:00",null,"2022-04-06T06:00:00",null,"11 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012568/21","Praha - Choceň","<>","Cerhenice","Velim",2022,2022,14,14,"2022-04-06T18:00:00",null,"2022-04-07T06:00:00",null,"1 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006775/21","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Fulnek",2022,2022,39,42,"2022-10-01",null,"2022-10-17T23:59:59.997",null,"17 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006741/21","Plzen - Praha","<>","Hořovice","Kařízek",2022,2022,26,26,"2022-07-01T18:00:00",null,"2022-07-03T06:00:00",null,"2 x 12 hours","periodical","Signal","","LT","","","","","","B","","","zab. zař. TZZ 1. a 2. TK.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006741/21","Plzen - Praha","<>","Hořovice","Kařízek",2022,2022,26,26,"2022-07-01T18:00:00",null,"2022-07-03T06:00:00",null,"2 x 12 hours","periodical","Signal","","LT","","","","","","B","","","sděl. zař. informační a přenosové systémy.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006738/21","Plzen - Praha","<>","Hořovice","",2022,2022,25,26,"2022-06-25T18:00:00",null,"2022-06-28T06:00:00",null,"3 x 12 hours","periodical","Signal","","ST","","","","","","B","","","zab. zař. SZZ - zhlaví směr Kařízek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006740/21","Plzen - Praha","<>","Hořovice","",2022,2022,26,26,"2022-06-30T18:00:00",null,"2022-07-01T06:00:00",null,"1 x 12 hours","periodical","Signal","","ST","","","","","","B","","","zab. zař. SZZ - zhlaví směr Kařízek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006738/21","Plzen - Praha","<>","Hořovice","",2022,2022,25,26,"2022-06-25T18:00:00",null,"2022-06-28T06:00:00",null,"3 x 12 hours","periodical","Signal","","ST","","","","","","B","","","sděl. zař. informační a přenosové systémy.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006740/21","Plzen - Praha","<>","Hořovice","",2022,2022,26,26,"2022-06-30T18:00:00",null,"2022-07-01T06:00:00",null,"1 x 12 hours","periodical","Signal","","ST","","","","","","B","","","sděl. zař. informační a přenosové systémy.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006643/21","Praha - Choceň","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,41,42,"2022-10-15",null,"2022-10-20T23:59:59.997",null,"6 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 2. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006642/21","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,39,41,"2022-09-29",null,"2022-10-14T23:59:59.997",null,"16 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 1. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006641/21","Praha - Choceň","<>","Uhersko","Moravany",2022,2022,19,19,"2022-05-13",null,"2022-05-14T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 2. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006640/21","Praha - Choceň","<>","Moravany","Uhersko",2022,2022,19,19,"2022-05-11",null,"2022-05-12T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 1. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017939/20","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,9,9,"2022-03-01",null,"2022-03-05T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2/2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006600/21","Praha - Choceň","<>","Moravany","Kostěnice",2022,2022,19,19,"2022-05-09",null,"2022-05-10T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 2. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006593/21","Praha - Choceň","<>","Kostěnice","Moravany",2022,2022,18,18,"2022-05-07",null,"2022-05-08T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 1. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006547/21","Praha - Choceň","<>","Choceň","Vysoké Mýto",2022,2022,35,37,"2022-09-01",null,"2022-09-14T23:59:59.997",null,"14 days","continuous","Signal","","LT","","","","","","","","","zab. zař. \nPZZ v km 2,595 (P5156)\nPZZ v km 4,776 (P5158)\nPZZ v km 6,897 (P5161).","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006516/21","Plzen - Praha","<>","Zdice","Hořovice",2022,2022,39,40,"2022-10-02T18:00:00",null,"2022-10-03T06:00:00",null,"2 x 22 hours","periodical","Track & Rail","","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006516/21","Plzen - Praha","<>","Hořovice","",2022,2022,39,40,"2022-10-02T18:00:00",null,"2022-10-03T06:00:00",null,"1 x 22 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví směr Zdice 2. traťové koleje, od návěstidla 2L po návěstidlo S2 a S4.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006516/21","Plzen - Praha","<>","Hořovice","",2022,2022,39,40,"2022-10-02T18:00:00",null,"2022-10-03T06:00:00",null,"1 x 22 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví směr Kařízek 2. traťové koleje, od návěstidla 2S po návěstidlo Lc2 a Lc4.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006516/21","Plzen - Praha","<>","Hořovice","",2022,2022,39,40,"2022-10-02T18:00:00",null,"2022-10-03T06:00:00",null,"1 x 22 hours","periodical","Track & Rail","","ST","","","","","","B","","","2.,4. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006414/19","Hranice na Moravě - Žilina","<>","Vsetín","",2022,2022,10,15,"2022-03-08T18:00:00",null,"2022-04-13T06:00:00",null,"36 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","2a + TV. \nzáhlaví a zhlaví 2 / 2a býv odb.Bečva.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006450/19","Hranice na Moravě - Žilina","<>","Vsetín","",2022,2022,15,16,"2022-04-13T18:00:00",null,"2022-04-19T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","2a + TV. \nzáhlaví a zhlaví 2 / 2a býv odb.Bečva.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006414/19","Hranice na Moravě - Žilina","<>","Valašská Polanka","Vsetín",2022,2022,10,15,"2022-03-08T18:00:00",null,"2022-04-13T06:00:00",null,"36 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006450/19","Hranice na Moravě - Žilina","<>","Valašská Polanka","Vsetín",2022,2022,15,16,"2022-04-13T18:00:00",null,"2022-04-19T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009005/21","Praha - Choceň","<>","Pečky","",2022,2022,11,11,"2022-03-19T18:00:00",null,"2022-03-20T06:00:00",null,"1 x 12 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1 bez TV, lichá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009006/21","Praha - Choceň","<>","Pečky","",2022,2022,16,16,"2022-04-18T18:00:00",null,"2022-04-19T06:00:00",null,"1 x 12 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1 bez TV, lichá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008056/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Malešice",2022,2022,24,24,"2022-06-15",null,"2022-06-17T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008039/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Eden",2022,2022,24,25,"2022-06-18",null,"2022-06-21T23:59:59.997",null,"4 days","continuous","Catenary","","LT","","","","","","","","","202 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008038/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2022,2022,30,30,"2022-07-25",null,"2022-07-26T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ, PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008037/21","Plzen - Praha","<>","Praha-Eden","Praha-Zahradní Město",2022,2022,25,25,"2022-06-21",null,"2022-06-25T23:59:59.997",null,"5 days","continuous","Catenary","","LT","","","","","","","","","201 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011511/18","Hranice na Moravě - Žilina","<>","Valašská Polanka","Vsetín",2022,2022,26,50,"2022-06-28",null,"2022-12-12T23:59:59.997",null,"168 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011510/18","Hranice na Moravě - Žilina","<>","Vsetín","Valašská Polanka",2022,2022,9,26,"2022-03-01",null,"2022-06-27T23:59:59.997",null,"119 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007986/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Hostivař",2022,2022,18,18,"2022-05-08",null,"2022-05-08T23:59:59.997",null,"1 x 18 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007985/21","Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,18,18,"2022-05-07T18:00:00",null,"2022-05-08T06:00:00",null,"1 x 7 hours","periodical","Track & Rail","T","LT","","","","","","","","","1,2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007984/21","Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,18,18,"2022-05-06",null,"2022-05-06T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023603/19","Hranice na Moravě - Ostrava","<>","Polom","Suchdol nad Odrou",2022,2022,26,37,"2022-06-28",null,"2022-09-12T23:59:59.997",null,"77 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011192/21","Plzen - Praha","<>","Rokycany","",2022,2022,29,30,"2022-07-21",null,"2022-07-27T23:59:59.997",null,"7 days","continuous","Track & Rail","","ST","","","","","","B","","","11a bez TV. \nzhlaví směr Mirošov od Se9 ke hrotu výh.č.2, od hrotu výh.č.4 ke hrotu výh.č.8.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007954/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,13,48,"2022-04-01",null,"2022-11-30T23:59:59.997",null,"244 days","continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ, PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007057/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,36,44,"2022-09-09",null,"2022-11-02T23:59:59.997",null,"110 x 10 hours","periodical","Catenary","","LT","","","","","","B","","","1,2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007057/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","",2022,2022,36,44,"2022-09-09",null,"2022-11-02T23:59:59.997",null,"55 x 10 hours","periodical","Catenary","","ST","","","","","","B","","","celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007057/20","Choceň - Hranice na Moravě","<>","Prosenice","Dluhonice výhybna",2022,2022,36,44,"2022-09-09",null,"2022-11-02T23:59:59.997",null,"55 x 10 hours","periodical","Catenary","","LT","","","","","","B","","","1S,2S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011046/19","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,39,43,"2022-10-01",null,"2022-10-30T23:59:59.997",null,"30 days","continuous","Track & Rail","","ST","","","D","","","","","","211.,212.,213.,214. bez TV, 201.-222. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004753/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,11,11,"2022-03-14",null,"2022-03-18T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2/2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011011/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,42,42,"2022-10-17",null,"2022-10-19T23:59:59.997",null,"3 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2/2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010906/21","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Nový Jičín město",2022,2022,23,24,"2022-06-08",null,"2022-06-16T23:59:59.997",null,"9 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 0,345 P6777 a v km 1,363 P6780.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010902/21","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Odry",2022,2022,41,42,"2022-10-10",null,"2022-10-19T23:59:59.997",null,"10 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 2,367 P6696 a v km 5,089 P6699.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007933/21","Ostrava - Detmarovice - Cesky Tesin","<>","Petrovice u Karviné","Dětmarovice",2022,2022,44,45,"2022-11-04",null,"2022-11-07T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007932/21","Ostrava - Detmarovice - Cesky Tesin","<>","Petrovice u Karviné","Dětmarovice",2022,2022,44,44,"2022-11-02",null,"2022-11-03T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007925/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2022,2022,42,42,"2022-10-21",null,"2022-10-23T23:59:59.997",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017524/20","Ostrava - Český Těšín","<>","Ostrava střed","Ostrava-Kunčice",2022,2022,13,14,"2022-04-02",null,"2022-04-08T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017483/20","Ostrava - Český Těšín","<>","Ostrava-Kunčice","Ostrava-Bartovice",2022,2022,19,20,"2022-05-12",null,"2022-05-20T23:59:59.997",null,"9 days","continuous","Switch","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017482/20","Ostrava - Český Těšín","<>","Ostrava-Bartovice","Ostrava-Kunčice",2022,2022,18,19,"2022-05-02",null,"2022-05-11T23:59:59.997",null,"10 days","continuous","Switch","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017472/20","Hranice na Moravě - Ostrava","<>","Studénka","Suchdol nad Odrou",2022,2022,15,15,"2022-04-13",null,"2022-04-17T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017471/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Studénka",2022,2022,14,15,"2022-04-08",null,"2022-04-12T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017469/20","Hranice na Moravě - Ostrava","<>","Polom","Hranice na Moravě",2022,2022,14,14,"2022-04-06",null,"2022-04-07T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017466/20","Hranice na Moravě - Ostrava","<>","Hranice na Moravě","Polom",2022,2022,14,14,"2022-04-04",null,"2022-04-05T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017276/20","Hranice na Moravě - Žilina","<>","Valašské Meziříčí","Branky na Moravě",2022,2022,35,37,"2022-09-01",null,"2022-09-15T23:59:59.997",null,"15 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007924/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2022,2022,41,42,"2022-10-14",null,"2022-10-20T23:59:59.997",null,"7 days","continuous","Track & Rail","T","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007924/21","Ostrava - Detmarovice - Cesky Tesin","<>","Závada odb.","Koukolná odb.",2022,2022,41,42,"2022-10-14",null,"2022-10-20T23:59:59.997",null,"7 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007922/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Bohumín",2022,2022,45,46,"2022-11-13",null,"2022-11-14T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007921/21","Ostrava - Detmarovice - Cesky Tesin","<>","Závada odb.","Dětmarovice",2022,2022,45,45,"2022-11-11",null,"2022-11-12T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007920/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Závada odb.",2022,2022,41,41,"2022-10-12",null,"2022-10-13T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010900/21","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Odry",2022,2022,42,43,"2022-10-20",null,"2022-10-27T23:59:59.997",null,"8 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 7,244  P6703.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007918/21","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín","Dětmarovice",2022,2022,41,41,"2022-10-10",null,"2022-10-11T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008869/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Hostivař",2022,2022,22,22,"2022-06-05",null,"2022-06-05T23:59:59.997",null,"1 x 12 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008865/21","Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,22,22,"2022-06-02T18:00:00",null,"2022-06-04T06:00:00",null,"2 x 6 hours","periodical","Catenary","T","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010709/21","Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2022,2022,14,15,"2022-04-04",null,"2022-04-13T23:59:59.997",null,"10 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010698/21","Nürnberg - Plzen","<>","Cheb","Lipová u Chebu",2022,2022,12,13,"2022-03-25",null,"2022-04-03T23:59:59.997",null,"10 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008798/21","Plzen - Praha","<>","Praha-Malešice","Praha-Zahradní Město",2022,2022,24,24,"2022-06-13",null,"2022-06-15T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008792/21","Plzen - Praha","<>","Praha-Eden","Praha-Zahradní Město",2022,2022,22,23,"2022-06-02",null,"2022-06-12T23:59:59.997",null,"11 days","continuous","Catenary","","LT","","","","","","","","","101 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008789/21","Plzen - Praha","<>","Praha-Vršovice","Praha-Krč",2022,2022,20,20,"2022-05-18",null,"2022-05-18T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008771/21","Plzen - Praha","<>","Praha-Eden","Praha-Zahradní Město",2022,2022,19,19,"2022-05-10",null,"2022-05-13T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","201 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008765/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Eden",2022,2022,19,19,"2022-05-11",null,"2022-05-14T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","202 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008741/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Eden",2022,2022,21,22,"2022-05-25",null,"2022-06-01T23:59:59.997",null,"8 days","continuous","Catenary","","LT","","","","","","","","","102 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008739/21","Plzen - Praha","<>","Praha-Malešice","Praha-Zahradní Město",2022,2022,21,21,"2022-05-23",null,"2022-05-24T23:59:59.997",null,"2 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008735/21","Plzen - Praha","<>","Praha-Eden","Praha-Zahradní Město",2022,2022,20,20,"2022-05-21",null,"2022-05-22T23:59:59.997",null,"2 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","101 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008734/21","Plzen - Praha","<>","Praha-Eden","Praha-Zahradní Město",2022,2022,18,18,"2022-05-05",null,"2022-05-07T23:59:59.997",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","101 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008730/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Hostivař",2022,2022,21,21,"2022-05-25T18:00:00",null,"2022-05-27T06:00:00",null,"2 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008729/21","Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,21,21,"2022-05-28",null,"2022-05-28T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006260/21","Hranice na Moravě - Ostrava","<>","Ostrava-Svinov","Opava východ",2022,2022,9,9,"2022-03-01",null,"2022-03-04T23:59:59.997",null,"4 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006234/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,14,14,"2022-04-05",null,"2022-04-06T23:59:59.997",null,"2 x 8 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008728/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Hostivař",2022,2022,21,21,"2022-05-28",null,"2022-05-28T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008718/21","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,9,10,"2022-03-06T18:00:00",null,"2022-03-08T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010697/19","Plzen - Praha","<>","Praha-Radotín","Odb Barrandov",2022,2022,52,23,"2022-01-01",null,"2022-06-10T23:59:59.997",null,"161 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010697/19","Plzen - Praha","<>","Praha-Radotín","Tunel odb.",2022,2022,52,23,"2022-01-01",null,"2022-06-10T23:59:59.997",null,"161 days","continuous","Miscellaneous","","LT","","","","","","","","","3. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007707/21","Nürnberg - Plzen","<>","Mariánské Lázně","Lipová u Chebu",2022,2022,12,15,"2022-03-25",null,"2022-04-13T23:59:59.997",null,"20 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007667/21","Nürnberg - Plzen","<>","Mariánské Lázně","",2022,2022,12,15,"2022-03-25",null,"2022-04-13T23:59:59.997",null,"21 x 10 hours","periodical","Track & Rail","","ST","","","","","","B","","","celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010676/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2022,2022,42,43,"2022-10-21",null,"2022-10-30T23:59:59.997",null,"10 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017183/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Přerov",2022,2022,46,47,"2022-11-20",null,"2022-11-25T23:59:59.997",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016716/20","Choceň - Hranice na Moravě","<>","Litovel","Červenka",2022,2022,39,42,"2022-10-01",null,"2022-10-21T23:59:59.997",null,"21 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ,PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008712/21","Praha - Choceň","<>","Pardubice hlavní nádraží","",2022,2022,8,9,"2022-02-27T18:00:00",null,"2022-03-03T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008711/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Eden",2022,2022,18,18,"2022-05-06",null,"2022-05-08T23:59:59.997",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","102 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008707/21","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,5,5,"2022-02-02T18:00:00",null,"2022-02-06T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008707/21","Praha - Choceň","<>","Pardubice hlavní nádraží","",2022,2022,5,5,"2022-02-02T18:00:00",null,"2022-02-06T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010666/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2022,2022,8,8,"2022-02-21",null,"2022-02-25T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010671/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2022,2022,9,9,"2022-02-28",null,"2022-03-04T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010659/21","Nürnberg - Plzen","<>","Cheb","",2022,2022,22,25,"2022-06-01",null,"2022-06-20T23:59:59.997",null,"20 days","continuous","Miscellaneous","","ST","","","","","","B","","","3.,5.,7b jen TV, výh.: 62,63,66,69,71,73. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008706/21","Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,21,22,"2022-05-28",null,"2022-05-30T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008705/21","Plzen - Praha","<>","Praha-Malešice","Praha-Zahradní Město",2022,2022,20,20,"2022-05-19",null,"2022-05-19T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","T","LT","","","","","","","","","1,2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008699/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Bolehošť",2022,2022,46,46,"2022-11-16",null,"2022-11-18T23:59:59.997",null,"3 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008702/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Bolehošť",2022,2022,48,48,"2022-11-30",null,"2022-12-02T23:59:59.997",null,"3 x 9 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008665/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Bolehošť",2022,2022,42,45,"2022-10-18",null,"2022-11-09T23:59:59.997",null,"24 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008665/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,42,42,"2022-10-18",null,"2022-10-18T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 3 směr Bolehošť.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008698/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,45,45,"2022-11-08",null,"2022-11-08T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 3 směr Bolehošť.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016424/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2022,2022,26,26,"2022-06-30T18:00:00",null,"2022-07-01T06:00:00",null,"2 x 6 hours","periodical","Signal","T","LT","","","","","","","","","zab. zař. TZZ, PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016425/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Choceň",2022,2022,29,29,"2022-07-21T18:00:00",null,"2022-07-22T06:00:00",null,"2 x 6 hours","periodical","Signal","T","LT","","","","","","","","","zab. zař. TZZ, PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016408/21","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Havířov",2022,2022,42,45,"2022-10-23T18:00:00",null,"2022-11-12T06:00:00",null,"16 x 6 hours","periodical","Bridge","T","LT","","","D","","","","","","2,1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016396/21","Ostrava - Český Těšín","<>","Havířov","",2022,2022,42,43,"2022-10-23T18:00:00",null,"2022-10-29T06:00:00",null,"6 x 6 hours","periodical","Bridge","","ST","","","D","","","","","","1,2 bez TV, celá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016393/21","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Havířov",2022,2022,42,42,"2022-10-20",null,"2022-10-22T23:59:59.997",null,"3 x 6 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010558/21","Hranice na Moravě - Ostrava","<>","Ostrava-Svinov","Opava východ",2022,2022,23,24,"2022-06-06",null,"2022-06-15T23:59:59.997",null,"10 days","continuous","Signal","","LT","","","","","","","","","zab. zař. vypnutí počítačů náprav po úsecích.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008665/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,42,42,"2022-10-18",null,"2022-10-18T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","19,23,25 bez TV, 3,17,21 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008698/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,45,45,"2022-11-08",null,"2022-11-08T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","19,23,25 bez TV, 3,17,21 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008665/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,42,42,"2022-10-18",null,"2022-10-18T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Bolehošť","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008698/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,45,45,"2022-11-08",null,"2022-11-08T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Bolehošť","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008694/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,47,48,"2022-11-27",null,"2022-11-30T23:59:59.997",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Třebechovice p. O.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008495/21","Praha - Hr. Králové - Choceň","<>","Borohrádek","Týniště nad Orlicí",2022,2022,30,30,"2022-07-28",null,"2022-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008532/21","Praha - Hr. Králové - Choceň","<>","Borohrádek","Týniště nad Orlicí",2022,2022,30,30,"2022-07-31",null,"2022-07-31T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008694/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2022,2022,47,48,"2022-11-27",null,"2022-11-30T23:59:59.997",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016389/21","Ostrava - Český Těšín","<>","Havířov","Albrechtice u Českého Těšína",2022,2022,41,42,"2022-10-16",null,"2022-10-19T23:59:59.997",null,"4 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016134/20","Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","Návsí (Nawsie)",2022,2022,16,16,"2022-04-19",null,"2022-04-22T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016133/20","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Mosty u Jabl. (Mosty koło Jabł.)",2022,2022,13,15,"2022-04-01",null,"2022-04-13T23:59:59.997",null,"13 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007854/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2022,2022,4,4,"2022-01-25",null,"2022-01-30T23:59:59.997",null,"6 x 8 hours","periodical","Catenary","T","LT","","","D","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007860/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2022,2022,7,8,"2022-02-14",null,"2022-02-21T23:59:59.997",null,"8 x 8 hours","periodical","Catenary","T","LT","","","D","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008651/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,43,44,"2022-10-26",null,"2022-11-06T23:59:59.997",null,"12 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Třebechovice p. O.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008439/21","Praha - Hr. Králové - Choceň","<>","Borohrádek","Týniště nad Orlicí",2022,2022,26,27,"2022-07-01",null,"2022-07-10T23:59:59.997",null,"10 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008651/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2022,2022,43,44,"2022-10-26",null,"2022-11-06T23:59:59.997",null,"12 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022235/19","Choceň - Hranice na Moravě","<>","Olomouc-Nová Ulice","Olomouc hlavní nádraží",2022,2022,25,26,"2022-06-23",null,"2022-06-30T23:59:59.997",null,"8 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012316/20","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,42,44,"2022-10-21T18:00:00",null,"2022-10-31T06:00:00",null,"10 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022174/19","Hranice na Moravě - Žilina","<>","Hustopeče nad Bečvou","Hranice na Moravě město",2022,2022,19,22,"2022-05-12",null,"2022-05-31T23:59:59.997",null,"20 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022171/19","Hranice na Moravě - Žilina","<>","Hranice na Moravě město","Hustopeče nad Bečvou",2022,2022,22,25,"2022-06-01",null,"2022-06-20T23:59:59.997",null,"20 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022163/19","Hranice na Moravě - Žilina","<>","Valašská Polanka","Vsetín bývalá Odb Bečva",2022,2022,26,27,"2022-06-28",null,"2022-07-04T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022162/19","Hranice na Moravě - Žilina","<>","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,25,26,"2022-06-20",null,"2022-06-27T23:59:59.997",null,"8 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022160/19","Hranice na Moravě - Žilina","<>","Jablůnka","Valašské Meziříčí",2022,2022,7,8,"2022-02-16",null,"2022-02-23T23:59:59.997",null,"8 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022159/19","Hranice na Moravě - Žilina","<>","Valašské Meziříčí","Jablůnka",2022,2022,8,9,"2022-02-24",null,"2022-02-28T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022157/19","Hranice na Moravě - Žilina","<>","Hovězí","Vsetín bývalá Odb Bečva",2022,2022,37,39,"2022-09-16",null,"2022-09-30T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010071/21","Praha - Choceň","<>","Praha-Libeň","Praha-Vysočany",2022,2022,12,13,"2022-03-21T18:00:00",null,"2022-03-29T06:00:00",null,"8 x 6 hours","periodical","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021955/19","Plzen - Praha","<>","Praha-Smíchov","Praha-Radotín",2022,2022,23,26,"2022-06-10",null,"2022-06-30T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021953/19","Plzen - Praha","<>","Praha-Radotín","Dobřichovice",2022,2022,26,28,"2022-06-30",null,"2022-07-16T23:59:59.997",null,"17 days","continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009298/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,30,32,"2022-07-30T18:00:00",null,"2022-08-12T06:00:00",null,"13 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1.,3. + TV. \nzáhlaví a zhlaví 1. TK směr Bezpráví záhlaví a zhlaví 1. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021689/18","Praha - Choceň","<>","Praha-Libeň","Praha-Vysočany",2022,2022,6,9,"2022-02-13",null,"2022-02-28T23:59:59.997",null,"16 days","continuous","Miscellaneous","","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007718/20","Nürnberg - Plzen","<>","Pňovany","Stříbro",2022,2022,17,17,"2022-04-25",null,"2022-04-29T23:59:59.997",null,"5 x 6 hours","periodical","Maintenance","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007008/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Prosenice",2022,2022,52,1,"2022-01-02",null,"2022-01-08T23:59:59.997",null,"7 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007015/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Prosenice",2022,2022,19,20,"2022-05-11",null,"2022-05-19T23:59:59.997",null,"9 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009298/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,30,32,"2022-07-30T18:00:00",null,"2022-08-12T06:00:00",null,"13 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009298/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2022,2022,30,32,"2022-07-30T18:00:00",null,"2022-08-12T06:00:00",null,"26 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008495/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-28",null,"2022-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Borohrádek","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008532/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-31",null,"2022-07-31T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Borohrádek","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008532/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-31",null,"2022-07-31T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 3 směr Borohrádek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008532/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-31",null,"2022-07-31T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","3 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008508/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-28",null,"2022-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Častolovice","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008508/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-28",null,"2022-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 1 směr Častolovice.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008508/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-28",null,"2022-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021247/20","Praha - Choceň","<>","Uhersko","",2022,2022,13,14,"2022-04-01T18:00:00",null,"2022-04-05T06:00:00",null,"3 x 6 hours","periodical","Others","","ST","","","","","","B","","","celá bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021250/20","Praha - Choceň","<>","Uhersko","",2022,2022,16,17,"2022-04-22T18:00:00",null,"2022-04-26T06:00:00",null,"3 x 6 hours","periodical","Others","","ST","","","","","","B","","","celá bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021246/20","Plzen - Praha","<>","Zdice","Lochovice",2022,2022,37,46,"2022-09-16",null,"2022-11-14T23:59:59.997",null,"60 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008501/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,26,27,"2022-07-03",null,"2022-07-07T23:59:59.997",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Častolovice","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008501/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,26,27,"2022-07-03",null,"2022-07-07T23:59:59.997",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 1 směr Častolovice.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008501/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,26,27,"2022-07-03",null,"2022-07-07T23:59:59.997",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020787/19","Praha - Choceň","<>","Cerhenice","Pečky",2022,2022,20,31,"2022-05-19",null,"2022-08-05T23:59:59.997",null,"79 days","continuous","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020786/19","Praha - Choceň","<>","Pečky","Tatce",2022,2022,20,24,"2022-05-22",null,"2022-06-15T23:59:59.997",null,"25 days","continuous","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012443/21","Praha - Choceň","<>","Kolín","Velim",2022,2022,33,35,"2022-08-20",null,"2022-08-31T23:59:59.997",null,"12 days","continuous","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012440/21","Praha - Choceň","<>","Velim","Kolín",2022,2022,32,33,"2022-08-08",null,"2022-08-19T23:59:59.997",null,"12 days","continuous","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020785/19","Praha - Choceň","<>","Tatce","Pečky",2022,2022,9,12,"2022-03-04",null,"2022-03-24T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020784/19","Praha - Choceň","<>","Pečky","Cerhenice",2022,2022,9,20,"2022-03-01",null,"2022-05-18T23:59:59.997",null,"79 days","continuous","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020783/19","Praha - Choceň","<>","Tatce","Poříčany",2022,2022,24,29,"2022-06-16",null,"2022-07-19T23:59:59.997",null,"34 days","continuous","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020783/19","Praha - Choceň","<>","Poříčany","",2022,2022,24,29,"2022-06-16",null,"2022-07-19T23:59:59.997",null,"34 days","continuous","Miscellaneous","","ST","","","","","","B","","","0,2 + TV, výh.: 2,3. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006986/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Přerov",2022,2022,20,33,"2022-05-21",null,"2022-08-19T23:59:59.997",null,"91 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. \nzáhlaví a zhlaví směr Přerov.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006984/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","",2022,2022,9,14,"2022-03-02",null,"2022-04-09T23:59:59.997",null,"39 days","continuous","Track & Rail","","ST","","","","","","B","","","8,10 + TV. \nzáhlaví a zhlaví směr Brodek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006984/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,9,14,"2022-03-02",null,"2022-04-09T23:59:59.997",null,"39 days","continuous","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006983/20","Choceň - Hranice na Moravě","<>","Přerov","Dluhonice výhybna",2022,2022,5,20,"2022-02-01",null,"2022-05-20T23:59:59.997",null,"109 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006982/20","Choceň - Hranice na Moravě","<>","Prosenice","Dluhonice výhybna",2022,2022,5,9,"2022-02-01",null,"2022-03-01T23:59:59.997",null,"29 days","continuous","Track & Rail","","LT","","","","","","","","","1S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008487/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,30,30,"2022-07-29",null,"2022-07-29T23:59:59.997",null,"1 x 6 hours","periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020755/19","Praha - Choceň","<>","Praha-Libeň","Praha-Vysočany",2022,2022,29,29,"2022-07-20",null,"2022-07-23T23:59:59.997",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009909/21","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,44,46,"2022-11-03",null,"2022-11-17T23:59:59.997",null,"15 x 7 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009874/21","Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,37,42,"2022-09-17T18:00:00",null,"2022-10-21T06:00:00",null,"34 x 8 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008451/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,26,26,"2022-07-01",null,"2022-07-02T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008439/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,26,27,"2022-07-01",null,"2022-07-10T23:59:59.997",null,"10 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Borohrádek","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008448/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,27,27,"2022-07-08",null,"2022-07-10T23:59:59.997",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví SK 3 směr Borohrádek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008448/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2022,2022,27,27,"2022-07-08",null,"2022-07-10T23:59:59.997",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","3 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012303/20","Plzen - Praha","<>","Karlštejn","Beroun",2022,2022,49,49,"2022-12-08",null,"2022-12-09T23:59:59.997",null,"2 days","continuous","Miscellaneous","","LT","","","","","","","","","2 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020574/20","Praha - Choceň","<>","Kolín","Ratboř",2022,2022,16,16,"2022-04-19",null,"2022-04-23T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005894/21","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,15,15,"2022-04-13",null,"2022-04-14T23:59:59.997",null,"2 x 8 hours","periodical","Catenary","","ST","","","D","","","","","","2.,14.,16. bez TV, 2.,4a,4b,6.,14.,16.,18. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005891/21","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,14,14,"2022-04-07",null,"2022-04-08T23:59:59.997",null,"2 x 10 hours","periodical","Catenary","","ST","","","D","","","","","","16. bez TV, 14.,16.,18. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020400/20","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Opočno pod Orlickými horami",2022,2022,37,48,"2022-09-14",null,"2022-12-02T23:59:59.997",null,"80 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009773/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,29,30,"2022-07-23T18:00:00",null,"2022-07-28T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009778/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,31,32,"2022-08-02T18:00:00",null,"2022-08-08T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009784/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,33,33,"2022-08-15T18:00:00",null,"2022-08-19T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009788/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,44,48,"2022-11-01T18:00:00",null,"2022-12-01T06:00:00",null,"30 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009818/21","Plzen - Praha","<>","Praha-Radotín","",2022,2022,49,51,"2022-12-05T18:00:00",null,"2022-12-20T06:00:00",null,"15 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-019995/20","Praha - Choceň","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,46,46,"2022-11-14",null,"2022-11-14T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","2 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-019994/20","Praha - Choceň","<>","Pardubice hlavní nádraží","Kostěnice",2022,2022,45,45,"2022-11-13",null,"2022-11-13T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","1 bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-019989/20","Praha - Choceň","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,41,42,"2022-10-15",null,"2022-10-20T23:59:59.997",null,"6 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009748/21","Plzen - Praha","<>","Dobřichovice","Praha-Radotín",2022,2022,26,27,"2022-07-01T18:00:00",null,"2022-07-06T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009753/21","Plzen - Praha","<>","Dobřichovice","Praha-Radotín",2022,2022,27,28,"2022-07-10T18:00:00",null,"2022-07-15T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009745/21","Plzen - Praha","<>","Dobřichovice","Praha-Radotín",2022,2022,28,30,"2022-07-16",null,"2022-07-28T23:59:59.997",null,"13 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009726/21","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2022,2022,23,24,"2022-06-11T18:00:00",null,"2022-06-13T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009728/21","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2022,2022,24,25,"2022-06-16T18:00:00",null,"2022-06-20T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009732/21","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2022,2022,25,26,"2022-06-23T18:00:00",null,"2022-06-27T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009703/21","Plzen - Praha","<>","Praha-Smíchov","Praha-Radotín",2022,2022,21,22,"2022-05-27T18:00:00",null,"2022-06-01T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009708/21","Plzen - Praha","<>","Praha-Smíchov","Praha-Radotín",2022,2022,22,23,"2022-06-03T18:00:00",null,"2022-06-08T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005881/21","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,12,12,"2022-03-24",null,"2022-03-26T23:59:59.997",null,"3 x 8 hours","periodical","Catenary","","ST","","","D","","","","","","7. bez TV, 1.,3a,3b,5.,7.9. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005881/21","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,12,12,"2022-03-24",null,"2022-03-26T23:59:59.997",null,"3 x 8 hours","periodical","Catenary","","ST","","","D","","","","","","zhlaví pražské, jeho část od návěstidla L7 po návěstidlo Se64 a námezník výhybky číslo 43.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005878/21","Choceň - Hranice na Moravě","<>","Česká Třebová","",2022,2022,12,12,"2022-03-21",null,"2022-03-23T23:59:59.997",null,"3 x 8 hours","periodical","Catenary","","ST","","","D","","","","","","1. bez TV, 1.,3a,3b,5. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005871/20","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Blatec",2022,2022,44,45,"2022-11-03",null,"2022-11-12T23:59:59.997",null,"10 days","continuous","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004118/20","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Blatec",2022,2022,18,20,"2022-05-02",null,"2022-05-16T23:59:59.997",null,"15 x 10 hours","periodical","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004526/21","Hranice na Moravě - Ostrava","<>","Studénka","Suchdol nad Odrou",2022,2022,15,15,"2022-04-13",null,"2022-04-17T23:59:59.997",null,"5 days","continuous","Maintenance","","LT","","","D","","","","","","2. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004525/21","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Studénka",2022,2022,14,15,"2022-04-08",null,"2022-04-12T23:59:59.997",null,"5 days","continuous","Maintenance","","LT","","","D","","","","","","1. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007166/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,44,48,"2022-11-01",null,"2022-11-30T23:59:59.997",null,"30 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008308/21","Regensburg - Plzen","<>","Staňkov","Horšovský Týn",2022,2022,20,22,"2022-05-17",null,"2022-05-31T23:59:59.997",null,"15 days","continuous","Signal","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008305/21","Regensburg - Plzen","<>","Blížejov","Domažlice",2022,2022,12,13,"2022-03-23",null,"2022-04-01T23:59:59.997",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008298/21","Regensburg - Plzen","<>","Vejprnice","Nýřany",2022,2022,12,12,"2022-03-21",null,"2022-03-22T23:59:59.997",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008300/21","Regensburg - Plzen","<>","Stod","Holýšov",2022,2022,12,12,"2022-03-24",null,"2022-03-25T23:59:59.997",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008302/21","Regensburg - Plzen","<>","Holýšov","Staňkov",2022,2022,13,13,"2022-03-28",null,"2022-03-29T23:59:59.997",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008303/21","Regensburg - Plzen","<>","Staňkov","Blížejov",2022,2022,13,13,"2022-03-30",null,"2022-03-31T23:59:59.997",null,"2 x 6 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004508/21","Ostrava - Český Těšín","<>","Havířov","Ostrava-Bartovice",2022,2022,7,7,"2022-02-14",null,"2022-02-15T23:59:59.997",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004478/21","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín","Bohumín st.hr.",2022,2022,45,47,"2022-11-12",null,"2022-11-25T23:59:59.997",null,"14 days","continuous","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004468/21","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín","Bohumín st.hr.",2022,2022,22,23,"2022-06-01",null,"2022-06-10T23:59:59.997",null,"10 x 10 hours","periodical","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004268/21","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Blatec",2022,2022,26,31,"2022-07-01",null,"2022-08-04T23:59:59.997",null,"35 days","continuous","Signal","","LT","","","","","","","","","zab. zař. traťové.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004258/21","Hranice na Moravě - Žilina","<>","Hostašovice","Valašské Meziříčí",2022,2022,44,47,"2022-11-02",null,"2022-11-21T23:59:59.997",null,"20 days","continuous","Switch","","LT","","","","","","","","","zab. zař. PZS P7330 v km 62,635 a  P7334 v km 66,594.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007164/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,40,41,"2022-10-03",null,"2022-10-16T23:59:59.997",null,"14 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007163/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,36,37,"2022-09-05",null,"2022-09-18T23:59:59.997",null,"14 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007162/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,32,33,"2022-08-08",null,"2022-08-21T23:59:59.997",null,"14 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007161/21","Praha - Choceň","<>","Prachovice","Přelouč nákladní nádraží",2022,2022,28,29,"2022-07-11",null,"2022-07-24T23:59:59.997",null,"14 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005274/21","Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2022,2022,16,16,"2022-04-19",null,"2022-04-19T23:59:59.997",null,"1 x 8 hours","periodical","Signal","","LT","","","","","","","","","2. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008229/21","Plzen - Praha","<>","Praha-Zahradní Město","Praha-Eden",2022,2022,20,20,"2022-05-20",null,"2022-05-20T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","102 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005273/21","Nürnberg - Plzen","<>","Cheb","Lipová u Chebu",2022,2022,16,16,"2022-04-18",null,"2022-04-18T23:59:59.997",null,"1 x 8 hours","periodical","Signal","","LT","","","","","","","","","1. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005213/21","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Chotěbuz",2022,2022,38,39,"2022-09-24",null,"2022-09-30T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005211/21","Ostrava - Český Těšín","<>","Český Těšín","Albrechtice u Českého Těšína",2022,2022,15,15,"2022-04-11",null,"2022-04-14T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004181/20","Hranice na Moravě - Žilina","<>","Hranice na Moravě","Hranice na Moravě město",2022,2022,12,14,"2022-03-24",null,"2022-04-06T23:59:59.997",null,"14 days","continuous","Signal","","LT","","","","","","","","","zab. zař.  odbočky Skalka.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005207/21","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Chotěbuz",2022,2022,22,22,"2022-06-01",null,"2022-06-01T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005206/21","Ostrava - Český Těšín","<>","Chotěbuz","Albrechtice u Českého Těšína",2022,2022,17,17,"2022-04-26",null,"2022-04-30T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005205/21","Ostrava - Český Těšín","<>","Český Těšín","Albrechtice u Českého Těšína",2022,2022,22,22,"2022-05-31",null,"2022-05-31T23:59:59.997",null,"1 x 12 hours","periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005204/21","Ostrava - Český Těšín","<>","Český Těšín","Albrechtice u Českého Těšína",2022,2022,16,17,"2022-04-19",null,"2022-04-25T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005126/19","Praha - Choceň","<>","Poříčany","Tatce",2022,2022,12,16,"2022-03-25",null,"2022-04-22T23:59:59.997",null,"29 days","continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004885/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Častolovice",2022,2022,29,30,"2022-07-20",null,"2022-07-29T23:59:59.997",null,"10 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004883/21","Praha - Hr. Králové - Choceň","<>","Borohrádek","Týniště nad Orlicí",2022,2022,27,27,"2022-07-04",null,"2022-07-08T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004779/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,41,41,"2022-10-11",null,"2022-10-11T23:59:59.997",null,"1 x 10 hours","periodical","Switch","","LT","","","","","","","","","2/2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004777/21","Ostrava - Detmarovice - Cesky Tesin","<>","Karviná hlavní nádraží","Louky nad Olší",2022,2022,41,41,"2022-10-10",null,"2022-10-10T23:59:59.997",null,"1 x 10 hours","periodical","Switch","","LT","","","","","","","","","1/1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004776/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,37,39,"2022-09-17",null,"2022-09-26T23:59:59.997",null,"10 days","continuous","Switch","","LT","","","","","","","","","2/2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003956/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,3,3,"2022-01-17T18:00:00",null,"2022-01-18T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003957/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,3,4,"2022-01-21T18:00:00",null,"2022-01-24T06:00:00",null,"3 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003960/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,5,5,"2022-01-31T18:00:00",null,"2022-02-03T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003962/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,8,8,"2022-02-25T18:00:00",null,"2022-02-26T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003963/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,9,9,"2022-02-28T18:00:00",null,"2022-03-03T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003965/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,10,11,"2022-03-12T18:00:00",null,"2022-03-16T06:00:00",null,"3 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003968/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,12,12,"2022-03-25T18:00:00",null,"2022-03-26T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003969/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,13,13,"2022-03-28T18:00:00",null,"2022-03-30T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003971/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,15,15,"2022-04-14T18:00:00",null,"2022-04-15T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003974/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,16,17,"2022-04-22T18:00:00",null,"2022-04-25T06:00:00",null,"3 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003978/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,18,18,"2022-05-02T18:00:00",null,"2022-05-04T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003980/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,18,18,"2022-05-06T18:00:00",null,"2022-05-07T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003981/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,19,19,"2022-05-09T18:00:00",null,"2022-05-11T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003983/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,20,20,"2022-05-16T18:00:00",null,"2022-05-18T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003985/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,20,20,"2022-05-20T18:00:00",null,"2022-05-21T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003986/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,21,21,"2022-05-23T18:00:00",null,"2022-05-24T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003987/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,22,22,"2022-05-30T18:00:00",null,"2022-06-01T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003989/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,22,22,"2022-06-03T18:00:00",null,"2022-06-04T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003990/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,23,23,"2022-06-06T18:00:00",null,"2022-06-08T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003992/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,24,24,"2022-06-13T18:00:00",null,"2022-06-15T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003994/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,24,24,"2022-06-17T18:00:00",null,"2022-06-18T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003995/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,25,25,"2022-06-20T18:00:00",null,"2022-06-22T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003997/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,26,26,"2022-06-27T18:00:00",null,"2022-06-29T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003999/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,26,26,"2022-07-01T18:00:00",null,"2022-07-02T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004000/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,27,27,"2022-07-04T18:00:00",null,"2022-07-06T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004002/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,28,28,"2022-07-11T18:00:00",null,"2022-07-13T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004004/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,28,28,"2022-07-15T18:00:00",null,"2022-07-16T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004005/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,29,29,"2022-07-18T18:00:00",null,"2022-07-20T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004007/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,30,30,"2022-07-25T18:00:00",null,"2022-07-27T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004009/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,30,30,"2022-07-29T18:00:00",null,"2022-07-30T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004010/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,31,31,"2022-08-01T18:00:00",null,"2022-08-03T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004012/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,32,32,"2022-08-08T18:00:00",null,"2022-08-10T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004014/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,32,32,"2022-08-12T18:00:00",null,"2022-08-13T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004015/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,33,33,"2022-08-15T18:00:00",null,"2022-08-17T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004017/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,34,34,"2022-08-26T18:00:00",null,"2022-08-27T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004018/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,35,35,"2022-08-29T18:00:00",null,"2022-08-31T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004020/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,39,39,"2022-09-30T18:00:00",null,"2022-10-01T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004021/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,40,40,"2022-10-03T18:00:00",null,"2022-10-05T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004015/20","Hranice na Moravě - Žilina","<>","Valašské Meziříčí","Střítež nad Bečvou",2022,2022,39,40,"2022-10-01",null,"2022-10-07T23:59:59.997",null,"7 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004772/21","Ostrava - Detmarovice - Cesky Tesin","<>","Karviná hlavní nádraží","Louky nad Olší",2022,2022,36,37,"2022-09-05",null,"2022-09-16T23:59:59.997",null,"12 days","continuous","Switch","","LT","","","","","","","","","1/1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004766/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná-Doly",2022,2022,11,11,"2022-03-16",null,"2022-03-18T23:59:59.997",null,"3 x 10 hours","periodical","Maintenance","T","LT","","","","","","","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004769/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná-Doly",2022,2022,41,41,"2022-10-13",null,"2022-10-14T23:59:59.997",null,"2 x 10 hours","periodical","Maintenance","T","LT","","","","","","","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004009/20","Hranice na Moravě - Žilina","<>","Valašské Klobouky","Horní Lideč",2022,2022,19,21,"2022-05-09",null,"2022-05-23T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004745/21","Ostrava - Detmarovice - Cesky Tesin","<>","Karviná hlavní nádraží","Louky nad Olší",2022,2022,10,10,"2022-03-07",null,"2022-03-11T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1/1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004750/21","Ostrava - Detmarovice - Cesky Tesin","<>","Karviná hlavní nádraží","Louky nad Olší",2022,2022,40,40,"2022-10-03",null,"2022-10-05T23:59:59.997",null,"3 x 10 hours","periodical","Track & Rail","","LT","","","","","","","","","1/1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004730/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Bystřice (Bystrzyca)",2022,2022,36,36,"2022-09-11",null,"2022-09-11T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004729/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Bystřice (Bystrzyca)",2022,2022,32,32,"2022-08-12",null,"2022-08-14T23:59:59.997",null,"3 days","continuous","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004728/21","Cesky Tesin - Zilina","<>","Bystřice (Bystrzyca)","Návsí (Nawsie)",2022,2022,36,36,"2022-09-10",null,"2022-09-10T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004727/21","Cesky Tesin - Zilina","<>","Bystřice (Bystrzyca)","Návsí (Nawsie)",2022,2022,32,32,"2022-08-09",null,"2022-08-11T23:59:59.997",null,"3 days","continuous","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004726/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Bystřice (Bystrzyca)",2022,2022,36,36,"2022-09-08",null,"2022-09-08T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004725/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Bystřice (Bystrzyca)",2022,2022,31,32,"2022-08-05",null,"2022-08-08T23:59:59.997",null,"4 days","continuous","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004724/21","Cesky Tesin - Zilina","<>","Bystřice (Bystrzyca)","Návsí (Nawsie)",2022,2022,36,36,"2022-09-09",null,"2022-09-09T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004723/21","Cesky Tesin - Zilina","<>","Bystřice (Bystrzyca)","Návsí (Nawsie)",2022,2022,31,31,"2022-08-01",null,"2022-08-04T23:59:59.997",null,"4 days","continuous","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007122/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,48,48,"2022-11-28",null,"2022-12-01T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","B","","","2 + TV. \nzáhlaví a zhlaví směr Brodek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007122/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","",2022,2022,48,48,"2022-11-28",null,"2022-12-01T23:59:59.997",null,"4 days","continuous","Track & Rail","","ST","","","","","","B","","","4,6,8,10 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007121/20","Choceň - Hranice na Moravě","<>","Brodek u Přerova","Dluhonice výhybna",2022,2022,47,47,"2022-11-26",null,"2022-11-27T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","B","","","1 + TV. \nzáhlaví a zhlaví směr Brodek.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007121/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","",2022,2022,47,47,"2022-11-26",null,"2022-11-27T23:59:59.997",null,"2 days","continuous","Track & Rail","","ST","","","","","","B","","","1,3 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007120/20","Choceň - Hranice na Moravě","<>","Přerov","Dluhonice výhybna",2022,2022,46,46,"2022-11-14",null,"2022-11-19T23:59:59.997",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007119/20","Choceň - Hranice na Moravě","<>","Prosenice","Dluhonice výhybna",2022,2022,45,45,"2022-11-08",null,"2022-11-13T23:59:59.997",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","1S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003919/21","Plzen - Praha","<>","Zdice","Lochovice",2022,2022,38,39,"2022-09-20",null,"2022-09-29T23:59:59.997",null,"10 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. \nzab. zař. přejezdové v km 97,397 (P562).","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007118/20","Choceň - Hranice na Moravě","<>","Dluhonice výhybna","Prosenice",2022,2022,44,45,"2022-11-02",null,"2022-11-07T23:59:59.997",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","2S + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003391/21","Choceň - Hranice na Moravě","<>","Zábřeh na Moravě","Hoštejn předjízdné koleje",2022,2022,8,8,"2022-02-25",null,"2022-02-25T23:59:59.997",null,"1 x 7 hours","periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003390/21","Choceň - Hranice na Moravě","<>","Hoštejn předjízdné koleje","Zábřeh na Moravě",2022,2022,8,8,"2022-02-24",null,"2022-02-24T23:59:59.997",null,"1 x 7 hours","periodical","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003218/21","Choceň - Hranice na Moravě","<>","Velká Bystřice","Olomouc hlavní nádraží",2022,2022,26,30,"2022-07-01",null,"2022-07-31T23:59:59.997",null,"31 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009330/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,48,50,"2022-11-30T18:00:00",null,"2022-12-18T06:00:00",null,"18 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009330/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,48,50,"2022-11-30T18:00:00",null,"2022-12-18T06:00:00",null,"18 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1.,3. + TV. \nzáhlaví a zhlaví 1. TK směr Bezpráví záhlaví a zhlaví 1. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009330/21","Choceň - Hranice na Moravě","<>","Choceň","Brandýs nad Orlicí",2022,2022,48,50,"2022-11-30T18:00:00",null,"2022-12-18T06:00:00",null,"36 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009325/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,44,44,"2022-11-01T18:00:00",null,"2022-11-06T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009325/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2022,2022,44,44,"2022-11-01T18:00:00",null,"2022-11-06T06:00:00",null,"10 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009325/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,44,44,"2022-11-01T18:00:00",null,"2022-11-06T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1.,3. + TV. \nzáhlaví a zhlaví 1. TK směr Bezpráví záhlaví a zhlaví 1. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009313/21","Choceň - Hranice na Moravě","<>","Choceň","Brandýs nad Orlicí",2022,2022,37,38,"2022-09-16T18:00:00",null,"2022-09-20T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009313/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2022,2022,37,38,"2022-09-16T18:00:00",null,"2022-09-20T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009313/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2022,2022,37,38,"2022-09-16T18:00:00",null,"2022-09-20T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009313/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,37,38,"2022-09-16T18:00:00",null,"2022-09-20T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","1.,3. + TV. \nzáhlaví a zhlaví 1. TK směr Bezpráví záhlaví a zhlaví 1. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009293/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2022,2022,19,20,"2022-05-15T18:00:00",null,"2022-05-20T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009293/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Choceň",2022,2022,19,20,"2022-05-15T18:00:00",null,"2022-05-20T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009293/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,19,20,"2022-05-15T18:00:00",null,"2022-05-20T06:00:00",null,"5 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví záhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009289/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,14,15,"2022-04-09T18:00:00",null,"2022-04-12T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví\nzáhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009289/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Choceň",2022,2022,14,15,"2022-04-09T18:00:00",null,"2022-04-12T06:00:00",null,"6 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009280/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Choceň",2022,2022,12,13,"2022-03-21T18:00:00",null,"2022-03-29T06:00:00",null,"16 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009280/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,12,13,"2022-03-21T18:00:00",null,"2022-03-29T06:00:00",null,"8 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví\nzáhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009273/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2022,2022,6,7,"2022-02-09T18:00:00",null,"2022-02-16T06:00:00",null,"14 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009273/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,6,7,"2022-02-09T18:00:00",null,"2022-02-16T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví\nzáhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009268/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2022,2022,5,5,"2022-02-01T18:00:00",null,"2022-02-05T06:00:00",null,"4 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","2.,4. + TV. \nzáhlaví a zhlaví 2. TK směr Bezpráví\nzáhlaví a zhlaví 2. TK směr Choceň.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009268/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2022,2022,5,5,"2022-02-01T18:00:00",null,"2022-02-05T06:00:00",null,"8 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009266/21","Plzen - Praha","<>","Zdice","Hořovice",2022,2022,26,26,"2022-06-27T18:00:00",null,"2022-06-28T06:00:00",null,"1 x 12 hours","periodical","Signal","","LT","","","","","","B","","","zab. zař. TZZ 1. a 2. TK.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009263/21","Praha - Choceň","<>","Pečky","Poříčany",2022,2022,40,40,"2022-10-09",null,"2022-10-09T23:59:59.997",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009265/21","Praha - Choceň","<>","Velim","Pečky",2022,2022,41,41,"2022-10-16",null,"2022-10-16T23:59:59.997",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009262/21","Praha - Choceň","<>","Poříčany","Pečky",2022,2022,40,40,"2022-10-08",null,"2022-10-08T23:59:59.997",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009264/21","Praha - Choceň","<>","Pečky","Velim",2022,2022,41,41,"2022-10-15",null,"2022-10-15T23:59:59.997",null,"1 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009261/21","Praha - Choceň","<>","Poříčany","Sadská",2022,2022,40,40,"2022-10-07T18:00:00",null,"2022-10-08T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009261/21","Praha - Choceň","<>","Poříčany","",2022,2022,40,40,"2022-10-07T18:00:00",null,"2022-10-08T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","sudá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009259/21","Praha - Choceň","<>","Poříčany","Pečky",2022,2022,40,40,"2022-10-06T18:00:00",null,"2022-10-07T06:00:00",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009257/21","Praha - Choceň","<>","Velim","Pečky",2022,2022,40,40,"2022-10-05T18:00:00",null,"2022-10-06T06:00:00",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009254/21","Praha - Choceň","<>","Pečky","Velim",2022,2022,39,40,"2022-10-02T18:00:00",null,"2022-10-05T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009253/21","Praha - Choceň","<>","Velim","Pečky",2022,2022,39,40,"2022-10-01T18:00:00",null,"2022-10-04T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009252/21","Praha - Choceň","<>","Pečky","Cerhenice",2022,2022,33,33,"2022-08-15",null,"2022-08-17T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009251/21","Praha - Choceň","<>","Velim","",2022,2022,33,34,"2022-08-20",null,"2022-08-23T23:59:59.997",null,"4 days","continuous","Catenary","","ST","","","","","","B","","","sudá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009250/21","Praha - Choceň","<>","Cerhenice","Pečky",2022,2022,34,35,"2022-08-28",null,"2022-08-30T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009249/21","Praha - Choceň","<>","Velim","Cerhenice",2022,2022,34,34,"2022-08-24",null,"2022-08-26T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009247/21","Praha - Choceň","<>","Cerhenice","Velim",2022,2022,32,32,"2022-08-12",null,"2022-08-14T23:59:59.997",null,"3 days","continuous","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009104/21","Praha - Choceň","<>","Velim","Cerhenice",2022,2022,23,24,"2022-06-08T18:00:00",null,"2022-06-13T06:00:00",null,"2 x 12 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009246/21","Praha - Choceň","<>","Pečky","Tatce",2022,2022,24,25,"2022-06-19T18:00:00",null,"2022-06-20T06:00:00",null,"1 x 12 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009096/21","Praha - Choceň","<>","Velim","Cerhenice",2022,2022,22,23,"2022-06-02T18:00:00",null,"2022-06-10T06:00:00",null,"8 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009238/21","Praha - Choceň","<>","Pečky","Tatce",2022,2022,25,26,"2022-06-20T18:00:00",null,"2022-06-28T06:00:00",null,"8 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009129/20","Nürnberg - Plzen","<>","Ošelín","Lázně Kynžvart",2022,2022,13,26,"2022-04-01",null,"2022-06-30T23:59:59.997",null,"91 days","continuous","Others","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009114/21","Praha - Choceň","<>","Tatce","Poříčany",2022,2022,22,23,"2022-05-30T18:00:00",null,"2022-06-07T06:00:00",null,"8 x 7 hours","periodical","Miscellaneous","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009053/21","Praha - Choceň","<>","Tatce","Pečky",2022,2022,14,14,"2022-04-08T18:00:00",null,"2022-04-09T06:00:00",null,"1 x 12 hours","periodical","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-019653/20","Wroclaw - Breclav","<>","Brno-Černovice odb.","Brno hlavní nádraží",2023,2023,12,13,"2023-03-24",null,"2023-03-30T23:59:59.997",null,"7 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. \nzáhlaví Odb.Brno-Černovice od náv.BS po IS za výh.6","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-019217/20","Praha - Hr. Králové - Choceň","<>","Nový Bydžov","Chlumec nad Cidlinou",2023,2023,40,42,"2023-10-02",null,"2023-10-16T23:59:59.997",null,"15 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007165/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,1,7,"2023-01-02T18:00:00",null,"2023-02-15T06:00:00",null,"44 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","2,1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017522/20","Hranice na Moravě - Ostrava","<>","Ostrava-Svinov","",2023,2023,46,47,"2023-11-15",null,"2023-11-21T23:59:59.997",null,"7 days","continuous","Switch","","ST","","","","","","B","","","12.,14. bez TV, 6.,12. jen TV, výh.: 4,5,7. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017522/20","Hranice na Moravě - Ostrava","<>","Ostrava-Svinov","Háj ve Slezsku",2023,2023,46,47,"2023-11-15",null,"2023-11-21T23:59:59.997",null,"7 days","continuous","Switch","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017475/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Budišov nad Budišovkou",2023,2023,27,38,"2023-07-03",null,"2023-09-18T23:59:59.997",null,"78 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017470/20","Choceň - Hranice na Moravě","<>","Senice na Hané","Červenka",2023,2023,22,23,"2023-06-01",null,"2023-06-10T23:59:59.997",null,"10 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017461/20","Hranice na Moravě - Ostrava","<>","Studénka","Bílovec",2023,2023,23,24,"2023-06-08",null,"2023-06-12T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017445/20","Hranice na Moravě - Žilina","<>","Hustopeče nad Bečvou","Hranice na Moravě město",2023,2023,23,25,"2023-06-11",null,"2023-06-21T23:59:59.997",null,"11 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017444/20","Hranice na Moravě - Žilina","<>","Hranice na Moravě město","Hustopeče nad Bečvou",2023,2023,22,23,"2023-06-01",null,"2023-06-10T23:59:59.997",null,"10 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017443/20","Hranice na Moravě - Žilina","<>","Hranice na Moravě","Hranice na Moravě město",2023,2023,18,22,"2023-05-01",null,"2023-05-30T23:59:59.997",null,"30 days","continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017343/20","Hranice na Moravě - Žilina","<>","Hostašovice","Valašské Meziříčí",2023,2023,31,33,"2023-08-02",null,"2023-08-15T23:59:59.997",null,"14 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017295/20","Hranice na Moravě - Žilina","<>","Horní Lideč","Horní Lideč st.hr.",2023,2023,18,19,"2023-05-01",null,"2023-05-10T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026820/20","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2023,2023,20,25,"2023-05-17",null,"2023-06-20T23:59:59.997",null,"35 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026819/20","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","Bezpráví",2023,2023,15,20,"2023-04-12",null,"2023-05-16T23:59:59.997",null,"35 days","continuous","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026819/20","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,15,20,"2023-04-12",null,"2023-05-16T23:59:59.997",null,"35 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017294/20","Hranice na Moravě - Žilina","<>","Valašské Meziříčí","Jablůnka",2023,2023,44,45,"2023-11-01",null,"2023-11-10T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017293/20","Hranice na Moravě - Žilina","<>","Jablůnka","Valašské Meziříčí",2023,2023,35,44,"2023-09-02",null,"2023-10-31T23:59:59.997",null,"60 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017292/20","Hranice na Moravě - Žilina","<>","Horní Lideč","Valašská Polanka",2023,2023,20,22,"2023-05-21",null,"2023-05-30T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017291/20","Hranice na Moravě - Žilina","<>","Valašská Polanka","Horní Lideč",2023,2023,19,20,"2023-05-11",null,"2023-05-20T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-017290/20","Hranice na Moravě - Žilina","<>","Rožnov pod Radhoštěm","Valašské Meziříčí",2023,2023,35,37,"2023-09-02",null,"2023-09-17T23:59:59.997",null,"16 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016732/20","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Blatec",2023,2023,16,27,"2023-04-17",null,"2023-07-09T23:59:59.997",null,"84 days","continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016729/20","Choceň - Hranice na Moravě","<>","Senice na Hané","Olomouc hlavní nádraží",2023,2023,31,35,"2023-08-01",null,"2023-08-30T23:59:59.997",null,"30 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016727/20","Hranice na Moravě - Žilina","<>","Hranice na Moravě město","Hranice na Moravě",2023,2023,13,17,"2023-04-01",null,"2023-04-30T23:59:59.997",null,"30 days","continuous","Catenary","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005453/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2023,2023,7,7,"2023-02-13",null,"2023-02-16T23:59:59.997",null,"4 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005453/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2023,2023,7,7,"2023-02-13",null,"2023-02-16T23:59:59.997",null,"4 days","continuous","Signal","","LT","","","","","","","","","zab. zař. přejezdové v km 147,774 (P314), v km 146,112 (P313), v km 145,405 (P312), v km 144,584 (P311), v km 143,379 (P310) .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005450/21","Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2023,2023,6,6,"2023-02-06",null,"2023-02-10T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ 1.,2..","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005450/21","Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2023,2023,6,6,"2023-02-06",null,"2023-02-10T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. přejezdové v km 450,996 (P308) a v km 453,267 (P309) .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026819/20","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,15,20,"2023-04-12",null,"2023-05-16T23:59:59.997",null,"35 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Ústí nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026818/20","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2023,2023,10,15,"2023-03-08",null,"2023-04-11T23:59:59.997",null,"35 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026816/20","Choceň - Hranice na Moravě","<>","Bezpráví","Ústí nad Orlicí",2023,2023,5,10,"2023-02-01",null,"2023-03-07T23:59:59.997",null,"35 days","continuous","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008762/21","Praha - Hr. Králové - Choceň","<>","Libice nad Cidlinou","Velký Osek",2023,2023,31,31,"2023-08-01",null,"2023-08-02T23:59:59.997",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026816/20","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,5,10,"2023-02-01",null,"2023-03-07T23:59:59.997",null,"35 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Ústí nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-026816/20","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,5,10,"2023-02-01",null,"2023-03-07T23:59:59.997",null,"35 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-025019/19","Hranice na Moravě - Žilina","<>","Vsetín","Jablůnka",2023,2023,30,32,"2023-07-26",null,"2023-08-08T23:59:59.997",null,"14 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008040/21","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Grygov",2023,2023,16,17,"2023-04-17",null,"2023-04-24T23:59:59.997",null,"8 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-016149/20","Ostrava - Český Těšín","<>","Český Těšín","Albrechtice u Českého Těšína",2023,2023,16,17,"2023-04-17",null,"2023-04-30T23:59:59.997",null,"14 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-015105/18","Ostrava - Český Těšín","<>","Odra odb.","Ostrava-Vítkovice",2023,2023,40,45,"2023-10-07",null,"2023-11-11T23:59:59.997",null,"36 days","continuous","Others","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005336/21","Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","Návsí (Nawsie)",2023,2023,36,36,"2023-09-08",null,"2023-09-08T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008752/21","Praha - Hr. Králové - Choceň","<>","Velký Osek","Libice nad Cidlinou",2023,2023,29,30,"2023-07-18",null,"2023-07-27T23:59:59.997",null,"10 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012789/21","Praha - Choceň","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2023,2023,48,50,"2023-12-02",null,"2023-12-13T23:59:59.997",null,"12 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012697/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,50,50,"2023-12-14T18:00:00",null,"2023-12-17T06:00:00",null,"3 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012634/20","Plzen - Praha","<>","Beroun","Karlštejn",2023,2023,41,51,"2023-10-15",null,"2023-12-20T23:59:59.997",null,"67 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012632/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,23,41,"2023-06-11",null,"2023-10-14T23:59:59.997",null,"126 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005335/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Mosty u Jabl. (Mosty koło Jabł.)",2023,2023,36,36,"2023-09-07",null,"2023-09-07T23:59:59.997",null,"1 x 8 hours","periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005334/21","Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","Návsí (Nawsie)",2023,2023,32,32,"2023-08-07",null,"2023-08-10T23:59:59.997",null,"4 days","continuous","Maintenance","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005333/21","Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Mosty u Jabl. (Mosty koło Jabł.)",2023,2023,31,31,"2023-08-01",null,"2023-08-04T23:59:59.997",null,"4 days","continuous","Maintenance","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005332/21","Cesky Tesin - Zilina","<>","Mosty u Jablunkova st.hr.","Mosty u Jabl. (Mosty koło Jabł.)",2023,2023,15,16,"2023-04-14",null,"2023-04-23T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005331/21","Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","Mosty u Jablunkova st.hr.",2023,2023,14,15,"2023-04-03",null,"2023-04-12T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005087/21","Praha - Hr. Králové - Choceň","<>","Hradec Králové hlavní nádraží","Hradec Králové-Slez. Předměstí",2023,2023,27,27,"2023-07-03",null,"2023-07-07T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012339/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,19,19,"2023-05-09T18:00:00",null,"2023-05-11T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012333/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,19,19,"2023-05-13",null,"2023-05-14T23:59:59.997",null,"2 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012310/20","Plzen - Praha","<>","Beroun","Karlštejn",2023,2023,19,19,"2023-05-11T18:00:00",null,"2023-05-13T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012310/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,19,19,"2023-05-11T18:00:00",null,"2023-05-13T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-012324/20","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,13,16,"2023-03-31",null,"2023-04-18T23:59:59.997",null,"19 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009928/21","Plzen - Praha","<>","Beroun","Karlštejn",2023,2023,20,21,"2023-05-15T18:00:00",null,"2023-05-22T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009928/21","Plzen - Praha","<>","Karlštejn","Beroun",2023,2023,20,21,"2023-05-15T18:00:00",null,"2023-05-22T06:00:00",null,"7 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005084/21","Praha - Hr. Králové - Choceň","<>","Třebechovice pod Orebem","",2023,2023,23,25,"2023-06-08",null,"2023-06-21T23:59:59.997",null,"14 days","continuous","Track & Rail","","ST","","","D","","","","","","2 bez TV, 1,2,3 jen TV, výh.: 3,5. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005074/21","Praha - Hr. Králové - Choceň","<>","Opatovice nad Labem-Pohřebačka","Plačice odb.",2023,2023,16,16,"2023-04-17",null,"2023-04-21T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005051/21","Praha - Hr. Králové - Choceň","<>","Chlumec nad Cidlinou","Městec Králové",2023,2023,40,40,"2023-10-02",null,"2023-10-06T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005056/21","Praha - Hr. Králové - Choceň","<>","Chlumec nad Cidlinou","Městec Králové",2023,2023,41,41,"2023-10-09",null,"2023-10-13T23:59:59.997",null,"5 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008742/21","Praha - Hr. Králové - Choceň","<>","Libice nad Cidlinou","Velký Osek",2023,2023,27,28,"2023-07-03",null,"2023-07-12T23:59:59.997",null,"10 x 10 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011488/18","Ostrava - Český Těšín","<>","Ostrava-Vítkovice","Odra odb.",2023,2023,35,40,"2023-09-01",null,"2023-10-06T23:59:59.997",null,"36 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011042/19","Choceň - Hranice na Moravě","<>","Česká Třebová","",2023,2023,38,44,"2023-09-22",null,"2023-10-31T23:59:59.997",null,"40 days","continuous","Track & Rail","","ST","","","D","","","","","","231,232,233 bez TV, 231-234 jen TV, výh.: 250 -257. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-011018/21","Nürnberg - Plzen","<>","Pňovany","Planá u Mariánských Lázní",2023,2023,42,49,"2023-10-21",null,"2023-12-09T23:59:59.997",null,"50 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004825/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,25,25,"2023-06-19T18:00:00",null,"2023-06-21T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004827/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,25,25,"2023-06-23T18:00:00",null,"2023-06-24T06:00:00",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004828/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,26,26,"2023-06-26T18:00:00",null,"2023-06-28T06:00:00",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010596/21","Hranice na Moravě - Ostrava","<>","Jistebník","Studénka",2023,2023,19,20,"2023-05-09",null,"2023-05-15T23:59:59.997",null,"7 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 251,286.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010595/21","Hranice na Moravě - Ostrava","<>","Jistebník","Studénka",2023,2023,18,19,"2023-05-02",null,"2023-05-08T23:59:59.997",null,"7 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 250,404.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010594/21","Hranice na Moravě - Ostrava","<>","Jistebník","Studénka",2023,2023,15,16,"2023-04-11",null,"2023-04-17T23:59:59.997",null,"7 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km 248,943.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-010593/21","Hranice na Moravě - Ostrava","<>","Jistebník","Studénka",2023,2023,14,15,"2023-04-04",null,"2023-04-10T23:59:59.997",null,"7 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZS v km246,669.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004643/21","Praha - Hr. Králové - Choceň","<>","Chlumec nad Cidlinou","Hradec Králové hlavní nádraží",2023,2023,29,30,"2023-07-17",null,"2023-07-26T23:59:59.997",null,"10 days","continuous","Bridge","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008723/18","Hranice na Moravě - Ostrava","<>","Ostrava-Svinov","",2023,2023,22,35,"2023-06-02",null,"2023-08-30T23:59:59.997",null,"90 days","continuous","Miscellaneous","","ST","","","D","","","","","","2.,4. bez TV, 2.,4a,4. jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008228/21","Plzen - Praha","<>","Tunel odb.","Praha-Krč",2023,2023,48,50,"2023-12-01",null,"2023-12-15T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008228/21","Plzen - Praha","<>","Praha-Krč","Praha-Vršovice",2023,2023,48,50,"2023-12-01",null,"2023-12-15T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008228/21","Plzen - Praha","<>","Praha-Krč","Praha-Zahradní Město",2023,2023,48,50,"2023-12-01",null,"2023-12-15T23:59:59.997",null,"15 days","continuous","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008216/19","Praha - Hr. Králové - Choceň","<>","Nový Bydžov","Chlumec nad Cidlinou",2023,2023,40,42,"2023-10-02",null,"2023-10-19T23:59:59.997",null,"18 days","continuous","Signal","","LT","","","","","","","","","zab. zař. PZZ v km 32,657, v km 31,841, v km 30,231, v km 30,045, v km 29,586, v km 29,170.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008080/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2023,2023,40,40,"2023-10-07T18:00:00",null,"2023-10-08T06:00:00",null,"1 x 16 hours","periodical","Signal","","LT","","","","","","","","","zab. zař. SZZ, TZZ, PZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008078/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2023,2023,24,25,"2023-06-15",null,"2023-06-22T23:59:59.997",null,"8 days","continuous","Bridge","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008077/21","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Grygov",2023,2023,23,24,"2023-06-07",null,"2023-06-14T23:59:59.997",null,"8 days","continuous","Bridge","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008074/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2023,2023,30,30,"2023-07-26",null,"2023-07-27T23:59:59.997",null,"2 x 6 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008072/21","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Grygov",2023,2023,30,30,"2023-07-28",null,"2023-07-29T23:59:59.997",null,"2 x 6 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009918/21","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2023,2023,16,17,"2023-04-23",null,"2023-04-26T23:59:59.997",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","1. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009918/21","Plzen - Praha","<>","Praha-Radotín","Závodiště odbočka",2023,2023,16,17,"2023-04-23",null,"2023-04-26T23:59:59.997",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","3. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008057/21","Choceň - Hranice na Moravě","<>","Olomouc hlavní nádraží","Grygov",2023,2023,21,22,"2023-05-28",null,"2023-05-29T23:59:59.997",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008054/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2023,2023,22,22,"2023-05-30",null,"2023-05-31T23:59:59.997",null,"2 x 8 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009917/21","Plzen - Praha","<>","Praha-Smíchov","Praha-Radotín",2023,2023,16,16,"2023-04-19",null,"2023-04-22T23:59:59.997",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009917/21","Plzen - Praha","<>","Závodiště odbočka","Praha-Radotín",2023,2023,16,16,"2023-04-19",null,"2023-04-22T23:59:59.997",null,"4 days","continuous","Miscellaneous","","LT","","","","","","","","","4. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009506/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2023,2023,37,37,"2023-09-14T18:00:00",null,"2023-09-17T06:00:00",null,"3 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","sudá + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009506/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2023,2023,37,37,"2023-09-14T18:00:00",null,"2023-09-17T06:00:00",null,"3 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Choceň; zhlaví 2. TK směr Bezpráví.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008047/21","Choceň - Hranice na Moravě","<>","Grygov","Olomouc hlavní nádraží",2023,2023,17,17,"2023-04-24",null,"2023-04-30T23:59:59.997",null,"7 x 6 hours","periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009504/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2023,2023,37,37,"2023-09-12T18:00:00",null,"2023-09-14T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009502/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","Bezpráví",2023,2023,36,37,"2023-09-10T18:00:00",null,"2023-09-12T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009502/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,36,37,"2023-09-10T18:00:00",null,"2023-09-12T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009502/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,36,37,"2023-09-10T18:00:00",null,"2023-09-12T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Ústí n. O.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009502/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,36,37,"2023-09-10T18:00:00",null,"2023-09-12T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007966/21","Nürnberg - Plzen","<>","Mariánské Lázně","Cheb",2023,2023,37,38,"2023-09-11",null,"2023-09-20T23:59:59.997",null,"10 x 10 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009496/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2023,2023,36,36,"2023-09-05T18:00:00",null,"2023-09-07T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004513/21","Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Bohumín",2023,2023,14,35,"2023-04-04",null,"2023-08-31T23:59:59.997",null,"150 days","continuous","Catenary","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004513/21","Ostrava - Detmarovice - Cesky Tesin","<>","Dětmarovice","Petrovice u Karviné",2023,2023,14,35,"2023-04-04",null,"2023-08-31T23:59:59.997",null,"150 days","continuous","Catenary","","LT","","","","","","","","","","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004154/20","Regensburg - Plzen","<>","Domažlice odb.v.401","Česká Kubice",2023,2023,14,42,"2023-04-04",null,"2023-10-20T23:59:59.997",null,"200 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004154/20","Regensburg - Plzen","<>","Česká Kubice","",2023,2023,14,42,"2023-04-04",null,"2023-10-20T23:59:59.997",null,"200 days","continuous","Miscellaneous","","ST","","","","","","B","","","celá bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004154/20","Regensburg - Plzen","<>","Česká Kubice","Česká Kubice st.hr.",2023,2023,14,42,"2023-04-04",null,"2023-10-20T23:59:59.997",null,"200 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009492/21","Choceň - Hranice na Moravě","<>","Bezpráví","Ústí nad Orlicí",2023,2023,35,36,"2023-09-03T18:00:00",null,"2023-09-05T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009492/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,35,36,"2023-09-03T18:00:00",null,"2023-09-05T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009492/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,35,36,"2023-09-03T18:00:00",null,"2023-09-05T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Ústí n. O.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009492/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,35,36,"2023-09-03T18:00:00",null,"2023-09-05T06:00:00",null,"2 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004094/21","Choceň - Hranice na Moravě","<>","Rudoltice v Čechách","Třebovice v Čechách",2023,2023,43,43,"2023-10-23",null,"2023-10-27T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004093/21","Choceň - Hranice na Moravě","<>","Krasíkov předjízdné koleje","Rudoltice v Čechách",2023,2023,42,42,"2023-10-20",null,"2023-10-22T23:59:59.997",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004092/21","Choceň - Hranice na Moravě","<>","Hoštejn","Tatenice",2023,2023,41,42,"2023-10-15",null,"2023-10-19T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004091/21","Choceň - Hranice na Moravě","<>","Tatenice","Hoštejn",2023,2023,41,41,"2023-10-10",null,"2023-10-14T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004090/21","Choceň - Hranice na Moravě","<>","Rudoltice v Čechách","Krasíkov předjízdné koleje",2023,2023,40,41,"2023-10-07",null,"2023-10-09T23:59:59.997",null,"3 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004089/21","Choceň - Hranice na Moravě","<>","Třebovice v Čechách","Rudoltice v Čechách",2023,2023,40,40,"2023-10-02",null,"2023-10-06T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004088/21","Choceň - Hranice na Moravě","<>","Parník odb.","Česká Třebová odjezdová skupina",2023,2023,15,15,"2023-04-10",null,"2023-04-14T23:59:59.997",null,"5 days","continuous","Track & Rail","","LT","","","","","","","","","3. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004055/21","Hranice na Moravě - Žilina","<>","Horní Lideč st.hr.","Horní Lideč",2023,2023,16,17,"2023-04-21",null,"2023-04-30T23:59:59.997",null,"10 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004048/21","Hranice na Moravě - Žilina","<>","Velké Karlovice","Vsetín",2023,2023,36,37,"2023-09-05",null,"2023-09-11T23:59:59.997",null,"7 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004043/21","Hranice na Moravě - Žilina","<>","Bylnice","Horní Lideč",2023,2023,38,39,"2023-09-22",null,"2023-09-26T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004042/21","Hranice na Moravě - Žilina","<>","Bylnice","Horní Lideč",2023,2023,18,18,"2023-05-02",null,"2023-05-06T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004024/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,20,20,"2023-05-15T18:00:00",null,"2023-05-16T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004025/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,20,20,"2023-05-19T18:00:00",null,"2023-05-20T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004026/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,21,21,"2023-05-22T18:00:00",null,"2023-05-24T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004028/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,22,22,"2023-05-29T18:00:00",null,"2023-05-30T06:00:00",null,"1 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-004029/21","Plzen - Praha","<>","Plzeň hlavní nádraží","",2023,2023,22,22,"2023-06-02T18:00:00",null,"2023-06-04T06:00:00",null,"2 x 6 hours","periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009466/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","Bezpráví",2023,2023,5,5,"2023-01-31T18:00:00",null,"2023-02-01T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009467/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","Bezpráví",2023,2023,10,10,"2023-03-07T18:00:00",null,"2023-03-08T06:00:00",null,"2 x 12 hours","periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009471/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2023,2023,25,25,"2023-06-20T18:00:00",null,"2023-06-21T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009471/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,25,25,"2023-06-20T18:00:00",null,"2023-06-21T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Brandýs nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009466/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,5,5,"2023-01-31T18:00:00",null,"2023-02-01T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009467/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,10,10,"2023-03-07T18:00:00",null,"2023-03-08T06:00:00",null,"2 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009471/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2023,2023,25,25,"2023-06-20T18:00:00",null,"2023-06-21T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009470/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","Bezpráví",2023,2023,20,20,"2023-05-16T18:00:00",null,"2023-05-17T06:00:00",null,"2 x 12 hours","periodical","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009470/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2023,2023,20,20,"2023-05-16T18:00:00",null,"2023-05-17T06:00:00",null,"2 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009470/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,20,20,"2023-05-16T18:00:00",null,"2023-05-17T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Brandýs nad Orlicí, záhlaví 1. TK směr Ústí nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009470/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,20,20,"2023-05-16T18:00:00",null,"2023-05-17T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009469/21","Choceň - Hranice na Moravě","<>","Bezpráví","Ústí nad Orlicí",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009469/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Ústí nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003925/21","Praha - Choceň","<>","Poříčany","Sadská",2023,2023,11,13,"2023-03-14",null,"2023-03-27T23:59:59.997",null,"14 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003393/21","Choceň - Hranice na Moravě","<>","Zábřeh na Moravě","Hoštejn předjízdné koleje",2023,2023,9,9,"2023-02-28",null,"2023-02-28T23:59:59.997",null,"1 x 7 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009469/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009468/21","Choceň - Hranice na Moravě","<>","Bezpráví","Brandýs nad Orlicí",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009468/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Brandýs nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009468/21","Choceň - Hranice na Moravě","<>","Brandýs nad Orlicí","",2023,2023,15,15,"2023-04-11T18:00:00",null,"2023-04-12T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Bezpráví","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007927/21","Regensburg - Plzen","<>","Domažlice","Klenčí pod Čerchovem",2023,2023,14,14,"2023-04-05",null,"2023-04-07T23:59:59.997",null,"3 x 8 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009467/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,10,10,"2023-03-07T18:00:00",null,"2023-03-08T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Ústí nad Orlicí, záhlaví 2. TK směr Brandýs nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009467/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,10,10,"2023-03-07T18:00:00",null,"2023-03-08T06:00:00",null,"1 x 12 hours","periodical","Track & Rail","","ST","","","","","","B","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-003392/21","Choceň - Hranice na Moravě","<>","Hoštejn předjízdné koleje","Zábřeh na Moravě",2023,2023,9,9,"2023-02-27",null,"2023-02-27T23:59:59.997",null,"1 x 7 hours","periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007883/21","Regensburg - Plzen","<>","Pocinovice","Domažlice",2023,2023,11,12,"2023-03-16",null,"2023-03-23T23:59:59.997",null,"8 x 8 hours","periodical","Signal","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007808/21","Regensburg - Plzen","<>","Domažlice odb.v.401","Česká Kubice",2023,2023,7,8,"2023-02-15",null,"2023-02-22T23:59:59.997",null,"16 x 6 hours","periodical","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009466/21","Choceň - Hranice na Moravě","<>","Bezpráví","",2023,2023,5,5,"2023-01-31T18:00:00",null,"2023-02-01T06:00:00",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 2. TK směr Ústí nad Orlicí","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007808/21","Regensburg - Plzen","<>","Česká Kubice","",2023,2023,7,8,"2023-02-15",null,"2023-02-22T23:59:59.997",null,"8 x 6 hours","periodical","Miscellaneous","","ST","","","","","","B","","","celá bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007775/21","Praha - Hr. Králové - Choceň","<>","Chlumec nad Cidlinou","Dobšice nad Cidlinou",2023,2023,29,29,"2023-07-17",null,"2023-07-21T23:59:59.997",null,"5 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007228/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,13,14,"2023-03-29",null,"2023-04-04T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007227/20","Hranice na Moravě - Ostrava","<>","Polom","Suchdol nad Odrou",2023,2023,44,46,"2023-11-01",null,"2023-11-16T23:59:59.997",null,"16 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007226/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,12,12,"2023-03-25",null,"2023-03-26T23:59:59.997",null,"2 days","continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007223/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,9,9,"2023-03-04",null,"2023-03-05T23:59:59.997",null,"2 x 2 hours","periodical","Catenary","T","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-007198/20","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,46,51,"2023-11-17T18:00:00",null,"2023-12-24T06:00:00",null,"37 x 6 hours","periodical","Miscellaneous","T","LT","","","D","","","","","","1,2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009422/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,18,19,"2023-05-07",null,"2023-05-09T23:59:59.997",null,"3 x 12 hours","periodical","Miscellaneous","","ST","","","D","","","","","","zhlaví SK 2 směr Bezpráví.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009422/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,18,19,"2023-05-07",null,"2023-05-09T23:59:59.997",null,"3 x 12 hours","periodical","Miscellaneous","","ST","","","D","","","","","","2,2c jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006812/19","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín-Vrbice st.hr.","Bohumín-Vrbice",2023,2023,35,44,"2023-09-01",null,"2023-10-30T23:59:59.997",null,"60 days","continuous","Switch","T","LT","","","D","","","","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009421/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,18,18,"2023-05-01",null,"2023-05-01T23:59:59.997",null,"1 x 12 hours","periodical","Miscellaneous","","ST","","","D","","","","","","2,2c jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009414/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,15,15,"2023-04-14",null,"2023-04-15T23:59:59.997",null,"2 days","continuous","Miscellaneous","","ST","","","D","","","","","","zhlaví SK 2 směr Bezpráví.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009414/21","Choceň - Hranice na Moravě","<>","Ústí nad Orlicí","",2023,2023,15,15,"2023-04-14",null,"2023-04-15T23:59:59.997",null,"2 days","continuous","Miscellaneous","","ST","","","D","","","","","","2,2c jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009155/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,4,4,"2023-01-24",null,"2023-01-29T23:59:59.997",null,"6 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009161/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,5,6,"2023-02-01",null,"2023-02-12T23:59:59.997",null,"12 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009173/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,12,12,"2023-03-24",null,"2023-03-26T23:59:59.997",null,"3 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009176/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,15,15,"2023-04-10",null,"2023-04-11T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009178/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,20,20,"2023-05-19",null,"2023-05-19T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009179/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,23,23,"2023-06-08",null,"2023-06-08T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009180/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,33,33,"2023-08-18",null,"2023-08-19T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009182/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,38,38,"2023-09-19",null,"2023-09-19T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009183/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,39,39,"2023-09-27",null,"2023-09-27T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009184/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,43,43,"2023-10-25",null,"2023-10-25T23:59:59.997",null,"1 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009185/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,43,43,"2023-10-28",null,"2023-10-29T23:59:59.997",null,"2 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009187/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,49,49,"2023-12-04",null,"2023-12-10T23:59:59.997",null,"7 x 6 hours","periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006812/19","Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín-Vrbice","",2023,2023,35,44,"2023-09-01",null,"2023-10-30T23:59:59.997",null,"60 days","continuous","Switch","","ST","","","D","","","","","","624. bez TV, 604.-628. jen TV, 98. + TV, výh.: 606,610. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006769/19","Ostrava - Český Těšín","<>","Havířov","Ostrava-Bartovice",2023,2023,24,30,"2023-06-14",null,"2023-07-28T23:59:59.997",null,"45 days","continuous","Bridge","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006768/19","Ostrava - Český Těšín","<>","Ostrava-Bartovice","Havířov",2023,2023,18,24,"2023-05-01",null,"2023-06-14T23:59:59.997",null,"45 days","continuous","Bridge","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006645/21","Praha - Choceň","<>","Přelouč nákladní nádraží","Pardubice hlavní nádraží",2023,2023,28,33,"2023-07-15",null,"2023-08-15T23:59:59.997",null,"32 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 1. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006644/21","Praha - Choceň","<>","Přelouč nákladní nádraží","Pardubice hlavní nádraží",2023,2023,28,33,"2023-07-15",null,"2023-08-15T23:59:59.997",null,"32 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ v 1. traťové koleji mezi dopravnami .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-006455/21","Choceň - Hranice na Moravě","<>","Lanšperk","Ústí nad Orlicí",2023,2023,39,51,"2023-10-01",null,"2023-12-21T23:59:59.997",null,"82 days","continuous","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009154/21","Praha - Hr. Králové - Choceň","<>","Borohrádek","Týniště nad Orlicí",2023,2023,33,38,"2023-08-18",null,"2023-09-18T23:59:59.997",null,"32 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009154/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2023,2023,33,38,"2023-08-18",null,"2023-09-18T23:59:59.997",null,"32 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009151/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2023,2023,11,11,"2023-03-15",null,"2023-03-17T23:59:59.997",null,"3 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-009151/21","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Bolehošť",2023,2023,11,11,"2023-03-15",null,"2023-03-17T23:59:59.997",null,"3 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005741/21","Ostrava - Český Těšín","<>","Albrechtice u Českého Těšína","Havířov",2023,2023,34,35,"2023-08-21",null,"2023-08-28T23:59:59.997",null,"8 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005740/21","Ostrava - Český Těšín","<>","Havířov","Albrechtice u Českého Těšína",2023,2023,33,33,"2023-08-15",null,"2023-08-20T23:59:59.997",null,"6 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005478/21","Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2023,2023,14,14,"2023-04-04",null,"2023-04-05T23:59:59.997",null,"2 x 8 hours","periodical","Track & Rail","","LT","","","","","","","","","2. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005713/21","Nürnberg - Plzen","<>","Tršnice","Cheb",2023,2023,21,21,"2023-05-28",null,"2023-05-28T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","2. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005473/21","Nürnberg - Plzen","<>","Cheb","Lipová u Chebu",2023,2023,14,14,"2023-04-03",null,"2023-04-04T23:59:59.997",null,"2 x 2 hours","periodical","Track & Rail","","LT","","","","","","","","","1. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005713/21","Nürnberg - Plzen","<>","Cheb","Tršnice",2023,2023,21,21,"2023-05-28",null,"2023-05-28T23:59:59.997",null,"1 x 6 hours","periodical","Track & Rail","","LT","","","","","","","","","1. bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005643/21","Nürnberg - Plzen","<>","Cheb","Schirnding",2023,2023,15,15,"2023-04-13",null,"2023-04-14T23:59:59.997",null,"2 x 2 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005711/21","Nürnberg - Plzen","<>","Cheb","Františkovy Lázně",2023,2023,21,21,"2023-05-24",null,"2023-05-24T23:59:59.997",null,"1 x 8 hours","periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005711/21","Nürnberg - Plzen","<>","Cheb","",2023,2023,21,21,"2023-05-24",null,"2023-05-24T23:59:59.997",null,"1 x 8 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví směr Františkovy Lázně, jeho část od návěstidla FS po námezník výh. č. 88.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005643/21","Nürnberg - Plzen","<>","Cheb","",2023,2023,15,15,"2023-04-13",null,"2023-04-14T23:59:59.997",null,"2 x 2 hours","periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví směr Schirnding, od návěstidla PS po návěstidlo Se15.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005466/21","Nürnberg - Plzen","<>","Cheb","Františkovy Lázně",2023,2023,11,11,"2023-03-13",null,"2023-03-17T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005466/21","Nürnberg - Plzen","<>","Cheb","Františkovy Lázně",2023,2023,11,11,"2023-03-13",null,"2023-03-17T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. přejezdové v km 71,603 (P323), v km 70,796 (P322), v km 70,080 (P321) .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005465/21","Nürnberg - Plzen","<>","Tršnice","Cheb",2023,2023,10,10,"2023-03-06",null,"2023-03-10T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ 1.,2..","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-005465/21","Nürnberg - Plzen","<>","Tršnice","Cheb",2023,2023,10,10,"2023-03-06",null,"2023-03-10T23:59:59.997",null,"5 days","continuous","Signal","","LT","","","","","","","","","zab. zař. přejezdové v km 234,565 (P100) a v km 233,121 (P99) .","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008797/21","Praha - Hr. Králové - Choceň","<>","Velký Osek","Libice nad Cidlinou",2023,2023,36,37,"2023-09-04",null,"2023-09-13T23:59:59.997",null,"10 days","continuous","Catenary","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008776/21","Praha - Hr. Králové - Choceň","<>","Libice nad Cidlinou","Velký Osek",2023,2023,33,34,"2023-08-14",null,"2023-08-23T23:59:59.997",null,"10 days","continuous","Catenary","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-008764/21","Praha - Hr. Králové - Choceň","<>","Velký Osek","Libice nad Cidlinou",2023,2023,31,31,"2023-08-03",null,"2023-08-04T23:59:59.997",null,"2 x 10 hours","periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-024993/19","Hranice na Moravě - Žilina","<>","Jablůnka","Vsetín",2023,2023,28,30,"2023-07-12",null,"2023-07-25T23:59:59.997",null,"14 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023891/19","Hranice na Moravě - Ostrava","<>","Polom","Suchdol nad Odrou",2023,2023,13,13,"2023-03-31",null,"2023-04-01T23:59:59.997",null,"2 x 2 hours","periodical","Miscellaneous","T","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023857/19","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,29,44,"2023-07-19",null,"2023-10-31T23:59:59.997",null,"105 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023797/19","Hranice na Moravě - Ostrava","<>","Polom","Suchdol nad Odrou",2023,2023,14,29,"2023-04-05",null,"2023-07-17T23:59:59.997",null,"104 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023795/19","Hranice na Moravě - Ostrava","<>","Suchdol nad Odrou","Polom",2023,2023,10,13,"2023-03-08",null,"2023-03-28T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023794/19","Hranice na Moravě - Ostrava","<>","Polom","Suchdol nad Odrou",2023,2023,7,10,"2023-02-15",null,"2023-03-07T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023254/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2023,2023,23,29,"2023-06-08",null,"2023-07-17T23:59:59.997",null,"40 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023254/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,23,29,"2023-06-08",null,"2023-07-17T23:59:59.997",null,"40 days","continuous","Miscellaneous","","ST","","","","","","B","","","záhlaví směr Třebechovice p. O.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023254/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","",2023,2023,23,29,"2023-06-08",null,"2023-07-17T23:59:59.997",null,"40 days","continuous","Miscellaneous","","ST","","","","","","B","","","1,2 + TV. \nzhlaví směr Třebechovice p. O..","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023248/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Bolehošť",2023,2023,15,20,"2023-04-10",null,"2023-05-19T23:59:59.997",null,"40 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023240/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Častolovice",2023,2023,12,12,"2023-03-24",null,"2023-03-26T23:59:59.997",null,"3 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-023240/18","Praha - Hr. Králové - Choceň","<>","Týniště nad Orlicí","Borohrádek",2023,2023,12,12,"2023-03-24",null,"2023-03-26T23:59:59.997",null,"3 days","continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022120/20","Plzen - Praha","<>","Plzeň hlavní nádraží","Dobřany",2023,2023,38,41,"2023-09-22",null,"2023-10-10T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022118/20","Regensburg - Plzen","<>","Vejprnice","Nýřany",2023,2023,15,17,"2023-04-14",null,"2023-04-25T23:59:59.997",null,"12 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022118/20","Regensburg - Plzen","<>","Nýřany","",2023,2023,15,17,"2023-04-14",null,"2023-04-25T23:59:59.997",null,"12 days","continuous","Track & Rail","","ST","","","","","","B","","","celá bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022117/20","Regensburg - Plzen","<>","Nýřany","Stod",2023,2023,17,18,"2023-04-26",null,"2023-05-07T23:59:59.997",null,"12 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022116/20","Regensburg - Plzen","<>","Stod","Holýšov",2023,2023,31,33,"2023-07-31",null,"2023-08-18T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022115/20","Regensburg - Plzen","<>","Holýšov","Staňkov",2023,2023,31,33,"2023-07-31",null,"2023-08-18T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022114/20","Regensburg - Plzen","<>","Blížejov","Domažlice",2023,2023,31,33,"2023-07-31",null,"2023-08-18T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022113/20","Nürnberg - Plzen","<>","Svojšín","Bor",2023,2023,42,45,"2023-10-21",null,"2023-11-09T23:59:59.997",null,"20 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022113/20","Nürnberg - Plzen","<>","Svojšín","",2023,2023,42,45,"2023-10-21",null,"2023-11-09T23:59:59.997",null,"20 days","continuous","Track & Rail","","ST","","","","","","B","","","záhlaví směr Bor","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022112/20","Regensburg - Plzen","<>","Domažlice odb.v.401","Klenčí pod Čerchovem",2023,2023,14,16,"2023-04-03",null,"2023-04-21T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022107/20","Regensburg - Plzen","<>","Staňkov bývalá Odb Vránov","Horšovský Týn",2023,2023,28,30,"2023-07-10",null,"2023-07-28T23:59:59.997",null,"19 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-022094/20","Nürnberg - Plzen","<>","Pňovany","Trpísty",2023,2023,18,22,"2023-05-02",null,"2023-05-31T23:59:59.997",null,"30 days","continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021954/19","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2023,2023,2,5,"2023-01-11",null,"2023-01-31T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. 1,2.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021954/19","Plzen - Praha","<>","Praha-Radotín","Tunel odb.",2023,2023,2,5,"2023-01-11",null,"2023-01-31T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. 3,4.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021373/20","Praha - Choceň","<>","Poříčany","Český Brod",2023,2023,33,33,"2023-08-14",null,"2023-08-17T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021372/20","Praha - Choceň","<>","Český Brod","Úvaly",2023,2023,32,32,"2023-08-10",null,"2023-08-13T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021371/20","Praha - Choceň","<>","Úvaly","Praha-Běchovice",2023,2023,31,32,"2023-08-06",null,"2023-08-09T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021370/20","Praha - Choceň","<>","Praha-Běchovice","Praha-Libeň",2023,2023,31,31,"2023-08-02",null,"2023-08-05T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021368/20","Praha - Choceň","<>","Český Brod","Poříčany",2023,2023,30,31,"2023-07-29",null,"2023-08-01T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021367/20","Praha - Choceň","<>","Úvaly","Český Brod",2023,2023,30,30,"2023-07-25",null,"2023-07-28T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021366/20","Praha - Choceň","<>","Praha-Běchovice","Úvaly",2023,2023,29,30,"2023-07-21",null,"2023-07-24T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021365/20","Praha - Choceň","<>","Praha-Libeň","Praha-Běchovice",2023,2023,29,29,"2023-07-17",null,"2023-07-20T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021364/20","Praha - Choceň","<>","Český Brod","Poříčany",2023,2023,28,28,"2023-07-13",null,"2023-07-16T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021363/20","Praha - Choceň","<>","Úvaly","Český Brod",2023,2023,27,28,"2023-07-09",null,"2023-07-12T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021362/20","Praha - Choceň","<>","Praha-Běchovice","Úvaly",2023,2023,27,27,"2023-07-05",null,"2023-07-08T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-021361/20","Praha - Choceň","<>","Praha-Libeň","Praha-Běchovice",2023,2023,26,27,"2023-07-01",null,"2023-07-04T23:59:59.997",null,"4 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020678/19","Plzen - Praha","<>","Praha-Smíchov","Praha-Radotín",2023,2023,10,11,"2023-03-08",null,"2023-03-14T23:59:59.997",null,"7 days","continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020677/19","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2023,2023,10,10,"2023-03-06",null,"2023-03-07T23:59:59.997",null,"2 days","continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020675/19","Plzen - Praha","<>","Praha-Radotín","Praha-Smíchov",2023,2023,44,45,"2023-11-01",null,"2023-11-09T23:59:59.997",null,"9 days","continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020125/20","Praha - Choceň","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2023,2023,41,48,"2023-10-13",null,"2023-12-01T23:59:59.997",null,"50 days","continuous","Miscellaneous","T","LT","","","","","","B","","","2,1 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020026/20","Praha - Choceň","<>","Pardubice hlavní nádraží","Přelouč",2023,2023,26,29,"2023-07-02",null,"2023-07-22T23:59:59.997",null,"21 days","continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020011/20","Praha - Choceň","<>","Pardubice hlavní nádraží","",2023,2023,5,22,"2023-02-01",null,"2023-06-01T23:59:59.997",null,"121 days","continuous","Miscellaneous","","ST","","","D","","","","","","1,1a,3,5,9,7,11,19a + TV. ","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,54,"V-020011/20","Praha - Choceň","<>","Pardubice hlavní nádraží","",2023,2023,5,22,"2023-02-01",null,"2023-06-01T23:59:59.997",null,"121 days","continuous","Miscellaneous","","ST","","","D","","","","","","zhlaví SK 1 směr Přelouč po výh. č. 88.","","","","2021-06-25","unclassified",null,null,null,null,null,null,"publication",null,"Y"]
[null,53,null,"Arad - Brașov","< >","Barzava","Conop",null,null,null,null,"2017-09-25",null,"2022-06-14",null,1723,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Conop ","Milova",null,null,null,null,"2019-03-01",null,"2022-06-14",null,1201,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Barzava","Milova",null,null,null,null,"2022-06-08",null,"2022-06-14",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Barzava","Milova",null,null,null,null,"2022-06-14",null,"2023-03-08",null,267,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Milova","Radna",null,null,null,null,"2018-03-06",null,"2021-07-05",null,1217,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Milova","Radna",null,null,null,null,"2021-07-05",null,"2023-03-08",null,611,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Conop","Radna",null,null,null,null,"2021-06-29",null,"2021-07-05",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Radna","Paulis",null,null,null,null,"2020-09-30",null,"2021-11-10",null,406,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Radna","Paulis",null,null,null,null,"2022-06-14",null,"2023-03-08",null,267,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Paulis","Ghioroc",null,null,null,null,"2020-09-30",null,"2021-11-10",null,406,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Radna","Ghioroc",null,null,null,null,"2021-11-04",null,"2021-11-10",null,6,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilteu","Savarsin",null,null,null,null,"2019-02-06",null,"2021-04-21",null,805,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Ilteu","Savarsin",null,null,null,null,"2021-04-21",null,"2022-06-10",null,415,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin"," Varadia",null,null,null,null,"2018-03-29",null,"2021-08-19",null,1239,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Varadia","Batuta",null,null,null,null,"2019-02-27",null,"2022-10-04",null,1315,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Varadia","Batuta",null,null,null,null,"2022-10-04",null,"2023-06-22",null,261,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Batuta","Barzava",null,null,null,null,"2022-10-04",null,"2023-06-22",null,261,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Barzava","Barzava Noua",null,null,null,null,"2019-06-19",null,"2023-06-22",null,1464,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Barzava","Barzava Noua",null,null,null,null,"2019-06-19",null,"2022-10-04",null,1203,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Barzava","Barzava Noua",null,null,null,null,"2022-10-04",null,"2023-06-22",null,261,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Varadia","Barzava Noua",null,null,null,null,"2022-09-27",null,"2022-10-04",null,7,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Barzava Noua","Milova",null,null,null,null,"2022-09-27",null,"2022-10-04",null,7,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilteu","Savarsin",null,null,null,null,"2021-02-24",null,"2021-02-24",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilteu","Savarsin",null,null,null,null,"2021-04-15",null,"2021-04-21",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilteu","Savarsin",null,null,null,null,"2021-04-21",null,"2022-06-10",null,415,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2018-03-29",null,"2021-08-19",null,1239,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2021-08-12",null,"2021-08-18",null,8,"continuous","Track & Rail","T","LT",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2021-08-19",null,"2022-06-10",null,295,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2022-06-03",null,"2022-06-10",null,7,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2022-06-10",null,"2023-02-20",null,255,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Savarsin","Varadia",null,null,null,null,"2023-02-14",null,"2023-02-20",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Gurasada","Ilteu",null,null,null,null,"2020-03-11",null,"2022-03-14",null,734,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Gurasada","Ilteu",null,null,null,null,"2022-04-06",null,"2022-09-16",null,163,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Simeria","Deva",null,null,null,null,"2020-04-23",null,"2023-03-30",null,1071,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Simeria","Deva",null,null,null,null,"2021-10-01",null,"2021-10-01",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Deva","Mintia",null,null,null,null,"2019-06-22",null,"2023-03-30",null,1377,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Mintia",null,null,null,null,"2021-06-30",null,"2021-10-25",null,117,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Mintia",null,null,null,null,"2021-10-25",null,"2021-10-25",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Mintia",null,null,null,null,"2021-10-25",null,"2022-08-08",null,287,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >"," Branisca ","Mintia",null,null,null,null,"2022-08-08",null,"2022-08-13",null,5,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Ilia",null,null,null,null,"2020-01-07",null,"2021-09-08",null,610,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Ilia",null,null,null,null,"2021-09-08",null,"2022-08-08",null,334,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Branisca","Ilia",null,null,null,null,"2022-08-08",null,"2022-08-13",null,5,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilia","Gurasada",null,null,null,null,"2020-08-05",null,"2021-09-08",null,399,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Ilia"," Gurasada",null,null,null,null,"2021-05-19",null,"2022-07-28",null,435,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"A (Z ≥ 30 zile; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Ilia","Gurasada",null,null,null,null,"2022-07-28",null,"2022-11-04",null,99,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Gurasada","Campuri",null,null,null,null,"2021-09-08",null,"2021-09-08",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Brasov","Stupini",null,null,null,null,"01.09.2020",null,"20.07.2021",null,322,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Brasov","Stupini",null,null,null,null,"21.07.2021",null,"15.02.2022",null,209,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"01.09.2020",null,"20.07.2021",null,322,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"15.07.2021",null,"20.07.2021",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"21.07.2021",null,"04.11.2022",null,477,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"2022-10-30",null,"04.11.2022",null,6,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"05.11.2022",null,"05.05.2023",null,182,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"05.05.2023",null,"14.06.2023",null,41,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Stupini","Bod",null,null,null,null,"15.06.2023",null,"30.08.2023",null,77,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Feldioara","Apata",null,null,null,null,"21.07.2021",null,"15.02.2022",null,209,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Feldioara","Apata",null,null,null,null,"21.07.2021",null,"15.02.2022",null,210,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Feldioara","Apata",null,null,null,null,"16.02.2022",null,"30.08.2023",null,560,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Feldioara","Apata",null,null,null,null,"30.08.2023",null,"15.05.2024",null,259,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Feldioara","Apata",null,null,null,null,"16.05.2024",null,"24.06.2024",null,40,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Brasov","Bartolomeu ",null,null,null,null,"04.06.2021",null,"04.06.2021",null,1,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"C (Z ≤ 7days; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"16.02.2022",null,"03.03.2022",null,16,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"04.03.2022",null,"04.11.2022",null,245,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"30.10.2022",null,"04.11.2022",null,6,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"05.11.2022",null,"05.05.2023",null,181,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"05.05.2023",null,"14.06.2023",null,41,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A (Z ≥ 30 zile; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"15.06.2023",null,"30.08.2023",null,76,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"30.08.2023",null,"15.05.2024",null,259,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Bod","Feldioara",null,null,null,null,"16.05.2024",null,"24.06.2024",null,40,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"24.11.2021",null,"30.11.2021",null,7,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"01.12.2021",null,"09.11.2022",null,344,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"10.11.2022",null,"15.08.2023",null,278,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"16.08.2023",null,"10.03.2024",null,105,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"11.03.2024",null,"30.05.2024",null,81,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"01.12.2021",null,"09.11.2022",null,344,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"16.08.2023",null,"10.03.2024",null,105,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Mureni","Vanatori",null,null,null,null,"10.11.2022",null,"15.08.2023",null,278,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"16.04.2021",null,"30.11.2021",null,228,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"01.12.2021",null,"07.08.2022",null,250,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"08.08.2022",null,"09.11.2022",null,458,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"10.11.2022",null,"15.02.2023",null,98,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"10.11.2022",null,"15.08.2023",null,278,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Vanatori","Albesti",null,null,null,null,"16.08.2023",null,"10.03.2024",null,205,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"16.04.2021",null,"30.11.2021",null,228,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"2022-05-01",null,"2022-05-31",null,31,"continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A (Z ≥ 30 zile; Y ≥ 50%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"01.12.2021",null,"07.08.2022",null,249,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"08.08.2022",null,"09.11.2022",null,94,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"01.12.2021",null,"07.08.2022",null,250,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Albesti","Sighisoara",null,null,null,null,"08.08.2022",null,"09.11.2022",null,93,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Cata","Beia",null,null,null,null,"08.08.2022",null,"08.09.2022",null,31,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Cata","Beia",null,null,null,null,"09.09.2022",null,"15.02.2023",null,160,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Cata","Beia",null,null,null,null,"11.03.2024",null,"30.05.2024",null,81,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Cata","Beia",null,null,null,null,"16.02.2023",null,"10.03.2024",null,388,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Beia","Mureni",null,null,null,null,"10.11.2022",null,"15.02.2023",null,97,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Beia","Mureni",null,null,null,null,"10.11.2022",null,"15.02.2023",null,98,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Beia","Mureni",null,null,null,null,"11.03.2024",null,"30.05.2024",null,81,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Beia","Mureni",null,null,null,null,"16.02.2023",null,"10.03.2024",null,388,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Beia","Mureni",null,null,null,null,"16.02.2023",null,"10.03.2024",null,388,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,null,null,null,null,"B (Z > 7 days; Y ≥ 30%) "]
[null,53,null,"Arad - Brașov","< >","Rupea","Cata",null,null,null,null,"2021-06-01",null,"2024-04-01",null,1033,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,null,"Arad - Brașov","< >","Augustin","Rupea",null,null,null,null,"2022-01-10",null,"2024-12-10",null,1054,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,null,"Arad - Brașov","< >","Apata","Augustin",null,null,null,null,"2022-04-05",null,"2023-02-06",null,303,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,56,561812005,"Hranice na Moravě - Žilina","< >","Púchov","Považská Bystrica",2021,2021,1,37,"2021-01-01","00:00:00","2021-09-16",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",54,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"publication",null,"Y"]
[null,56,561812006,"Hranice na Moravě - Žilina","< >","Púchov","Považská Bystrica",2021,2021,37,50,"2021-09-16","00:00:00","2021-12-15",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",54,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"publication",null,"Y"]
[null,56,562012001,"Hranice na Moravě - Žilina","< >","Považská Bystrica","Považská Bystrica",2021,2021,49,50,"2021-12-08","00:00:00","2021-12-15",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 1,3",54,"Y",null,"2021-06-18","medium",null,null,null,null,null,null,"publication",null,"Y"]
[null,56,562101011,"Žilina - Košice","< >","Svit","Výh. Lučivná",2021,2021,30,38,"2021-07-29","00:00:00","2021-09-21",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"publication",null,"Y"]
[null,56,562101013,"Žilina - Košice","< >","Svit","Výh. Lučivná",2021,2021,38,45,"2021-09-22","00:00:00","2021-11-10",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"publication",null,"Y"]
[null,56,562106002,"Žilina - Košice","< >","Svit","Svit",2021,2022,45,16,"2021-11-11","00:00:00","2022-04-20",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 2, 4, 6",null,"Y",null,null,"unclassified",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101016,"Žilina - Košice","< >","Svit","Svit",2022,2022,16,26,"2022-04-21","00:00:00","2022-06-29",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 1,3,5",null,"Y",null,"2021-06-18","medium",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101017,"Žilina - Košice","< >","Svit","Svit",2022,2022,26,27,"2022-06-30","00:00:00","2022-07-07",1,null,"continuous","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"modernization, track 2,4,6",null,"Y",null,"2021-06-18","medium",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101018,"Žilina - Košice","< >","Svit","Výh. Lučivná",2022,2022,16,26,"2022-04-21","00:00:00","2022-06-29",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101019,"Žilina - Košice","< >","Svit","Výh. Lučivná",2022,2022,26,27,"2022-06-30","00:00:00","2022-07-07",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 2",null,"Y",null,"2021-06-18","major",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101020,"Žilina - Košice","< >","Svit","Štrba",2022,2022,27,27,"2022-07-08","00:00:00","2022-07-10",1,null,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization, track 1",null,"Y",null,"2021-06-18","minor",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562101021,"Žilina - Košice","< >","Svit","Štrba",2022,2022,28,28,"2022-07-11","00:00:00","2022-07-13","00:00:00",null,"continuous","Track & Rail",null,"LT","s",null,null,null,null,null,null,null,"modernisation, track 2",null,"Y",null,"2021-06-18","minor",null,null,null,null,null,null,"planned",null,"Y"]
[null,56,562106004,"Hranice na Moravě - Žilina","<","Púchov","Považská Bystrica",2022,2022,9,22,"2022-03-01",null,"2022-05-31",null,null,"continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Modernisation",null,"Y",null,null,"major",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562106001,"Hranice na Moravě - Žilina","< >","Púchov","Dolný Hričov",2021,2021,39,43,null,null,null,null,"14 days","periodical","Maintenance",null,"LT","S",null,null,null,null,null,null,null,"OGPK",null,"N",null,null,"minor",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562106002,"Parndorf - Bratislava","< >","Bratislava ÚNS","Bratislava ÚNS",2021,2021,35,39,null,null,null,null,"10 days","continuous","Maintenance",null,"ST","S",null,null,null,null,null,null,null,"OKLV",null,"N",null,null,"minor",null,null,null,null,null,null,"Planned",null,"Y"]
[null,56,562106003,"Parndorf - Bratislava","< >","Bratislava ÚNS","Bratislava ÚNS",2021,2021,35,39,null,null,null,null,"8 days","periodical","Maintenance",null,"ST","S",null,null,null,null,null,null,null,"OKLV",null,"N",null,null,"minor",null,null,null,null,null,null,"Planned",null,"Y"]

{"sheet":"Graphic Overview","index":2,"n_rows":1063,"n_cols":375,"rows_kept":1063,"cut":false,"hidden":false,"merged":[[3,306,3,312],[3,313,3,319],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,271,3,277],[3,278,3,284],[3,285,3,291],[3,292,3,298],[3,299,3,305],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,282,2,312],[2,313,2,342],[2,343,2,373],[3,159,3,165],[3,166,3,172],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,194,3,200],[3,201,3,207],[3,341,3,347],[3,348,3,354],[3,355,3,361],[3,362,3,368],[3,369,3,373],[3,215,3,221],[3,222,3,228],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,229,3,235],[3,208,3,214],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,138,3,144],[3,145,3,151],[3,33,3,39],[2,129,2,159],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[3,68,3,74],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128],[3,257,3,263],[3,264,3,270],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,103,3,109],[3,110,3,116],[3,152,3,158],[3,236,3,242],[3,243,3,249],[3,250,3,256]]}
[null,"Rhine-Danube, Overview"]
[]
[null,null,null,null,null,null,2021,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-12-12","2022-07-29T18:00:00","229 d, 18 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-09-26T22:00:00","2021-09-27T05:00:00","7 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-09-30T08:00:00","2021-10-05T08:59:00","5 d, 01 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-05T05:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Partenstein - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Nantenbach - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Nantenbach - Partenstein",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Weinheim (Bergstr) - Weinheim (Bergstr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-01T01:00:00","2021-02-05T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-08T05:00:00","2021-02-12T21:00:00","4 d, 16 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-15T01:00:00","2021-02-19T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Neu-Edingen/Mhm-Friedrichsfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-05-27","2021-06-18T23:59:00","23 d","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Heidelberg-Wieblingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-06-04T21:00:00","2021-06-08T04:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Nord - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-01-15T23:30:00","2021-01-18T01:30:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-13T00:30:00","2021-02-15T13:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-15T13:00:00","2021-11-09T23:45:00","267 d, 11 h","DB Netz AG"]
[]
[null,"Dieburg - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-22T09:00:00","2021-11-15T23:59:00","10 d, 15 h","DB Netz AG"]
[]
[null,"Dieburg - Messel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Messel - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt-Kranichstein - Babenhausen (Hess)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-24T23:30:00","2021-11-07T05:30:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-01T08:00:00","2021-11-16T06:00:00","14 d, 22 h","DB Netz AG"]
[]
[null,"Mainaschaff Abzw - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T21:00:00","2021-11-16T05:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T22:00:00","2021-11-16T06:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T23:45:00","2021-11-17T04:45:00","7 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-15T06:00:00","2021-11-30T06:00:00","15 d","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-22T05:00:00","2021-11-26T22:00:00","4 d, 17 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Stuttgart Hbf - Stuttgart-Zuffenhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Ebersbach (Fils) - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-25T22:00:00","2021-01-26T04:30:00","7 h","DB Netz AG"]
[]
[null,"Stuttgart-Bad Cannstatt - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-04T21:00:00","2021-02-08T05:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Geislingen (Steige) - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-09T21:00:00","2021-02-12T05:00:00","1 d","DB Netz AG"]
[]
[null,"Ulm Hbf - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-02-28T23:30:00","2021-03-02T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-02T23:30:00","2021-03-14T04:30:00","11 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm-Örlingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-14T23:00:00","2021-03-25T04:30:00","10 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-15T22:00:00","2021-03-22T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Ulm-Örlingen - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-25T23:30:00","2021-03-27T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19","2021-08-09T04:00:00","21 d, 04 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-02T01:00:00","2021-08-13T22:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Ulm Hbf Em Nord - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T20:00:00","2021-08-16T04:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Amstetten (Württ) - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-16T22:00:00","3 d","DB Netz AG"]
[]
[null,"Göppingen - Eislingen (Fils)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-27T04:00:00","13 d, 06 h","DB Netz AG"]
[]
[null,"Geislingen West - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Uhingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-26T22:00:00","2021-08-27T04:00:00","6 h","DB Netz AG"]
[]
[null,"Eislingen (Fils) - Gingen (Fils) Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-27T22:00:00","2021-09-03T22:00:00","7 d","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-29T22:30:00","2021-02-02T05:15:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:00:00","2021-04-24T05:20:00","14 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:20:00","2021-04-12T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:00:00","2021-05-10T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:30:00","2021-05-10T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-14T22:30:00","2021-05-17T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-07","2021-08-09T04:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Burgau (Schwab)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Unterfahlheim - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Nersingen - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-29","2021-12-04T05:00:00","5 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Mannheim Hbf Ost - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-02-06T02:35:00","2021-02-08T04:35:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Mannheim-Rheinau - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-06-20T22:00:00","2021-08-03T04:00:00","43 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-07-28T22:00:00","2021-08-03T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-08-03T04:00:00","2021-09-13T04:00:00","41 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-07T21:00:00","2021-08-23T05:00:00","2 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-09T23:00:00","2021-08-21T05:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Schwetzingen - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Oftersheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-08T22:00:00","2021-09-16T06:00:00","7 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Waghäusel - Waghäusel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Graben-Neudorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-03-08","2021-03-23T23:59:00","16 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Forchheim (b Karlsruhe) - Durmersheim Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-05-13T00:01:00","2021-05-17T04:30:00","4 d, 04 h","DB Netz AG"]
[]
[null,"Karlsruhe Hbf Bft Südeinfahrt - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-07-19T23:00:00","2021-08-07T05:00:00","3 d, 18 h","DB Netz AG"]
[]
[null,"Durmersheim Nord - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-20T23:00:00","2021-08-23T05:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bashaide - Karlsruhe Hbf Bft Südeinfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-30T23:00:00","2021-11-08T04:30:00","69 d, 05 h","DB Netz AG"]
[]
[null,"Durmersheim - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-03T22:00:00","2021-10-29T05:00:00","25 d, 07 h","DB Netz AG"]
[]
[null,"Durmersheim - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-29T23:00:00","2021-11-02T04:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Pforzheim Hbf - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Vaihingen (Enz) - Vaihingen (Enz)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-03-18","2021-05-03T23:59:00","47 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-07","2021-05-11T23:59:00","5 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-08T02:00:00","2021-05-10T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Sachsenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Sachsenheim - Tamm (Württ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-03-02T22:00:00","2021-03-06T04:30:00","1 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Karlshöhe - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-22T01:45:00","2021-06-07T04:00:00","16 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Pbf - Kornwestheim Karlshöhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-07T08:00:00","2021-09-07T16:00:00","8 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-10-23T01:45:00","2021-10-25T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-06T23:00:00","2021-12-11T23:59:00","308 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-22T08:00:00","2021-12-11T23:59:00","292 d, 16 h","DB Netz AG"]
[]
[null,"Appenweier-Muhrhaag - Appenweier Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-12T23:35:00","2021-03-15T04:15:00","2 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-29T00:15:00","2021-04-02T00:15:00","4 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T00:15:00","2021-04-06T03:00:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-08-30","149 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-05-24T23:00:00","2021-07-01T04:30:00","37 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-08-30","2021-11-08T04:30:00","70 d, 04 h","DB Netz AG"]
[]
[null,"Appenweier Nord - Appenweier Kurve",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-03-27T00:30:00","2021-03-29T04:30:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-04-23T07:00:00","2021-05-05T17:00:00","12 d, 10 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-04T00:45:00","2021-07-04T06:45:00","6 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-09T23:00:00","2021-07-17T05:00:00","7 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-10T22:00:00","2021-07-11T06:45:00","9 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-07-11T22:00:00","2021-07-14T04:40:00","20 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-25T00:45:00","2021-07-25T06:45:00","6 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-09-27T07:00:00","2021-10-25T18:00:00","28 d, 11 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T07:00:00","2021-10-05T17:00:00","4 d, 10 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-01T22:00:00","2021-10-04T04:50:00","21 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-04T22:00:00","2021-10-12T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-16","2021-10-18T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-20T05:00:00","2021-10-25T05:00:00","5 d","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-20T22:00:00","2021-10-25T05:00:00","21 h","DB Netz AG"]
[]
[null,"München-Lochhausen - München-Pasing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-22T22:00:00","2021-03-27T05:40:00","4 d, 08 h","DB Netz AG"]
[]
[null,"München-Pasing - München-Lochhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-03-22T22:45:00","2021-03-27T05:20:00","1 d, 09 h","DB Netz AG"]
[]
[null,"München-Pasing - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Rosenheim - Rosenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-03-10T00:40:00","2021-03-14T02:40:00","4 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-09T02:00:00","2021-11-23T04:00:00","14 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-23T04:00:00","2021-12-11T23:59:00","18 d, 20 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-05","2021-02-08T04:50:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-12T00:25:00","2021-02-15T05:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-14T19:10:00","2021-02-15T04:10:00","9 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical continuous","2021-02-21T00:25:00","2021-03-01T04:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-06T22:20:00","2021-03-07T05:20:00","7 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-07T22:00:00","2021-03-08T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-11T21:40:00","2021-03-12T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-13T22:20:00","2021-03-15T04:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-19T16:00:00","2021-03-21T16:00:00","2 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-03-20T22:20:00","2021-03-21T05:10:00","7 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-04-01T23:30:00","2021-04-06T06:00:00","4 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-04-09T23:30:00","2021-05-17T06:00:00","13 d, 15 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-21T23:30:00","2021-05-25T06:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Postbauer-Heng - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-05-27T01:00:00","2021-06-21T05:00:00","25 d, 04 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-05T21:00:00","2021-06-26T05:00:00","20 d, 08 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-07T21:00:00","2021-06-19T04:00:00","2 d, 22 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Postbauer-Heng",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical","2021-06-07T22:00:00","2021-06-10T05:00:00","21 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-12T20:30:00","2021-06-20T04:30:00","1 d","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-06-19","2021-07-04T23:50:00","16 d","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-26T23:30:00","2021-06-28T06:00:00","1 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-07-02T23:30:00","2021-08-02T06:00:00","11 d, 09 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-07-29T23:00:00","2021-08-02T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-08-02T23:00:00","2021-08-06T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Ost",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-06T00:30:00","2021-11-11T00:30:00","5 d","DB Netz AG"]
[]
[null,"Sünching - Mangolding",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-07T01:30:00","2021-11-11T00:30:00","3 d, 23 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-05T09:00:00","2021-03-07T12:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-12T09:00:00","2021-03-15T12:00:00","3 d, 03 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T01:00:00","2021-05-02T05:00:00","6 d, 04 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T04:00:00","2021-05-02T02:00:00","5 d, 22 h","DB Netz AG"]
[]
[null,"Köfering - Eggmühl",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-28T01:00:00","2021-05-29T13:00:00","1 d, 12 h","DB Netz AG"]
[]
[null,"Eggmühl - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-29T13:00:00","2021-05-31T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-04T23:00:00","2021-06-08T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-05T03:00:00","2021-06-05T17:00:00","14 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-10T23:00:00","2021-06-14T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-11T03:00:00","2021-06-11T17:00:00","14 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-16T14:00:00","2021-06-18T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-18T22:00:00","2021-06-21T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-23T14:00:00","2021-06-25T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-25T22:00:00","2021-06-28T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-07-04T01:00:00","2021-07-04T11:00:00","10 h","DB Netz AG"]
[]
[null,"München Kanal - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Köfering - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-09-19T01:00:00","2021-10-03T05:00:00","14 d, 04 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T22:00:00","2021-10-23T05:00:00","11 d, 07 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-23T22:00:00","2021-11-01T04:00:00","8 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-11-01T22:00:00","2021-11-07T05:00:00","5 d, 07 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Richtungsgruppe Süd - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-05T14:00:00","2021-04-06T09:00:00","19 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-10T12:00:00","2021-04-12T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-12T15:00:00","2021-04-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-04-17T12:00:00","2021-05-31T15:00:00","14 d, 21 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-04-19T15:00:00","2021-05-04T06:00:00","1 d, 21 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-05-10T15:00:00","2021-06-01T06:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-05T12:00:00","2021-06-14T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-07T15:00:00","2021-06-15T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-19T12:00:00","2021-06-28T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-21T15:00:00","2021-06-29T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-03T12:00:00","2021-07-05T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-05T15:00:00","2021-07-06T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-10T12:00:00","2021-07-19T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-12T15:00:00","2021-07-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19T15:00:00","2021-07-20T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-24T12:00:00","2021-07-26T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-26T15:00:00","2021-07-27T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-31T12:00:00","2021-08-09T15:00:00","2 d, 20 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-31T12:00:00","2021-08-10T06:00:00","5 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-14T12:00:00","2021-09-13T15:00:00","7 d, 02 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-08-14T12:00:00","2021-09-14T06:00:00","13 d, 18 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-07","2021-10-11T22:00:00","4 d, 22 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-11T22:00:00","2021-10-17T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"München-Freimann - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-30T00:30:00","2021-11-03T03:30:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-01-25T22:30:00","2021-05-24T05:00:00","118 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T15:00:00","2021-04-03T20:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T22:30:00","2021-04-05T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-03T20:00:00","2021-04-04T10:00:00","14 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-04T10:00:00","2021-04-05T15:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:00:00","2021-04-10T04:00:00","6 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:30:00","2021-04-12T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-10T04:00:00","2021-04-11T10:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-11T10:00:00","2021-04-12T16:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-16T22:30:00","2021-04-19T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-17T05:00:00","2021-04-17T20:00:00","15 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-05-25T22:30:00","2021-08-13T05:00:00","79 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-02T05:00:00","9 d, 11 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-03T18:00:00","11 d","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:00:00","2021-09-02T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:30:00","2021-09-02T04:00:00","6 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Seligenstadt (b Würzburg)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:45:00","2021-08-30T04:15:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-27T22:30:00","2021-08-30T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Wernfeld - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-16T08:00:00","2021-02-23T16:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Eußenheim - Wernfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-24T08:00:00","2021-03-04T16:00:00","2 d","DB Netz AG"]
[]
[null,"Eußenheim - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-08T08:00:00","2021-03-09T16:00:00","16 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-10T08:00:00","2021-03-16T16:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-17T08:00:00","2021-03-18T16:00:00","16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-22T08:00:00","2021-04-01T16:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-06T08:00:00","2021-04-08T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-12T08:00:00","2021-04-14T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-15T08:00:00","2021-04-19T16:00:00","16 h","DB Netz AG"]
[]
[null,"Waigolshausen - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-20T08:00:00","2021-04-22T16:00:00","1 d","DB Netz AG"]
[]
[null,"Nürnberg Rbf Einfahrt - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-02-22T06:00:00","2021-12-11T23:59:00","292 d, 18 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-13T06:00:00","2021-03-14T04:00:00","22 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-20T06:00:00","2021-03-21T04:00:00","22 h","DB Netz AG"]
[]
[null,"Bamberg - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-27T22:00:00","2021-03-01T05:00:00","14 h","DB Netz AG"]
[]
[null,"Hirschaid - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-28T22:00:00","2021-03-01T05:00:00","7 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Vach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-22T23:00:00","2021-03-26T23:00:00","4 d","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T04:00:00","2021-03-29T04:00:00","3 d","DB Netz AG"]
[]
[null,"Vach - Fürth (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bad Staffelstein - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T21:00:00","2021-03-28T06:00:00","9 h","DB Netz AG"]
[]
[null,"Hirschaid - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T23:00:00","2021-04-01T04:00:00","4 d, 05 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-04T04:00:00","7 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-10-05T22:00:00","2021-12-01T01:00:00","56 d, 03 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-01T01:00:00","2021-12-06T04:00:00","5 d, 03 h","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-05T21:00:00","2021-12-06T04:00:00","7 h","DB Netz AG"]
[]
[null,"Bodenwöhr Nord - Bodenwöhr Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Plzen","continuous","2021-03-23T07:00:00","2021-05-10T07:00:00","48 d","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-10T07:00:00","2021-06-18T21:00:00","39 d, 14 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe-Dammerstock",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-08-30T23:00:00","2021-11-08T05:00:00","69 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-08","2021-09-29T23:59:00","22 d","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-25T06:00:00","2021-09-27T04:00:00","1 d, 22 h","DB Netz AG"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","30.11.2020","10.07.2021","221 days + 22,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Linz - Wien","cont.","20.02.2021","22.02.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","08.03.2021","16.03.2021","8 days + 9,5 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.03.2021","15.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","12 days","ÖBB Infra"]
[]
[null,"Sbl Spw 2 - St.Valentin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","11 days + 12,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","19.03.2021","22.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","22.03.2021","03.04.2021","12 days + 8,5 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","26.03.2021","29.03.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.04.2021","16.04.2021","4 days","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","12.04.2021","21.04.2021","9 days + 9,5 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - Untergaumberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","16.04.2021","03.05.2021","16 days + 6,5 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","21.05.2021","25.05.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","22.05.2021","24.05.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","04.06.2021","07.06.2021","2 days + 5,5 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Lambach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","09.07.2021","12.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Üst Ams 2 - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","7 days + 4,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","6 days + 5,0 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Sbl Gun 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","16.07.2021","19.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","17.07.2021","22.07.2021","5 days","ÖBB Infra"]
[]
[null,"Gunskirchen - Wels Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","23.07.2021","26.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Ybbs a.d.Donau - Abzw Knoten Karlsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","03.08.2021","23.08.2021","20 days","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","17.09.2021","20.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.09.2021","27.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","01.10.2021","04.10.2021","2 days + 19,0 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","15.10.2021","18.10.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","18.10.2021","22.10.2021","4 days + 10,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","23.10.2021","26.10.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","30.10.2021","02.11.2021","3 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","30.10.2021","02.11.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","05.11.2021","08.11.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Seekirchen am Wallersee - Steindorf bei Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","20.11.2021","24.11.2021","4 days","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Seekirchen am Wallersee",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.11.2021","29.11.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Meidling - W.Mat.-Oswaldgasse",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Linz - Wien","cont.","12.12.2021","16.04.2023","491 days","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","26.02.2021","01.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","05.03.2021","08.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.03.2021","15.03.2021","3 days + 16,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.03.2021","22.03.2021","3 days + 17,0 h","ÖBB Infra"]
[]
[null,"Andorf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.05.2021","15.05.2021","7 days + 10,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.10.2021","11.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","15.10.2021","18.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.11.2021","15.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.11.2021","22.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Parndorf Ort - Zurndorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Parndorf - Hegyeshalom","cont.","12.04.2021","16.04.2021","4 days + 4,7 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","08.03.2021","12.03.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.03.2021","14.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","19.03.2021","21.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","03.04.2021","06.04.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","10.04.2021","11.04.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - Lanzendorf-Rannersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.04.2021","18.04.2021","6 days + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","13.05.2021","16.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","22.05.2021","25.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","29.05.2021","30.05.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.06.2021","20.06.2021","13 days + 10,0 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","26.06.2021","20.08.2021","55 days + 9,0 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","05.07.2021","16.07.2021","10 days + 20,5 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","16.07.2021","06.08.2021","21 days + 12,5 h","ÖBB Infra"]
[]
[null,"Abzww Str 11815 - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.08.2021","16.09.2021","39 days + 20,5 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","20.08.2021","05.09.2021","15 days + 23,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Wien - Parndorf","cont.","01.09.2021","31.12.2022","487 days","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","15.10.2021","18.10.2021","2 days + 5,2 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","18.10.2021","31.10.2021","13 days + 11,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","23.10.2021","27.10.2021","3 days + 5,2 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","28.05.2021","02.06.2021","5 days + 15,0 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Inzersdorf Ort-Ost - Oberlaa",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","22.03.2021","29.03.2021","6 days + 20,0 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","29.10.2021","03.11.2021","4 days + 7,5 h","ÖBB Infra"]
[]
[null,"Linz Oed - Linz Wegscheid",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-26","2021-08-01","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-19","2021-07-25","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-02","2021-08-08","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-09","2021-08-15","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Rutzing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Rutzing - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":62,"n_cols":21,"rows_kept":62,"cut":false,"hidden":false,"merged":[[0,2,0,3],[0,0,0,1]]}
["IM",null,"Section",null,"Direction","Duration","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","International Coordination","In yearly timetable","Classification","Status","Automatic process"]
["GySEV",43,"Strasbourg - Karlsruhe",1,"< >","continuous","Signal","T","LT","S","W","D","C,,","R,,",",B,","O,,",43,"Y","Major","Planned","Y"]
["CFR",53,"Appenweier - Karlsruhe (div.)",2,">","periodical","Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,",53,"N","High","Coordination","N"]
["SŽCZ",54,"Karlsruhe - Bruchsal",3,"<","periodical continuous","Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",54,null,"Medium","Consultation"]
["MÁV",55,"Bruchsal - Mannheim",4,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",55,null,"Minor","Published"]
["ŽSR",56,"Karlsruhe - Mannheim",5,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",56,null,"Unclassified","Canceled"]
["DB Netz AG",80,"Mannheim - Darmstadt",6,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",80]
["ÖBB-Infra",81,"Mannheim - Gr. Gerau - Fr.",7,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",81]
["SNCF Reseau",87,"Darmstadt - Frankfurt",8,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,87]
[null,null,"Frankfurt - Aschaffenburg",9,null,null,"Others",null,null,null,null,null,null,null,null,null,54.81]
[null,null,"Darmstadt - Aschaffenburg",10,null,null,null,null,null,null,null,null,null,null,null,null,80.81]
[null,null,"Aschaffenburg - Gemünden",11,null,null,null,null,null,null,null,null,null,null,null,null,"54,80"]
[null,null,"Gemünden - Bamberg - Nürnberg",12,null,null,null,null,null,null,null,null,null,null,null,null,"55,56"]
[null,null,"Gemünden - Würzburg - Nürnberg",13,null,null,null,null,null,null,null,null,null,null,null,null,"54,81"]
[null,null,"Nürnberg - Regensburg",14,null,null,"Signal",null,null,null,null,null,null,null,null,null,"56,81"]
[null,null,"Regensburg - München",15,null,null,"Switch",null,null,null,null,null,null,null,null,null,"55,81"]
[null,null,"Regensburg - Wels",16,null,null,"Catenary",null,null,null,null,null,null,null,null,null,"43,55"]
[null,null,"Bruchsal - Mühlacker",17,null,null,"Track & Rail",null,null,null,null,null,null,null,null,null,"43,81"]
[null,null,"Karlsruhe - Stuttgart",18,null,null,"Tunnel"]
[null,null,"Stuttgart - München",19,null,null,"Bridge"]
[null,null,"München - Rosenheim - Salzburg ",20,null,null,"Miscellaneous*"]
[null,null,"München - Mühld. - Freilassing",21,null,null,"Maintenance"]
[null,null,"Nürnberg - Plzen",22,null,null,"Others**"]
[null,null,"Regensburg - Plzen",23]
[null,null,"Plzen - Praha",24]
[null,null,"Praha - Choceň",25]
[null,null,"Praha - Hr. Králové - Choceň",26]
[null,null,"Choceň - Hranice na Moravě",27]
[null,null,"Hranice na Moravě - Žilina",28]
[null,null,"Hranice na Moravě - Ostrava",29]
[null,null,"Ostrava - Český Těšín",30]
[null,null,"Ostr. - Dětmarovice - Č. Těšín",31]
[null,null,"Český Těšín - Žilina",32]
[null,null,"Žilina - Košice",33]
[null,null,"Košice - Čierna nad Tisou",34]
[null,null,"Čierna nad Tisou - Chop",35]
[null,null,"Košice - Haniska pri Košiciach",36]
[null,null,"Haniska pri Košic. - Maťovce",37]
[null,null,"Salzburg - Wels",38]
[null,null,"Wels - Linz",39]
[null,null,"Wels - Traun - Linz",40]
[null,null,"Linz - Wien",41]
[null,null,"Wien - Parndorf",42]
[null,null,"Parndorf - Bratislava",43]
[null,null,"Parndorf - Hegyeshalom",44]
[null,null,"Wien - Sopron",45]
[null,null,"Sopron - Győr",46]
[null,null,"Bratislava - Hegyeshalom",47]
[null,null,"Hegyeshalom - Györ",48]
[null,null,"Györ - Budapest",49]
[null,null,"Budapest - Újszász - Szolnok",50]
[null,null,"Budapest - Cegléd - Szolnok",51]
[null,null,"Szolnok - Arad",52]
[null,null,"Szolnok - Cluj",53]
[null,null,"Cluj - Coșlariu",54]
[null,null,"Arad - Brașov",55]
[null,null,"Brașov - Bucuresti",56]
[null,null,"Arad - Craiova",57]
[null,null,"Craiova - Bucuresti",58]
[null,null,"Bucuresti - Constanţa",59]
[null,null,"Ploiești triaj - Fetești",60]
[null,null,"Simeria - Filiasi",61]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}