{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":11,"defined_names":5,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Schedule","index":1,"n_rows":3801,"n_cols":43,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,1,2,1],[1,2,2,2],[1,3,2,3],[2064,2,2064,30],[1,30,2,30],[1,28,2,28],[1,27,2,27],[1,4,1,5],[1,6,1,7],[1,8,1,9],[1,10,1,11],[1,12,1,13],[1,17,1,21],[1,16,2,16],[1,22,1,26],[1,29,2,29],[1,14,2,14],[1,15,2,15]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day\n(character of timely closure)","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In annual timetable","Last update"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other"]
[null,80,"Hanau Südseite - Rohrbach","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2022,2022,8,11,"2022-02-25T07:00:00","07:00:00","2022-03-17T20:00:00","20:00:00","20 d, 13 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.0153 NAH WE W107 W109 25.02.-17.03.2022",null,"N","2021-07-09T12:40:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Aschaffenburg-Goldbach","Aschaffenburg Hbf",2022,2022,10,11,"2022-03-11T22:00:00","22:00:00","2022-03-14T04:00:00","04:00:00","2 d, 06 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.0153 NAH WE W107 W109 25.02.-17.03.2022 in Aschaffenbg Hbf",null,"N","2021-09-03T11:21:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2022,2022,12,14,"2022-03-26T07:00:00","07:00:00","2022-04-06T20:00:00","20:00:00","11 d, 13 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.0155 NAH  WE W95 W153-155, W159-161 in Aschaffenbg Hbf",null,"N","2021-08-06T09:22:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2022,2022,13,14,"2022-03-28T04:00:00","04:00:00","2022-04-06","00:00:00","8 d, 20 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.0155 NAH  WE W95 W153-155, W159-161",null,"N","2021-08-06T09:41:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Lohr Bahnhof",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-06T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Harrbach",null,"N","2020-11-26T14:08:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-11T20:00:00","20:00:00","6 d, 12 h","continuous","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Hohlstellenbildung u. Rissverpressen im Tunnel Schönrain",null,"N","2020-11-26T13:10:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-07T08:00:00","08:00:00","2022-09-08T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Ständelberg",null,"N","2020-11-26T14:06:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Nantenbach",2022,2022,37,37,"2022-09-12T06:00:00","06:00:00","2022-09-18T22:00:00","22:00:00","4 d, 16 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain RKZ 2_im PKI",null,"N","2020-11-26T14:23:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-22T07:00:00","07:00:00","2022-10-04T16:00:00","16:00:00","4 d, 21 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain_RKZ 1",null,"N","2020-11-26T14:30:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-25T05:30:00","05:30:00","2022-10-08T17:00:00","17:00:00","6 d, 17 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - RWH",null,"Y","2020-04-27T06:53:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,40,42,"2022-10-09T05:30:00","05:30:00","2022-10-17T04:00:00","04:00:00","7 d, 22 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - RWH",null,"Y","2020-06-08T10:04:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Hemsbach",2022,2022,1,1,"2022-01-08T23:00:00","23:00:00","2022-01-09T05:00:00","05:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen BBM.22.0146 ETCS Kor Rhine-Alpine TP Mitte",null,"N","2021-06-14T13:58:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,1,1,"2022-01-08T23:00:00","23:00:00","2022-01-09T05:00:00","05:00:00","6 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0379 SÜ Eschollbrücker Str. Rohrbrücke",null,"N","2021-09-10T07:23:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,2,3,"2022-01-14T23:45:00","23:45:00","2022-01-17T04:20:00","04:20:00","2 d, 05 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS Str 3601 RGCH-RMF+RMF-RGCH / SEV",null,"N","2021-06-09T08:43:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,4,4,"2022-01-28T21:00:00","21:00:00","2022-01-29T13:00:00","13:00:00","16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0147 Ersatzneubau SÜ Rheinstraße",null,"N","2021-07-02T11:49:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,4,4,"2022-01-29T13:00:00","13:00:00","2022-01-30T15:00:00","15:00:00","1 d, 02 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0147 Ersatzneubau SÜ Rheinstraße",null,"N","2021-07-02T11:49:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Hemsbach",2022,2022,4,4,"2022-01-29T22:35:00","22:35:00","2022-01-30T06:10:00","06:10:00","8 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen BBM.22.0207 ETCS DA003 Softwarewechsel",null,"N","2021-06-28T11:17:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,4,4,"2022-01-29T22:35:00","22:35:00","2022-01-30T06:10:00","06:10:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0380 SÜ Eschollbrücker Str. Rohrbrücke",null,"N","2021-09-10T07:27:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,4,5,"2022-01-30T13:00:00","13:00:00","2022-01-31T05:00:00","05:00:00","16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0147 Ersatzneubau SÜ Rheinstraße",null,"N","2021-07-02T11:49:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Weinheim (Bergstr)","Weinheim (Bergstr)",2022,2022,12,13,"2022-03-25T01:00:00","01:00:00","2022-03-30T04:30:00","04:30:00","5 d, 04 h","continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"Schienenerneuerung SE2_Weinheim Gl.3/103 in Weinheim Hbf",null,"N","2021-09-17T17:24:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-03-28T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0069 Sanierung Rohrbrücke km 29,312",null,"N","2021-08-25T11:18:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,12,14,"2022-03-25T22:00:00","22:00:00","2022-04-07T23:00:00","23:00:00","13 d, 01 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE",null,"N","2021-08-31T21:30:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt-Eberstadt Nord","Darmstadt Hbf",2022,2022,12,12,"2022-03-25T23:55:00","23:55:00","2022-03-26T07:20:00","07:20:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0069 Sanierung Rohrbrücke km 29,312",null,"N","2021-08-25T11:24:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,12,12,"2022-03-26","00:00:00","2022-03-27T07:00:00","07:00:00","14 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0374 Ersatzneubau SÜ Rheinstraße",null,"N","2021-08-31T13:20:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Weinheim (Bergstr)","Weinheim (Bergstr)",2022,2022,12,13,"2022-03-26T00:30:00","00:30:00","2022-03-29T04:30:00","04:30:00","3 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung SE2_Weinheim Gl.3/103 in Weinheim Hbf",null,"N","2021-09-20T10:17:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt-Eberstadt Nord","Darmstadt Hbf",2022,2022,12,12,"2022-03-26T23:55:00","23:55:00","2022-03-27T08:20:00","08:20:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0069 Sanierung Rohrbrücke km 29,312",null,"N","2021-08-25T11:24:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt-Eberstadt Nord","Darmstadt Hbf",2022,2022,12,13,"2022-03-27T22:55:00","22:55:00","2022-03-28T05:00:00","05:00:00","6 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0069 Sanierung Rohrbrücke km 29,312",null,"N","2021-08-25T11:24:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,12,13,"2022-03-27T23:00:00","23:00:00","2022-03-28T05:00:00","05:00:00","6 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0374 Ersatzneubau SÜ Rheinstraße",null,"N","2021-08-31T13:20:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,13,13,"2022-03-28T23:00:00","23:00:00","2022-03-29T05:00:00","05:00:00","6 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0374 Ersatzneubau SÜ Rheinstraße",null,"N","2021-08-31T13:20:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,13,13,"2022-03-29T23:00:00","23:00:00","2022-03-30T05:00:00","05:00:00","6 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0374 Ersatzneubau SÜ Rheinstraße",null,"N","2021-08-31T10:23:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,31,32,"2022-08-05T22:00:00","22:00:00","2022-08-08T05:30:00","05:30:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW / SEV",null,"N","2021-07-06T18:38:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,33,36,"2022-08-15T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","7 d, 07 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:25:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,36,"2022-09-09T21:00:00","21:00:00","2022-09-11T05:00:00","05:00:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T13:45:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,37,"2022-09-11T05:00:00","05:00:00","2022-09-12T05:00:00","05:00:00","1 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T13:45:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,37,38,"2022-09-17T16:00:00","16:00:00","2022-09-19T04:00:00","04:00:00","1 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:08:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,37,38,"2022-09-18T08:00:00","08:00:00","2022-09-19T04:00:00","04:00:00","20 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:08:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,38,38,"2022-09-24T16:00:00","16:00:00","2022-09-25T08:00:00","08:00:00","16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:53:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,38,39,"2022-09-25T12:00:00","12:00:00","2022-09-26T04:00:00","04:00:00","16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:53:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,40,41,"2022-10-09","00:00:00","2022-10-10T04:00:00","04:00:00","1 d, 04 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-22T09:46:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,41,42,"2022-10-15T20:00:00","20:00:00","2022-10-17T04:00:00","04:00:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-22T10:37:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt",2022,2022,42,42,"2022-10-23T04:00:00","04:00:00","2022-10-23T20:00:00","20:00:00","16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-29T15:43:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,43,43,"2022-10-30T08:00:00","08:00:00","2022-10-30T18:00:00","18:00:00","10 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-30T14:11:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,47,"2022-11-07T06:00:00","06:00:00","2022-11-24T18:00:00","18:00:00","17 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T04:00:00","04:00:00","2 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf",">","Darmstadt Gbf","Darmstadt Nord",2021,2022,49,17,"2021-12-12","00:00:00","2022-04-28T23:45:00","23:45:00","138 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0260 Kreuzungsbauwerk Darmstadt 3557/3541",null,"N","2021-08-16T14:15:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2022,2022,8,8,"2022-02-21T04:30:00","04:30:00","2022-02-26","00:00:00","4 d, 20 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung BBM.22.0154 NAH GE Gl4 13.02.-22.03.2022 in Aschaffenbg Hbf",null,"N","2021-08-03T15:05:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,46,"2022-11-09T05:00:00","05:00:00","2022-11-14T05:00:00","05:00:00","5 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","<","Stuttgart-Bad Cannstatt","Stuttgart Hbf",2022,2022,6,7,"2022-02-13T01:40:00","01:40:00","2022-02-14T04:00:00","04:00:00","1 d, 02 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weicheneinbau Bauweiche, OLA, Gründungen in Stg-Bad Cannst",null,"N","2021-07-20T23:54:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt",">","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2022,2022,21,23,"2022-05-27T21:00:00","21:00:00","2022-06-10T21:00:00","21:00:00","14 d","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2021-10-12T10:28:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,21,23,"2022-05-27T23:00:00","23:00:00","2022-06-10T05:00:00","05:00:00","3 d, 12 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2021-10-12T10:28:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Beimerstetten","Beimerstetten",2022,2022,7,7,"2022-02-19T07:00:00","07:00:00","2022-02-20T21:00:00","21:00:00","1 d, 14 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten BMP in Beimerstetten",null,"N","2021-06-18T11:43:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Beimerstetten","Beimerstetten",2022,2022,8,8,"2022-02-26T07:00:00","07:00:00","2022-02-27T21:00:00","21:00:00","1 d, 14 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten BMP in Beimerstetten",null,"N","2021-06-18T12:11:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim Pbf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-11T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Herstellung Querung, Gründungen, KTB, Ol-Arb in Stg-Bad Cannst",null,"N","2021-09-14T12:53:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Westerstetten","Ulm-Örlingen",2022,2022,15,15,"2022-04-15T21:00:00","21:00:00","2022-04-16T13:00:00","13:00:00","16 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Bahnsteigarbeiten BMP in Beimerstetten",null,"N","2021-06-18T12:18:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Eislingen (Fils)","Gingen (Fils) Süd",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Altbestand - Rückbau alte Signalfundamente+Kabel, SEV",null,"N","2021-08-20T09:31:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Geislingen (Steige)","Amstetten (Württ)",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Durchlassarbeiten Erneuerung Durchlass Str 4700 km 65,954",null,"N","2021-08-20T09:05:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Eislingen (Fils)","Göppingen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-18T05:00:00","05:00:00","2 d, 08 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Schienenerneuerung SE2 Eislingen-Göppingen",null,"N","2021-08-23T12:38:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim Pbf",2022,2022,15,17,"2022-04-15T21:00:00","21:00:00","2022-04-25T04:59:00","04:59:00","4 d, 16 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Ol-Arbeiten",null,"N","2021-09-20T14:40:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim Pbf",2022,2022,15,17,"2022-04-15T21:00:00","21:00:00","2022-04-25T05:00:00","05:00:00","4 d, 16 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten Herstellen neuer Kabeltrasse",null,"N","2021-09-29T12:39:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Westerstetten","Ulm-Örlingen",2022,2022,15,15,"2022-04-16T20:00:00","20:00:00","2022-04-17T08:00:00","08:00:00","12 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Bahnsteigarbeiten BMP in Beimerstetten",null,"N","2021-06-18T12:18:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Westerstetten","Ulm-Örlingen",2022,2022,15,16,"2022-04-17T13:00:00","13:00:00","2022-04-18T05:00:00","05:00:00","16 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Bahnsteigarbeiten BMP in Beimerstetten",null,"N","2021-06-18T12:18:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Eislingen (Fils)","Süßen",2022,2022,16,17,"2022-04-22T21:00:00","21:00:00","2022-04-25T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Altbestand - Rückbau alte Signalfundamente + Kabel, SEV",null,"N","2021-08-20T13:52:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Süßen","Gingen (Fils) Süd",2022,2022,16,17,"2022-04-22T21:00:00","21:00:00","2022-04-25T04:59:00","04:59:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Altbestand - Ergänzung zur J(XEI)",null,"N","2021-08-20T13:53:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Bad Cannstatt","Esslingen (Neckar)",2022,2022,17,17,"2022-04-25T23:00:00","23:00:00","2022-04-29T05:00:00","05:00:00","1 d","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten Herstellen neuer Kabeltrasse",null,"N","2021-09-29T12:39:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Beimerstetten","Beimerstetten",2022,2022,17,17,"2022-04-28T06:00:00","06:00:00","2022-04-29T22:00:00","22:00:00","1 d, 08 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung SE2 Beimerstetten Gl.1 - Schienenerneuerung + Schutz La in Beimerstetten",null,"N","2021-09-01T12:09:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Untertürkheim Pbf","Stuttgart-Bad Cannstatt",2022,2022,17,18,"2022-04-29T21:00:00","21:00:00","2022-05-02T05:00:00","05:00:00","2 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten Herstellen neuer Kabeltrasse",null,"N","2021-10-27T12:48:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Stuttgart-Bad Cannstatt","Esslingen (Neckar)",2022,2022,18,20,"2022-05-02T23:00:00","23:00:00","2022-05-16T05:00:00","05:00:00","3 d, 12 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten Herstellen neuer Kabeltrasse",null,"N","2021-09-29T12:39:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Ulm Hbf Bft Pbf","Neu-Ulm",2022,2022,20,21,"2022-05-21T23:00:00","23:00:00","2022-05-23T05:00:00","05:00:00","1 d, 06 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenausbau Weichen einbau, Bstgarb., Olarb in Ulm Hbf",null,"N","2021-08-06T12:58:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Ulm Hbf","Ulm Hbf",2022,2022,46,49,"2022-11-20T23:00:00","23:00:00","2022-12-09T05:00:00","05:00:00","18 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleiserneuerung in Ulm Hbf",null,"N","2020-10-22T11:57:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","<","Ulm Hbf","Ulm Hbf",2022,2022,49,49,"2022-12-07T05:00:00","05:00:00","2022-12-09T05:00:00","05:00:00","2 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleiserneuerung in Ulm Hbf",null,"N","2020-10-22T11:57:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,7,8,"2022-02-18T21:25:00","21:25:00","2022-02-25T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916, SEV in Günzburg",null,"N","2021-07-22T11:38:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Neuoffingen",2022,2022,7,8,"2022-02-18T21:25:00","21:25:00","2022-02-25T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-22T11:46:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,7,8,"2022-02-18T21:25:00","21:25:00","2022-02-25T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-22T11:46:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Unterfahlheim","Günzburg",2022,2022,7,8,"2022-02-18T21:25:00","21:25:00","2022-02-25T21:00:00","21:00:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-22T11:46:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-27T09:00:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Neuoffingen",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Unterfahlheim","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,2,3,"2022-01-14T23:45:00","23:45:00","2022-01-17T04:20:00","04:20:00","2 d, 05 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS Str 3601 RGCH-RMF+RMF-RGCH / SEV",null,"N","2021-06-09T08:43:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Mannheim Ziehbrunnen","Schwetzingen",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","2021-07-05T16:30:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2022,2022,10,11,"2022-03-11T22:00:00","22:00:00","2022-03-15T05:00:00","05:00:00","3 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Schienenerneuerung 4060_22_SE2_MA-Ziehbrunnen - Abschn RMF-RZHB",null,"N","2021-08-17T10:55:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Mannheim Ziehbrunnen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,11,11,"2022-03-14T22:05:00","22:05:00","2022-03-15T05:00:00","05:00:00","7 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Schienenerneuerung SE 2 Gleis RMF-RZHB",null,"N","2021-08-23T16:26:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","<","Schwetzingen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,11,11,"2022-03-15T05:00:00","05:00:00","2022-03-18T12:00:00","12:00:00","3 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Schienenerneuerung Gleis RZHB-RMF",null,"N","2021-08-23T16:42:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Mannheim Ziehbrunnen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,11,12,"2022-03-18T22:25:00","22:25:00","2022-03-23T05:30:00","05:30:00","1 d, 11 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Schienenerneuerung SE2_MA-Ziehbrunnen",null,"N","2021-08-23T17:00:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Schwetzingen","Schwetzingen",2022,2022,12,14,"2022-03-24T07:00:00","07:00:00","2022-04-08T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim - Logistik RSZ+RBR in Schwetzingen",null,"N","2021-09-06T12:28:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,14,15,"2022-04-07T23:00:00","23:00:00","2022-04-15T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE",null,"N","2021-09-20T15:07:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,14,15,"2022-04-07T23:00:00","23:00:00","2022-04-15T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE - Ergänzung zu J(XEI)",null,"N","2021-10-05T16:36:00"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,14,15,"2022-04-07T23:00:00","23:00:00","2022-04-15T04:30:00","04:30:00","7 d, 05 h","continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE 4061_Neu-Edingen/F-Feld_GE+WE in N-Edingen/F-feld",null,"N","2021-10-05T17:55:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Mannheim-Rheinau","Waghäusel",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","2021-07-05T16:30:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Oftersheim",2022,2022,4,5,"2022-01-29T03:05:00","03:05:00","2022-01-31T04:00:00","04:00:00","2 d, 01 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS RSZ+RHK - TSP Str 4020 / SEV",null,"N","2021-07-05T16:30:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Hockenheim","Philippsburg Molzau",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Dua Stromversorgung UZ RGN / SEV",null,"N","2021-07-13T19:06:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel - Logistik RSZ + RWG",null,"N","2021-08-10T11:46:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Waghäusel","Waghäusel",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel - Logistik RSZ + RWG",null,"N","2021-08-10T11:46:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Waghäusel","Waghäusel",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel - Logistik RSZ + RWG",null,"N","2021-08-10T11:46:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","2021-08-10T12:08:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","2021-08-10T12:46:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Hockenheim","Hockenheim",2022,2022,9,11,"2022-03-03T07:00:00","07:00:00","2022-03-18T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","2021-08-10T12:46:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau",">","Schwetzingen","Waghäusel",2022,2022,9,11,"2022-03-04T23:00:00","23:00:00","2022-03-14T06:00:00","06:00:00","9 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","2021-08-10T12:08:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau",">","Hockenheim","Waghäusel",2022,2022,9,11,"2022-03-04T23:00:00","23:00:00","2022-03-14T06:00:00","06:00:00","9 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Hockenheim-Waghäusel",null,"N","2021-08-10T12:17:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,12,14,"2022-03-24T07:00:00","07:00:00","2022-04-08T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim - Logistik RSZ+RBR in Schwetzingen",null,"N","2021-09-06T12:28:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,12,14,"2022-03-24T07:00:00","07:00:00","2022-04-08T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","2021-09-06T12:23:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Schwetzingen",2022,2022,12,14,"2022-03-24T07:00:00","07:00:00","2022-04-08T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","2021-09-06T13:50:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Hockenheim","Hockenheim",2022,2022,12,14,"2022-03-24T07:00:00","07:00:00","2022-04-08T16:00:00","16:00:00","15 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","2021-09-06T13:50:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","<","Waghäusel","Hockenheim",2022,2022,12,14,"2022-03-26T23:00:00","23:00:00","2022-04-06T05:00:00","05:00:00","10 d, 06 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Waghäusel-Hockenheim",null,"N","2021-09-06T12:36:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Waghäusel","Waghäusel",2022,2022,14,17,"2022-04-06T08:00:00","08:00:00","2022-04-29T12:00:00","12:00:00","23 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Sanierung SÜ Mannheimer Straße km 30,731",null,"N","2020-06-02T14:43:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Waghäusel","Waghäusel",2022,2022,17,23,"2022-04-29T08:00:00","08:00:00","2022-06-07T12:00:00","12:00:00","39 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Sanierung SÜ Mannheimer Straße km 30,731",null,"N","2020-06-02T14:43:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Waghäusel","Waghäusel",2022,2022,17,23,"2022-04-29T08:00:00","08:00:00","2022-06-07T12:00:00","12:00:00","39 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Sanierung SÜ Mannheimer Straße km 30,731",null,"N","2020-06-02T14:43:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Schwetzingen","Oftersheim",2022,2022,18,20,"2022-05-07T22:20:00","22:20:00","2022-05-22T05:10:00","05:10:00","21 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS RSZ+RHK - Sperrung Gl RSZ-RHK (4020)",null,"N","2020-08-21T15:42:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Mannheim-Rheinau","Mannheim-Rheinau",2022,2022,19,19,"2022-05-09T07:00:00","07:00:00","2022-05-13T17:00:00","17:00:00","4 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung GE Gl.7 in Mannheim-Rheinau",null,"N","2020-09-29T14:49:00"]
[null,80,"Mannheim Hbf - Philippsburg Molzau","< >","Mannheim-Rheinau","Mannheim-Rheinau",2022,2022,19,19,"2022-05-09T07:00:00","07:00:00","2022-05-13T17:00:00","17:00:00","4 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung GE Gl.7 in Mannheim-Rheinau",null,"N","2020-09-29T14:49:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Philippsburg Molzau","Graben-Neudorf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Dua Stromversorgung UZ RGN / SEV",null,"N","2021-07-13T19:06:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Waghäusel Saalbach","Karlsruhe Hbf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Dua Stromversorgung UZ RGN / SEV",null,"N","2021-07-13T19:06:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 2",null,"N","2021-07-13T17:53:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,7,8,"2022-02-19","00:00:00","2022-02-24T23:59:00","23:59:00","6 d","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"Schleifen von Schienen KS-Schleifen Str 4082 - Abstellung Schleifmaschine in Graben-Neudorf",null,"N","2021-08-03T12:24:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe Hbf","Blankenloch",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-08-09T17:54:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,9,10,"2022-03-05","00:00:00","2022-03-11T08:00:00","08:00:00","6 d, 08 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T14:24:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe Hbf","Blankenloch",2022,2022,9,13,"2022-03-05","00:00:00","2022-03-30T21:00:00","21:00:00","25 d, 21 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T09:05:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,9,10,"2022-03-06T21:00:00","21:00:00","2022-03-07T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","2021-08-09T17:54:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe Hbf",2022,2022,9,10,"2022-03-06T21:00:00","21:00:00","2022-03-07T05:00:00","05:00:00","8 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T14:24:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe Hbf","Blankenloch",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-08-09T18:04:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,10,11,"2022-03-07T21:00:00","21:00:00","2022-03-17T05:00:00","05:00:00","9 d, 08 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 3a",null,"N","2021-08-16T15:36:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Bashaide","Karlsruhe-Dammerstock",2022,2022,10,11,"2022-03-12T07:30:00","07:30:00","2022-03-14T05:30:00","05:30:00","1 d, 22 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","2021-08-09T11:58:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Bashaide","Karlsruhe Hbf",2022,2022,10,11,"2022-03-12T23:30:00","23:30:00","2022-03-14T05:30:00","05:30:00","1 d, 06 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","2021-08-09T11:58:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Forchheim (b Karlsruhe)","Forchheim (b Karlsruhe)",2022,2022,10,11,"2022-03-12T23:30:00","23:30:00","2022-03-14T05:30:00","05:30:00","1 d, 06 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","2021-08-09T11:58:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,11,11,"2022-03-17T05:00:00","05:00:00","2022-03-18T21:00:00","21:00:00","1 d, 16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 / Bohrpfahlwand Gl 1, 2 und 9 in Graben-Neudorf",null,"N","2021-08-24T10:13:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,11,11,"2022-03-17T05:00:00","05:00:00","2022-03-18T21:00:00","21:00:00","1 d, 16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 / Bohrpfahlwand Gl 1, 2 und 9 in Graben-Neudorf",null,"N","2021-08-24T10:13:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,11,11,"2022-03-17T05:00:00","05:00:00","2022-03-18T21:00:00","21:00:00","1 d, 16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 / Bohrpfahlwand Gl 1, 2 und 9 in Graben-Neudorf",null,"N","2021-08-24T10:13:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,13,13,"2022-03-30T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","2021-08-09T18:04:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe Hbf",2022,2022,13,13,"2022-03-30T21:00:00","21:00:00","2022-03-31T05:00:00","05:00:00","8 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T12:08:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe Hbf","Blankenloch",2022,2022,13,13,"2022-03-31T05:00:00","05:00:00","2022-04-03T23:59:00","23:59:00","3 d, 19 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-09-07T12:07:00"]
[null,80,"Waghäusel Saalbach - Rastatt","<","Karlsruhe Hbf","Blankenloch",2022,2022,13,13,"2022-03-31T05:00:00","05:00:00","2022-04-03T23:59:00","23:59:00","3 d, 19 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T09:05:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,14,"2022-04-04","00:00:00","2022-04-06T21:00:00","21:00:00","2 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-09-07T12:23:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,14,"2022-04-04","00:00:00","2022-04-06T21:00:00","21:00:00","2 d, 21 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T12:08:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,14,"2022-04-06T21:00:00","21:00:00","2022-04-07T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","2021-09-07T12:23:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Blankenloch","Karlsruhe Hbf",2022,2022,14,14,"2022-04-06T21:00:00","21:00:00","2022-04-07T05:00:00","05:00:00","8 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T12:08:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,15,"2022-04-07T05:00:00","05:00:00","2022-04-14T16:00:00","16:00:00","7 d, 11 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T10:08:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,14,17,"2022-04-07T05:00:00","05:00:00","2022-04-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-09-07T12:31:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,15,17,"2022-04-13T21:00:00","21:00:00","2022-04-26T05:00:00","05:00:00","12 d, 08 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 - Bph 3b",null,"N","2020-04-27T07:03:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,16,17,"2022-04-19T16:00:00","16:00:00","2022-04-30T21:00:00","21:00:00","11 d, 05 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T10:08:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe-Hagsfeld","Blankenloch",2022,2022,17,17,"2022-04-30T21:00:00","21:00:00","2022-05-01T05:00:00","05:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"N","2021-09-07T12:31:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,17,17,"2022-04-30T22:05:00","22:05:00","2022-05-01T14:05:00","14:05:00","16 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gl 166 in Karlsruhe Hbf",null,"N","2021-08-09T11:56:00"]
[null,80,"Waghäusel Saalbach - Rastatt",">","Blankenloch","Karlsruhe-Hagsfeld",2022,2022,17,18,"2022-05-01T05:00:00","05:00:00","2022-05-04T23:59:00","23:59:00","3 d, 19 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-09-07T12:46:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,18,19,"2022-05-08T22:45:00","22:45:00","2022-05-09T12:00:00","12:00:00","13 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 168 - Erweiterung / SEV in Karlsruhe Hbf",null,"N","2021-08-09T12:12:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,19,19,"2022-05-09T12:00:00","12:00:00","2022-05-10T04:50:00","04:50:00","17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 168 - Erweiterung+Rückbau Isos in SG 1+7 in Karlsruhe Hbf",null,"N","2021-08-09T12:13:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,19,21,"2022-05-13T20:20:00","20:20:00","2022-05-23T04:10:00","04:10:00","9 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 8 inkl. Nachbargleis in Karlsruhe Hbf",null,"N","2021-08-09T12:56:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,19,21,"2022-05-13T20:20:00","20:20:00","2022-05-23T04:10:00","04:10:00","4 d, 16 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 8 -Erw Ri RETL, GE Gl 191 inkl. WE W116+Nachlauf-La in Karlsruhe Hbf",null,"N","2021-08-09T12:57:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,20,21,"2022-05-20T23:40:00","23:40:00","2022-05-23T04:10:00","04:10:00","2 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 8 -Erw Ri RKDU (Abschn W17-W66) in Karlsruhe Hbf",null,"N","2021-08-09T13:01:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:20:00","21:20:00","2022-01-21T04:50:00","04:50:00","2 d, 04 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","2021-06-22"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:20:00","21:20:00","2022-01-21T04:50:00","04:50:00","2 d, 04 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","2021-06-22T13:39:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,2,3,"2022-01-14T21:20:00","21:20:00","2022-01-21T04:50:00","04:50:00","2 d, 04 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","2021-06-22T14:28:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,15,16,"2022-04-15T20:00:00","20:00:00","2022-04-18T05:00:00","05:00:00","2 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10, Gl.70, Gl.75 in Karlsruhe Hbf",null,"N","2021-08-09T13:09:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)",">","Karlsruhe Hbf","Karlsruhe-Durlach",2022,2022,15,16,"2022-04-15T20:00:00","20:00:00","2022-04-18T05:00:00","05:00:00","2 d, 09 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10, Gl.70, Gl.75 in Karlsruhe Hbf",null,"N","2021-08-09T13:09:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,15,16,"2022-04-15T20:00:00","20:00:00","2022-04-22T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:11:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,15,16,"2022-04-15T20:00:00","20:00:00","2022-04-22T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:11:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,15,16,"2022-04-15T20:00:00","20:00:00","2022-04-22T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:11:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","2021-06-22T12:22:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung+Mastgründung), SEV",null,"N","2021-09-23T08:08:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,15,16,"2022-04-15T21:00:00","21:00:00","2022-04-19T05:00:00","05:00:00","3 d, 08 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","2021-09-23T09:17:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,17,17,"2022-04-27","00:00:00","2022-04-30T04:00:00","04:00:00","3 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T09:19:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,17,25,"2022-04-27","00:00:00","2022-06-26T04:00:00","04:00:00","60 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:20:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,17,20,"2022-04-30T04:00:00","04:00:00","2022-05-21T04:00:00","04:00:00","21 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Aufbau Flächengerüst, Demontage, Aufbau Schutzwand, SEV in Pforzheim Hbf",null,"N","2021-09-24T10:01:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,19,21,"2022-05-13T20:20:00","20:20:00","2022-05-23T04:10:00","04:10:00","9 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 8 inkl. Nachbargleis in Karlsruhe Hbf",null,"N","2021-08-09T12:56:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,20,21,"2022-05-20T23:40:00","23:40:00","2022-05-23T04:10:00","04:10:00","2 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 8 -Erw Ri RKDU (Abschn W17-W66) in Karlsruhe Hbf",null,"N","2021-08-09T13:01:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,20,21,"2022-05-21","00:00:00","2022-05-23T04:00:00","04:00:00","2 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Aufbau Flächengerüst, Demontage, Aufbau Schutzwand, SEV in Pforzheim Hbf",null,"N","2021-09-24T10:01:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,20,36,"2022-05-21","00:00:00","2022-09-07T04:00:00","04:00:00","109 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:20:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,21,25,"2022-05-23","00:00:00","2022-06-26T04:00:00","04:00:00","34 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:20:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,21,24,"2022-05-28T04:00:00","04:00:00","2022-06-18T04:00:00","04:00:00","21 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Abschnitt Gl.2-3+63 in Pforzheim Hbf",null,"N","2021-09-24T10:32:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,31,46,"2022-08-01","00:00:00","2022-11-18T23:59:00","23:59:00","110 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Erneuerung Bahnsteigbelag Kar Hbf Bstg 5/6",null,"N","2020-04-27T07:16:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen","<","Bietigheim-Bissingen","Sachsenheim",2022,2022,12,13,"2022-03-25T21:00:00","21:00:00","2022-04-01T20:59:00","20:59:00","7 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten PSS Bietigheim-Sachsenheim",null,"N","2021-08-16T14:03:00"]
[null,80,"Rastatt - Basel Grenze","< >","Rastatt","Rastatt",2021,2022,49,30,"2021-12-12","00:00:00","2022-07-29T18:00:00","18:00:00","229 d, 18 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Barrierefreier Umbau Bahnhof Rastatt",null,"N","2021-05-18T14:44:00"]
[null,80,"Rastatt - Basel Grenze",">","Rastatt","Rastatt-Süd",2022,2022,11,11,"2022-03-19T19:00:00","19:00:00","2022-03-20T12:00:00","12:00:00","17 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Teilerneuerung EÜ Gewerbekanal Lagersanierung RRA-RRAS",null,"N","2021-08-04T11:22:00"]
[null,80,"Rastatt - Basel Grenze",">","Rastatt","Rastatt-Süd",2022,2022,15,15,"2022-04-11T00:15:00","00:15:00","2022-04-15T00:15:00","00:15:00","4 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an Lärmschutzanlagen Instandsetzung LSW Hp Haueneberstein",null,"N","2021-09-21T14:56:00"]
[null,80,"Rastatt - Basel Grenze",">","Rastatt","Rastatt-Süd",2022,2022,15,15,"2022-04-11T00:15:00","00:15:00","2022-04-15T00:15:00","00:15:00","4 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Verschwenkung zur Umfahrung Tunnel Rastatt",null,"N","2021-06-24T14:44:00"]
[null,80,"Rastatt - Basel Grenze","< >","Rastatt","Rastatt-Süd",2022,2022,15,16,"2022-04-15T00:15:00","00:15:00","2022-04-19T03:00:00","03:00:00","4 d, 03 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Verschwenkung zur Umfahrung Tunnel Rastatt",null,"N","2021-06-24T14:44:00"]
[null,80,"Rastatt - Basel Grenze","< >","Rastatt","Rastatt-Süd",2022,2022,15,16,"2022-04-15T00:15:00","00:15:00","2022-04-19T03:00:00","03:00:00","4 d, 03 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an Lärmschutzanlagen Instandsetzung LSW Hp Haueneberstein",null,"N","2021-09-21T14:07:00"]
[null,80,"Rastatt - Basel Grenze","< >","Baden-Baden","Rastatt",2022,2022,15,16,"2022-04-15T00:15:00","00:15:00","2022-04-19T03:00:00","03:00:00","4 d, 03 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an Lärmschutzanlagen Instandsetzung LSW Hp Haueneberstein",null,"N","2021-09-21T14:07:00"]
[null,80,"Rastatt - Basel Grenze",">","Rastatt","Rastatt-Süd",2022,2022,15,16,"2022-04-16T20:00:00","20:00:00","2022-04-19T03:00:00","03:00:00","2 d, 07 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Teilerneuerung EÜ Gewerbekanal Lagersanierung RRA-RRAS",null,"N","2021-08-04T11:33:00"]
[null,80,"Rastatt - Basel Grenze","<","Baden-Baden","Rastatt",2022,2022,16,17,"2022-04-23T07:00:00","07:00:00","2022-04-25T04:00:00","04:00:00","1 d, 21 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an Lärmschutzanlagen Instandsetzung LSW Hp Haueneberstein",null,"N","2021-09-21T14:18:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr D","Mannheim Rbf Gr D",2022,2022,31,32,"2022-08-03","00:00:00","2022-08-09T23:59:00","23:59:00","7 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW",null,"N","2021-07-06T18:34:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr D","Mannheim Rbf Gr D",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr K/Kn","Mannheim Rbf Gr K/Kn",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,33,33,"2022-08-15T22:00:00","22:00:00","2022-08-19T05:00:00","05:00:00","1 d, 04 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2020-10-12T13:52:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,33,34,"2022-08-19T22:00:00","22:00:00","2022-08-22T05:00:00","05:00:00","2 d, 07 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2020-10-12T13:52:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,34,36,"2022-08-22T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","5 d, 06 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2020-10-12T13:54:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,47,"2022-11-26T21:40:00","21:40:00","2022-11-27T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2020-12-14T15:32:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,48,"2022-11-27T21:40:00","21:40:00","2022-11-28T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2020-12-14T15:47:00"]
[null,80,"Würzburg Hbf - Nürnberg Hbf","< >","Fürth (Bay) Gbf","Nürnberg Hbf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T11:31:00"]
[null,80,"Würzburg Hbf - Nürnberg Hbf","< >","Nürnberg Jansenbrücke","Nürnberg Jansenbrücke",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T11:31:00"]
[null,80,"Würzburg Hbf - Nürnberg Hbf","< >","Fürth (Bay) Hbf","Mainbernheim",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T11:31:00"]
[null,80,"Würzburg Hbf - Nürnberg Hbf","< >","Fürth (Bay) Gbf","Nürnberg Jansenbrücke",2022,2022,17,18,"2022-05-01T22:25:00","22:25:00","2022-05-02T04:40:00","04:40:00","6 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Fahrdrahtwechsel in Fürth (Bay) Gbf Bft",null,"N","2021-10-05T13:06:00"]
[null,80,"Nantenbach - Würzburg Hbf","< >","Gemünden (Main)","Gemünden (Main)",2022,2022,17,23,"2022-04-29T23:15:00","23:15:00","2022-06-06T04:50:00","04:50:00","37 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS  km 19,583-km 26,742 u. Gl.1+2 NHG",null,"N","2021-09-28T10:13:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2022,2022,29,30,"2022-07-22T23:00:00","23:00:00","2022-07-25T11:00:00","11:00:00","2 d, 12 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung We Lauf rdP W 601, 602",null,"N","2020-04-27T06:52:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2022,2022,34,35,"2022-08-23","00:00:00","2022-08-30T05:00:00","05:00:00","7 d, 05 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Brückenarbeiten",null,"N","2021-02-11T11:17:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,36,37,"2022-09-10T19:00:00","19:00:00","2022-09-12T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten 6 Lager",null,"N","2020-08-20T12:27:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2022,2022,37,38,"2022-09-17T19:00:00","19:00:00","2022-09-19T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten 6 Lager",null,"N","2020-08-20T12:27:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Marktredwitz","Schirnding Grenze",2022,2022,37,39,"2022-09-16","00:00:00","2022-09-26T06:00:00","06:00:00","10 d, 06 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung WE Marktredwitz-Landesgrenze",null,"N","2021-07-09T12:18:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Schnabelwaid","Kirchenlaibach",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Speichersdorf  km 93,183",null,"N","2020-06-15T13:25:00"]
[null,80,"Augsburg Hbf - München Hbf",">","München-Pasing","München Hbf",2022,2022,11,12,"2022-03-18T23:00:00","23:00:00","2022-03-21T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2021-08-04T14:07:00"]
[null,80,"Augsburg Hbf - München Hbf","< >","Augsburg Hbf","Augsburg Hbf",2022,2022,12,20,"2022-03-22T00:30:00","00:30:00","2022-05-18T04:30:00","04:30:00","57 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BI-BBM22-AUG-204 PAC-H MDA EÜ: Teil 1 MDA",null,"N","2021-08-12T14:13:00"]
[null,80,"Augsburg Hbf - München Hbf","< >","München Hbf","München-Pasing",2022,2022,12,13,"2022-03-25T23:00:00","23:00:00","2022-03-28T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2021-08-04T14:12:00"]
[null,80,"Augsburg Hbf - München Hbf","< >","München Hbf","München-Pasing",2022,2022,13,14,"2022-04-01T23:00:00","23:00:00","2022-04-04T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2021-08-04T14:16:00"]
[null,80,"Augsburg Hbf - München Hbf","<","München Hbf","München-Pasing",2022,2022,14,15,"2022-04-08T23:00:00","23:00:00","2022-04-11T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2021-08-04T14:21:00"]
[null,80,"Augsburg Hbf - München Hbf","< >","München Hbf","München Hbf",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-06T06:00:00","06:00:00","3 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE MH W 215-217, 221-223, 236, 237, 267 und GE Verb W 220-W250 Qualistopfgang",null,"N","2021-06-08T15:51:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Grafing Bahnhof","Grafing Bahnhof",2022,2022,9,12,"2022-02-28T04:40:00","04:40:00","2022-03-27T23:59:00","23:59:00","27 d, 19 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst in Grafing Bahnhof",null,"N","2021-07-27T14:29:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","München Ost Pbf","München Süd",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T06:00:00","06:00:00","1 d","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Balanstraße km 9,054",null,"N","2021-07-15T08:50:00"]
[null,80,"München Hbf - Salzburg Hbf","<","München Ost Pbf","München Süd",2022,2022,14,15,"2022-04-09T05:00:00","05:00:00","2022-04-11T05:00:00","05:00:00","2 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Balanstraße km 9,054",null,"N","2021-07-15T09:02:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Grafing Bahnhof","Grafing Bahnhof",2022,2022,15,22,"2022-04-11T04:40:00","04:40:00","2022-05-30T01:40:00","01:40:00","48 d, 21 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst in Grafing Bahnhof",null,"N","2021-07-27T15:14:00"]
[null,80,"München Hbf - Salzburg Hbf","<","Grafing Bahnhof","Grafing Bahnhof",2022,2022,15,29,"2022-04-11T04:40:00","04:40:00","2022-07-18T04:40:00","04:40:00","98 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Bf GrafingBahnhof, Erneuerung Vst",null,"N","2021-07-30T13:37:00"]
[null,80,"München Hbf - Salzburg Hbf",">","Bergen Rumgraben","Traunstein",2022,2022,24,28,"2022-06-16T22:00:00","22:00:00","2022-07-13T05:00:00","05:00:00","26 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Stützmauerarbeiten 5703 SW 47,201 rdB Schwergew.mauer-Ern",null,"Y","2020-10-06T16:20:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Freilassing","Freilassing",2022,2022,28,31,"2022-07-14T05:00:00","05:00:00","2022-08-07T05:00:00","05:00:00","24 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-10-07T15:37:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Traunstein","Traunstein",2022,2022,28,31,"2022-07-14T05:00:00","05:00:00","2022-08-07T05:00:00","05:00:00","24 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-10-07T15:37:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Teisendorf","Teisendorf",2022,2022,28,29,"2022-07-14T22:00:00","22:00:00","2022-07-24T05:00:00","05:00:00","9 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-06-09T13:25:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Teisendorf","Teisendorf",2022,2022,30,31,"2022-07-27T22:00:00","22:00:00","2022-08-06T05:00:00","05:00:00","9 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-04-27T06:52:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Traunstein","Traunstein",2022,2022,44,44,"2022-11-01T05:00:00","05:00:00","2022-11-04T05:00:00","05:00:00","3 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-10-07T16:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Obertraubling","Regensburg Ost",2022,2022,1,1,"2022-01-08T22:05:00","22:05:00","2022-01-09T05:45:00","05:45:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting_Aufbau Schutzgerüst Gl.1+2 in Regensbg Ost",null,"N","2021-05-05T15:11:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,5,5,"2022-02-05T18:00:00","18:00:00","2022-02-06T12:00:00","12:00:00","18 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE, Weiche 11, 12 u. OL-Erneuerung in Undorf",null,"N","2021-01-11T10:42:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,7,8,"2022-02-18T21:35:00","21:35:00","2022-02-23T10:40:00","10:40:00","4 d, 13 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","2020-05-27T10:36:00"]
[null,80,"Nürnberg Hbf - Passau Grenze",">","Undorf","Regensburg Bbf",2022,2022,8,9,"2022-02-26T22:35:00","22:35:00","2022-02-28T14:05:00","14:05:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","2020-05-27T10:36:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Deining Üst","Seubersdorf",2022,2022,9,10,"2022-03-03T23:15:00","23:15:00","2022-03-07T04:10:00","04:10:00","3 d, 05 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Abbruch SÜ Sallmannsdorf, Km 50,811",null,"N","2021-08-02T16:01:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Bbf","Regensburg Bbf",2022,2022,9,10,"2022-03-04T08:00:00","08:00:00","2022-03-07T08:00:00","08:00:00","3 d","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","2020-05-27T10:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,9,10,"2022-03-04T08:00:00","08:00:00","2022-03-07T08:00:00","08:00:00","3 d","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","2020-05-27T10:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Regensburg-Prüfening               (NRH)","Beratzhausen",2022,2022,9,9,"2022-03-05T17:00:00","17:00:00","2022-03-06T05:00:00","05:00:00","12 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten WE Weiche 11 u. 12 u. OL-Neubau in Undorf",null,"N","2020-05-27T10:29:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Parsberg","Parsberg",2022,2022,10,13,"2022-03-11T08:00:00","08:00:00","2022-03-28T18:00:00","18:00:00","17 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS Ge, Se2 mit BR und PSS, BrSchwellenErn km 52, 587 - 49,200",null,"N","2021-08-05T13:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,10,13,"2022-03-11T08:00:00","08:00:00","2022-03-28T18:00:00","18:00:00","17 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS Ge, Se2 mit BR und PSS, BrSchwellenErn km 52, 587 - 49,200",null,"N","2021-08-05T13:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,10,13,"2022-03-11T08:00:00","08:00:00","2022-03-28T18:00:00","18:00:00","17 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS Ge, Se2 mit BR und PSS, BrSchwellenErn km 52, 587 - 49,200",null,"N","2021-08-05T13:34:00"]
[null,80,"Nürnberg Hbf - Passau Grenze",">","Deining Üst","Seubersdorf",2022,2022,10,13,"2022-03-11T22:00:00","22:00:00","2022-03-28T05:00:00","05:00:00","16 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS Ge, Se2 mit BR und PSS, BrSchwellenErn km 52, 587 - 49,200",null,"N","2021-08-05T13:28:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,10,11,"2022-03-12T15:00:00","15:00:00","2022-03-14T03:40:00","03:40:00","1 d, 13 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,11,12,"2022-03-17T22:00:00","22:00:00","2022-03-21T05:00:00","05:00:00","3 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T10:15:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Parsberg","Parsberg",2022,2022,11,15,"2022-03-18T07:00:00","07:00:00","2022-04-12","00:00:00","24 d, 17 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T13:33:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,11,15,"2022-03-18T07:00:00","07:00:00","2022-04-12T18:00:00","18:00:00","25 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T13:33:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,11,12,"2022-03-19T15:00:00","15:00:00","2022-03-21T03:40:00","03:40:00","1 d, 13 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,11,11,"2022-03-19T21:50:00","21:50:00","2022-03-20T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-08-24T16:33:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,12,13,"2022-03-25","00:00:00","2022-03-28T04:00:00","04:00:00","3 d, 04 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T10:23:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Parsberg","Parsberg",2022,2022,12,15,"2022-03-25T07:00:00","07:00:00","2022-04-12T18:00:00","18:00:00","18 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T13:33:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,13,20,"2022-04-01","00:00:00","2022-05-19T05:00:00","05:00:00","48 d, 05 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T10:50:00"]
[null,80,"Nürnberg Hbf - Passau Grenze",">","Beratzhausen","Undorf",2022,2022,13,14,"2022-04-01T22:00:00","22:00:00","2022-04-04T05:00:00","05:00:00","2 d, 07 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T13:41:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Beratzhausen","Beratzhausen",2022,2022,14,14,"2022-04-04T05:00:00","05:00:00","2022-04-09T01:00:00","01:00:00","4 d, 20 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T15:39:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Undorf","Parsberg",2022,2022,14,14,"2022-04-09T01:10:00","01:10:00","2022-04-10T16:00:00","16:00:00","1 d, 15 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T14:17:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Radldorf (Niederbay)","Mangolding",2022,2022,14,15,"2022-04-10","00:00:00","2022-04-11T04:00:00","04:00:00","1 d, 04 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T10:50:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Undorf","Parsberg",2022,2022,14,15,"2022-04-10T16:00:00","16:00:00","2022-04-11T12:00:00","12:00:00","20 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS We Beratzhausen W 1-3",null,"N","2021-08-24T14:17:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Parsberg","Parsberg",2022,2022,15,18,"2022-04-11T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","20 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,15,18,"2022-04-11T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","20 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,15,18,"2022-04-11T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","20 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Fels-/Hangsanierung FS 37,350-38,200 rdB Parsberg",null,"N","2021-09-09T09:05:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Parsberg","Seubersdorf",2022,2022,15,18,"2022-04-14T22:00:00","22:00:00","2022-05-02T05:00:00","05:00:00","17 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:24:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Parsberg","Deining Üst",2022,2022,16,16,"2022-04-18T23:59:00","23:59:00","2022-04-24T04:00:00","04:00:00","8 h","periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:05:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Beratzhausen","Seubersdorf",2022,2022,16,17,"2022-04-21T23:59:00","23:59:00","2022-04-26T04:00:00","04:00:00","8 h","periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Schienenerneuerung Se2 mit KE Wechsel, Parsberg-Seubersdorf km 37,460-43,494",null,"N","2021-09-10T11:05:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Plattling","Plattling",2022,2022,31,35,"2022-08-05T18:00:00","18:00:00","2022-08-30T02:00:00","02:00:00","24 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS GA/PSS + Se 2 Schwaigen - Landau",null,"N","2020-05-25T16:45:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,34,37,"2022-08-27T08:00:00","08:00:00","2022-09-15T18:00:00","18:00:00","19 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,36,38,"2022-09-05T07:00:00","07:00:00","2022-09-21T05:00:00","05:00:00","15 d, 22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Bbf","Regensburg Bbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Schalding","Schalding",2022,2022,37,37,"2022-09-17T22:40:00","22:40:00","2022-09-18T20:15:00","20:15:00","22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenausbau Rückbau mit Lückenschluss W618 in Schalding",null,"N","2020-05-29T10:13:00"]
[null,80,"Nürnberg Hbf - Passau Grenze",">","Schalding","Schalding",2022,2022,37,37,"2022-09-17T22:40:00","22:40:00","2022-09-18T20:15:00","20:15:00","22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenausbau Rückbau mit Lückenschluss W618 in Schalding",null,"N","2020-05-29T10:13:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,41,42,"2022-10-14T22:00:00","22:00:00","2022-10-23T04:00:00","04:00:00","8 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","2020-05-26T12:55:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Obertraubling","Obertraubling",2022,2022,41,42,"2022-10-14T23:00:00","23:00:00","2022-10-23T04:00:00","04:00:00","8 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","2020-05-26T12:51:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,42,42,"2022-10-22T21:50:00","21:50:00","2022-10-23T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2020-11-12T10:30:00"]
[null,80,"Obertraubling - München Hbf",">","München-Moosach","München-Neulustheim",2022,2022,9,10,"2022-03-05T07:00:00","07:00:00","2022-03-13T22:00:00","22:00:00","2 d, 12 h","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2021-08-02T16:01:00"]
[null,80,"Obertraubling - München Hbf","<","München-Neulustheim","München-Moosach",2022,2022,15,16,"2022-04-15T02:40:00","02:40:00","2022-04-18T22:40:00","22:40:00","3 d, 20 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West",null,"N","2020-04-27T06:49:00"]
[null,80,"Obertraubling - München Hbf",">","München-Moosach","München Hbf",2022,2022,15,16,"2022-04-15T23:00:00","23:00:00","2022-04-18T05:00:00","05:00:00","2 d, 06 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West in Mü-Laim Pbf",null,"N","2021-08-04T16:04:00"]
[null,80,"Obertraubling - München Hbf","< >","München Hbf","München Kanal",2022,2022,16,17,"2022-04-22T23:00:00","23:00:00","2022-04-25T04:40:00","04:40:00","2 d, 06 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Einbau Hbr für UVR Süd",null,"N","2021-10-01T14:05:00"]
[null,80,"Obertraubling - München Hbf",">","München-Moosach","München-Neulustheim",2022,2022,16,18,"2022-04-23T06:00:00","06:00:00","2022-05-08T22:00:00","22:00:00","4 d","periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.S-Bahn Stammstrecke München_ Oberirdisch West in Mü-Laim Pbf",null,"N","2020-09-28T08:33:00"]
[null,80,"Obertraubling - München Hbf","< >","München Kanal","München Hbf",2022,2022,17,18,"2022-04-29T23:00:00","23:00:00","2022-05-02T04:40:00","04:40:00","2 d, 06 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Einbau Hbr für UVR Süd",null,"N","2021-10-01T14:32:00"]
[null,80,"Obertraubling - München Hbf","<","München Hbf","München-Moosach",2022,2022,18,19,"2022-05-06T23:05:00","23:05:00","2022-05-09T04:40:00","04:40:00","2 d, 06 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Einbau Hbr für UVR Süd",null,"N","2021-10-01T14:48:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,28,35,"2022-07-16T08:00:00","08:00:00","2022-09-01T19:00:00","19:00:00","47 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS GA/PSS/WE Dingolfing",null,"N","2021-07-09T13:59:00"]
[null,80,"Obertraubling - München Hbf","<","Moosburg","Landshut (Bay) Hbf",2022,2022,29,30,"2022-07-23T18:00:00","18:00:00","2022-07-25T05:00:00","05:00:00","1 d, 11 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Lagerwechsel EÜ Km 60,093",null,"N","2020-05-20T12:42:00"]
[null,80,"Obertraubling - München Hbf","<","Freising","Freising",2022,2022,31,33,"2022-08-04T22:00:00","22:00:00","2022-08-21T07:00:00","07:00:00","16 d, 09 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA Pulling in Pulling b Freis Hp",null,"N","2021-06-29T07:28:00"]
[null,80,"Obertraubling - München Hbf","< >","Freising","Landshut (Bay) Hbf",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang Erneuerung BÜ km 53,8",null,"N","2020-05-28T14:52:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Freising",2022,2022,31,31,"2022-08-06T22:00:00","22:00:00","2022-08-07T10:00:00","10:00:00","12 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","2020-05-26T17:42:00"]
[null,80,"Obertraubling - München Hbf","< >","Oberschleißheim","Neufahrn (b Freising)",2022,2022,34,34,"2022-08-26T20:40:00","20:40:00","2022-08-27T04:00:00","04:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA Lohhof, Km 23,735 in Lohhof",null,"N","2021-06-29T08:05:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Moosburg",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2020-05-26T13:12:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2020-05-26T13:16:00"]
[null,80,"Obertraubling - München Hbf","< >","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,35,36,"2022-08-30T01:00:00","01:00:00","2022-09-06T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-04-27T06:52:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,36,37,"2022-09-07T01:00:00","01:00:00","2022-09-14T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-26T11:28:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,36,37,"2022-09-07T01:00:00","01:00:00","2022-09-14T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-26T11:28:00"]
[null,80,"Obertraubling - München Hbf",">","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-10-31T04:50:00","04:50:00","2 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 5 u. 25 in Neufahrn/Nbay",null,"N","2020-07-03T12:00:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Freimann",2022,2022,2,20,"2022-01-15T06:00:00","06:00:00","2022-05-21T12:00:00","12:00:00","126 d, 06 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-14T11:41:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,2,2,"2022-01-16T00:45:00","00:45:00","2022-01-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-06-14T11:38:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,3,5,"2022-01-22T12:00:00","12:00:00","2022-01-31T15:00:00","15:00:00","4 d, 06 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-06-16T12:07:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Milbertshofen",2022,2022,4,4,"2022-01-24T06:00:00","06:00:00","2022-01-25T06:00:00","06:00:00","1 d","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-16T12:31:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,4,4,"2022-01-24T15:00:00","15:00:00","2022-01-25T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-16T12:42:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Milbertshofen",2022,2022,4,5,"2022-01-29T12:00:00","12:00:00","2022-01-31T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-16T13:04:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,5,"2022-01-31T07:00:00","07:00:00","2022-01-31T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:44:00"]
[null,80,"Olching - München-Waldtrudering",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,5,5,"2022-01-31T15:00:00","15:00:00","2022-02-01T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-16T13:26:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,5,"2022-02-01T07:00:00","07:00:00","2022-02-01T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,5,"2022-02-02T07:00:00","07:00:00","2022-02-02T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,5,"2022-02-03T07:00:00","07:00:00","2022-02-03T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Freimann",2022,2022,5,6,"2022-02-05T12:00:00","12:00:00","2022-02-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-06-21T09:31:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Freimann",2022,2022,5,6,"2022-02-05T12:00:00","12:00:00","2022-02-08T06:00:00","06:00:00","2 d, 18 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-21T09:45:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,6,6,"2022-02-07T07:00:00","07:00:00","2022-02-07T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:44:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,6,6,"2022-02-07T15:00:00","15:00:00","2022-02-08T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-21T09:31:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,6,6,"2022-02-08T07:00:00","07:00:00","2022-02-08T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:49:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,6,6,"2022-02-09T07:00:00","07:00:00","2022-02-09T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:49:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,6,6,"2022-02-10T07:00:00","07:00:00","2022-02-10T19:00:00","19:00:00","12 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Mängelbeseitigung RiGruppe 2 in Mü Nord Rbf Mi Bft",null,"N","2021-12-07T10:49:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,6,7,"2022-02-12T12:00:00","12:00:00","2022-02-14T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-06-21T12:27:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,34,"2022-02-14T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","193 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,34,"2022-02-14T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","193 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,7,7,"2022-02-14T15:00:00","15:00:00","2022-02-15T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-21T12:27:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-29T09:39:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Freimann",2022,2022,7,8,"2022-02-19T12:00:00","12:00:00","2022-02-21T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-06-29T09:39:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München Nord Rbf Lassallestraße",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-29T12:09:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Milbertshofen","München Nord Rbf Lassallestraße",2022,2022,8,8,"2022-02-21T15:00:00","15:00:00","2022-02-22T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-06-29T12:09:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-01T16:49:00"]
[null,80,"Olching - München-Waldtrudering",">","München Nord Rbf Lassallestraße","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-01T16:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Milbertshofen",2022,2022,8,9,"2022-02-26T12:00:00","12:00:00","2022-02-28T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-07-01T16:44:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-02-28T15:00:00","15:00:00","2022-03-08T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-01T16:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,9,10,"2022-03-05T12:00:00","12:00:00","2022-03-07T15:00:00","15:00:00","2 d, 03 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-07-05T12:49:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Freimann",2022,2022,10,11,"2022-03-12T12:00:00","12:00:00","2022-03-15T06:00:00","06:00:00","2 d, 18 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-24T15:23:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Johanneskirchen",2022,2022,10,13,"2022-03-12T12:00:00","12:00:00","2022-03-28T15:00:00","15:00:00","6 d, 09 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-07-24T15:54:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Milbertshofen",2022,2022,11,12,"2022-03-14T15:00:00","15:00:00","2022-03-22T06:00:00","06:00:00","1 d, 06 h","periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-24T15:54:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Freimann",2022,2022,12,12,"2022-03-27T12:00:00","12:00:00","2022-03-27T21:00:00","21:00:00","9 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"Y","2021-07-24T16:11:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Milbertshofen","München-Johanneskirchen",2022,2022,13,13,"2022-03-28T15:00:00","15:00:00","2022-03-29T06:00:00","06:00:00","15 h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-24T16:11:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Milbertshofen",2022,2022,13,14,"2022-04-02T12:00:00","12:00:00","2022-04-04T06:00:00","06:00:00","1 d, 18 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-31T10:18:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Freimann",2022,2022,14,14,"2022-04-06T08:00:00","08:00:00","2022-04-06T18:00:00","18:00:00","10 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-31T10:18:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Milbertshofen","München-Milbertshofen",2022,2022,15,16,"2022-04-14T18:00:00","18:00:00","2022-04-19T06:00:00","06:00:00","4 d, 12 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-07-31T10:34:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,17,17,"2022-04-30T14:00:00","14:00:00","2022-05-01T10:00:00","10:00:00","20 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung GE MTR-MBAL (5555) u. MTR-MWTR (5560)",null,"N","2021-11-24T09:00:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,19,20,"2022-05-11T08:00:00","08:00:00","2022-05-17T08:00:00","08:00:00","6 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE W1-4 in Mü Isartor",null,"N","2020-06-22T14:04:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-21T06:00:00","06:00:00","2022-07-22T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:02:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,29,29,"2022-07-23T06:00:00","06:00:00","2022-07-23T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:02:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,29,29,"2022-07-24T06:00:00","06:00:00","2022-07-24T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T15:02:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,30,30,"2022-07-25T06:00:00","06:00:00","2022-07-28T22:00:00","22:00:00","2 d, 16 h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T15:02:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,30,30,"2022-07-29T06:00:00","06:00:00","2022-07-29T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T14:54:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,30,30,"2022-07-30T06:00:00","06:00:00","2022-07-30T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T14:54:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,30,31,"2022-07-31T06:00:00","06:00:00","2022-08-07T22:00:00","22:00:00","2 d","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Daglfing",2022,2022,31,31,"2022-08-01T06:00:00","06:00:00","2022-08-05T22:00:00","22:00:00","3 d, 08 h","periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,32,32,"2022-08-08T06:00:00","06:00:00","2022-08-08T14:00:00","14:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:20:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Daglfing",2022,2022,33,33,"2022-08-16T06:00:00","06:00:00","2022-08-17T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T15:34:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,33,33,"2022-08-19T06:00:00","06:00:00","2022-08-21T22:00:00","22:00:00","2 d","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,34,41,"2022-08-27T04:00:00","04:00:00","2022-10-16T04:00:00","04:00:00","50 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Forstweg",2022,2022,35,38,"2022-08-29T22:00:00","22:00:00","2022-09-21T23:59:00","23:59:00","23 d, 02 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA in Mü Nord Rbf For Bft",null,"N","2020-07-15T09:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Freimann",2022,2022,35,41,"2022-09-02","00:00:00","2022-10-14","00:00:00","42 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Freimann",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-05T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T16:36:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","9 d, 05 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-09T16:40:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","4 d, 10 h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T15:59:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T21:00:00","21:00:00","4 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T16:36:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T23:00:00","23:00:00","4 d, 19 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T16:34:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,36,37,"2022-09-09T22:00:00","22:00:00","2022-09-12T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:45:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,37,37,"2022-09-12T04:00:00","04:00:00","2022-09-17T04:00:00","04:00:00","5 d","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T16:34:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,37,41,"2022-09-12T04:00:00","04:00:00","2022-10-14T04:00:00","04:00:00","32 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,37,37,"2022-09-16T22:00:00","22:00:00","2022-09-17T06:00:00","06:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T17:13:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,39,40,"2022-09-26T04:00:00","04:00:00","2022-10-03T04:00:00","04:00:00","7 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Freimann",2022,2022,40,40,"2022-10-04","00:00:00","2022-10-08T22:00:00","22:00:00","4 d, 22 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T09:12:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Freimann",2022,2022,40,41,"2022-10-08T22:00:00","22:00:00","2022-10-14T04:00:00","04:00:00","5 d, 06 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T09:18:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,40,41,"2022-10-09T14:00:00","14:00:00","2022-10-11T04:00:00","04:00:00","1 d, 14 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,41,42,"2022-10-10T21:00:00","21:00:00","2022-10-21T04:00:00","04:00:00","2 d, 08 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,42,43,"2022-10-19T08:00:00","08:00:00","2022-10-25T08:00:00","08:00:00","6 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE W1-4 in Mü Isartor",null,"N","2020-06-22T14:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,43,43,"2022-10-24T21:00:00","21:00:00","2022-10-28T04:00:00","04:00:00","1 d, 04 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:20:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,44,46,"2022-11-04T21:00:00","21:00:00","2022-11-14T04:00:00","04:00:00","4 d, 14 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:30:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,45,45,"2022-11-07T04:00:00","04:00:00","2022-11-07T21:00:00","21:00:00","17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,45,45,"2022-11-08T21:00:00","21:00:00","2022-11-11T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-06-07T16:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,46,46,"2022-11-14T04:00:00","04:00:00","2022-11-15T20:00:00","20:00:00","1 d, 16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-16T21:00:00","21:00:00","2022-11-17T04:00:00","04:00:00","7 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:44:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,46,46,"2022-11-17T04:00:00","04:00:00","2022-11-18T14:00:00","14:00:00","1 d, 10 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:52:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,47,"2022-11-18T21:00:00","21:00:00","2022-11-21T04:00:00","04:00:00","2 d, 07 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:52:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T21:00:00","21:00:00","2 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:08:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,47,47,"2022-11-23T21:00:00","21:00:00","2022-11-25T04:00:00","04:00:00","1 d, 07 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:32:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Freimann","München-Daglfing",2022,2022,47,47,"2022-11-25T21:00:00","21:00:00","2022-11-27T13:00:00","13:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:32:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,47,48,"2022-11-27T20:00:00","20:00:00","2022-11-28T21:00:00","21:00:00","1 d, 01 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:46:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T08:00:00","08:00:00","2022-12-04T16:00:00","16:00:00","2 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T10:05:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T10:00:00","10:00:00","2022-12-03T20:00:00","20:00:00","1 d, 10 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T11:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,48,49,"2022-12-02T21:00:00","21:00:00","2022-12-05T19:00:00","19:00:00","2 d, 22 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-04-27T06:53:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T22:00:00","22:00:00","2022-12-03T04:00:00","04:00:00","6 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T11:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,49,49,"2022-12-09T21:00:00","21:00:00","2022-12-10T23:59:00","23:59:00","1 d, 03 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-04-27T06:53:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,13,14,"2022-04-02T14:00:00","14:00:00","2022-04-04T12:00:00","12:00:00","1 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleisauswechslung GA Gl.9 in Schweinfurt in Schweinfurt Hbf",null,"N","2021-08-23T11:41:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,13,15,"2022-04-02T14:00:00","14:00:00","2022-04-11T10:00:00","10:00:00","8 d, 20 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleisauswechslung GA Gl.9 in Schweinfurt in Schweinfurt Hbf",null,"N","2021-08-23T11:41:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,13,15,"2022-04-02T14:00:00","14:00:00","2022-04-11T10:00:00","10:00:00","8 d, 20 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleisauswechslung GA Gl.9 in Schweinfurt in Schweinfurt Hbf",null,"N","2021-08-23T11:41:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,14,15,"2022-04-04T12:00:00","12:00:00","2022-04-12T15:00:00","15:00:00","8 d, 03 h","continuous","Track & Rail",null,null,null,"P",null,null,null,null,null,null,"Gleisauswechslung GA Gl.9 in Schweinfurt in Schweinfurt Hbf",null,"N","2021-08-23T11:41:00"]
[null,80,"Rottendorf - Bamberg","< >","Bamberg","Ebelsbach-Eltmann",2022,2022,14,15,"2022-04-08T23:00:00","23:00:00","2022-04-15T16:00:00","16:00:00","6 d, 17 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzbauten für BÜ km 7,3 in Oberhaid",null,"N","2021-09-07T11:20:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,14,15,"2022-04-09T14:00:00","14:00:00","2022-04-11T08:00:00","08:00:00","1 d, 12 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleisauswechslung GA Gl.9 in Schweinfurt in Schweinfurt Hbf",null,"N","2021-08-23T12:05:00"]
[null,80,"Rottendorf - Bamberg","< >","Haßfurt","Gädheim",2022,2022,14,14,"2022-04-09T21:30:00","21:30:00","2022-04-10T06:00:00","06:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Aufstellung Schalung WL Nord",null,"N","2020-07-15T07:13:00"]
[null,80,"Rottendorf - Bamberg","< >","Gädheim","Haßfurt",2022,2022,17,17,"2022-04-30T21:30:00","21:30:00","2022-05-01T06:00:00","06:00:00","8 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Aufstellung Pfeiler DB Bereich",null,"N","2020-11-20T12:13:00"]
[null,80,"Rottendorf - Bamberg",">","Ebelsbach-Eltmann","Bamberg",2022,2022,18,19,"2022-05-07","00:00:00","2022-05-09T04:00:00","04:00:00","2 d, 04 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzbauten für BÜ km 7,3 in Oberhaid",null,"N","2021-09-07T17:16:00"]
[null,80,"Rottendorf - Bamberg","< >","Gädheim","Haßfurt",2022,2022,18,19,"2022-05-07T21:00:00","21:00:00","2022-05-15T17:00:00","17:00:00","1 d, 16 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Einhub Fertigteile",null,"N","2020-08-28T09:18:00"]
[null,80,"Rottendorf - Bamberg","<","Bamberg","Ebelsbach-Eltmann",2022,2022,19,20,"2022-05-13T22:00:00","22:00:00","2022-05-16T04:00:00","04:00:00","2 d, 06 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzbauten für BÜ km 7,3 in Oberhaid",null,"N","2021-09-07T17:16:00"]
[null,80,"Rottendorf - Bamberg","<","Bamberg","Ebelsbach-Eltmann",2022,2022,19,20,"2022-05-14T12:00:00","12:00:00","2022-05-16T04:00:00","04:00:00","1 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzbauten für BÜ km 7,3 in Oberhaid",null,"N","2021-09-07T17:16:00"]
[null,80,"Rottendorf - Bamberg","< >","Gädheim","Haßfurt",2022,2022,39,39,"2022-10-01T21:00:00","21:00:00","2022-10-02T09:00:00","09:00:00","12 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ km 38,4 und km 76,6_Aushub Behelfsbrücke",null,"N","2020-05-15T08:19:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,2,2,"2022-01-16T13:00:00","13:00:00","2022-01-16T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,2,2,"2022-01-16T13:00:00","13:00:00","2022-01-16T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,2,2,"2022-01-16T13:00:00","13:00:00","2022-01-16T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,3,3,"2022-01-23T13:00:00","13:00:00","2022-01-23T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,3,3,"2022-01-23T13:00:00","13:00:00","2022-01-23T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,3,3,"2022-01-23T13:00:00","13:00:00","2022-01-23T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:21:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,4,4,"2022-01-30T13:00:00","13:00:00","2022-01-30T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:22:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,4,4,"2022-01-30T13:00:00","13:00:00","2022-01-30T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:22:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,4,4,"2022-01-30T13:00:00","13:00:00","2022-01-30T23:59:00","23:59:00","11 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:22:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,6,6,"2022-02-07T06:00:00","06:00:00","2022-02-07T16:00:00","16:00:00","10 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:26:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,6,7,"2022-02-13T12:00:00","12:00:00","2022-02-14T02:00:00","02:00:00","14 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,6,7,"2022-02-13T12:00:00","12:00:00","2022-02-14T02:00:00","02:00:00","14 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,6,7,"2022-02-13T12:00:00","12:00:00","2022-02-14T02:00:00","02:00:00","14 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,6,7,"2022-02-13T12:00:00","12:00:00","2022-02-14T02:00:00","02:00:00","14 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10_Einbau Ol-Trenner in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T09:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,9,10,"2022-02-28T06:00:00","06:00:00","2022-03-12T20:00:00","20:00:00","7 d, 14 h","periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T08:54:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,9,12,"2022-02-28T06:00:00","06:00:00","2022-03-22T06:00:00","06:00:00","22 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T08:54:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,10,11,"2022-03-13T06:00:00","06:00:00","2022-03-20T01:00:00","01:00:00","6 d, 19 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T08:47:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,10,11,"2022-03-13T06:00:00","06:00:00","2022-03-20T01:00:00","01:00:00","4 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T08:47:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,11,12,"2022-03-19T23:00:00","23:00:00","2022-03-22T02:00:00","02:00:00","2 d, 03 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 116-124_Paket 10 in Nür Rbf Einfahrt Bft",null,"N","2021-12-02T08:47:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,18,18,"2022-05-06T06:00:00","06:00:00","2022-05-07T20:00:00","20:00:00","1 d, 04 h","periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 531-535_ Paket 8",null,"N","2021-11-26T08:54:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Minervabrücke","Nürnberg Rbf Einfahrt",2022,2022,18,19,"2022-05-08T06:00:00","06:00:00","2022-05-14T20:00:00","20:00:00","4 d, 02 h","periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 531-535_ Paket 8",null,"N","2021-11-26T08:54:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,32,32,"2022-08-13T06:00:00","06:00:00","2022-08-14T22:00:00","22:00:00","1 d, 08 h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Aufbau FA, Gründungsarbeiten",null,"N","2020-09-22T11:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,32,41,"2022-08-13T06:00:00","06:00:00","2022-10-16T22:00:00","22:00:00","64 d, 16 h","continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"Oberleitungsarbeiten Aufbau FA, Gründungsarbeiten",null,"N","2020-09-22T11:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,33,35,"2022-08-21T06:00:00","06:00:00","2022-09-04T22:00:00","22:00:00","2 d","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-22T11:44:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,36,36,"2022-09-11T06:00:00","06:00:00","2022-09-11T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-22T12:03:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,38,39,"2022-09-24T14:00:00","14:00:00","2022-09-26T14:00:00","14:00:00","2 d","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:19:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,39,39,"2022-10-01T14:00:00","14:00:00","2022-10-02T06:00:00","06:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:19:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,39,39,"2022-10-02T14:00:00","14:00:00","2022-10-02T22:00:00","22:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:48:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,39,40,"2022-10-02T22:00:00","22:00:00","2022-10-03T14:00:00","14:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:48:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,40,41,"2022-10-08T14:00:00","14:00:00","2022-10-10T14:00:00","14:00:00","2 d","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-23T13:59:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,40,40,"2022-10-09T06:00:00","06:00:00","2022-10-09T22:00:00","22:00:00","16 h","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-23T13:59:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,41,41,"2022-10-14T14:00:00","14:00:00","2022-10-16T06:00:00","06:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,41,41,"2022-10-16T06:00:00","06:00:00","2022-10-16T22:00:00","22:00:00","16 h","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,41,42,"2022-10-16T06:00:00","06:00:00","2022-10-17T14:00:00","14:00:00","1 d, 08 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,41,42,"2022-10-16T06:00:00","06:00:00","2022-10-17T22:00:00","22:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Reichswald",2022,2022,49,49,"2022-12-05T06:00:00","06:00:00","2022-12-05T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Kettenwerk ziehen u. Abnahme",null,"N","2021-05-19T16:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Hirschaid","Hirschaid",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gleis 3 (Anm. Tem-005) in Hirschaid",null,"N","2021-05-17T11:45:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf",">","Hirschaid","Forchheim (Oberfr)",2022,2022,1,5,"2022-01-07T21:00:00","21:00:00","2022-02-04T21:00:00","21:00:00","28 d","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"sonstige Arbeiten (Anm. Tem-001) PA19+21_Streckenbau u. Neubau EÜ km 40,011 + 40,167 + 55,504",null,"N","2021-06-14T17:23:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Forchheim (Oberfr)",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten (Anm. Tem-001) diverse EÜ Abschnitt NBA-NFO",null,"N","2021-06-14T17:45:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Strullendorf","Strullendorf",2022,2022,5,6,"2022-02-04T21:00:00","21:00:00","2022-02-07T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten (Anm. Tem-001) diverse EÜ Abschnitt NBA-NFO",null,"N","2021-06-14T17:45:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","<","Strullendorf","Bamberg",2022,2022,5,5,"2022-02-05T06:00:00","06:00:00","2022-02-05T23:59:00","23:59:00","18 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten OL-Vollinspektion in Bamberg",null,"N","2021-07-09T09:24:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf",">","Bamberg","Strullendorf",2022,2022,5,5,"2022-02-06T06:00:00","06:00:00","2022-02-06T23:59:00","23:59:00","18 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten OL-Vollinspektion in Bamberg",null,"N","2021-07-09T09:24:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Breitengüßbach","Bamberg",2022,2022,7,8,"2022-02-18T23:30:00","23:30:00","2022-02-21T23:30:00","23:30:00","3 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Anm_IB_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23, hier: Einhub Süd SÜ BAB 73-93b km 6,573_ Aufbau 3. und 4. Gleis Hallstadt- Breitengüßbach (NBS 02/22IB)",null,"N","2021-07-27T15:47:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Breitengüßbach",2022,2022,8,9,"2022-02-25T23:30:00","23:30:00","2022-03-01T11:30:00","11:30:00","3 d, 12 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Anm_IB_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23, hier: Einhub Süd SÜ BAB 73-93b km 6,573_ Aufbau 3. und 4. Gleis Hallstadt- Breitengüßbach (NBS 02/22IB)",null,"N","2021-07-27T16:05:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Fürth (Bay) Hbf","Vach",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach_Ol Anpassung in NF in Fürth (Bay) Hbf",null,"N","2021-09-21T13:57:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Vach","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-101 VDE 8.1.1 PA17 NEF Neubau Gleis, Weichen, OLA, LST f. S-Bahnsteige, SWW ESTW-UZ Erlangen",null,"N","2021-08-25T08:51:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Fürth (Bay) Hbf","Vach",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T14:11:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Fürth (Bay) Hbf","Eltersdorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T14:11:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Strullendorf","Strullendorf",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","2021-08-27T10:38:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Erlangen",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","2021-08-27T10:38:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bad Staffelstein",2022,2022,14,15,"2022-04-08T21:00:00","21:00:00","2022-04-15T21:00:00","21:00:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten 808 Anm_Bbm_2022, ABS/NBS NÜR-Ebensfeld-EF, BA 23 (NBS 05/22U))",null,"N","2021-08-31T10:57:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Eltersdorf","Forchheim (Oberfr)",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","2021-08-26T13:43:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Vach","Bamberg",2022,2022,14,14,"2022-04-08T22:00:00","22:00:00","2022-04-09T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-102 VDE 8.1.1 PA19 Neubau Eggolsheim Süd (NEOS) u. Hp Forchheim Nord (NFON) sowie Ing.-Bauwerke_ PA21 Rückbau/Neubau EÜ Jurastr. km 48,512, Bahnsteige NSU, IBN NEOS Ostseite mit OLA, LST und SWW ESTW-A NEO u. UZ Erlangen",null,"N","2021-08-26T13:43:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Vach","Strullendorf",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Inbetriebnahme IBN Abzw Fürth-Unterfarrnbach",null,"N","2021-09-21T11:31:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Vach","Bamberg",2022,2022,15,15,"2022-04-14T22:00:00","22:00:00","2022-04-15T04:00:00","04:00:00","6 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-101 VDE 8.1.1 PA17 NEF Neubau Gleis, Weichen, OLA, LST f. S-Bahnsteige, SWW ESTW-UZ Erlangen",null,"N","2021-08-25T08:51:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Forchheim (Oberfr)","Bamberg",2022,2022,48,48,"2022-12-03T22:45:00","22:45:00","2022-12-04T08:30:00","08:30:00","10 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-104 VDE 8.1.1 PA21 Erneuerung SÜ B505 km 55,504_ PA19 OLA-Arbeiten, Verbau EÜ BAB A73 km 41,686",null,"N","2020-06-25T13:05:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,18,20,"2022-05-02T06:00:00","06:00:00","2022-05-20T18:00:00","18:00:00","18 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:16:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,18,20,"2022-05-02T06:00:00","06:00:00","2022-05-20T18:00:00","18:00:00","18 d, 12 h","continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:42:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Schwandorf","Schwandorf",2022,2022,19,20,"2022-05-09T06:00:00","06:00:00","2022-05-17T18:00:00","18:00:00","8 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:42:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,19,20,"2022-05-11T22:00:00","22:00:00","2022-05-16T06:00:00","06:00:00","4 d, 08 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:16:00"]
[null,80,"Marktredwitz - Regensburg Hbf",">","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,19,20,"2022-05-11T22:00:00","22:00:00","2022-05-16T06:00:00","06:00:00","4 d, 08 h","continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:42:00"]
[null,80,"Marktredwitz - Regensburg Hbf",">","Schwandorf","Regenstauf",2022,2022,19,20,"2022-05-14T06:15:00","06:15:00","2022-05-16T05:00:00","05:00:00","1 d, 23 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:16:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,19,20,"2022-05-14T06:15:00","06:15:00","2022-05-16T05:00:00","05:00:00","1 d, 23 h","continuous","Switch",null,null,null,"P",null,null,null,null,null,null,"Weichenauswechslung W 56W4, W5, W29 Maxhütte-Haidhof",null,"N","2021-10-15T10:42:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Bodenwöhr Nord","Bodenwöhr Nord",2022,2022,11,11,"2022-03-14","00:00:00","2022-03-20T23:59:00","23:59:00","7 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Abbruch PU unterm Gleis + Auffüllung PU in offener Bauweise in Bodenwöhr Nord",null,"N","2021-07-30T11:51:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Bodenwöhr Nord","Bodenwöhr Nord",2022,2022,11,11,"2022-03-14","00:00:00","2022-03-20T23:59:00","23:59:00","7 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Abbruch PU unterm Gleis + Auffüllung PU in offener Bauweise in Bodenwöhr Nord",null,"N","2021-07-30T11:51:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Furth im Wald","Furth im Wald",2022,2022,17,20,"2022-04-25T06:00:00","06:00:00","2022-05-20T18:00:00","18:00:00","25 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13 in Furth i Wald",null,"N","2021-10-08T09:07:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Furth im Wald","Furth im Wald",2022,2022,17,20,"2022-04-25T06:00:00","06:00:00","2022-05-20T18:00:00","18:00:00","25 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13 in Furth i Wald",null,"N","2021-10-08T09:07:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Schwandorf","Schwandorf",2022,2022,17,20,"2022-04-25T06:00:00","06:00:00","2022-05-20T18:00:00","18:00:00","25 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13 in Furth i Wald",null,"N","2021-10-08T09:07:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Furth im Wald","Furth im Wald",2022,2022,18,20,"2022-05-06T22:00:00","22:00:00","2022-05-16T06:00:00","06:00:00","9 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13 in Furth i Wald",null,"N","2021-10-08T09:07:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Arnschwang","Furth im Wald",2022,2022,19,20,"2022-05-13T22:05:00","22:05:00","2022-05-16T04:40:00","04:40:00","2 d, 07 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13 in Furth i Wald",null,"N","2021-10-08T09:07:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Cham (Oberpf)",2022,2022,38,43,"2022-09-19T06:00:00","06:00:00","2022-10-28T18:00:00","18:00:00","39 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Schwandorf","Schwandorf",2022,2022,38,43,"2022-09-22T06:00:00","06:00:00","2022-10-26T18:00:00","18:00:00","34 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Kothmaißling",2022,2022,39,43,"2022-09-26T06:00:00","06:00:00","2022-10-24T06:00:00","06:00:00","28 d","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Arnschwang","Furth im Wald",2022,2022,42,42,"2022-10-22T22:00:00","22:00:00","2022-10-23T06:00:00","06:00:00","8 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13",null,"N","2020-08-18T11:55:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2022,2022,5,6,"2022-02-06T22:00:00","22:00:00","2022-02-07T05:00:00","05:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Dua Stromversorgung UZ RGN / SEV",null,"N","2021-07-13T19:06:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,9,9,"2022-03-05","00:00:00","2022-03-06T21:00:00","21:00:00","1 d, 21 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-08-09T17:54:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,9,13,"2022-03-05","00:00:00","2022-03-30T21:00:00","21:00:00","25 d, 21 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T09:05:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,10,13,"2022-03-07T05:00:00","05:00:00","2022-03-30T21:00:00","21:00:00","23 d, 16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-08-09T18:04:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,10,11,"2022-03-12","00:00:00","2022-03-14T23:59:00","23:59:00","3 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","2021-08-09T11:58:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe-Dammerstock","Karlsruhe Gbf",2022,2022,10,11,"2022-03-12T07:30:00","07:30:00","2022-03-14T05:30:00","05:30:00","1 d, 22 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung W410 Anschluß Unterwerk inkl. Logistik in Karlsruhe Unterw Awanst",null,"N","2021-08-09T11:58:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,13,13,"2022-03-31T05:00:00","05:00:00","2022-04-03T23:59:00","23:59:00","3 d, 19 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Pfinzkanal Str. 4020 km 52,878",null,"Y","2021-09-07T12:07:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,13,13,"2022-03-31T05:00:00","05:00:00","2022-04-03T23:59:00","23:59:00","3 d, 19 h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Kabelarbeiten ETCS KorA Abschlussarbeiten KTB Blankenloch-Karlsruhe",null,"N","2021-12-07T09:05:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2022,2022,18,19,"2022-05-06T22:00:00","22:00:00","2022-05-09T12:00:00","12:00:00","2 d, 14 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. KrBw Durlach - Kabelquerung mit Schacht in offener Bauweise",null,"N","2020-10-16T11:45:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","4 d, 16 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2020-09-28T14:47:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","9 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2020-09-28T14:47:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,45,46,"2022-11-12T22:15:00","22:15:00","2022-11-14T06:00:00","06:00:00","1 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 zw W834+W835 in Karlsruhe Gbf",null,"N","2020-09-28T14:57:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,48,49,"2022-12-03T01:10:00","01:10:00","2022-12-05T07:00:00","07:00:00","2 d, 06 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W807 in Karlsruhe Gbf",null,"N","2020-09-28T16:35:00"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Würzburg Hbf","Gemünden (Main)",2022,2023,49,49,"2022-12-11","22:00:00","2023-12-04","05:00:00","357d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Durmersheim",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Bashaide",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-11-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,13,49,"2023-03-31","21:00:00","2023-12-09","23:59:00","253d, 3h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous",null,null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Durmersheim",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Forchheim/Karlsr",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,24,25,"2023-06-12","07:00:00","2023-06-19","07:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,25,27,"2023-06-19","07:00:00","2023-07-03","07:00:00","14d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,24,25,"2023-06-12","07:00:00","2023-06-19","07:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Aschaffenbg Hbf","Nantenbach",2022,2023,50,48,"2022-12-17","22:00:00","2023-12-03","05:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-12"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Nantenbach","Gemünden (Main)",2022,2023,50,48,"2022-12-17","22:00:00","2023-12-03","05:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-04"]
[null,80,"Eltersdorf, 28W402 - RB-Grenze km 117,357 - Erfurt Hbf - Leipzig Hbf, Gl 12 (Gröbers - Lpz-Mockau Personenzugbahn)","<","Unterleiterbach","Eltersdorf",2022,2023,50,49,"2022-12-15","22:30:00","2023-12-08","05:40:00","357d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-11-08"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn","<>","Karlsruhe Gbf","Dammerstock",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-26"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-26"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-26"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-26"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn",">","Karlsruhe Gbf","Dammerstock",2023,2023,11,15,"2023-03-17","21:00:00","2023-04-14","21:00:00","27d, 23h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn","<>","Karlsruhe Gbf","Dammerstock",2023,2023,13,14,"2023-04-01","09:00:00","2023-04-03","16:00:00","2d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-27"]
[null,80,"Mainz-Bischofsheim, W 6 - Darmstadt Hbf, W 314",">","Mz-Bisch Überl I","Darmstadt Gbf",2022,2023,50,48,"2022-12-17","23:50:00","2023-12-03","04:50:00","350d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-15"]
[null,80,"Eltersdorf, 28W402 - RB-Grenze km 117,357 - Erfurt Hbf - Leipzig Hbf, Gl 12 (Gröbers - Lpz-Mockau Personenzugbahn)",">","Forchheim (Ofr)","Eltersdorf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-04"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü-Waldtrudering","München-Daglfing",2023,2023,7,8,"2023-02-18","06:00:00","2023-02-26","22:00:00","8d, 16h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim","Übersee",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Prien am Chiemsee, Gl 2406 - Aschau (Chiemgau)","<>","Prien a Chiemsee","Aschau/Chiemgau",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Holzkirchen, W 23 - Rosenheim, 19W211","<>","Rosenheim","Kolbermoor",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,18,18,"2023-05-01","18:00:00","2023-05-02","06:00:00","0d, 12h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Mühldorf - Neumarkt-St Veit DB-Grenze","<>","Rosenheim","Rott (Inn)",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,27,28,"2023-07-07","07:00:00","2023-07-13","18:00:00","6d, 11h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,28,29,"2023-07-14","18:00:00","2023-07-21","18:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,22,23,"2023-05-31","07:00:00","2023-06-05","05:00:00","4d, 22h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,22,23,"2023-06-02","18:00:00","2023-06-05","05:00:00","2d, 11h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt-Süd","Achern",2023,2023,22,31,"2023-06-01","23:30:00","2023-07-31","06:00:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Achern (F)",2023,2023,31,39,"2023-08-01","23:30:00","2023-09-30","06:00:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-06"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt-Süd","Achern",2023,2023,5,13,"2023-02-01","23:30:00","2023-03-31","06:00:00","57d, 5h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Achern (F)",2023,2023,13,22,"2023-04-01","23:30:00","2023-05-31","06:00:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-07-28"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"München Hbf - Augsburg Hbf",">","Olching","Mering Üst",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Olching - Augsburg Hbf",">","Olching","Maisach Abzw",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"München Hbf - Augsburg Hbf",">","Olching","Mering Üst",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Olching - Augsburg Hbf",">","Olching","Maisach Abzw",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","05:00:00","1d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-27"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,14,17,"2023-04-04","09:00:00","2023-04-29","16:00:00","25d, 7h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,9,17,"2023-03-05","00:00:00","2023-04-30","05:00:00","56d, 4h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,9,9,"2023-03-03","09:00:00","2023-03-04","16:00:00","1d, 7h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023,2023,13,17,"2023-04-02","00:00:00","2023-04-30","05:00:00","28d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023,2023,9,13,"2023-03-05","00:00:00","2023-04-02","05:00:00","28d, 4h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,17,18,"2023-04-30","05:00:00","2023-05-04","22:00:00","4d, 17h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,44,44,"2023-10-30","06:00:00","2023-10-30","20:00:00","0d, 14h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,13,14,"2023-04-02","05:00:00","2023-04-04","16:00:00","2d, 11h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"München Hbf - Augsburg Hbf","<","Mering Üst","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560",">","Olching","Mü Nord Rbf For",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Olching - Augsburg Hbf","<","Maisach Abzw","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Maisach Abzw",2023,2023,9,10,"2023-03-05","00:00:00","2023-03-06","16:00:00","1d, 16h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,14,17,"2023-04-08","22:00:00","2023-04-24","16:00:00","15d, 18h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Schnabelwaid, W 21 - Bayreuth Hbf, W 46","<>","Schnabelwaid","Bayreuth Hbf",2023,2023,44,44,"2023-11-04","20:15:00","2023-11-05","07:45:00","0d, 11h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-11-25"]
[null,80,"Schnabelwaid, W 21 - Bayreuth Hbf, W 46","<>","Schnabelwaid","Bayreuth Hbf",2023,2023,32,35,"2023-08-12","01:30:00","2023-08-28","04:50:00","16d, 3h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-11-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,16,17,"2023-04-21","06:00:00","2023-04-24","06:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,16,17,"2023-04-21","06:00:00","2023-04-24","06:00:00","3d, 0h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,16,17,"2023-04-21","06:00:00","2023-04-24","06:00:00","3d, 0h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,13,14,"2023-03-31","21:40:00","2023-04-03","05:40:00","2d, 8h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,13,14,"2023-03-31","21:40:00","2023-04-03","05:40:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,13,14,"2023-03-31","21:40:00","2023-04-03","05:40:00","2d, 8h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,15,15,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,15,15,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,15,15,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,11,11,"2023-03-18","23:00:00","2023-03-19","06:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,11,11,"2023-03-18","23:00:00","2023-03-19","06:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,11,11,"2023-03-18","23:00:00","2023-03-19","06:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-13","22:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-13","22:00:00","3d, 0h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-13","22:00:00","3d, 0h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,15,16,"2023-04-14","22:00:00","2023-04-17","22:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim","Bad Endorf (Obb)",2023,2023,13,14,"2023-04-01","21:40:00","2023-04-03","05:40:00","1d, 8h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,14,15,"2023-04-06","22:00:00","2023-04-11","06:00:00","4d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,12,13,"2023-03-24","21:40:00","2023-03-27","05:40:00","2d, 7h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,12,13,"2023-03-25","21:40:00","2023-03-27","05:40:00","1d, 7h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,12,13,"2023-03-25","21:40:00","2023-03-27","05:40:00","1d, 7h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,12,13,"2023-03-25","21:40:00","2023-03-27","05:40:00","1d, 7h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,7,9,"2023-02-18","00:00:00","2023-02-27","05:00:00","9d, 5h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,7,9,"2023-02-18","00:00:00","2023-02-27","05:00:00","9d, 5h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,7,9,"2023-02-18","00:00:00","2023-02-27","05:00:00","9d, 5h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,11,12,"2023-03-17","22:00:00","2023-03-20","06:00:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,9,10,"2023-03-03","22:00:00","2023-03-06","06:00:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-17","06:00:00","3d, 8h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-17","06:00:00","3d, 8h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-17","06:00:00","3d, 8h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,16,16,"2023-04-17","22:00:00","2023-04-21","06:00:00","3d, 8h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,10,10,"2023-03-06","22:00:00","2023-03-10","06:00:00","3d, 8h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,43,44,"2023-10-27","12:00:00","2023-11-04","12:00:00","8d, 1h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-20"]
[null,80,"Stuttgart-Untertürkheim, W 45 - Kornwestheim Pbf, W 453","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,43,45,"2023-10-23","00:00:00","2023-11-07","00:00:00","15d, 1h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-12"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Traunstein",2023,2023,43,44,"2023-10-29","00:00:00","2023-10-30","04:00:00","1d, 5h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Prien a Chiemsee","Traunstein",2023,2023,14,14,"2023-04-03","00:30:00","2023-04-07","04:30:00","4d, 4h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,15,17,"2023-04-14","22:00:00","2023-04-24","06:00:00","9d, 8h","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Rottau",2023,2023,18,18,"2023-05-02","22:00:00","2023-05-03","06:00:00","0d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,37,37,"2023-09-11","06:00:00","2023-09-12","22:00:00","1d, 16h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Traunstein",2023,2023,45,45,"2023-11-10","22:00:00","2023-11-12","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Rottau",2023,2023,45,45,"2023-11-06","06:00:00","2023-11-06","14:00:00","0d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,15,17,"2023-04-11","22:00:00","2023-04-28","06:00:00","16d, 8h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,45,46,"2023-11-12","14:00:00","2023-11-17","14:00:00","5d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Übersee",2023,2023,47,47,"2023-11-23","01:00:00","2023-11-24","10:00:00","1d, 9h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Übersee",2023,2023,46,47,"2023-11-19","14:00:00","2023-11-22","22:00:00","3d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rottau",2023,2023,46,46,"2023-11-17","22:00:00","2023-11-19","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rumgraben","Traunstein",2023,2023,43,44,"2023-10-27","06:00:00","2023-11-04","22:00:00","8d, 17h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,17,17,"2023-04-28","22:00:00","2023-04-29","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rottau","Übersee",2023,2023,14,15,"2023-04-07","04:30:00","2023-04-11","06:00:00","4d, 1h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Traunstein","Rumgraben",2023,2023,42,43,"2023-10-17","06:00:00","2023-10-26","22:00:00","9d, 16h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Rottau",2023,2023,17,18,"2023-04-30","22:00:00","2023-05-02","06:00:00","1d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Übersee",2023,2023,40,42,"2023-10-05","06:00:00","2023-10-16","22:00:00","11d, 16h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Traunstein","Übersee",2023,2023,41,41,"2023-10-15","06:00:00","2023-10-15","22:00:00","0d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rottau","Übersee",2023,2023,44,44,"2023-11-05","06:00:00","2023-11-05","22:00:00","0d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Traunstein","Rumgraben",2023,2023,42,42,"2023-10-21","06:00:00","2023-10-22","22:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rottau","Übersee",2023,2023,45,45,"2023-11-08","22:00:00","2023-11-10","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rottau",2023,2023,17,17,"2023-04-29","22:00:00","2023-04-30","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Übersee",2023,2023,37,37,"2023-09-13","06:00:00","2023-09-15","22:00:00","2d, 16h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rottau",2023,2023,45,45,"2023-11-06","14:00:00","2023-11-08","14:00:00","2d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Rottau",2023,2023,45,45,"2023-11-09","00:00:00","2023-11-10","05:00:00","1d, 5h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rumgraben","Traunstein",2023,2023,43,43,"2023-10-28","06:00:00","2023-10-29","22:00:00","1d, 17h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Nürnberg Hbf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-11-18"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining (Oberpf)","Nürnberg Hbf",2022,2023,50,48,"2022-12-17","23:00:00","2023-12-03","06:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-05-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Ottersweier",2023,2023,45,45,"2023-11-06","21:00:00","2023-11-11","02:00:00","4d, 5h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Appenweier",2023,2023,45,45,"2023-11-06","21:00:00","2023-11-11","02:00:00","4d, 5h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Baden-Baden",2023,2023,45,46,"2023-11-11","02:00:00","2023-11-13","04:30:00","2d, 2h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Ottersweier",2023,2023,45,46,"2023-11-11","02:00:00","2023-11-13","04:30:00","2d, 2h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Appenweier","Appenweier",2023,2023,45,46,"2023-11-06","21:00:00","2023-11-13","04:30:00","6d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Mü Donnersbgbr",2023,2023,10,14,"2023-03-10","22:40:00","2023-04-03","04:40:00","23d, 5h","periodical continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-21"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Mü Hirschgarten",2023,2023,14,15,"2023-04-06","22:40:00","2023-04-11","04:40:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"München Hbf tief - Gauting, 35W22","<","München-Pasing","Mü Hirschgarten",2023,2023,17,18,"2023-04-28","22:40:00","2023-05-02","04:40:00","3d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München Hbf","München-Pasing",2023,2023,21,22,"2023-05-26","22:40:00","2023-05-30","04:40:00","3d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Mü Hirschgarten",2023,2023,21,22,"2023-05-26","22:40:00","2023-05-30","04:40:00","3d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","München-Pasing","Mü Friedenhei Br",2023,2023,40,40,"2023-10-07","10:50:00","2023-10-08","07:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023,2023,40,40,"2023-10-06","22:50:00","2023-10-07","10:50:00","0d, 12h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023,2023,32,32,"2023-08-12","18:50:00","2023-08-13","00:50:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","München-Pasing","Mü Friedenhei Br",2023,2023,24,24,"2023-06-16","21:20:00","2023-06-17","18:20:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023,2023,40,40,"2023-10-07","10:50:00","2023-10-08","07:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","München-Pasing","Mü Friedenhei Br",2023,2023,48,49,"2023-12-01","22:50:00","2023-12-04","04:50:00","2d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München Hbf tief - Gauting, 35W22",">","Mü Hirschgarten","München-Pasing",2023,2023,6,12,"2023-02-07","22:40:00","2023-03-20","04:40:00","40d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<","München-Pasing","München Hbf",2023,2023,32,33,"2023-08-12","03:50:00","2023-08-14","04:50:00","2d, 1h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023,2023,24,24,"2023-06-17","18:20:00","2023-06-18","00:20:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<>","München-Pasing","Mü-Neuhausen",2023,2023,24,25,"2023-06-16","21:20:00","2023-06-19","10:20:00","2d, 13h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023,2023,40,41,"2023-10-08","07:50:00","2023-10-09","04:50:00","0d, 21h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München Hbf tief - Gauting, 35W22","<","München-Pasing","Mü Hirschgarten",2023,2023,15,20,"2023-04-11","22:40:00","2023-05-19","04:40:00","37d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-18"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023,2023,32,32,"2023-08-12","00:50:00","2023-08-12","18:50:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","München-Pasing","Mü Friedenhei Br",2023,2023,32,32,"2023-08-11","21:50:00","2023-08-12","18:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023,2023,48,49,"2023-12-01","22:50:00","2023-12-04","04:50:00","2d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023,2023,24,24,"2023-06-17","00:20:00","2023-06-17","18:20:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf",">","Fürth (Bay) Hbf","Würzburg Hbf",2022,2023,50,48,"2022-12-17","23:00:00","2023-12-03","06:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-07-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-05","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Achern",2023,2023,44,44,"2023-10-31","22:00:00","2023-11-03","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2023,2023,9,49,"2023-03-01","06:00:00","2023-12-09","23:59:00","283d, 17h","continuous","Signal",null,null,"S",null,null,null,null,null,null,null,null,null,"Y","2021-06-01"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt-Süd","Achern",2023,2023,5,13,"2023-02-01","23:30:00","2023-03-31","06:00:00","57d, 5h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-06"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Baden-Baden","Achern (F)",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:20:00","50d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-07"]
[null,80,"München Hbf tief - München Ost Pbf","<>","Mü Isartor","München Ost Pbf",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-16"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen","<>","München Ost Pbf","Mü-Steinhausen",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707","<>","München Ost Pbf","Mü-Riem West",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<>","München Ost Pbf","München-Giesing",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf","<>","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-10-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-10-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Bashaide","Durmersheim",2023,2023,13,21,"2023-03-31","21:00:00","2023-05-27","06:00:00","56d, 9h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-11"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Karlsruhe Hbf","Durmersheim Nord",2023,2023,45,45,"2023-11-06","04:30:00","2023-11-07","05:00:00","1d, 0h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Bashaide",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Forchheim/Karlsr",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Bashaide","Durmersheim Nord",2023,2023,45,46,"2023-11-07","05:00:00","2023-11-18","05:00:00","11d, 0h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,22,30,"2023-05-29","08:00:00","2023-07-26","16:00:00","58d, 8h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Göppingen","Göppingen",2023,2023,22,30,"2023-05-29","08:00:00","2023-07-26","16:00:00","58d, 8h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,3,4,"2023-01-22","21:00:00","2023-01-23","21:00:00","1d, 0h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,3,29,"2023-01-18","05:00:00","2023-07-21","05:00:00","183d, 23h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-23"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,3,29,"2023-01-18","05:00:00","2023-07-21","05:00:00","183d, 23h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-18","21:00:00","2023-05-19","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-18","21:00:00","2023-05-19","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,29,49,"2023-07-21","01:00:00","2023-12-09","23:59:00","141d, 23h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,4,29,"2023-01-23","21:00:00","2023-07-21","23:59:00","179d, 1h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-04","21:00:00","2023-05-05","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-04","21:00:00","2023-05-05","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,29,49,"2023-07-21","05:00:00","2023-12-09","23:59:00","141d, 19h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,4,4,"2023-01-23","21:00:00","2023-01-25","05:00:00","1d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,4,4,"2023-01-23","21:00:00","2023-01-25","05:00:00","1d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,30,49,"2023-07-25","05:00:00","2023-12-09","23:59:00","137d, 19h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-23"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,3,3,"2023-01-18","02:00:00","2023-01-22","05:00:00","4d, 3h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,3,3,"2023-01-18","02:00:00","2023-01-22","05:00:00","4d, 3h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,29,30,"2023-07-21","15:00:00","2023-07-24","19:00:00","3d, 4h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,19,20,"2023-05-14","22:00:00","2023-05-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023,2023,39,41,"2023-09-25","18:00:00","2023-10-09","18:00:00","14d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,39,41,"2023-09-25","18:00:00","2023-10-09","18:00:00","14d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,33,34,"2023-08-20","22:00:00","2023-08-21","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,39,39,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-20"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,24,24,"2023-06-12","03:00:00","2023-06-12","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal","Graben-Neudorf",2023,2023,2,7,"2023-01-15","22:00:00","2023-02-17","04:45:00","32d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,2,3,"2023-01-15","23:35:00","2023-01-20","05:15:00","4d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<","Graben-Neudorf","Bruchsal-Sport",2023,2023,2,8,"2023-01-15","22:00:00","2023-02-24","04:45:00","39d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<","Graben-Neudorf","Bruchsal",2022,2022,49,51,"2022-12-11","22:00:00","2022-12-23","04:45:00","11d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<","Graben-Neudorf","Bruchsal",2023,2023,7,12,"2023-02-19","22:00:00","2023-03-24","04:45:00","32d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-23"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<","Graben-Neudorf","Bruchsal",2023,2023,7,12,"2023-02-19","22:00:00","2023-03-24","04:45:00","32d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal-Sport","Graben-Neudorf",2022,2022,49,51,"2022-12-11","22:00:00","2022-12-23","04:45:00","11d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal-Sport","Graben-Neudorf",2023,2023,2,8,"2023-01-15","22:00:00","2023-02-24","04:45:00","39d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,2,4,"2023-01-15","23:35:00","2023-01-27","05:15:00","11d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-12"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Graben-Neudorf","Graben-Neudorf",2023,2023,2,4,"2023-01-15","23:35:00","2023-01-27","05:15:00","11d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-23"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,1,3,"2023-01-08","22:00:00","2023-01-20","05:15:00","11d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-23"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Bickenbach",2023,2023,15,16,"2023-04-15","23:00:00","2023-04-17","04:00:00","1d, 5h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberstadt","Pfungstadt",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,16,18,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Bickenbach",2023,2023,18,19,"2023-05-06","23:00:00","2023-05-08","04:00:00","1d, 5h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Bickenbach Nord",2023,2023,16,18,"2023-04-21","22:00:00","2023-05-01","04:00:00","9d, 6h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,16,18,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,42,43,"2023-10-21","12:00:00","2023-10-23","12:00:00","2d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Bamberg - Hof Hbf, W 121","<>","Bamberg","Bamberg",2023,2023,2,4,"2023-01-14","22:45:00","2023-01-29","06:45:00","14d, 8h","periodical continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-13"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,46,46,"2023-11-13","03:00:00","2023-11-13","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,47,48,"2023-11-26","22:00:00","2023-11-27","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,35,36,"2023-09-03","22:00:00","2023-09-04","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,11,12,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,34,34,"2023-08-21","23:20:00","2023-08-22","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,22,22,"2023-05-29","23:20:00","2023-05-30","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Ebelsbach-Eltm",2023,2023,14,14,"2023-04-09","08:00:00","2023-04-09","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Ebelsbach-Eltm",2023,2023,15,15,"2023-04-10","08:00:00","2023-04-10","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Höflein",2023,2023,18,19,"2023-05-01","21:00:00","2023-05-12","04:40:00","10d, 7h","periodical continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,29,30,"2023-07-23","22:00:00","2023-07-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","04:00:00","1d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,17,18,"2023-04-27","18:00:00","2023-05-04","18:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","04:00:00","2d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023,2023,43,43,"2023-10-29","00:00:00","2023-10-29","06:00:00","0d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach","Bickenbach Nord",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach","Bickenbach",2023,2023,17,18,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,17,18,"2023-04-27","18:00:00","2023-05-04","18:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023,2023,43,44,"2023-10-28","12:00:00","2023-10-30","12:00:00","2d, 1h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,20,20,"2023-05-15","03:00:00","2023-05-15","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,10,10,"2023-03-07","22:00:00","2023-03-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,24,24,"2023-06-13","22:00:00","2023-06-14","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,15,15,"2023-04-11","22:00:00","2023-04-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,2,2,"2023-01-10","22:00:00","2023-01-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,6,6,"2023-02-07","22:00:00","2023-02-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,37,37,"2023-09-12","22:00:00","2023-09-13","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,41,41,"2023-10-10","22:00:00","2023-10-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,32,32,"2023-08-08","22:00:00","2023-08-09","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,46,46,"2023-11-14","22:00:00","2023-11-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,28,28,"2023-07-11","22:00:00","2023-07-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,19,19,"2023-05-09","22:00:00","2023-05-10","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,36,37,"2023-09-08","23:00:00","2023-09-13","05:00:00","4d, 6h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,41,42,"2023-10-13","23:00:00","2023-10-18","05:00:00","4d, 6h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf Ost","Schwetzingen",2023,2023,7,9,"2023-02-18","21:30:00","2023-02-27","04:30:00","8d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023,2023,3,5,"2023-01-18","23:30:00","2023-01-30","05:30:00","11d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim Hbf Ost",2023,2023,5,7,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim Hbf",2023,2023,7,9,"2023-02-18","21:30:00","2023-02-27","04:30:00","8d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim-Rheinau",2023,2023,5,5,"2023-01-30","23:30:00","2023-02-02","05:30:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mhm-Neckarau",2023,2023,6,7,"2023-02-09","23:30:00","2023-02-18","05:30:00","8d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Schwetzingen",2023,2023,5,7,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim-Rheinau",2023,2023,3,5,"2023-01-18","23:30:00","2023-01-30","05:30:00","11d, 6h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023,2023,5,5,"2023-01-30","23:30:00","2023-02-02","05:30:00","2d, 6h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Schwetzingen",2023,2023,5,6,"2023-02-02","23:30:00","2023-02-09","04:30:00","6d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart-Bad Cannstatt, W 28 - Stuttgart-Untertürkheim, W 202","<>","Stg-Bad Cannst","Stg-Untertürkhm",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-21","15:00:00","4d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Plochingen","<","Stg-Obertürkheim","Neckarpark",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","04:00:00","2d, 3h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,14,"2023-04-03","03:00:00","2023-04-03","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023,2023,19,28,"2023-05-08","22:25:00","2023-07-11","06:00:00","63d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023,2023,18,28,"2023-05-07","22:25:00","2023-07-10","06:00:00","63d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023,2023,18,27,"2023-05-06","22:25:00","2023-07-09","07:25:00","63d, 9h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023,2023,18,27,"2023-05-05","22:25:00","2023-07-08","06:25:00","63d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,45,45,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,45,45,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,38,41,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,38,41,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Oftersheim",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Waghäusel",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Hockenheim","Schwetzingen",2023,2023,40,41,"2023-10-05","23:30:00","2023-10-11","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023,2023,30,33,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Hockenheim",2023,2023,41,42,"2023-10-11","23:30:00","2023-10-17","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Hockenheim",2023,2023,33,36,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,33,36,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,40,41,"2023-10-05","23:30:00","2023-10-11","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Hockenheim",2023,2023,40,41,"2023-10-05","23:30:00","2023-10-11","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Hockenheim",2023,2023,45,45,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Oftersheim","Waghäusel",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,36,38,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Hockenheim","Waghäusel",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-05","00:00:00","16d, 2h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,41,43,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Mannheim-Rheinau",2023,2023,33,36,"2023-08-20","00:30:00","2023-09-04","04:30:00","15d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,33,36,"2023-08-20","00:30:00","2023-09-04","04:30:00","15d, 4h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,33,36,"2023-08-20","00:30:00","2023-09-04","04:30:00","15d, 4h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Waghäusel","Schwetzingen",2023,2023,43,45,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,43,45,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Mannheim-Rheinau",2023,2023,39,41,"2023-09-25","00:30:00","2023-10-09","04:30:00","14d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,39,41,"2023-09-25","00:30:00","2023-10-09","04:30:00","14d, 4h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Hockenheim","Waghäusel",2023,2023,41,42,"2023-10-11","23:30:00","2023-10-17","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023,2023,41,42,"2023-10-11","23:30:00","2023-10-17","04:30:00","5d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Hockenheim","Schwetzingen",2023,2023,33,36,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023,2023,38,41,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023,2023,36,40,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","Schwetzingen","Schwetzingen",2023,2023,33,36,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Hockenheim","Waghäusel",2023,2023,45,45,"2023-11-07","00:30:00","2023-11-08","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Hockenheim",2023,2023,45,45,"2023-11-07","00:30:00","2023-11-08","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Hockenheim",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Oftersheim","Waghäusel",2023,2023,43,45,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsb Hirbl Str","Westheim/Schwab",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-12"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277",">","Augsb-Oberhausen","Augsb Hirbl Str",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-12"]
[null,80,"Augsburg Hbf - Nördlingen","<","Gersthofen","Augsburg Hbf",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","04:00:00","7d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen",">","Augsburg Hbf","Gersthofen",2023,2023,30,31,"2023-07-29","06:00:00","2023-07-31","00:30:00","1d, 18h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,29,29,"2023-07-21","09:00:00","2023-07-21","15:00:00","0d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Augsburg Hbf - Nördlingen","<","Gersthofen","Augsburg Hbf",2023,2023,45,46,"2023-11-12","22:30:00","2023-11-13","04:30:00","0d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,30,31,"2023-07-29","06:00:00","2023-07-31","09:00:00","2d, 3h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,34,34,"2023-08-21","03:00:00","2023-08-21","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,16,16,"2023-04-17","23:20:00","2023-04-18","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,41,42,"2023-10-15","22:00:00","2023-10-16","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,8,8,"2023-02-20","03:00:00","2023-02-20","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,43,44,"2023-10-29","22:00:00","2023-10-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,30,30,"2023-07-24","03:00:00","2023-07-24","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,31,32,"2023-08-06","22:00:00","2023-08-07","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,44,"2023-10-27","23:00:00","2023-10-30","05:00:00","2d, 7h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,44,"2023-10-27","23:00:00","2023-10-30","05:00:00","2d, 7h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,42,44,"2023-10-21","06:00:00","2023-10-30","18:00:00","9d, 13h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,42,44,"2023-10-21","06:00:00","2023-10-30","18:00:00","9d, 13h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,44,"2023-10-27","22:00:00","2023-10-30","06:00:00","2d, 9h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,44,"2023-10-27","22:00:00","2023-10-30","06:00:00","2d, 9h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,44,44,"2023-10-31","00:00:00","2023-11-01","05:00:00","1d, 5h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,44,44,"2023-10-31","00:00:00","2023-11-01","05:00:00","1d, 5h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,42,44,"2023-10-21","06:00:00","2023-10-30","18:00:00","9d, 13h","continuous","Switch",null,null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,42,44,"2023-10-21","06:00:00","2023-10-30","18:00:00","9d, 13h","continuous","Switch",null,null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,49,49,"2023-12-07","22:00:00","2023-12-08","05:00:00","0d, 7h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,49,49,"2023-12-07","22:00:00","2023-12-08","05:00:00","0d, 7h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,43,"2023-10-26","00:00:00","2023-10-27","05:00:00","1d, 5h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,43,43,"2023-10-26","00:00:00","2023-10-27","05:00:00","1d, 5h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,21,"2023-05-12","20:00:00","2023-05-22","12:00:00","9d, 16h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,22,23,"2023-06-02","22:00:00","2023-06-08","23:30:00","6d, 1h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,20,21,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-15","05:00:00","2023-05-16","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,19,19,"2023-05-13","04:00:00","2023-05-14","04:00:00","1d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,20,20,"2023-05-21","10:00:00","2023-05-21","17:45:00","0d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,21,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,23,24,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-18"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,20,21,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,19,25,"2023-05-08","05:00:00","2023-06-19","05:00:00","42d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,23,23,"2023-06-10","16:00:00","2023-06-11","19:00:00","1d, 3h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,24,24,"2023-06-12","05:00:00","2023-06-13","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<","Fürth-Burgfbach","Fürth (Bay) Hbf",2023,2023,18,19,"2023-05-05","00:00:00","2023-05-08","05:00:00","3d, 5h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,23,24,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,24,25,"2023-06-12","05:00:00","2023-06-19","05:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,20,21,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,25,25,"2023-06-19","05:00:00","2023-06-20","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-15","05:00:00","2023-05-16","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,21,21,"2023-05-22","12:00:00","2023-05-22","18:00:00","0d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,24,24,"2023-06-12","05:00:00","2023-06-13","05:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,25,"2023-05-10","12:00:00","2023-06-19","05:00:00","39d, 17h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,19,25,"2023-05-10","12:00:00","2023-06-19","05:00:00","39d, 17h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,23,23,"2023-06-11","13:00:00","2023-06-11","19:00:00","0d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,28,28,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,27,28,"2023-07-09","22:00:00","2023-07-10","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,43,44,"2023-10-29","22:00:00","2023-10-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Nürnberg Hbf - Irrenlohe, W 3","<>","Nürnberg Hbf","Nürnberg Hbf",2023,2023,16,18,"2023-04-21","06:00:00","2023-05-05","22:00:00","14d, 16h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Babenhausen","Darmstadt Hbf",2022,2023,50,48,"2022-12-17","22:30:00","2023-12-03","05:30:00","350d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-17"]
[null,80,"Hallstadt (b Bamberg) - Abzw Höflein","<>","Hallstadt(Bambg)","Höflein",2023,2023,45,46,"2023-11-10","22:30:00","2023-11-13","05:00:00","2d, 6h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,28,28,"2023-07-10","23:20:00","2023-07-11","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,13,14,"2023-04-01","05:00:00","2023-04-08","21:00:00","7d, 16h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-04-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,17,21,"2023-04-24","01:00:00","2023-05-26","16:00:00","32d, 15h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-03"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,15,16,"2023-04-11","05:00:00","2023-04-22","21:00:00","11d, 16h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Nantenbach",2023,2023,43,47,"2023-10-28","23:30:00","2023-11-20","04:30:00","22d, 6h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Lohr Bahnhof","Partenstein",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,43,48,"2023-10-26","06:00:00","2023-11-29","18:00:00","34d, 13h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","08:00:00","2023-11-20","12:00:00","23d, 5h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","periodical","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Lohr Bahnhof",2023,2023,47,47,"2023-11-25","14:00:00","2023-11-26","12:00:00","0d, 22h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Lohr Bahnhof","Partenstein",2023,2023,47,47,"2023-11-25","14:00:00","2023-11-26","12:00:00","0d, 22h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Karlsruhe Hbf","Karlsr-Durlach",2023,2023,21,22,"2023-05-26","12:00:00","2023-05-30","05:00:00","3d, 17h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-13"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,41,42,"2023-10-13","22:00:00","2023-10-16","12:00:00","2d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Karlsruhe Gbf, W 118 - Karlsruhe-Durlach , W 52","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,42,43,"2023-10-22","12:00:00","2023-10-23","12:00:00","1d, 0h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,42,43,"2023-10-20","22:00:00","2023-10-23","12:00:00","2d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,5,5,"2023-01-30","22:50:00","2023-01-31","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,10,10,"2023-03-06","03:00:00","2023-03-06","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-20","18:00:00","2023-04-27","18:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-20","18:00:00","2023-04-27","18:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach","Da-Eberst Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,2,2,"2023-01-09","23:20:00","2023-01-10","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,38,41,"2023-09-22","18:00:00","2023-10-09","12:00:00","16d, 18h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,16,17,"2023-04-22","23:30:00","2023-04-24","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,15,16,"2023-04-15","11:00:00","2023-04-22","14:00:00","7d, 3h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Partenstein","Lohr Bahnhof",2023,2023,38,41,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,38,41,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Laufach","Wiesthal",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Lohr Bahnhof",2023,2023,37,38,"2023-09-16","23:30:00","2023-09-18","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,15,17,"2023-04-13","06:00:00","2023-04-26","18:00:00","13d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,15,16,"2023-04-15","23:30:00","2023-04-17","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Partenstein",2023,2023,47,48,"2023-11-26","12:00:00","2023-11-27","05:00:00","0d, 17h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,38,40,"2023-09-23","08:00:00","2023-10-08","14:00:00","15d, 6h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,15,17,"2023-04-14","18:00:00","2023-04-24","12:00:00","9d, 18h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Partenstein","Lohr Bahnhof",2023,2023,47,48,"2023-11-26","12:00:00","2023-11-27","05:00:00","0d, 17h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,39,41,"2023-09-25","05:00:00","2023-10-10","12:00:00","15d, 7h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Wiesthal",2023,2023,39,40,"2023-09-30","23:30:00","2023-10-02","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Wiesthal",2023,2023,39,40,"2023-09-30","23:30:00","2023-10-02","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Partenstein",2023,2023,38,41,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","periodical","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Wiesthal",2023,2023,40,41,"2023-10-07","23:30:00","2023-10-09","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,37,41,"2023-09-14","06:00:00","2023-10-11","18:00:00","27d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-31"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Nantenbach",2023,2023,38,39,"2023-09-23","23:30:00","2023-09-25","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Wiesthal",2023,2023,38,39,"2023-09-23","23:30:00","2023-09-25","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,26,26,"2023-06-26","23:20:00","2023-06-27","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,17,18,"2023-04-30","22:00:00","2023-05-01","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,44,45,"2023-11-03","23:00:00","2023-11-08","05:00:00","4d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-17","05:00:00","4d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,39,40,"2023-10-01","22:00:00","2023-10-02","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,45,46,"2023-11-12","22:00:00","2023-11-13","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,6,7,"2023-02-11","22:00:00","2023-02-13","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Beratzhausen",2023,2023,40,40,"2023-10-03","20:30:00","2023-10-04","06:00:00","0d, 9h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-02"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,7,8,"2023-02-18","22:00:00","2023-02-20","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,3,4,"2023-01-21","22:00:00","2023-01-23","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,4,5,"2023-01-28","22:00:00","2023-01-30","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,5,6,"2023-02-04","22:00:00","2023-02-06","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Beratzhausen",2023,2023,2,3,"2023-01-14","22:00:00","2023-01-16","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-02"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,37,40,"2023-09-15","22:00:00","2023-10-03","23:00:00","18d, 1h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-02"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023,2023,24,26,"2023-06-12","22:00:00","2023-06-30","05:00:00","17d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,29,30,"2023-07-23","22:00:00","2023-07-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,23,24,"2023-06-11","22:00:00","2023-06-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,24,24,"2023-06-12","22:50:00","2023-06-13","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,24,24,"2023-06-12","22:50:00","2023-06-13","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,24,24,"2023-06-12","22:50:00","2023-06-13","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,42,42,"2023-10-20","21:00:00","2023-10-21","14:00:00","0d, 17h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,17,17,"2023-04-26","17:00:00","2023-04-27","07:00:00","0d, 14h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Gbf",2023,2023,19,19,"2023-05-08","17:00:00","2023-05-10","04:00:00","1d, 11h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-17"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,48,48,"2023-11-27","05:00:00","2023-11-28","17:00:00","1d, 12h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-17"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,48,48,"2023-12-02","14:00:00","2023-12-03","10:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,15,15,"2023-04-11","01:00:00","2023-04-11","21:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023,2023,18,19,"2023-05-06","17:00:00","2023-05-08","04:00:00","1d, 11h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023,2023,20,20,"2023-05-20","14:00:00","2023-05-21","16:00:00","1d, 2h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,21,21,"2023-05-24","04:00:00","2023-05-24","10:00:00","0d, 6h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023,2023,43,44,"2023-10-28","14:00:00","2023-10-30","03:00:00","1d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,43,43,"2023-10-27","21:00:00","2023-10-28","14:00:00","0d, 17h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Gbf",2023,2023,14,14,"2023-04-08","21:00:00","2023-04-09","17:00:00","0d, 20h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Gbf",2023,2023,17,17,"2023-04-25","11:00:00","2023-04-26","17:00:00","1d, 6h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Darmstadt Hbf","Da-Arheilgen",2023,2023,14,14,"2023-04-08","01:00:00","2023-04-08","21:00:00","0d, 20h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,15,15,"2023-04-13","13:00:00","2023-04-15","05:00:00","1d, 16h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,14,14,"2023-04-03","05:00:00","2023-04-04","01:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,15,15,"2023-04-12","17:00:00","2023-04-13","13:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,15,15,"2023-04-11","21:00:00","2023-04-12","17:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,13,21,"2023-03-27","00:00:00","2023-05-27","23:59:00","61d, 23h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-10-29"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Gbf",2023,2023,9,49,"2023-03-01","00:00:00","2023-12-09","23:59:00","283d, 23h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Gbf",2023,2023,17,18,"2023-04-29","07:00:00","2023-05-01","09:00:00","2d, 2h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,17,17,"2023-04-24","05:00:00","2023-04-25","11:00:00","1d, 6h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,20,20,"2023-05-17","01:00:00","2023-05-17","11:00:00","0d, 10h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,17,18,"2023-04-29","07:00:00","2023-05-01","09:00:00","2d, 2h","continuous",null,null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Darmstadt Hbf","Da-Arheilgen",2023,2023,19,19,"2023-05-10","09:00:00","2023-05-11","05:00:00","0d, 20h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Gbf",2023,2023,49,49,"2023-12-04","05:00:00","2023-12-05","17:00:00","1d, 12h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-24"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,14,14,"2023-04-08","01:00:00","2023-04-08","21:00:00","0d, 20h","continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,21,21,"2023-05-23","11:00:00","2023-05-24","17:00:00","1d, 6h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsburg Hbf","Augsb Hirbl Str",2023,2023,32,46,"2023-08-13","04:30:00","2023-11-19","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,null,null,null,null,null,null,null,"Y","2021-08-09"]
[null,80,"Olching - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-04"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Westheim/Schwab","Augsburg Hbf",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-04"]
[null,80,"München Hbf - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-13"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,36,38,"2023-09-04","22:00:00","2023-09-20","05:00:00","15d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Mühlacker","Bretten Rechberg",2023,2023,48,49,"2023-11-27","23:00:00","2023-12-06","06:00:00","8d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Grötzingen","Wilferdgn-Singen",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-21"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,36,36,"2023-09-04","22:50:00","2023-09-05","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,36,36,"2023-09-04","22:50:00","2023-09-05","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,33,34,"2023-08-20","22:00:00","2023-08-21","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,37,37,"2023-09-11","22:50:00","2023-09-12","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Stg-Utürkhm Pbf","Plochingen",2023,2023,36,38,"2023-09-04","22:00:00","2023-09-20","05:30:00","15d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Eislingen (Fils)","Süßen",2023,2023,43,43,"2023-10-24","22:00:00","2023-10-25","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,35,35,"2023-08-29","22:00:00","2023-08-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,30,30,"2023-07-25","22:00:00","2023-07-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Plochingen","Göppingen",2023,2023,39,39,"2023-09-26","22:00:00","2023-09-27","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,21,21,"2023-05-23","22:00:00","2023-05-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Eislingen (Fils)","Süßen",2023,2023,21,21,"2023-05-23","22:00:00","2023-05-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,17,17,"2023-04-25","22:00:00","2023-04-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,26,26,"2023-06-27","22:00:00","2023-06-28","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","21:30:00","2023-04-21","05:00:00","3d, 7h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-12"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","06:00:00","2023-04-22","06:00:00","5d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-12"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","06:00:00","2023-04-22","06:00:00","5d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-12"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,7,8,"2023-02-19","22:00:00","2023-02-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,34,34,"2023-08-21","22:50:00","2023-08-22","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,34,34,"2023-08-21","22:50:00","2023-08-22","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,21,23,"2023-05-27","22:00:00","2023-06-06","05:00:00","9d, 7h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-05"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,45,45,"2023-11-11","23:00:00","2023-11-12","06:00:00","0d, 7h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Obertraubling","Mangolding",2023,2023,23,23,"2023-06-06","22:00:00","2023-06-07","04:00:00","0d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Obertraubling","Mangolding",2023,2023,21,23,"2023-05-27","22:00:00","2023-06-06","05:00:00","9d, 7h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-05"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,41,42,"2023-10-15","22:00:00","2023-10-16","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,1,2,"2023-01-08","22:00:00","2023-01-09","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Stuttgart Hbf","Kornwestheim Pbf",2023,2023,24,25,"2023-06-18","23:00:00","2023-06-20","05:00:00","1d, 6h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Pragtunnel","Kornwestheim Pbf",2023,2023,12,13,"2023-03-24","23:30:00","2023-03-27","04:40:00","2d, 4h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Stuttgart Hbf","Kornwestheim Pbf",2023,2023,27,27,"2023-07-04","20:00:00","2023-07-05","05:00:00","0d, 9h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Ludwigsburg","Ludwigsburg",2023,2023,22,23,"2023-06-03","01:20:00","2023-06-05","05:00:00","2d, 3h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-07"]
[null,80,"Backnang, W 69 - Ludwigsburg, W 64",">","Freiberg/Neckar","Ludwigsburg",2023,2023,23,23,"2023-06-09","00:10:00","2023-06-11","04:50:00","2d, 4h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-16"]
[null,80,"Backnang, W 69 - Ludwigsburg, W 64","<","Ludwigsburg","Freiberg/Neckar",2023,2023,21,23,"2023-05-27","23:00:00","2023-06-08","05:00:00","11d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-07"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining Üst","Neumarkt(Oberpf)",2023,2023,19,20,"2023-05-12","22:00:00","2023-05-15","05:00:00","2d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining Üst","Neumarkt(Oberpf)",2023,2023,22,23,"2023-06-02","22:00:00","2023-06-05","05:00:00","2d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining Üst","Neumarkt(Oberpf)",2023,2023,26,26,"2023-06-30","22:00:00","2023-07-02","02:00:00","1d, 4h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Neumarkt(Oberpf)","Deining Üst",2023,2023,23,24,"2023-06-09","22:00:00","2023-06-12","05:00:00","2d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Landshut (Bay) Hbf - Bayerisch Eisenstein, Gl 4(DB-Grenze)","<>","Wallersdorf","Plattling",2023,2023,29,30,"2023-07-20","23:00:00","2023-07-28","05:00:00","7d, 6h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"Landshut (Bay) Hbf - Bayerisch Eisenstein, Gl 4(DB-Grenze)","<>","Wallersdorf","Plattling",2023,2023,28,29,"2023-07-16","23:00:00","2023-07-20","05:00:00","3d, 6h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Langenprozelten",2023,2023,9,12,"2023-03-04","08:00:00","2023-03-20","05:00:00","15d, 21h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,9,13,"2023-02-28","06:00:00","2023-03-29","18:00:00","29d, 11h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,9,9,"2023-03-01","23:00:00","2023-03-03","05:00:00","1d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,9,10,"2023-03-04","08:00:00","2023-03-06","05:00:00","1d, 21h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Rohrbach",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Langenprozelten",2023,2023,9,11,"2023-03-04","08:00:00","2023-03-13","05:00:00","8d, 21h","periodical","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Nantenbach",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Rohrbach",2023,2023,12,13,"2023-03-25","08:00:00","2023-03-27","05:00:00","1d, 20h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Lohr Bahnhof",2023,2023,12,13,"2023-03-25","23:30:00","2023-03-27","04:30:00","1d, 4h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Langenprozelten",2023,2023,9,9,"2023-03-02","22:00:00","2023-03-03","06:00:00","0d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,21,21,"2023-05-22","22:50:00","2023-05-23","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,21,21,"2023-05-22","22:50:00","2023-05-23","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,48,48,"2023-11-27","22:50:00","2023-11-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Heppenhm/Bergstr",2023,2023,24,48,"2023-06-18","06:00:00","2023-12-03","13:00:00","168d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-12-02"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Pragtunnel",2023,2023,48,49,"2023-11-30","01:30:00","2023-12-09","23:59:00","9d, 22h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-19"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Feucht","Ochenbruck",2023,2023,24,25,"2023-06-18","00:01:00","2023-06-21","05:00:00","3d, 4h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-04"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108","<>","Feucht","Feucht",2023,2023,23,28,"2023-06-09","06:00:00","2023-07-14","22:00:00","35d, 16h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-03"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,27,28,"2023-07-05","22:00:00","2023-07-14","22:00:00","9d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108",">","Nür-Dürrenhof","Feucht",2023,2023,27,27,"2023-07-05","22:00:00","2023-07-06","05:00:00","0d, 7h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Ochenbruck","Reichswald",2023,2023,27,28,"2023-07-06","00:00:00","2023-07-14","05:00:00","8d, 5h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,20,20,"2023-05-15","06:00:00","2023-05-15","18:00:00","0d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-03"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,24,24,"2023-06-14","22:00:00","2023-06-15","06:00:00","0d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Ochenbruck","Reichswald",2023,2023,26,26,"2023-06-29","22:00:00","2023-06-30","04:00:00","0d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-04"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,26,26,"2023-06-28","06:00:00","2023-06-29","06:00:00","1d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-04"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108",">","Nür Frankenstad","Feucht",2023,2023,26,27,"2023-07-01","00:00:00","2023-07-05","05:00:00","4d, 5h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-16"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108",">","Nür-Dürrenhof","Feucht",2023,2023,26,26,"2023-06-29","22:00:00","2023-06-30","04:00:00","0d, 6h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Feucht","Reichswald",2023,2023,26,27,"2023-06-30","04:00:00","2023-07-05","22:00:00","5d, 18h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,49,49,"2023-12-04","22:50:00","2023-12-05","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,49,49,"2023-12-04","22:50:00","2023-12-05","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Mangolding",2023,2023,20,21,"2023-05-21","21:00:00","2023-05-26","05:00:00","4d, 8h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,15,16,"2023-04-16","22:00:00","2023-04-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,26,26,"2023-06-26","22:50:00","2023-06-27","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,35,35,"2023-08-28","22:50:00","2023-08-29","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,3,3,"2023-01-16","22:50:00","2023-01-17","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,8,8,"2023-02-20","23:20:00","2023-02-21","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Partenstein","Wiesthal",2023,2023,44,45,"2023-10-30","23:00:00","2023-11-09","05:00:00","9d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Wiesthal","Partenstein",2023,2023,48,49,"2023-11-27","23:00:00","2023-12-07","05:00:00","9d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Wiesthal","Aburg-Goldbach",2023,2023,46,46,"2023-11-15","22:00:00","2023-11-18","05:00:00","2d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,2,2,"2023-01-09","22:50:00","2023-01-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,10,48,"2023-03-11","23:00:00","2023-12-03","05:00:00","266d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-10"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Nür Rbf Ausfahrt",2023,2023,25,25,"2023-06-20","00:00:00","2023-06-21","11:00:00","1d, 11h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,27,28,"2023-07-07","00:00:00","2023-07-11","06:00:00","4d, 6h","periodical continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,26,28,"2023-07-02","06:00:00","2023-07-11","06:00:00","9d, 0h","continuous",null,null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,26,27,"2023-07-02","00:00:00","2023-07-03","06:00:00","1d, 6h","periodical continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-26","04:00:00","2023-04-27","04:00:00","1d, 0h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Blankenloch","Graben-Neudorf",2023,2023,16,17,"2023-04-20","10:30:00","2023-04-26","04:00:00","5d, 17h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Rheinsh4132/3450","Graben-Neudorf",2023,2023,17,17,"2023-04-26","04:00:00","2023-04-28","11:00:00","2d, 7h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Molzau","Molzau",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-20","06:30:00","5d, 9h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Bruchsal","Graben-Neudorf",2023,2023,17,17,"2023-04-26","19:30:00","2023-04-28","11:00:00","1d, 15h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Rheinsh4132/3450",2023,2023,17,17,"2023-04-26","19:30:00","2023-04-28","11:00:00","1d, 15h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Blankenloch","Graben-Neudorf",2023,2023,17,17,"2023-04-28","11:00:00","2023-04-28","19:00:00","0d, 8h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Molzau","Molzau",2023,2023,17,17,"2023-04-28","11:00:00","2023-04-28","19:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,44,44,"2023-10-30","23:20:00","2023-10-31","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,17,18,"2023-04-30","22:00:00","2023-05-01","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,11,11,"2023-03-14","00:40:00","2023-03-15","04:50:00","1d, 4h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2d, 2h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart-Untertürkheim, W 45 - Kornwestheim Pbf, W 453","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,11,"2023-03-09","05:00:00","2023-03-13","04:00:00","3d, 23h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,28,28,"2023-07-10","22:00:00","2023-07-11","05:00:00","0d, 7h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,28,28,"2023-07-11","22:00:00","2023-07-12","05:00:00","0d, 7h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Radldorf (Nbay)",2023,2023,27,27,"2023-07-05","22:00:00","2023-07-07","05:00:00","1d, 7h","periodical continuous","Catenary",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-05"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,30,30,"2023-07-24","23:20:00","2023-07-25","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,24,26,"2023-06-16","22:00:00","2023-06-26","06:00:00","9d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,23,26,"2023-06-05","06:00:00","2023-06-28","18:00:00","23d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,4,4,"2023-01-23","22:50:00","2023-01-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Westerstetten","Beimerstetten",2023,2023,27,27,"2023-07-08","05:00:00","2023-07-09","21:00:00","1d, 16h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm-Örlingen","Beimerstetten",2023,2023,25,28,"2023-06-23","21:00:00","2023-07-10","05:00:00","16d, 8h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm-Örlingen","Gingen Süd",2023,2023,25,28,"2023-06-23","21:00:00","2023-07-10","05:00:00","16d, 8h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Beimerstetten","Ulm-Örlingen",2023,2023,26,26,"2023-07-01","05:00:00","2023-07-02","21:00:00","1d, 16h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Beimerstetten","Beimerstetten",2023,2023,25,28,"2023-06-19","00:00:00","2023-07-15","00:00:00","26d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Westerstetten","Beimerstetten",2023,2023,26,26,"2023-07-01","05:00:00","2023-07-02","21:00:00","1d, 16h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Geislingen (St)","Geislingen (St)",2023,2023,25,28,"2023-06-19","00:00:00","2023-07-15","00:00:00","26d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,41,42,"2023-10-15","22:00:00","2023-10-20","21:00:00","4d, 23h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,30,33,"2023-07-29","23:00:00","2023-08-16","05:00:00","17d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Karlstadt (Main)",2023,2023,37,37,"2023-09-16","22:00:00","2023-09-17","06:00:00","0d, 8h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,45,45,"2023-11-06","23:00:00","2023-11-11","05:00:00","4d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Karlstadt (Main)","Gemünden (Main)",2023,2023,35,36,"2023-09-03","23:00:00","2023-09-06","05:00:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,35,36,"2023-09-03","23:00:00","2023-09-06","05:00:00","2d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,41,44,"2023-10-09","06:00:00","2023-11-05","20:00:00","27d, 15h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Karlstadt (Main)",2023,2023,27,30,"2023-07-07","23:00:00","2023-07-29","05:00:00","21d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Karlstadt (Main)",2023,2023,45,45,"2023-11-06","04:00:00","2023-11-07","04:00:00","1d, 0h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-11-17"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Karlstadt (Main)","Gemünden (Main)",2023,2023,33,35,"2023-08-16","23:00:00","2023-09-03","05:00:00","17d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Karlstadt (Main)","Gemünden (Main)",2023,2023,30,33,"2023-07-29","23:00:00","2023-08-16","05:00:00","17d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,24,27,"2023-06-15","23:00:00","2023-07-07","05:00:00","21d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023.01369133667,2023.0012893104099,25.848006874112698,26.881402042986402,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023.0138932976199,2023.0013126757401,25.8534120948169,26.8845652113014,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023.0140279382499,2023.0013282526299,25.8570155752864,26.8866739901781,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023.0142972195199,2023.0013594064001,25.864222536225402,26.8908915479314,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Durmersheim",2023.01436453984,2023.00136719484,25.866024276460099,26.891945937369702,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous",null,null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023.0146338211,2023.0013983486101,25.873231237399001,26.896163495123002,"2023-06-12","07:00:00","2023-06-19","07:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Aschaffenbg Hbf","Nantenbach",2023.0147011414199,2023.00140613706,25.875032977633801,26.8972178845613,"2022-12-17","22:00:00","2023-12-03","05:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-12"]
[null,80,"Eltersdorf, 28W402 - RB-Grenze km 117,357 - Erfurt Hbf - Leipzig Hbf, Gl 12 (Gröbers - Lpz-Mockau Personenzugbahn)","<","Unterleiterbach","Eltersdorf",2023.0148357820501,2023.0014217139401,25.878636458103198,26.899326663438,"2022-12-15","22:30:00","2023-12-08","05:40:00","357d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-11-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Durlach",2023.015037743,2023.0014450792701,25.884041678807499,26.902489831753002,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-26"]
[null,80,"Mainz-Bischofsheim, W 6 - Darmstadt Hbf, W 315",">","Mz-Bisch Überl I","Darmstadt Gbf",2023.01530702427,2023.00147623304,25.891248639746401,26.906707389506298,"2022-12-17","23:50:00","2023-12-03","04:50:00","350d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-15"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 73","<>","Mü-Waldtrudering","München-Daglfing",2023.0154416649,2023.00149180993,25.894852120215901,26.908816168383002,"2023-02-18","06:00:00","2023-02-26","22:00:00","8d, 16h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023.0156436258501,2023.00151517525,25.900257340920099,26.9119793366979,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023.0158455868,2023.00153854058,25.9056625616243,26.915142505012899,"2023-05-01","18:00:00","2023-05-02","06:00:00","0d, 12h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023.01598022743,2023.0015541174701,25.909266042093801,26.917251283889598,"2023-07-07","07:00:00","2023-07-13","18:00:00","6d, 11h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023.0160475477501,2023.00156190591,25.911067782328502,26.9183056733279,"2023-07-14","18:00:00","2023-07-21","18:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Achern (F)",2023.0163168290101,2023.0015930596801,25.9182747432674,26.9225232310812,"2023-08-01","23:30:00","2023-09-30","06:00:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-06"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Achern (F)",2023.0164514696501,2023.0016086365699,25.921878223736901,26.9246320099579,"2023-04-01","23:30:00","2023-05-31","06:00:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-07-28"]
[null,80,"Olching - Augsburg Hbf",">","Olching","Maisach Abzw",2023.0166534305899,2023.0016320018999,25.927283444441098,26.927795178272898,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"München Hbf - Augsburg Hbf",">","Olching","Mering Üst",2023.0167880712299,2023.00164757878,25.930886924910599,26.929903957149499,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023.0170573524899,2023.0016787325501,25.938093885849501,26.934121514902799,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5561","<>","Olching","Mü Nord Rbf For",2023.01712467281,2023.001686521,25.939895626084301,26.9351759043412,"2023-04-04","09:00:00","2023-04-29","16:00:00","25d, 7h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023.01739395408,2023.0017176747699,25.947102587023199,26.9393934620945,"2023-04-02","00:00:00","2023-04-30","05:00:00","28d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023.0174612743899,2023.0017254632101,25.948904327257999,26.940447851532799,"2023-03-05","00:00:00","2023-04-02","05:00:00","28d, 4h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023.0175959150199,2023.0017410400901,25.9525078077274,26.942556630409499,"2023-10-30","06:00:00","2023-10-30","20:00:00","0d, 14h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5561",">","Olching","Mü Nord Rbf For",2023.01779787597,2023.0017644054201,25.957913028431701,26.945719798724401,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5561","<>","Olching","Mü Nord Rbf For",2023.0179998369199,2023.0017877707501,25.963318249135899,26.948882967039399,"2023-04-08","22:00:00","2023-04-24","16:00:00","15d, 18h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-28"]
[null,80,"Schnabelwaid, W 21 - Bayreuth Hbf, W 46","<>","Schnabelwaid","Bayreuth Hbf",2023.0181344775599,2023.0018033476399,25.9669217296053,26.950991745916099,"2023-08-12","01:30:00","2023-08-28","04:50:00","16d, 3h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-11-25"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023.0184037588201,2023.00183450141,25.974128690544301,26.955209303669399,"2023-03-31","21:40:00","2023-04-03","05:40:00","2d, 8h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023.01860571977,2023.00185786674,25.979533911248499,26.958372471984401,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023.0187403604,2023.0018734436201,25.983137391718,26.960481250861001,"2023-04-11","06:00:00","2023-04-14","22:00:00","3d, 16h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim",2023.0188076807201,2023.00188123206,25.9849391319527,26.961535640299399,"2023-03-18","23:00:00","2023-03-19","06:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023.0190769619901,2023.0019123858399,25.992146092891598,26.965753198052699,"2023-03-10","22:00:00","2023-03-13","22:00:00","3d, 0h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023.0192116026201,2023.0019279627199,25.995749573361099,26.967861976929299,"2023-04-14","22:00:00","2023-04-17","22:00:00","3d, 0h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023.01941356357,2023.0019513280499,26.0011547940653,26.971025145244301,"2023-03-24","21:40:00","2023-03-27","05:40:00","2d, 7h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023.0195482042,2023.00196690493,26.004758274534801,26.973133924121001,"2023-03-25","21:40:00","2023-03-27","05:40:00","1d, 7h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023.0197501651501,2023.00199027026,26.010163495238999,26.9762970924359,"2023-02-18","00:00:00","2023-02-27","05:00:00","9d, 5h","periodical continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023.0199521261,2023.0020136355899,26.0155687159432,26.979460260750901,"2023-03-03","22:00:00","2023-03-06","06:00:00","2d, 8h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023.0200194464201,2023.0020214240301,26.017370456178,26.980514650189299,"2023-03-13","22:00:00","2023-03-17","06:00:00","3d, 8h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023.0202214073699,2023.0020447893601,26.022775676882201,26.983677818504301,"2023-04-17","22:00:00","2023-04-21","06:00:00","3d, 8h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 644","<>","Plochingen","Plochingen",2023.0203560479999,2023.0020603662499,26.026379157351599,26.985786597380901,"2023-10-27","12:00:00","2023-11-04","12:00:00","8d, 1h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Prien a Chiemsee","Traunstein",2023.02055800895,2023.0020837315799,26.0317843780558,26.988949765695899,"2023-04-03","00:30:00","2023-04-07","04:30:00","4d, 4h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023.0207599698999,2023.0021070969001,26.037189598760101,26.992112934010901,"2023-09-11","06:00:00","2023-09-12","22:00:00","1d, 16h","periodical continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Rottau",2023.0208946105299,2023.0021226737899,26.040793079229498,26.994221712887501,"2023-11-06","06:00:00","2023-11-06","14:00:00","0d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Übersee",2023.0211638917899,2023.0021538275601,26.0480000401685,26.998439270640802,"2023-11-19","14:00:00","2023-11-22","22:00:00","3d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rottau",2023.02123121211,2023.002161616,26.0498017804032,26.999493660079199,"2023-11-17","22:00:00","2023-11-19","14:00:00","1d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023.02136585274,2023.00217719289,26.053405260872701,27.0016024389558,"2023-04-28","22:00:00","2023-04-29","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Rottau",2023.0215678136899,2023.00220055822,26.058810481576899,27.004765607270802,"2023-04-30","22:00:00","2023-05-02","06:00:00","1d, 8h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Traunstein","Übersee",2023.0217024543299,2023.0022161351001,26.062413962046399,27.006874386147501,"2023-10-15","06:00:00","2023-10-15","22:00:00","0d, 16h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rottau",2023.0219717355899,2023.00224728887,26.069620922985301,27.011091943900801,"2023-04-29","22:00:00","2023-04-30","22:00:00","1d, 0h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-18"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Rottau",2023.02217369654,2023.0022706541999,26.075026143689499,27.0142551122158,"2023-11-09","00:00:00","2023-11-10","05:00:00","1d, 5h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining (Oberpf)","Nürnberg Hbf",2023.0223756574901,2023.0022940195299,26.0804313643937,27.017418280530698,"2022-12-17","23:00:00","2023-12-03","06:00:00","350d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-05-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Appenweier",2023.0225102981201,2023.00230959642,26.084034844863201,27.019527059407402,"2023-11-06","21:00:00","2023-11-11","02:00:00","4d, 5h","continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Appenweier","Appenweier",2023.02271225907,2023.00233296174,26.089440065567398,27.0226902277224,"2023-11-06","21:00:00","2023-11-13","04:30:00","6d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Mü Hirschgarten",2023.02284689971,2023.00234853863,26.093043546036899,27.024799006599,"2023-04-06","22:40:00","2023-04-11","04:40:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"München Hbf tief - Gauting, 35W22","<","München-Pasing","Mü Hirschgarten",2023.0229142200201,2023.0023563270699,26.0948452862716,27.025853396037402,"2023-04-28","22:40:00","2023-05-02","04:40:00","3d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-27"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023.0231835012901,2023.0023874808401,26.102052247210601,27.030070953790698,"2023-10-06","22:50:00","2023-10-07","10:50:00","0d, 12h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-28"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W706","<>","München-Pasing","Mü Friedenhei Br",2023.0233181419201,2023.0024030577299,26.105655727679999,27.032179732667299,"2023-06-16","21:20:00","2023-06-17","18:20:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"München Hbf tief - Gauting, 35W23",">","Mü Hirschgarten","München-Pasing",2023.02352010287,2023.0024264230599,26.111060948384299,27.0353429009823,"2023-02-07","22:40:00","2023-03-20","04:40:00","40d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2023.0236547434999,2023.0024419999399,26.1146644288537,27.037451679859,"2023-06-17","18:20:00","2023-06-18","00:20:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023.0239240247699,2023.0024731537101,26.121871389792702,27.0416692376123,"2023-08-12","00:50:00","2023-08-12","18:50:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W706","<>","München-Pasing","Mü Friedenhei Br",2023.02399134508,2023.00248094216,26.123673130027399,27.042723627050599,"2023-08-11","21:50:00","2023-08-12","18:50:00","0d, 21h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-08"]
[null,80,"München Hbf - Augsburg Hbf","<>","München Hbf","München-Pasing",2023.02412598572,2023.0024965190401,26.127276610496899,27.044832405927298,"2023-06-17","00:20:00","2023-06-17","18:20:00","0d, 18h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-17"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Achern",2023.0243279466699,2023.00251988437,26.132681831201101,27.0479955742423,"2023-10-31","22:00:00","2023-11-03","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt-Süd","Achern",2023.0244625872999,2023.0025354612601,26.136285311670601,27.0501043531189,"2023-02-01","23:30:00","2023-03-31","06:00:00","57d, 5h","periodical continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-06"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen","<>","München Ost Pbf","Mü-Steinhausen",2023.02466454825,2023.0025588265801,26.141690532374799,27.053267521433899,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf","<>","Mü-Berg a L Abzw","Mü-Trudering",2023.0248665091999,2023.0025821919101,26.147095753079,27.0564306897489,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-04-19"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023.0251357904599,2023.0026133456799,26.154302714017899,27.060648247502201,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Bashaide",2023.0252704310999,2023.00262892257,26.157906194487399,27.0627570263789,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023.02547239205,2023.0026522879,26.1633114151916,27.065920194693799,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Göppingen","Göppingen",2023.02560703268,2023.0026678647801,26.166914895661101,27.068028973570499,"2023-05-29","08:00:00","2023-07-26","16:00:00","58d, 8h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023.0256743530001,2023.00267565323,26.168716635895802,27.069083363008801,"2023-01-22","21:00:00","2023-01-23","21:00:00","1d, 0h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 205","<>","Freilassing","Freilassing",2023.0259436342601,2023.0027068070001,26.175923596834799,27.073300920762101,"2023-05-18","21:00:00","2023-05-19","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023.0260782748901,2023.0027223838799,26.179527077304201,27.075409699638801,"2023-01-23","21:00:00","2023-07-21","23:59:00","179d, 1h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023.02628023584,2023.0027457492099,26.184932298008501,27.078572867953799,"2023-07-21","05:00:00","2023-12-09","23:59:00","141d, 19h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023.0264821967901,2023.0027691145399,26.190337518712699,27.081736036268801,"2023-07-25","05:00:00","2023-12-09","23:59:00","137d, 19h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"Y","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023.0266168374301,2023.0027846914199,26.1939409991821,27.083844815145401,"2023-01-18","02:00:00","2023-01-22","05:00:00","4d, 3h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 275","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023.02681879837,2023.0028080567499,26.199346219886301,27.087007983460399,"2023-09-25","18:00:00","2023-10-09","18:00:00","14d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.0268861186901,2023.0028158452001,26.201147960121101,27.088062372898701,"2023-09-25","18:00:00","2023-10-09","18:00:00","14d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023.02708807964,2023.0028392105201,26.206553180825299,27.091225541213699,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023.0272900405901,2023.00286257585,26.2119584015295,27.094388709528701,"2023-09-25","22:50:00","2023-09-26","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W003",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023.0274246812201,2023.0028781527401,26.215561881999001,27.096497488405401,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-20"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal","Graben-Neudorf",2023.0276266421699,2023.0029015180701,26.220967102703199,27.0996606567203,"2023-01-15","22:00:00","2023-02-17","04:45:00","32d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<","Graben-Neudorf","Bruchsal-Sport",2023.0277612827999,2023.0029170949499,26.224570583172699,27.101769435596999,"2023-01-15","22:00:00","2023-02-24","04:45:00","39d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal-Sport","Graben-Neudorf",2023.0280305640699,2023.00294824872,26.231777544111601,27.105986993350299,"2022-12-11","22:00:00","2022-12-23","04:45:00","11d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Bruchsal-Sport","Graben-Neudorf",2023.02809788439,2023.00295603717,26.233579284346298,27.107041382788601,"2023-01-15","22:00:00","2023-02-24","04:45:00","39d, 6h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-07-15"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450",">","Graben-Neudorf","Graben-Neudorf",2023.02823252502,2023.00297161405,26.237182764815799,27.109150161665301,"2023-01-15","23:35:00","2023-01-27","05:15:00","11d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-07-23"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberstadt","Pfungstadt",2023.0284344859699,2023.00299497938,26.24258798552,27.112313329980299,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Da-Eberst Nord",2023.0287037672299,2023.0030261331499,26.249794946459001,27.1165308877336,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Bamberg - Hof Hbf, W 122","<>","Bamberg","Bamberg",2023.0288384078699,2023.00304171004,26.253398426928399,27.1186396666102,"2023-01-14","22:45:00","2023-01-29","06:45:00","14d, 8h","periodical continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-13"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W003",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023.02904036882,2023.0030650753599,26.2588036476327,27.121802834925202,"2023-11-26","22:00:00","2023-11-27","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.0292423297701,2023.0030884406899,26.264208868336901,27.1249660032402,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023.0293769704001,2023.00310401758,26.267812348806299,27.1270747821169,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023.02944429071,2023.0031118060199,26.269614089041099,27.128129171555202,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023.02971357198,2023.00314295979,26.276821049980001,27.132346729308502,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W003",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023.0297808923001,2023.0031507482299,26.278622790214801,27.1334011187468,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.0300501735601,2023.0031819020101,26.285829751153699,27.1376186765001,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Ebelsbach-Eltm",2023.0301848142001,2023.0031974788899,26.2894332316232,27.1397274553768,"2023-04-09","08:00:00","2023-04-09","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/183",">","N-Edingen/F-feld","Schwetzingen",2023.03038677514,2023.0032208442201,26.294838452327401,27.142890623691802,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach Nord","Zwingenbg/Bergst",2023.03052141578,2023.0032364210999,26.298441932796901,27.144999402568398,"2023-05-01","22:00:00","2023-05-03","04:00:00","1d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023.0307906970399,2023.0032675748801,26.3056488937358,27.149216960321802,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach",2023.0308580173601,2023.00327536332,26.3074506339705,27.1502713497601,"2023-10-29","00:00:00","2023-10-29","06:00:00","0d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach","Bickenbach",2023.0309926579901,2023.0032909402,26.311054114440001,27.1523801286367,"2023-04-28","06:00:00","2023-05-03","06:00:00","5d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023.0311946189399,2023.00331430553,26.316459335144199,27.155543296951699,"2023-05-15","03:00:00","2023-05-15","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023.03139657989,2023.00333767086,26.3218645558484,27.1587064652667,"2023-04-11","22:00:00","2023-04-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023.03153122052,2023.0033532477501,26.325468036317901,27.1608152441434,"2023-02-07","22:00:00","2023-02-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023.03180050179,2023.00338440152,26.332674997256799,27.1650328018967,"2023-11-14","22:00:00","2023-11-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-09"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023.0320024627399,2023.0034077668499,26.3380802179611,27.168195970211698,"2023-09-08","23:00:00","2023-09-13","05:00:00","4d, 6h","periodical continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W003",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023.0321371033699,2023.00342334373,26.341683698430501,27.170304749088299,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023.03220442369,2023.0034311321699,26.343485438665301,27.1713591385267,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023.03247370495,2023.00346228595,26.350692399604199,27.17557669628,"2023-01-18","23:30:00","2023-01-30","05:30:00","11d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim Hbf Ost",2023.0325410252699,2023.00347007439,26.352494139838999,27.176631085718299,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Schwetzingen",2023.0328103065399,2023.0035012281601,26.359701100777901,27.180848643471599,"2023-02-04","22:30:00","2023-02-13","05:30:00","8d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023.0329449471701,2023.0035168050399,26.363304581247402,27.182957422348299,"2023-01-30","23:30:00","2023-02-02","05:30:00","2d, 6h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-05-31"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023.03314690812,2023.0035401703699,26.368709801951599,27.186120590663201,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<","Stg-Obertürkheim","Neckarpark",2023.0333488690701,2023.0035635357001,26.374115022655801,27.189283758978199,"2023-04-08","01:00:00","2023-04-10","04:00:00","2d, 3h","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023.03355083002,2023.0035869010301,26.379520243359998,27.192446927293201,"2023-05-07","22:25:00","2023-07-10","06:00:00","63d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023.0336181503301,2023.00359468947,26.381321983594699,27.193501316731499,"2023-05-06","22:25:00","2023-07-09","07:25:00","63d, 9h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-04-22"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023.0337527909701,2023.0036102663601,26.384925464064199,27.195610095608199,"2023-11-09","00:30:00","2023-11-10","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023.03395475191,2023.00363363169,26.390330684768401,27.198773263923201,"2023-09-24","21:30:00","2023-10-09","04:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023.0341567128601,2023.00365699701,26.395735905472598,27.201936432238199,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023.0342913535001,2023.0036725739001,26.399339385942099,27.204045211114799,"2023-09-09","22:30:00","2023-09-24","05:30:00","14d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023.0345606347601,2023.00370372767,26.406546346881001,27.208262768868099,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Waghäusel","Waghäusel",2023.0346279550799,2023.0037115161099,26.408348087115801,27.209317158306501,"2023-07-29","22:30:00","2023-08-14","05:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Hockenheim",2023.0348972363399,2023.00374266988,26.415555048054699,27.213534716059801,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Schwetzingen","Schwetzingen",2023.03496455666,2023.0037504583299,26.417356788289499,27.214589105498099,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Schwetzingen",2023.03509919729,2023.00376603521,26.4209602687589,27.2166978843747,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Oftersheim","Waghäusel",2023.03536847856,2023.0037971889799,26.428167229697902,27.220915442128099,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Hockenheim","Waghäusel",2023.0355704395099,2023.0038205543101,26.433572450402099,27.224078610443101,"2023-07-31","23:30:00","2023-08-18","04:30:00","17d, 5h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-10-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Schwetzingen","Waghäusel",2023.0357050801399,2023.0038361311999,26.4371759308716,27.226187389319701,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023.03590704109,2023.0038594965299,26.442581151575801,27.229350557634699,"2023-10-14","22:00:00","2023-10-23","05:00:00","8d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023.0361090020399,2023.0038828618499,26.447986372279999,27.232513725949701,"2023-08-20","00:30:00","2023-09-04","04:30:00","15d, 4h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023.0362436426699,2023.00389843874,26.4515898527495,27.234622504826302,"2023-10-28","22:00:00","2023-11-06","05:00:00","8d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Mannheim-Rheinau",2023.03631096299,2023.0039062271801,26.4533915929842,27.235676894264699,"2023-09-25","00:30:00","2023-10-09","04:30:00","14d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Hockenheim","Schwetzingen",2023.03658024426,2023.00393738095,26.460598553923099,27.239894452018,"2023-08-18","23:30:00","2023-09-07","04:30:00","19d, 5h","periodical continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Hockenheim","Hockenheim",2023.03671488489,2023.0039529578401,26.464202034392599,27.2420032308946,"2023-09-07","23:30:00","2023-10-05","04:30:00","27d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/183","<>","Schwetzingen","Schwetzingen",2023.0369168458401,2023.00397632317,26.4696072550968,27.245166399209602,"2023-08-19","21:30:00","2023-09-04","04:30:00","15d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Waghäusel","Hockenheim",2023.0370514864701,2023.0039919000501,26.473210735566301,27.247275178086301,"2023-11-07","00:30:00","2023-11-08","04:30:00","1d, 4h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 278",">","Augsb-Oberhausen","Augsb Hirbl Str",2023.0373207677401,2023.00402305382,26.480417696505199,27.251492735839602,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-12"]
[null,80,"Augsburg Hbf - Nördlingen","<","Gersthofen","Augsburg Hbf",2023.03738808805,2023.0040308422699,26.482219436739999,27.2525471252779,"2023-07-21","22:00:00","2023-07-29","04:00:00","7d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023.03752272869,2023.00404641915,26.4858229172095,27.2546559041546,"2023-07-21","22:00:00","2023-07-29","06:00:00","7d, 8h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023.0377246896301,2023.00406978448,26.491228137913701,27.257819072469601,"2023-07-29","06:00:00","2023-07-31","09:00:00","2d, 3h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023.0378593302701,2023.00408536137,26.494831618383099,27.259927851346198,"2023-04-17","23:20:00","2023-04-18","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023.0380612912199,2023.00410872669,26.5002368390873,27.2630910196612,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023.0382632521701,2023.00413209202,26.505642059791601,27.266254187976202,"2023-07-24","03:00:00","2023-07-24","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.0383978928,2023.00414766891,26.509245540260999,27.268362966852798,"2023-10-27","23:00:00","2023-10-30","05:00:00","2d, 7h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.03866717406,2023.0041788226799,26.5164525012,27.272580524606099,"2023-10-27","22:00:00","2023-10-30","06:00:00","2d, 9h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.0388691350099,2023.0042021880099,26.521857721904201,27.2757436929211,"2023-10-31","00:00:00","2023-11-01","05:00:00","1d, 5h","periodical continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.0390037756499,2023.00421776489,26.525461202373702,27.2778524717978,"2023-10-21","06:00:00","2023-10-30","18:00:00","9d, 13h","continuous","Switch",null,null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023.03907109596,2023.0042255533399,26.527262942608399,27.278906861236099,"2023-12-07","22:00:00","2023-12-08","05:00:00","0d, 7h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023.03934037723,2023.00425670711,26.534469903547301,27.283124418989399,"2023-05-12","20:00:00","2023-05-22","12:00:00","9d, 16h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023.03947501786,2023.0042722839901,26.538073384016801,27.285233197866098,"2023-05-20","12:00:00","2023-05-22","12:00:00","2d, 0h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023.0396769788099,2023.0042956493201,26.543478604720999,27.2883963661811,"2023-05-21","10:00:00","2023-05-21","17:45:00","0d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023.0398116194399,2023.0043112262099,26.5470820851905,27.290505145057701,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-18"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023.04001358039,2023.0043345915301,26.552487305894701,27.293668313372699,"2023-06-10","16:00:00","2023-06-11","19:00:00","1d, 3h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023.0402155413401,2023.0043579568601,26.557892526598899,27.2968314816877,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023.04028286166,2023.00436574531,26.559694266833699,27.297885871125999,"2023-06-12","05:00:00","2023-06-19","05:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023.0404848226101,2023.00438911063,26.5650994875379,27.301049039441001,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023.0406194632401,2023.00440468752,26.568702968007301,27.3031578183177,"2023-05-22","12:00:00","2023-05-22","18:00:00","0d, 6h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023.04082142419,2023.00442805285,26.574108188711499,27.306320986632599,"2023-05-10","12:00:00","2023-06-19","05:00:00","39d, 17h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023.0410233851401,2023.00445141818,26.579513409415799,27.309484154947601,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.0411580257701,2023.0044669950601,26.583116889885201,27.311592933824301,"2023-07-10","22:50:00","2023-07-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 144","<>","Babenhausen","Darmstadt Hbf",2023.0414273070401,2023.00449814883,26.590323850824198,27.315810491577601,"2022-12-17","22:30:00","2023-12-03","05:30:00","350d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-09-17"]
[null,80,"Hallstadt (b Bamberg) - Abzw Höflein","<>","Hallstadt(Bambg)","Höflein",2023.0414946273499,2023.0045059372801,26.592125591058899,27.316864881015899,"2023-11-10","22:30:00","2023-11-13","05:00:00","2d, 6h","periodical continuous","Catenary","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-26"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023.0416292679899,2023.0045215141599,26.5957290715284,27.318973659892599,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023.0418312289401,2023.0045448794899,26.601134292232601,27.322136828207601,"2023-04-01","05:00:00","2023-04-08","21:00:00","7d, 16h","periodical continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023.0421005102,2023.00457603326,26.608341253171499,27.326354385960901,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Nantenbach",2023.04223515083,2023.0045916101501,26.611944733641,27.328463164837501,"2023-10-28","23:30:00","2023-11-20","04:30:00","22d, 6h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023.0424371117799,2023.0046149754701,26.617349954345201,27.331626333152499,"2023-10-26","06:00:00","2023-11-29","18:00:00","34d, 13h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Lohr Bahnhof",2023.04263907273,2023.0046383408001,26.622755175049399,27.334789501467501,"2023-11-25","14:00:00","2023-11-26","12:00:00","0d, 22h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023.04277371337,2023.0046539176899,26.626358655518899,27.336898280344201,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 3","<>","Karlsruhe Hbf","Karlsr-Durlach",2023.0429756743199,2023.0046772830201,26.631763876223101,27.3400614486591,"2023-05-26","12:00:00","2023-05-30","05:00:00","3d, 17h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-13"]
[null,80,"Karlsruhe Gbf, W 118 - Karlsruhe-Durlach , W 53","<>","Karlsruhe Gbf","Karlsr-Durlach",2023.0431103149499,2023.0046928598999,26.635367356692601,27.342170227535799,"2023-10-22","12:00:00","2023-10-23","12:00:00","1d, 0h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 52","<>","Karlsr-Durlach","Karlsruhe Gbf",2023.04317763526,2023.0047006483401,26.637169096927298,27.343224616974101,"2023-10-20","22:00:00","2023-10-23","12:00:00","2d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-17"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023.04344691653,2023.00473180212,26.6443760578663,27.347442174727401,"2023-03-06","03:00:00","2023-03-06","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023.04358155716,2023.004747379,26.647979538335701,27.349550953604101,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023.0437835181101,2023.00477074433,26.653384759040001,27.352714121919099,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023.0439181587501,2023.0047863212101,26.656988239509399,27.3548229007957,"2023-04-20","18:00:00","2023-04-27","18:00:00","7d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-05-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023.0441874400101,2023.00481747499,26.6641952004484,27.359040458549,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.04425476033,2023.0048252634299,26.665996940683101,27.360094847987401,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023.04438940096,2023.00484084031,26.669600421152602,27.362203626864002,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023.0445913619101,2023.0048642056399,26.675005641856799,27.365366795179,"2023-09-22","18:00:00","2023-10-09","12:00:00","16d, 18h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Partenstein","Lohr Bahnhof",2023.04479332286,2023.0048875709699,26.680410862561001,27.368529963494002,"2023-09-23","14:00:00","2023-10-09","05:00:00","15d, 15h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Laufach","Wiesthal",2023.04492796349,2023.00490314786,26.684014343030501,27.370638742370701,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023.0451299244401,2023.00492651318,26.689419563734699,27.3738019106856,"2023-04-13","06:00:00","2023-04-26","18:00:00","13d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023.0453992057101,2023.0049576669601,26.696626524673601,27.3780194684389,"2023-04-14","18:00:00","2023-04-24","12:00:00","9d, 18h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023.04553384634,2023.0049732438399,26.700230005143101,27.3801282473156,"2023-09-25","05:00:00","2023-10-10","12:00:00","15d, 7h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023.0457358072899,2023.0049966091699,26.705635225847299,27.383291415630602,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Wiesthal",2023.0458704479199,2023.00501218605,26.7092387063168,27.385400194507302,"2023-10-07","23:30:00","2023-10-09","04:30:00","1d, 5h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023.04593776824,2023.0050199745001,26.7110404465515,27.3864545839456,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-09-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023.0462070495,2023.00505112827,26.718247407490502,27.3906721416989,"2023-06-26","23:20:00","2023-06-27","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023.04634169014,2023.0050667051501,26.721850887959899,27.3927809205755,"2023-11-03","23:00:00","2023-11-08","05:00:00","4d, 6h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023.0465436510899,2023.00509007048,26.727256108664101,27.395944088890499,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023.04674561203,2023.00511343581,26.732661329368401,27.3991072572055,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.04688025267,2023.0051290127001,26.736264809837799,27.4012160360822,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/183",">","N-Edingen/F-feld","Schwetzingen",2023.0469475729799,2023.00513680114,26.738066550072599,27.402270425520499,"2023-11-12","22:00:00","2023-11-13","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023.04714953393,2023.00516016647,26.7434717707768,27.4054335938355,"2023-02-18","22:00:00","2023-02-20","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023.0473514948801,2023.0051835318,26.748876991481001,27.408596762150498,"2023-02-04","22:00:00","2023-02-06","05:00:00","1d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Seubersdorf","Parsberg",2023.04755345583,2023.0052068971199,26.754282212185199,27.4117599304655,"2023-06-12","22:00:00","2023-06-30","05:00:00","17d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/183",">","N-Edingen/F-feld","Schwetzingen",2023.04768809646,2023.00522247401,26.7578856926547,27.413868709342101,"2023-06-11","22:00:00","2023-06-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-07"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.0478900574101,2023.00524583934,26.763290913358901,27.417031877657099,"2023-06-12","22:50:00","2023-06-13","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Hbf",2023.0480246980501,2023.00526141622,26.766894393828402,27.419140656533799,"2023-04-26","17:00:00","2023-04-27","07:00:00","0d, 14h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-14"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Darmstadt Hbf","Darmstadt Hbf",2023.0482939793101,2023.0052925699899,26.7741013547673,27.423358214287099,"2023-04-11","01:00:00","2023-04-11","21:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023.04836129963,2023.0053003584401,26.775903095002,27.424412603725401,"2023-05-06","17:00:00","2023-05-08","04:00:00","1d, 11h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Gbf","Darmstadt Hbf",2023.04849594026,2023.0053159353199,26.779506575471501,27.426521382602001,"2023-05-24","04:00:00","2023-05-24","10:00:00","0d, 6h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-15"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023.0486979012101,2023.0053393006499,26.784911796175699,27.429684550916999,"2023-04-01","14:00:00","2023-04-03","04:00:00","1d, 14h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Hbf","Darmstadt Gbf",2023.0489671824801,2023.00537045442,26.7921187571147,27.433902108670299,"2023-04-08","21:00:00","2023-04-09","17:00:00","0d, 20h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-08-20"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.04910182311,2023.0053860313101,26.795722237584101,27.436010887546999,"2023-04-15","05:00:00","2023-04-15","15:00:00","0d, 10h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Darmstadt Hbf","Da-Arheilgen",2023.0493037840599,2023.0054093966401,26.801127458288299,27.439174055862001,"2023-04-08","01:00:00","2023-04-08","21:00:00","0d, 20h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.04950574501,2023.00543276196,26.8065326789926,27.442337224176999,"2023-04-13","13:00:00","2023-04-15","05:00:00","1d, 16h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.04964038564,2023.0054483388501,26.810136159462001,27.444446003053599,"2023-04-03","05:00:00","2023-04-04","01:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Gbf","Darmstadt Hbf",2023.0497077059599,2023.00545612729,26.811937899696801,27.445500392492001,"2023-04-12","17:00:00","2023-04-13","13:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.0499769872199,2023.0054872810599,26.819144860635699,27.449717950245301,"2023-04-11","21:00:00","2023-04-12","17:00:00","0d, 20h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.05004430754,2023.0054950695101,26.8209466008704,27.450772339683599,"2023-03-27","00:00:00","2023-05-27","23:59:00","61d, 23h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-10-29"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Gbf",2023.05031358881,2023.00552622328,26.828153561809401,27.454989897436899,"2023-03-01","00:00:00","2023-12-09","23:59:00","283d, 23h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Hbf","Darmstadt Gbf",2023.05044822944,2023.00554180016,26.831757042278898,27.457098676313599,"2023-04-29","07:00:00","2023-05-01","09:00:00","2d, 2h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.0507175107,2023.0055729539299,26.8389640032178,27.461316234066899,"2023-04-24","05:00:00","2023-04-25","11:00:00","1d, 6h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-26"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 144","<>","Darmstadt Hbf","Darmstadt Hbf",2023.0507848310201,2023.0055807423801,26.8407657434526,27.462370623505201,"2023-05-17","01:00:00","2023-05-17","11:00:00","0d, 10h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.0510541122901,2023.00561189615,26.847972704391498,27.466588181258501,"2023-04-27","07:00:00","2023-04-29","07:00:00","2d, 0h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Darmstadt Hbf","Da-Arheilgen",2023.0511214326,2023.0056196845901,26.849774444626199,27.4676425706968,"2023-05-10","09:00:00","2023-05-11","05:00:00","0d, 20h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023.05125607323,2023.0056352614799,26.8533779250957,27.4697513495735,"2023-05-01","09:00:00","2023-05-07","09:00:00","6d, 0h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Gbf","Darmstadt Hbf",2023.0514580341801,2023.0056586267999,26.858783145799901,27.472914517888501,"2023-04-08","01:00:00","2023-04-08","21:00:00","0d, 20h","continuous",null,"T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 767","<>","Darmstadt Gbf","Darmstadt Hbf",2023.05165999513,2023.0056819921299,26.864188366504099,27.476077686203499,"2023-05-23","11:00:00","2023-05-24","17:00:00","1d, 6h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-06-01"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Hirschaid","Forchheim (Ofr)",2023.05179463577,2023.00569756902,26.867791846973599,27.4781864650801,"2022-12-11","00:00:00","2023-03-24","21:00:00","103d, 21h","continuous","Bridge",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-06-21"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 268",">","Augsburg Hbf","Augsb Hirbl Str",2023.05206391703,2023.0057287227901,26.874998807912501,27.4824040228334,"2023-08-13","04:30:00","2023-11-19","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,null,null,null,null,null,null,null,"Y","2021-08-09"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsburg Hbf","Augsburg Hbf",2023.0522658779801,2023.0057520881201,26.880404028616798,27.485567191148402,"2023-08-14","23:30:00","2023-08-23","05:00:00","8d, 5h","periodical continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-07-13"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 268","<>","Westheim/Schwab","Augsburg Hbf",2023.0524005186101,2023.0057676649999,26.884007509086199,27.487675970025101,"2023-08-12","23:30:00","2023-08-14","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-05-04"]
[null,80,"München Hbf - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023.0524678389299,2023.00577545345,26.885809249320999,27.4887303594634,"2023-08-12","23:30:00","2023-08-14","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-07-13"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023.0527371201999,2023.0058066072199,26.893016210259901,27.4929479172167,"2023-09-04","22:00:00","2023-09-20","05:00:00","15d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-16"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4801",">","Mühlacker","Bretten Rechberg",2023.0528717608299,2023.0058221841,26.896619690729398,27.4950566960934,"2023-11-27","23:00:00","2023-12-06","06:00:00","8d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-15"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 3","<>","Grötzingen","Wilferdgn-Singen",2023.05307372178,2023.00584554943,26.9020249114336,27.498219864408401,"2023-05-12","23:00:00","2023-05-15","05:00:00","2d, 6h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-21"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023.05320836241,2023.00586112632,26.9056283919031,27.500328643284998,"2023-04-17","03:00:00","2023-04-17","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-05-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023.0534103233599,2023.00588449164,26.911033612607302,27.5034918116,"2023-09-04","22:50:00","2023-09-05","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023.05361228431,2023.00590785697,26.916438833311499,27.506654979915002,"2023-09-11","22:50:00","2023-09-12","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-06-08"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,30,31,"2023-07-29","06:00:00","2023-07-31","02:00:00","1d, 20h","continuous","Track and Rail",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-16"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,29,30,"2023-07-21","18:00:00","2023-07-29","04:00:00","7d, 10h","continuous","Track and Rail",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Augsburg Hbf - Buchloe","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,29,31,"2023-07-19","07:00:00","2023-08-01","17:00:00","13d, 10h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-13"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Sünching","Sünching",2023,2023,22,26,"2023-05-30","05:00:00","2023-06-28","05:00:00","29d, 0h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-17","22:00:00","7d, 0h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,11,12,"2023-03-17","22:00:00","2023-03-20","06:00:00","2d, 8h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-08","06:00:00","7d, 8h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-08","06:00:00","7d, 8h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,14,15,"2023-04-06","22:00:00","2023-04-11","06:00:00","4d, 8h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim Ost","Bad Endorf (Obb)",2023,2023,16,17,"2023-04-21","06:00:00","2023-04-24","06:00:00","3d, 0h","continuous","Switch",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,30,49,"2023-07-25","05:00:00","2023-12-09","23:59:00","137d, 19h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-08-23"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560",">","Olching","Mü Nord Rbf For",2023,2023,9,9,"2023-03-03","09:00:00","2023-03-04","16:00:00","1d, 7h","periodical continuous","Track and Rail",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2021-08-25"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Buttenheim","Eggolsheim Süd",2023,2023,13,13,"2023-03-31","21:00:00","2023-04-01","09:00:00","0d, 12h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-25"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Buttenheim","Eggolsheim Süd",2023,2023,13,14,"2023-04-01","09:00:00","2023-04-03","06:00:00","1d, 21h","continuous","Miscellaneous",null,null,"S",null,null,null,null,null,null,null,null,null,"N","2021-08-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2020-09-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2020-09-28"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","05:00:00","1d, 7h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2020-09-28"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Aburg-Goldbach",2023,2023,5,7,"2023-02-03","22:00:00","2023-02-13","05:00:00","9d, 7h","periodical","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2021-08-27"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,23,24,"2023-06-09","05:00:00","2023-06-16","22:00:00","7d, 17h","continuous","Track and Rail",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2020-09-29"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108",">","Feucht","Feucht",2023,2023,27,28,"2023-07-07","00:00:00","2023-07-13","05:00:00","6d, 5h","periodical continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2020-09-29"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2022,2023,50,5,"2022-12-12","00:30:00","2023-01-31","06:20:00","50d, 5h","periodical continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Appenweier","Appenweier",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-21"]
[null,80,"Appenweier, W 207 - Kehl (DB-Grenze)","<>","Appenweier Kurve","Appenweier Kurve",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Achern, W 541 - DB/SWEG - (Ottenhöfen)","<>","Achern DB/SWEG","Achern",2023,2023,44,44,"2023-10-31","22:00:00","2023-11-03","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,null,null,"N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,13,49,"2023-03-31","00:00:00","2023-12-08","23:59:00","253d, 0h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-10-12"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,21,23,"2023-05-26","23:00:00","2023-06-08","05:00:00","12d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,23,24,"2023-06-08","23:00:00","2023-06-15","05:00:00","6d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Pforzheim Hbf","Wilferdgn-Singen",2023,2023,9,10,"2023-03-03","21:00:00","2023-03-06","05:00:00","2d, 8h","periodical continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2021-09-16"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,18,49,"2023-05-04","23:30:00","2023-12-09","23:59:00","219d, 1h","continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2020-09-29"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Karlstadt (Main)","Gemünden (Main)",2023,2023,24,36,"2023-06-15","23:00:00","2023-09-09","05:00:00","85d, 6h","periodical continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2021-11-17"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Karlstadt (Main)","Gemünden (Main)",2023,2023,49,49,"2023-12-05","23:00:00","2023-12-09","05:00:00","3d, 6h","periodical continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München Ost Pbf","München Ost Pbf",2023,2024,49,50,"2023-12-10","00:00:00","2024-12-14","23:59:00","370d, 23h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-10-15"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Bamberg",2023,2023,13,16,"2023-03-29","06:00:00","2023-04-22","18:00:00","24d, 12h","continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-11-30"]
[null,80,"Hallstadt (b Bamberg) - Abzw Höflein","<>","Höflein","Hallstadt(Bambg)",2023,2023,13,16,"2023-03-30","00:00:00","2023-04-21","04:00:00","22d, 4h","periodical continuous","Track and Rail","T",null,null,null,null,null,null,null,null,null,null,null,"N","2020-09-30"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,18,19,"2023-05-05","00:00:00","2023-05-08","05:00:00","3d, 5h","periodical continuous","Track and Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,"N","2021-12-09"]
[null,80,"For this IM, information about TCRs for TT 2024 can currently be found on the following websites:  BID Portal: https://www1.deutschebahn.com/service/security/bid-portal/3351048 and  PlaTo: https://neco.smallsolutions.comp.db.de/f?p=PLATO "]
[null,81,"Linz - Wien (NRZ)","< >","Üst Up 2","Tullnerbach-Pressbaum",2023,2023,23,26,"08.06.2023","02:00","30.06.2023","20:00","22 days + 18,0 h","cont.","SP","","LT","","","","","","","","","Bauphase 2.2.1:\nUmbau Weichenkopf OST Ri Up! Umbau Fahrleitung, Fundamente herstellen für OBerleitung und Maste.","","N","14.12.2021","N","",90893,1015,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Tullnerbach-Pressbaum","",2023,2023,28,29,"12.07.2023","04:00","17.07.2023","04:00","5 days","cont.","SP","","ST","","","","C","","B","","","Bauphase 3.2:\nSchwenk von Nord auf Südseiten! Umbau Südseite. Umbau Weichenkopf OST Ri Up! Umbau Fahrleitung; Umbau Signalstandorte!\nDoppelgleissperren in den Nächten!","","N","14.12.2021","N","",1015,"","","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Unter Purkersdorf","",2021,2022,33,26,"16.08.2021","00:00","01.07.2022","24:00","320 days","cont.","BFUM","","ST","","","","","","","","","Bauphase 1D:\nErrichten der Gleise 3,5b,7 + W13,31,32,33 + Signale\nInselbahnsteig mit Infrastrunktur\nAbstrag alter Übergangssteg","","N","14.12.2021","N","",1012,"","","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,1,1,"09.01.2022","01:10","09.01.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,1,1,"09.01.2022","01:10","09.01.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,3,3,"23.01.2022","01:10","23.01.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,4,4,"24.01.2022","01:00","24.01.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,5,5,"06.02.2022","01:10","06.02.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","<","Abzww St.Peter-Seitenstetten Ost","Üst Spw 13",2022,2022,6,7,"07.02.2022","22:35","18.02.2022","04:00","8x 5,4 h","period.","GES-N","","LT","","","","C","","B","","","Vorarbeiten  \nGLN+PLV Gl1: km 151,256-153,913","","Y","14.12.2021","N","",91010,90269,"","","","","","","",""]
[null,81,"Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,6,7,"12.02.2022","20:00","15.02.2022","06:00","3x 10,0 h","period.","SP","","LT","","","","","","",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","N","14.12.2021","N","","",1105,2,2,"","","","","",""]
[null,81,"Salzburg - Wels",">","Neumarkt am Wallersee","Steindorf bei Straßwalchen",2022,2022,7,8,"19.02.2022","20:00","21.02.2022","06:00","2x 10,0 h","period.","SP","","LT","","","","","","",3,"","Erneuerung OL Bereich Neuerrichteter Hst Neumarkt am Wallersee\nAbtrag Bestands OL, aufziehen und ausfertigen neuer OL","","N","14.12.2021","N","","",1105,2,2,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,7,7,"20.02.2022","01:10","20.02.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,8,8,"21.02.2022","01:00","21.02.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)",">","St.Peter-Seitenstetten","Üst Spw 13",2022,2022,8,8,"21.02.2022","22:35","25.02.2022","04:00","4x 5,4 h","period.","GES-N","","LT","","","","C","","B","","","Vorarbeiten  \nGLN+PLV Gl1: km 151,256-153,913, GDA SP","","Y","14.12.2021","N","",1056,90269,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Loosdorf","Sbl Los 4",2022,2022,8,8,"26.02.2022","22:00","27.02.2022","05:00","7,0 h","cont.","GES-N","","LT","","","","C","","B","","","Sonderinspektion \nTUF","","N","14.12.2021","N","",1040,90503,"","","","","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Vbf","",2022,2022,9,10,"04.03.2022","22:00","07.03.2022","17:00","2 days + 19,0 h","cont.","SP","","ST","","","","C","","","","","WN DKW66/67","","Y","14.12.2021","N","",1080,"","","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,9,9,"06.03.2022","01:10","06.03.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,10,10,"07.03.2022","01:00","07.03.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Abzww St.Peter-Seitenstetten Ost","St.Valentin",2022,2022,10,10,"07.03.2022","22:00","11.03.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021","N","",91010,1061,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,10,11,"11.03.2022","23:30","20.03.2022","05:30","9x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021","N","",90285,90862,"","","","","","","",""]
[null,81,"Wien - Parndorf","< >","Wien Zvbf","",2022,2022,10,11,"12.03.2022","07:00","14.03.2022","14:00","2 days + 7,0 h","cont.","SP","","ST","","","","","","","","","Weichenneulage W 322, 323","","N","14.12.2021","N","",2962,"","","","","","","","",""]
[null,81,"Wien - Sopron","< >","Wien Zvbf","",2022,2022,10,11,"12.03.2022","07:00","14.03.2022","14:00","2 days + 7,0 h","cont.","SP","","ST","","","","","","","","","Weichenneulage W 322, 323","","N","14.12.2021","N","",2962,"","","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,11,11,"14.03.2022","22:00","18.03.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","<","Abzww St.Peter-Seitenstetten Ost","Üst Spw 13",2022,2022,11,11,"14.03.2022","22:35","20.03.2022","04:00","4x 5,4 h","period.","GES-N","","LT","","","","C","","B","","","Vorarbeiten  \nGLN+PLV Gl1: km 151,256-153,913","","Y","14.12.2021","N","",91010,90269,"","","","","","","",""]
[null,81,"Wels - Linz",">","Linz Hbf","Marchtrenk",2022,2022,12,13,"25.03.2022","22:00","29.03.2022","05:00","4x 7,0 h","period.","SP","","LT","","","","","","","","","IB ESTW Hörsching","","N","14.12.2021","N","",1073,1079,"","","","","","","",""]
[null,81,"Wels - Linz",">","Sbl Lz 3","Hörsching",2022,2022,12,12,"26.03.2022","22:00","27.03.2022","05:00","6,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 1 (Gl 2 Lz-Hoe)","","N","14.12.2021","N","",90513,1077,"","","","","","","",""]
[null,81,"Wels - Linz","<","Hörsching","Sbl Hoe 1",2022,2022,13,13,"28.03.2022","17:00","29.03.2022","05:00","12,0 h","cont.","SP","","LT","S","","","","","","","","IB ESTW Hörsching - Phase 4 (Gl 1 Hoe-Mak)","","N","14.12.2021","N","",1077,90329,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Linz Hbf","Linz Hbf Westbrücke",2022,2022,11,12,"18.03.2022","22:30","21.03.2022","20:00","2 days + 21,5 h","cont.","SP","","LT","","","","","","","","","Anbindung Gleis 2 (Gleis 4Neu)","","N","14.12.2021","N","",1073,5914,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Linz Hbf","Linz Hbf Westbrücke",2022,2022,12,12,"27.03.2022","01:00","27.03.2022","03:00","1,0 h","cont.","SP","","LT","S","","","","","","","","IB Linz SWT 2- aufgehobene Signalabhängigkeit\nmit Sicherheitserprobung","","N","14.12.2021","N","",1073,5914,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,11,11,"20.03.2022","01:10","20.03.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,12,12,"21.03.2022","01:00","21.03.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,12,12,"21.03.2022","22:00","25.03.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)",">","Sbl Spw 5","Sbl Spw 2",2022,2022,12,14,"21.03.2022","23:50","10.04.2022","05:20","15x 5,5 h","period.","GES-N","","LT","","","","C","","B",6,"","Kanalspülen","","N","04.01.2022","N","",90782,90776,4,0,"","","","","",""]
[null,81,"Wien - Parndorf","< >","Wampersdorf","Gramatneusiedl",2022,2022,12,12,"26.03.2022","09:00","27.03.2022","18:00","1 day + 8,0 h","cont.","GES","T","LT","","","","C","","B","","","Herstellung einer Querung und Einbau Schotterbettsicherung","","Y","14.12.2021","N","100%",3197,2968,"","","","","","","","Medium"]
[null,81,"Salzburg - Wels","< >","Üst Lz 2","Sbl We 2",2022,2022,12,49,"27.03.2022","00:00","10.12.2022","24:00","259 days","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 1 - 4","","N","14.12.2021","N","",90515,90948,"","","","","","","",""]
[null,81,"Wels - Linz","< >","Üst Lz 2","Sbl We 2",2022,2022,12,49,"27.03.2022","00:00","10.12.2022","24:00","259 days","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 1 - 4","","N","14.12.2021","N","",90515,90948,"","","","","","","",""]
[null,81,"Parndorf - Hegyeshalom","< >","Parndorf","Kittsee",2022,2022,13,13,"28.03.2022","07:50","01.04.2022","12:30","5x 4,7 h","period.","WF","T","LT","","","","C","","B","","","Instandsetzungsarbeiten","","N","14.12.2021","N","",2976,3002,"","","","","","","",""]
[null,81,"Parndorf - Bratislava","< >","Parndorf","Kittsee",2022,2022,13,13,"28.03.2022","07:50","01.04.2022","12:30","5x 4,7 h","period.","WF","T","LT","","","","C","","B","","","Instandsetzungsarbeiten","","N","14.12.2021","N","",2976,3002,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,13,13,"28.03.2022","22:00","01.04.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"Wels - Linz",">","Üst Lz 2","Hörsching",2022,2022,13,16,"29.03.2022","21:30","24.04.2022","05:00","23x 7,5 h","period.","SP","","LT","S","","","","","","","","Erneuerung Bstg in Pasching","","N","14.12.2021","N","",90515,1077,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,13,13,"03.04.2022","01:10","03.04.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,14,14,"04.04.2022","01:00","04.04.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Wien - Parndorf","< >","Wampersdorf","Gramatneusiedl",2022,2022,14,14,"04.04.2022","09:00","04.04.2022","12:00","3,0 h","cont.","GES","T","LT","","","","C","","B","","","Herstellung einer Querung und Einbau Schotterbettsicherung","","Y","14.12.2021","N","100%",3197,2968,"","","","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","Gramatneusiedl",2022,2022,14,14,"04.04.2022","09:00","04.04.2022","12:00","3,0 h","cont.","GES","T","LT","","","","C","","B","","","Herstellung einer Querung und Einbau Schotterbettsicherung","","Y","14.12.2021","N","100%",3197,2968,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,14,14,"04.04.2022","22:00","08.04.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021","N","",1042,1045,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Enns","",2022,2022,14,18,"08.04.2022","20:00","07.05.2022","17:00","28 days + 21,0 h","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021","N","",1064,"","","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Abzw Ams 11","Waidhofen a.d.Ybbs",2022,2022,14,16,"09.04.2022","00:00","19.04.2022","04:00","10 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Schotterbettreinigung km 22,350-23,000 Böhlerwerke-Waidhofen;\nErneuerung Oberleitung: km7,045-8,902; km7,808-8,071; \nErneuerung ABWeichen: km11,853-11,850; \nTausch Einzelschw, ZW, MDZ-Einsatz: Kröllendf-Hilm\nSchienenneulage+Schotterbettr: Hilm-Rosenau","","N","14.12.2021","N","",90046,1437,"","","","","","","",""]
[null,81,"Wien - Parndorf","< >","Wien Zvbf","",2022,2022,14,15,"09.04.2022","07:00","11.04.2022","14:00","2 days + 7,0 h","cont.","SP","","ST","","","","","","","","","Weichenneulage W 458, 445","","N","14.12.2021","N","",2962,"","","","","","","","",""]
[null,81,"Wien - Parndorf","< >","Abzww Str 11815","Abzw Bl 1",2022,2022,15,15,"11.04.2022","01:35","11.04.2022","03:30","1,9 h","cont.","GES-N","","LT","","","","C","","B","","","Errichtung eines Schaltpostens","","Y","11.01.2022","N","100%",91011,90055,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","<","Abzww St.Peter-Seitenstetten Ost","Üst Spw 13",2022,2022,15,18,"15.04.2022","01:00","05.05.2022","05:00","20 days + 4,0 h","cont.","SP","","LT","","","","C","","B","","","Sankt Peter-Seitenstetten: Schotterbettreinigung W 6,7,52,54,  \nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","Y","14.12.2021","N","",91010,90269,"","","","","","","",""]
[null,81,"Salzburg - Wels","< >","Wels Hbf","Lambach",2022,2022,15,16,"15.04.2022","08:00","18.04.2022","20:00","3 days + 12,0 h","cont.","RES","","LT","","","","C","","","","","WN W 65,66","","Y","03.11.2021","N","",1081,1086,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)",">","Abzw Knoten St.Peter-Seitenstetten West","Üst Spw 13",2022,2022,15,17,"15.04.2022","23:00","30.04.2022","05:30","15x 6,5 h","period.","GES-N","","LT","","","","","","","","","GLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","14.12.2021","N","",90784,90269,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Zvbf-Einfgr","",2022,2022,15,16,"16.04.2022","07:00","19.04.2022","14:00","3 days + 7,0 h","cont.","SP","","ST","","","","","","","","","Weichenneulage Kreuzung 1, DKW 175/176, DKW 172/173","","N","14.12.2021","N","",4530,"","","","","","","","",""]
[null,81,"Linz - Wien (GZ)","<","St.Peter-Seitenstetten","Üst Spw 13",2022,2022,17,18,"25.04.2022","01:00","05.05.2022","04:00","10 days + 3,0 h","cont.","SP","","LT","","","","C","","B","","","Errichtung Grabenmauer km 145,260-146,500\nGLN+PLV Gl1: km 151,256-153,913\nErrichtung Begleitweg: km 153,100-153,800","","N","14.12.2021","Y","",1056,90269,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Neulengbach","Sbl Nl 1",2022,2022,17,44,"29.04.2022","00:00","31.10.2022","24:00","186 days + 1,0 h","cont.","SP","","LT","","","","","","","","","Gleiseindeckung EK km 39,714 Hst. Ollersbach\ntlw. Tagsperren, bei Bedarf  Doppelgleissperren in der Nacht oder Zugspausen","","N","14.12.2021","N","",1025,90595,"","","","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,17,17,"01.05.2022","01:10","01.05.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,18,19,"02.05.2022","23:30","09.05.2022","05:30","7x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021","N","",90859,91052,"","","","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,18,18,"08.05.2022","01:10","08.05.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,19,19,"09.05.2022","01:00","09.05.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,19,19,"09.05.2022","01:00","09.05.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021","N","100%",90285,90288,"","","","","","","","Medium"]
[null,81,"Salzburg - Wels",">","Sbl We 1","Abzww Lambach-West",2022,2022,19,49,"15.05.2022","00:00","10.12.2022","24:00","210 days + 1,0 h","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 5 - 6","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Parndorf","< >","Wampersdorf","Gramatneusiedl",2022,2022,20,20,"16.05.2022","09:00","16.05.2022","14:00","5,0 h","cont.","GES","T","LT","","","","C","","B","","","Fahrleitungsumbau für prov. Anschwenkung","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","<","Knoten Rohr","Loosdorf",2022,2022,20,20,"18.05.2022","22:00","19.05.2022","05:00","7,0 h","cont.","WF","","LT","","","","","","","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,20,20,"22.05.2022","01:10","22.05.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wien - Parndorf","<","Himberg","Gramatneusiedl",2022,2022,21,24,"23.05.2022","05:00","13.06.2022","05:00","21 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Einfahrgr","",2022,2022,21,23,"25.05.2022","07:00","10.06.2022","17:00","16 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Hbf","Abzww Lambach-Ost",2022,2022,21,21,"26.05.2022","07:00","29.05.2022","01:15","2 days + 18,2 h","cont.","SP","","LT","","","","","","","","","Überprüfung und Einstellung der Blocksignale am Gegengleis zw.La und Gun: Einstellung der AS R1,R3,R5,H5 u. ES Y,EVS y von Bf. Gun (insgesamt 10 Signalstandorte), Prüfung von 7 Gleisfreimeldeabschnitten am Westkopf Gun","","N","14.12.2021",null,null,null,null,null,"","","","","","",""]
[null,81,"Salzburg - Wels",">","Sbl Mak 2","Gunskirchen",2022,2022,21,21,"29.05.2022","01:15","29.05.2022","04:15","3,0 h","cont.","SP","","LT","","","","","","","","","IBN Gunskirchen;Wels SWT","","N","14.12.2021",null,null,null,null,null,"","","","","","",""]
[null,81,"Salzburg - Wels","< >","Gunskirchen","",2022,2022,21,22,"29.05.2022","01:15","30.05.2022","22:00","1 day + 20,8 h","cont.","SP","","ST","S","","","","","",5,"","Überprüfungs- und Einstellungsarbeiten, aufgehobene Signalabhängigkeit im Bf Gunskirchen (Vmax 40)","","N","14.12.2021","N","",1085,"",4,3,"","","","","",""]
[null,81,"Regensburg - Wels",">","Sbl Mak 2","Gunskirchen",2022,2022,21,21,"29.05.2022","01:15","29.05.2022","04:15","3,0 h","cont.","SP","","LT","","","","","","","","","IBN Gunskirchen;Wels SWT","","N","14.12.2021","N","",90532,1085,"","","","","","","",""]
[null,81,"Wels - Linz","< >","Wels Hbf","Abzww Lambach-Ost",2022,2022,21,22,"29.05.2022","04:15","30.05.2022","03:00","22,8 h","cont.","SP","","LT","","","","C","","B","","","Überprüfung und Einstellung der Blocksignale am Regelgleis zw.La u. Gun.\nÜberprüfung und Einstellung der Signale von Bf.Gun\n(insgesamt 9 Signalstandorte)\nStreckblockfunktionalität ZG62 zw. Gun u. La überprüfen, Prüffahrten","","Y","14.12.2021",null,null,null,null,null,"","","","","","",""]
[null,81,"Salzburg - Wels","< >","Wels Hbf","Gunskirchen",2022,2022,22,22,"30.05.2022","03:00","30.05.2022","13:00","10,0 h","cont.","SP","","LT","","","","","","","","","Überprüfung und Einstellung der Blocksignale am Regelgleis zw.We u. Gun\nÜberprüfung und Einstellung von Signalen im Bf.Gun (insgesamt 9 Signalstandorte) Streckblockfunktionalität ZG62 zw. Gun u. We überprüfen, Prüffahrten","","N","14.12.2021",null,null,null,null,null,"","","","","","",""]
[null,81,"Wien - Parndorf","< >","Wien Zvbf","",2022,2022,22,23,"03.06.2022","07:00","06.06.2022","17:00","3 days + 10,0 h","cont.","SP","","ST","","","","","","","","","Weichenneulage W 311, 312, 313, 316","","N","14.12.2021",null,null,null,null,null,"","","","","","",""]
[null,81,"Wels - Linz","<","Marchtrenk","",2022,2022,22,23,"03.06.2022","22:00","07.06.2022","05:00","3 days + 7,0 h","cont.","SP","","ST","","","","","","",3,"","WN 33P, 34P, 49P = Einbau Verbindungen Gl 1/3 NEU  und 2/4 NEU","","N","14.12.2021",null,null,null,null,null,1,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,23,23,"12.06.2022","01:10","12.06.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,"","","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,23,23,"12.06.2022","01:10","12.06.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,"","","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","Gramatneusiedl",2022,2022,24,24,"13.06.2022","09:00","13.06.2022","14:00","5,0 h","cont.","GES","T","LT","","","","C","","B","","","Fahrleitungsumbau für prov. Anschwenkung","","Y","14.12.2021",null,null,null,null,null,"","","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Münchendorf","Ebreichsdorf",2022,2022,24,25,"15.06.2022","22:00","20.06.2022","04:00","4 days + 6,0 h","cont.","GES","T","LT","","","","C","","B","","","ziehen Spundwände für Gleisverschwenkung","","Y","14.12.2021",null,null,null,null,null,"","","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Hennersdorf","Wiener Neustadt Hbf-Schleppbf",2022,2022,24,24,"19.06.2022","01:30","19.06.2022","02:30","1,0 h","cont.","GES-N","","LT","","","","C","","B","","","Softwaretausch in der BFZ Wien","","Y","11.01.2022",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","Gramatneusiedl",2022,2022,25,25,"20.06.2022","09:00","20.06.2022","14:00","5,0 h","cont.","GES","T","LT","","","","C","","B","","","Fahrleitungsumbau für prov. Anschwenkung","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,25,25,"26.06.2022","01:10","26.06.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Reihungsgr","",2022,2022,26,28,"01.07.2022","07:00","13.07.2022","17:00","12 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2023,26,26,"01.07.2022","08:00","02.07.2023","01:00","365 days + 17,0 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2023,26,36,"01.07.2022","08:00","04.09.2023","04:00","430 days","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,26,26,"02.07.2022","22:10","03.07.2022","06:00","7,8 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Maxing","Wien Quartier Belvedere",2022,2022,26,26,"03.07.2022","01:45","03.07.2022","03:55","2,2 h","cont.","RES","","LT","","","","C","","B","","","Softwaretausch im ESTW Wien Matzleinsdorf","","N","05.07.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,26,27,"03.07.2022","23:10","04.07.2022","04:30","5,3 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,27,27,"09.07.2022","23:10","10.07.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Abtrag Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,27,27,"10.07.2022","01:10","10.07.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,27,28,"10.07.2022","23:10","11.07.2022","04:30","5,3 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,28,28,"11.07.2022","01:00","11.07.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Regensburg - Wels",">","Sbl Wa 2","Grieskirchen-Gallspach",2022,2022,28,29,"11.07.2022","06:00","22.07.2022","22:00","11 days + 16,0 h","cont.","SP","","LT","","","","","","",3,"","Bahnsteigerneuerung Gl 2 (Bstg 2 km 16,490 – 16,750) in der Hst Schlüßlberg","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Amstetten","Abzw Knoten St.Peter-Seitenstetten West",2022,2022,29,30,"18.07.2022","01:00","27.07.2022","04:00","9 days + 3,0 h","cont.","GES","T","LT","","","","C","","B",4,"","Üst Ams2: Weichentausch W401,402,403,404 inkl. Schottertausch\nAbzww Sp W1: Schotterbettreinigung W10, Abtrag W13,14\nWest200","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Vbf-Terminal","",2022,2022,29,30,"23.07.2022","18:00","25.07.2022","12:00","1 day + 18,0 h","cont.","GES","T","ST","","","","C","","","","","Sperre Berggleis (Einfahrt Wels-Verschiebebahnhof) Errichtung Bohrpfähle für MA5.3, Einbau Hilfsbrücke zwischen Weichenverbindung ½ Wels Verschiebeb., Einbau einer Durchfahrt unter Berggleis östlich der Autobahnbrücke","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,29,29,"23.07.2022","23:10","24.07.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,29,29,"24.07.2022","01:10","24.07.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","<","Unter Purkersdorf","",2022,2022,30,34,"30.07.2022","02:00","22.08.2022","04:30","23 days + 2,5 h","cont.","BFUM","","ST","","","","","","","","","Bauphase 3A,3B,3C,3D:\nAnbinden der Gleise 3,7 an den Ostkopf.\nNeulage Gl3, Gl5 + W 12\nWestkopf: Neubau W56alt 63); Neulage Gleis 1","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,30,30,"30.07.2022","23:10","31.07.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf, Inbetriebnahme ESTW Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,30,30,"31.07.2022","01:10","31.07.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,30,35,"31.07.2022","05:00","04.09.2022","17:00","35 days + 12,0 h","cont.","SP","","LT","","","","C","","B",40,"","Einbau Weiche 56 und 57 in Wampersdorf, versetzen Lufttrennung und Einfahrsignal","","Y","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Vbf","",2022,2022,31,32,"01.08.2022","07:00","09.08.2022","07:00","8 days","cont.","SP","","ST","","","","","","","","","Ausbau der KR1 und Weiche 50, in diesem Bereich Einbau der Weiche 49 inkl. Anschlüsse, WN W64, IB mit SWT 13.08.","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Unter Purkersdorf","",2022,2022,31,34,"06.08.2022","01:30","22.08.2022","04:00","16 days + 2,5 h","cont.","SP","","ST","","","","C","","B","","","Migration Estw Up neu:\n06.08.22: Softwaretausch Hf/Hdd, EstwUpneu; BFZ\nes stehen nur die Gleise 2+4 im Bf. Up zur Verfügung\nSignalabhängigkeit aufgehoben!\nSchluss/Freimelder erforderlich!\nStr. 123 nicht befahrbar!","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Vbf","",2022,2022,32,32,"09.08.2022","07:00","13.08.2022","22:00","4 days + 15,0 h","cont.","SP","","ST","","","","C","","","","","Durchbindung Wels Verschiebebahnhof Einbau Weiche 62\nAusbau der Weichen 355, 356, diese wieder mit Gleisfelder schließen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Abzw Mak 1","Sbl Hoe 2",2022,2022,32,33,"09.08.2022","21:00","16.08.2022","05:00","6 days + 8,0 h","cont.","SP","","LT","S","","","","","","","","V 40 km/hI\nB ESTW Marchtrenk - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Marchtrenk","",2022,2022,32,32,"11.08.2022","21:00","12.08.2022","05:00","8,0 h","cont.","SP","","ST","","","","","","","","","Phase 3 - IB Sig. Elemente Gleis 103 zw. AS H3 und ES C\n(Traunerschleife)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz",">","Marchtrenk","",2022,2022,32,32,"12.08.2022","21:00","14.08.2022","05:00","1 day + 8,0 h","cont.","SP","","ST","","","","C","","B",2,"","Phase 0 - IB Einbau W 49P - Ausbau W7","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Marchtrenk","",2022,2022,32,33,"14.08.2022","17:00","15.08.2022","05:00","12,0 h","cont.","SP","","ST","","","","","","","","","Phase 0 - Einbau Weiche 34P","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","<","Wels Hbf","Marchtrenk",2022,2022,33,33,"15.08.2022","21:00","16.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","",10,"","Phase 6 - IB Sig. Elemente  Gleis 1 von ES Z bis AS R1","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,32,32,"13.08.2022","23:10","14.08.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Abtrag Querfelder","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Abzw Mak 1","Wels Vbf-Einfgr",2022,2022,33,49,"16.08.2022","00:00","07.12.2022","24:00","114 days + 1,0 h","cont.","GES","T","LT","","","","","","","","","4gleisiger Ausbau Linz - Wels\nIm Bf Wels Vbf Rückbau der \nGleise  924, 104-504, 106-506, 508","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,33,33,"20.08.2022","22:10","21.08.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","01.02.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,33,34,"21.08.2022","22:10","22.08.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","01.02.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,34,34,"22.08.2022","00:00","22.08.2022","04:00","4,0 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,34,34,"27.08.2022","22:10","28.08.2022","06:00","7,8 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","01.02.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,34,34,"28.08.2022","00:00","28.08.2022","05:30","5,5 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,34,34,"28.08.2022","01:10","28.08.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,34,35,"28.08.2022","23:10","29.08.2022","04:30","5,3 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,35,35,"29.08.2022","01:00","29.08.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Salzburg - Wels","<","Schwanenstadt","Sbl Sas 1",2022,2022,35,35,"03.09.2022","20:00","04.09.2022","06:00","10,0 h","cont.","SP","","LT","","","","","","",5,"","Inbetriebnahme ESTW Gl 1,3","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,35,35,"03.09.2022","23:10","04.09.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,35,35,"04.09.2022","00:00","04.09.2022","05:30","5,5 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,35,36,"04.09.2022","22:10","05.09.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","01.02.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,35,36,"04.09.2022","23:10","05.09.2022","04:30","5,3 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Sbl Zur 1","Himberg",2022,2022,36,40,"09.09.2022","05:00","03.10.2022","05:00","24 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,36,36,"11.09.2022","01:10","11.09.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,37,37,"12.09.2022","00:00","12.09.2022","04:00","4,0 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Abzww Zur","Wien Zvbf",2022,2022,37,38,"12.09.2022","07:00","25.09.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Abzww Zur","Wien Zvbf",2022,2022,37,38,"12.09.2022","07:00","25.09.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Wels Hbf","Lambach",2022,2022,37,38,"16.09.2022","19:00","19.09.2022","04:00","2 days + 9,0 h","cont.","RES","","LT","","","","C","","","","","Ausbau DKW67/68, Einbau EW67","","Y","05.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"München - Rosenheim - Salzburg",">","Salzburg Hbf","",2022,2022,37,38,"16.09.2022","22:00","19.09.2022","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","","","",3,"","WN 308-309","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,37,37,"18.09.2022","00:00","18.09.2022","05:30","5,5 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,38,38,"19.09.2022","22:00","23.09.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,39,39,"26.09.2022","01:00","26.09.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,39,39,"26.09.2022","22:00","30.09.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf",">","Lanzendorf-Rannersdorf","Himberg",2022,2022,40,43,"03.10.2022","05:00","24.10.2022","05:00","21 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Parndorf - Bratislava","< >","Parndorf","Kittsee",2022,2022,40,40,"03.10.2022","07:50","07.10.2022","12:30","5x 4,7 h","period.","WF","T","LT","","","","C","","B","","","Instandsetzungsarbeiten","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,40,42,"03.10.2022","23:30","21.10.2022","05:30","18x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Gunskirchen","",2022,2022,40,41,"08.10.2022","08:00","10.10.2022","18:00","2 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,40,40,"09.10.2022","01:10","09.10.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,41,41,"10.10.2022","01:00","10.10.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Reihungsgr","",2022,2022,42,43,"17.10.2022","07:00","26.10.2022","17:00","9 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Zvbf-Einfgr","",2022,2022,42,43,"22.10.2022","07:00","26.10.2022","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,43,43,"24.10.2022","01:00","24.10.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)",">","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2022,2022,43,47,"24.10.2022","07:00","25.11.2022","17:00","32 days + 11,0 h","cont.","SP","","LT","","","","","","","","","Entwässerungsanlagen, Brückensanierung, Kabelwege","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","<","Inzersdorf Ort-Ost","Oberlaa",2022,2022,43,44,"27.10.2022","08:00","02.11.2022","05:00","5 days + 22,0 h","cont.","SP","","LT","","","","","","",10,"","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,43,44,"28.10.2022","23:30","31.10.2022","05:30","3x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Amstetten","Amstetten Ost",2022,2022,43,43,"30.10.2022","01:40","30.10.2022","04:20","3,7 h","cont.","GES-N","","LT","","","","C","","B","","","SWT Amstetten","","N","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Linz","< >","Marchtrenk","",2022,2022,44,45,"04.11.2022","22:00","07.11.2022","04:00","2 days + 6,0 h","cont.","SP","","ST","","","","C","","B",15,"","LM 22 - Einbau Hib","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,44,44,"06.11.2022","01:10","06.11.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Linz","<","Linz Hbf","Linz Hbf Westbrücke",2022,2022,47,47,"27.11.2022","01:00","27.11.2022","03:00","2,0 h","cont.","SP","","LT","","","","","","","","","Linz Hbf SWT 3 - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,45,45,"07.11.2022","01:00","07.11.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wien - Parndorf","< >","Wien Zvbf","Abzww Zur",2022,2022,45,46,"07.11.2022","07:00","20.11.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,45,45,"07.11.2022","23:30","12.11.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,46,46,"14.11.2022","23:30","16.11.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,47,47,"21.11.2022","01:00","21.11.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,47,47,"21.11.2022","01:00","21.11.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wien - Parndorf","< >","Abzww Zur","Wien Zvbf",2022,2022,48,49,"28.11.2022","07:00","11.12.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,48,48,"28.11.2022","23:30","03.12.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,49,49,"05.12.2022","01:00","05.12.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,50,50,"12.12.2022","23:30","14.12.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,51,51,"19.12.2022","01:00","19.12.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,51,51,"19.12.2022","01:00","19.12.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Linz",">","Üst Lz 2","Linz Hbf",2023,2023,7,8,"17.02.2023","22:00","22.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 01 km 191,248\nschlagen dukdiler Phäle","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","<","Linz Gaumberg","",2023,2023,8,9,"22.02.2023","22:00","27.02.2023","04:00","4 days + 6,0 h","cont.","SP","","ST","","","","","","","","","Einbau Hib LM 01 km 191,248\nschlagen dukdiler Phäle","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","St.Valentin","",2023,2023,10,10,"06.03.2023","07:00","10.03.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,10,10,"08.03.2023","22:45","09.03.2023","05:00","6,2 h","cont.","SP","","LT","","","","","","",7,"","Errichtung OL-Maste","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","Sbl Spw 5","Sbl Spw 2",2023,2023,12,14,"20.03.2023","22:30","05.04.2023","05:00","16x 6,5 h","period.","GES-N","","LT","","","","C","","B",6,"","Kanalspülen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Regensburg - Wels","< >","Wels Vbf-Einfgr","",2023,2023,12,14,"21.03.2023","07:00","03.04.2023","17:00","13 days + 9,0 h","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Linz Hbf","",2023,2023,13,50,"27.03.2023","00:00","12.12.2023","24:00","261 days + 1,0 h","cont.","SP","","ST","","","","","","","","","WN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wien Meidling","Wiener Neustadt Hbf",2023,2023,13,15,"01.04.2023","00:00","11.04.2023","04:30","10 days + 4,5 h","cont.","RES","","LT","","","","C","","B","","","Weichnenneulage in Md","","N","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,13,13,"01.04.2023","22:45","02.04.2023","06:00","7,2 h","cont.","SP","","LT","","","","","","",15,"","OL-Querungen aufziehen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Kledering","",2023,2023,14,15,"08.04.2023","09:00","11.04.2023","05:00","2 days + 20,0 h","cont.","SP","T","ST","","","","","","","","","Weichenneulage DKW 453/454 und DKW 455/456","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2023,2023,14,14,"08.04.2023","23:10","09.04.2023","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Einbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,14,15,"09.04.2023","22:45","10.04.2023","07:00","8,2 h","cont.","SP","","LT","","","","","","",5,"","IB neues Schaltgerüst","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Durchfahrgr","",2023,2023,15,16,"13.04.2023","07:00","17.04.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","EK 0,915 Scharlinz \n(Umsetzung zeitgleich mit Gl 1 km 0,862 - 1,010 0 (115lf)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","< >","Abzww Zur","Wien Zvbf",2023,2023,16,17,"17.04.2023","07:00","30.04.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Abzww Knoten Rohr West","Pöchlarn",2023,2023,18,21,"01.05.2023","00:00","22.05.2023","04:00","21 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Weichentausch Knoten Rohr 3 und 6\nWest 200\nErneuerung Löschwasserleitung Melker Tunnel Gl 3 (Sperren zum Tunnelspülen werden mitgenutzt.)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Abzww Knoten Rohr West","Pöchlarn",2023,2023,18,21,"01.05.2023","00:00","22.05.2023","04:00","21 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Weichentausch Knoten Rohr 3 und 6\nWest 200\nErneuerung Löschwasserleitung Melker Tunnel Gl 3 (Sperren zum Tunnelspülen werden mitgenutzt.)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Zvbf-Einfgr","",2023,2023,19,20,"13.05.2023","07:00","18.05.2023","17:00","5 days + 10,0 h","cont.","SP","","ST","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Abzww Knoten Rohr West","Pöchlarn",2023,2023,20,20,"21.05.2023","00:30","21.05.2023","04:30","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","SWT - keine Fahrten im Stellbereich möglich","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz",">","Hörsching","Marchtrenk",2023,2023,21,22,"26.05.2023","22:00","30.05.2023","04:00","3 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Ausbau Hib LM 19, LM 21,","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Ederbauer","Üst Fm 2",2023,2023,23,24,"07.06.2023","23:00","12.06.2023","05:00","4 days + 6,0 h","cont.","SP","","LT","","","","C","","B",5,"","Ed - Tausch Untergrund W 53 und 54","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Abzww Zur","Wien Zvbf",2023,2023,24,25,"12.06.2023","07:00","25.06.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Abzw Ams 11","Waidhofen a.d.Ybbs",2023,2023,26,36,"30.06.2023","23:00","04.09.2023","04:30","65 days + 5,5 h","cont.","GES","T","LT","","","","C","","B","","","Bahnhof Ul: Montage Schaltgerüst\nAbzw. Ams 11 - Ul und Bf. Ul:, Aufziehen der Spitzenleitungen,  Aufziehen und Ausfertigen der Oberleitung\nStrecke UI bis Hk:  Gleisneulage km 12,925 - km 15,032 im Zeitraum 07.08 bis 25.08.2023","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron",">","Wampersdorf","",2023,2023,26,47,"02.07.2023","08:00","24.11.2023","16:00","145 days + 9,0 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2023,2024,26,26,"02.07.2023","08:00","29.06.2024","04:30","362 days + 20,5 h","cont.","BFUM","","ST","","","","","","",40,"","Bf-Umbau","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Amstetten","",2023,2023,27,28,"03.07.2023","00:00","14.07.2023","24:00","12 days","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Parndorf - Hegyeshalom",">","Zurndorf","Nickelsdorf",2023,2023,27,30,"04.07.2023","08:00","30.07.2023","16:00","26 days + 8,0 h","cont.","SP","","LT","","","","C","","B",20,"","Gleisneulage mit Untergrundverstärkung","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"München - Rosenheim - Salzburg","< >","Salzburg Taxham Europark","",2023,2023,27,37,"08.07.2023","22:00","11.09.2023","06:00","64 days + 8,0 h","cont.","SP","","ST","","","","","","","","","Neubau Bahnsteigdach","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,29,30,"23.07.2023","23:10","24.07.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,30,31,"30.07.2023","23:10","31.07.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Abzw Pb 1","Prinzersdorf",2023,2023,32,33,"12.08.2023","01:00","18.08.2023","18:00","6 days + 17,0 h","cont.","SP","","LT","","","","C","","B","","","Weichenneulage Weichen 3,6,9 (Gl 204)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Abzw Pb 1","Prinzersdorf",2023,2023,33,33,"20.08.2023","01:00","20.08.2023","04:00","3,0 h","cont.","GES-N","","LT","","","","C","","B","","","SWT - keine Fahrten im Stellbereich möglich","","Y","15.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Abzw Pb 1","Prinzersdorf",2023,2023,34,34,"27.08.2023","01:00","27.08.2023","04:00","3,0 h","cont.","GES-N","","LT","","","","C","","B","","","SWT - keine Fahrten im Stellbereich möglich","","Y","15.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","St.Valentin-Ennskanalbrücke","St.Valentin",2023,2023,34,35,"26.08.2023","08:00","28.08.2023","08:00","2 days","cont.","SP","","LT","","","","C","","B",7,"","Ausbau W 126/127","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,34,35,"27.08.2023","23:10","28.08.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","St.Valentin","Linz Kleinmünchen",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","LT","","","","","","","","","Schotterbetttausch SAZ (Ennsbrücke)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","<","St.Valentin-Ennskanalbrücke","",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","ST","","","","","","","","","UGV Weiche  152, 154, 155, 156","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,35,36,"03.09.2023","23:10","04.09.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","< >","Wien Zvbf","Kledering",2023,2023,36,37,"09.09.2023","10:00","15.09.2023","17:00","6 days + 7,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wien Zvbf","Kledering",2023,2023,36,37,"09.09.2023","10:00","15.09.2023","17:00","6 days + 7,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,38,38,"18.09.2023","01:30","18.09.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,39,39,"25.09.2023","01:30","25.09.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Matzleinsdorf","",2023,2023,39,43,"25.09.2023","07:00","25.10.2023","12:00","30 days + 5,0 h","cont.","SP","","ST","","","","","","","","","Gleisneulage mit Untergrundstabilisierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,40,40,"02.10.2023","01:30","02.10.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,41,41,"09.10.2023","01:30","09.10.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf",">","Himberg","Gramatneusiedl",2023,2023,41,43,"13.10.2023","22:00","25.10.2023","22:00","12 days","cont.","SP","","LT","","","","C","","B",30,"","Anschwenkungen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,41,41,"14.10.2023","23:10","15.10.2023","05:45","6,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,42,42,"16.10.2023","01:30","16.10.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,42,42,"21.10.2023","23:10","22.10.2023","05:45","6,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,43,43,"28.10.2023","23:10","29.10.2023","05:45","7,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Einfahrgr","",2023,2023,44,45,"30.10.2023","07:00","10.11.2023","17:00","11 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,44,44,"01.11.2023","06:00","03.11.2023","05:00","1 day + 23,0 h","cont.","SP","","LT","","","","C","","B",30,"","Einbau W 1-neu und anbinden an Bgl 2","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels",">","Seekirchen am Wallersee","Sbl See 1",2023,2023,46,47,"17.11.2023","19:00","20.11.2023","05:00","2 days + 10,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nAusbau Hib Gl 1+2","","Y","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Neumarkt am Wallersee",2023,2023,49,50,"08.12.2023","21:00","11.12.2023","05:00","2 days + 8,0 h","cont.","SP","","LT","","","","C","","B",5,"","Tausch Schotterbett in der ÜSt Steindorf b.Stw 3","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Linz Hbf","Salzburg Hbf",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","11.01.2022",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"Wels - Linz","< >","Linz Hbf","Selzthal",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","11.01.2022",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"Linz - Wien (GZ)","< >","Wien Hütteldorf","Knoten Wagram",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","11.01.2022",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"Linz - Wien (NRZ)",">","Enns","",2024,2024,18,19,"03.05.2024","22:00","06.05.2024","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","HIB Einbau\nBf Enns\nUf – km 171,932\nDL 171,886","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,20,21,"17.05.2024","23:00","21.05.2024","05:00","3 days + 6,0 h","cont.","SP","","LT","","","","C","","B","","","Rückschwenkung Gl 1+2","","Y","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","<","Marchtrenk","",2024,2024,22,23,"29.05.2024","22:00","03.06.2024","05:00","4 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Verschwenkung Gleis 1alt / 3neu / 1alt im Bahnhof Marchtrenk","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Abzww Traun West","Marchtrenk",2024,2024,23,31,"04.06.2024","08:00","04.08.2024","18:00","61 days + 10,0 h","cont.","GES","T","LT","","","","C","","B","","","4gleisiger Ausbau Linz - Wels - Umbau Marchtrenk","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,26,27,"29.06.2024","05:00","01.07.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Hbf-Südosttangente (in Wbf)","Gramatneusiedl",2024,2024,26,36,"29.06.2024","09:00","02.09.2024","04:00","64 days + 19,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","23.09.2021",null,null,null,null,null,null,null,"","","","","Major"]
[null,81,"Wien - Sopron","< >","Wien Meidling","Wiener Neustadt Hbf",2024,2024,26,36,"29.06.2024","09:00","02.09.2024","04:00","64 days + 19,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","23.09.2021",null,null,null,null,null,null,null,"","","","","Major"]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,28,29,"13.07.2024","05:00","15.07.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,30,31,"27.07.2024","05:00","29.07.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Linz",">","Abzw Mak 1","Wels Hbf",2024,2024,32,35,"10.08.2024","22:00","26.08.2024","05:00","15 days + 7,0 h","cont.","SP","","LT","","","","C","","B","","","GN mit RU, Ausbau Weiche 101","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (NRZ)",">","Linz Hbf","Sbl Kue 2",2024,2024,35,35,"31.08.2024","00:00","01.09.2024","24:00","2 days","cont.","SP","","LT","","","","","","",10,"","Anschwenkung Gleis 2 (Weststrecke) an Gleis 2We","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (NRZ)",">","Enns","",2024,2024,42,43,"18.10.2024","22:00","21.10.2024","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Einbau Weiche 66 und 67","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81]
[null,81,"Wels - Traun - Linz","<","Linz Gaumberg","Linz Hbf",2022,2022,12,13,"21.03.2022","20:00","29.03.2022","05:00","7 days + 8,0 h","cont.","SP","","LT","","","","","","","","","Anbindung Gleis 1 (Gleis 3Neu) \nWN W 348 und W 352","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Üst Lz 2","Sbl We 2",2022,2022,12,49,"27.03.2022","00:00","10.12.2022","24:00","259 days","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 1 - 4","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Wels Vbf-Terminal","",2022,2022,13,14,"02.04.2022","18:00","04.04.2022","17:00","1 day + 23,0 h","cont.","SP","","ST","","","","","","","","","WN W8","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Wels Vbf-Terminal","",2022,2022,28,29,"16.07.2022","18:00","18.07.2022","12:00","1 day + 18,0 h","cont.","GES","T","ST","","","","C","","","","","Sperre Berggleis (Einfahrt Wels-Verschiebebahnhof) Errichtung Bohrpfähle für MA5.3, Einbau Hilfsbrücke zwischen Weichenverbindung ½ Wels Verschiebeb., Einbau einer Durchfahrt unter Berggleis östlich der Autobahnbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Wels Vbf-Terminal","",2022,2022,30,31,"30.07.2022","18:00","01.08.2022","12:00","1 day + 18,0 h","cont.","GES","T","ST","","","","C","","","","","Sperre Berggleis (Einfahrt Wels-Verschiebebahnhof) Errichtung Bohrpfähle für MA5.3, Einbau Hilfsbrücke zwischen Weichenverbindung ½ Wels Verschiebeb., Einbau einer Durchfahrt unter Berggleis östlich der Autobahnbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz",">","Hörsching","Marchtrenk",2022,2022,32,32,"09.08.2022","21:00","10.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","","","","Phase 1 - IB Sig. Elemente  Gleis 2 zw ES A und AS R2","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Marchtrenk","",2022,2022,32,32,"11.08.2022","21:00","12.08.2022","05:00","8,0 h","cont.","SP","","ST","","","","","","","","","Phase 3 - IB Sig. Elemente Gleis 103 zw. AS H3 und ES C\n(Traunerschleife)","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Marchtrenk","",2022,2022,32,33,"14.08.2022","17:00","15.08.2022","05:00","12,0 h","cont.","SP","","ST","","","","","","","","","Phase 0 - Einbau Weiche 34P","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz",">","Marchtrenk","Wels Hbf",2022,2022,32,33,"14.08.2022","21:00","15.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","",10,"","Phase 5 - IB Sig. Elemente Gleis 2 zw. AS R und ES Y","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","<","Wels Hbf","Marchtrenk",2022,2022,33,33,"15.08.2022","21:00","16.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","",10,"","Phase 6 - IB Sig. Elemente  Gleis 1 von ES Z bis AS R1","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","<","Marchtrenk","Sbl Hoe 2",2022,2022,41,42,"14.10.2022","22:00","17.10.2022","04:00","2 days + 6,0 h","cont.","SP","","LT","","","","","","","","","LM 22 - Einbau  Hib","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz",">","Linz Hbf Westbrücke","",2022,2022,44,47,"06.11.2022","09:00","27.11.2022","17:00","21 days + 8,0 h","cont.","SP","","ST","","","","","","","","","Einbau und Neulage von Weichen:\n518,516Neu,606,515Nneu\nSWT vsl. 27.11.22","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","<","Linz Wegscheid","St.Martin bei Traun",2022,2022,46,48,"14.11.2022","08:00","28.11.2022","01:00","13 days + 17,0 h","cont.","SP","","LT","","","","","","",5,"","Migration Linz Wegscheid BFZ Linz","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","<","Linz Hbf Westbrücke","",2022,2022,48,50,"28.11.2022","01:00","16.12.2022","12:00","18 days + 11,0 h","cont.","SP","","ST","","","","","","","","","Einbau und Neulage von Weichen:\n514Neu, 517Nneu\nWN W511","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Marchtrenk","",2023,2023,6,7,"10.02.2023","22:00","13.02.2023","04:00","2 days + 6,0 h","cont.","GES","T","ST","","","","C","","B",15,"","LM 21 - Einbau Hib\nLM 22 - Ausbau Hib","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Linz Hbf","",2023,2023,13,50,"27.03.2023","00:00","12.12.2023","24:00","261 days + 1,0 h","cont.","SP","","ST","","","","","","","","","WN","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","< >","Linz Vbf-Durchfahrgr","",2023,2023,15,16,"13.04.2023","07:00","17.04.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","EK 0,915 Scharlinz \n(Umsetzung zeitgleich mit Gl 1 km 0,862 - 1,010 0 (115lf)","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz",">","Hörsching","Marchtrenk",2023,2023,21,22,"26.05.2023","22:00","30.05.2023","04:00","3 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Ausbau Hib LM 19, LM 21,","","N","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz",">","Marchtrenk","",2023,2023,43,44,"25.10.2023","08:00","30.10.2023","20:00","5 days + 13,0 h","cont.","SP","","ST","S","","","C","","B",15,"","Anschwenkung Gleis 2 / 4Neu","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Traun - Linz","<","Marchtrenk","",2024,2024,22,23,"29.05.2024","22:00","03.06.2024","05:00","4 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Verschwenkung Gleis 1alt / 3neu / 1alt im Bahnhof Marchtrenk","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,87,"Strasbourg",">","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Entrée Lavage",2023,2023,19,19,"2023-05-10","00:25:00","2023-05-10",0.18402777777777779,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 04:00, Nuit non passe-minuit, ME",null,"Y","2022-01-06"]
[null,87,"Strasbourg","<","Graffenstaden - Raccordement","Strasbourg-Neudorf - Aiguille 4,2",2023,2023,14,14,"2023-04-07","21:00:00","2023-04-08",8.3333333333333329E-2,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V2R, 05:00, Passe-minuit, VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg",">","Graffenstaden - Raccordement","Strasbourg-Neudorf - Aiguille 4,2",2023,2023,19,19,"2023-11-09","23:30:00","2023-05-11",0.16666666666666666,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1R, 04:30, Passe-minuit, MA/ME,ME/JE",null,"Y","2022-01-06"]
[null,87,"Strasbourg",">","Strasbourg-Neudorf - Aiguille 4,2","Strasbourg-Koenigshoffen - Poste 1",2023,2023,20,20,"2023-05-15","21:00:00","2023-05-17",6.25E-2,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, V1N,V1N, 04:30, Passe-minuit, LU/MA,MA/ME",null,"Y","2022-01-06"]
[null,87,"Strasbourg","<","Strasbourg-Neudorf - Aiguille 4,2","Strasbourg-Koenigshoffen - Poste 1",2023,2023,20,20,"2023-05-17","21:00:00","2023-05-19",6.25E-2,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, V2N, 04:30, Passe-minuit, ME/JE,JE/VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Jonction Ouest",2023,2023,36,"37","2023-09-04","22:40:00","2023-09-16",0.19444444444444445,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Jonction Est",2023,2023,38,43,"2023-09-18","22:40:00","2023-10-24",0.19444444444444445,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl",">","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2023,2023,9,9,"2023-02-28","00:15:00","2023-03-03",0.25347222222222221,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1, 1V/2, 05:50, Nuit non passe-minuit, MA,ME,JE,VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","<","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2023,2023,10,10,"2023-03-06","22:55:00","2023-03-10",0.18055555555555555,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl",">","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2023,2023,18,18,"2023-05-05","00:20:00","2023-05-05",0.18055555555555555,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1, 1V/2, 04:00, Nuit non passe-minuit, VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl",">","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2022,2023,50,49,"2022-12-12","11:23:00","2023-12-08",0.51597222222222217,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Sur, V1, 1V/2, 01:00, Jour, LU,MA,ME,JE,VE",null,"Y","2022-01-06"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn","Lukavice na Moravě",2022,2022,7,10,"2022-02-16T07:00:00","7:00","2022-03-07T14:00:00","14:00","4 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2021,2022,49,49,"2021-12-12","0:00","2022-12-10T23:59:59.997","23:59","363 days + 24 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Ústí nad Orlicí","Brandýs nad Orlicí",2021,2022,49,49,"2021-12-12","0:00","2022-12-10T23:59:59.997","23:59","363 days + 24 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","Závodiště odbočka",2021,2022,49,23,"2021-12-12","0:00","2022-06-10T17:30:00","17:30","180 days + 18 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","Odb Barrandov",2021,2022,49,23,"2021-12-12","0:00","2022-06-10T17:30:00","17:30","180 days + 18 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Albrechtice u Českého Těšína","Chotěbuz (Kocobędz)",2022,2022,5,5,"2022-02-01T08:00:00","8:00","2022-02-03T15:30:00","15:30","2 x 8 hours","Periodical","Others","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,3,3,"2022-01-17T07:30:00","7:30","2022-01-18T16:00:00","16:00","2 x 9 hours","Periodical","Others","","LT","","","","","","","","","2/2 + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","<>","Bohumín-Vrbice","Bohumín-Vrbice st.hr.",2022,2022,7,7,"2022-02-15T06:40:00","6:40","2022-02-17T14:40:00","14:40","3 x 8 hours","Periodical","Others","T","LT","","","","","","","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2021,2022,49,15,"2021-12-12","0:00","2022-04-14T18:00:00","18:00","123 days + 18 hours","Continuous","Track & Rail","","ST","","","D","","","","","","záhlaví 2. traťové koleje směr Plzeň-Koterov mezi návěstidly 2KL -  Se204","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2021,2022,49,15,"2021-12-12","0:00","2022-04-14T18:00:00","18:00","123 days + 18 hours","Continuous","Track & Rail","","ST","","","D","","","","","","202. jen TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Hranice na Moravě","Hranice na Moravě město",2022,2022,2,2,"2022-01-10T08:25:00","8:25","2022-01-11T13:30:00","13:30","2 x 6 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Hranice na Moravě město","Hranice na Moravě",2022,2022,2,2,"2022-01-12T08:25:00","8:25","2022-01-13T13:30:00","13:30","2 x 6 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","Ejpovice",2022,2022,3,3,"2022-01-20T23:15:00","23:15","2022-01-21T04:15:00","4:15","1 x 5 hours","Periodical","Signal","","LT","","","","","","","","","ost. zař.: technologie 1.traťové koleje.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","Ejpovice",2022,2022,11,11,"2022-03-17T23:15:00","23:15","2022-03-18T04:15:00","4:15","1 x 5 hours","Periodical","Signal","","LT","","","","","","","","","ost. zař.: technologie 1.traťové koleje.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Ejpovice","Plzeň hlavní nádraží",2022,2022,9,9,"2022-03-03T23:15:00","23:15","2022-03-04T04:15:00","4:15","1 x 5 hours","Periodical","Signal","","LT","","","","","","","","","ost. zař.: technologie 2. traťové koleje.","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Odra odb.","Ostrava-Vítkovice",2022,2022,11,11,"2022-03-17T07:40:00","7:40","2022-03-17T17:10:00","17:10","1 x 10 hours","Periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Polanka nad Odrou výh.","Odra odb.",2022,2022,4,4,"2022-01-27T07:40:00","7:40","2022-01-27T16:00:00","16:00","1 x 9 hours","Periodical","Maintenance","T","LT","","","","","","","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Ostrava-Svinov","Odra odb.",2022,2022,4,4,"2022-01-28T08:40:00","8:40","2022-01-28T15:00:00","15:00","1 x 7 hours","Periodical","Maintenance","T","LT","","","","","","","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Ejpovice","Plzeň hlavní nádraží",2022,2022,2,2,"2022-01-12T23:15:00","23:15","2022-01-13T04:15:00","4:15","1 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,4,4,"2022-01-25T08:00:00","8:00","2022-01-27T18:00:00","18:00","2 days + 10 hours","Continuous","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Choceň, jeho část od návěstidel L2, L4 po návěstidlo 2S.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Česká Třebová","Choceň",2022,2022,2,4,"2022-01-12T07:00:00","7:00","2022-01-26T13:00:00","13:00","5 x 6 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Hradec Králové-Slez. Předměstí","",2022,2022,2,2,"2022-01-10T08:00:00","8:00","2022-01-14T14:00:00","14:00","10 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","celá + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,3,4,"2022-01-19T23:20:00","23:20","2022-01-24T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví smíchovské od náv. 2L po náv. S2 (včetně celé 2a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,3,4,"2022-01-19T23:20:00","23:20","2022-01-24T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví záhlaví smíchovské, zhlaví a záhlaví radotínské od náv. 2L po náv. 2S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,4,4,"2022-01-24T23:20:00","23:20","2022-01-27T04:20:00","4:20","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví dobřichovické od náv. L6, L8, L10 po náv. Se21, výkolejku Vk4 a náv. Se14 (včetně celé 6a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,4,4,"2022-01-24T23:20:00","23:20","2022-01-27T04:20:00","4:20","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","4.,6.,8.,10. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Zahradní Město","Praha-Hostivař",2022,2022,1,1,"2022-01-06T00:50:00","0:50","2022-01-06T04:10:00","4:10","1 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,1,1,"2022-01-06T00:50:00","0:50","2022-01-06T04:10:00","4:10","1 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Zahradní Město","Praha-Malešice",2022,2022,1,1,"2022-01-06T07:30:00","7:30","2022-01-06T17:30:00","17:30","1 x 10 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,3,3,"2022-01-18T07:40:00","7:40","2022-01-18T17:40:00","17:40","1 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví střední, jeho část od návěstidla Lc2a po návěstidla Sc2, Sc4.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,3,3,"2022-01-18T07:40:00","7:40","2022-01-18T17:40:00","17:40","1 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","sudá jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,3,3,"2022-01-19T08:00:00","8:00","2022-01-19T18:00:00","18:00","1 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví kostěnické, jeho část od návěstidla S1a, S5, S7 po návěstidlo 1L.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,3,3,"2022-01-19T08:00:00","8:00","2022-01-19T18:00:00","18:00","1 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,1c,3.,5.,7a,11.,11a,13.,13a,13b,15.,17.,23.,25.,27. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,3,3,"2022-01-19T08:00:00","8:00","2022-01-19T18:00:00","18:00","1 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,5.,5a,5b bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,4,4,"2022-01-28T03:50:00","3:50","2022-01-29T18:00:00","18:00","1 days + 15 hours","Continuous","Miscellaneous","","LT","","","D","","","B","","","2. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,7,"2022-01-29T18:00:00","18:00","2022-02-16T18:00:00","18:00","18 days + 0 hours","Continuous","Miscellaneous","","ST","","","D","","","B","","","2a jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,7,"2022-01-29T18:00:00","18:00","2022-02-16T18:00:00","18:00","18 days + 0 hours","Continuous","Miscellaneous","","ST","","","D","","","B","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,7,"2022-01-29T18:00:00","18:00","2022-02-16T18:00:00","18:00","18 days + 0 hours","Continuous","Miscellaneous","","ST","","","D","","","B","","","6. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Lipník nad Bečvou","Prosenice",2022,2022,1,1,"2022-01-09T07:15:00","7:15","2022-01-09T17:00:00","17:00","1 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Poříčany","Sadská",2022,2022,2,2,"2022-01-10T07:30:00","7:30","2022-01-12T17:30:00","17:30","3 x 10 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","",2022,2022,2,2,"2022-01-10T07:30:00","7:30","2022-01-12T17:30:00","17:30","3 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví českobrodské od návěstidel L4,L6,L8 po zarážedlo kusé SK 4a (včetně SK 4a).","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","Odb Tatce",2022,2022,4,4,"2022-01-24T22:00:00","22:00","2022-01-28T05:00:00","5:00","4 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,1,2,"2022-01-05T22:00:00","22:00","2022-01-14T05:00:00","5:00","9 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,3,5,"2022-01-17T23:00:00","23:00","2022-01-31T04:30:00","4:30","6 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","201. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,9,9,"2022-03-01T23:00:00","23:00","2022-03-02T04:30:00","4:30","1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","201. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,13,13,"2022-03-28T23:00:00","23:00","2022-03-30T04:30:00","4:30","2 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","201. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,5,5,"2022-01-31T23:00:00","23:00","2022-02-01T04:30:00","4:30","1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","záhlaví 1. traťové koleje směr Plzeň-Koterov mezi návěstidly 1KL -  Se203","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,12,12,"2022-03-25T23:00:00","23:00","2022-03-26T04:30:00","4:30","1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","záhlaví 1. traťové koleje směr Plzeň-Koterov mezi návěstidly 1KL -  Se203","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,5,"2022-01-30T23:20:00","23:20","2022-02-01T04:00:00","4:00","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,3.,2.,4.,5.,11.,11a,13.,13a,15. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,5,"2022-01-30T23:20:00","23:20","2022-02-01T04:00:00","4:00","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví střední, jeho část od návěstidel Sc1, Sc3 po návěstidlo Lc1a.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,5,"2022-01-30T23:20:00","23:20","2022-02-01T04:00:00","4:00","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví 1. TK směr Kostěnice, jeho část od návěstidla S1a po návěstidlo 1L.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,4,5,"2022-01-30T23:20:00","23:20","2022-02-01T04:00:00","4:00","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","4. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,3,3,"2022-01-18T08:00:00","8:00","2022-01-18T18:00:00","18:00","1 x 10 hours","Periodical","Switch","","LT","","","","","","","","","zab. zař. PZS v km 297,908 (P4902) a v km 302,038 (P4903) mezi dopravnami.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,3,3,"2022-01-19T08:00:00","8:00","2022-01-19T18:00:00","18:00","1 x 10 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. PZS v km 297,908 (P4902) a v km 302,038 (P4903) mezi dopravnami.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Říkovice","Přerov",2022,2022,5,5,"2022-02-05T08:00:00","8:00","2022-02-05T17:00:00","17:00","1 x 9 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","",2022,2022,2,3,"2022-01-12T07:15:00","7:15","2022-01-23T17:00:00","17:00","11 days + 10 hours","Continuous","Signal","","ST","","","","","","B","","","zab. zař. staniční.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Lipník nad Bečvou",2022,2022,2,2,"2022-01-12T07:15:00","7:15","2022-01-15T17:00:00","17:00","3 days + 10 hours","Continuous","Signal","","LT","","","","","","B","","","zab. zař. traťové 1.,2.TK.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Prosenice",2022,2022,4,4,"2022-01-24T08:10:00","8:10","2022-01-24T11:55:00","11:55","1 x 4 hours","Periodical","Signal","","LT","","","","","","","","","2S bez TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","",2022,2022,4,4,"2022-01-24T12:10:00","12:10","2022-01-24T16:10:00","16:10","1 x 4 hours","Periodical","Signal","","ST","","","","","","B","","","záhlaví směr Přerov, jeho část od náv. 1S po náv. Se21","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","",2022,2022,2,2,"2022-01-11T08:00:00","8:00","2022-01-11T12:00:00","12:00","1 x 4 hours","Periodical","Signal","","ST","","","","","","B","","","záhlaví směr Přerov, jeho část od náv. 2S po náv. Se23","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Přerov",2022,2022,4,4,"2022-01-25T08:00:00","8:00","2022-01-25T12:00:00","12:00","1 x 4 hours","Periodical","Signal","","LT","","","","","","B","","","2 bez TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Dluhonice výhybna",2022,2022,4,4,"2022-01-25T12:10:00","12:10","2022-01-25T15:55:00","15:55","1 x 4 hours","Periodical","Signal","","LT","","","","","","","","","1S bez TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Ostrava hlavní nádraží","Ostrava-Svinov",2022,2022,9,9,"2022-03-03T07:00:00","7:00","2022-03-04T17:00:00","17:00","2 x 10 hours","Periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Ostrava-Svinov","Ostrava-Třebovice",2022,2022,8,8,"2022-02-21T07:35:00","7:35","2022-02-23T16:30:00","16:30","3 x 9 hours","Periodical","Maintenance","T","LT","","","D","","","B","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Jistebník","Polanka nad Odrou výh.",2022,2022,8,8,"2022-02-21T07:30:00","7:30","2022-02-21T16:30:00","16:30","1 x 9 hours","Periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Ostrava-Svinov","Polanka nad Odrou výh.",2022,2022,10,10,"2022-03-10T07:30:00","7:30","2022-03-10T15:00:00","15:00","1 x 8 hours","Periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Lhotka nad Bečvou","Hustopeče nad Bečvou",2022,2022,5,7,"2022-02-03T07:30:00","7:30","2022-02-16T13:30:00","13:30","3 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2022,2022,5,5,"2022-02-05T08:10:00","8:10","2022-02-05T13:50:00","13:50","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Ejpovice","Plzeň hlavní nádraží",2022,2022,6,6,"2022-02-10T23:15:00","23:15","2022-02-11T04:15:00","4:15","1 x 5 hours","Periodical","Tunnel","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Přerov",2022,2022,7,7,"2022-02-15T08:00:00","8:00","2022-02-15T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6 kV proautomatický blok.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Přerov","Dluhonice výhybna",2022,2022,7,7,"2022-02-15T08:00:00","8:00","2022-02-15T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6 kV pro automatický blok.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín bývalá Odb Bečva",2022,2022,2,3,"2022-01-15T07:40:00","7:40","2022-01-18T16:40:00","16:40","4 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Vsetín","",2022,2022,2,2,"2022-01-15T07:40:00","7:40","2022-01-16T17:15:00","17:15","2 x 10 hours","Periodical","Catenary","","ST","","","","","","B","","","záhlaví TK směr Hovězí","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Vsetín","",2022,2022,3,3,"2022-01-17T07:40:00","7:40","2022-01-18T17:15:00","17:15","2 x 10 hours","Periodical","Catenary","","ST","","","","","","B","","","zhlaví směr Hovězí, úsek koleje od začátku výh. č. 1 po námezník. výh. č. 2.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,4,5,"2022-01-25T08:00:00","8:00","2022-01-31T16:40:00","16:40","7 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Říkovice","Prosenice",2022,2022,7,7,"2022-02-15T07:00:00","7:00","2022-02-15T15:00:00","15:00","1 x 8 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Malešice","Praha-Zahradní Město",2022,2022,6,6,"2022-02-07T08:00:00","8:00","2022-02-07T16:00:00","16:00","1 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Malešice","Praha-Hostivař",2022,2022,8,8,"2022-02-26T08:00:00","8:00","2022-02-26T18:00:00","18:00","1 x 10 hours","Periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Zahradní Město","Praha-Malešice",2022,2022,1,1,"2022-01-06T00:50:00","0:50","2022-01-06T04:10:00","4:10","3 x 4 hours","Periodical","Miscellaneous","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2022,2022,7,7,"2022-02-16T07:00:00","7:00","2022-02-16T15:00:00","15:00","2 x 8 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Velim",2022,2022,6,6,"2022-02-12T08:00:00","8:00","2022-02-12T16:00:00","16:00","1 x 8 hours","Periodical","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ 1.TK - kolejové obvody 1T1,1T2,1T3,1T4,1T5.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Velim",2022,2022,3,3,"2022-01-22T08:30:00","8:30","2022-01-22T16:00:00","16:00","1 x 8 hours","Periodical","Miscellaneous","","LT","","","","","","","","","zab. zař. TZZ 1.TK - návěstidla 1-3575, 1-3582, 1-3585, 1-3592.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pečky","Poříčany",2022,2022,8,8,"2022-02-21T07:30:00","7:30","2022-02-25T17:30:00","17:30","4 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","",2022,2022,4,4,"2022-01-26T22:00:00","22:00","2022-01-29T05:00:00","5:00","3 x 7 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","0. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Dluhonice výhybna",2022,2022,4,10,"2022-01-30T05:30:00","5:30","2022-03-07T17:00:00","17:00","36 days + 12 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1S + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Přerov","",2022,2022,4,20,"2022-01-30T05:30:00","5:30","2022-05-20T17:00:00","17:00","110 days + 12 hours","Continuous","Miscellaneous","","ST","","","D","","","","","","4.,6. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","",2022,2022,4,4,"2022-01-29T22:50:00","22:50","2022-01-30T05:30:00","5:30","1 x 7 hours","Periodical","Catenary","","ST","","","D","","","B","","","1.,3.,4.,6.,8.,10. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Libeň","Praha-Holešovice",2022,2022,5,5,"2022-02-01T09:00:00","9:00","2022-02-01T15:00:00","15:00","1 x 6 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","",2022,2022,5,6,"2022-02-01T21:25:00","21:25","2022-02-10T04:25:00","4:25","7 x 7 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","1.,3. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Přerov",2022,2022,5,6,"2022-02-01T21:25:00","21:25","2022-02-10T04:25:00","4:25","7 x 7 hours","Periodical","Miscellaneous","","LT","","","D","","","B","","","1. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,8,9,"2022-02-27T22:10:00","22:10","2022-02-28T04:20:00","4:20","1 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví smíchovské od náv. 2L po náv. S2 (včetně celé 2a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,8,9,"2022-02-27T22:10:00","22:10","2022-02-28T04:20:00","4:20","1 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví záhlaví smíchovské, zhlaví a záhlaví radotínské od náv. 2L po náv. 2S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,9,9,"2022-02-28T22:10:00","22:10","2022-03-05T04:20:00","4:20","5 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví smíchovské od náv. 2L po náv. S2 (včetně celé 2a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,9,9,"2022-02-28T22:10:00","22:10","2022-03-05T04:20:00","4:20","5 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví záhlaví smíchovské, zhlaví a záhlaví radotínské od náv. 2L po náv. 2S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,9,9,"2022-02-28T22:10:00","22:10","2022-03-05T04:20:00","4:20","10 x 7 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,9,10,"2022-03-05T22:10:00","22:10","2022-03-12T04:20:00","4:20","14 x 7 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,6,7,"2022-02-13T22:10:00","22:10","2022-02-16T04:20:00","4:20","3 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví smíchovské od náv. 2L po náv. S2 (včetně celé 2a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,7,7,"2022-02-14T23:20:00","23:20","2022-02-16T04:20:00","4:20","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví smíchovské / krčské od námezníku výh. č. 14 a náv. Se13 po náv. Sc4, Sc6, S8 a S10 (včetně celé 4b staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,7,7,"2022-02-14T23:20:00","23:20","2022-02-16T04:20:00","4:20","2 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","8a bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Dobřichovice","Praha-Radotín",2022,2022,7,7,"2022-02-19T07:30:00","7:30","2022-02-20T17:30:00","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Tunel odb.","Závodiště odbočka",2022,2022,5,5,"2022-02-05T07:30:00","7:30","2022-02-06T07:30:00","7:30","1 days + 0 hours","Continuous","Miscellaneous","","LT","","","","","","","","","4. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Krč","Tunel odb.",2022,2022,6,7,"2022-02-11T23:20:00","23:20","2022-02-14T04:20:00","4:20","2 x 5 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,5,5,"2022-02-01T22:45:00","22:45","2022-02-05T04:35:00","4:35","4 x 6 hours","Periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví 1.TK směr Choceň, jeho část od návěstidla 1S po námezník výhybky číslo 12 .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,6,7,"2022-02-09T22:45:00","22:45","2022-02-14T04:35:00","4:35","5 x 6 hours","Periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví 1.TK směr Choceň, jeho část od návěstidla 1S po námezník výhybky číslo 12 .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,6,7,"2022-02-09T22:45:00","22:45","2022-02-14T04:35:00","4:35","5 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","2.,2a,4. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Odb Bezpráví","Brandýs nad Orlicí",2022,2022,6,7,"2022-02-09T22:45:00","22:45","2022-02-14T04:35:00","4:35","10 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,9,10,"2022-03-01T22:45:00","22:45","2022-03-10T04:35:00","4:35","8 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví 2.TK směr Odb Bezpráví.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,6,7,"2022-02-09T22:45:00","22:45","2022-02-14T04:35:00","4:35","5 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví 2.TK směr Odb Bezpráví","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,6,7,"2022-02-09T22:45:00","22:45","2022-02-14T04:35:00","4:35","5 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví 2.TK směr Choceň.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,6,7,"2022-02-13T22:10:00","22:10","2022-02-16T04:20:00","4:20","6 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,10,10,"2022-03-07T22:10:00","22:10","2022-03-12T04:20:00","4:20","10 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,13,13,"2022-03-28T22:10:00","22:10","2022-03-31T04:20:00","4:20","6 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,5,5,"2022-02-01T23:20:00","23:20","2022-02-04T04:00:00","4:00","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví střední, jeho část od návěstidla Lc2a po návěstidla Sc2, Sc4.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,5,5,"2022-02-01T23:20:00","23:20","2022-02-04T04:00:00","4:00","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví střední, jeho část od návěstidla Sc11 po návěstidla Lc5, Lc7, Lc11a.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,5,5,"2022-02-01T23:20:00","23:20","2022-02-04T04:00:00","4:00","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,1c,3.,5.,7a,11.,11a,13.,13a,13b,15.,17.,23.,25.,27. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,5,5,"2022-02-01T23:20:00","23:20","2022-02-04T04:00:00","4:00","3 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,3.,2.,4.,5.,11.,11a,13.,13a,15. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,8,8,"2022-02-25T23:40:00","23:40","2022-02-27T04:35:00","4:35","2 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","zhlaví střední, jeho část od návěstidla Sc1 po návěstidlo Lc1a.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,7,7,"2022-02-18T23:40:00","23:40","2022-02-20T04:35:00","4:35","2 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","záhlaví a zhlaví 2. TK směr Kostěnice, jeho část od návěstidla 2L po návěstidlo S2a.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,7,7,"2022-02-18T23:40:00","23:40","2022-02-20T04:35:00","4:35","2 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","2a,6. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,8,8,"2022-02-25T23:40:00","23:40","2022-02-27T04:35:00","4:35","2 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","2a,6. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,8,8,"2022-02-25T23:40:00","23:40","2022-02-27T04:35:00","4:35","2 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","1.,3. jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn","Česká Třebová",2022,2022,8,8,"2022-02-22T06:30:00","6:30","2022-02-22T13:30:00","13:30","1 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn","Tatenice",2022,2022,7,7,"2022-02-16T07:30:00","7:30","2022-02-17T14:30:00","14:30","2 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Česká Třebová odjezdová skupina","Parník odb.",2022,2022,8,8,"2022-02-23T07:30:00","7:30","2022-02-24T14:30:00","14:30","2 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","4. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Zámrsk","Uhersko",2022,2022,10,10,"2022-03-11T07:45:00","7:45","2022-03-11T14:40:00","14:40","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Choceň","",2022,2022,8,8,"2022-02-21T08:25:00","8:25","2022-02-22T14:25:00","14:25","2 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví traťové koleje směr Vysoké Mýto, jeho část od návěstidla Se33 po návěstidlo MS","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Lhotka nad Bečvou","Valašské Meziříčí",2022,2022,12,12,"2022-03-21T07:00:00","7:00","2022-03-24T15:00:00","15:00","3 days + 8 hours","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašské Meziříčí","Lhotka nad Bečvou",2022,2022,13,13,"2022-03-28T07:00:00","7:00","2022-03-31T15:00:00","15:00","3 days + 8 hours","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,3,4,"2022-01-19T23:20:00","23:20","2022-01-24T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","4.,6.,8.,10. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,3,4,"2022-01-19T23:20:00","23:20","2022-01-24T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","sudá jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","Dobřichovice",2022,2022,3,4,"2022-01-19T23:20:00","23:20","2022-01-24T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Říkovice","Přerov",2022,2022,6,6,"2022-02-07T08:00:00","8:00","2022-02-07T14:00:00","14:00","1 x 6 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. traťové 1.,2. TK.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Blatec",2022,2022,9,9,"2022-03-01T08:00:00","8:00","2022-03-01T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6 kV pro PZS v  km 99,184.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Vsetín","Valašské Meziříčí",2022,2022,10,10,"2022-03-08T08:00:00","8:00","2022-03-08T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. vypne senapájení 6 kV AB.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Horní Lideč","Valašská Polanka",2022,2022,15,15,"2022-04-12T08:00:00","8:00","2022-04-12T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. vypne se napájení 6kV.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Drahotuše","Hranice na Moravě",2022,2022,10,10,"2022-03-07T07:00:00","7:00","2022-03-10T17:00:00","17:00","3 days + 10 hours","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","",2022,2022,10,10,"2022-03-07T07:40:00","7:40","2022-03-08T14:40:00","14:40","2 x 7 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví směr Velká Bystřice","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašské Meziříčí","Hostašovice",2022,2022,11,11,"2022-03-15T07:45:00","7:45","2022-03-16T13:45:00","13:45","2 x 6 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. 6kV PZZ v km 62,635; 64,219; 65,474; 65,880; 66,594 a 68,662.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Štěpánov","Červenka",2022,2022,10,10,"2022-03-07T07:30:00","7:30","2022-03-07T13:30:00","13:30","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Mohelnice","Moravičany",2022,2022,7,10,"2022-02-19T07:30:00","7:30","2022-03-09T13:25:00","13:25","2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Hranice na Moravě město","Hranice na Moravě",2022,2022,11,11,"2022-03-14T07:30:00","7:30","2022-03-14T13:00:00","13:00","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Hranice na Moravě město","",2022,2022,11,11,"2022-03-15T07:30:00","7:30","2022-03-15T13:00:00","13:00","1 x 6 hours","Periodical","Catenary","","ST","","","D","","","","","","lichá jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn předjízdné koleje","Zábřeh na Moravě",2022,2022,8,8,"2022-02-24T07:45:00","7:45","2022-02-24T14:15:00","14:15","1 x 7 hours","Periodical","Tunnel","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Zábřeh na Moravě","Hoštejn předjízdné koleje",2022,2022,8,8,"2022-02-25T07:45:00","7:45","2022-02-25T14:15:00","14:15","1 x 7 hours","Periodical","Tunnel","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Moravičany","Červenka",2022,2022,13,13,"2022-03-28T07:00:00","7:00","2022-03-28T14:00:00","14:00","1 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. PZS v km 61,599.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Červenka","Štěpánov",2022,2022,13,13,"2022-03-28T07:00:00","7:00","2022-03-28T14:00:00","14:00","1 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. Vypnutí záložního napájení PZS v km 71,429 (Střeň).","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Horní Lideč","Vsetín",2022,2022,10,10,"2022-03-08T07:00:00","7:00","2022-03-08T14:00:00","14:00","1 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn","Lukavice na Moravě",2022,2022,15,15,"2022-04-13T07:00:00","7:00","2022-04-14T14:00:00","14:00","4 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,9,9,"2022-03-03T09:20:00","9:20","2022-03-03T12:30:00","12:30","1 x 4 hours","Periodical","Catenary","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","<>","Louky nad Olší","Karviná hlavní nádraží",2022,2022,12,12,"2022-03-21T07:30:00","7:30","2022-03-25T17:10:00","17:10","5 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","1/1 + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","Ejpovice",2022,2022,10,10,"2022-03-09T23:15:00","23:15","2022-03-10T04:15:00","4:15","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Ejpovice","Plzeň hlavní nádraží",2022,2022,10,10,"2022-03-10T23:15:00","23:15","2022-03-11T04:15:00","4:15","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Prosenice",2022,2022,6,7,"2022-02-13T22:50:00","22:50","2022-02-14T05:30:00","5:30","1 x 7 hours","Periodical","Signal","","LT","","","D","","","","","","2S jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Prosenice",2022,2022,9,9,"2022-03-02T22:20:00","22:20","2022-03-05T04:20:00","4:20","3 x 6 hours","Periodical","Catenary","T","LT","","","","","","","","","2S + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,9,9,"2022-03-04T23:00:00","23:00","2022-03-06T04:05:00","4:05","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,10,10,"2022-03-10T23:00:00","23:00","2022-03-12T04:05:00","4:05","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,13,13,"2022-03-29T23:00:00","23:00","2022-04-01T04:05:00","4:05","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,10,11,"2022-03-07T23:00:00","23:00","2022-03-18T04:05:00","4:05","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,11,11,"2022-03-14T23:00:00","23:00","2022-03-15T04:05:00","4:05","1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Odb Cerhenice","Pečky",2022,2022,13,13,"2022-03-31T23:00:00","23:00","2022-04-01T04:05:00","4:05","1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pečky","Poříčany",2022,2022,12,13,"2022-03-25T23:00:00","23:00","2022-03-28T04:05:00","4:05","3 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pečky","Poříčany",2022,2022,12,13,"2022-03-25T23:00:00","23:00","2022-03-28T04:05:00","4:05","3 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","Pečky",2022,2022,10,10,"2022-03-11T23:00:00","23:00","2022-03-12T04:05:00","4:05","1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","Pečky",2022,2022,10,11,"2022-03-13T23:00:00","23:00","2022-03-15T04:05:00","4:05","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Uhersko","Moravany",2022,2022,11,11,"2022-03-15T07:50:00","7:50","2022-03-15T14:50:00","14:50","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Cheb","Františkovy Lázně",2022,2022,1,1,"2022-01-08T07:20:00","7:20","2022-01-09T15:30:00","15:30","2 x 9 hours","Periodical","Catenary","T","LT","","","","","","B","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Poříčany",2022,2022,12,12,"2022-03-25T22:00:00","22:00","2022-03-27T05:00:00","5:00","2 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Poříčany",2022,2022,12,12,"2022-03-26T08:00:00","8:00","2022-03-26T16:00:00","16:00","1 x 8 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,13,13,"2022-03-30T23:00:00","23:00","2022-04-01T05:00:00","5:00","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Hostivař","Praha-Zahradní Město",2022,2022,13,13,"2022-03-30T23:00:00","23:00","2022-04-01T05:00:00","5:00","2 x 6 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Zadní Třebaň",2022,2022,9,9,"2022-03-04T09:05:00","9:05","2022-03-05T17:05:00","17:05","3 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Řevnice","Zadní Třebaň",2022,2022,10,11,"2022-03-13T09:05:00","9:05","2022-03-14T17:00:00","17:00","3 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Albrechtice u Českého Těšína","Havířov",2022,2022,10,11,"2022-03-07T07:00:00","7:00","2022-03-15T15:10:00","15:10","4 x 9 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Albrechtice u Českého Těšína","Havířov",2022,2022,13,13,"2022-04-01T07:00:00","7:00","2022-04-01T15:00:00","15:00","1 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Malešice","",2022,2022,5,5,"2022-02-05T08:00:00","8:00","2022-02-06T16:00:00","16:00","2 x 8 hours","Periodical","Catenary","","ST","","","D","","","","","","celá jen TV. \nzhlaví ve směru Praha-Hostivař a Praha-Zahradní Město.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Malešice","Praha-Hostivař",2022,2022,7,7,"2022-02-20T08:00:00","8:00","2022-02-20T18:00:00","18:00","1 x 10 hours","Periodical","Catenary","T","LT","","","","","","","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Malešice","Praha-Zahradní Město",2022,2022,6,6,"2022-02-10T08:00:00","8:00","2022-02-11T16:00:00","16:00","2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,11,11,"2022-03-14T23:00:00","23:00","2022-03-19T03:00:00","3:00","5 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,12,12,"2022-03-21T00:50:00","0:50","2022-03-25T04:20:00","4:20","10 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,10,10,"2022-03-07T23:20:00","23:20","2022-03-12T04:20:00","4:20","5 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","sudá jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,10,10,"2022-03-09T23:20:00","23:20","2022-03-12T04:20:00","4:20","3 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","záhlaví a zhlaví záhlaví krčské, zhlaví a záhlaví radotínské od náv. 4L po náv. 4S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,13,13,"2022-03-28T23:20:00","23:20","2022-03-31T04:20:00","4:20","3 x 5 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","záhlaví a zhlaví záhlaví krčské, zhlaví a záhlaví radotínské od náv. 4L po náv. 4S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Tunel odb.","Závodiště odbočka",2022,2022,13,13,"2022-03-28T23:20:00","23:20","2022-03-31T04:20:00","4:20","6 x 5 hours","Periodical","Miscellaneous","T","LT","","","D","","","","","","4. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,10,10,"2022-03-09T23:20:00","23:20","2022-03-10T04:00:00","4:00","1 x 5 hours","Periodical","Catenary","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Kostěnice, jeho část od návěstidla 2L po návěstidlo S2a, Se7.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,9,9,"2022-03-05T08:00:00","8:00","2022-03-06T18:00:00","18:00","2 x 10 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Ošelín","",2022,2022,12,12,"2022-03-23T07:30:00","7:30","2022-03-23T17:30:00","17:30","3 x 10 hours","Periodical","Track & Rail","","ST","","","","","","B","","","celá + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Chodová Planá","Mariánské Lázně",2022,2022,12,12,"2022-03-25T07:10:00","7:10","2022-03-25T15:00:00","15:00","2 x 8 hours","Periodical","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Cheb","",2022,2022,14,14,"2022-04-06T23:30:00","23:30","2022-04-08T04:00:00","4:00","4 x 5 hours","Periodical","Catenary","","ST","","","D","","","","","","","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,12,12,"2022-03-24T07:00:00","7:00","2022-03-24T15:00:00","15:00","1 x 8 hours","Periodical","Maintenance","","ST","","","D","","","","","","107a bez TV. ","","","2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Plzeň hl.n.Nová Hospoda","Vejprnice",2022,2022,12,12,"2022-03-22T08:00:00","8:00","2022-03-22T14:00:00","14:00","1 x 6 hours","Periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kolín","Velim",2022,2022,1,1,"2022-01-07T09:40:00","9:40","2022-01-09T13:00:00","13:00","3 x 4 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Krč","Tunel odb.",2022,2022,2,2,"2022-01-15T07:30:00","7:30","2022-01-16T17:30:00","17:30","2 x 10 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","traťová bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Poříčany",2022,2022,12,12,"2022-03-21T22:00:00","22:00","2022-03-24T05:00:00","5:00","3 x 7 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","Český Brod",2022,2022,12,12,"2022-03-21T23:00:00","23:00","2022-03-24T04:15:00","4:15","3 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Tršnice","Cheb",2022,2022,16,16,"2022-04-20T08:00:00","8:00","2022-04-20T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. traťové .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn předjízdné koleje","Zábřeh na Moravě",2022,2022,13,13,"2022-04-02T07:30:00","7:30","2022-04-02T15:30:00","15:30","1 x 8 hours","Periodical","Switch","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,11,11,"2022-03-16T22:10:00","22:10","2022-03-18T05:40:00","5:40","2 x 8 hours","Periodical","Switch","","ST","","","D","","","","","","962,512a jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Plzeň hlavní nádraží","",2022,2022,11,11,"2022-03-16T22:10:00","22:10","2022-03-18T05:40:00","5:40","2 x 8 hours","Periodical","Switch","","ST","","","D","","","","","","512a bez TV. ","","","2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Poříčany","Sadská",2022,2022,5,5,"2022-02-03T09:00:00","9:00","2022-02-03T14:00:00","14:00","1 x 5 hours","Periodical","Others","T","LT","","","","","","B","","","traťová + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,3,4,"2022-01-22T22:45:00","22:45","2022-01-25T04:35:00","4:35","3 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","zhlaví 1. TK směr Odb Bezpráví, od návěstidla Se3 po návěstidlo Sc1b .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,2,3,"2022-01-16T22:45:00","22:45","2022-01-20T04:35:00","4:35","4 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví 1., 2. TK směr Odb. Bezpráví","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,2,3,"2022-01-16T22:45:00","22:45","2022-01-20T04:35:00","4:35","4 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 1. TK směr Choceň, jeho část od návěstidla L1 a námezníku výhybky číslo 11 po návěstidlo 1S.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,3,4,"2022-01-22T22:45:00","22:45","2022-01-25T04:35:00","4:35","3 x 6 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Choceň, jeho část od návěstidel L2, L4 po návěstidlo 2S.","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Albrechtice u Českého Těšína","Havířov",2022,2022,17,17,"2022-04-26T07:00:00","7:00","2022-04-30T17:00:00","17:00","4 days + 10 hours","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Cesky Tesin - Zilina","<>","Český Těšín","Albrechtice u Českého Těšína",2022,2022,17,18,"2022-05-01T07:00:00","7:00","2022-05-02T17:00:00","17:00","2 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Havířov","Albrechtice u Českého Těšína",2022,2022,14,14,"2022-04-05T07:00:00","7:00","2022-04-06T15:00:00","15:00","2 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Velká Bystřice",2022,2022,14,14,"2022-04-07T08:00:00","8:00","2022-04-07T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6kV pro PZS v km 4,563 a km 5,605.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Lipník nad Bečvou","Prosenice",2022,2022,15,15,"2022-04-12T08:00:00","8:00","2022-04-12T13:00:00","13:00","1 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6 kV pro PZS v km 194,724.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Říkovice","Přerov",2021,2022,49,35,"2021-12-12","0:00","2022-08-31T16:00:00","16:00","262 days + 16 hours","Continuous","Miscellaneous","","LT","","","","","","","","","zab. zař. ETCS.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","",2022,2022,14,14,"2022-04-10T08:00:00","8:00","2022-04-10T13:00:00","13:00","1 x 5 hours","Periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Červenka","",2022,2022,14,14,"2022-04-10T08:00:00","8:00","2022-04-10T13:00:00","13:00","1 x 5 hours","Periodical","Catenary","","ST","","","D","","","","","","sudá + TV. \nzáhlaví a zhlaví směr Štěpánov, úsek koleje od náv. 2L po náv. S2, S4.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Červenka","",2022,2022,16,16,"2022-04-23T08:00:00","8:00","2022-04-23T13:00:00","13:00","1 x 5 hours","Periodical","Catenary","","ST","","","D","","","","","","1.,3. bez TV, lichá jen TV. \nzáhlaví a zhlaví směr Moravičany, úsek koleje od náv. 1S po námezník výh. 22.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Štěpánov","",2022,2022,15,15,"2022-04-11T08:30:00","8:30","2022-04-11T12:30:00","12:30","1 x 4 hours","Periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Moravičany","",2022,2022,17,17,"2022-04-25T08:30:00","8:30","2022-04-25T12:30:00","12:30","1 x 4 hours","Periodical","Catenary","","ST","","","D","","","","","","celá jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Blatec",2022,2022,14,14,"2022-04-04T23:00:00","23:00","2022-04-05T03:00:00","3:00","1 x 4 hours","Periodical","Catenary","","LT","","","D","","","","","","traťová jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brodek u Přerova","Dluhonice výhybna",2022,2022,21,21,"2022-05-23T08:00:00","8:00","2022-05-23T16:00:00","16:00","1 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hranice na Moravě","Drahotuše",2022,2022,16,16,"2022-04-23T07:00:00","7:00","2022-04-24T17:00:00","17:00","1 days + 10 hours","Continuous","Switch","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,4,5,"2022-01-28T22:45:00","22:45","2022-02-01T04:35:00","4:35","4 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","zhlaví 1. TK směr Odb Bezpráví, od návěstidla Se3 po návěstidlo Sc1b .","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,4,4,"2022-01-25T22:45:00","22:45","2022-01-26T04:35:00","4:35","1 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","1.,1a,1b + TV. \nzhlaví střední, jeho část od návěstidla Se5 po návěstidlo Sc1 a námezník výhybky číslo 7.","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brandýs n. Orlicí předjízdné koleje","",2022,2022,4,5,"2022-01-28T22:45:00","22:45","2022-02-01T04:35:00","4:35","4 x 6 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví 1., 2. TK směr Odb. Bezpráví","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Cheb","Tršnice",2022,2022,16,16,"2022-04-21T07:00:00","7:00","2022-04-21T14:30:00","14:30","1 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hustopeče nad Bečvou","Hranice na Moravě",2022,2022,14,14,"2022-04-04T07:30:00","7:30","2022-04-06T13:30:00","13:30","3 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Jablůnka","Valašské Meziříčí",2022,2022,14,14,"2022-04-07T07:30:00","7:30","2022-04-07T17:30:00","17:30","1 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,5,5,"2022-02-03T23:00:00","23:00","2022-02-05T03:00:00","3:00","2 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,14,14,"2022-04-04T23:00:00","23:00","2022-04-09T03:00:00","3:00","5 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,18,18,"2022-05-02T23:00:00","23:00","2022-05-07T03:00:00","3:00","5 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,21,21,"2022-05-23T23:00:00","23:00","2022-05-28T03:00:00","3:00","5 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Valašská Polanka","Vsetín",2022,2022,20,20,"2022-05-21T23:25:00","23:25","2022-05-22T03:50:00","3:50","1 x 5 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Cheb","Tršnice",2022,2022,6,6,"2022-02-08T07:30:00","7:30","2022-02-08T09:30:00","9:30","1 x 2 hours","Periodical","Signal","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Tršnice","Cheb",2022,2022,6,6,"2022-02-08T10:30:00","10:30","2022-02-08T12:30:00","12:30","1 x 2 hours","Periodical","Signal","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","Návsí (Nawsie)",2022,2022,15,15,"2022-04-14T07:20:00","7:20","2022-04-14T10:00:00","10:00","1 x 3 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Cesky Tesin - Zilina","<>","Návsí (Nawsie)","Mosty u Jabl. (Mosty koło Jabł.)",2022,2022,15,15,"2022-04-14T10:00:00","10:00","2022-04-14T19:00:00","19:00","1 x 9 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Ostrava-Vítkovice","Ostrava-Kunčice",2022,2022,15,15,"2022-04-14T08:00:00","8:00","2022-04-14T12:00:00","12:00","1 x 4 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 bez TV. ","","","2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Ostrava-Vítkovice","Odra odb.",2022,2022,16,16,"2022-04-19T07:00:00","7:00","2022-04-19T17:00:00","17:00","1 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Hranice na Moravě","Polom",2022,2022,14,14,"2022-04-04T07:30:00","7:30","2022-04-06T18:15:00","18:15","2 days + 11 hours","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Polom","Hranice na Moravě",2022,2022,14,14,"2022-04-09T18:00:00","18:00","2022-04-09T20:00:00","20:00","1 x 2 hours","Periodical","Others","","LT","","","","","","","","","zab. zař. v 2. traťové koleji.","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Polanka nad Odrou výh.","Jistebník",2022,2022,16,16,"2022-04-20T13:00:00","13:00","2022-04-20T19:00:00","19:00","1 x 6 hours","Periodical","Maintenance","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Hranice na Moravě","Polom",2022,2022,14,14,"2022-04-04T07:00:00","7:00","2022-04-05T17:00:00","17:00","2 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Polom",2022,2022,15,15,"2022-04-12T07:00:00","7:00","2022-04-12T13:00:00","13:00","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Polom","Suchdol nad Odrou",2022,2022,15,15,"2022-04-13T07:00:00","7:00","2022-04-13T13:00:00","13:00","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Lipová u Chebu","Cheb",2022,2022,12,12,"2022-03-25T11:00:00","11:00","2022-03-25T13:00:00","13:00","1 x 2 hours","Periodical","Signal","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Ejpovice","Plzeň hlavní nádraží",2022,2022,14,14,"2022-04-07T23:15:00","23:15","2022-04-08T04:15:00","4:15","1 x 5 hours","Periodical","Tunnel","","LT","","","","","","","","","ost. zař.: technologie 2. traťové koleje.","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Vsetín","Jablůnka",2022,2022,6,6,"2022-02-08T07:40:00","7:40","2022-02-12T15:40:00","15:40","5 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Jablůnka","Vsetín",2022,2022,8,9,"2022-02-27T08:00:00","8:00","2022-02-28T16:40:00","16:40","2 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Praha-Radotín","",2022,2022,13,14,"2022-04-01T22:10:00","22:10","2022-04-05T04:20:00","4:20","4 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví smíchovské od náv. 2L po náv. S2 (včetně celé 2a staniční koleje).","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,13,14,"2022-04-01T22:10:00","22:10","2022-04-05T04:20:00","4:20","4 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví záhlaví smíchovské, zhlaví a záhlaví radotínské od náv. 2L po náv. 2S.","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,14,14,"2022-04-05T23:20:00","23:20","2022-04-09T04:20:00","4:20","8 x 5 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Odb Barrandov","Závodiště odbočka",2022,2022,14,14,"2022-04-05T23:20:00","23:20","2022-04-09T04:20:00","4:20","8 x 5 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2021-12-23"]
[null,54,"Plzen - Praha","<>","Závodiště odbočka","",2022,2022,15,15,"2022-04-13T22:10:00","22:10","2022-04-14T04:20:00","4:20","1 x 7 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví radotínské od námezníku výh. č. 2 po náv. 2S","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Uhersko","",2022,2022,15,15,"2022-04-15T23:00:00","23:00","2022-04-17T05:00:00","5:00","2 x 6 hours","Periodical","Others","","ST","","","","","","B","","","celá bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2022,2022,14,14,"2022-04-07T08:00:00","8:00","2022-04-09T18:00:00","18:00","3 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2022,2022,16,16,"2022-04-18T23:20:00","23:20","2022-04-19T04:00:00","4:00","1 x 5 hours","Periodical","Miscellaneous","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Přelouč, jeho část od návěstidla L2 po návěstidlo 2S.","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Přelouč nákladní nádraží",2022,2022,16,16,"2022-04-18T23:20:00","23:20","2022-04-19T04:00:00","4:00","1 x 5 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","1.,2. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","",2022,2022,10,13,"2022-03-13T22:50:00","22:50","2022-03-30T04:20:00","4:20","4 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","B","","","1.,3.,4.,6 jen TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Brodek u Přerova","Dluhonice výhybna",2022,2022,10,13,"2022-03-13T22:50:00","22:50","2022-03-30T04:20:00","4:20","4 x 6 hours","Periodical","Miscellaneous","","LT","","","D","","","B","","","1. jen TV. ","","","2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Vejprnice","Nýřany",2022,2022,12,12,"2022-03-23T08:00:00","8:00","2022-03-25T14:00:00","14:00","3 x 6 hours","Periodical","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","",2022,2022,12,16,"2022-03-25T04:05:00","4:05","2022-04-22T17:30:00","17:30","28 days + 14 hours","Continuous","Miscellaneous","","ST","","","","","","B","","","záhlaví tatské od návěstidla 1L po návěstidlo Se3","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Poříčany","Odb Tatce",2022,2022,12,16,"2022-03-25T04:05:00","4:05","2022-04-22T17:30:00","17:30","28 days + 14 hours","Continuous","Miscellaneous","","LT","","","","","","B","","","1. + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Prosenice",2022,2022,11,12,"2022-03-19T22:40:00","22:40","2022-03-21T04:20:00","4:20","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2S + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Prosenice","Dluhonice výhybna",2022,2022,11,12,"2022-03-19T22:40:00","22:40","2022-03-21T04:20:00","4:20","2 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","1S + TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,12,13,"2022-03-27T23:25:00","23:25","2022-03-30T00:40:00","0:40","3 x 2 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Dluhonice výhybna","Brodek u Přerova",2022,2022,11,13,"2022-03-14T01:40:00","1:40","2022-03-30T03:40:00","3:40","4 x 2 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2. bez TV. ","","","2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Úvaly",2024,2024,32,33,"2024-08-10",null,"2024-08-13T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Nýřany","Heřmanova Huť",2024,2024,9,40,"2024-03-01",null,"2024-09-30T23:59:59.997",null,"214 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. \nzáhlaví stanice Nýřany",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Poříčany",2024,2024,31,31,"2024-07-29",null,"2024-08-01T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Běchovice","Úvaly",2024,2024,29,30,"2024-07-21",null,"2024-07-24T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Nýřany","",2024,2024,27,48,"2024-07-04",null,"2024-11-27T23:59:59.997",null,"147 days","Continuous","Miscellaneous","","ST","","","","","","B","","","1,2,3,4,6,8,10 bez TV. \nzáhlaví domažlické",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Poříčany",2024,2024,28,29,"2024-07-13",null,"2024-07-16T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Běchovice","Úvaly",2024,2024,32,32,"2024-08-05",null,"2024-08-08T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Libeň","Praha-Běchovice",2024,2024,27,27,"2024-07-01",null,"2024-07-04T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Plzeň hl.n.Nová Hospoda","Nýřany",2024,2024,9,27,"2024-02-28",null,"2024-07-03T23:59:59.997",null,"127 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Svojšín","",2024,2024,17,20,"2024-04-24",null,"2024-05-13T23:59:59.997",null,"20 days","Continuous","Track & Rail","","ST","","","","","","B","","","záhlaví směr Bor (od BL k Se3)",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Holýšov","",2024,2024,27,30,"2024-07-04",null,"2024-07-22T23:59:59.997",null,"19 days","Continuous","Track & Rail","","ST","","","","","","B","","","celá bez TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Nýřany","Heřmanova Huť",2024,2024,31,35,"2024-08-01",null,"2024-08-30T23:59:59.997",null,"30 days","Continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Horní Lideč","Horní Lideč st.hr.",2024,2024,14,28,"2024-04-01",null,"2024-07-09T23:59:59.997",null,"100 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Studénka","",2024,2024,47,48,"2024-11-18T18:00:00",null,"2024-11-25T06:00:00",null,"7 x 6 hours","Periodical","Bridge","","ST","","","D","","","","","","lichá jen TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Studénka","",2024,2024,11,12,"2024-03-17T18:00:00",null,"2024-03-24T06:00:00",null,"7 x 6 hours","Periodical","Bridge","","ST","","","D","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,16,17,"2024-04-17",null,"2024-04-24T23:59:59.997",null,"8 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Odra odb.","Ostrava-Vítkovice",2024,2024,41,46,"2024-10-11",null,"2024-11-15T23:59:59.997",null,"36 days","Continuous","Others","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,48,51,"2024-11-30",null,"2024-12-21T23:59:59.997",null,"22 days","Continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Ostrava-Vítkovice","Odra odb.",2024,2024,35,41,"2024-09-01",null,"2024-10-10T23:59:59.997",null,"40 days","Continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2024,2024,18,19,"2024-05-04",null,"2024-05-09T23:59:59.997",null,"6 days","Continuous","Track & Rail","T","LT","","","","","","B","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2024,2024,14,15,"2024-04-05",null,"2024-04-11T23:59:59.997",null,"7 days","Continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Kostěnice",2024,2024,22,22,"2024-05-27T18:00:00",null,"2024-05-29T06:00:00",null,"2 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2024,2024,21,21,"2024-05-25",null,"2024-05-25T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 1. TK směr Přelouč po výh. 81.",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2024,2024,22,22,"2024-05-29T18:00:00",null,"2024-05-31T06:00:00",null,"2 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice hlavní nádraží",2024,2024,17,18,"2024-04-24",null,"2024-05-03T23:59:59.997",null,"10 days","Continuous","Track & Rail","","LT","","","","","","","","","91 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,18,19,"2024-04-30T18:00:00",null,"2024-05-07T06:00:00",null,"7 x 3 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1 bez TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Přelouč nákladní nádraží",2024,2024,1,44,"2024-01-01",null,"2024-10-30T23:59:59.997",null,"304 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami.",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,5,7,"2024-02-01",null,"2024-02-12T23:59:59.997",null,"12 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,20,20,"2024-05-19",null,"2024-05-19T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,23,23,"2024-06-08",null,"2024-06-08T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,38,38,"2024-09-19",null,"2024-09-19T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,44,44,"2024-10-28",null,"2024-10-29T23:59:59.997",null,"2 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2024,2024,33,38,"2024-08-18",null,"2024-09-18T23:59:59.997",null,"32 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,41,41,"2024-10-07T18:00:00",null,"2024-10-08T06:00:00",null,"1 x 4 hours","Periodical","Signal","T","LT","","","","","","","","","zab. zař. SZZ, TZZ, PZZ.",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,23,24,"2024-06-07",null,"2024-06-14T23:59:59.997",null,"8 days","Continuous","Bridge","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,30,31,"2024-07-28",null,"2024-07-29T23:59:59.997",null,"2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,22,23,"2024-06-01T18:00:00",null,"2024-06-03T06:00:00",null,"2 x 4 hours","Periodical","Catenary","T","LT","","","","","","","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,22,22,"2024-05-28",null,"2024-05-29T23:59:59.997",null,"2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,17,18,"2024-04-24",null,"2024-04-30T23:59:59.997",null,"7 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Polom",2024,2024,13,13,"2024-03-25",null,"2024-03-26T23:59:59.997",null,"2 days","Continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ.",null,null,"2021-12-23"]
[null,56,"Žilina - Košice",">","Žilina","Varín",2022,2022,35,50,"2022-08-30",null,"2022-12-15",null,"107 days","continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Rekonštrukcia 1 TK a v.č.3, 4, 9, 10.",null,"Y"]
[null,56,"Žilina - Košice","< >","Žilina","Žilina",2021,2023,25,31,"2021-06-21",null,"2023-07-31",null,"754 days","continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"Demontáž psk, rekonštrukcia mostu km 250, 586, budovanie podchodov. 2K, č. 12-48.",null,"Y"]
[null,56,"Hranice na Moravě - Žilina","< >","Dolný Hričov","Dolný Hričov",2022,2022,41,41,null,null,null,null,"6 days","periodical","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"OGPK, OGPV, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Kysucké Nové Mesto","Krásno nad Kysucou",2022,2022,39,39,null,null,null,null,"6 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"OGPK, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Krásno nad Kysucou","Čadca",2022,2022,17,22,null,null,null,null,"30 days","continuous","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia v km 276,050 - 274,950, TK 1.",null,"N"]
[null,56,"Hranice na Moravě - Žilina","< >","Púchov","Lúky pod Makytou št. hr.",2022,2022,17,26,null,null,null,null,"60 days","continuous","Catenary",null,"LT+ST","S",null,null,null,null,null,null,null,"KRTV",null,"N"]
[null,56,"Žilina - Košice","< >","Ružomberok",null,2022,2022,27,30,"2022-07-04",null,"2022-07-25",null,"11 days","periodical","Switch",null,"ST","S",null,null,null,null,null,null,null,"KRŽZ užitý mat., výh. č. 36 - 41.",null,"N"]
[null,56,"Žilina - Košice","< >","Ružomberok",null,2022,2022,40,43,"2022-10-03",null,"2022-10-28",null,"15 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"KRŽZ užitý mat., koľ. č. 4 a 6.",null,"N"]
[null,56,"Žilina - Košice","< >","Vrútky nákl. st.",null,2022,2022,28,28,"2022-07-12",null,"2022-07-14",null,"3 days","periodical","Switch",null,"ST","S",null,null,null,null,null,null,null,"OKLV 26,27,29.",null,"N"]
[null,56,"Žilina - Košice","< >","Vrútky",null,2022,2022,18,19,"2022-05-02",null,"2022-05-13",null,"10 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"SVP k.č.2.",null,"N"]
[null,56,"Žilina - Košice","< >","Vrútky","Varín",2022,2022,39,39,"2022-09-26",null,"2022-09-30",null,"5 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"SVK k. č. 1,2",null,"N"]
[null,56,"Žilina - Košice","< >","Varín",null,2022,2022,17,50,"2022-04-29",null,"2022-12-15",null,"231 days","continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"NSK, rekonštrukcia k.č.1, 3 a výhybiek",null,"Y"]
[null,56,"Košice - Čierna nad Tisou","<","Ruskov","Nižná Myšľa",2022,2022,38,39,"2022-09-19",null,"2022-09-28",null,"9 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 1, výmena podvalov a koľajnic .",null,"N"]
[null,56,"Košice - Čierna nad Tisou",">","Ruskov","Nižná Myšľa",2022,2022,32,33,"2022-08-08",null,"2022-08-12",null,"11 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, prava koľajového lôžka koľaje.",null,"N"]
[null,56,"Košice - Čierna nad Tisou","<","Nižná Myšľa","Krásna nad Hornádom",2022,2022,40,41,"2022-10-03",null,"2022-10-14",null,"11 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, OGPK + SVK Km 85,500 - 89,500.",null,"N"]
[null,56,"Žilina - Košice",">","Malá Lodina","Margecany",2022,2022,31,33,"2022-08-01",null,"2022-08-15",null,"15 days","periodical","Others",null,"LT","S",null,null,null,null,null,null,null,"TK 1, Oprava nástupišťa zástavka Margecany km 131,070 - 131,250",null,"N"]
[null,56,"Žilina - Košice","< >","Margecany",null,2022,2022,40,41,"2022-10-03",null,"2022-10-14",null,"11 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"Koľ. č. 2., výmena podvalov koľ.č. 2 km 131,350-131,787 / 133,100-133,470.",null,"N"]
[null,56,"Žilina - Košice","< >","Markušovce","Spišské Vlachy",2022,2022,13,13,"2022-03-28",null,"2022-04-03",null,"8 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, VP.",null,"N"]
[null,56,"Žilina - Košice",">","Svit","Štrba",2022,2022,9,12,"2022-03-01",null,"2022-03-21",null,"21 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Modernizácia, TK 1.",null,"Y"]
[null,56,"Žilina - Košice",">","Svit","Štrba",2022,2022,10,12,"2022-03-07",null,"2022-03-21",null,"14 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 1, OKLK.",null,"Y"]
[null,56,"Žilina - Košice","<","Svit","Štrba",2022,2022,12,15,"2022-03-22",null,"2022-04-15",null,"25 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Modernizácia, TK 2.",null,"Y"]
[null,56,"Žilina - Košice","<","Svit","Výh. Lučivná",2022,2022,15,18,"2022-04-15",null,"2022-05-04",null,"20 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Modernizácia, TK 2.",null,"Y"]
[null,56,"Žilina - Košice","<","Svit","Štrba",2022,2022,13,15,"2022-04-01",null,"2022-04-15",null,"13 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, OKLK.",null,"Y"]
[null,56,"Haniska pri Košic. - Maťovce","< >","Vojany","Drahňov",2022,2022,17,18,null,null,null,null,"10 days","continuous","Bridge",null,"LT","S",null,null,null,null,null,null,null,"Výmena mostníc MO km 27,020.",null,"N"]
[null,43,"Sopron - Győr","< >","Sopron","Csorna",2022,2022,18,18,"2022-04-25","08:10:00","2022-04-29","16:40:00",4.354166666666667,"Day","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Csorna","Győr",2022,2022,20,22,"2022-05-15","07:45:00","2022-05-23","18:00:00",8.4270833333333339,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Sopron","Csorna",2022,2022,29,30,"2022-07-12","08:10:00","2022-07-22","17:40:00",10.395833333333332,"continuous","Track & Rail","T"]
[null,43,"Wien - Ebenfurth - Sopron","< >","Baumgarten","Sopron",2022,2022,32,35,"2022-08-13","07:00:00","2022-09-03","23:30:00",21.6875,"continuous","Track & Rail","T"]
[null,43,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2023,2023,20,20,"2023-05-08","08:30:00","2023-05-14","18:30:00",6.4166666666666661,"continuous","Track & Rail","T"]
[null,43,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2023,2023,20,23,"2023-05-08","08:30","2023-05-31","18:30",23.416666666666664,"continuous","Catenary","T"]
[null,43,"Sopron - Győr","< >","Csorna","Győr",2023,2023,38,40,"2023-09-17","06:40","2023-09-30","20:30",13.576388888888888,"continuous","Maintenance","T"]
[null,43,"Sopron - Győr","< >","Fertőendréd","Kapuvár",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Kapuvár","Rábatamási",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Sopron","Fertőszentmiklós",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Pinnye","Fertőszentmiklós",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Catenary","T"]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,12,12,"2022-03-21","22:00:00","2022-03-22","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44113]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,12,12,"2022-03-22","22:00:00","2022-03-23","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,12,12,"2022-03-23","22:00:00","2022-03-24","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Hegyeshalom - Györ",">","Mosonmagyaróvár","Hegyeshalom",2022,2022,13,14,"2022-04-01","22:00:00","2022-04-04","07:00:00",2.375,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,17,17,"2022-04-25","22:00:00","2022-04-26","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,17,17,"2022-04-26","22:00:00","2022-04-27","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,17,17,"2022-04-27","22:00:00","2022-04-28","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,17,17,"2022-04-28","22:00:00","2022-04-29","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,17,17,"2022-04-29","22:00:00","2022-04-30","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,18,18,"2022-05-02","22:00:00","2022-05-03","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Herceghalom","Bicske",2022,2022,18,18,"2022-05-02","21:30:00","2022-05-03","04:50:00",0.30555555555555547,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Herceghalom","Bicske",2022,2022,18,18,"2022-05-03","01:00:00","2022-05-03","03:30:00",0.10416666666666669,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,18,18,"2022-05-03","22:00:00","2022-05-04","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Herceghalom","Bicske",2022,2022,18,18,"2022-05-03","22:00:00","2022-05-04","04:50:00",0.28472222222222221,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Herceghalom","Bicske",2022,2022,18,18,"2022-05-04","01:00:00","2022-05-04","03:30:00",0.10416666666666669,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,18,18,"2022-05-04","22:00:00","2022-05-05","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,18,18,"2022-05-05","22:00:00","2022-05-06","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,18,18,"2022-05-06","22:00:00","2022-05-07","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,19,19,"2022-05-09","22:00:00","2022-05-10","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,19,19,"2022-05-10","22:00:00","2022-05-11","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,19,19,"2022-05-11","22:00:00","2022-05-12","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,19,19,"2022-05-12","22:00:00","2022-05-13","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,19,19,"2022-05-13","22:00:00","2022-05-14","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,20,20,"2022-05-16","22:00:00","2022-05-17","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,20,20,"2022-05-17","22:00:00","2022-05-18","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,20,20,"2022-05-18","22:00:00","2022-05-19","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,20,20,"2022-05-19","22:00:00","2022-05-20","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,20,20,"2022-05-20","22:00:00","2022-05-21","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Herceghalom","Bicske",2022,2022,20,21,"2022-05-22","00:10:00","2022-05-23","04:20:00",1.1736111111111112,"Continuous","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Tatabánya","Tata",2022,2022,21,21,"2022-05-28","00:00:00","2022-05-29","03:50:00",1.1597222222222223,"Continuous","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,24,24,"2022-06-14","22:00:00","2022-06-15","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,24,24,"2022-06-15","22:00:00","2022-06-16","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,24,24,"2022-06-16","22:00:00","2022-06-17","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,26,26,"2022-06-27","22:00:00","2022-06-28","05:30:00",0.31250000000000033,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,26,26,"2022-06-28","22:00:00","2022-06-29","05:30:00",0.31250000000000033,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,27,30,"2022-07-11","05:30:00","2022-08-03","05:30:00",23,"Continuous","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,27,27,"2022-07-12","00:30:00","2022-07-12","04:30:00",0.16666666666666666,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,27,27,"2022-07-13","00:30:00","2022-07-13","04:30:00",0.16666666666666666,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,30,30,"2022-08-03","05:30:00","2022-08-03","21:30:00",0.66666666666666663,"Continuous","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,30,33,"2022-08-03","21:30:00","2022-08-19","05:30:00",15.333333333333334,"Continuous","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-01","22:00:00","2022-09-02","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-02","22:00:00","2022-09-03","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-03","22:00:00","2022-09-04","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Budapest-Kelenföld","Budaörs",2022,2022,36,36,"2022-09-09","22:00:00","2022-09-12","05:00:00",2.2916666666666665,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Budapest-Kelenföld","Budaörs",2022,2022,37,37,"2022-09-16","22:00:00","2022-09-19","05:00:00",2.2916666666666665,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Komárom","Ács",2022,2022,40,41,"2022-10-07","22:00:00","2022-10-10","04:00:00",2.25,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Vecsés",2022,2022,24,25,"2022-06-17","23:00:00","2022-06-20","04:00:00",{"$f":"M3615-K3615+N3615-L3615","v":2.208333333333333},"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,24,"2022-06-17","23:50:00","2022-06-18","03:40:00",{"$f":"M3616-K3616+N3616-L3616","v":0.15972222222222221},"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,24,"2022-06-18","23:50:00","2022-06-19","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,25,"2022-06-19","23:50:00","2022-06-20","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Vecsés","Üllő",2022,2022,25,25,"2022-06-20","04:00:00","2022-06-24","23:00:00",4.7916666666666661,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-20","23:50:00","2022-06-21","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-21","23:50:00","2022-06-22","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-22","23:50:00","2022-06-23","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-23","23:50:00","2022-06-24","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,25,26,"2022-06-24","23:00:00","2022-06-27","04:00:00",2.208333333333333,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-24","23:50:00","2022-06-25","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-25","23:50:00","2022-06-26","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,26,"2022-06-26","23:50:00","2022-06-27","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Vecsés","Üllő",2022,2022,26,26,"2022-06-27","04:00:00","2022-06-29","03:40:00",1.9861111111111109,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-27","23:50:00","2022-06-28","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-28","23:50:00","2022-06-29","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Vecsés","Üllő",2022,2022,26,26,"2022-06-29","03:40:00","2022-07-01","23:00:00",2.8055555555555558,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-29","23:50:00","2022-06-30","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-30","23:50:00","2022-07-01","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,26,27,"2022-07-01","23:00:00","2022-07-04","04:00:00",2.208333333333333,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-07-01","23:50:00","2022-07-02","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-07-02","23:50:00","2022-07-03","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,27,"2022-07-03","23:50:00","2022-07-04","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Vecsés","Üllő",2022,2022,27,27,"2022-07-04","03:40:00","2022-07-08","23:00:00",4.8055555555555554,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-04","23:50:00","2022-07-05","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-05","23:50:00","2022-07-06","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-06","23:50:00","2022-07-07","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-07","23:50:00","2022-07-08","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,27,28,"2022-07-08","23:00:00","2022-07-11","23:00:00",3,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-08","23:50:00","2022-07-09","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-09","23:50:00","2022-07-10","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,28,"2022-07-10","23:50:00","2022-07-11","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Szolnok - Cluj","< >","Sáp","Biharkeresztes",2022,2022,24,44,"2022-06-18","00:00:00","2022-11-06","23:59:00",141.99930555555557,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Rákos","Rákoshegy",2022,2022,1,1,"2022-01-08","07:00:00","2022-01-08","15:00:00",0.33333333333333331,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Rákos","Rákoshegy",2022,2022,1,1,"2022-01-09","07:00:00","2022-01-09","15:00:00",0.33333333333333331,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Rákoshegy","Maglód",2022,2022,2,2,"2022-01-15","08:05:00","2022-01-15","15:20:00",0.30208333333333337,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Rákoshegy","Maglód",2022,2022,2,2,"2022-01-16","08:05:00","2022-01-16","15:20:00",0.30208333333333337,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Maglód","Gyömrő",2022,2022,3,3,"2022-01-22","08:00:00","2022-01-22","15:00:00",0.29166666666666669,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Maglód","Gyömrő",2022,2022,3,3,"2022-01-23","08:00:00","2022-01-23","15:00:00",0.29166666666666669,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Tápiószecső","Nagykáta",2022,2022,4,4,"2022-01-29","08:00:00","2022-01-29","15:40:00",0.31944444444444448,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Tápiószecső","Nagykáta",2022,2022,4,4,"2022-01-30","08:00:00","2022-01-30","15:40:00",0.31944444444444448,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Újszász","Szolnok",2022,2022,5,5,"2022-02-05","07:35:00","2022-02-05","15:20:00",0.32291666666666669,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Újszász","Szolnok",2022,2022,5,5,"2022-02-05","07:35:00","2022-02-05","15:20:00",0.32291666666666669,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Újszász","Szolnok",2022,2022,5,5,"2022-02-06","07:35:00","2022-02-06","15:20:00",0.32291666666666669,"Day","Others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok","<","Nagykáta","Tápiószele",2022,2022,28,29,"2022-07-11","00:00:00","2022-07-24","23:59:00",{"$f":"M3659-K3659+N3659-L3659","v":13.999305555555555},"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,null,null,43910]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,5,"2022-02-01","23:20:00","2022-02-02","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,5,"2022-02-02","23:20:00","2022-02-03","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,5,"2022-02-03","23:20:00","2022-02-04","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,5,"2022-02-04","23:20:00","2022-02-05","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,5,"2022-02-05","23:20:00","2022-02-06","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,5,6,"2022-02-06","23:20:00","2022-02-07","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-07","23:20:00","2022-02-08","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-08","23:20:00","2022-02-09","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-09","23:20:00","2022-02-10","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-10","23:20:00","2022-02-11","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-11","23:20:00","2022-02-12","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Budapest - Újszász - Szolnok",">","Gyömrő","Mende",2022,2022,6,6,"2022-02-12","11:00:00","2022-02-12","15:00:00",0.16666666666666666,"Day","others",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,6,"2022-02-12","23:20:00","2022-02-13","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,6,7,"2022-02-13","23:20:00","2022-02-14","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-14","23:20:00","2022-02-15","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-15","23:20:00","2022-02-16","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-16","23:20:00","2022-02-17","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-17","23:20:00","2022-02-18","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-18","23:20:00","2022-02-19","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,7,"2022-02-19","23:20:00","2022-02-20","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,7,8,"2022-02-20","23:20:00","2022-02-21","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-21","23:20:00","2022-02-22","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-22","23:20:00","2022-02-23","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-23","23:20:00","2022-02-24","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-24","23:20:00","2022-02-25","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-25","23:20:00","2022-02-26","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,8,"2022-02-26","23:20:00","2022-02-27","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,8,9,"2022-02-27","23:20:00","2022-02-28","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-02-28","23:20:00","2022-03-01","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-03-01","23:20:00","2022-03-02","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-03-02","23:20:00","2022-03-03","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-03-03","23:20:00","2022-03-04","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-03-04","23:20:00","2022-03-05","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,9,"2022-03-05","23:20:00","2022-03-06","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,9,10,"2022-03-06","23:20:00","2022-03-07","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-07","23:20:00","2022-03-08","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-08","23:20:00","2022-03-09","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-09","23:20:00","2022-03-10","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-10","23:20:00","2022-03-11","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-11","23:20:00","2022-03-12","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,10,"2022-03-12","23:20:00","2022-03-13","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,10,11,"2022-03-13","23:20:00","2022-03-14","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,11,11,"2022-03-16","23:20:00","2022-03-17","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,11,11,"2022-03-17","23:20:00","2022-03-18","03:50:00",0.18750000000000011,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,11,13,"2022-03-18","23:20:00","2022-03-29","03:50:00",10.1875,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Lőkösháza","Lőkösháza Országhatár",2022,2022,11,13,"2022-03-19","04:00:00","2022-03-28","23:30:00",9.8125,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,13,"2022-03-29","23:20:00","2022-03-30","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,13,"2022-03-30","23:20:00","2022-03-31","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,13,"2022-03-31","23:20:00","2022-04-01","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,13,"2022-04-01","23:20:00","2022-04-02","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,13,"2022-04-02","23:20:00","2022-04-03","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,13,14,"2022-04-03","23:20:00","2022-04-04","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-04","23:20:00","2022-04-05","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-05","23:20:00","2022-04-06","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-06","23:20:00","2022-04-07","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-07","23:20:00","2022-04-08","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-08","23:20:00","2022-04-09","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,14,"2022-04-09","23:20:00","2022-04-10","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,14,15,"2022-04-10","23:20:00","2022-04-11","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,15,15,"2022-04-11","23:20:00","2022-04-12","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,15,15,"2022-04-12","23:20:00","2022-04-13","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,15,15,"2022-04-13","23:20:00","2022-04-14","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,16,17,"2022-04-19","23:20:00","2022-04-30","03:50:00",10.1875,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-02","23:20:00","2022-05-03","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-03","23:20:00","2022-05-04","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-04","23:20:00","2022-05-05","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-05","23:20:00","2022-05-06","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-06","23:20:00","2022-05-07","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,18,"2022-05-07","23:20:00","2022-05-08","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,18,19,"2022-05-08","23:20:00","2022-05-09","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-09","23:20:00","2022-05-10","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-10","23:20:00","2022-05-11","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-11","23:20:00","2022-05-12","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-12","23:20:00","2022-05-13","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-13","23:20:00","2022-05-14","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,19,"2022-05-14","23:20:00","2022-05-15","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,19,20,"2022-05-15","23:20:00","2022-05-16","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-16","23:20:00","2022-05-17","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-17","23:20:00","2022-05-18","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-18","23:20:00","2022-05-19","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-19","23:20:00","2022-05-20","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-20","23:20:00","2022-05-21","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,20,"2022-05-21","23:20:00","2022-05-22","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,20,21,"2022-05-22","23:20:00","2022-05-23","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-23","23:20:00","2022-05-24","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-24","23:20:00","2022-05-25","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-25","23:20:00","2022-05-26","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-26","23:20:00","2022-05-27","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-27","23:20:00","2022-05-28","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,21,"2022-05-28","23:20:00","2022-05-29","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,21,22,"2022-05-29","23:20:00","2022-05-30","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,22,22,"2022-05-30","23:20:00","2022-05-31","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,22,22,"2022-05-31","23:20:00","2022-06-01","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,22,22,"2022-06-01","23:20:00","2022-06-02","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,22,22,"2022-06-02","23:20:00","2022-06-03","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,22,22,"2022-06-03","23:20:00","2022-06-04","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,23,"2022-06-07","23:20:00","2022-06-08","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,23,"2022-06-08","23:20:00","2022-06-09","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,23,"2022-06-09","23:20:00","2022-06-10","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,23,"2022-06-10","23:20:00","2022-06-11","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,23,"2022-06-11","23:20:00","2022-06-12","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,23,24,"2022-06-12","23:20:00","2022-06-13","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,24,24,"2022-06-13","23:20:00","2022-06-14","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,24,24,"2022-06-14","23:20:00","2022-06-15","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,24,24,"2022-06-15","23:20:00","2022-06-16","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,55,"Szolnok - Arad","< >","Békéscsaba","Lőkösháza",2022,2022,24,24,"2022-06-16","23:20:00","2022-06-17","03:50:00",0.18750000000000011,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,53,"Arad - Simeria","< >","Barzava","Milova",2022,2022,null,null,"2022-06-08","00:00:00","2022-06-14","00:00:00",6,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Arad - Simeria","< >","Barzava","Milova",2022,2023,null,null,"2022-06-14","00:00:00","2023-03-08","00:00:00",267,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Barzava ","Conop",2017,2022,null,null,"2017-09-25","00:00:00","2022-06-14","00:00:00",1723,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Conop","Milova",2019,2022,null,null,"2019-03-01","00:00:00","2022-06-14","00:00:00",1201,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Milova","Radna",2018,2023,null,null,"2018-03-06","00:00:00","2023-03-08","00:00:00",1828,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Radna","Paulis",2022,2023,null,null,"2022-06-14","00:00:00","2023-03-08","00:00:00",267,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Ilteu","Savarsin",2021,2022,null,null,"2021-04-21","00:00:00","2022-06-10","00:00:00",415,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Savarsin","Barzava Noua",2021,2023,null,null,"2021-08-19","00:00:00","2023-02-20","00:00:00",550,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Gurasada "," Campuri Surduc",2020,2022,null,null,"2020-04-03","00:00:00","2022-12-20","00:00:00",991,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Campuri Surduc"," Zam",2020,2022,null,null,"2020-03-11","00:00:00","2022-04-29","00:00:00",779,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Campuri Surduc"," Zam",2022,2022,null,null,"2022-12-15","00:00:00","2022-12-20","00:00:00",5,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Arad - Simeria","< >","Zam ","Ilteu",2022,2022,null,null,"2022-04-22","00:00:00","2022-04-29","00:00:00",7,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Vanatori ","Cristur",2023,2023,null,null,"05.10.2023","00:00:00","2023-10-16","00:00:00",11,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Cata","Rupea",2022,2025,null,null,"01.06.2022","00:00:00","21.03.2025","00:00:00",1024,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Beia","Mureni",2023,2025,null,null,"12.05.2023","00:00:00","21.03.2025","00:00:00",679,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Mureni","Vanatori",2022,2025,null,null,"01.05.2022","00:00:00","21.03.2025","00:00:00",1055,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Vanatori","Albesti",2021,2024,null,null,"19.04.2021","00:00:00","01.10.2024","00:00:00",1261,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >"," Albesti Station ",null,2022,2022,null,null,"01.05.2022","00:00:00","2022-06-01","00:00:00",31,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Albesti","Sighisoara",2021,2023,null,null,"19.04.2021","00:00:00","10.02.2023","00:00:00",662,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Apata","Augustin",2021,2023,null,null,"2021-04-15","00:00:00","2023-08-11","00:00:00",848,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Augustin","Rupea",2022,2024,null,null,"2022-03-01","00:00:00","2024-06-25","00:00:00",847,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Rupea","Cata",2022,2023,null,null,"2022-11-16","00:00:00","2023-10-09","00:00:00",327,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Brasov","Stupini",2020,2022,null,null,"01.09.2020","00:00:00","25.07.2022","00:00:00",692,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Brasov","Stupini",2024,2025,null,null,"28.08.2024","00:00:00","06.03.2025","00:00:00",190,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2020,2023,null,null,"26.08.2020","00:00:00","17.08.2023","00:00:00",1086,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2022,2022,null,null,"2022-03-05","00:00:00","2022-03-09","00:00:00",4,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2022,2022,null,null,"22.07.2022","00:00:00","2022-07-26","00:00:00",4,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2023,2023,null,null,"15.05.2023","00:00:00","2023-06-15","00:00:00",31,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2022,2025,null,null,"26.05.2022","00:00:00","06.03.2025","00:00:00",1015,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2022,2022,null,null,"22.07.2022","00:00:00","2022-07-26","00:00:00",4,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2022,2022,null,null,"22.09.2022","00:00:00","2022-09-25","00:00:00",3,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2023,2023,null,null,"15.05.2023","00:00:00","2023-06-15","00:00:00",31,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Feldioara","Apata",2022,2025,null,null,"25.04.2022","00:00:00","06.03.2025","00:00:00",1046,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Feldioara","Apata",2024,2024,null,null,"15.07.2024","00:00:00","2024-07-19","00:00:00",4,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Biharkeresztes - Coslariu","< >","Valea Florilor","Boju",2022,2022,null,null,"2022-06-01","00:00:00","2022-12-31","00:00:00",213,"Continuous","Track & Rail",null,"LT","S",null,"x",null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Biharkeresztes - Coslariu","< >","Cluj Napoca","Episcopia Bihor",2022,2025,null,null,"2022-07-01","00:00:00","2025-12-31","00:00:00",1279,"Continuous","Track & Rail"]

{"sheet":"Graphic Overview","index":2,"n_rows":1063,"n_cols":375,"rows_kept":1063,"cut":false,"hidden":false,"merged":[[3,362,3,368],[3,369,3,373],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,341,3,347],[3,348,3,354],[3,355,3,361],[3,278,3,284],[3,285,3,291],[3,292,3,298],[3,299,3,305],[3,306,3,312],[3,313,3,319],[3,236,3,242],[3,243,3,249],[3,250,3,256],[3,257,3,263],[3,264,3,270],[3,271,3,277],[3,194,3,200],[3,201,3,207],[3,208,3,214],[3,215,3,221],[3,222,3,228],[3,229,3,235],[3,152,3,158],[3,159,3,165],[3,166,3,172],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,110,3,116],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,138,3,144],[3,145,3,151],[3,68,3,74],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,103,3,109],[2,343,2,373],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,33,3,39],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,282,2,312],[2,313,2,342],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128],[2,129,2,159]]}
[null,"Rhine-Danube, Overview"]
[]
[null,null,null,null,null,null,2021,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-12-12","2022-07-29T18:00:00","229 d, 18 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-09-26T22:00:00","2021-09-27T05:00:00","7 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-09-30T08:00:00","2021-10-05T08:59:00","5 d, 01 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-05T05:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Partenstein - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Nantenbach - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Nantenbach - Partenstein",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Weinheim (Bergstr) - Weinheim (Bergstr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-01T01:00:00","2021-02-05T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-08T05:00:00","2021-02-12T21:00:00","4 d, 16 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-15T01:00:00","2021-02-19T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Neu-Edingen/Mhm-Friedrichsfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-05-27","2021-06-18T23:59:00","23 d","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Heidelberg-Wieblingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-06-04T21:00:00","2021-06-08T04:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Nord - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-01-15T23:30:00","2021-01-18T01:30:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-13T00:30:00","2021-02-15T13:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-15T13:00:00","2021-11-09T23:45:00","267 d, 11 h","DB Netz AG"]
[]
[null,"Dieburg - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-22T09:00:00","2021-11-15T23:59:00","10 d, 15 h","DB Netz AG"]
[]
[null,"Dieburg - Messel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Messel - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt-Kranichstein - Babenhausen (Hess)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-24T23:30:00","2021-11-07T05:30:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-01T08:00:00","2021-11-16T06:00:00","14 d, 22 h","DB Netz AG"]
[]
[null,"Mainaschaff Abzw - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T21:00:00","2021-11-16T05:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T22:00:00","2021-11-16T06:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T23:45:00","2021-11-17T04:45:00","7 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-15T06:00:00","2021-11-30T06:00:00","15 d","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-22T05:00:00","2021-11-26T22:00:00","4 d, 17 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Stuttgart Hbf - Stuttgart-Zuffenhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Ebersbach (Fils) - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-25T22:00:00","2021-01-26T04:30:00","7 h","DB Netz AG"]
[]
[null,"Stuttgart-Bad Cannstatt - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-04T21:00:00","2021-02-08T05:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Geislingen (Steige) - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-09T21:00:00","2021-02-12T05:00:00","1 d","DB Netz AG"]
[]
[null,"Ulm Hbf - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-02-28T23:30:00","2021-03-02T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-02T23:30:00","2021-03-14T04:30:00","11 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm-Örlingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-14T23:00:00","2021-03-25T04:30:00","10 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-15T22:00:00","2021-03-22T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Ulm-Örlingen - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-25T23:30:00","2021-03-27T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19","2021-08-09T04:00:00","21 d, 04 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-02T01:00:00","2021-08-13T22:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Ulm Hbf Em Nord - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T20:00:00","2021-08-16T04:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Amstetten (Württ) - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-16T22:00:00","3 d","DB Netz AG"]
[]
[null,"Göppingen - Eislingen (Fils)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-27T04:00:00","13 d, 06 h","DB Netz AG"]
[]
[null,"Geislingen West - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Uhingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-26T22:00:00","2021-08-27T04:00:00","6 h","DB Netz AG"]
[]
[null,"Eislingen (Fils) - Gingen (Fils) Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-27T22:00:00","2021-09-03T22:00:00","7 d","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-29T22:30:00","2021-02-02T05:15:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:00:00","2021-04-24T05:20:00","14 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:20:00","2021-04-12T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:00:00","2021-05-10T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:30:00","2021-05-10T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-14T22:30:00","2021-05-17T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-07","2021-08-09T04:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Burgau (Schwab)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Unterfahlheim - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Nersingen - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-29","2021-12-04T05:00:00","5 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Mannheim Hbf Ost - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-02-06T02:35:00","2021-02-08T04:35:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Mannheim-Rheinau - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-06-20T22:00:00","2021-08-03T04:00:00","43 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-07-28T22:00:00","2021-08-03T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-08-03T04:00:00","2021-09-13T04:00:00","41 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-07T21:00:00","2021-08-23T05:00:00","2 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-09T23:00:00","2021-08-21T05:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Schwetzingen - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Oftersheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-08T22:00:00","2021-09-16T06:00:00","7 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Waghäusel - Waghäusel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Graben-Neudorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-03-08","2021-03-23T23:59:00","16 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Forchheim (b Karlsruhe) - Durmersheim Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-05-13T00:01:00","2021-05-17T04:30:00","4 d, 04 h","DB Netz AG"]
[]
[null,"Karlsruhe Hbf Bft Südeinfahrt - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-07-19T23:00:00","2021-08-07T05:00:00","3 d, 18 h","DB Netz AG"]
[]
[null,"Durmersheim Nord - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-20T23:00:00","2021-08-23T05:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bashaide - Karlsruhe Hbf Bft Südeinfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-30T23:00:00","2021-11-08T04:30:00","69 d, 05 h","DB Netz AG"]
[]
[null,"Durmersheim - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-03T22:00:00","2021-10-29T05:00:00","25 d, 07 h","DB Netz AG"]
[]
[null,"Durmersheim - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-29T23:00:00","2021-11-02T04:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Pforzheim Hbf - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Vaihingen (Enz) - Vaihingen (Enz)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-03-18","2021-05-03T23:59:00","47 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-07","2021-05-11T23:59:00","5 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-08T02:00:00","2021-05-10T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Sachsenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Sachsenheim - Tamm (Württ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-03-02T22:00:00","2021-03-06T04:30:00","1 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Karlshöhe - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-22T01:45:00","2021-06-07T04:00:00","16 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Pbf - Kornwestheim Karlshöhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-07T08:00:00","2021-09-07T16:00:00","8 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-10-23T01:45:00","2021-10-25T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-06T23:00:00","2021-12-11T23:59:00","308 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-22T08:00:00","2021-12-11T23:59:00","292 d, 16 h","DB Netz AG"]
[]
[null,"Appenweier-Muhrhaag - Appenweier Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-12T23:35:00","2021-03-15T04:15:00","2 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-29T00:15:00","2021-04-02T00:15:00","4 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T00:15:00","2021-04-06T03:00:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-08-30","149 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-05-24T23:00:00","2021-07-01T04:30:00","37 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-08-30","2021-11-08T04:30:00","70 d, 04 h","DB Netz AG"]
[]
[null,"Appenweier Nord - Appenweier Kurve",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-03-27T00:30:00","2021-03-29T04:30:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-04-23T07:00:00","2021-05-05T17:00:00","12 d, 10 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-04T00:45:00","2021-07-04T06:45:00","6 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-09T23:00:00","2021-07-17T05:00:00","7 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-10T22:00:00","2021-07-11T06:45:00","9 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-07-11T22:00:00","2021-07-14T04:40:00","20 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-25T00:45:00","2021-07-25T06:45:00","6 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-09-27T07:00:00","2021-10-25T18:00:00","28 d, 11 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T07:00:00","2021-10-05T17:00:00","4 d, 10 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-01T22:00:00","2021-10-04T04:50:00","21 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-04T22:00:00","2021-10-12T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-16","2021-10-18T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-20T05:00:00","2021-10-25T05:00:00","5 d","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-20T22:00:00","2021-10-25T05:00:00","21 h","DB Netz AG"]
[]
[null,"München-Lochhausen - München-Pasing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-22T22:00:00","2021-03-27T05:40:00","4 d, 08 h","DB Netz AG"]
[]
[null,"München-Pasing - München-Lochhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-03-22T22:45:00","2021-03-27T05:20:00","1 d, 09 h","DB Netz AG"]
[]
[null,"München-Pasing - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Rosenheim - Rosenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-03-10T00:40:00","2021-03-14T02:40:00","4 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-09T02:00:00","2021-11-23T04:00:00","14 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-23T04:00:00","2021-12-11T23:59:00","18 d, 20 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-05","2021-02-08T04:50:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-12T00:25:00","2021-02-15T05:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-14T19:10:00","2021-02-15T04:10:00","9 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical continuous","2021-02-21T00:25:00","2021-03-01T04:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-06T22:20:00","2021-03-07T05:20:00","7 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-07T22:00:00","2021-03-08T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-11T21:40:00","2021-03-12T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-13T22:20:00","2021-03-15T04:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-19T16:00:00","2021-03-21T16:00:00","2 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-03-20T22:20:00","2021-03-21T05:10:00","7 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-04-01T23:30:00","2021-04-06T06:00:00","4 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-04-09T23:30:00","2021-05-17T06:00:00","13 d, 15 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-21T23:30:00","2021-05-25T06:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Postbauer-Heng - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-05-27T01:00:00","2021-06-21T05:00:00","25 d, 04 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-05T21:00:00","2021-06-26T05:00:00","20 d, 08 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-07T21:00:00","2021-06-19T04:00:00","2 d, 22 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Postbauer-Heng",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical","2021-06-07T22:00:00","2021-06-10T05:00:00","21 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-12T20:30:00","2021-06-20T04:30:00","1 d","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-06-19","2021-07-04T23:50:00","16 d","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-26T23:30:00","2021-06-28T06:00:00","1 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-07-02T23:30:00","2021-08-02T06:00:00","11 d, 09 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-07-29T23:00:00","2021-08-02T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-08-02T23:00:00","2021-08-06T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Ost",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-06T00:30:00","2021-11-11T00:30:00","5 d","DB Netz AG"]
[]
[null,"Sünching - Mangolding",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-07T01:30:00","2021-11-11T00:30:00","3 d, 23 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-05T09:00:00","2021-03-07T12:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-12T09:00:00","2021-03-15T12:00:00","3 d, 03 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T01:00:00","2021-05-02T05:00:00","6 d, 04 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T04:00:00","2021-05-02T02:00:00","5 d, 22 h","DB Netz AG"]
[]
[null,"Köfering - Eggmühl",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-28T01:00:00","2021-05-29T13:00:00","1 d, 12 h","DB Netz AG"]
[]
[null,"Eggmühl - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-29T13:00:00","2021-05-31T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-04T23:00:00","2021-06-08T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-05T03:00:00","2021-06-05T17:00:00","14 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-10T23:00:00","2021-06-14T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-11T03:00:00","2021-06-11T17:00:00","14 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-16T14:00:00","2021-06-18T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-18T22:00:00","2021-06-21T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-23T14:00:00","2021-06-25T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-25T22:00:00","2021-06-28T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-07-04T01:00:00","2021-07-04T11:00:00","10 h","DB Netz AG"]
[]
[null,"München Kanal - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Köfering - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-09-19T01:00:00","2021-10-03T05:00:00","14 d, 04 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T22:00:00","2021-10-23T05:00:00","11 d, 07 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-23T22:00:00","2021-11-01T04:00:00","8 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-11-01T22:00:00","2021-11-07T05:00:00","5 d, 07 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Richtungsgruppe Süd - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-05T14:00:00","2021-04-06T09:00:00","19 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-10T12:00:00","2021-04-12T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-12T15:00:00","2021-04-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-04-17T12:00:00","2021-05-31T15:00:00","14 d, 21 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-04-19T15:00:00","2021-05-04T06:00:00","1 d, 21 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-05-10T15:00:00","2021-06-01T06:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-05T12:00:00","2021-06-14T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-07T15:00:00","2021-06-15T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-19T12:00:00","2021-06-28T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-21T15:00:00","2021-06-29T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-03T12:00:00","2021-07-05T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-05T15:00:00","2021-07-06T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-10T12:00:00","2021-07-19T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-12T15:00:00","2021-07-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19T15:00:00","2021-07-20T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-24T12:00:00","2021-07-26T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-26T15:00:00","2021-07-27T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-31T12:00:00","2021-08-09T15:00:00","2 d, 20 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-31T12:00:00","2021-08-10T06:00:00","5 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-14T12:00:00","2021-09-13T15:00:00","7 d, 02 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-08-14T12:00:00","2021-09-14T06:00:00","13 d, 18 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-07","2021-10-11T22:00:00","4 d, 22 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-11T22:00:00","2021-10-17T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"München-Freimann - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-30T00:30:00","2021-11-03T03:30:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-01-25T22:30:00","2021-05-24T05:00:00","118 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T15:00:00","2021-04-03T20:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T22:30:00","2021-04-05T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-03T20:00:00","2021-04-04T10:00:00","14 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-04T10:00:00","2021-04-05T15:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:00:00","2021-04-10T04:00:00","6 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:30:00","2021-04-12T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-10T04:00:00","2021-04-11T10:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-11T10:00:00","2021-04-12T16:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-16T22:30:00","2021-04-19T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-17T05:00:00","2021-04-17T20:00:00","15 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-05-25T22:30:00","2021-08-13T05:00:00","79 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-02T05:00:00","9 d, 11 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-03T18:00:00","11 d","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:00:00","2021-09-02T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:30:00","2021-09-02T04:00:00","6 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Seligenstadt (b Würzburg)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:45:00","2021-08-30T04:15:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-27T22:30:00","2021-08-30T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Wernfeld - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-16T08:00:00","2021-02-23T16:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Eußenheim - Wernfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-24T08:00:00","2021-03-04T16:00:00","2 d","DB Netz AG"]
[]
[null,"Eußenheim - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-08T08:00:00","2021-03-09T16:00:00","16 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-10T08:00:00","2021-03-16T16:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-17T08:00:00","2021-03-18T16:00:00","16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-22T08:00:00","2021-04-01T16:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-06T08:00:00","2021-04-08T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-12T08:00:00","2021-04-14T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-15T08:00:00","2021-04-19T16:00:00","16 h","DB Netz AG"]
[]
[null,"Waigolshausen - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-20T08:00:00","2021-04-22T16:00:00","1 d","DB Netz AG"]
[]
[null,"Nürnberg Rbf Einfahrt - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-02-22T06:00:00","2021-12-11T23:59:00","292 d, 18 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-13T06:00:00","2021-03-14T04:00:00","22 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-20T06:00:00","2021-03-21T04:00:00","22 h","DB Netz AG"]
[]
[null,"Bamberg - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-27T22:00:00","2021-03-01T05:00:00","14 h","DB Netz AG"]
[]
[null,"Hirschaid - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-28T22:00:00","2021-03-01T05:00:00","7 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Vach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-22T23:00:00","2021-03-26T23:00:00","4 d","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T04:00:00","2021-03-29T04:00:00","3 d","DB Netz AG"]
[]
[null,"Vach - Fürth (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bad Staffelstein - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T21:00:00","2021-03-28T06:00:00","9 h","DB Netz AG"]
[]
[null,"Hirschaid - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T23:00:00","2021-04-01T04:00:00","4 d, 05 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-04T04:00:00","7 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-10-05T22:00:00","2021-12-01T01:00:00","56 d, 03 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-01T01:00:00","2021-12-06T04:00:00","5 d, 03 h","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-05T21:00:00","2021-12-06T04:00:00","7 h","DB Netz AG"]
[]
[null,"Bodenwöhr Nord - Bodenwöhr Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Plzen","continuous","2021-03-23T07:00:00","2021-05-10T07:00:00","48 d","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-10T07:00:00","2021-06-18T21:00:00","39 d, 14 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe-Dammerstock",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-08-30T23:00:00","2021-11-08T05:00:00","69 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-08","2021-09-29T23:59:00","22 d","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-25T06:00:00","2021-09-27T04:00:00","1 d, 22 h","DB Netz AG"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","30.11.2020","10.07.2021","221 days + 22,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Linz - Wien","cont.","20.02.2021","22.02.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","08.03.2021","16.03.2021","8 days + 9,5 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.03.2021","15.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","12 days","ÖBB Infra"]
[]
[null,"Sbl Spw 2 - St.Valentin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","11 days + 12,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","19.03.2021","22.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","22.03.2021","03.04.2021","12 days + 8,5 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","26.03.2021","29.03.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.04.2021","16.04.2021","4 days","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","12.04.2021","21.04.2021","9 days + 9,5 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - Untergaumberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","16.04.2021","03.05.2021","16 days + 6,5 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","21.05.2021","25.05.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","22.05.2021","24.05.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","04.06.2021","07.06.2021","2 days + 5,5 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Lambach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","09.07.2021","12.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Üst Ams 2 - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","7 days + 4,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","6 days + 5,0 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Sbl Gun 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","16.07.2021","19.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","17.07.2021","22.07.2021","5 days","ÖBB Infra"]
[]
[null,"Gunskirchen - Wels Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","23.07.2021","26.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Ybbs a.d.Donau - Abzw Knoten Karlsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","03.08.2021","23.08.2021","20 days","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","17.09.2021","20.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.09.2021","27.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","01.10.2021","04.10.2021","2 days + 19,0 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","15.10.2021","18.10.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","18.10.2021","22.10.2021","4 days + 10,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","23.10.2021","26.10.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","30.10.2021","02.11.2021","3 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","30.10.2021","02.11.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","05.11.2021","08.11.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Seekirchen am Wallersee - Steindorf bei Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","20.11.2021","24.11.2021","4 days","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Seekirchen am Wallersee",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.11.2021","29.11.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Meidling - W.Mat.-Oswaldgasse",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Linz - Wien","cont.","12.12.2021","16.04.2023","491 days","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","26.02.2021","01.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","05.03.2021","08.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.03.2021","15.03.2021","3 days + 16,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.03.2021","22.03.2021","3 days + 17,0 h","ÖBB Infra"]
[]
[null,"Andorf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.05.2021","15.05.2021","7 days + 10,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.10.2021","11.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","15.10.2021","18.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.11.2021","15.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.11.2021","22.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Parndorf Ort - Zurndorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Parndorf - Hegyeshalom","cont.","12.04.2021","16.04.2021","4 days + 4,7 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","08.03.2021","12.03.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.03.2021","14.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","19.03.2021","21.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","03.04.2021","06.04.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","10.04.2021","11.04.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - Lanzendorf-Rannersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.04.2021","18.04.2021","6 days + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","13.05.2021","16.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","22.05.2021","25.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","29.05.2021","30.05.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.06.2021","20.06.2021","13 days + 10,0 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","26.06.2021","20.08.2021","55 days + 9,0 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","05.07.2021","16.07.2021","10 days + 20,5 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","16.07.2021","06.08.2021","21 days + 12,5 h","ÖBB Infra"]
[]
[null,"Abzww Str 11815 - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.08.2021","16.09.2021","39 days + 20,5 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","20.08.2021","05.09.2021","15 days + 23,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Wien - Parndorf","cont.","01.09.2021","31.12.2022","487 days","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","15.10.2021","18.10.2021","2 days + 5,2 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","18.10.2021","31.10.2021","13 days + 11,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","23.10.2021","27.10.2021","3 days + 5,2 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","28.05.2021","02.06.2021","5 days + 15,0 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Inzersdorf Ort-Ost - Oberlaa",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","22.03.2021","29.03.2021","6 days + 20,0 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","29.10.2021","03.11.2021","4 days + 7,5 h","ÖBB Infra"]
[]
[null,"Linz Oed - Linz Wegscheid",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-26","2021-08-01","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-19","2021-07-25","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-02","2021-08-08","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-09","2021-08-15","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Rutzing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Rutzing - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":62,"n_cols":21,"rows_kept":62,"cut":false,"hidden":false,"merged":[[0,2,0,3],[0,0,0,1]]}
["IM",null,"Section",null,"Direction","Duration","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","International Coordination","In yearly timetable","Classification","Status","Automatic process"]
["GySEV",43,"Strasbourg - Karlsruhe",1,"< >","continuous","Signal","T","LT","S","W","D","C,,","R,,",",B,","O,,",43,"Y","Major","Planned","Y"]
["CFR",53,"Appenweier - Karlsruhe (div.)",2,">","periodical","Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,",53,"N","High","Coordination","N"]
["SŽCZ",54,"Karlsruhe - Bruchsal",3,"<","periodical continuous","Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",54,null,"Medium","Consultation"]
["MÁV",55,"Bruchsal - Mannheim",4,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",55,null,"Minor","Published"]
["ŽSR",56,"Karlsruhe - Mannheim",5,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",56,null,"Unclassified","Canceled"]
["DB Netz AG",80,"Mannheim - Darmstadt",6,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",80]
["ÖBB-Infra",81,"Mannheim - Gr. Gerau - Fr.",7,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",81]
["SNCF Reseau",87,"Darmstadt - Frankfurt",8,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,87]
[null,null,"Frankfurt - Aschaffenburg",9,null,null,"Others",null,null,null,null,null,null,null,null,null,54.81]
[null,null,"Darmstadt - Aschaffenburg",10,null,null,null,null,null,null,null,null,null,null,null,null,80.81]
[null,null,"Aschaffenburg - Gemünden",11,null,null,null,null,null,null,null,null,null,null,null,null,"54,80"]
[null,null,"Gemünden - Bamberg - Nürnberg",12,null,null,null,null,null,null,null,null,null,null,null,null,"55,56"]
[null,null,"Gemünden - Würzburg - Nürnberg",13,null,null,null,null,null,null,null,null,null,null,null,null,"54,81"]
[null,null,"Nürnberg - Regensburg",14,null,null,"Signal",null,null,null,null,null,null,null,null,null,"56,81"]
[null,null,"Regensburg - München",15,null,null,"Switch",null,null,null,null,null,null,null,null,null,"55,81"]
[null,null,"Regensburg - Wels",16,null,null,"Catenary",null,null,null,null,null,null,null,null,null,"43,55"]
[null,null,"Bruchsal - Mühlacker",17,null,null,"Track & Rail",null,null,null,null,null,null,null,null,null,"43,81"]
[null,null,"Karlsruhe - Stuttgart",18,null,null,"Tunnel"]
[null,null,"Stuttgart - München",19,null,null,"Bridge"]
[null,null,"München - Rosenheim - Salzburg ",20,null,null,"Miscellaneous*"]
[null,null,"München - Mühld. - Freilassing",21,null,null,"Maintenance"]
[null,null,"Nürnberg - Plzen",22,null,null,"Others**"]
[null,null,"Regensburg - Plzen",23]
[null,null,"Plzen - Praha",24]
[null,null,"Praha - Choceň",25]
[null,null,"Praha - Hr. Králové - Choceň",26]
[null,null,"Choceň - Hranice na Moravě",27]
[null,null,"Hranice na Moravě - Žilina",28]
[null,null,"Hranice na Moravě - Ostrava",29]
[null,null,"Ostrava - Český Těšín",30]
[null,null,"Ostr. - Dětmarovice - Č. Těšín",31]
[null,null,"Český Těšín - Žilina",32]
[null,null,"Žilina - Košice",33]
[null,null,"Košice - Čierna nad Tisou",34]
[null,null,"Čierna nad Tisou - Chop",35]
[null,null,"Košice - Haniska pri Košiciach",36]
[null,null,"Haniska pri Košic. - Maťovce",37]
[null,null,"Salzburg - Wels",38]
[null,null,"Wels - Linz",39]
[null,null,"Wels - Traun - Linz",40]
[null,null,"Linz - Wien",41]
[null,null,"Wien - Parndorf",42]
[null,null,"Parndorf - Bratislava",43]
[null,null,"Parndorf - Hegyeshalom",44]
[null,null,"Wien - Sopron",45]
[null,null,"Sopron - Győr",46]
[null,null,"Bratislava - Hegyeshalom",47]
[null,null,"Hegyeshalom - Györ",48]
[null,null,"Györ - Budapest",49]
[null,null,"Budapest - Újszász - Szolnok",50]
[null,null,"Budapest - Cegléd - Szolnok",51]
[null,null,"Szolnok - Arad",52]
[null,null,"Szolnok - Cluj",53]
[null,null,"Cluj - Coșlariu",54]
[null,null,"Arad - Brașov",55]
[null,null,"Brașov - Bucuresti",56]
[null,null,"Arad - Craiova",57]
[null,null,"Craiova - Bucuresti",58]
[null,null,"Bucuresti - Constanţa",59]
[null,null,"Ploiești triaj - Fetești",60]
[null,null,"Simeria - Filiasi",61]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}