{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":4,"macros":1,"external_links":7,"defined_names":5,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Schedule","index":1,"n_rows":4923,"n_cols":43,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,1,5],[1,6,1,7],[1,17,1,21],[1,8,1,9],[3388,2,3388,30],[1,22,1,26],[1,27,2,27],[1,28,2,28],[1,29,2,29],[1,30,2,30],[1,10,1,11],[1,12,1,13],[1,14,2,14],[1,15,2,15],[1,16,2,16]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day\n(character of timely closure)","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In annual timetable","Last update"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other"]
[]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,23,38,"2022-06-10T22:00:00","22:00:00","2022-09-24T17:00:00","17:00:00","105 d, 19 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - NWH",null,"Y","2021-11-16T14:17:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Nantenbach",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-06T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Harrbach",null,"N","2021-12-20T08:07:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-11T20:00:00","20:00:00","6 d, 12 h","continuous","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Hohlstellenbildung u. Rissverpressen im Tunnel Schönrain",null,"N","2022-02-02T11:22:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-07T08:00:00","08:00:00","2022-09-08T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Ständelberg",null,"N","2021-12-15T08:50:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,39,"2022-09-22T07:00:00","07:00:00","2022-09-29T16:00:00","16:00:00","3 d","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain_RKZ 1",null,"N","2021-12-16T14:38:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-25T05:30:00","05:30:00","2022-10-08T17:00:00","17:00:00","6 d, 17 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - NWH",null,"Y","2022-02-25T10:03:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,40,42,"2022-10-09T05:30:00","05:30:00","2022-10-17T04:00:00","04:00:00","7 d, 22 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - NWH",null,"Y","2022-03-09T13:46:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Nantenbach",2022,2022,37,37,"2022-09-12T06:00:00","06:00:00","2022-09-18T22:00:00","22:00:00","4 d, 16 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain RKZ 2_im PKI",null,"N","2021-12-16T13:58:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Lohr Bahnhof",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-06T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Harrbach",null,"N","2020-11-26T14:08:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-05T08:00:00","08:00:00","2022-09-11T20:00:00","20:00:00","6 d, 12 h","continuous","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Hohlstellenbildung u. Rissverpressen im Tunnel Schönrain",null,"N","2020-11-26T13:10:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,36,36,"2022-09-07T08:00:00","08:00:00","2022-09-08T17:00:00","17:00:00","18 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Ständelberg",null,"N","2020-11-26T14:06:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Rohrbach","Nantenbach",2022,2022,37,37,"2022-09-12T06:00:00","06:00:00","2022-09-18T22:00:00","22:00:00","4 d, 16 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain RKZ 2_im PKI",null,"N","2020-11-26T14:23:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-22T07:00:00","07:00:00","2022-10-04T16:00:00","16:00:00","4 d, 21 h","periodical","Tunnel","T",null,null,null,null,null,null,null,null,null,"Tunnelarbeiten Spülung u. Inspektion TE im Tunnel Schönrain_RKZ 1",null,"N","2020-11-26T14:30:00"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,38,40,"2022-09-25T05:30:00","05:30:00","2022-10-08T17:00:00","17:00:00","6 d, 17 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - RWH",null,"Y","2020-04-27T06:53:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,33,36,"2022-08-15T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","7 d, 07 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2022-02-01T15:37:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,37,"2022-09-09T21:00:00","21:00:00","2022-09-12T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-08T13:36:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,36,37,"2022-09-09T21:00:00","21:00:00","2022-09-12T05:00:00","05:00:00","2 d, 08 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-08T13:36:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,37,38,"2022-09-17T20:30:00","20:30:00","2022-09-19T04:30:00","04:30:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:05:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,37,38,"2022-09-17T20:30:00","20:30:00","2022-09-19T04:30:00","04:30:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:05:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,37,38,"2022-09-17T20:30:00","20:30:00","2022-09-19T04:30:00","04:30:00","1 d, 08 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:05:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Heidelberg-Wieblingen","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,37,38,"2022-09-17T22:00:00","22:00:00","2022-09-24T06:00:00","06:00:00","2 d, 08 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW",null,"N","2022-01-12T16:11:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,37,38,"2022-09-17T22:00:00","22:00:00","2022-09-24T18:00:00","18:00:00","6 d, 20 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW",null,"N","2022-01-12T14:21:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","<","Darmstadt Hbf","Darmstadt Hbf",2022,2022,38,39,"2022-09-24","00:00:00","2022-09-26T04:00:00","04:00:00","2 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:12:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,38,38,"2022-09-24T16:00:00","16:00:00","2022-09-25T08:00:00","08:00:00","16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:12:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","<","Darmstadt Hbf","Darmstadt Hbf",2022,2022,39,40,"2022-10-01T16:00:00","16:00:00","2022-10-03T04:00:00","04:00:00","1 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.2118 Ersatzneubau SÜ Rheinstraße",null,"N","2022-03-10T14:15:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,47,"2022-11-07T06:00:00","06:00:00","2022-11-24T18:00:00","18:00:00","17 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.3253 WE 326/331/332 FD 07.-24.11.2022",null,"N","2022-04-14T15:58:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T04:00:00","04:00:00","2 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.3253 WE 326/331/332 FD 07.-24.11.2022",null,"N","2022-04-14T16:06:00"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<>","Babenhausen","Darmstadt Hbf",2022,2023,50,48,"2022-12-17","22:30:00","2023-12-03","05:30:00","350d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,"80","Y","2021-09-17"]
[null,80,"Hanau Südseite - Rohrbach","< >","Nantenbach","Rohrbach",2022,2022,40,42,"2022-10-09T05:30:00","05:30:00","2022-10-17T04:00:00","04:00:00","7 d, 22 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - RWH",null,"Y","2020-06-08T10:04:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,23,42,"2022-06-10T22:00:00","22:00:00","2022-10-17T04:00:00","04:00:00","128 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR SFS 1733 - Ra3a: RB Süd NMOT - NWH",null,"N","2022-02-08T08:57:00"]
[null,80,"Rottendorf - Bamberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2022,2022,36,37,"2022-09-09T08:00:00","08:00:00","2022-09-13T08:00:00","08:00:00","4 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleisauswechslung Gl.9_Belastungsstopfgang in Schweinfurt Hbf",null,"N","2021-08-23T13:12:00"]
[null,80,"Rottendorf - Bamberg","< >","Gädheim","Haßfurt",2022,2022,39,39,"2022-10-01T21:00:00","21:00:00","2022-10-02T09:00:00","09:00:00","12 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ km 38,4 und km 76,6 NHT-NGAE",null,"N","2022-03-01T13:10:00"]
[null,80,"Rottendorf - Bamberg","< >","Waigolshausen","Schweinfurt Hbf",2022,2022,48,49,"2022-12-01T22:00:00","22:00:00","2022-12-09T04:00:00","04:00:00","7 d, 06 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung EÜ A70 km 60,242",null,"N","2022-03-30T15:39:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Hirschaid","Hirschaid",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gleis 3 (Anm. Tem-005) in Hirschaid",null,"N","2021-05-17T11:45:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143",">","Darmstadt Gbf","Darmstadt Nord",2022,2023,49,49,"2022-12-11","00:00:00","2023-12-09","23:45:00","363d, 23h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-04"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Forchheim (Oberfr)","Bamberg",2022,2022,48,48,"2022-12-03T22:45:00","22:45:00","2022-12-04T08:30:00","08:30:00","10 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Tem-009 VDE 8.1.1 PA21 Ern. SÜ B505 km 55,504 + PA19 OL-Arb",null,"N","2022-04-14T11:56:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2022,2022,33,36,"2022-08-15T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","7 d, 07 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:25:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,36,"2022-09-09T21:00:00","21:00:00","2022-09-11T05:00:00","05:00:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T13:45:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,36,37,"2022-09-11T05:00:00","05:00:00","2022-09-12T05:00:00","05:00:00","1 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T13:45:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,37,38,"2022-09-17T16:00:00","16:00:00","2022-09-19T04:00:00","04:00:00","1 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:08:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,37,38,"2022-09-18T08:00:00","08:00:00","2022-09-19T04:00:00","04:00:00","20 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:08:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,38,38,"2022-09-24T16:00:00","16:00:00","2022-09-25T08:00:00","08:00:00","16 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:53:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,38,39,"2022-09-25T12:00:00","12:00:00","2022-09-26T04:00:00","04:00:00","16 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-19T14:53:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen",">","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,40,41,"2022-10-09","00:00:00","2022-10-10T04:00:00","04:00:00","1 d, 04 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-22T09:46:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,41,42,"2022-10-15T20:00:00","20:00:00","2022-10-17T04:00:00","04:00:00","1 d, 08 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-22T10:37:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt",2022,2022,42,42,"2022-10-23T04:00:00","04:00:00","2022-10-23T20:00:00","20:00:00","16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-29T15:43:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt-Eberstadt Nord",2022,2022,43,43,"2022-10-30T08:00:00","08:00:00","2022-10-30T18:00:00","18:00:00","10 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ersatzneubau SÜ Rheinstraße",null,"N","2020-06-30T14:11:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,47,"2022-11-07T06:00:00","06:00:00","2022-11-24T18:00:00","18:00:00","17 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Darmstadt Hbf - Heidelberg-Wieblingen","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T04:00:00","04:00:00","2 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf",">","Darmstadt Gbf","Darmstadt Nord",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten BBM.22.0260 Kreuzungsbauwerk Darmstadt 3557/3541",null,"N","2022-02-02T09:58:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,46,"2022-11-09T05:00:00","05:00:00","2022-11-14T05:00:00","05:00:00","5 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.3253 WE 326/331/332 FD 07.-24.11.2022",null,"N","2022-05-30T12:30:00"]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,47,48,"2022-11-25","00:00:00","2022-11-28T23:59:00","23:59:00","4 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung BBM.22.3401 WE FD 25.-28.11.2022",null,"N","2022-05-02T15:31:00"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Laufach","Aschaffenbg Hbf",2022,2022,49,50,"2022-12-11","23:50:00","2022-12-12","05:00:00","0d, 5h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-06-15"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaffenbg Hbf","Aschaff Hbf Einf",2022,2022,49,50,"2022-12-11","23:50:00","2022-12-12","05:00:00","0d, 5h","continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-13"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Laufach","Aschaffenbg Hbf",2022,2022,49,50,"2022-12-11","23:50:00","2022-12-12","05:00:00","0d, 5h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-15"]
[null,80,"Neu-Edingen/Mhm-Friedrichsfeld - Schwetzingen","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2022,2022,37,38,"2022-09-17T22:00:00","22:00:00","2022-09-24T18:00:00","18:00:00","6 d, 20 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW",null,"N","2022-01-12T15:59:00"]
[]
[null,80,"Darmstadt Hbf - Aschaffenburg Hbf","< >","Darmstadt Hbf","Darmstadt Hbf",2022,2022,45,46,"2022-11-09T05:00:00","05:00:00","2022-11-14T05:00:00","05:00:00","5 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weichen 326, 331 und 332",null,"N","2020-04-27T06:44:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt",">","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2022,2022,43,45,"2022-10-28T21:00:00","21:00:00","2022-11-11T21:00:00","21:00:00","14 d","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2022-06-29T08:45:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt",">","Stuttgart-Zuffenhausen","Stuttgart Pragtunnel",2022,2022,43,45,"2022-10-28T21:00:00","21:00:00","2022-11-11T21:00:00","21:00:00","14 d","continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2022-07-07T14:11:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,43,45,"2022-10-28T23:00:00","23:00:00","2022-11-11T05:00:00","05:00:00","3 d, 12 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2022-06-29T08:45:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,43,45,"2022-10-28T23:00:00","23:00:00","2022-11-11T05:00:00","05:00:00","3 d, 12 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen LST-, OLA-Arbeiten",null,"N","2022-07-07T14:11:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,43,44,"2022-10-29T23:00:00","23:00:00","2022-11-04T05:00:00","05:00:00","1 d, 12 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-06-28T20:16:00"]
[null,80,"Stuttgart-Zuffenhausen - Stuttgart-Bad Cannstatt","< >","Stuttgart Pragtunnel","Stuttgart-Zuffenhausen",2022,2022,43,44,"2022-10-29T23:00:00","23:00:00","2022-11-04T05:00:00","05:00:00","1 d, 12 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-07-07T14:12:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,35,35,"2022-08-31T12:00:00","12:00:00","2022-09-03T12:00:00","12:00:00","3 d","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"Schleifen von Schienen RH, RRM, RBKS, RWS SChienenschleifen",null,"N","2022-05-23T12:51:00"]
[null,80,"Waghäusel Saalbach - Rastatt","< >","Graben-Neudorf","Graben-Neudorf",2022,2022,43,45,"2022-10-28T19:00:00","19:00:00","2022-11-13T17:59:00","17:59:00","15 d, 23 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Ern. EÜ Saalbachkanal Str. 4020, km 38,887 (Bph 3b - Einbau Hbr Gl. 2, 1, 9) in Graben-Neudorf",null,"N","2022-07-05T17:11:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Ulm Hbf","Ulm Hbf",2022,2022,46,49,"2022-11-20T23:00:00","23:00:00","2022-12-09T05:00:00","05:00:00","18 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleiserneuerung in Ulm Hbf",null,"N","2020-10-22T11:57:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Göppingen","Göppingen",2022,2022,43,44,"2022-10-28T07:00:00","07:00:00","2022-11-02T17:00:00","17:00:00","5 d, 10 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten PSS Göppingen - Uhingen - Logistik",null,"N","2022-03-31T13:23:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","< >","Ebersbach (Fils)","Göppingen",2022,2022,43,43,"2022-10-29T22:00:00","22:00:00","2022-10-30T05:00:00","05:00:00","7 h","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,"Durcharbeitung von Gleisen PSS Göppingen - Uhingen",null,"N","2022-03-31T12:18:00"]
[null,80,"Stuttgart-Bad Cannstatt - Neu-Ulm","<","Ulm Hbf","Ulm Hbf",2022,2022,49,49,"2022-12-07T05:00:00","05:00:00","2022-12-09T05:00:00","05:00:00","2 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleiserneuerung in Ulm Hbf",null,"N","2020-10-22T11:57:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-27T09:00:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Neuoffingen",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Unterfahlheim","Günzburg",2022,2022,48,48,"2022-11-28T21:00:00","21:00:00","2022-11-29T21:00:00","21:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2021-07-12T12:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Augsburg-Oberhausen","Augsburg Hbf",2022,2022,46,47,"2022-11-18T22:30:00","22:30:00","2022-11-21T04:30:00","04:30:00","18 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten PAC-H SW Hotzbachbrücke OL-Arb - Ph-BBM22-AUG-211",null,"N","2022-04-05T09:35:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-29T02:00:00","02:00:00","2022-11-30T02:00:00","02:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2022-04-19T13:02:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Neuoffingen",2022,2022,48,48,"2022-11-29T02:00:00","02:00:00","2022-11-30T02:00:00","02:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2022-04-19T13:03:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Günzburg","Günzburg",2022,2022,48,48,"2022-11-29T02:00:00","02:00:00","2022-11-30T02:00:00","02:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2022-04-19T13:03:00"]
[null,80,"Ulm Hbf - Augsburg Hbf","< >","Unterfahlheim","Günzburg",2022,2022,48,48,"2022-11-29T02:00:00","02:00:00","2022-11-30T02:00:00","02:00:00","1 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Ergänzung zur J(XEI), Neubau SÜ B16, Str 5302, km 60,916 in Günzburg",null,"N","2022-04-19T13:03:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,20,36,"2022-05-21","00:00:00","2022-09-07T04:00:00","04:00:00","109 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:20:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,26,36,"2022-06-27","00:00:00","2022-09-07T04:00:00","04:00:00","72 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:19:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,31,46,"2022-08-01","00:00:00","2022-11-18T23:59:00","23:59:00","110 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Erneuerung Bahnsteigbelag Kar Hbf Bstg 5/6",null,"N","2022-01-10T10:36:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,31,36,"2022-08-02","00:00:00","2022-09-10T05:00:00","05:00:00","39 d, 05 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Aufbau Schutzwand zw. Gl.7+8, Ein- und Ausbau Iso Gl.6+7, Brückenarb. Gl.6-8 in Pforzheim Hbf",null,"N","2021-10-28T11:59:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,31,41,"2022-08-02","00:00:00","2022-10-12T04:00:00","04:00:00","71 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:19:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,31,35,"2022-08-06T04:00:00","04:00:00","2022-09-03T04:00:00","04:00:00","28 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Aufbau Schutzwand zw. Gl.7+8, Ein- und Ausbau Iso Gl.6+7, Brückenarb. Gl.6-8 in Pforzheim Hbf",null,"N","2021-10-27T13:18:00"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2022,2023,49,5,"2022-12-11","00:30:00","2023-01-31","06:20:00","51d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<","Önsbach","Baden-Baden",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:20:00","50d, 6h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-06-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<","Baden-Baden","Baden-Baden",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:20:00","50d, 6h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,"80","N","2022-06-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Baden-Baden","Önsbach",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:20:00","50d, 6h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-06-07"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Baden-Baden",2022,2023,49,5,"2022-12-11","23:30:00","2023-01-31","06:20:00","50d, 6h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,"80","N","2022-06-07"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,35,36,"2022-09-02T20:00:00","20:00:00","2022-09-09T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:15:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,35,36,"2022-09-02T20:00:00","20:00:00","2022-09-09T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:15:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,35,36,"2022-09-02T20:00:00","20:00:00","2022-09-09T18:00:00","18:00:00","6 d, 22 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl.10 in Karlsruhe Hbf",null,"N","2021-08-09T13:15:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","2022-01-14T10:31:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","2022-01-14T11:05:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","2022-01-14T12:49:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Söllingen (b Karlsruhe) Abzw","Söllingen (b Karlsruhe) Abzw",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang Ergänzung zur J(XEI), SEV",null,"N","2020-08-28T08:25:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Söllingen (b Karlsruhe) Abzw","Söllingen (b Karlsruhe) Abzw",2022,2022,35,35,"2022-09-02T22:00:00","22:00:00","2022-09-04T04:00:00","04:00:00","12 h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,"Auswechslung v Weichengroßteilen Herzstückwechsel + PKI W115, W111, W112, W113, Abzw. Söllingen in Söllingen Abzw",null,"N","2022-06-03T12:24:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Wilferdingen-Singen","Söllingen (b Karlsruhe) Abzw",2022,2022,36,36,"2022-09-07T21:00:00","21:00:00","2022-09-09T07:00:00","07:00:00","20 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung Schlammstellenbeseitigung Gl. Wilferdingen-Singen - Söllingen Abzw. in km 8,550",null,"N","2022-06-03T14:16:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,36,40,"2022-09-10T05:00:00","05:00:00","2022-10-08T04:00:00","04:00:00","27 d, 23 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Umbau Schutzwand zw. Gl.7-8 + Einbau Iso in Pforzheim Hbf",null,"N","2021-10-28T12:10:00"]
[null,80]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Pforzheim Hbf","Pforzheim Hbf",2022,2022,20,36,"2022-05-21","00:00:00","2022-09-07T04:00:00","04:00:00","109 d, 04 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Nordstadtbrücke Pforzheim - Einbau Iso für Aufbau Schutzwand zwischen Gl.1 und W221 in Pforzheim Hbf",null,"N","2021-09-24T11:20:00"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Sandweier","Baden-Baden",2022,2023,50,5,"2022-12-12","00:30:00","2023-01-31","06:20:00","50d, 5h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2020-09-30"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2022,2023,50,5,"2022-12-12","00:30:00","2023-01-31","06:20:00","50d, 5h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Karlsruhe Hbf","Karlsruhe Hbf",2022,2022,31,46,"2022-08-01","00:00:00","2022-11-18T23:59:00","23:59:00","110 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Erneuerung Bahnsteigbelag Kar Hbf Bstg 5/6",null,"N","2020-04-27T07:16:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten am Bahnübergang BÜ-Beseitigung Söllingen (4200, km 7,640), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"Arbeiten an TK-Anlagen Erneuerung Streckenfernmeldekabel (4200, RK-TWL), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Karlsruhe Hbf - Vaihingen (Enz)","< >","Grötzingen","Wilferdingen-Singen",2022,2022,35,36,"2022-09-02T21:00:00","21:00:00","2022-09-09T20:59:00","20:59:00","7 d","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Söllingen Bahnwinkel (Baufeldfreimachung), SEV",null,"N","2020-04-27T07:17:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen","<","Vaihingen (Enz)","Vaihingen (Enz)",2022,2022,43,46,"2022-10-28T07:00:00","07:00:00","2022-11-18T16:00:00","16:00:00","21 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-06-28T19:48:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen","<","Vaihingen (Enz)","Vaihingen (Enz)",2022,2022,43,46,"2022-10-28T07:00:00","07:00:00","2022-11-18T16:00:00","16:00:00","21 d, 09 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-07-07T14:09:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,43,45,"2022-10-28T21:00:00","21:00:00","2022-11-11T21:00:00","21:00:00","14 d","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-06-28T19:48:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,43,45,"2022-10-28T21:00:00","21:00:00","2022-11-11T21:00:00","21:00:00","14 d","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-07-07T14:09:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,45,46,"2022-11-11T21:00:00","21:00:00","2022-11-18T05:00:00","05:00:00","6 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-06-28T20:31:00"]
[null,80,"Vaihingen (Enz) - Stuttgart-Zuffenhausen",">","Kornwestheim Pbf","Stuttgart-Zuffenhausen",2022,2022,45,46,"2022-11-11T21:00:00","21:00:00","2022-11-18T05:00:00","05:00:00","6 d, 08 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Kornwestheim-STg.-Zuffenhausen",null,"N","2022-07-07T14:13:00"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86","<>","Graben-Neudorf","Graben-Neudorf",2022,2023,49,16,"2022-12-11","00:00:00","2023-04-20","10:30:00","130d, 9h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Graben-Neudorf","Graben-Neudorf",2022,2023,49,16,"2022-12-11","00:00:00","2023-04-20","10:30:00","130d, 9h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr D","Mannheim Rbf Gr D",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr K/Kn","Mannheim Rbf Gr K/Kn",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,33,34,"2022-08-19T22:00:00","22:00:00","2022-08-22T05:00:00","05:00:00","2 d, 07 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2022-02-01T15:19:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr D","Mannheim Rbf Gr D",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr K/Kn","Mannheim Rbf Gr K/Kn",2022,2022,32,37,"2022-08-10","00:00:00","2022-09-14T23:59:00","23:59:00","36 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen",null,"N","2020-07-15T10:20:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,34,36,"2022-08-22T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","5 d, 06 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2022-02-01T16:01:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,33,34,"2022-08-19T22:00:00","22:00:00","2022-08-22T05:00:00","05:00:00","2 d, 07 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2020-10-12T13:52:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,34,36,"2022-08-22T22:00:00","22:00:00","2022-09-09T05:00:00","05:00:00","5 d, 06 h","periodical","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI)",null,"N","2020-10-12T13:54:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,47,"2022-11-26T21:40:00","21:40:00","2022-11-27T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2020-12-14T15:32:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,48,"2022-11-27T21:40:00","21:40:00","2022-11-28T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2020-12-14T15:47:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Gr D","Mannheim Rbf Gr D",2022,2022,37,39,"2022-09-15","00:00:00","2022-10-01T23:59:00","23:59:00","17 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Untergrundverbesserung 2022_3601_PSS RMF - RHBW",null,"N","2021-09-06T17:08:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","<","Mannheim Rbf Gr K/Kn","Mannheim Hbf Ost",2022,2022,42,42,"2022-10-22T11:00:00","11:00:00","2022-10-23T18:00:00","18:00:00","1 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Untergrundverbesserung Untergrundverbesserung im Bereich zwischen W107 und Kr.109 in Mannheim Rbf in KW40 in Ma Rbf Westeinf Bft",null,"N","2022-03-25T13:08:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim Rbf Westeinfahrt","Mannheim Rbf Westeinfahrt",2022,2022,42,42,"2022-10-22T11:00:00","11:00:00","2022-10-23T18:00:00","18:00:00","1 d, 07 h","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"Untergrundverbesserung Untergrundverbesserung im Bereich zwischen W107 und Kr.109 in Mannheim Rbf in KW40 in Ma Rbf Westeinf Bft",null,"N","2022-03-25T13:08:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,47,"2022-11-26T21:40:00","21:40:00","2022-11-27T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2022-05-05T09:59:00"]
[null,80,"Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf","< >","Mannheim-Friedrichsfeld Südeinf/Ausf","Mannheim Rbf Gr K/Kn",2022,2022,47,48,"2022-11-27T21:40:00","21:40:00","2022-11-28T04:10:00","04:10:00","6 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV",null,"N","2022-05-05T10:00:00"]
[]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2022,2022,34,35,"2022-08-23","00:00:00","2022-08-30T05:00:00","05:00:00","7 d, 05 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Brückenarbeiten",null,"N","2021-02-11T11:17:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,36,37,"2022-09-10T19:00:00","19:00:00","2022-09-12T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten 6 Lager",null,"N","2020-08-20T12:27:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2022,2022,37,38,"2022-09-17T19:00:00","19:00:00","2022-09-19T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten 6 Lager",null,"N","2020-08-20T12:27:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Marktredwitz","Schirnding Grenze",2022,2022,37,39,"2022-09-16","00:00:00","2022-09-26T06:00:00","06:00:00","10 d, 06 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung WE Marktredwitz-Landesgrenze",null,"N","2021-07-09T12:18:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Schnabelwaid","Kirchenlaibach",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Speichersdorf  km 93,183",null,"N","2020-06-15T13:25:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Neunkirchen a Sand","Neunkirchen a Sand",2022,2022,26,37,"2022-06-29","00:00:00","2022-09-12T05:00:00","05:00:00","50 d, 03 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200",null,"Y","2021-11-19T13:04:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Hbf","Nürnberg Hbf",2022,2022,29,35,"2022-07-22T00:01:00","00:01:00","2022-09-01T23:59:00","23:59:00","42 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung nur Logistikgleis 301/302/303 für WE NN in Nürnberg Hbf",null,"N","2022-04-28T13:36:00"]
[null,80,"Augsburg Hbf - München Hbf","< >","München Hbf","München Hbf",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-06T06:00:00","06:00:00","3 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE MH W 215-217, 221-223, 236, 237, 267 und GE Verb W 220-W250 Qualistopfgang",null,"N","2021-06-08T15:51:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Nürnberg Ost",2022,2022,29,35,"2022-07-22T22:00:00","22:00:00","2022-09-01T23:59:00","23:59:00","41 d, 02 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung nur Logistikgleis 301/302/303 für WE NN in Nürnberg Hbf",null,"N","2022-04-28T13:36:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2022,2022,32,34,"2022-08-08T04:45:00","04:45:00","2022-08-23","00:00:00","14 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200",null,"Y","2021-11-24T10:05:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Hbf","Nürnberg Hbf",2022,2022,33,34,"2022-08-15T07:00:00","07:00:00","2022-08-23T17:00:00","17:00:00","8 d, 10 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 161, 162, 165,166, 167, 175 u.177 in Nürnberg Hbf",null,"N","2021-11-23T12:48:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Hbf","Nürnberg Hbf",2022,2022,33,34,"2022-08-15T07:00:00","07:00:00","2022-08-23T22:00:00","22:00:00","8 d, 15 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W 161, 162, 165,166, 167, 175 u.177 in Nürnberg Hbf",null,"N","2021-11-23T12:48:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2022,2022,34,35,"2022-08-23","00:00:00","2022-08-30T04:50:00","04:50:00","7 d, 05 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Brückenarbeiten",null,"N","2022-01-25T15:03:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,34,35,"2022-08-23","00:00:00","2022-09-02T04:45:00","04:45:00","10 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200",null,"N","2021-11-24T10:05:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Nürnberg Hbf",2022,2022,34,34,"2022-08-23T22:00:00","22:00:00","2022-08-26T05:00:00","05:00:00","2 d, 07 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 161, 162, 165,166, 167, 175 u.177 in Nürnberg Hbf",null,"N","2021-11-23T13:07:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Ost","Nürnberg Hbf",2022,2022,34,35,"2022-08-23T22:00:00","22:00:00","2022-08-31T05:00:00","05:00:00","7 d, 07 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung W 161, 162, 165,166, 167, 175 u.177 in Nürnberg Hbf",null,"N","2021-11-23T13:10:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Nürnberg Hbf","Nürnberg Hbf",2022,2022,34,35,"2022-08-23T22:00:00","22:00:00","2022-08-31T05:00:00","05:00:00","7 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung nur Logistikgleis 301/302/303 für WE NN in Nürnberg Hbf",null,"N","2022-04-28T13:36:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Rückersdorf (Mittelfr)","Lauf (rechts Pegnitz)",2022,2022,35,35,"2022-08-29T07:00:00","07:00:00","2022-08-31T05:00:00","05:00:00","1 d, 22 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200_Kabelumschaltarbeiten LST",null,"N","2022-05-11T08:10:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2022,2022,35,36,"2022-09-02T04:45:00","04:45:00","2022-09-08","00:00:00","5 d, 19 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200",null,"Y","2021-11-24T10:35:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2022,2022,36,37,"2022-09-08","00:00:00","2022-09-12T04:45:00","04:45:00","4 d, 05 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Untergrundverbesserung Heuchlinger Damm km 17,800 bis 18,200",null,"N","2021-11-24T10:35:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,37,38,"2022-09-17T19:10:00","19:10:00","2022-09-19T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Brückenlagerwechsel EÜ km 47,650 Vorra - Neuhaus (Pegnitz)",null,"N","2022-03-01T12:54:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2022,2022,37,38,"2022-09-17T19:10:00","19:10:00","2022-09-19T05:00:00","05:00:00","1 d, 10 h","continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"Brückenarbeiten Brückenlagerwechsel EÜ km 47,650 Vorra - Neuhaus (Pegnitz)",null,"N","2022-03-01T12:54:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2022,2022,37,38,"2022-09-17T19:10:00","19:10:00","2022-09-19T05:00:00","05:00:00","1 d, 10 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung Mängelbeseitigung nach GE NHR Gleis 103 in Hersbruck (re P)",null,"N","2022-05-27T09:13:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2022,2022,38,39,"2022-09-24T19:15:00","19:15:00","2022-09-26T05:15:00","05:15:00","1 d, 10 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Brückenlagerwechsel EÜ km 47,650 Vorra - Neuhaus (Pegnitz)",null,"N","2022-03-01T12:54:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2022,2022,38,39,"2022-09-24T19:15:00","19:15:00","2022-09-26T05:15:00","05:15:00","1 d, 10 h","continuous","Bridge",null,null,null,"P",null,null,null,null,null,null,"Brückenarbeiten Brückenlagerwechsel EÜ km 47,650 Vorra - Neuhaus (Pegnitz)",null,"N","2022-03-01T12:54:00"]
[null,80,"Nürnberg Hbf - Schnabelwaid","< >","Nürnberg Hbf","Nürnberg Hbf",2022,2022,40,41,"2022-10-03T08:00:00","08:00:00","2022-10-16T18:00:00","18:00:00","13 d, 10 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Qualistopfgang W 131-133 u. W 134  u. W 141 in Nürnberg Hbf",null,"N","2021-10-21T13:21:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Marktredwitz","Schirnding Grenze",2022,2022,37,39,"2022-09-16","00:00:00","2022-09-26T06:00:00","06:00:00","10 d, 06 h","continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Gleiserneuerung WE Marktredwitz-Landesgrenze",null,"N","2022-02-09T13:51:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Schirnding","Schirnding",2022,2022,37,39,"2022-09-16","00:00:00","2022-09-26T06:00:00","06:00:00","10 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung WE Marktredwitz-Landesgrenze",null,"N","2022-02-09T11:20:00"]
[null,80,"Schnabelwaid - Schirnding Grenze","< >","Schnabelwaid","Kirchenlaibach",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-11-04T14:00:00","14:00:00","6 d, 16 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten EÜ Speichersdorf  km 93,183 in Kirchenlaibach",null,"N","2022-04-07T15:04:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2022-02-18T16:21:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Schwandorf","Schwandorf",2022,2022,39,39,"2022-09-26T06:00:00","06:00:00","2022-09-29T18:00:00","18:00:00","3 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Schleifen und Belastungsstopfgang W 56W4, W5, W29 in Maxhütte-Haidhof",null,"N","2021-10-15T13:00:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Maxhütte-Haidhof","Maxhütte-Haidhof",2022,2022,39,39,"2022-09-27T22:00:00","22:00:00","2022-09-29T05:00:00","05:00:00","14 h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Schleifen und Belastungsstopfgang W 56W4, W5, W29 in Maxhütte-Haidhof",null,"N","2021-10-15T13:00:00"]
[null,80,"München Hbf - Salzburg Hbf","< >","Traunstein","Traunstein",2022,2022,44,44,"2022-11-01T05:00:00","05:00:00","2022-11-04T05:00:00","05:00:00","3 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE GE MTO Gl.602 u. Gl.604",null,"N","2020-10-07T16:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-05-05T14:10:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,28,34,"2022-07-16T16:00:00","16:00:00","2022-08-22T03:45:00","03:45:00","36 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2020-06-22T07:21:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,28,49,"2022-07-16T16:00:00","16:00:00","2022-12-10T23:59:00","23:59:00","147 d, 08 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2020-06-22T07:21:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Plattling","Plattling",2022,2022,32,35,"2022-08-08T08:00:00","08:00:00","2022-08-30T18:00:00","18:00:00","22 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS GA/PSS + Se 2 Schwaigen - Landau",null,"N","2022-07-20T15:16:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,33,35,"2022-08-16T07:00:00","07:00:00","2022-08-29T19:00:00","19:00:00","13 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2022-01-11T15:29:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,33,35,"2022-08-16T07:00:00","07:00:00","2022-08-29T19:00:00","19:00:00","13 d, 12 h","continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2022-01-11T15:29:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,35,36,"2022-08-29T08:00:00","08:00:00","2022-09-07T18:00:00","18:00:00","9 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-07T08:15:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,35,36,"2022-08-29T08:00:00","08:00:00","2022-09-07T18:00:00","18:00:00","9 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-07T08:15:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Plattling","Plattling",2022,2022,31,35,"2022-08-05T18:00:00","18:00:00","2022-08-30T02:00:00","02:00:00","24 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR und PSS GA/PSS + Se 2 Schwaigen - Landau",null,"N","2020-05-25T16:45:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,34,37,"2022-08-27T08:00:00","08:00:00","2022-09-15T18:00:00","18:00:00","19 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,36,38,"2022-09-05T07:00:00","07:00:00","2022-09-21T05:00:00","05:00:00","15 d, 22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Bbf","Regensburg Bbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Schalding","Schalding",2022,2022,37,37,"2022-09-17T22:40:00","22:40:00","2022-09-18T20:15:00","20:15:00","22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenausbau Rückbau mit Lückenschluss W618 in Schalding",null,"N","2020-05-29T10:13:00"]
[null,80,"Nürnberg Hbf - Passau Grenze",">","Schalding","Schalding",2022,2022,37,37,"2022-09-17T22:40:00","22:40:00","2022-09-18T20:15:00","20:15:00","22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenausbau Rückbau mit Lückenschluss W618 in Schalding",null,"N","2020-05-29T10:13:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,41,42,"2022-10-14T22:00:00","22:00:00","2022-10-23T04:00:00","04:00:00","8 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","2020-05-26T12:55:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Obertraubling","Obertraubling",2022,2022,41,42,"2022-10-14T23:00:00","23:00:00","2022-10-23T04:00:00","04:00:00","8 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","2020-05-26T12:51:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,42,42,"2022-10-22T21:50:00","21:50:00","2022-10-23T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2020-11-12T10:30:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Passau Gbf","Passau Gbf",2022,2022,36,36,"2022-09-05T07:00:00","07:00:00","2022-09-09T13:00:00","13:00:00","4 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schwellenauswechslung Schwellenwechsel NPA Gl.403",null,"N","2022-06-10T12:56:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,36,38,"2022-09-05T07:00:00","07:00:00","2022-09-21T05:00:00","05:00:00","15 d, 22 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2022-02-18T16:21:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","<","Regensburg Ost","Regensburg Ost",2022,2022,36,37,"2022-09-09T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","2 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung GE  Bf Regensburg Ost Gl. 2_ km 134,230 - 135,515 in Regensbg Ost",null,"N","2022-01-28T14:59:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,36,37,"2022-09-10T21:50:00","21:50:00","2022-09-18T05:10:00","05:10:00","15 h","periodical","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-08-25T12:48:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Obertraubling",2022,2022,36,38,"2022-09-10T22:00:00","22:00:00","2022-09-25T05:00:00","05:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten NOT-NROB Erneuerung Speisekabel Anbindung an OL",null,"N","2022-06-21T11:12:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Bbf","Regensburg Bbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2022-02-18T16:21:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,38,38,"2022-09-24T21:50:00","21:50:00","2022-09-25T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2021-08-25T13:16:00"]
[null,80]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Ost","Regensburg Ost",2022,2022,41,42,"2022-10-14T22:00:00","22:00:00","2022-10-23T04:00:00","04:00:00","8 d, 06 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleiserneuerung Obertraubling Gl 3 mit OL Anpassung in Obertraubling",null,"N","2022-03-14T09:59:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Obertraubling","Obertraubling",2022,2022,41,42,"2022-10-14T23:00:00","23:00:00","2022-10-23T04:00:00","04:00:00","8 d, 05 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Obertraubling Gl 3 in Obertraubling",null,"N","2022-03-14T10:00:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,42,44,"2022-10-21T22:00:00","22:00:00","2022-10-31T05:00:00","05:00:00","9 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T11:15:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Regensburg Hbf","Obertraubling",2022,2022,42,42,"2022-10-22T21:50:00","21:50:00","2022-10-23T05:10:00","05:10:00","7 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Erneuerung SÜ A3 Burgweinting in Regensbg Ost",null,"N","2022-03-24T08:29:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,44,45,"2022-11-04T22:00:00","22:00:00","2022-11-07T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T11:16:00"]
[null,80,"Nürnberg Hbf - Passau Grenze","< >","Sünching","Sünching",2022,2022,45,46,"2022-11-11T22:00:00","22:00:00","2022-11-14T05:00:00","05:00:00","2 d, 07 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"Bahnsteigarbeiten Sünching, (Zip) - Neubau Mittelbahnsteig Gl. 2/3 mit PU, Verziehung Gleis 3",null,"N","2021-08-20T11:17:00"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Nür Jansenbr","Unterfarrnb Abzw",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-23"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Hohe Marter","Fürth (Bay) Hbf",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Nür-Muggenhof Streckenwechsel 5923/5912 - Fürth (Bay) Hbf Gbf, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<>","Nür Jansenbr","Fürth (Bay) Gbf",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Nür-Muggenhof Streckenwechsel 5923/5912 - Fürth (Bay) Hbf Gbf, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Hohe Marter","Fürth (Bay) Hbf",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Nür Jansenbr","Unterfarrnb Abzw",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-23"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<>","Nür Jansenbr","Fürth (Bay) Gbf",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2022,2023,49,5,"2022-12-11","00:00:00","2023-02-05","19:00:00","56d, 19h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2022,2023,49,25,"2022-12-11","00:00:00","2023-06-25","19:00:00","196d, 18h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2022,2023,49,27,"2022-12-11","00:00:00","2023-07-09","19:00:00","210d, 18h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Treuchtlingen - Nürnberg Hbf, W 44","<","Nürnberg Hbf","Treuchtlingen",2022,2023,50,48,"2022-12-17","22:00:00","2023-12-03","06:00:00","350d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-12-17"]
[null,80,"Obertraubling - München Hbf","< >","Oberschleißheim","Neufahrn (b Freising)",2022,2022,34,34,"2022-08-26T20:40:00","20:40:00","2022-08-27T04:00:00","04:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA Lohhof, Km 23,735 in Lohhof",null,"N","2021-06-29T08:05:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Moosburg",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2020-05-26T13:12:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,34,36,"2022-08-28T22:00:00","22:00:00","2022-09-11T05:00:00","05:00:00","13 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2020-05-26T13:16:00"]
[null,80,"Obertraubling - München Hbf","< >","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,35,37,"2022-08-29T08:00:00","08:00:00","2022-09-14T18:00:00","18:00:00","16 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-19T16:38:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,35,36,"2022-08-30T01:00:00","01:00:00","2022-09-06T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-04-27T06:52:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,36,37,"2022-09-07T01:00:00","01:00:00","2022-09-14T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-26T11:28:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,36,37,"2022-09-07T01:00:00","01:00:00","2022-09-14T05:00:00","05:00:00","7 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2020-05-26T11:28:00"]
[null,80,"Obertraubling - München Hbf",">","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-10-31T04:50:00","04:50:00","2 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 5 u. 25 in Neufahrn/Nbay",null,"N","2020-07-03T12:00:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,28,35,"2022-07-16T08:00:00","08:00:00","2022-09-01T19:00:00","19:00:00","47 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS GA/PSS/WE Dingolfing",null,"N","2021-07-09T13:59:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,20,34,"2022-05-16T08:00:00","08:00:00","2022-08-26T16:00:00","16:00:00","102 d, 08 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau Überleitstelle Bruckbergau",null,"N","2021-10-26T09:49:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,28,35,"2022-07-16T08:00:00","08:00:00","2022-09-01T19:00:00","19:00:00","47 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS GA/PSS/WE Dingolfing",null,"N","2021-07-09T13:59:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,28,35,"2022-07-16T08:00:00","08:00:00","2022-09-01T19:00:00","19:00:00","47 d, 11 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS GA/PSS/WE Dingolfing",null,"N","2021-12-16T09:47:00"]
[null,80,"Obertraubling - München Hbf","< >","Oberschleißheim","Neufahrn (b Freising)",2022,2022,34,34,"2022-08-26T20:40:00","20:40:00","2022-08-27T04:00:00","04:00:00","7 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA Lohhof, Km 23,735 in Lohhof",null,"N","2021-06-29T08:05:00"]
[null,80,"Obertraubling - München Hbf","< >","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,35,36,"2022-08-29T08:00:00","08:00:00","2022-09-07T18:00:00","18:00:00","9 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-07T08:15:00"]
[null,80,"Obertraubling - München Hbf","< >","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,35,36,"2022-08-29T08:00:00","08:00:00","2022-09-07T18:00:00","18:00:00","9 d, 10 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-07T08:15:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,35,35,"2022-08-30T01:00:00","01:00:00","2022-09-02T05:00:00","05:00:00","3 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-03T12:51:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Moosburg",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-08T04:40:00","04:40:00","5 d, 07 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2022-02-03T09:23:00"]
[null,80,"Obertraubling - München Hbf",">","Landshut (Bay) Hbf","Landshut (Bay) Hbf",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-08T04:40:00","04:40:00","5 d, 07 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR GE Landshut - Moosburg km 73,310-69,910",null,"N","2022-01-27T11:23:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,35,36,"2022-09-03T01:00:00","01:00:00","2022-09-06T05:00:00","05:00:00","3 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-03T14:02:00"]
[null,80,"Obertraubling - München Hbf","< >","Eggmühl","Eggmühl",2022,2022,35,36,"2022-09-03T01:00:00","01:00:00","2022-09-06T05:00:00","05:00:00","3 d, 04 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 2 und 3 Eggmühl",null,"N","2022-02-03T14:02:00"]
[null,80,"Obertraubling - München Hbf","< >","Neufahrn (b Freising) Nord","Lohhof",2022,2022,41,42,"2022-10-14T22:20:00","22:20:00","2022-10-17T04:00:00","04:00:00","2 d, 06 h","continuous","Bridge","T",null,null,null,null,null,null,null,null,null,"Brückenarbeiten Abbruch SÜ Kurt-Kittel-Ring in Neufahrn b Frei",null,"N","2022-03-11T10:22:00"]
[null,80,"Obertraubling - München Hbf","< >","München-Moosach","München-Moosach",2022,2022,42,43,"2022-10-21T22:40:00","22:40:00","2022-10-24T04:40:00","04:40:00","2 d, 06 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Neubau 2.SBSS Bauweichen Hirschgarten",null,"N","2021-07-26T14:18:00"]
[null,80,"Obertraubling - München Hbf","< >","München-Moosach","München-Moosach",2022,2022,42,43,"2022-10-21T23:00:00","23:00:00","2022-10-24T05:00:00","05:00:00","2 d, 06 h","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"Planbare kleine Instandhaltung IH-Korridor Stammstrecke in Mü Donnersbgbr",null,"N","2021-11-16T10:07:00"]
[null,80,"Obertraubling - München Hbf",">","Neufahrn (Niederbay)","Neufahrn (Niederbay)",2022,2022,43,44,"2022-10-28T22:00:00","22:00:00","2022-10-31T04:50:00","04:50:00","2 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 5 u. 25 in Neufahrn/Nbay",null,"N","2022-03-25T08:29:00"]
[null,80,"Obertraubling - München Hbf",">","München-Moosach","München Hbf",2022,2022,44,45,"2022-11-04T23:30:00","23:30:00","2022-11-07T05:00:00","05:00:00","2 d, 06 h","continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Brückenarbeiten Hilfsbrücke für UVR Laim",null,"N","2022-03-15T09:35:00"]
[null,80]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,34,"2022-02-14T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","193 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,34,"2022-02-14T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","193 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,7,44,"2022-02-14T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","259 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2021-07-26T12:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,34,"2022-02-01T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","206 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,34,"2022-02-01T06:00:00","06:00:00","2022-08-26T23:00:00","23:00:00","206 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,44,"2022-02-01T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","272 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:26:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,44,"2022-02-01T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","272 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,44,"2022-02-01T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","272 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,5,44,"2022-02-01T06:00:00","06:00:00","2022-10-31T23:00:00","23:00:00","272 d, 17 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Gleis 331-338 in Mü Nord Rbf Mi Bft",null,"N","2022-01-17T11:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,22,49,"2022-05-30T06:00:00","06:00:00","2022-12-10T23:59:00","23:59:00","194 d, 18 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE RiGruppe 4 Gleis 341 - 348 in Mü Nord Rbf Mi Bft",null,"N","2022-05-02T09:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,22,49,"2022-05-30T06:00:00","06:00:00","2022-12-10T23:59:00","23:59:00","194 d, 18 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Ri-Gruppe 4 Gleis 341 - 348 in Mü Nord Rbf Mi Bft",null,"N","2022-05-02T09:37:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,33,34,"2022-08-19T06:00:00","06:00:00","2022-08-26T16:00:00","16:00:00","7 d, 10 h","continuous","Miscellaneous",null,null,null,"P",null,null,null,null,null,null,"sonstige Arbeiten Ern. Whz 1 - 3 in Mü-Johanneskir",null,"N","2021-11-28T16:16:00"]
[null,80,"Olching - München-Waldtrudering",">","Olching","München Nord Rbf Forstweg",2022,2022,33,34,"2022-08-19T23:00:00","23:00:00","2022-08-22T04:30:00","04:30:00","2 d, 05 h","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Gleiserneuerung Gleis 3 Logistik in Olching",null,"N","2022-01-25T11:40:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,34,35,"2022-08-26T08:00:00","08:00:00","2022-08-29T08:00:00","08:00:00","3 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Schienenerneuerung Tunnelabschnitte",null,"N","2022-01-31T14:01:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,34,44,"2022-08-26T23:00:00","23:00:00","2022-10-31T23:00:00","23:00:00","66 d","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Ri-Gruppe 4 Gleis 341 - 348 in Mü Nord Rbf Mi Bft",null,"N","2022-05-02T09:37:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,34,41,"2022-08-27T04:00:00","04:00:00","2022-10-16T04:00:00","04:00:00","50 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-27T16:39:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Forstweg",2022,2022,35,38,"2022-08-29T22:00:00","22:00:00","2022-09-21T23:59:00","23:59:00","23 d, 02 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA in Mü Nord Rbf For Bft",null,"N","2022-01-26T10:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Freimann",2022,2022,35,41,"2022-09-02","00:00:00","2022-10-14","00:00:00","42 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-27T16:39:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Freimann",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-05T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2022-01-12T12:38:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","9 d, 05 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-28T10:09:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","4 d, 10 h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-28T10:05:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,35,36,"2022-09-03T20:00:00","20:00:00","2022-09-05T04:00:00","04:00:00","16 h","periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Ern. Whz 1 - 3 in Mü-Johanneskir",null,"N","2021-12-02T10:46:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T21:00:00","21:00:00","4 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2022-01-12T12:38:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T23:00:00","23:00:00","4 d, 19 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-28T10:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,36,37,"2022-09-09T22:00:00","22:00:00","2022-09-12T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2022-01-12T12:56:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,34,41,"2022-08-27T04:00:00","04:00:00","2022-10-16T04:00:00","04:00:00","50 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Forstweg",2022,2022,35,38,"2022-08-29T22:00:00","22:00:00","2022-09-21T23:59:00","23:59:00","23 d, 02 h","continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA in Mü Nord Rbf For Bft",null,"N","2020-07-15T09:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Freimann",2022,2022,35,41,"2022-09-02","00:00:00","2022-10-14","00:00:00","42 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Freimann",2022,2022,35,36,"2022-09-02T22:00:00","22:00:00","2022-09-05T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T16:36:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","9 d, 05 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-09T16:40:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,35,37,"2022-09-02T23:00:00","23:00:00","2022-09-12T04:00:00","04:00:00","4 d, 10 h","periodical","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T15:59:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T21:00:00","21:00:00","4 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T16:36:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,36,36,"2022-09-05T04:00:00","04:00:00","2022-09-09T23:00:00","23:00:00","4 d, 19 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T16:34:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,36,37,"2022-09-09T22:00:00","22:00:00","2022-09-12T04:00:00","04:00:00","2 d, 06 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2020-06-07T13:45:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,37,37,"2022-09-12T04:00:00","04:00:00","2022-09-17T04:00:00","04:00:00","5 d","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-04T16:34:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,37,41,"2022-09-12T04:00:00","04:00:00","2022-10-14T04:00:00","04:00:00","32 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,37,37,"2022-09-16T22:00:00","22:00:00","2022-09-17T06:00:00","06:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2021-03-16T17:13:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,39,40,"2022-09-26T04:00:00","04:00:00","2022-10-03T04:00:00","04:00:00","7 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-02-12T14:14:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Freimann",2022,2022,40,40,"2022-10-04","00:00:00","2022-10-08T22:00:00","22:00:00","4 d, 22 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T09:12:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Freimann",2022,2022,40,41,"2022-10-08T22:00:00","22:00:00","2022-10-14T04:00:00","04:00:00","5 d, 06 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T09:18:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,40,41,"2022-10-09T14:00:00","14:00:00","2022-10-11T04:00:00","04:00:00","1 d, 14 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,41,42,"2022-10-10T21:00:00","21:00:00","2022-10-21T04:00:00","04:00:00","2 d, 08 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,42,43,"2022-10-19T08:00:00","08:00:00","2022-10-25T08:00:00","08:00:00","6 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE W1-4 in Mü Isartor",null,"N","2020-06-22T14:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,43,43,"2022-10-24T21:00:00","21:00:00","2022-10-28T04:00:00","04:00:00","1 d, 04 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:20:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,44,46,"2022-11-04T21:00:00","21:00:00","2022-11-14T04:00:00","04:00:00","4 d, 14 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:30:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,45,45,"2022-11-07T04:00:00","04:00:00","2022-11-07T21:00:00","21:00:00","17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,45,45,"2022-11-08T21:00:00","21:00:00","2022-11-11T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-06-07T16:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,46,46,"2022-11-14T04:00:00","04:00:00","2022-11-15T20:00:00","20:00:00","1 d, 16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-16T21:00:00","21:00:00","2022-11-17T04:00:00","04:00:00","7 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:44:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,46,46,"2022-11-17T04:00:00","04:00:00","2022-11-18T14:00:00","14:00:00","1 d, 10 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:52:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,47,"2022-11-18T21:00:00","21:00:00","2022-11-21T04:00:00","04:00:00","2 d, 07 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T09:52:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T21:00:00","21:00:00","2 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:08:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,47,47,"2022-11-23T21:00:00","21:00:00","2022-11-25T04:00:00","04:00:00","1 d, 07 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:32:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Freimann","München-Daglfing",2022,2022,47,47,"2022-11-25T21:00:00","21:00:00","2022-11-27T13:00:00","13:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:32:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,47,48,"2022-11-27T20:00:00","20:00:00","2022-11-28T21:00:00","21:00:00","1 d, 01 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2021-03-18T10:46:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T08:00:00","08:00:00","2022-12-04T16:00:00","16:00:00","2 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T10:05:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T10:00:00","10:00:00","2022-12-03T20:00:00","20:00:00","1 d, 10 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T11:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,48,49,"2022-12-02T21:00:00","21:00:00","2022-12-05T19:00:00","19:00:00","2 d, 22 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-04-27T06:53:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T22:00:00","22:00:00","2022-12-03T04:00:00","04:00:00","6 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2021-03-10T11:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,49,49,"2022-12-09T21:00:00","21:00:00","2022-12-10T23:59:00","23:59:00","1 d, 03 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2020-04-27T06:53:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,37,37,"2022-09-12T04:00:00","04:00:00","2022-09-17T04:00:00","04:00:00","5 d","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-28T10:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,37,41,"2022-09-12T04:00:00","04:00:00","2022-10-14T04:00:00","04:00:00","32 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-27T16:39:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,37,37,"2022-09-16T22:00:00","22:00:00","2022-09-17T06:00:00","06:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MJK und MDFG - 1",null,"N","2022-01-13T08:57:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,39,40,"2022-09-26T04:00:00","04:00:00","2022-10-03T04:00:00","04:00:00","7 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-01-27T16:39:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,39,39,"2022-10-02T00:45:00","00:45:00","2022-10-02T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T06:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,39,39,"2022-10-02T06:00:00","06:00:00","2022-10-02T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T06:30:00"]
[null,80,"Olching - München-Waldtrudering","< >","Olching","München Nord Rbf Forstweg",2022,2022,39,39,"2022-10-02T06:00:00","06:00:00","2022-10-02T12:00:00","12:00:00","6 h","periodical","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen HOA in Mü Nord Rbf For Bft",null,"N","2022-06-09T07:39:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Johanneskirchen","München-Freimann",2022,2022,40,40,"2022-10-04","00:00:00","2022-10-08T22:00:00","22:00:00","4 d, 22 h","continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-02-21T11:44:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Daglfing",2022,2022,40,40,"2022-10-04T21:00:00","21:00:00","2022-10-07T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-10T09:26:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Freimann",2022,2022,40,41,"2022-10-08T22:00:00","22:00:00","2022-10-14T04:00:00","04:00:00","5 d, 06 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-02-22T11:25:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,40,41,"2022-10-09T14:00:00","14:00:00","2022-10-11T04:00:00","04:00:00","1 d, 14 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-14T08:52:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,41,42,"2022-10-10T21:00:00","21:00:00","2022-10-21T04:00:00","04:00:00","2 d, 08 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-14T08:52:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Daglfing",2022,2022,41,42,"2022-10-10T21:00:00","21:00:00","2022-10-21T04:00:00","04:00:00","2 d, 08 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-14T08:52:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,41,41,"2022-10-16T00:45:00","00:45:00","2022-10-16T21:00:00","21:00:00","20 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T06:45:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,41,41,"2022-10-16T06:00:00","06:00:00","2022-10-16T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T06:46:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Trudering","München-Trudering",2022,2022,42,43,"2022-10-19T08:00:00","08:00:00","2022-10-25T08:00:00","08:00:00","6 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung WE W1-4 in Mü Isartor",null,"N","2020-06-22T14:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,43,43,"2022-10-24T21:00:00","21:00:00","2022-10-28T04:00:00","04:00:00","1 d, 04 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-14T09:05:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Daglfing",2022,2022,43,43,"2022-10-24T21:00:00","21:00:00","2022-10-28T04:00:00","04:00:00","1 d, 04 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-14T09:05:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,44,49,"2022-10-31T23:00:00","23:00:00","2022-12-10T23:59:00","23:59:00","40 d, 01 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Ri-Gruppe 4 Gleis 341 - 348 in Mü Nord Rbf Mi Bft",null,"N","2022-05-02T09:37:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Mitte","München Nord Rbf Mitte",2022,2022,44,49,"2022-10-31T23:00:00","23:00:00","2022-12-10T23:59:00","23:59:00","40 d, 01 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR, PSS und TE Ri-Gruppe 4 Gleis 341 - 348 in Mü Nord Rbf Mi Bft",null,"N","2022-05-02T09:37:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,44,46,"2022-11-04T21:00:00","21:00:00","2022-11-14T04:00:00","04:00:00","4 d, 14 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-05-16T09:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Daglfing",2022,2022,44,46,"2022-11-04T21:00:00","21:00:00","2022-11-14T04:00:00","04:00:00","4 d, 14 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-05-16T09:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Lassallestraße","München-Johanneskirchen",2022,2022,44,45,"2022-11-06T00:45:00","00:45:00","2022-11-09T15:00:00","15:00:00","3 d, 14 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T07:42:00"]
[null,80,"Olching - München-Waldtrudering","< >","München Nord Rbf Forstweg","München Nord Rbf Lassallestraße",2022,2022,44,44,"2022-11-06T06:00:00","06:00:00","2022-11-06T12:00:00","12:00:00","6 h","continuous","Signal","T",null,null,null,null,null,null,null,null,null,"Arbeiten an LST-Anlagen Neubau ESTW Milbertshofen / Freimann",null,"N","2021-10-22T07:38:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,45,45,"2022-11-07T04:00:00","04:00:00","2022-11-08T21:00:00","21:00:00","1 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-05-16T09:06:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Trudering",2022,2022,45,45,"2022-11-08T21:00:00","21:00:00","2022-11-11T04:00:00","04:00:00","21 h","periodical","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-24T11:08:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,46,46,"2022-11-14T04:00:00","04:00:00","2022-11-15T20:00:00","20:00:00","1 d, 16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-25T12:19:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,46,"2022-11-16T21:00:00","21:00:00","2022-11-17T04:00:00","04:00:00","7 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-02-25T12:19:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,46,46,"2022-11-17T04:00:00","04:00:00","2022-11-18T14:00:00","14:00:00","1 d, 10 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-07T09:29:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,46,47,"2022-11-18T21:00:00","21:00:00","2022-11-21T04:00:00","04:00:00","2 d, 07 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-07T09:29:00"]
[null,80,"Olching - München-Waldtrudering","<","München-Daglfing","München-Johanneskirchen",2022,2022,47,47,"2022-11-21T04:00:00","04:00:00","2022-11-23T21:00:00","21:00:00","2 d, 17 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-07T10:51:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Johanneskirchen","München-Daglfing",2022,2022,47,47,"2022-11-23T21:00:00","21:00:00","2022-11-25T04:00:00","04:00:00","1 d, 07 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-12T10:03:00"]
[null,80,"Olching - München-Waldtrudering",">","München-Freimann","München-Daglfing",2022,2022,47,47,"2022-11-25T21:00:00","21:00:00","2022-11-27T13:00:00","13:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-12T10:03:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Trudering",2022,2022,47,47,"2022-11-27T13:00:00","13:00:00","2022-11-27T20:00:00","20:00:00","7 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-12T10:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,47,48,"2022-11-27T20:00:00","20:00:00","2022-11-28T21:00:00","21:00:00","1 d, 01 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-03-12T10:25:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T08:00:00","08:00:00","2022-12-04T16:00:00","16:00:00","2 d, 08 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-04-12T10:16:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Johanneskirchen","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T10:00:00","10:00:00","2022-12-03T20:00:00","20:00:00","1 d, 10 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-04-12T10:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Daglfing","München-Trudering",2022,2022,48,49,"2022-12-02T21:00:00","21:00:00","2022-12-05T19:00:00","19:00:00","2 d, 22 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-04-13T12:14:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Johanneskirchen",2022,2022,48,48,"2022-12-02T22:00:00","22:00:00","2022-12-03T04:00:00","04:00:00","6 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS WE, GE, Rü Bf Johanneskirchen",null,"N","2022-04-12T10:10:00"]
[null,80,"Olching - München-Waldtrudering","< >","München-Freimann","München-Daglfing",2022,2022,49,49,"2022-12-09T21:00:00","21:00:00","2022-12-10T23:59:00","23:59:00","1 d, 03 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Erneuerung der OL zw. MDGF un MJK - 2",null,"N","2022-04-13T12:26:00"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","Mü Landsbger Str","Mü Landsbger Str",2022,2023,49,49,"2022-12-11","00:00:00","2023-12-09","23:59:00","363d, 23h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,"80","N","2022-05-16"]
[null,80,"München-Pasing, W 11W302 - Bft Mü Friedenheimer Brücke Abzw, 17W705","<>","Mü Landsbger Str","Mü Landsbger Str",2022,2023,49,49,"2022-12-11","00:00:00","2023-12-09","23:59:00","363d, 23h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Augsburg Hbf",">","München Hbf","München-Pasing",2022,2023,49,48,"2022-12-11","00:00:00","2023-12-01","22:50:00","355d, 22h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","Mü-Neuhausen","München-Pasing",2022,2023,49,44,"2022-12-11","00:00:00","2023-11-03","15:50:00","327d, 15h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2022-06-21"]
[null,80,"München Hbf - Augsburg Hbf","<","München-Pasing","München Hbf",2022,2023,49,48,"2022-12-11","00:00:00","2023-12-01","22:50:00","355d, 22h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<","München-Pasing","Mü-Neuhausen",2022,2023,49,44,"2022-12-11","00:00:00","2023-11-03","15:50:00","327d, 15h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2022-06-21"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,32,41,"2022-08-13T06:00:00","06:00:00","2022-10-16T22:00:00","22:00:00","64 d, 16 h","continuous","Catenary",null,null,null,"P",null,null,null,null,null,null,"Oberleitungsarbeiten Aufbau FA, Gründungsarbeiten",null,"N","2020-09-22T11:27:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,33,35,"2022-08-21T06:00:00","06:00:00","2022-09-04T22:00:00","22:00:00","2 d","periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-22T11:44:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,36,36,"2022-09-11T06:00:00","06:00:00","2022-09-11T22:00:00","22:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-22T12:03:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,38,39,"2022-09-24T14:00:00","14:00:00","2022-09-26T14:00:00","14:00:00","2 d","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:19:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,39,39,"2022-10-01T14:00:00","14:00:00","2022-10-02T06:00:00","06:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:19:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,39,39,"2022-10-02T14:00:00","14:00:00","2022-10-02T22:00:00","22:00:00","8 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:48:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,39,40,"2022-10-02T22:00:00","22:00:00","2022-10-03T14:00:00","14:00:00","16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Stellen von Masten",null,"N","2020-09-22T13:48:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,40,41,"2022-10-08T14:00:00","14:00:00","2022-10-10T14:00:00","14:00:00","2 d","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-23T13:59:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,40,40,"2022-10-09T06:00:00","06:00:00","2022-10-09T22:00:00","22:00:00","16 h","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Gründungsarbeiten",null,"N","2020-09-23T13:59:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","<","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,41,41,"2022-10-14T14:00:00","14:00:00","2022-10-16T06:00:00","06:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg Rbf Einfahrt","Nürnberg Rbf Einfahrt",2022,2022,41,41,"2022-10-16T06:00:00","06:00:00","2022-10-16T22:00:00","22:00:00","16 h","continuous","Catenary",null,"ST",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Rbf Einfahrt",2022,2022,41,42,"2022-10-16T06:00:00","06:00:00","2022-10-17T14:00:00","14:00:00","1 d, 08 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald",">","Nürnberg Rbf Einfahrt","Nürnberg-Langwasser",2022,2022,41,42,"2022-10-16T06:00:00","06:00:00","2022-10-17T22:00:00","22:00:00","1 d, 16 h","continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Rück-und Neubau Kettenwerk",null,"N","2020-09-22T14:28:00"]
[null,80,"Fürth (Bay) Gbf - Nürnberg Reichswald","< >","Nürnberg-Langwasser","Nürnberg Reichswald",2022,2022,49,49,"2022-12-05T06:00:00","06:00:00","2022-12-05T22:00:00","22:00:00","16 h","continuous","Catenary","T",null,null,null,null,null,null,null,null,null,"Oberleitungsarbeiten Kettenwerk ziehen u. Abnahme",null,"N","2021-05-19T16:00:00"]
[null,80,"Fürth (Bay) Hbf, W 144 - Cadolzburg","<>","Zirndorf","Fürth (Bay) Hbf",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Fürth (Bay) Hbf, W 144 - Cadolzburg","<>","Zirndorf","Fürth (Bay) Hbf",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth-Burgfbach","Fürth (Bay) Hbf",2022,2022,49,49,"2022-12-11","00:40:00","2022-12-11","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth-Burgfbach","Fürth (Bay) Hbf",2022,2022,50,50,"2022-12-12","00:40:00","2022-12-12","04:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-17"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Hirschaid","Hirschaid",2021,2022,49,49,"2021-12-12","00:00:00","2022-12-10T23:59:00","23:59:00","364 d","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gleis 3 (Anm. Tem-005) in Hirschaid",null,"N","2021-05-17T11:45:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Bamberg","Bamberg",2022,2022,48,49,"2022-12-01T07:00:00","07:00:00","2022-12-10T23:59:00","23:59:00","9 d, 17 h","continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sonstige Arbeiten Rückbau Gla Mälzerei in Bamberg",null,"N","2020-06-02T13:00:00"]
[null,80,"Saaleck - Fürth (Bay) Hbf","< >","Forchheim (Oberfr)","Bamberg",2022,2022,48,48,"2022-12-03T22:45:00","22:45:00","2022-12-04T08:30:00","08:30:00","10 h","continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"sonstige Arbeiten Rie-IB2022 Mos-104 VDE 8.1.1 PA21 Erneuerung SÜ B505 km 55,504_ PA19 OLA-Arbeiten, Verbau EÜ BAB A73 km 41,686",null,"N","2020-06-25T13:05:00"]
[null,80,"Marktredwitz - Regensburg Hbf","< >","Regensburg Hbf","Regensburg Hbf",2022,2022,37,38,"2022-09-16T22:00:00","22:00:00","2022-09-21T05:00:00","05:00:00","4 d, 07 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung Weiche 60, 61 u. 69 in Regensburg Hbf",null,"N","2020-06-09T10:57:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Cham (Oberpf)",2022,2022,38,43,"2022-09-19T06:00:00","06:00:00","2022-10-28T18:00:00","18:00:00","39 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Schwandorf","Schwandorf",2022,2022,38,43,"2022-09-22T06:00:00","06:00:00","2022-10-26T18:00:00","18:00:00","34 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Kothmaißling",2022,2022,39,43,"2022-09-26T06:00:00","06:00:00","2022-10-24T06:00:00","06:00:00","28 d","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11",null,"N","2020-08-18T14:02:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Arnschwang","Furth im Wald",2022,2022,42,42,"2022-10-22T22:00:00","22:00:00","2022-10-23T06:00:00","06:00:00","8 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13",null,"N","2020-08-18T11:55:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Cham (Oberpf)",2022,2022,38,43,"2022-09-19T06:00:00","06:00:00","2022-10-28T18:00:00","18:00:00","39 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11 in Cham (Oberpf)",null,"N","2022-03-09T15:39:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Schwandorf","Schwandorf",2022,2022,38,43,"2022-09-22T06:00:00","06:00:00","2022-10-26T18:00:00","18:00:00","34 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11 in Cham (Oberpf)",null,"N","2022-03-09T15:39:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Kothmaißling",2022,2022,39,43,"2022-09-26T06:00:00","06:00:00","2022-10-24T05:45:00","05:45:00","28 d","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11 in Cham (Oberpf)",null,"N","2022-03-09T15:39:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Cham (Oberpf)",2022,2022,39,43,"2022-09-26T06:00:00","06:00:00","2022-10-24T18:00:00","18:00:00","28 d, 12 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11 in Cham (Oberpf)",null,"N","2022-03-09T16:17:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Cham (Oberpf)","Cham (Oberpf)",2022,2022,41,43,"2022-10-13T06:00:00","06:00:00","2022-10-24T05:45:00","05:45:00","11 d","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenauswechslung GA Gl. 3+11, WA W11 + 44 + 47 + 70, RüLü Gl. 11 in Cham (Oberpf)",null,"N","2022-03-09T16:17:00"]
[null,80,"Schwandorf - Furth im Wald Grenze","< >","Arnschwang","Furth im Wald",2022,2022,42,42,"2022-10-22T22:05:00","22:05:00","2022-10-23T05:55:00","05:55:00","8 h","continuous","Switch","T",null,null,null,null,null,null,null,null,null,"Weichenerneuerung mit PSS Weichen 3, 6, 8, 9, 10, 12, 13_Belastungsstopfgang",null,"N","2022-03-24T14:17:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","4 d, 16 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2022-03-21T13:15:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","9 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2022-03-21T13:15:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,45,46,"2022-11-12T22:15:00","22:15:00","2022-11-14T06:00:00","06:00:00","1 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 zw W834+W835 in Karlsruhe Gbf",null,"N","2022-03-21T13:31:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,48,49,"2022-12-03T01:10:00","01:10:00","2022-12-05T07:00:00","07:00:00","2 d, 06 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W807 in Karlsruhe Gbf",null,"N","2022-03-21T13:57:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","4 d, 16 h","periodical","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2020-09-28T14:47:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,44,46,"2022-11-04T22:00:00","22:00:00","2022-11-14T06:00:00","06:00:00","9 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 in Karlsruhe Gbf",null,"N","2020-09-28T14:47:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,45,46,"2022-11-12T22:15:00","22:15:00","2022-11-14T06:00:00","06:00:00","1 d, 08 h","continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"Gleiserneuerung mit BR Gl 521 zw W834+W835 in Karlsruhe Gbf",null,"N","2020-09-28T14:57:00"]
[null,80,"Karlsruhe-Hagsfeld - Karlsruhe-Dammerstock","< >","Karlsruhe Gbf","Karlsruhe Gbf",2022,2022,48,49,"2022-12-03T01:10:00","01:10:00","2022-12-05T07:00:00","07:00:00","2 d, 06 h","continuous","Switch",null,"ST",null,null,null,null,null,null,null,null,"Weichenerneuerung W807 in Karlsruhe Gbf",null,"N","2020-09-28T16:35:00"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Würzburg Hbf","Gemünden (Main)",2022,2023,49,49,"2022-12-11","22:00:00","2023-12-04","05:00:00","357d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y","2021-06-04"]
[]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-07","04:30:00","6d, 7h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-03-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,"1,1,1",null,null,"80","N","2022-03-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,13,49,"2023-03-31","21:00:00","2023-12-09","23:59:00","253d, 3h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","Y","2021-06-01"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn","<>","Karlsruhe Gbf","Dammerstock",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-26"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-25"]
[null,80,"Karlsruhe Gbf, W 118 - Karlsruhe-Durlach , W 52","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-25"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-25"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn",">","Karlsruhe Gbf","Dammerstock",2023,2023,11,15,"2023-03-17","21:00:00","2023-04-14","21:00:00","27d, 23h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-06-04"]
[null,80,"Karlsruhe Gbf - Abzw Karlsruhe Brunnenstück, W 502, G-Bahn","<>","Karlsruhe Gbf","Dammerstock",2023,2023,13,14,"2023-04-01","09:00:00","2023-04-03","16:00:00","2d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-27"]
[null,80,"Mainz-Bischofsheim, W 6 - Darmstadt Hbf, W 314",">","Mz-Bisch Überl I","Darmstadt Gbf",2022,2023,50,48,"2022-12-17","23:50:00","2023-12-03","04:50:00","350d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,"80","Y","2022-04-07"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt-Süd","Achern",2023,2023,5,13,"2023-02-01","23:20:00","2023-03-31","05:48:00","57d, 5h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2022-03-29"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Achern (F)",2023,2023,13,22,"2023-04-01","23:20:00","2023-05-31","05:48:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2022-03-29"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2021-08-26"]
[null,80,"München Hbf - Augsburg Hbf",">","Olching","Mering Üst",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-28"]
[null,80,"Olching - Augsburg Hbf",">","Olching","Maisach Abzw",2023,2023,14,17,"2023-04-03","16:00:00","2023-04-30","05:00:00","26d, 13h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-28"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-26"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,10,13,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,14,17,"2023-04-04","09:00:00","2023-04-29","16:00:00","25d, 7h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-26"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,9,17,"2023-03-05","00:00:00","2023-04-30","05:00:00","56d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-26"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,9,9,"2023-03-03","09:00:00","2023-03-04","16:00:00","1d, 7h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2021-05-27"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023,2023,13,17,"2023-04-02","00:00:00","2023-04-30","05:00:00","28d, 5h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,",null,null,"80","N","2021-06-25"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023,2023,9,13,"2023-03-05","00:00:00","2023-04-02","05:00:00","28d, 4h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-06-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,13,14,"2023-04-02","05:00:00","2023-04-04","16:00:00","2d, 11h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-25"]
[null,80,"München Hbf - Augsburg Hbf","<","Mering Üst","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2021-05-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560",">","Olching","Mü Nord Rbf For",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,"80","N","2021-05-27"]
[null,80,"Olching - Augsburg Hbf","<","Maisach Abzw","Olching",2023,2023,10,13,"2023-03-06","16:00:00","2023-03-31","22:00:00","25d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-27"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Maisach Abzw",2023,2023,9,10,"2023-03-05","00:00:00","2023-03-06","16:00:00","1d, 16h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Mü Nord Rbf For",2023,2023,14,17,"2023-04-08","22:00:00","2023-04-24","16:00:00","15d, 18h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560",">","Olching","Mü Nord Rbf For",2023,2023,9,9,"2023-03-05","02:00:00","2023-03-05","05:00:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-08-30"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Nürnberg Hbf",2022,2023,49,49,"2022-12-11","23:00:00","2023-12-04","05:00:00","357d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-11-18"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2023,2023,9,49,"2023-03-01","06:00:00","2023-12-09","23:59:00","283d, 17h","continuous","Signal",null,null,"S",null,null,",,",",,",null,",4,",null,null,"80","Y","2021-06-01"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Achern","Baden-Baden",2023,2023,5,13,"2023-02-01","23:20:00","2023-03-31","05:48:00","57d, 5h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-04-11"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Baden-Baden","Achern (F)",2022,2023,49,5,"2022-12-11","23:20:00","2023-01-31","05:48:00","50d, 6h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2022-05-05"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Bashaide","Durmersheim",2023,2023,13,21,"2023-03-31","21:00:00","2023-05-27","06:00:00","56d, 9h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2022-03-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Forchheim/Karlsr",2023,2023,14,14,"2023-04-04","21:00:00","2023-04-07","04:30:00","2d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,13,14,"2023-03-31","21:00:00","2023-04-04","04:30:00","3d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,11,12,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Ebelsbach-Eltm",2023,2023,14,14,"2023-04-09","08:00:00","2023-04-09","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,10,10,"2023-03-07","22:00:00","2023-03-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,2,2,"2023-01-10","22:00:00","2023-01-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-09"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,6,6,"2023-02-07","22:00:00","2023-02-08","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-09"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Stuttgart Hbf - Plochingen","<","Stg-Obertürkheim","Neckarpark",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","04:00:00","2d, 3h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2021-06-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,14,14,"2023-04-03","03:00:00","2023-04-03","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,8,8,"2023-02-20","03:00:00","2023-02-20","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,9,10,"2023-03-05","22:00:00","2023-03-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,13,14,"2023-04-01","05:00:00","2023-04-08","21:00:00","7d, 16h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Oberhaid","Zeil",2023,2023,13,13,"2023-03-31","00:00:00","2023-03-31","04:00:00","0d, 4h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,9,9,"2023-02-27","22:50:00","2023-02-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,10,10,"2023-03-06","03:00:00","2023-03-06","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,11,11,"2023-03-13","22:50:00","2023-03-14","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,null,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023,2023,48,49,"2023-12-02","22:00:00","2023-12-09","05:00:00","6d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,null,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim-Rheinau",2023,2023,48,49,"2023-12-02","22:00:00","2023-12-09","06:00:00","6d, 8h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-07-23"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,14,14,"2023-04-03","22:50:00","2023-04-04","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,12,12,"2023-03-20","22:50:00","2023-03-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,11,12,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,5,6,"2023-02-05","22:00:00","2023-02-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,6,6,"2023-02-06","03:00:00","2023-02-06","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,10,10,"2023-03-06","23:20:00","2023-03-07","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Strullendorf","Bamberg",2023,2023,12,13,"2023-03-24","21:00:00","2023-03-31","21:00:00","6d, 23h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,12,12,"2023-03-20","23:30:00","2023-03-21","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,7,8,"2023-02-19","22:00:00","2023-02-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,7,8,"2023-02-19","22:00:00","2023-02-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,12,49,"2023-03-21","23:00:00","2023-12-06","05:00:00","259d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","Y","2022-04-10"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Pragtunnel","Kornwestheim Pbf",2023,2023,12,13,"2023-03-24","23:30:00","2023-03-27","04:40:00","2d, 4h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Pragtunnel","Kornwestheim Pbf",2023,2023,8,9,"2023-02-24","23:30:00","2023-02-27","04:40:00","2d, 5h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2021-06-07"]
[null,80,"Holzkirchen, W 23 - Rosenheim, 19W211","<>","Rosenheim","Bad Aibling",2023,2023,9,9,"2023-03-04","08:00:00","2023-03-04","18:00:00","0d, 10h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-22"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,8,8,"2023-02-20","23:30:00","2023-02-21","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Langenprozelten",2023,2023,9,12,"2023-03-04","08:00:00","2023-03-20","05:00:00","15d, 21h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,9,13,"2023-02-28","06:00:00","2023-03-29","18:00:00","29d, 11h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,9,9,"2023-03-01","20:00:00","2023-03-02","06:00:00","0d, 10h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Gemünden (Main)",2023,2023,9,10,"2023-03-04","23:30:00","2023-03-06","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Bft Gemünden Zollberg Abzw, W 291 - Langenprozelten, W 401, G-Bahn","<>","Zollberg","Langenprozelten",2023,2023,9,9,"2023-03-04","23:30:00","2023-03-05","01:00:00","0d, 1h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,9,9,"2023-03-01","23:00:00","2023-03-03","05:00:00","1d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<","Rohrbach","Lohr Bahnhof",2023,2023,9,9,"2023-03-01","23:00:00","2023-03-02","05:00:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Lohr Bahnhof",2023,2023,11,11,"2023-03-18","23:30:00","2023-03-19","03:30:00","0d, 4h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Lohr Bahnhof",2023,2023,11,11,"2023-03-18","23:30:00","2023-03-19","03:30:00","0d, 4h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Nantenbach","Rohrbach",2023,2023,9,9,"2023-03-04","20:00:00","2023-03-04","20:20:00","0d, 0h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,9,10,"2023-03-03","22:00:00","2023-03-06","12:00:00","2d, 14h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,9,10,"2023-03-04","08:00:00","2023-03-06","05:00:00","1d, 21h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<","Rohrbach","Lohr Bahnhof",2023,2023,9,10,"2023-03-04","08:00:00","2023-03-06","05:00:00","1d, 21h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Lohr Bahnhof",2023,2023,12,12,"2023-03-20","02:00:00","2023-03-20","04:00:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Lohr Bahnhof",2023,2023,12,12,"2023-03-20","02:00:00","2023-03-20","04:00:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Langenprozelten",2023,2023,11,12,"2023-03-18","23:30:00","2023-03-20","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Rohrbach",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Langenprozelten",2023,2023,9,11,"2023-03-04","08:00:00","2023-03-13","05:00:00","8d, 21h","periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2021-09-10"]
[null,80,"Bft Gemünden Zollberg Abzw, W 291 - Langenprozelten, W 401, G-Bahn","<>","Zollberg","Langenprozelten",2023,2023,10,10,"2023-03-06","02:30:00","2023-03-06","04:00:00","0d, 1h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,10,11,"2023-03-11","08:00:00","2023-03-13","05:00:00","1d, 21h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Nantenbach",2023,2023,9,10,"2023-03-04","08:00:00","2023-03-06","05:00:00","1d, 21h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Langenprozelten",2023,2023,10,11,"2023-03-11","23:30:00","2023-03-13","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Nantenbach",2023,2023,11,12,"2023-03-18","08:00:00","2023-03-20","05:00:00","1d, 21h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Lohr Bahnhof",2023,2023,12,13,"2023-03-25","08:00:00","2023-03-27","05:00:00","1d, 20h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,10,11,"2023-03-11","08:00:00","2023-03-13","05:00:00","1d, 21h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Rohrbach",2023,2023,12,13,"2023-03-25","08:00:00","2023-03-27","05:00:00","1d, 20h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Langenprozelten",2023,2023,12,13,"2023-03-25","08:00:00","2023-03-27","05:00:00","1d, 20h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-04"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Nantenbach","Rohrbach",2023,2023,9,9,"2023-03-04","21:00:00","2023-03-04","21:20:00","0d, 0h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Lohr Bahnhof",2023,2023,12,13,"2023-03-25","23:30:00","2023-03-27","04:30:00","1d, 4h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Langenprozelten",2023,2023,12,12,"2023-03-20","23:00:00","2023-03-21","05:00:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Lohr Bahnhof","Rohrbach",2023,2023,12,12,"2023-03-20","23:00:00","2023-03-21","05:00:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,9,13,"2023-03-03","18:00:00","2023-03-27","12:00:00","23d, 17h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Langenprozelten",2023,2023,9,9,"2023-03-02","22:00:00","2023-03-03","06:00:00","0d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-10"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,8,8,"2023-02-20","23:20:00","2023-02-21","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,12,12,"2023-03-20","03:00:00","2023-03-20","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,12,12,"2023-03-20","23:20:00","2023-03-21","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,11,11,"2023-03-14","00:40:00","2023-03-15","04:50:00","1d, 4h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2d, 2h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,11,11,"2023-03-13","04:00:00","2023-03-15","10:00:00","2d, 6h","continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2d, 2h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,14,14,"2023-04-03","23:30:00","2023-04-04","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,14,14,"2023-04-03","23:20:00","2023-04-04","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Nantenbach",2023,2023,9,10,"2023-03-03","22:00:00","2023-03-10","06:00:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-12"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Gemünden (Main)",2023,2023,9,10,"2023-03-03","22:00:00","2023-03-10","06:00:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-12"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Nantenbach","Aschaffenbg Hbf",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-17","06:00:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-25"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Nantenbach",2023,2023,10,11,"2023-03-10","22:00:00","2023-03-17","06:00:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-25"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,10,"2023-03-06","05:00:00","2023-03-08","10:00:00","2d, 5h","continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Ludwigsburg","Stg-Zuffenhausen",2023,2023,9,9,"2023-03-05","00:30:00","2023-03-05","04:10:00","0d, 3h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,9,9,"2023-03-03","01:30:00","2023-03-03","04:30:00","0d, 3h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,9,10,"2023-03-04","00:55:00","2023-03-06","05:00:00","2d, 4h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Stg-Zuffenhausen","Ludwigsburg",2023,2023,10,10,"2023-03-07","00:25:00","2023-03-08","04:00:00","1d, 3h","periodical continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,9,9,"2023-03-04","00:35:00","2023-03-04","05:00:00","0d, 4h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,10,11,"2023-03-10","23:00:00","2023-03-15","05:00:00","4d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-16"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,10,10,"2023-03-06","23:30:00","2023-03-07","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,7,7,"2023-02-13","22:50:00","2023-02-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,7,7,"2023-02-13","22:50:00","2023-02-14","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,7,7,"2023-02-13","22:50:00","2023-02-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-05","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,6,6,"2023-02-06","22:50:00","2023-02-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,6,6,"2023-02-06","22:50:00","2023-02-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,6,6,"2023-02-06","22:50:00","2023-02-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,13,13,"2023-03-27","22:50:00","2023-03-28","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,13,13,"2023-03-27","22:50:00","2023-03-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,13,13,"2023-03-27","22:50:00","2023-03-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,11,12,"2023-03-19","22:00:00","2023-03-20","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,6,6,"2023-02-06","23:20:00","2023-02-07","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart-Untertürkheim, W 45 - Kornwestheim Pbf, W 453","<>","Stg-Utürkhm Pbf","Stg-Zazenhausen",2023,2023,10,12,"2023-03-11","13:00:00","2023-03-20","05:00:00","8d, 16h","periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-10-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,10,10,"2023-03-06","22:50:00","2023-03-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,10,10,"2023-03-06","22:50:00","2023-03-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,10,10,"2023-03-06","22:50:00","2023-03-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,13,14,"2023-04-02","22:00:00","2023-04-03","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Oberhaid","Bamberg",2023,2023,13,16,"2023-03-30","00:00:00","2023-04-21","04:00:00","22d, 4h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-26"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Oberhaid","Höflein",2023,2023,13,15,"2023-03-31","22:00:00","2023-04-11","04:00:00","10d, 6h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-11-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Höflein","Oberhaid",2023,2023,13,15,"2023-03-31","22:00:00","2023-04-11","04:00:00","10d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-11-30"]
[null,80,"Abzw Hallstadt (b Bamberg), 31W102 - Abzw Höflein, W302","<>","Hallstadt(Bambg)","Höflein",2023,2023,13,15,"2023-04-01","00:00:00","2023-04-11","08:00:00","10d, 8h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-29"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,6,6,"2023-02-06","23:30:00","2023-02-07","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Nürnberg Hbf","Bamberg",2023,2023,11,12,"2023-03-17","22:00:00","2023-03-20","05:00:00","2d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-03-24"]
[null,80,"Mainz-Bischofsheim, W 6 - Darmstadt Hbf, W 314","<>","Mz-Bisch Überl I","Darmstadt Gbf",2023,2023,14,16,"2023-04-07","23:00:00","2023-04-21","05:00:00","13d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,"80","N","2021-12-03"]
[null,80,"Nürnberg Hbf - Fürth-Unterfarrnbach, 40W906, S-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,13,13,"2023-03-27","23:10:00","2023-03-31","04:30:00","3d, 5h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-11"]
[null,80,"Nürnberg Hbf - Fürth-Unterfarrnbach, 40W906, S-Bahn","<>","Nür Jansenbr","Fürth (Bay) Hbf",2023,2023,13,13,"2023-03-27","23:10:00","2023-03-31","04:30:00","3d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-11"]
[null,80,"Nürnberg Hbf - Fürth-Unterfarrnbach, 40W906, S-Bahn","<>","Nür Jansenbr","Fürth (Bay) Gbf",2023,2023,14,14,"2023-04-03","23:10:00","2023-04-07","04:30:00","3d, 5h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-11"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Radldorf (Nbay)","Straßkirchen",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-14","05:00:00","0d, 7h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,"80","N","2021-11-09"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Straubing","Straubing",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-14","05:00:00","0d, 7h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Straubing","Straubing",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-14","05:00:00","0d, 7h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,null,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Straubing","Straubing",2023,2023,11,11,"2023-03-13","22:00:00","2023-03-14","05:00:00","0d, 7h","continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Bamberg","Ebelsbach-Eltm",2023,2023,14,15,"2023-04-08","22:00:00","2023-04-10","04:00:00","1d, 6h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"12,,12",null,null,"80","N","2022-07-05"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Sünching",2023,2023,8,8,"2023-02-25","23:50:00","2023-02-26","00:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,"80","N","2022-05-04"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Geiselhöring",2023,2023,8,8,"2023-02-26","00:50:00","2023-02-26","01:50:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Sünching","Straubing",2023,2023,8,8,"2023-02-26","01:50:00","2023-02-26","06:15:00","0d, 4h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"20,20,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Radldorf (Nbay)","Sünching",2023,2023,8,8,"2023-02-26","03:00:00","2023-02-26","04:00:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Geiselhöring",2023,2023,8,8,"2023-02-26","04:00:00","2023-02-26","05:00:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Straubing","Radldorf (Nbay)",2023,2023,8,9,"2023-02-26","23:45:00","2023-02-27","00:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Sünching","Straubing",2023,2023,9,9,"2023-02-27","00:50:00","2023-02-27","04:50:00","0d, 4h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"20,,",null,null,"80","N","2022-01-21"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Radldorf (Nbay)",2023,2023,9,9,"2023-02-27","00:50:00","2023-02-27","04:50:00","0d, 4h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Geiselhöring",2023,2023,9,9,"2023-02-27","00:50:00","2023-02-27","04:20:00","0d, 3h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Straubing","Radldorf (Nbay)",2023,2023,9,9,"2023-02-27","02:50:00","2023-02-27","04:00:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-01-21"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Radldorf (Nbay)","Radldorf (Nbay)",2023,2023,8,9,"2023-02-26","23:45:00","2023-02-27","04:50:00","0d, 5h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Radldorf (Nbay)","Radldorf (Nbay)",2023,2023,8,8,"2023-02-25","23:50:00","2023-02-26","06:15:00","0d, 6h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-05-04"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,9,17,"2023-03-05","00:00:00","2023-04-30","05:00:00","56d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800",">","StrWe 4800/4842","Illingen (Württ)",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-05","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühlacker",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-05","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Frankfurt (Main) Süd - Frankfurt (Main) Ost - Aschaffenburg Hbf","<","Hanau Südseite","Aschaffenbg Hbf",2022,2023,49,49,"2022-12-11","23:30:00","2023-12-04","05:00:00","357d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,"80","N","2021-12-13"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Rottau",2023,2023,14,15,"2023-04-07","04:00:00","2023-04-11","06:00:00","4d, 2h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-05-07"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rumgraben","Rumgraben",2023,2023,14,14,"2023-04-06","00:00:00","2023-04-07","04:00:00","1d, 4h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-07"]
[null,80,"Traunstein, W 51 - Garching, 46W2","<>","Traunstein","Traunstein",2023,2023,14,48,"2023-04-03","08:00:00","2023-11-30","16:00:00","241d, 9h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-07"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Übersee",2023,2023,14,14,"2023-04-04","00:00:00","2023-04-05","04:00:00","1d, 4h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-07"]
[null,80,"Traunstein, W 51 - Garching, 46W2","<>","Traunstein","Traunstein",2023,2023,14,48,"2023-04-03","08:00:00","2023-11-30","16:00:00","241d, 9h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-07"]
[null,80,"Holzkirchen, W 23 - Rosenheim, 19W211","<>","Rosenheim","Kolbermoor",2023,2023,12,12,"2023-03-20","22:30:00","2023-03-22","04:55:00","1d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-27"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Regensbg-Prüfe","Beratzhausen",2022,2022,50,50,"2022-12-12","22:00:00","2022-12-14","04:20:00","1d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2022-05-12"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Regensbg-Prüfe","Beratzhausen",2022,2022,50,50,"2022-12-12","22:00:00","2022-12-14","04:20:00","1d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Bamberg - Hof Hbf, W 121","<>","Bamberg","Bad Staffelstein",2023,2023,12,12,"2023-03-26","00:00:00","2023-03-26","05:00:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-24"]
[null,80,"Abzw Hallstadt (b Bamberg), 31W102 - Abzw Höflein, W302","<>","Hallstadt(Bambg)","Höflein",2023,2023,12,12,"2023-03-26","00:00:00","2023-03-26","05:00:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-24"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Aschaffenbg Hbf","Laufach",2023,2023,12,12,"2023-03-22","23:40:00","2023-03-23","03:00:00","0d, 3h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Aschaffenbg Hbf",2023,2023,12,12,"2023-03-23","02:00:00","2023-03-23","03:00:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Wiesthal","Aburg-Goldbach",2023,2023,12,12,"2023-03-23","03:00:00","2023-03-23","04:30:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,12,12,"2023-03-22","23:40:00","2023-03-23","04:30:00","0d, 4h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Aschaffenbg Hbf","Laufach",2023,2023,12,12,"2023-03-23","23:40:00","2023-03-24","01:00:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Wiesthal","Aburg-Goldbach",2023,2023,12,12,"2023-03-24","01:00:00","2023-03-24","04:50:00","0d, 3h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aburg-Goldbach","Laufach",2023,2023,12,12,"2023-03-24","02:10:00","2023-03-24","03:30:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,12,12,"2023-03-23","23:40:00","2023-03-24","04:50:00","0d, 5h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-12-02"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Nür Minervabr","Fürth (Bay) Gbf",2023,2023,13,21,"2023-04-01","23:00:00","2023-05-24","06:00:00","52d, 7h","continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,13,14,"2023-04-02","21:00:00","2023-04-03","05:00:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,13,14,"2023-04-02","21:00:00","2023-04-03","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nür-Muggenhof Streckenwechsel 5923/5912 - Fürth (Bay) Hbf Gbf, G-Bahn","<>","Fürth (Bay) Gbf","Muggenhof Strw",2023,2023,13,14,"2023-04-02","21:00:00","2023-04-03","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-09-22"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,13,14,"2023-04-02","21:00:00","2023-04-03","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,14,14,"2023-04-03","00:00:00","2023-04-03","04:00:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,14,14,"2023-04-03","00:00:00","2023-04-03","04:00:00","0d, 4h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Nür Großmarkt",2023,2023,14,14,"2023-04-07","23:00:00","2023-04-08","05:00:00","0d, 6h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Nür Rbf Ausfahrt","Fürth (Bay) Gbf",2023,2023,14,14,"2023-04-09","21:00:00","2023-04-09","23:00:00","0d, 2h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"20,,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Hohe Marter",2023,2023,14,15,"2023-04-09","23:00:00","2023-04-10","03:00:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Nürnberg Hbf - Schirnding Grenze","<>","Marktredwitz","Schirnding Grenz",2023,2023,12,12,"2023-03-22","20:00:00","2023-03-24","06:00:00","1d, 10h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54","N","2021-09-30"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","N-Edingen/F-feld",2023,2023,13,14,"2023-04-01","23:00:00","2023-04-06","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,"80","N","2021-04-29"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Kar Hbf Südeinf","Bashaide",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-07","05:00:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-04-29"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Kar Hbf Südeinf","Ötigheim",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-07","05:00:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,"80","N","2022-04-19"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-07","05:00:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-19"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","N-Edingen/F-feld",2023,2023,7,8,"2023-02-19","23:00:00","2023-02-26","05:00:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-12-14"]
[null,80,"Backnang, W 69 - Ludwigsburg, W 64","<>","Benningen (N)","Ludwigsburg",2023,2023,13,14,"2023-03-29","22:00:00","2023-04-07","04:55:00","8d, 6h","periodical continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-02-24"]
[null,80,"München Hbf - Rosenheim","<>","Rosenheim","Gr-Karolinenf  Ü",2023,2023,13,14,"2023-04-01","22:45:00","2023-04-04","05:40:00","2d, 6h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<>","Gr-Karolinenf  Ü","Rosenheim",2023,2023,13,14,"2023-04-01","22:45:00","2023-04-04","05:20:00","2d, 6h","periodical continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<>","Gr-Karolinenf  Ü","Rosenheim",2023,2023,13,14,"2023-04-01","22:45:00","2023-04-04","05:40:00","2d, 6h","periodical continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim",">","Gr-Karolinenf  Ü","Rosenheim",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-07","05:20:00","2d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<","Rosenheim","Gr-Karolinenf  Ü",2023,2023,13,14,"2023-04-01","22:45:00","2023-04-04","05:40:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-11-25"]
[null,80,"München Hbf - Rosenheim","<>","Rosenheim","Gr-Karolinenf  Ü",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-07","05:20:00","2d, 7h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<>","Gr-Karolinenf  Ü","Gr-Karolinenf  Ü",2023,2023,14,15,"2023-04-07","22:20:00","2023-04-12","05:20:00","4d, 7h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<>","Gr-Karolinenf  Ü","Gr-Karolinenf  Ü",2023,2023,14,15,"2023-04-07","22:20:00","2023-04-12","05:20:00","4d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim",">","Gr-Karolinenf  Ü","Rosenheim",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-07","05:20:00","2d, 7h","periodical continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<","Rosenheim","Gr-Karolinenf  Ü",2023,2023,14,15,"2023-04-07","22:20:00","2023-04-12","05:20:00","4d, 7h","periodical continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<","Rosenheim","Ostermünchen",2023,2023,14,15,"2023-04-07","22:20:00","2023-04-12","05:20:00","4d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-03-17"]
[null,80,"München Hbf - Rosenheim","<>","Rosenheim","Gr-Karolinenf  Ü",2023,2023,14,14,"2023-04-04","22:00:00","2023-04-07","05:20:00","2d, 7h","periodical continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-04-28"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560",">","Olching","Mü Nord Rbf For",2023,2023,9,9,"2023-03-03","09:00:00","2023-03-04","16:00:00","1d, 7h","periodical continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,"0,0,0",null,null,"80","N","2021-08-25"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","km 3,6/6,8 (MOL)",2023,2023,9,10,"2023-03-05","00:00:00","2023-03-06","16:00:00","1d, 16h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,10,13,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-26"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,10,13,"2023-03-07","09:00:00","2023-03-31","16:00:00","24d, 6h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,10,13,"2023-03-11","22:00:00","2023-03-27","16:00:00","15d, 17h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,13,14,"2023-03-31","22:00:00","2023-04-03","16:00:00","2d, 18h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2022,2023,50,5,"2022-12-12","00:30:00","2023-01-31","06:20:00","50d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Stg-Zazenhausen, W 666 - Rbf - Ludwigsburg, W 19","<>","Stg-Zazenhausen","Kornwesth Rbf SO",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-03","05:00:00","2d, 6h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-25"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Achern",2023,2023,5,13,"2023-02-01","00:30:00","2023-03-31","06:20:00","58d, 4h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-07"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,13,49,"2023-03-31","00:00:00","2023-12-08","23:59:00","253d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-10-12"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,13,49,"2023-03-31","00:00:00","2023-12-08","23:59:00","253d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-10-12"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,10,"2023-03-11","01:30:00","2023-03-11","02:30:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2d, 2h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,10,"2023-03-11","02:30:00","2023-03-11","03:30:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2d, 2h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,11,11,"2023-03-13","01:30:00","2023-03-13","02:30:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,11,11,"2023-03-13","02:30:00","2023-03-13","03:30:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,11,11,"2023-03-13","04:00:00","2023-03-15","10:00:00","2d, 6h","continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-11-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,9,"2023-03-03","01:30:00","2023-03-03","04:30:00","0d, 3h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,9,"2023-03-03","01:30:00","2023-03-03","04:30:00","0d, 3h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,9,"2023-03-04","00:35:00","2023-03-04","05:00:00","0d, 4h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,9,"2023-03-04","00:55:00","2023-03-04","02:00:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,10,"2023-03-04","02:00:00","2023-03-06","05:00:00","2d, 3h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,10,"2023-03-04","05:00:00","2023-03-06","04:10:00","1d, 23h","continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,9,9,"2023-03-05","00:30:00","2023-03-05","04:10:00","0d, 3h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,10,"2023-03-06","01:30:00","2023-03-06","04:10:00","0d, 2h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Kornwestheim Pbf","Kornwestheim Pbf",2023,2023,10,10,"2023-03-06","03:00:00","2023-03-06","04:00:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsb Rbf Mitte","Augsburg Hbf",2023,2023,12,44,"2023-03-20","07:00:00","2023-10-31","17:00:00","225d, 10h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-05"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsb Rbf Mitte","Augsburg Hbf",2023,2023,12,44,"2023-03-20","07:00:00","2023-10-31","17:00:00","225d, 10h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-05"]
[null,80,"Schirnding (DB-Grenze) - Cheb/SZDC","<>","Schirnding Grenz","Schirnding Grenz",2023,2023,12,12,"2023-03-22","20:00:00","2023-03-24","06:00:00","1d, 10h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54","N","2021-05-18"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","Unterhaching Üst",2023,2023,11,12,"2023-03-19","02:50:00","2023-03-20","02:50:00","1d, 0h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,",,3",null,null,"80","N","2022-03-10"]
[null,80,"München Hbf tief - München Ost Pbf",">","Mü Isartor","München Ost Pbf",2023,2023,11,12,"2023-03-19","02:50:00","2023-03-20","02:50:00","1d, 0h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2022-03-10"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München Ost Pbf","München-Giesing",2023,2023,11,12,"2023-03-19","02:50:00","2023-03-20","02:50:00","1d, 0h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-10"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Gbf","Ff-Louisa",2023,2023,13,14,"2023-03-31","22:30:00","2023-04-07","05:30:00","6d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-02"]
[null,80,"Ulm Hbf, W 240 - Sigmaringen","<>","Ulm Hbf","Ulm Hbf",2023,2023,11,14,"2023-03-17","23:00:00","2023-04-03","04:30:00","16d, 4h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-21"]
[null,80,"Ulm Hbf, W 240 - Sigmaringen","<>","Ulm Hbf","Ulm Hbf",2023,2023,14,17,"2023-04-03","04:30:00","2023-04-24","04:30:00","21d, 0h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-21"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Mangolding",2023,2023,8,8,"2023-02-20","22:50:00","2023-02-20","23:20:00","0d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,"80","N","2022-05-19"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Mangolding",2023,2023,8,8,"2023-02-20","23:20:00","2023-02-21","04:40:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-19"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,8,8,"2023-02-21","04:40:00","2023-02-21","05:10:00","0d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,"80","N","2022-05-19"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Vilshofen(Nbay)","Girching",2023,2023,8,8,"2023-02-21","22:05:00","2023-02-22","03:50:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Vilshofen(Nbay)","Osterhofen/Nbay",2023,2023,8,8,"2023-02-22","03:50:00","2023-02-22","04:50:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2021-10-07"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Girching","Vilshofen(Nbay)",2023,2023,8,8,"2023-02-22","22:30:00","2023-02-23","04:30:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Vilshofen(Nbay)","Vilshofen(Nbay)",2023,2023,8,8,"2023-02-22","22:30:00","2023-02-22","23:00:00","0d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Vilshofen(Nbay)",2023,2023,8,8,"2023-02-23","04:30:00","2023-02-23","05:30:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Vilshofen(Nbay)","Girching",2023,2023,10,10,"2023-03-10","22:10:00","2023-03-11","04:20:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Vilshofen(Nbay)","Osterhofen/Nbay",2023,2023,10,10,"2023-03-11","04:20:00","2023-03-11","05:20:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Girching","Vilshofen(Nbay)",2023,2023,10,10,"2023-03-11","22:30:00","2023-03-12","04:50:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Girching","Sandbach (Nbay)",2023,2023,10,10,"2023-03-11","22:30:00","2023-03-11","23:00:00","0d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"13,,",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Vilshofen(Nbay)",2023,2023,10,10,"2023-03-12","04:50:00","2023-03-12","05:50:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-05-03"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Mangolding",2023,2023,10,10,"2023-03-12","20:40:00","2023-03-12","21:40:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"13,,13",null,null,"80","N","2022-05-19"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Mangolding",2023,2023,10,11,"2023-03-12","21:40:00","2023-03-13","03:40:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-10-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,11,11,"2023-03-13","03:40:00","2023-03-13","04:40:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-05-19"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<","Baden-Baden","Rastatt",2023,2023,9,9,"2023-03-04","23:00:00","2023-03-05","05:00:00","0d, 6h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<","Rastatt-Süd","Rastatt",2023,2023,9,9,"2023-03-04","23:00:00","2023-03-05","05:00:00","0d, 6h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Rastatt-Süd",2023,2023,9,10,"2023-03-05","22:30:00","2023-03-06","04:30:00","0d, 6h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-07-13"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Baden-Baden",2023,2023,9,10,"2023-03-05","22:30:00","2023-03-06","04:30:00","0d, 6h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-07-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Rastatt-Süd",2023,2023,9,10,"2023-03-05","22:30:00","2023-03-06","04:30:00","0d, 6h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Baden-Baden",2023,2023,13,27,"2023-04-01","00:01:00","2023-07-06","05:00:00","96d, 4h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,27,"2023-04-01","00:01:00","2023-07-06","05:00:00","96d, 4h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<","Baden-Baden","Rastatt",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Rastatt-Süd",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<","Baden-Baden","Rastatt-Süd",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<","Rastatt-Süd","Rastatt",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<","Rastatt","Rastatt-Süd",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<","Rastatt-Süd","Baden-Baden",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-07","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Rastatt-Süd",2023,2023,14,15,"2023-04-09","23:00:00","2023-04-14","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Baden-Baden",2023,2023,14,15,"2023-04-09","23:00:00","2023-04-14","05:00:00","4d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Rastatt-Süd",2023,2023,14,15,"2023-04-09","23:00:00","2023-04-14","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Baden-Baden",2023,2023,14,15,"2023-04-09","23:00:00","2023-04-14","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Ulm Hbf, W 101 - Friedrichshafen Stadt, W 262",">","Ulm Hbf","Laupheim West",2023,2023,11,47,"2023-03-15","21:30:00","2023-11-23","04:30:00","252d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","Heidelb-Wiebl",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-03","05:00:00","2d, 6h","periodical continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,"80","N","2022-03-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","N-Edingen/F-feld","Heidelb-Wiebl",2023,2023,13,14,"2023-03-31","23:00:00","2023-04-03","05:00:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-03-08"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Regensbg-Prüfe","Undorf",2023,2023,11,11,"2023-03-15","22:10:00","2023-03-16","03:20:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-19"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Regensbg-Prüfe","Beratzhausen",2023,2023,11,11,"2023-03-16","03:20:00","2023-03-16","04:20:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"13,,",null,null,"80","N","2022-05-19"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Undorf","Regensburg Bbf",2023,2023,11,11,"2023-03-16","21:30:00","2023-03-17","04:30:00","0d, 7h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-19"]
[null,80,"Nürnberg Hbf - Bamberg","<","Bamberg","Nürnberg Hbf",2023,2023,12,12,"2023-03-20","21:30:00","2023-03-24","05:00:00","3d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-05-02"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,12,12,"2023-03-20","21:30:00","2023-03-24","05:00:00","3d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-05-02"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Heppenhm/Bergstr",2023,2023,13,17,"2023-03-31","22:30:00","2023-04-28","05:30:00","27d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-12-02"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,10,10,"2023-03-11","20:00:00","2023-03-12","00:00:00","0d, 4h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Weingarten (Ba)","Karlsr-Durlach",2023,2023,13,14,"2023-04-02","23:00:00","2023-04-03","05:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,13,13,"2023-04-01","23:00:00","2023-04-02","05:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Deining (Oberpf)","Nürnberg Hbf",2023,2023,6,8,"2023-02-06","21:00:00","2023-02-20","05:00:00","13d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt-Süd","Baden-Baden",2023,2023,13,13,"2023-04-01","00:01:00","2023-04-02","04:00:00","1d, 3h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Bamberg",2023,2023,13,16,"2023-03-29","18:00:00","2023-04-21","18:00:00","23d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-11-26"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Bamberg",2023,2023,13,16,"2023-03-29","06:00:00","2023-04-22","18:00:00","24d, 12h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-11-30"]
[null,80,"Abzw Hallstadt (b Bamberg), 31W102 - Abzw Höflein, W302","<>","Höflein","Hallstadt(Bambg)",2023,2023,13,16,"2023-03-30","00:00:00","2023-04-21","04:00:00","22d, 4h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Bamberg","Oberhaid",2023,2023,13,15,"2023-04-01","00:00:00","2023-04-11","08:00:00","10d, 8h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2020-09-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Bamberg","Höflein",2023,2023,13,15,"2023-03-31","22:00:00","2023-04-11","08:00:00","10d, 10h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"13,13,13",null,null,"80","N","2020-09-30"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Ulm Hbf","Neu-Ulm",2023,2023,7,8,"2023-02-17","23:00:00","2023-02-20","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Burgau (Schwab)","Neuoffingen",2023,2023,7,8,"2023-02-17","23:00:00","2023-02-20","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,7,8,"2023-02-17","23:00:00","2023-02-20","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neu-Ulm","Ulm Hbf",2023,2023,7,8,"2023-02-17","23:00:00","2023-02-20","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Burgau (Schwab)","Neuoffingen",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neu-Ulm","Ulm Hbf",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm Hbf","Neu-Ulm",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Burgau (Schwab)","Neuoffingen",2023,2023,9,10,"2023-03-03","23:00:00","2023-03-06","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neu-Ulm","Ulm Hbf",2023,2023,9,10,"2023-03-03","23:00:00","2023-03-06","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm Hbf","Neu-Ulm",2023,2023,9,10,"2023-03-03","23:00:00","2023-03-06","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,9,10,"2023-03-03","23:00:00","2023-03-06","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,7,10,"2023-02-13","23:00:00","2023-03-07","04:00:00","21d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,7,10,"2023-02-13","23:00:00","2023-03-07","04:00:00","21d, 5h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Plochingen","Esslingen/Neckar",2023,2023,14,15,"2023-04-07","21:00:00","2023-04-14","21:00:00","7d, 0h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-04-29"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,7,8,"2023-02-17","22:00:00","2023-02-26","04:00:00","8d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2022-03-18"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800","<","StrWe 4800/4842","Illingen (Württ)",2023,2023,7,8,"2023-02-17","22:00:00","2023-02-26","04:00:00","8d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-03-18"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühla Rößlesweg",2023,2023,7,8,"2023-02-17","22:00:00","2023-02-26","04:00:00","8d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-03-18"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Günzburg","Neu-Ulm",2023,2023,7,8,"2023-02-17","23:00:00","2023-02-20","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Günzburg","Neu-Ulm",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Günzburg","Neu-Ulm",2023,2023,9,10,"2023-03-03","23:00:00","2023-03-06","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,"80","N","2021-05-20"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Hemsbach","Weinheim Hbf",2023,2023,13,14,"2023-04-01","21:00:00","2023-04-03","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Hemsbach","Weinheim Hbf",2023,2023,13,14,"2023-04-01","21:00:00","2023-04-03","05:00:00","1d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heppenhm/Bergstr","Hemsbach",2023,2023,14,14,"2023-04-03","21:00:00","2023-04-05","05:00:00","1d, 8h","periodical continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Weinheim Hbf","Heppenhm/Bergstr",2023,2023,14,14,"2023-04-03","21:00:00","2023-04-05","05:00:00","1d, 8h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heppenhm/Bergstr","Hemsbach",2023,2023,14,14,"2023-04-03","21:00:00","2023-04-05","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Hemsbach","Hemsbach",2023,2023,14,14,"2023-04-03","21:00:00","2023-04-05","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Hemsbach","Weinheim Hbf",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Weinheim Hbf","Weinheim Hbf",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Weinheim Hbf","Hemsbach",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Weinheim (Bergstr) Hbf, W 95 - Fürth (Odenw)","<>","Weinheim Hbf","Weinheim Hbf",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Weinheim (Bergstr) Hbf, W 95 - Fürth (Odenw)","<>","Birkenau","Weinheim Hbf",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Weinheim (Bergstr) Hbf, W 95 - Fürth (Odenw)","<>","Weinheim Hbf","Hemsbach",2023,2023,14,14,"2023-04-05","21:00:00","2023-04-07","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,14,14,"2023-04-07","21:00:00","2023-04-09","05:00:00","1d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,14,14,"2023-04-07","21:00:00","2023-04-09","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heddesheim/Hberg","Ladenburg",2023,2023,14,15,"2023-04-09","21:00:00","2023-04-11","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heddesheim/Hberg","N-Edingen/F-feld",2023,2023,14,15,"2023-04-09","21:00:00","2023-04-11","05:00:00","1d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,14,15,"2023-04-07","09:00:00","2023-04-11","16:00:00","4d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,null,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,13,49,"2023-03-31","21:00:00","2023-12-09","23:59:00","253d, 3h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","Y","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,13,21,"2023-03-31","21:00:00","2023-05-27","06:00:00","56d, 9h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2022-03-27"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Baden-Baden",2023,2023,13,22,"2023-04-01","23:20:00","2023-05-31","05:48:00","59d, 6h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2020-09-30"]
[null,null,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2023,2023,9,49,"2023-03-01","06:00:00","2023-12-09","23:59:00","283d, 17h","continuous","Signal",null,null,"S",null,null,",,",",,",null,",4,",null,null,"80","Y","2021-06-01"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Ottersweier","Ottersweier",2023,2023,5,13,"2023-02-01","23:20:00","2023-03-31","05:48:00","57d, 5h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Baden-Baden","Baden-Baden",2023,2023,5,13,"2023-02-01","23:20:00","2023-03-31","05:48:00","57d, 5h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Baden-Baden","Önsbach",2023,2023,13,22,"2023-04-01","23:20:00","2023-05-31","05:48:00","59d, 6h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-05"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München Hbf","München-Pasing",2023,2023,13,14,"2023-03-31","22:40:00","2023-04-03","04:40:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","Mü-Neuhausen","München-Pasing",2023,2023,13,14,"2023-03-31","22:40:00","2023-04-03","04:40:00","2d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München-Pasing","München-Pasing",2023,2023,13,14,"2023-03-31","22:40:00","2023-04-03","04:40:00","2d, 6h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",1,1",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","Mü-Neuhausen","München-Pasing",2023,2023,14,15,"2023-04-06","22:40:00","2023-04-11","04:40:00","4d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München-Pasing","München-Pasing",2023,2023,14,15,"2023-04-06","22:40:00","2023-04-11","04:40:00","4d, 6h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München Hbf","München-Pasing",2023,2023,14,14,"2023-04-08","22:40:00","2023-04-09","04:40:00","0d, 6h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München-Pasing","München-Pasing",2023,2023,14,14,"2023-04-08","22:40:00","2023-04-09","04:40:00","0d, 6h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2022-05-16"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Forchheim/Karlsr","Ötigheim",2023,2023,16,18,"2023-04-21","21:00:00","2023-05-05","04:30:00","13d, 7h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2022-03-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-25"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-10-11"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Durmersheim",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-28","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,"80","N","2021-10-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Bickenbach",2023,2023,15,16,"2023-04-15","23:00:00","2023-04-17","04:00:00","1d, 5h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-26"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberstadt","Pfungstadt",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Bickenbach Nord","Da-Eberst Nord",2023,2023,16,16,"2023-04-18","00:00:00","2023-04-18","05:00:00","0d, 5h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-26"]
[null,null,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heppenhm/Bergstr","Darmstadt Hbf",2023,2023,24,49,"2023-06-17","14:00:00","2023-12-09","21:00:00","175d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-12-02"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,16,18,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-13"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Bickenbach Nord",2023,2023,16,18,"2023-04-21","22:00:00","2023-05-01","04:00:00","9d, 6h","periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-14"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,16,18,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-07-13"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Ebelsbach-Eltm",2023,2023,15,15,"2023-04-10","08:00:00","2023-04-10","16:00:00","0d, 8h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,15,15,"2023-04-11","22:00:00","2023-04-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-09"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,17,17,"2023-04-24","22:50:00","2023-04-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,16,16,"2023-04-17","23:30:00","2023-04-18","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart-Bad Cannstatt, W 28 - Stuttgart-Untertürkheim, W 202","<>","Stg-Bad Cannst","Stg-Untertürkhm",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-21","15:00:00","4d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-07"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,16,16,"2023-04-17","23:20:00","2023-04-18","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,16,16,"2023-04-17","22:50:00","2023-04-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,17,21,"2023-04-24","01:00:00","2023-05-26","16:00:00","32d, 15h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-03"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Ebelsbach-Eltm",2023,2023,15,16,"2023-04-11","05:00:00","2023-04-22","21:00:00","11d, 16h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32",">","Oberhaid","Zeil",2023,2023,16,16,"2023-04-22","00:00:00","2023-04-22","04:00:00","0d, 4h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,"80","N","2021-04-30"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-20","18:00:00","2023-04-27","18:00:00","7d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,16,17,"2023-04-20","18:00:00","2023-04-27","18:00:00","7d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach","Da-Eberst Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-11"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,16,17,"2023-04-22","23:30:00","2023-04-24","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,15,16,"2023-04-15","11:00:00","2023-04-22","14:00:00","7d, 3h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Laufach","Wiesthal",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,15,17,"2023-04-13","06:00:00","2023-04-26","18:00:00","13d, 12h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Laufach",2023,2023,15,16,"2023-04-15","23:30:00","2023-04-17","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,15,17,"2023-04-14","18:00:00","2023-04-24","12:00:00","9d, 18h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,16,16,"2023-04-17","05:00:00","2023-04-17","08:00:00","0d, 3h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,15,17,"2023-04-15","14:00:00","2023-04-24","05:00:00","8d, 15h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,16,16,"2023-04-17","03:00:00","2023-04-17","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Plochingen","Göppingen",2023,2023,17,17,"2023-04-25","22:00:00","2023-04-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,17,17,"2023-04-25","22:00:00","2023-04-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Eislingen (Fils)","Süßen",2023,2023,17,17,"2023-04-25","22:00:00","2023-04-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","21:30:00","2023-04-21","05:00:00","3d, 7h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","21:30:00","2023-04-21","05:00:00","3d, 7h","periodical continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-12"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","06:00:00","2023-04-22","06:00:00","5d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-12"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Lorsch",2023,2023,16,16,"2023-04-17","21:30:00","2023-04-21","05:00:00","3d, 7h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","06:00:00","2023-04-22","06:00:00","5d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-12"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,15,16,"2023-04-16","22:00:00","2023-04-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Pragtunnel","Kornwestheim Pbf",2023,2023,15,16,"2023-04-14","23:30:00","2023-04-17","04:40:00","2d, 5h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,"80","N","2021-06-07"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Mangolding",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-28","05:00:00","3d, 8h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-04-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,15,16,"2023-04-16","22:00:00","2023-04-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,15,16,"2023-04-16","22:00:00","2023-04-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,15,16,"2023-04-14","23:00:00","2023-04-19","05:00:00","4d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-16"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,16,17,"2023-04-17","07:00:00","2023-04-28","17:00:00","11d, 10h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,16,17,"2023-04-22","07:00:00","2023-04-28","17:00:00","6d, 10h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Wernfeld","Wernfeld",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-21","17:00:00","4d, 10h","periodical continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-07"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Eußenheim","Gemünden (Main)",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-17","14:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Eußenheim","Gemünden (Main)",2023,2023,16,17,"2023-04-22","14:00:00","2023-04-27","17:00:00","5d, 3h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,15,15,"2023-04-10","22:50:00","2023-04-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,15,15,"2023-04-10","22:50:00","2023-04-11","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,15,15,"2023-04-10","22:50:00","2023-04-11","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,16,16,"2023-04-18","22:00:00","2023-04-19","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart-Bad Cannstatt, W 28 - Stuttgart-Untertürkheim, W 202","<>","Stg-Bad Cannst","Stg-Untertürkhm",2023,2023,16,16,"2023-04-17","07:00:00","2023-04-21","15:00:00","4d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-06"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Oberhaid",2023,2023,15,15,"2023-04-11","08:00:00","2023-04-12","08:00:00","1d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-11-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<","Oberhaid","Bamberg",2023,2023,15,16,"2023-04-11","04:00:00","2023-04-20","08:00:00","9d, 4h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,15,15",null,null,"80","N","2021-11-29"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Oberhaid","Höflein",2023,2023,16,16,"2023-04-20","08:00:00","2023-04-22","08:00:00","2d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-12-13"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Oberhaid",2023,2023,15,16,"2023-04-11","04:00:00","2023-04-21","08:00:00","10d, 4h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-11-30"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Höflein","Oberhaid",2023,2023,15,15,"2023-04-12","04:00:00","2023-04-15","04:00:00","3d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2021-11-30"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Obertraubling","Vilshofen(Nbay)",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-28","05:00:00","3d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-01-22"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Obertraubling","Vilshofen(Nbay)",2023,2023,16,16,"2023-04-17","21:00:00","2023-04-21","05:00:00","3d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-01-22"]
[null,80,"Hofheim (Ried) - Bensheim, W 3","<>","Bensheim","Bensheim",2023,2023,16,16,"2023-04-17","06:00:00","2023-04-22","06:00:00","5d, 0h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,17,17,"2023-04-24","08:00:00","2023-04-25","15:00:00","1d, 7h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2021-11-30"]
[null,80,"Flieden, W 58 - Gemünden (Main), W 111","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,17,17,"2023-04-24","08:00:00","2023-04-25","15:00:00","1d, 7h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2021-11-30"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,17,17,"2023-04-24","08:00:00","2023-04-25","15:00:00","1d, 7h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-13"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Oberhaid","Oberhaid",2023,2023,15,15,"2023-04-10","04:00:00","2023-04-11","20:00:00","1d, 16h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-05"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<","Oberhaid","Oberhaid",2023,2023,16,16,"2023-04-17","04:00:00","2023-04-18","04:00:00","1d, 0h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-05"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<","Ebelsbach-Eltm","Bamberg",2023,2023,15,16,"2023-04-15","12:00:00","2023-04-17","04:00:00","1d, 16h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,"80","N","2022-07-05"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Wernfeld","Gemünden (Main)",2023,2023,17,17,"2023-04-25","22:30:00","2023-04-27","05:00:00","1d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-13"]
[null,80,"Flieden, W 58 - Gemünden (Main), W 111","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,17,17,"2023-04-25","22:30:00","2023-04-27","05:00:00","1d, 6h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2021-11-30"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800",">","StrWe 4800/4842","Illingen (Württ)",2023,2023,16,16,"2023-04-18","22:00:00","2023-04-19","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","Mühlacker",2023,2023,16,16,"2023-04-18","22:00:00","2023-04-19","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rumgraben","Übersee",2023,2023,15,17,"2023-04-11","22:00:00","2023-04-29","22:00:00","18d, 0h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-07"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,17,17,"2023-04-24","22:00:00","2023-04-28","05:30:00","3d, 7h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-07-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim Ost",2023,2023,17,17,"2023-04-24","22:00:00","2023-04-28","05:30:00","3d, 7h","periodical continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-05-13"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Landl (Obb) Abzw",2023,2023,17,17,"2023-04-24","22:00:00","2023-04-28","05:30:00","3d, 7h","periodical continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-13"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Bad Endorf (Obb)",2023,2023,17,17,"2023-04-24","22:00:00","2023-04-28","05:30:00","3d, 7h","periodical continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-13"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Ost","Rosenheim Süd",2023,2023,17,17,"2023-04-24","22:00:00","2023-04-28","05:30:00","3d, 7h","periodical continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-07-23"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsburg Hbf","Westheim/Schwab",2023,2023,16,16,"2023-04-21","23:00:00","2023-04-22","02:00:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<","Augsb Hirbl Str","Augsb Rbf Mitte",2023,2023,16,16,"2023-04-22","02:00:00","2023-04-22","07:00:00","0d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Westheim/Schwab","Augsb Hirbl Str",2023,2023,16,16,"2023-04-22","02:00:00","2023-04-22","07:00:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,16,16,"2023-04-21","23:00:00","2023-04-22","02:00:00","0d, 3h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,16,16,"2023-04-23","14:00:00","2023-04-23","18:00:00","0d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,16,16,"2023-04-22","07:00:00","2023-04-22","17:00:00","0d, 10h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,16,16,"2023-04-22","07:00:00","2023-04-22","17:00:00","0d, 10h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsb Rbf Nord","Augsb-Oberhausen",2023,2023,16,16,"2023-04-22","20:00:00","2023-04-23","14:00:00","0d, 18h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"München Hbf - Rosenheim","<>","Aßling/Obb","Aßling/Obb",2023,2023,15,16,"2023-04-12","22:20:00","2023-04-17","05:30:00","4d, 7h","periodical continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<","Ostermünchen","Aßling/Obb",2023,2023,15,16,"2023-04-12","22:20:00","2023-04-17","05:30:00","4d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-04-28"]
[null,80,"München Hbf - Rosenheim","<>","Aßling/Obb","Aßling/Obb",2023,2023,15,16,"2023-04-12","22:20:00","2023-04-17","05:30:00","4d, 7h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-28"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Mü-Trudering","Zorneding",2023,2023,16,16,"2023-04-18","00:35:00","2023-04-18","05:20:00","0d, 4h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,8",null,null,"80","N","2022-07-20"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Mü-Trudering","Zorneding",2023,2023,16,16,"2023-04-19","00:35:00","2023-04-21","05:20:00","2d, 4h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,8",null,null,"80","N","2022-07-20"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf","<","Zorneding","Mü-Trudering",2023,2023,17,17,"2023-04-25","00:35:00","2023-04-26","04:50:00","1d, 4h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,10",null,null,"80","N","2022-07-20"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Bickenbach",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023,2023,16,17,"2023-04-21","22:00:00","2023-04-24","04:00:00","2d, 6h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Da-Eberst Nord",2023,2023,17,17,"2023-04-24","23:00:00","2023-04-28","05:00:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Darmstadt Hbf",2023,2023,17,17,"2023-04-24","23:00:00","2023-04-28","05:00:00","3d, 6h","periodical continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-10"]
[null,80,"München Hbf tief - Gauting, 35W22",">","Mü-Laim Pbf","München-Pasing",2023,2023,15,21,"2023-04-11","04:40:00","2023-05-26","22:40:00","45d, 18h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,0",null,null,"80","N","2022-05-16"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü-Riem West",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","Mü Isartor","München Ost Pbf",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<","München Ost Pbf","München Ost Pbf",2023,2023,15,15,"2023-04-13","00:30:00","2023-04-14","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München Ost Pbf","München Ost Pbf",2023,2023,15,16,"2023-04-13","22:00:00","2023-04-17","22:00:00","4d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,15,16,"2023-04-14","00:00:00","2023-04-17","05:00:00","3d, 5h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,15,16,"2023-04-14","23:30:00","2023-04-17","04:30:00","2d, 5h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen","<>","Mü O Wendeanlage","München Ost Pbf",2023,2023,15,16,"2023-04-14","23:30:00","2023-04-17","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf","<","München Ost Pbf","München Ost Pbf",2023,2023,15,16,"2023-04-14","23:30:00","2023-04-17","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<>","München Ost Pbf","München Ost Pbf",2023,2023,15,16,"2023-04-14","23:30:00","2023-04-17","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü-Riem West",2023,2023,15,15,"2023-04-16","01:00:00","2023-04-16","04:30:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,15,15,"2023-04-16","01:00:00","2023-04-16","04:30:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","Mü Isartor","München Ost Pbf",2023,2023,15,15,"2023-04-16","01:00:00","2023-04-16","04:30:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,16,16,"2023-04-17","00:30:00","2023-04-19","04:30:00","2d, 4h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München Ost Pbf",2023,2023,16,16,"2023-04-17","00:30:00","2023-04-19","04:30:00","2d, 4h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,16,16,"2023-04-17","00:30:00","2023-04-19","04:30:00","2d, 4h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen",">","München Ost Pbf","Mü O Wendeanlage",2023,2023,16,16,"2023-04-17","04:30:00","2023-04-21","23:30:00","4d, 19h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,16,16,"2023-04-20","00:00:00","2023-04-21","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-25","05:30:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü-Riem West",2023,2023,17,17,"2023-04-24","01:30:00","2023-04-26","04:30:00","2d, 3h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","München Ost Pbf","München Ost Pbf",2023,2023,17,17,"2023-04-24","01:30:00","2023-04-26","04:30:00","2d, 3h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,17,17,"2023-04-25","00:00:00","2023-04-26","04:30:00","1d, 4h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü-Riem West",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München Ost Pbf",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","Mü Isartor","München Ost Pbf",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,16,17,"2023-04-21","23:30:00","2023-04-24","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München-Giesing",2023,2023,17,17,"2023-04-25","02:30:00","2023-04-25","04:30:00","0d, 2h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,17,17,"2023-04-25","02:30:00","2023-04-25","04:30:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W20  - Bft Mü-Steinhausen",">","München Ost Pbf","Mü O Wendeanlage",2023,2023,17,17,"2023-04-25","02:30:00","2023-04-25","04:30:00","0d, 2h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","Mü Isartor","München Ost Pbf",2023,2023,17,17,"2023-04-25","02:30:00","2023-04-25","04:30:00","0d, 2h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,17,17,"2023-04-25","02:30:00","2023-04-25","04:30:00","0d, 2h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"Karlsruhe Gbf, W912 - Abzw Karlsruhe-Dammerstock, W 401",">","Karlsruhe Gbf","Forchheim/Karlsr",2023,2023,15,15,"2023-04-15","23:00:00","2023-04-16","05:00:00","0d, 6h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Forchheim/Karlsr","Karlsruhe Gbf",2023,2023,15,16,"2023-04-16","22:00:00","2023-04-17","04:30:00","0d, 6h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Dammerstock","Dammerstock",2023,2023,16,16,"2023-04-17","00:00:00","2023-04-17","04:30:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Dammerstock","Dammerstock",2023,2023,16,16,"2023-04-17","00:00:00","2023-04-17","04:30:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,16,17,"2023-04-23","23:00:00","2023-04-28","04:30:00","4d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,16,17,"2023-04-23","23:00:00","2023-04-28","04:30:00","4d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-20"]
[null,80,"Günzburg, W 5 - RB-Grenze km 2,000 - Mindelheim, W 20","<>","Günzburg","Ichenhausen",2023,2023,15,16,"2023-04-15","01:00:00","2023-04-17","05:00:00","2d, 4h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-29"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Burgau (Schwab)","Neuoffingen",2023,2023,15,17,"2023-04-13","23:00:00","2023-04-24","05:00:00","10d, 6h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,15,17,"2023-04-13","23:00:00","2023-04-24","05:00:00","10d, 6h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Günzburg","Neu-Ulm",2023,2023,15,17,"2023-04-13","23:00:00","2023-04-24","05:00:00","10d, 6h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Neu-Ulm","Ulm Hbf",2023,2023,15,17,"2023-04-13","23:00:00","2023-04-24","05:00:00","10d, 6h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm Hbf","Neu-Ulm",2023,2023,15,17,"2023-04-13","23:00:00","2023-04-24","05:00:00","10d, 6h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heddesheim/Hberg","Ladenburg",2023,2023,15,15,"2023-04-11","21:00:00","2023-04-13","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,15,15,"2023-04-11","21:00:00","2023-04-13","05:00:00","1d, 8h","periodical continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","Ladenburg",2023,2023,15,15,"2023-04-11","21:00:00","2023-04-13","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","N-Edingen/F-feld","Ladenburg",2023,2023,15,15,"2023-04-11","21:00:00","2023-04-13","05:00:00","1d, 8h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","N-Edingen/F-feld","Ladenburg",2023,2023,15,15,"2023-04-13","21:00:00","2023-04-14","05:00:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","Ladenburg",2023,2023,15,15,"2023-04-13","21:00:00","2023-04-14","05:00:00","0d, 8h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","Ladenburg",2023,2023,15,15,"2023-04-13","21:00:00","2023-04-14","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,15,15,"2023-04-13","21:00:00","2023-04-14","05:00:00","0d, 8h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,15,15,"2023-04-13","21:00:00","2023-04-14","05:00:00","0d, 8h","continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Weinheim Hbf","Ladenburg",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Weinheim Hbf","Heddesheim/Hberg",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 907","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-17","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Weinheim Hbf","Weinheim Hbf",2023,2023,16,16,"2023-04-17","21:00:00","2023-04-19","05:00:00","1d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-03-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Hemsbach","Heddesheim/Hberg",2023,2023,16,16,"2023-04-17","21:00:00","2023-04-19","05:00:00","1d, 8h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Weinheim Hbf","Weinheim Hbf",2023,2023,16,16,"2023-04-17","21:00:00","2023-04-19","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,16,16,"2023-04-19","21:00:00","2023-04-21","05:00:00","1d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Ladenburg","N-Edingen/F-feld",2023,2023,16,16,"2023-04-19","21:00:00","2023-04-21","05:00:00","1d, 8h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,16,16,"2023-04-19","21:00:00","2023-04-21","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,16,16,"2023-04-19","21:00:00","2023-04-21","05:00:00","1d, 8h","periodical continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Ladenburg","N-Edingen/F-feld",2023,2023,16,16,"2023-04-19","21:00:00","2023-04-21","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-24","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-24","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,16,17,"2023-04-21","21:00:00","2023-04-24","05:00:00","2d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-30","05:00:00","5d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-30","05:00:00","5d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-30","05:00:00","5d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-30","05:00:00","5d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-30","05:00:00","5d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,16,18,"2023-04-21","21:00:00","2023-05-05","04:30:00","13d, 7h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Bashaide",2023,2023,15,16,"2023-04-14","21:00:00","2023-04-21","04:30:00","6d, 7h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-03-28"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","Mü-Laim Pbf","München-Pasing",2023,2023,15,15,"2023-04-11","10:00:00","2023-04-14","04:40:00","2d, 18h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","Mü-Laim Pbf","München-Pasing",2023,2023,15,15,"2023-04-11","10:00:00","2023-04-14","04:40:00","2d, 18h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,2",null,null,"80","N","2022-05-16"]
[null,80,"Flieden, W 58 - Gemünden (Main), W 111","<>","Gemünden (Main)","Gemünden (Main)",2023,2023,17,17,"2023-04-24","08:00:00","2023-04-25","15:00:00","1d, 7h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-22"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,16,18,"2023-04-17","06:00:00","2023-05-02","06:00:00","15d, 0h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberstadt","Da-Eberst Nord",2023,2023,16,18,"2023-04-21","22:00:00","2023-05-01","04:00:00","9d, 6h","periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Durmersheim",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-06-01"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim","Übersee",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-31"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rosenheim","Übersee",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-20"]
[null,80,"Prien am Chiemsee, Gl 2406 - Aschau (Chiemgau)","<>","Prien a Chiemsee","Aschau/Chiemgau",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","13:00:00","2d, 15h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-20"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Rohrdorf/Obb",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-01"]
[null,80,"Holzkirchen, W 23 - Rosenheim, 19W211","<>","Rosenheim","Kolbermoor",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-23"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,18,18,"2023-05-01","18:00:00","2023-05-02","06:00:00","0d, 12h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-19"]
[null,80,"Rosenheim, 19W63 - Kufstein (DB-Grenze)","<>","Rosenheim","Kiefersfelden",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-01-11"]
[null,80,"München Hbf - Rosenheim","<>","Rosenheim","Rosenheim",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-01-11"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Rosenheim",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-01-11"]
[null,80,"Rosenheim - Mühldorf - Neumarkt-St Veit DB-Grenze","<>","Rosenheim","Rott (Inn)",2023,2023,17,18,"2023-04-30","23:59:00","2023-05-01","06:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-20"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,18,18,"2023-05-01","22:00:00","2023-05-03","05:00:00","1d, 7h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-27"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü Nord Rbf For","Olching",2023,2023,17,18,"2023-04-30","05:00:00","2023-05-04","22:00:00","4d, 17h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-25"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Durmersheim","Bashaide",2023,2023,17,18,"2023-04-28","21:00:00","2023-05-05","04:30:00","6d, 7h","periodical continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,19,20,"2023-05-14","22:00:00","2023-05-15","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<","Bickenbach Nord","Da-Eberst Nord",2023,2023,18,18,"2023-05-06","00:00:00","2023-05-06","05:00:00","0d, 5h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-26"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Darmstadt Hbf","Bickenbach",2023,2023,18,19,"2023-05-06","23:00:00","2023-05-08","04:00:00","1d, 5h","periodical continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-26"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,18,18,"2023-05-01","22:50:00","2023-05-02","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-16","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Bamberg, W 112 - Rottendorf, W 31 und W 32","<>","Ebelsbach-Eltm","Höflein",2023,2023,18,19,"2023-05-01","21:00:00","2023-05-12","04:40:00","10d, 7h","periodical continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","04:00:00","2d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Bickenbach Nord","Bickenbach Nord",2023,2023,17,18,"2023-04-27","18:00:00","2023-05-04","18:00:00","7d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,20,20,"2023-05-15","23:30:00","2023-05-16","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Osterhofen/Nbay","Girching",2023,2023,18,28,"2023-05-07","22:25:00","2023-07-10","06:00:00","63d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-04-22"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-15","05:00:00","2023-05-16","05:00:00","1d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-06-01"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,19,"2023-05-12","20:00:00","2023-05-12","23:00:00","0d, 3h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Gbf","Vach",2023,2023,20,20,"2023-05-15","01:00:00","2023-05-15","05:00:00","0d, 4h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-09"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,19,25,"2023-05-10","12:00:00","2023-06-19","05:00:00","39d, 17h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-12-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,19,20,"2023-05-12","23:00:00","2023-05-17","05:00:00","4d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-16"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Deining Üst","Neumarkt(Oberpf)",2023,2023,20,20,"2023-05-15","22:00:00","2023-05-19","05:00:00","3d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Holzkirchen, W 23 - Rosenheim, 19W211","<>","Rosenheim","Bad Aibling",2023,2023,17,17,"2023-04-29","07:00:00","2023-04-30","20:00:00","1d, 13h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-22"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Stg-Zuffenhausen","Ludwigsburg",2023,2023,18,18,"2023-05-04","00:40:00","2023-05-04","04:50:00","0d, 4h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-07-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,19,19,"2023-05-08","22:50:00","2023-05-09","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<","Wilferdgn-Singen","Karlsr-Durlach",2023,2023,18,19,"2023-05-05","23:00:00","2023-05-10","05:00:00","4d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-01-26"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,18,18,"2023-05-01","03:00:00","2023-05-01","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Eußenheim","Gemünden (Main)",2023,2023,17,17,"2023-04-28","07:00:00","2023-04-28","17:00:00","0d, 10h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-25"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Laufach","Laufach",2023,2023,18,49,"2023-05-04","21:00:00","2023-12-09","23:59:00","219d, 3h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2021-06-04"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,18,18,"2023-05-01","23:20:00","2023-05-02","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Treuchtlingen - Nürnberg Hbf, W 44",">","Nürnberg Hbf","Treuchtlingen",2023,2023,18,20,"2023-05-05","21:00:00","2023-05-19","05:00:00","13d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-01-18"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Girching","Osterhofen/Nbay",2023,2023,19,28,"2023-05-08","22:25:00","2023-07-11","06:00:00","63d, 7h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,17,18,"2023-04-29","23:00:00","2023-05-01","04:00:00","1d, 5h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-04-16"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Sünching","Radldorf (Nbay)",2023,2023,18,18,"2023-05-05","03:30:00","2023-05-05","04:30:00","0d, 1h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-11"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sandbach (Nbay)","Vilshofen(Nbay)",2023,2023,18,18,"2023-05-06","23:10:00","2023-05-07","00:40:00","0d, 1h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,"80","N","2021-12-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Schalding","Sandbach (Nbay)",2023,2023,19,19,"2023-05-08","03:50:00","2023-05-08","04:40:00","0d, 0h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-15"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,18,18,"2023-05-06","06:00:00","2023-05-06","14:00:00","0d, 8h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2022-07-15"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,19,19,"2023-05-08","23:00:00","2023-05-12","05:00:00","3d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-11-29"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,20,20,"2023-05-15","22:00:00","2023-05-16","05:00:00","0d, 7h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15",">","Reichswald","Kinding",2023,2023,18,18,"2023-05-05","23:50:00","2023-05-06","05:50:00","0d, 6h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",5,",null,null,"80","N","2022-07-19"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15","<>","Reichswald","Allersb(Rothsee)",2023,2023,18,18,"2023-05-06","23:50:00","2023-05-07","05:50:00","0d, 6h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",4,",null,null,"80","N","2022-07-19"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Schalding","Sandbach (Nbay)",2023,2023,18,19,"2023-05-06","22:40:00","2023-05-08","04:40:00","1d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-10"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Ulm Hbf","Neu-Ulm",2023,2023,18,19,"2023-05-05","22:40:00","2023-05-10","04:40:00","4d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-21"]
[null,80,"Nürnberg Hbf - Schirnding Grenze","<>","Marktredwitz","Schirnding Grenz",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-07","06:00:00","8d, 8h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54","N","2022-07-26"]
[null,80,"Nürnberg Hbf - Bamberg",">","Hirschaid","Eggolsheim Süd",2023,2023,19,19,"2023-05-13","20:00:00","2023-05-14","04:00:00","0d, 8h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-07"]
[null,80,"Bamberg - Hof Hbf, W 121","<>","Bamberg","Breitengüßbach",2023,2023,19,19,"2023-05-11","22:00:00","2023-05-12","06:00:00","0d, 8h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-05-25"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,19,"2023-05-10","22:00:00","2023-05-11","05:00:00","0d, 7h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2022-07-19"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,18,20,"2023-05-02","06:00:00","2023-05-17","12:00:00","15d, 6h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Da-Eberst Nord",2023,2023,20,20,"2023-05-15","18:00:00","2023-05-17","04:00:00","1d, 10h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-10"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Bamberg",2023,2023,19,20,"2023-05-12","18:00:00","2023-05-16","10:00:00","3d, 16h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-05-03"]
[null,80,"Abzw Hallstadt (b Bamberg), 31W102 - Abzw Höflein, W302","<>","Höflein","Hallstadt(Bambg)",2023,2023,19,19,"2023-05-12","22:00:00","2023-05-14","06:00:00","1d, 8h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-03"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307",">","Nür-Langwasser","Nür-Dutzendteich",2023,2023,19,20,"2023-05-10","00:00:00","2023-05-17","13:00:00","7d, 13h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<>","Nür-Dutzendteich","Nür-Langwasser",2023,2023,19,19,"2023-05-12","18:00:00","2023-05-12","23:00:00","0d, 5h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<>","Nür-Langwasser","Nür-Dutzendteich",2023,2023,19,19,"2023-05-13","13:00:00","2023-05-13","18:00:00","0d, 5h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,18,18,"2023-05-02","07:00:00","2023-05-03","17:00:00","1d, 10h","periodical continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2022-07-05"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2023,2023,19,20,"2023-05-14","00:01:00","2023-05-15","04:00:00","1d, 3h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Baden-Baden",2023,2023,20,21,"2023-05-15","23:00:00","2023-05-27","05:00:00","11d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<>","Obertraubling","Regensburg Hbf",2023,2023,18,19,"2023-05-07","23:20:00","2023-05-08","04:15:00","0d, 4h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,18,19,"2023-05-07","23:20:00","2023-05-08","04:15:00","0d, 4h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-27","01:30:00","2023-04-27","05:30:00","0d, 4h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-28","01:30:00","2023-04-28","05:30:00","0d, 4h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-28","11:00:00","2023-04-28","19:00:00","0d, 8h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-28","11:00:00","2023-04-28","19:00:00","0d, 8h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-29","01:00:00","2023-04-29","05:00:00","0d, 4h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,17,17,"2023-04-30","01:00:00","2023-04-30","05:00:00","0d, 4h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,18,18,"2023-05-02","01:00:00","2023-05-02","05:00:00","0d, 4h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,18,18,"2023-05-03","01:00:00","2023-05-03","05:00:00","0d, 4h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86",">","Molzau","Graben-Neudorf",2023,2023,19,19,"2023-05-08","01:00:00","2023-05-08","04:00:00","0d, 3h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Graben-Neudorf","Molzau",2023,2023,17,17,"2023-04-26","23:00:00","2023-04-27","01:00:00","0d, 2h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Molzau","Graben-Neudorf",2023,2023,19,19,"2023-05-10","23:00:00","2023-05-11","01:00:00","0d, 2h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,19,19,"2023-05-10","23:00:00","2023-05-11","01:00:00","0d, 2h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Karlsr-Durlach","Karlsruhe Hbf",2023,2023,19,19,"2023-05-09","22:00:00","2023-05-10","06:00:00","0d, 8h","continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-12-14"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Seubersdorf","Parsberg",2023,2023,19,19,"2023-05-11","02:50:00","2023-05-11","03:50:00","0d, 1h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-07"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,18,49,"2023-05-04","23:30:00","2023-12-09","23:59:00","219d, 1h","continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-05-16"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensbg Ost","Obertraubling",2023,2023,18,19,"2023-05-05","23:00:00","2023-05-10","05:00:00","4d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Obertraubling","Köfering",2023,2023,18,19,"2023-05-06","05:00:00","2023-05-08","14:00:00","2d, 9h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensbg Ost","Köfering",2023,2023,18,19,"2023-05-07","23:20:00","2023-05-08","04:15:00","0d, 4h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106",">","Köfering","Obertraubling",2023,2023,19,19,"2023-05-10","05:00:00","2023-05-14","14:00:00","4d, 9h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensbg Ost","Obertraubling",2023,2023,20,20,"2023-05-15","22:50:00","2023-05-18","04:15:00","2d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,"80","N","2022-07-15"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Durlach",2023,2023,17,18,"2023-04-29","23:00:00","2023-05-01","05:00:00","1d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-03","00:00:00","2023-05-03","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-03","00:00:00","2023-05-03","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Freilassing","Freilassing",2023,2023,18,18,"2023-05-03","03:00:00","2023-05-03","05:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-03","01:00:00","2023-05-03","03:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-07","01:00:00","2023-05-07","03:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-07","03:00:00","2023-05-07","05:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,18,18,"2023-05-07","03:00:00","2023-05-07","05:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,19,19,"2023-05-14","08:30:00","2023-05-14","10:00:00","0d, 1h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Mainz-Bischofsheim, W 6 - Darmstadt Hbf, W 314","<>","Mz-Bischofsh Pbf","Darmstadt Hbf",2023,2023,18,19,"2023-05-02","00:30:00","2023-05-13","04:30:00","11d, 4h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"16,16,16",null,null,"80","N","2022-06-03"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,18,18,"2023-05-05","21:00:00","2023-05-06","05:00:00","0d, 8h","continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,18,18,"2023-05-05","21:00:00","2023-05-06","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","Ziehbrunnen",2023,2023,18,18,"2023-05-06","21:00:00","2023-05-07","05:00:00","0d, 8h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 908","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,18,20,"2023-05-07","21:00:00","2023-05-16","05:00:00","8d, 8h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Philippsbg (Bad)",2023,2023,19,19,"2023-05-11","00:45:00","2023-05-12","04:45:00","1d, 4h","periodical continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,18,19,"2023-05-07","23:20:00","2023-05-08","04:15:00","0d, 4h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,22,30,"2023-05-29","08:00:00","2023-07-26","16:00:00","58d, 8h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-06-08"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,21,21,"2023-05-22","01:30:00","2023-05-22","03:00:00","0d, 1h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<>","Fürth (Bay) Gbf","Nürnberg-Doos",2023,2023,21,21,"2023-05-22","01:00:00","2023-05-22","05:00:00","0d, 4h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-14"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,21,21,"2023-05-22","01:00:00","2023-05-22","05:00:00","0d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-14"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,21,21,"2023-05-22","12:00:00","2023-05-22","18:00:00","0d, 6h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-11"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,21,21,"2023-05-23","22:00:00","2023-05-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,21,23,"2023-05-27","22:00:00","2023-06-06","05:00:00","9d, 7h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-08-05"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,21,22,"2023-05-28","22:00:00","2023-05-31","04:00:00","2d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,21,22,"2023-05-28","22:00:00","2023-05-29","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Seubersdorf","Neumarkt(Oberpf)",2023,2023,20,20,"2023-05-21","00:00:00","2023-05-21","04:00:00","0d, 4h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-03"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Neumarkt(Oberpf)","Deining Üst",2023,2023,21,22,"2023-05-28","02:00:00","2023-05-29","05:00:00","1d, 3h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,21,21,"2023-05-22","22:50:00","2023-05-23","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,22,22,"2023-05-29","03:00:00","2023-05-29","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Bamberg","Strullendorf",2023,2023,20,42,"2023-05-21","23:00:00","2023-10-21","22:00:00","152d, 23h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-23"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,21,22,"2023-05-28","22:00:00","2023-05-29","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,20,20,"2023-05-16","22:00:00","2023-05-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Mangolding","Radldorf (Nbay)",2023,2023,21,22,"2023-05-27","14:00:00","2023-05-30","04:00:00","2d, 14h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-04"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,22,22,"2023-05-29","22:50:00","2023-05-30","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Flieden, W 58 - Gemünden (Main), W 111","<","Gemünden (Main)","Sterbfritz",2023,2023,20,21,"2023-05-19","21:45:00","2023-05-26","05:45:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-01-27"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800",">","StrWe 4800/4842","Illingen (Württ)",2023,2023,20,20,"2023-05-16","22:00:00","2023-05-17","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühlacker",2023,2023,22,22,"2023-05-30","22:00:00","2023-05-31","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Nürnberg Hbf - Bamberg",">","Vach","Eltersdorf",2023,2023,20,20,"2023-05-20","20:00:00","2023-05-21","02:00:00","0d, 6h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-06-22"]
[null,80,"Eltersdorf, 28W402 - RB-Grenze km 117,357 - Erfurt Hbf - Leipzig Hbf, Gl 12 (Gröbers - Lpz-Mockau Personenzugbahn)",">","Eltersdorf","Eltersdorf",2023,2023,20,20,"2023-05-21","02:00:00","2023-05-21","04:00:00","0d, 2h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-06-22"]
[null,80,"Eltersdorf, 28W402 - RB-Grenze km 117,357 - Erfurt Hbf - Leipzig Hbf, Gl 12 (Gröbers - Lpz-Mockau Personenzugbahn)","<","Eltersdorf","Eltersdorf",2023,2023,20,20,"2023-05-18","21:00:00","2023-05-19","05:00:00","0d, 8h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-06-22"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsb Rbf Nord","Augsburg Hbf",2023,2023,21,21,"2023-05-25","12:00:00","2023-05-25","17:00:00","0d, 5h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Ludwigsburg","Ludwigsburg",2023,2023,21,21,"2023-05-28","02:00:00","2023-05-28","03:00:00","0d, 1h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-04"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Kornwestheim Pbf","Ludwigsburg",2023,2023,21,21,"2023-05-28","02:00:00","2023-05-28","03:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2021-05-04"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Bietigheim-Biss","Bietigheim-Biss",2023,2023,21,23,"2023-05-26","00:01:00","2023-06-09","23:59:00","14d, 23h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-04"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Mü Hbf tief",2023,2023,21,22,"2023-05-26","23:00:00","2023-05-30","04:00:00","3d, 5h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-01-04"]
[null,80,"München Hbf tief - München Ost Pbf","<","München Ost Pbf","München Ost Pbf",2023,2023,21,22,"2023-05-26","23:00:00","2023-05-30","04:30:00","3d, 5h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-19"]
[null,80,"München Hbf - Rosenheim",">","München Süd","München Ost Pbf",2023,2023,20,20,"2023-05-20","19:00:00","2023-05-21","05:00:00","0d, 10h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-10-08"]
[null,80,"München Hbf - Rosenheim",">","München Ost Pbf","München Ost Pbf",2023,2023,20,20,"2023-05-20","19:00:00","2023-05-21","05:00:00","0d, 10h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-13"]
[null,80,"München Hbf - Rosenheim","<","München Ost Pbf","München Süd",2023,2023,20,20,"2023-05-21","05:00:00","2023-05-21","08:00:00","0d, 3h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-10-08"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<>","Nür-Langwasser","Nür-Dutzendteich",2023,2023,20,20,"2023-05-17","13:00:00","2023-05-18","13:00:00","1d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<","Nür-Dutzendteich","Nür-Langwasser",2023,2023,20,21,"2023-05-17","20:00:00","2023-05-24","08:00:00","6d, 12h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<>","Nür-Langwasser","Nür-Dutzendteich",2023,2023,20,21,"2023-05-17","20:00:00","2023-05-24","08:00:00","6d, 12h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<","Nür-Dutzendteich","Nür-Langwasser",2023,2023,20,20,"2023-05-18","13:00:00","2023-05-19","03:00:00","0d, 14h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"11,11,",null,null,"80","N","2021-05-12"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307","<>","Nür-Langwasser","Nür-Dutzendteich",2023,2023,21,21,"2023-05-25","02:00:00","2023-05-25","08:00:00","0d, 6h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","München Ost Pbf",2023,2023,22,22,"2023-05-29","22:40:00","2023-05-30","04:40:00","0d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-20"]
[null,80,"München Hbf  - Lenggries","<>","München Hbf","Mü Heimeranplatz",2023,2023,22,22,"2023-05-29","22:40:00","2023-05-30","04:40:00","0d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-05-16"]
[null,80,"Nürnberg Hbf - Bamberg","<","Hirschaid","Forchheim (Ofr)",2023,2023,20,20,"2023-05-19","20:00:00","2023-05-20","04:00:00","0d, 8h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2022-07-07"]
[null,80,"Strullendorf, 21W01 - Frensdorf (-Ebrach), Gl 1, G-Bahn","<>","Strullendorf","Strullendorf",2023,2023,20,20,"2023-05-20","20:00:00","2023-05-21","04:00:00","0d, 8h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-07"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Karlsruhe Hbf","Karlsr-Durlach",2023,2023,22,49,"2023-05-30","05:00:00","2023-12-09","23:59:00","193d, 19h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,"80","N","2021-05-04"]
[null,80,"München Ost Pbf, W 131 - Simbach (Inn) Grenze",">","München Ost Pbf","München Ost Pbf",2023,2023,20,20,"2023-05-21","05:00:00","2023-05-21","08:00:00","0d, 3h","continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-13"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt-Süd","Baden-Baden",2023,2023,22,22,"2023-05-29","23:00:00","2023-06-03","04:55:00","4d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<>","Burgweinting","Obertraubling",2023,2023,21,22,"2023-05-27","23:00:00","2023-05-30","05:00:00","2d, 6h","periodical continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,21,22,"2023-05-28","05:00:00","2023-05-30","14:00:00","2d, 9h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Obertraubling","Obertraubling",2023,2023,21,22,"2023-05-28","05:00:00","2023-05-30","14:00:00","2d, 9h","periodical continuous","Catenary",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106",">","Obertraubling","Regensbg Ost",2023,2023,22,22,"2023-05-30","23:00:00","2023-05-31","04:50:00","0d, 5h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Obertraubling","Köfering",2023,2023,20,20,"2023-05-20","04:50:00","2023-05-20","14:00:00","0d, 9h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,20,21,"2023-05-20","23:00:00","2023-05-24","04:50:00","3d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Obertraubling","Obertraubling",2023,2023,20,21,"2023-05-20","23:00:00","2023-05-24","04:50:00","3d, 5h","periodical continuous","Catenary",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2022-07-15"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-17","00:00:00","2023-05-17","02:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-17","00:00:00","2023-05-17","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-17","03:00:00","2023-05-17","05:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-17","03:00:00","2023-05-17","05:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-21","01:00:00","2023-05-21","03:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,20,20,"2023-05-21","03:00:00","2023-05-21","05:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-21","05:00:00","2023-05-21","10:00:00","0d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-12-10"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<","Fürth-Burgfbach","Fürth (Bay) Hbf",2023,2023,21,21,"2023-05-22","05:00:00","2023-05-22","10:00:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-12-15"]
[null,80,"Nürnberg Hbf, W 286 - Fürth (Bay) Gbf, DKW 116  (Südgleis)","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2023,2023,20,20,"2023-05-20","13:30:00","2023-05-20","18:00:00","0d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-12-11"]
[null,80,"München Hbf tief - München Ost Pbf","<>","Mü Hbf tief","München Ost Pbf",2023,2023,21,22,"2023-05-26","23:00:00","2023-05-30","04:00:00","3d, 5h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-26"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 907","<>","N-Edingen/F-feld","M-Fr Südein/Ausf",2023,2023,20,20,"2023-05-16","21:00:00","2023-05-20","05:00:00","3d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,20,21,"2023-05-20","21:00:00","2023-05-22","05:00:00","1d, 8h","periodical continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,21,21,"2023-05-22","02:00:00","2023-05-26","05:00:00","4d, 3h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","N-Edingen/F-feld","N-Edingen/F-feld",2023,2023,21,21,"2023-05-22","02:00:00","2023-05-26","05:00:00","4d, 3h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Heddesheim/Hberg","Weinheim Hbf",2023,2023,21,21,"2023-05-22","21:00:00","2023-05-27","05:00:00","4d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Weinheim (Bergstr) Hbf, W 95 - Fürth (Odenw)","<>","Weinheim Hbf","Weinheim Hbf",2023,2023,21,21,"2023-05-22","21:00:00","2023-05-27","05:00:00","4d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,24,25,"2023-06-12","07:00:00","2023-06-19","07:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,22,22,"2023-06-02","18:00:00","2023-06-02","19:00:00","0d, 1h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-06-08"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<>","München Ost Pbf","München-Giesing",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-19"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf","<>","Mü-Berg a L Abzw","Mü-Trudering",2023,2023,23,24,"2023-06-07","22:20:00","2023-06-12","04:20:00","4d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-19"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,23,23,"2023-06-05","22:50:00","2023-06-06","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,23,24,"2023-06-08","23:30:00","2023-06-12","05:00:00","3d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-13"]
[null,80,"Nürnberg Hbf - Bamberg","<","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,25,25,"2023-06-19","05:00:00","2023-06-20","05:00:00","1d, 0h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-12"]
[null,80,"Nürnberg Hbf - Bamberg",">","Fürth (Bay) Hbf","Fürth (Bay) Gbf",2023,2023,23,23,"2023-06-11","13:00:00","2023-06-11","19:00:00","0d, 6h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-11"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,23,24,"2023-06-11","22:00:00","2023-06-12","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Plochingen","Göppingen",2023,2023,26,26,"2023-06-27","22:00:00","2023-06-28","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Sünching",2023,2023,23,24,"2023-06-11","22:00:00","2023-06-16","05:00:00","4d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-12"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,23,23,"2023-06-06","05:00:00","2023-06-06","15:00:00","0d, 10h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-08-05"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Stuttgart Hbf","Kornwestheim Pbf",2023,2023,24,25,"2023-06-18","23:00:00","2023-06-20","05:00:00","1d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-07"]
[null,80,"Backnang, W 69 - Ludwigsburg, W 64","<>","Freiberg/Neckar","Ludwigsburg",2023,2023,22,23,"2023-06-03","01:40:00","2023-06-05","04:50:00","2d, 3h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-16"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Heppenhm/Bergstr",2023,2023,24,48,"2023-06-18","06:00:00","2023-12-03","13:00:00","168d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-12-02"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,25,25,"2023-06-20","00:00:00","2023-06-21","11:00:00","1d, 11h","periodical continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-12-16"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn",">","Hohe Marter","Fürth (Bay) Gbf",2023,2023,23,23,"2023-06-10","03:00:00","2023-06-10","06:00:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,",null,null,"80","N","2021-12-15"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,24,26,"2023-06-16","22:00:00","2023-06-26","06:00:00","9d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-26"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,24,26,"2023-06-16","22:00:00","2023-06-26","06:00:00","9d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-18"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,23,26,"2023-06-05","06:00:00","2023-06-28","18:00:00","23d, 12h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-26"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Westerstetten","Beimerstetten",2023,2023,25,25,"2023-06-24","05:00:00","2023-06-25","21:00:00","1d, 16h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Beimerstetten","Westerstetten",2023,2023,25,28,"2023-06-23","21:00:00","2023-07-10","05:00:00","16d, 8h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Geislingen (St)","Geislingen (St)",2023,2023,25,28,"2023-06-19","00:00:00","2023-07-15","00:00:00","26d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-17"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,25,25,"2023-06-19","22:50:00","2023-06-20","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Sünching","Sünching",2023,2023,25,25,"2023-06-20","22:00:00","2023-06-24","05:00:00","3d, 7h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-06-01"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Sünching","Sünching",2023,2023,25,26,"2023-06-24","05:00:00","2023-06-28","05:00:00","4d, 0h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,"80","N","2021-08-04"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Mangolding",2023,2023,23,24,"2023-06-10","20:00:00","2023-06-18","06:00:00","7d, 10h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-06-01"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023,2023,26,26,"2023-06-26","06:00:00","2023-06-26","09:00:00","0d, 3h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-07"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,26,26,"2023-06-26","03:00:00","2023-06-26","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"München Hbf - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,25,25,"2023-06-20","02:35:00","2023-06-20","03:10:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-04-15"]
[null,80,"München Hbf - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,25,25,"2023-06-20","03:25:00","2023-06-20","04:05:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-04-15"]
[null,80,"Bft Gemünden Zollberg Abzw, W 291 - Langenprozelten, W 401, G-Bahn","<>","Zollberg","Langenprozelten",2023,2023,24,24,"2023-06-13","03:30:00","2023-06-13","05:30:00","0d, 2h","continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-30"]
[null,80,"Waigolshausen, W 6 - Gemünden (Main)","<>","Wernfeld","Wernfeld",2023,2023,24,24,"2023-06-12","00:00:00","2023-06-12","07:00:00","0d, 7h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-18"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühlacker",2023,2023,26,26,"2023-06-27","22:00:00","2023-06-28","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15",">","Reichswald","Allersb(Rothsee)",2023,2023,25,25,"2023-06-19","20:40:00","2023-06-20","04:45:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,"80","N","2021-11-24"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Langenprozelten","Lohr Bahnhof",2023,2023,25,26,"2023-06-25","23:30:00","2023-06-26","02:20:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-19"]
[null,80,"Abzw Nantenbach - Rohrbach","<","Nantenbach","Rohrbach",2023,2023,26,26,"2023-06-26","02:20:00","2023-06-26","05:10:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,"80","N","2022-02-08"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Dinkelscherben","Gessertshausen",2023,2023,24,24,"2023-06-16","22:45:00","2023-06-17","01:15:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Gessertshausen","Dinkelscherben",2023,2023,24,24,"2023-06-17","01:15:00","2023-06-17","05:30:00","0d, 4h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Dinkelscherben","Freihalden Üst",2023,2023,24,24,"2023-06-18","01:30:00","2023-06-18","02:45:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Gessertshausen","Dinkelscherben",2023,2023,24,25,"2023-06-18","22:35:00","2023-06-19","00:00:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Dinkelscherben","Gessertshausen",2023,2023,25,25,"2023-06-23","22:20:00","2023-06-24","01:00:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Gessertshausen","Dinkelscherben",2023,2023,25,25,"2023-06-24","01:00:00","2023-06-24","05:30:00","0d, 4h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Gessertshausen","Dinkelscherben",2023,2023,25,25,"2023-06-24","22:15:00","2023-06-25","00:00:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Dinkelscherben","Gessertshausen",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","00:00:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Gessertshausen, W 52W6 - Türkheim (Bay) Bahnhof, W 523","<>","Gessertshausen","Gessertshausen",2023,2023,26,26,"2023-06-26","00:00:00","2023-06-26","05:10:00","0d, 5h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Gessertshausen","Gessertshausen",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-26","05:10:00","0d, 7h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Sünching","Sünching",2023,2023,23,24,"2023-06-11","20:00:00","2023-06-17","06:00:00","5d, 10h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-08-16"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","N-Edingen/F-feld","Heidelb-Wiebl",2023,2023,22,23,"2023-06-02","23:00:00","2023-06-09","05:00:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-14"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Kornwestheim Pbf","Ludwigsburg",2023,2023,22,23,"2023-06-03","01:40:00","2023-06-05","02:40:00","2d, 1h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-11-08"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Ludwigsburg","Ludwigsburg",2023,2023,22,23,"2023-06-03","01:40:00","2023-06-05","02:40:00","2d, 1h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-10-06"]
[null,80,"Backnang, W 69 - Ludwigsburg, W 64",">","Favoritepark RWE","Ludwigsburg",2023,2023,22,23,"2023-06-03","01:40:00","2023-06-05","04:50:00","2d, 3h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-04"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Kornwestheim Pbf","Ludwigsburg",2023,2023,23,23,"2023-06-08","03:00:00","2023-06-08","04:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-04"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,23,24,"2023-06-08","23:00:00","2023-06-15","05:00:00","6d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Schirnding (DB-Grenze) - Cheb/SZDC","<>","Schirnding Grenz","Cheb",2023,2023,24,39,"2023-06-12","22:50:00","2023-09-25","04:50:00","104d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54,80,54","N","2021-11-26"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270",">","Kornwestheim Pbf","Bietigheim-Biss",2023,2023,22,23,"2023-06-03","02:40:00","2023-06-05","03:40:00","2d, 1h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-05-04"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,25,25,"2023-06-20","00:00:00","2023-06-23","05:00:00","3d, 5h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,25,26,"2023-06-23","23:30:00","2023-06-26","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,25,26,"2023-06-23","23:30:00","2023-06-26","04:30:00","2d, 5h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München-Giesing",2023,2023,25,26,"2023-06-24","01:30:00","2023-06-26","04:30:00","2d, 3h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,26,27,"2023-06-29","00:00:00","2023-07-07","05:00:00","8d, 5h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","München Ost Pbf","München Ost Pbf",2023,2023,26,27,"2023-06-30","23:30:00","2023-07-03","04:30:00","2d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München-Giesing",2023,2023,26,26,"2023-06-30","23:30:00","2023-07-01","04:30:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,23,23,"2023-06-06","01:30:00","2023-06-06","05:30:00","0d, 4h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-05"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,23,24,"2023-06-07","01:30:00","2023-06-14","05:30:00","7d, 4h","periodical continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-05-05"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,24,24,"2023-06-12","04:30:00","2023-06-12","05:30:00","0d, 1h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-05"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,24,24,"2023-06-12","04:30:00","2023-06-12","05:30:00","0d, 1h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-05"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Plochingen","Plochingen",2023,2023,24,24,"2023-06-12","03:30:00","2023-06-12","04:30:00","0d, 1h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-05"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,25,25,"2023-06-23","23:30:00","2023-06-24","04:30:00","0d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Rastatt-Süd",2023,2023,23,23,"2023-06-05","23:00:00","2023-06-08","05:00:00","2d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2023,2023,23,23,"2023-06-08","23:00:00","2023-06-11","05:00:00","2d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-02"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,25,26,"2023-06-24","15:00:00","2023-06-26","03:40:00","1d, 12h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Obertraubling","Regensbg Ost",2023,2023,24,25,"2023-06-17","23:00:00","2023-06-22","04:50:00","4d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106",">","Köfering","Regensbg Ost",2023,2023,24,25,"2023-06-17","23:00:00","2023-06-22","04:50:00","4d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2022-07-15"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensbg Ost","Obertraubling",2023,2023,25,27,"2023-06-22","22:50:00","2023-07-05","04:15:00","12d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,25,26,"2023-06-23","04:15:00","2023-06-29","14:00:00","6d, 9h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Obertraubling","Obertraubling",2023,2023,26,27,"2023-06-30","04:15:00","2023-07-05","14:00:00","5d, 9h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-15"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Neumarkt(Oberpf)","Postbauer-Heng",2023,2023,22,22,"2023-06-03","23:50:00","2023-06-04","05:40:00","0d, 5h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-28"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,23,24,"2023-06-11","23:00:00","2023-06-17","04:30:00","5d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-20"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<","Fürth-Burgfbach","Fürth (Bay) Hbf",2023,2023,23,23,"2023-06-08","23:30:00","2023-06-09","01:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<","Fürth-Burgfbach","Fürth (Bay) Hbf",2023,2023,23,23,"2023-06-09","01:00:00","2023-06-09","02:30:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2023,2023,24,25,"2023-06-12","05:00:00","2023-06-19","05:00:00","7d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,24,25,"2023-06-12","05:00:00","2023-06-19","05:00:00","7d, 0h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,25,26,"2023-06-23","23:00:00","2023-06-26","05:00:00","2d, 6h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,"80","N"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2023,2023,24,24,"2023-06-12","03:00:00","2023-06-12","05:00:00","0d, 2h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,27,27,"2023-07-03","03:00:00","2023-07-03","06:00:00","0d, 3h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Plochingen","<>","Plochingen","Plochingen",2023,2023,28,29,"2023-07-14","18:00:00","2023-07-21","18:00:00","7d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-06-08"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsb-Oberhausen","Augsb Hirbl Str",2023,2023,30,30,"2023-07-28","23:30:00","2023-07-29","02:00:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen","<","Gersthofen","Augsburg Hbf",2023,2023,29,30,"2023-07-21","22:00:00","2023-07-29","04:00:00","7d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-13"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,30,31,"2023-07-29","06:00:00","2023-07-31","09:00:00","2d, 3h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-08-13"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,30,30,"2023-07-24","03:00:00","2023-07-24","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,28,28,"2023-07-10","23:20:00","2023-07-11","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,30,30,"2023-07-24","22:50:00","2023-07-25","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,28,28,"2023-07-15","22:00:00","2023-07-16","01:00:00","0d, 3h","continuous",null,null,null,null,null,"X",",,",",,",null,"2,2,2",null,null,"80","N","2021-08-02"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Stuttgart Hbf","Kornwestheim Pbf",2023,2023,27,27,"2023-07-04","20:00:00","2023-07-05","05:00:00","0d, 9h","continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-07"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Neumarkt(Oberpf)","Seubersdorf",2023,2023,27,27,"2023-07-03","02:00:00","2023-07-03","05:00:00","0d, 3h","continuous",null,null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-16"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,29,30,"2023-07-23","22:00:00","2023-07-24","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<>","Nür Großmarkt","Fürth (Bay) Gbf",2023,2023,27,27,"2023-07-07","00:00:00","2023-07-09","06:00:00","2d, 6h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-16"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,28,28,"2023-07-10","22:00:00","2023-07-11","05:00:00","0d, 7h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-02"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Westerstetten","Beimerstetten",2023,2023,27,27,"2023-07-08","05:00:00","2023-07-09","21:00:00","1d, 16h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Geislingen West",2023,2023,26,26,"2023-07-01","05:00:00","2023-07-02","21:00:00","1d, 16h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-17"]
[null,null,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Karlstadt (Main)","Gemünden (Main)",2023,2023,49,49,"2023-12-05","23:00:00","2023-12-09","05:00:00","3d, 6h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-02"]
[null,null,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,40,49,"2023-10-02","21:00:00","2023-12-09","23:59:00","68d, 3h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2021-08-24"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Sünching","Obertraubling",2023,2023,28,28,"2023-07-12","22:00:00","2023-07-15","05:00:00","2d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-12"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,30,30,"2023-07-25","22:00:00","2023-07-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,29,29,"2023-07-17","22:50:00","2023-07-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,29,29,"2023-07-17","22:50:00","2023-07-18","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,27,28,"2023-07-09","22:00:00","2023-07-10","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Parsberg","Undorf",2023,2023,28,28,"2023-07-14","03:00:00","2023-07-14","05:00:00","0d, 2h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-02"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Undorf","Beratzhausen",2023,2023,27,28,"2023-07-06","22:00:00","2023-07-14","05:00:00","7d, 7h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-03"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Parsberg","Undorf",2023,2023,27,27,"2023-07-06","22:00:00","2023-07-07","00:00:00","0d, 2h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-02"]
[null,80,"Regensburg Hbf, W 90 - Weiden (Oberpf)",">","Regensburg Hbf","Regensbg Walhal",2023,2023,28,29,"2023-07-14","22:45:00","2023-07-17","04:20:00","2d, 5h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,"80","N","2022-07-19"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Zorneding","Grafing Bahnhof",2023,2023,30,30,"2023-07-28","02:10:00","2023-07-28","02:50:00","0d, 0h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,"80","N","2022-07-21"]
[null,80,"München Hbf - Rosenheim","<","Grafing Bahnhof","Kirchseeon",2023,2023,30,30,"2023-07-28","23:30:00","2023-07-29","00:30:00","0d, 1h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Grafing Bahnhof",2023,2023,30,30,"2023-07-28","23:30:00","2023-07-29","04:40:00","0d, 5h","continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Grafing Bahnhof",2023,2023,30,30,"2023-07-30","02:00:00","2023-07-30","03:10:00","0d, 1h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Grafing Bahnhof",2023,2023,30,31,"2023-07-30","22:30:00","2023-07-31","05:00:00","0d, 6h","continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühlacker",2023,2023,30,30,"2023-07-25","22:00:00","2023-07-26","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15","<","Allersb(Rothsee)","Reichswald",2023,2023,27,27,"2023-07-03","20:50:00","2023-07-04","05:00:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",5,",null,null,"80","N","2021-11-24"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Nür-Dutzendteich","Reichswald",2023,2023,27,27,"2023-07-05","20:50:00","2023-07-06","04:50:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N","2021-11-24"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<","Reichswald","Feucht",2023,2023,27,27,"2023-07-06","20:40:00","2023-07-07","04:45:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,"80","N","2021-11-24"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15","<","Allersb(Rothsee)","Reichswald",2023,2023,28,28,"2023-07-11","20:50:00","2023-07-12","05:00:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",5,",null,null,"80","N","2021-11-24"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Reichswald","Reichswald",2023,2023,28,28,"2023-07-11","20:50:00","2023-07-12","05:00:00","0d, 8h","periodical continuous","Signal",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-11-24"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf",">","Reichswald","Allersb(Rothsee)",2023,2023,28,28,"2023-07-13","20:40:00","2023-07-14","04:45:00","0d, 8h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,",3,",null,null,"80","N","2021-11-24"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rückstetten","Traunstein",2023,2023,29,30,"2023-07-23","23:59:00","2023-07-24","01:45:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Lauter","Traunstein",2023,2023,29,30,"2023-07-23","23:59:00","2023-07-24","06:00:00","0d, 6h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Dinkelscherben","Dinkelscherben",2023,2023,27,27,"2023-07-03","21:20:00","2023-07-04","00:30:00","0d, 3h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-19"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Dinkelscherben","Freihalden Üst",2023,2023,27,27,"2023-07-05","00:30:00","2023-07-05","04:00:00","0d, 3h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,"80","N","2022-01-21"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<>","Dinkelscherben","Dinkelscherben",2023,2023,27,27,"2023-07-05","23:15:00","2023-07-06","01:45:00","0d, 2h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"Nürnberg Hbf - Schirnding Grenze","<","Neuhaus(Pegnitz)","Vorra (Pegnitz)",2023,2023,27,28,"2023-07-08","00:20:00","2023-07-10","04:10:00","2d, 3h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-04-16"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsburg Hbf","Westheim/Schwab",2023,2023,29,29,"2023-07-17","22:25:00","2023-07-20","05:10:00","2d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-07-26"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,28,30,"2023-07-15","22:00:00","2023-07-24","06:00:00","8d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Augsburg Hbf - Gleis 970 - Bft Au-Oberhausen","<>","Augsb-Oberhausen","Augsburg Hbf",2023,2023,29,29,"2023-07-21","22:00:00","2023-07-22","00:30:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-16"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Augsb-Oberhausen","Augsb-Oberhausen",2023,2023,30,31,"2023-07-29","06:00:00","2023-07-31","04:00:00","1d, 22h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-08-13"]
[null,80,"München Hbf  - Lenggries",">","Mü Heimeranplatz","München-Solln",2023,2023,30,30,"2023-07-24","23:30:00","2023-07-28","04:50:00","3d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,3",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Bietigheim-Bissingen, W270","<>","Ludwigsburg","Ludwigsburg",2023,2023,29,29,"2023-07-17","00:10:00","2023-07-17","04:50:00","0d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-05-04"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München Ost Pbf","München Ost Pbf",2023,2023,27,28,"2023-07-06","22:00:00","2023-07-10","22:00:00","4d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Rosenheim","<","Mü-Trudering","München Ost Pbf",2023,2023,27,28,"2023-07-07","23:30:00","2023-07-11","05:30:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-05-17"]
[null,80,"Bft Dürrenhof, W 60  - Feucht, 51W108","<>","Nür Frankenstad","Feucht",2023,2023,30,31,"2023-07-30","22:00:00","2023-07-31","04:20:00","0d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-29"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,28,28,"2023-07-11","01:30:00","2023-07-13","04:30:00","2d, 3h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,27,28,"2023-07-07","23:30:00","2023-07-10","04:30:00","2d, 5h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)",">","München-Pasing","Gauting",2023,2023,29,29,"2023-07-21","22:00:00","2023-07-23","06:00:00","1d, 8h","periodical continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2022-07-25"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<>","München-Pasing","München-Pasing",2023,2023,29,29,"2023-07-21","22:00:00","2023-07-23","06:00:00","1d, 8h","periodical continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,"80","N","2022-07-25"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,27,27,"2023-07-03","07:00:00","2023-07-09","19:00:00","6d, 12h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Mangolding","Obertraubling",2023,2023,28,28,"2023-07-15","21:45:00","2023-07-16","13:30:00","0d, 15h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-15"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Blankenloch","Karlsr-Hagsfeld",2023,2023,26,27,"2023-07-02","23:00:00","2023-07-03","05:00:00","0d, 6h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf","Ulm Hbf",2023,2023,30,30,"2023-07-24","01:30:00","2023-07-24","04:30:00","0d, 3h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-21"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,27,27,"2023-07-03","23:00:00","2023-07-07","04:30:00","3d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-20"]
[null,80,"Mühldorf (Oberbay) 41W91 - Freilassing, W 204","<>","Freilassing","Freilassing",2023,2023,29,29,"2023-07-20","00:00:00","2023-07-20","05:00:00","0d, 5h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,29,29,"2023-07-21","00:00:00","2023-07-21","05:00:00","0d, 5h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Freilassing","Freilassing",2023,2023,29,29,"2023-07-21","00:00:00","2023-07-21","02:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,29,29,"2023-07-21","00:00:00","2023-07-21","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,30,30,"2023-07-24","19:00:00","2023-07-25","05:00:00","0d, 10h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-04-26"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,33,34,"2023-08-20","22:00:00","2023-08-21","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,34,34,"2023-08-21","23:20:00","2023-08-22","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,33,33,"2023-08-14","22:50:00","2023-08-15","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Olching - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,34,35,"2023-08-26","23:30:00","2023-08-28","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"München Hbf - Augsburg Hbf","<>","Augsb Haunst str","Augsburg Hbf",2023,2023,34,35,"2023-08-26","23:30:00","2023-08-28","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Plochingen","Göppingen",2023,2023,35,35,"2023-08-29","22:00:00","2023-08-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Süßen",2023,2023,35,35,"2023-08-29","22:00:00","2023-08-30","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,35,35,"2023-08-28","22:50:00","2023-08-29","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,32,32,"2023-08-07","23:30:00","2023-08-08","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Karlstadt (Main)","Gemünden (Main)",2023,2023,33,35,"2023-08-16","23:00:00","2023-09-03","05:00:00","17d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-06-02"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,34,34,"2023-08-22","22:00:00","2023-08-23","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,31,31,"2023-07-31","22:50:00","2023-08-01","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143",">","Darmstadt Hbf","Messel",2023,2023,34,34,"2023-08-25","22:00:00","2023-08-26","06:00:00","0d, 8h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-11"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,34,34,"2023-08-26","22:00:00","2023-08-27","06:00:00","0d, 8h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-26"]
[null,80,"München Hbf - Rosenheim","<","Grafing Bahnhof","Zorneding",2023,2023,31,31,"2023-08-01","03:20:00","2023-08-01","04:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim",">","Zorneding","Grafing Bahnhof",2023,2023,31,31,"2023-08-02","00:40:00","2023-08-02","02:10:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<","Zorneding","Haar",2023,2023,31,31,"2023-08-05","01:40:00","2023-08-05","03:20:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<","Kirchseeon","Haar",2023,2023,31,31,"2023-08-05","01:40:00","2023-08-05","02:20:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,"80","N","2022-07-19"]
[null,80,"Fürth (Bay) Hbf, W 144 - Cadolzburg","<>","Fürth (Bay) Hbf","Zirndorf",2023,2023,31,33,"2023-07-31","23:30:00","2023-08-19","05:30:00","18d, 6h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-03-29"]
[null,80,"Abzw Berg am Laim, W 72 - Grafing Bf",">","Zorneding","Grafing Bahnhof",2023,2023,31,31,"2023-08-06","03:40:00","2023-08-06","04:25:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,12",null,null,"80","N","2022-01-10"]
[null,80,"München Hbf - Rosenheim","<>","Haar","Haar",2023,2023,32,32,"2023-08-09","00:50:00","2023-08-09","04:50:00","0d, 4h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2022-07-19"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72",">","Mü-Trudering","Mü-Waldtrudering",2023,2023,32,32,"2023-08-08","23:45:00","2023-08-09","00:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim",">","Haar","Zorneding",2023,2023,32,32,"2023-08-09","23:00:00","2023-08-10","00:00:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<>","Haar","Haar",2023,2023,32,32,"2023-08-09","23:00:00","2023-08-10","04:55:00","0d, 5h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Aßling/Obb",2023,2023,31,31,"2023-07-31","02:20:00","2023-07-31","03:30:00","0d, 1h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München Ost Pbf","München Ost Pbf",2023,2023,31,34,"2023-08-03","10:00:00","2023-08-26","14:00:00","23d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-25"]
[null,80,"München Ost Pbf, W 211 - Mü-Giesing, W 421","<>","München-Giesing","München Ost Pbf",2023,2023,33,33,"2023-08-14","23:00:00","2023-08-16","04:00:00","1d, 5h","continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-25"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800",">","StrWe 4800/4842","Illingen (Württ)",2023,2023,34,34,"2023-08-22","22:00:00","2023-08-23","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Augsburg Hbf - Nördlingen","<","Augsb-Oberhausen","Augsburg Hbf",2023,2023,34,48,"2023-08-27","04:30:00","2023-12-03","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-17"]
[null,80,"München Hbf - Augsburg Hbf",">","Augsb Haunst str","Augsburg Hbf",2023,2023,34,48,"2023-08-27","04:30:00","2023-12-03","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-17"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277",">","Augsburg Hbf","Augsb Hirbl Str",2023,2023,34,48,"2023-08-27","04:30:00","2023-12-03","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-12-17"]
[null,80,"Augsburg Hbf - Gleis 970 - Bft Au-Oberhausen","<>","Augsburg Hbf","Augsb-Oberhausen",2023,2023,34,35,"2023-08-26","23:30:00","2023-08-28","04:30:00","1d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"Augsburg Hbf - Gleis 970 - Bft Au-Oberhausen","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,35,36,"2023-08-28","23:30:00","2023-09-06","05:00:00","8d, 5h","periodical continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","München-Daglfing","Mü-Trudering",2023,2023,31,32,"2023-08-06","22:30:00","2023-08-07","04:20:00","0d, 5h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsburg Hbf","Westheim/Schwab",2023,2023,31,31,"2023-07-31","22:25:00","2023-08-03","05:10:00","2d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-22"]
[null,80,"Schirnding (DB-Grenze) - Cheb/SZDC","<>","Schirnding Grenz","Cheb",2023,2023,31,31,"2023-08-03","08:00:00","2023-08-06","18:00:00","3d, 10h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54,80,54","N","2021-09-01"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<>","Augsburg Hbf","Augsb Rbf Mitte",2023,2023,34,34,"2023-08-26","20:00:00","2023-08-27","06:00:00","0d, 10h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-05"]
[null,80,"München Hbf  - Lenggries","<","München-Solln","Mü Heimeranplatz",2023,2023,31,31,"2023-07-31","23:40:00","2023-08-04","04:45:00","3d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Feucht","Feucht",2023,2023,31,33,"2023-07-31","06:00:00","2023-08-20","22:00:00","20d, 16h","periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-04-29"]
[null,80,"Feucht, 51W111 - Altdorf (b Nürnberg), Gl 1","<>","Feucht","Feucht-Moosbach",2023,2023,33,34,"2023-08-20","22:00:00","2023-08-21","04:20:00","0d, 6h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-29"]
[null,80,"Regensburg Hbf (Bft Bbf), W 455 - Ingolstadt Nord, 20W32","<>","Regensburg Bbf","Sinzing/Regensbg",2023,2023,32,33,"2023-08-11","21:30:00","2023-08-14","04:00:00","2d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-11-03"]
[null,80,"Regensburg Hbf (Bft Bbf), W 455 - Ingolstadt Nord, 20W32","<>","Regensburg Bbf","Sinzing/Regensbg",2023,2023,33,34,"2023-08-18","21:30:00","2023-08-21","04:00:00","2d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-11-03"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<>","Gauting","München-Pasing",2023,2023,34,35,"2023-08-27","04:00:00","2023-08-30","13:00:00","3d, 9h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,"80","N","2021-11-18"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","Ludwigsburg",2023,2023,34,35,"2023-08-25","22:30:00","2023-09-03","04:50:00","8d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,"80","N","2021-04-29"]
[null,80,"Ludwigsburg, W 4 - Markgröningen, Gl 2","<>","Ludwigsburg","Ludwigsb DB/Lott",2023,2023,34,36,"2023-08-25","22:30:00","2023-09-04","05:00:00","9d, 6h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-29"]
[null,80,"Ludwigsburg, W 4 - Markgröningen, Gl 2","<>","Ludwigsburg","Ludwigsb DB/Lott",2023,2023,34,36,"2023-08-25","22:30:00","2023-09-04","05:00:00","9d, 6h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-29"]
[null,80,"München Hbf tief - Gauting, 35W22","<>","München-Pasing","Germering-Upfhfn",2023,2023,31,32,"2023-08-04","22:00:00","2023-08-07","05:00:00","2d, 7h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-10"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf","Ulm Hbf",2023,2023,31,32,"2023-08-06","21:00:00","2023-08-07","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-21"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Burgau (Schwab)","Neuoffingen",2023,2023,34,35,"2023-08-24","23:00:00","2023-08-28","05:00:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-20"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm Hbf","Neu-Ulm",2023,2023,34,35,"2023-08-24","23:00:00","2023-08-28","05:00:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-12-07"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Karlsr-Durlach","Karlsruhe Hbf",2023,2023,31,32,"2023-08-05","23:00:00","2023-08-07","04:30:00","1d, 5h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,32,32,"2023-08-12","23:00:00","2023-08-13","03:20:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,32,34,"2023-08-13","23:00:00","2023-08-21","04:30:00","7d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,32,34,"2023-08-13","23:00:00","2023-08-21","04:30:00","7d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,34,34,"2023-08-26","23:00:00","2023-08-27","04:00:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,34,35,"2023-08-27","23:00:00","2023-08-28","04:30:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Fürth (Bay) Hbf, 11W154 - Würzburg Hbf","<>","Fürth (Bay) Hbf","Fürth-Burgfbach",2023,2023,32,32,"2023-08-08","08:00:00","2023-08-08","14:30:00","0d, 6h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Landshut (Bay) Hbf - Bayerisch Eisenstein, Gl 4(DB-Grenze)","<>","Plattling","Grafling",2023,2023,34,35,"2023-08-23","22:00:00","2023-08-31","04:00:00","7d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,31,31,"2023-08-02","00:00:00","2023-08-02","02:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,31,31,"2023-08-02","01:00:00","2023-08-02","03:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Augsburg Hbf, W 130 - Augsburg Morellstraße, W 935","<>","Augsburg Hbf","Augsburg Rbf Süd",2023,2023,34,48,"2023-08-27","04:30:00","2023-12-03","04:30:00","98d, 1h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,"80","N"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023,2023,39,41,"2023-09-25","18:00:00","2023-10-09","18:00:00","14d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","N-Edingen/F-feld","Schwetzingen",2023,2023,35,36,"2023-09-03","22:00:00","2023-09-04","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Partenstein","Lohr Bahnhof",2023,2023,38,42,"2023-09-23","14:00:00","2023-10-16","05:00:00","22d, 15h","periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-03-07"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2023,2023,38,38,"2023-09-18","05:00:00","2023-09-18","08:00:00","0d, 3h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,39,42,"2023-09-25","05:00:00","2023-10-17","12:00:00","22d, 7h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-07"]
[null,80,"Abzw Nantenbach - Rohrbach","<>","Rohrbach","Nantenbach",2023,2023,38,39,"2023-09-23","23:30:00","2023-09-25","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-02"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,36,36,"2023-09-04","22:50:00","2023-09-05","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,37,37,"2023-09-11","22:50:00","2023-09-12","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,37,37,"2023-09-11","22:50:00","2023-09-12","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Göppingen","Eislingen (Fils)",2023,2023,39,39,"2023-09-26","22:00:00","2023-09-27","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-15"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,36,36,"2023-09-04","23:20:00","2023-09-05","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Karlstadt (Main)","Gemünden (Main)",2023,2023,36,36,"2023-09-06","23:00:00","2023-09-09","05:00:00","2d, 6h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Nantenbach",2023,2023,39,40,"2023-09-29","22:00:00","2023-10-06","06:00:00","6d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-08-25"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,38,38,"2023-09-18","22:50:00","2023-09-19","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,36,36,"2023-09-05","22:00:00","2023-09-06","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143",">","Darmstadt Hbf","Messel",2023,2023,37,41,"2023-09-15","21:00:00","2023-10-13","21:00:00","28d, 0h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-26"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Obertraubling","Vilshofen(Nbay)",2023,2023,38,38,"2023-09-18","21:00:00","2023-09-22","05:00:00","3d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-01-22"]
[null,80,"Fürth (Bay) Hbf, W 144 - Cadolzburg","<>","Fürth (Bay) Hbf","Zirndorf",2023,2023,36,36,"2023-09-04","23:30:00","2023-09-08","05:30:00","3d, 6h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-03-29"]
[null,80,"Bamberg - Hof Hbf, W 121","<","Hallstadt(Bambg)","Bamberg",2023,2023,37,38,"2023-09-17","00:30:00","2023-09-18","05:00:00","1d, 4h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-14"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Rumgraben",2023,2023,37,37,"2023-09-13","06:00:00","2023-09-15","22:00:00","2d, 16h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-07"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rumgraben","Übersee",2023,2023,37,37,"2023-09-11","06:00:00","2023-09-12","22:00:00","1d, 16h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-07"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Mangolding",2023,2023,37,38,"2023-09-16","21:40:00","2023-09-18","04:40:00","1d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"15,15,15",null,null,"80","N","2022-07-21"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<","Mangolding","Radldorf (Nbay)",2023,2023,38,39,"2023-09-23","21:50:00","2023-09-25","05:00:00","1d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"13,,13",null,null,"80","N","2022-07-21"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Straubing","Sünching",2023,2023,38,38,"2023-09-18","20:50:00","2023-09-20","04:20:00","1d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,"80","N","2022-07-21"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Radldorf (Nbay)",2023,2023,38,38,"2023-09-18","20:50:00","2023-09-20","04:20:00","1d, 7h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-21"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Geiselhöring",2023,2023,39,39,"2023-09-25","23:35:00","2023-09-27","05:10:00","1d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-21"]
[null,80,"Neufahrn (Niederbay), W 3 - Radldorf (Niederbay), W 3","<>","Radldorf (Nbay)","Radldorf (Nbay)",2023,2023,39,39,"2023-09-27","23:00:00","2023-09-28","05:10:00","0d, 6h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-07-21"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800","<>","Maulbronn West","Mühlacker",2023,2023,36,44,"2023-09-08","22:00:00","2023-11-03","05:30:00","55d, 8h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-07-27"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<>","Olching","Olching",2023,2023,37,37,"2023-09-11","22:00:00","2023-09-12","05:00:00","0d, 7h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"Abzw Nürnberg Reichswald, 61W45 - Ingolstadt Nord, 20W15","<>","Allersb(Rothsee)","Reichswald",2023,2023,35,35,"2023-09-01","23:50:00","2023-09-02","05:50:00","0d, 6h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",5,",null,null,"80","N","2022-07-20"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6","<>","Schalding","Sandbach (Nbay)",2023,2023,39,40,"2023-09-30","22:40:00","2023-10-02","04:40:00","1d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Partenstein",2023,2023,38,42,"2023-09-23","14:00:00","2023-10-16","05:00:00","22d, 15h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-07"]
[null,80,"Nürnberg Hbf - Bamberg","<>","Fürth (Bay) Hbf","Forchheim (Ofr)",2023,2023,36,36,"2023-09-06","22:00:00","2023-09-07","05:00:00","0d, 7h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-05-25"]
[null,80,"Nürnberg Rbf A, Gl 303/304 - Nürnberg-Dutzendteich, Gl 306/307",">","Nür-Langwasser","Nür-Dutzendteich",2023,2023,35,35,"2023-09-03","05:00:00","2023-09-03","10:00:00","0d, 5h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,",null,null,"80","N","2021-05-12"]
[null,80,"Augsburg Hbf - Buchloe","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,35,35,"2023-09-01","22:00:00","2023-09-03","06:00:00","1d, 8h","periodical continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-05"]
[null,80,"Regensburg Hbf (Bft Bbf), W 455 - Ingolstadt Nord, 20W32","<>","Regensburg Bbf","Sinzing/Regensbg",2023,2023,35,36,"2023-09-01","21:30:00","2023-09-04","04:00:00","2d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-11-03"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","Ludwigsburg",2023,2023,36,36,"2023-09-05","01:30:00","2023-09-06","04:30:00","1d, 3h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,"80","N","2021-04-29"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,37,38,"2023-09-16","06:00:00","2023-09-18","03:45:00","1d, 21h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<>","Obertraubling","Regensburg Hbf",2023,2023,39,42,"2023-09-30","22:55:00","2023-10-22","05:10:00","21d, 6h","periodical continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-17"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,39,42,"2023-09-30","22:55:00","2023-10-22","05:10:00","21d, 6h","periodical continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-13"]
[null,80,"Ulm Hbf, W 101 - Friedrichshafen Stadt, W 262","<>","Ulm Hbf","Ulm Hbf",2023,2023,37,38,"2023-09-12","18:00:00","2023-09-18","06:00:00","5d, 12h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-05-21"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neuoffingen","Günzburg",2023,2023,35,36,"2023-08-31","23:00:00","2023-09-04","05:00:00","3d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,"80","N","2021-05-20"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,35,35,"2023-09-02","23:00:00","2023-09-03","01:20:00","0d, 2h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,35,35,"2023-09-03","01:20:00","2023-09-03","04:10:00","0d, 2h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,35,35,"2023-09-03","01:20:00","2023-09-03","04:10:00","0d, 2h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Karlsr-Durlach","Karlsruhe Hbf",2023,2023,35,38,"2023-09-03","23:00:00","2023-09-18","03:45:00","14d, 4h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Karlsr-Durlach","Karlsr-Durlach",2023,2023,38,38,"2023-09-23","23:00:00","2023-09-24","03:20:00","0d, 4h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<","Karlsruhe Hbf","Bruchsal",2023,2023,38,39,"2023-09-24","23:00:00","2023-09-25","03:30:00","0d, 4h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Karlsr-Durlach","Karlsr-Durlach",2023,2023,38,39,"2023-09-24","23:00:00","2023-09-25","03:30:00","0d, 4h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Durmersheim","Karlsruhe Hbf",2023,2023,38,39,"2023-09-24","23:00:00","2023-09-25","03:30:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,"22,22,22",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W912 - Abzw Karlsruhe-Dammerstock, W 401",">","Karlsruhe Gbf","Dammerstock",2023,2023,39,39,"2023-09-25","03:30:00","2023-09-25","05:50:00","0d, 2h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Karlsr-Durlach","Karlsr-Durlach",2023,2023,39,39,"2023-09-25","03:30:00","2023-09-25","05:50:00","0d, 2h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Blankenloch","Karlsruhe Hbf",2023,2023,39,39,"2023-09-30","23:00:00","2023-10-01","04:30:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Stuttgart-Bad Cannstatt, W 28 - Stuttgart-Untertürkheim, W 202","<>","Stg-Bad Cannst","Stg-Untertürkhm",2023,2023,37,38,"2023-09-17","23:45:00","2023-09-22","05:10:00","4d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-25"]
[null,80,"Nürnberg Rbf, Ausf, W 326 - Fürth (Bay) Hbf, W 165, G-Bahn","<","Fürth (Bay) Gbf","Nür Großmarkt",2023,2023,36,36,"2023-09-05","22:00:00","2023-09-07","06:00:00","1d, 8h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-01-24"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,41,41,"2023-10-09","22:50:00","2023-10-10","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2",">","Wilferdgn-Singen","Mühlacker",2023,2023,41,41,"2023-10-10","22:00:00","2023-10-11","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Langenprozelten","Wiesthal",2023,2023,40,41,"2023-10-07","23:30:00","2023-10-09","04:30:00","1d, 5h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-03-07"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Heppenhm/Bergstr","Heidelb-Wiebl",2023,2023,39,40,"2023-10-01","22:00:00","2023-10-02","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-07"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Karlstadt (Main)","Gemünden (Main)",2023,2023,41,42,"2023-10-15","22:00:00","2023-10-20","21:00:00","4d, 23h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-05-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,41,41,"2023-10-11","05:00:00","2023-10-15","22:00:00","4d, 17h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","Y","2021-05-31"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,40,41,"2023-10-02","21:00:00","2023-10-13","05:00:00","10d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-08-24"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,40,40,"2023-10-02","23:20:00","2023-10-03","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023,2023,41,43,"2023-10-13","22:00:00","2023-10-23","06:00:00","9d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,41,43,"2023-10-13","22:00:00","2023-10-23","06:00:00","9d, 8h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Rbf - Abzw Mannheim  Ziehbrunnen, W 203","<","Ziehbrunnen","Mannh Rbf Gr D",2023,2023,39,40,"2023-10-01","22:00:00","2023-10-02","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,"80","N","2021-06-08"]
[null,80,"Fürth (Bay) Hbf, W 144 - Cadolzburg","<>","Fürth (Bay) Hbf","Zirndorf",2023,2023,40,40,"2023-10-02","23:30:00","2023-10-06","05:30:00","3d, 6h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-03-29"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Übersee","Rumgraben",2023,2023,40,42,"2023-10-05","06:00:00","2023-10-16","22:00:00","11d, 16h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-07"]
[null,80,"München Hbf tief - München Ost Pbf","<","München Ost Pbf","Mü Isartor",2023,2023,41,41,"2023-10-11","00:10:00","2023-10-11","01:00:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2022-07-20"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707","<","Mü Leuchtenberg","München Ost Pbf",2023,2023,41,41,"2023-10-11","01:50:00","2023-10-11","04:30:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim",">","München Ost Pbf","Mü-Trudering",2023,2023,40,40,"2023-10-06","23:00:00","2023-10-07","05:00:00","0d, 6h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<>","München Ost Pbf","Mü-Trudering",2023,2023,41,41,"2023-10-10","01:40:00","2023-10-10","02:50:00","0d, 1h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","München Ost Pbf","München Ost Pbf",2023,2023,41,41,"2023-10-10","02:50:00","2023-10-10","04:00:00","0d, 1h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"Augsburg Hbf - Buchloe","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,40,45,"2023-10-02","07:00:00","2023-11-11","04:30:00","39d, 22h","continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-19"]
[null,80,"München Hbf - Rosenheim",">","München Süd","München Ost Pbf",2023,2023,41,41,"2023-10-15","00:30:00","2023-10-15","02:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","München Süd","München Hbf",2023,2023,41,42,"2023-10-15","22:45:00","2023-10-16","00:30:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,10",null,null,"80","N","2022-07-20"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Regensburg Bbf","Regensburg Bbf",2023,2023,40,41,"2023-10-07","08:00:00","2023-10-15","06:00:00","7d, 22h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-21"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Regensburg Bbf","Regensburg Bbf",2023,2023,40,41,"2023-10-07","08:00:00","2023-10-15","06:00:00","7d, 22h","continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Regensburg Bbf","Regensburg Bbf",2023,2023,41,43,"2023-10-15","06:00:00","2023-10-23","03:00:00","7d, 21h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Regensburg Hbf","Regensburg Hbf",2023,2023,41,43,"2023-10-15","06:00:00","2023-10-23","06:00:00","8d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-21"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Landl (Obb) Abzw","Bad Endorf (Obb)",2023,2023,40,40,"2023-10-04","22:10:00","2023-10-05","01:00:00","0d, 2h","continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-05-06"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Landl (Obb) Abzw","Bad Endorf (Obb)",2023,2023,40,40,"2023-10-06","00:50:00","2023-10-06","03:50:00","0d, 3h","continuous","Switch",null,null,"S",null,null,",,",",,",null,",,",null,null,"80","N","2021-05-06"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Landl (Obb) Abzw","Bad Endorf (Obb)",2023,2023,40,40,"2023-10-07","22:15:00","2023-10-08","01:15:00","0d, 3h","continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-05-06"]
[null,80,"Abzw Landl (Oberbay), 22W703 - Rohrdorf (Oberbay)","<>","Landl (Obb) Abzw","Landl (Oberbay)",2023,2023,40,40,"2023-10-08","04:15:00","2023-10-08","05:15:00","0d, 1h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-06"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Landl (Obb) Abzw","Bad Endorf (Obb)",2023,2023,40,41,"2023-10-08","22:20:00","2023-10-09","01:00:00","0d, 2h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-11-25"]
[null,80,"München Hbf - Rosenheim","<>","Haar","Haar",2023,2023,41,41,"2023-10-09","08:00:00","2023-10-09","14:00:00","0d, 6h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Gbf",2023,2023,41,42,"2023-10-13","22:00:00","2023-10-17","06:00:00","3d, 8h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Laufach","Laufach",2023,2023,41,41,"2023-10-13","04:15:00","2023-10-13","05:00:00","0d, 0h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-16"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274",">","Aschaffenbg Hbf","Aschaffenbg Hbf",2023,2023,41,41,"2023-10-11","06:00:00","2023-10-11","22:00:00","0d, 16h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-04-28"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,40,40,"2023-10-05","01:00:00","2023-10-06","04:30:00","1d, 3h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf",">","München Ost Pbf","München Ost Pbf",2023,2023,40,40,"2023-10-06","23:30:00","2023-10-08","04:30:00","1d, 5h","periodical continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,40,40,"2023-10-07","02:00:00","2023-10-07","04:30:00","0d, 2h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München  Ost W 35 - München-Leuchtenbergring W 58","<>","München Ost Pbf","Mü Leuchtenberg",2023,2023,40,41,"2023-10-08","22:30:00","2023-10-09","01:00:00","0d, 2h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf tief - München Ost Pbf","<","München Ost Pbf","Mü Isartor",2023,2023,41,41,"2023-10-09","01:00:00","2023-10-09","02:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707",">","München Ost Pbf","Mü Leuchtenberg",2023,2023,41,41,"2023-10-09","02:00:00","2023-10-09","04:30:00","0d, 2h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N","2021-05-17"]
[null,80,"München Hbf - Mittenwald (DB-Grenze)","<","Gauting","München-Pasing",2023,2023,41,41,"2023-10-09","00:00:00","2023-10-09","06:00:00","0d, 6h","continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,"80","N","2022-07-25"]
[null,80,"Offenbach (Main) Hbf, W 104 - Dieburg","<>","Rödermk-Ober Rod","Dieburg",2023,2023,40,40,"2023-10-06","20:00:00","2023-10-08","04:00:00","1d, 8h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-17"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,41,41,"2023-10-14","16:00:00","2023-10-15","19:30:00","1d, 3h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-10-27"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86",">","Molzau","Graben-Neudorf",2023,2023,41,41,"2023-10-12","21:00:00","2023-10-13","05:00:00","0d, 8h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,41,41,"2023-10-14","21:00:00","2023-10-15","05:00:00","0d, 8h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-05-10"]
[null,80,"Bruchsal - Rheinsheim, Streckenwechsel 4132/3450","<>","Graben-Neudorf","Graben-Neudorf",2023,2023,41,41,"2023-10-14","21:00:00","2023-10-15","05:00:00","0d, 8h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-10"]
[null,80,"Rastatt, W 21 - Freudenstadt Hbf, Gl 2","<>","Rastatt","Rastatt",2023,2023,40,40,"2023-10-03","00:00:00","2023-10-03","04:00:00","0d, 4h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,40,42,"2023-10-07","23:00:00","2023-10-16","04:30:00","8d, 5h","periodical continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Karlstadt (Main)","Gemünden (Main)",2023,2023,41,42,"2023-10-11","05:00:00","2023-10-20","21:00:00","9d, 16h","periodical continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Karlsruhe Gbf, W 119 - Karlsruhe-Durlach, W 51","<>","Karlsr-Durlach","Karlsruhe Gbf",2023,2023,39,40,"2023-10-01","23:00:00","2023-10-08","04:00:00","6d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn","<>","Karlsr-Hagsfeld","Karlsruhe Gbf",2023,2023,39,40,"2023-10-01","23:00:00","2023-10-08","04:00:00","6d, 5h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Karlsruhe Hbf","Muggensturm",2023,2023,41,42,"2023-10-15","23:00:00","2023-10-16","03:45:00","0d, 4h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Karlsr-Hagsfeld","Karlsruhe Gbf",2023,2023,41,41,"2023-10-14","23:00:00","2023-10-15","04:30:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W 118 - Karlsruhe-Durlach , W 52","<>","Karlsr-Durlach","Karlsr-Durlach",2023,2023,41,41,"2023-10-14","23:00:00","2023-10-15","04:30:00","0d, 5h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Gbf, W912 - Abzw Karlsruhe-Dammerstock, W 401","<>","Dammerstock","Karlsruhe Gbf",2023,2023,41,41,"2023-10-09","00:15:00","2023-10-09","03:30:00","0d, 3h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Blankenloch","Blankenloch",2023,2023,41,41,"2023-10-09","00:15:00","2023-10-09","03:30:00","0d, 3h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-11-11"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü Nord Rbf For","Olching",2023,2023,43,44,"2023-10-29","06:00:00","2023-10-30","06:00:00","1d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-31"]
[null,80,"Olching - Olching Streckenwechsel 5561/5560","<","km 3,6/6,8 (MOL)","Olching",2023,2023,43,43,"2023-10-29","16:00:00","2023-10-29","20:00:00","0d, 4h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-08-27"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<>","Ötigheim","Bashaide",2023,2023,43,45,"2023-10-27","21:00:00","2023-11-06","04:30:00","9d, 8h","continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-10-11"]
[null,80,"Darmstadt-Eberstadt - Pfungstadt","<>","Da-Eberst Nord","Da-Eberst Nord",2023,2023,42,43,"2023-10-21","12:00:00","2023-10-23","12:00:00","2d, 0h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-05-26"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim Hbf","Molzau",2023,2023,43,43,"2023-10-23","22:50:00","2023-10-24","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bickenbach Nord","Zwingenbg/Bergst",2023,2023,43,43,"2023-10-29","03:00:00","2023-10-29","06:00:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-10"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Nantenbach",2023,2023,43,47,"2023-10-28","23:30:00","2023-11-20","04:30:00","22d, 6h","periodical continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-09-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Partenstein","Lohr Bahnhof",2023,2023,43,47,"2023-10-28","14:00:00","2023-11-20","05:00:00","22d, 16h","periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-09-09"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Plochingen","Göppingen",2023,2023,43,43,"2023-10-24","22:00:00","2023-10-25","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002",">","Bensheim-Auerb","Heppenhm/Bergstr",2023,2023,43,43,"2023-10-24","01:00:00","2023-10-24","04:00:00","0d, 3h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-05-12"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Heidelberg Hbf","Karlsr-Durlach",2023,2023,44,44,"2023-10-30","23:20:00","2023-10-31","05:20:00","0d, 6h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Retzb-Zellingen",2023,2023,44,45,"2023-11-01","04:00:00","2023-11-06","04:00:00","5d, 0h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,"80","Y","2021-11-18"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Bietigheim-Biss","StrWe 4800/4842",2023,2023,42,42,"2023-10-17","22:00:00","2023-10-18","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,42,42,"2023-10-16","22:50:00","2023-10-17","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Darmstadt Hbf, W 316 - Aschaffenburg Hbf, W 143","<","Darmstadt Nord","Darmstadt Gbf",2023,2023,43,43,"2023-10-27","22:00:00","2023-10-28","22:00:00","1d, 0h","continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-02"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Gbf",2023,2023,44,44,"2023-10-31","09:00:00","2023-11-03","22:00:00","3d, 13h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-05-03"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2023,2023,44,44,"2023-10-30","22:50:00","2023-10-31","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Nürnberg Hbf - Bamberg",">","Nürnberg Hbf","Bamberg",2023,2023,43,43,"2023-10-23","21:30:00","2023-10-27","05:00:00","3d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-01"]
[null,80,"Sersheim, Streckenwechsel 4800/4842 - Illingen, Streckenw. 4842/4800",">","StrWe 4800/4842","Illingen (Württ)",2023,2023,42,42,"2023-10-17","22:00:00","2023-10-18","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Illingen (Württ)","Mühlacker",2023,2023,42,42,"2023-10-17","22:00:00","2023-10-18","05:00:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rumgraben","Bergen (Oberbay)",2023,2023,42,43,"2023-10-17","06:00:00","2023-10-26","22:00:00","9d, 16h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-05-07"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Radldorf (Nbay)","Mangolding",2023,2023,44,44,"2023-10-31","01:10:00","2023-10-31","02:00:00","0d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","München Ost Pbf","München Süd",2023,2023,42,42,"2023-10-16","00:30:00","2023-10-16","02:15:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","Haar","München Ost Pbf",2023,2023,42,42,"2023-10-16","02:15:00","2023-10-16","04:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim",">","Kirchseeon","Grafing Bahnhof",2023,2023,42,42,"2023-10-17","02:15:00","2023-10-17","03:55:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","Kirchseeon","Zorneding",2023,2023,42,42,"2023-10-18","00:05:00","2023-10-18","01:35:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<","Ostermünchen","Aßling/Obb",2023,2023,42,42,"2023-10-21","00:05:00","2023-10-21","02:10:00","0d, 2h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<>","Grafing Bahnhof","Ostermünchen",2023,2023,42,42,"2023-10-20","22:45:00","2023-10-21","06:10:00","0d, 7h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim",">","Ostermünchen","Rosenheim",2023,2023,42,42,"2023-10-22","01:00:00","2023-10-22","02:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Rosenheim","Landl (Obb) Abzw",2023,2023,43,43,"2023-10-23","04:10:00","2023-10-23","04:50:00","0d, 0h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"München Hbf - Rosenheim","<>","Rosenheim","Rosenheim",2023,2023,43,43,"2023-10-23","04:10:00","2023-10-23","04:50:00","0d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rosenheim Ost","Rosenheim",2023,2023,43,43,"2023-10-23","01:45:00","2023-10-23","02:30:00","0d, 0h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2022-07-20"]
[null,80,"Abzw Waghäusel Saalbach, W 22 - Graben-Neudorf, W 86",">","Saalbach","Graben-Neudorf",2023,2023,42,43,"2023-10-20","22:50:00","2023-10-27","04:50:00","6d, 6h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-12-02"]
[null,80,"München Hbf  - Lenggries","<","Mü Heimeranplatz","München Hbf",2023,2023,42,42,"2023-10-21","23:00:00","2023-10-22","06:00:00","0d, 7h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-04-26"]
[null,80,"Rosenheim, 19W63 - Kufstein (DB-Grenze)","<>","Rosenheim","Rosenheim",2023,2023,42,43,"2023-10-22","23:55:00","2023-10-23","04:50:00","0d, 4h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Ottersweier",2023,2023,43,44,"2023-10-29","00:00:00","2023-10-30","05:00:00","1d, 6h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-12"]
[null,80,"Regensburg Hbf (Bft Bbf), W 455 - Ingolstadt Nord, 20W32","<>","Regensburg Bbf","Sinzing",2023,2023,42,42,"2023-10-20","23:00:00","2023-10-22","03:00:00","1d, 4h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Regensburg Bbf","Regensburg Bbf",2023,2023,42,43,"2023-10-22","03:00:00","2023-10-23","05:00:00","1d, 2h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"Olching - Augsburg Hbf","<>","Olching","Olching",2023,2023,43,43,"2023-10-29","16:00:00","2023-10-29","20:00:00","0d, 4h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-08-27"]
[null,80,"München Hbf - Augsburg Hbf","<>","Olching","Olching",2023,2023,43,43,"2023-10-29","16:00:00","2023-10-29","20:00:00","0d, 4h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"München Hbf tief - Gauting, 35W22",">","Mü Hirschgarten","München-Pasing",2023,2023,42,42,"2023-10-21","08:00:00","2023-10-21","16:00:00","0d, 8h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N","2021-05-28"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,42,44,"2023-10-17","06:00:00","2023-10-30","18:00:00","13d, 13h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-05-21"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,43,44,"2023-10-27","22:00:00","2023-10-30","06:00:00","2d, 9h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2021-05-21"]
[null,80,"München Hbf - Rosenheim",">","Haar","Haar",2023,2023,42,42,"2023-10-16","00:10:00","2023-10-21","05:15:00","5d, 5h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<>","Mü-Trudering","Mü-Waldtrudering",2023,2023,42,42,"2023-10-16","03:50:00","2023-10-21","04:50:00","5d, 1h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"(Olching) Streckenwechsel 5561/5560 - Abzw M-Waldtrudering,W 72","<","Mü-Waldtrudering","Mü-Trudering",2023,2023,43,43,"2023-10-24","00:15:00","2023-10-27","05:15:00","3d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Retzb-Zellingen",2023,2023,43,44,"2023-10-29","09:00:00","2023-11-01","04:00:00","2d, 19h","continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,"80","N","2021-09-10"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Nord",2023,2023,42,42,"2023-10-16","03:00:00","2023-10-16","06:00:00","0d, 3h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-09-14"]
[null,80,"Schirnding (DB-Grenze) - Cheb/SZDC","<>","Schirnding Grenz","Cheb",2023,2023,43,48,"2023-10-29","22:50:00","2023-11-28","04:50:00","29d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54,80,54","N","2021-11-26"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Karlsruhe Hbf","Karlsr-Durlach",2023,2023,42,42,"2023-10-16","00:00:00","2023-10-16","04:00:00","0d, 4h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-29"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Karlsr-Hagsfeld","Karlsruhe Gbf",2023,2023,42,42,"2023-10-16","00:00:00","2023-10-16","04:00:00","0d, 4h","continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-04-29"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,42,42,"2023-10-17","00:00:00","2023-10-17","04:30:00","0d, 4h","continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rastatt, W 21 - Freudenstadt Hbf, Gl 2","<>","Rastatt DB/AVG","Rastatt",2023,2023,42,42,"2023-10-17","00:00:00","2023-10-17","04:30:00","0d, 4h","continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rastatt, W 21 - Freudenstadt Hbf, Gl 2","<>","Rastatt DB/AVG","Rastatt",2023,2023,42,42,"2023-10-17","00:00:00","2023-10-17","04:30:00","0d, 4h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,43,44,"2023-10-29","00:00:00","2023-10-30","04:30:00","1d, 5h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,43,44,"2023-10-29","00:00:00","2023-10-30","04:30:00","1d, 5h","periodical continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Landshut (Bay) Hbf - Bayerisch Eisenstein, Gl 4(DB-Grenze)","<>","Plattling","Grafling",2023,2023,42,42,"2023-10-21","23:00:00","2023-10-22","06:00:00","0d, 7h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,42,42,"2023-10-17","00:00:00","2023-10-17","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,42,42,"2023-10-18","21:00:00","2023-10-19","05:00:00","0d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,42,42,"2023-10-18","21:00:00","2023-10-19","05:00:00","0d, 8h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,42,42,"2023-10-21","01:00:00","2023-10-21","03:00:00","0d, 2h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,42,42,"2023-10-21","01:00:00","2023-10-21","03:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,44,44,"2023-10-31","00:00:00","2023-10-31","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,44,44,"2023-10-31","00:00:00","2023-10-31","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","N-Edingen/F-feld","Ziehbrunnen",2023,2023,42,43,"2023-10-20","21:00:00","2023-10-23","05:00:00","2d, 8h","periodical continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182","<>","Ziehbrunnen","Schwetzingen",2023,2023,43,44,"2023-10-29","21:00:00","2023-10-30","05:00:00","0d, 8h","continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Hbf","Darmstadt Hbf",2023,2023,42,43,"2023-10-20","22:00:00","2023-10-24","10:00:00","3d, 12h","continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2020-09-30"]
[null,80,"Frankfurt (Main) Hbf, Gl 411 - Abzw Heidelberg-Wieblingen, W002","<>","Darmstadt Gbf","Darmstadt Hbf",2023,2023,44,44,"2023-10-31","09:00:00","2023-11-03","22:00:00","3d, 13h","continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Ottersweier","Ottersweier",2023,2023,45,45,"2023-11-06","21:00:00","2023-11-11","02:00:00","4d, 5h","continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Baden-Baden","Achern (F)",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-05","06:00:00","2d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-01"]
[null,80,"Karlsruhe Gbf - Karlsruhe-Hagsfeld, W 60, G-Bahn",">","Karlsruhe Gbf","Karlsr-Hagsfeld",2023,2023,46,46,"2023-11-13","03:00:00","2023-11-13","12:00:00","0d, 9h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,"80","N","2021-05-18"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,45,45,"2023-11-06","22:50:00","2023-11-07","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Abzw Hallstadt (b Bamberg), 31W102 - Abzw Höflein, W302","<>","Hallstadt(Bambg)","Höflein",2023,2023,45,46,"2023-11-10","22:30:00","2023-11-13","05:00:00","2d, 6h","periodical continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-26"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Lohr Bahnhof","Partenstein",2023,2023,47,48,"2023-11-26","12:00:00","2023-11-27","05:00:00","0d, 17h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-02"]
[null,80,"Stuttgart Hbf - Bretten, Streckenwechsel 4130/4800",">","Mühlacker","Bretten Rechberg",2023,2023,48,49,"2023-11-27","23:00:00","2023-12-06","06:00:00","8d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-15"]
[null,80,"Passau Hbf - Obertraubling, W 5 und W 6",">","Mangolding","Obertraubling",2023,2023,45,45,"2023-11-11","23:00:00","2023-11-12","06:00:00","0d, 7h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Bashaide","Ötigheim",2023,2023,48,48,"2023-11-27","22:50:00","2023-11-28","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2021-06-14"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Partenstein","Laufach",2023,2023,46,46,"2023-11-13","22:00:00","2023-11-15","05:00:00","1d, 7h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-06-04"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,46,46,"2023-11-13","23:30:00","2023-11-14","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Rastatt","Sandweier",2023,2023,48,48,"2023-11-27","23:30:00","2023-11-28","05:20:00","0d, 5h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<","Gemünden (Main)","Karlstadt (Main)",2023,2023,45,45,"2023-11-06","23:00:00","2023-11-11","05:00:00","4d, 6h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,1",null,null,"80","N","2021-06-02"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Karlstadt (Main)","Gemünden (Main)",2023,2023,45,47,"2023-11-12","23:00:00","2023-11-24","05:00:00","11d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","Y","2021-05-31"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,47,47,"2023-11-20","06:00:00","2023-11-24","18:00:00","4d, 12h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-04-30"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Karlsruhe Hbf","Bashaide",2023,2023,46,46,"2023-11-13","22:50:00","2023-11-14","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsruhe Hbf",2023,2023,47,47,"2023-11-20","22:50:00","2023-11-21","05:50:00","0d, 7h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-08"]
[null,80,"Abzw Aschaffenburg-Goldbach, W 602 - Aschaffenburg Hbf, W 274","<>","Aschaff Hbf Einf","Aburg-Goldbach",2023,2023,45,46,"2023-11-08","22:00:00","2023-11-14","22:00:00","6d, 0h","continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-07-14"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16","<","Schwetzingen","Mannheim-Rheinau",2023,2023,45,46,"2023-11-06","22:30:00","2023-11-13","04:30:00","6d, 6h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023,2023,45,46,"2023-11-06","22:30:00","2023-11-13","06:00:00","6d, 7h","continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-07-23"]
[null,80,"Abzw Stockschneise, W 503 - Darmstadt-Kranichstein, G-Bahn","<>","Da-Kranichstein","Da-Kranichstein",2023,2023,47,47,"2023-11-20","06:00:00","2023-11-24","18:00:00","4d, 12h","continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<","Unterhaching Üst","München Ost Pbf",2023,2023,44,45,"2023-11-05","21:00:00","2023-11-06","04:00:00","0d, 7h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2021-04-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rumgraben","Übersee",2023,2023,45,46,"2023-11-10","22:00:00","2023-11-17","14:00:00","6d, 16h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,"80","N","2021-05-07"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rottau","Übersee",2023,2023,45,45,"2023-11-06","06:00:00","2023-11-08","14:00:00","2d, 8h","continuous","Catenary",null,null,"S",null,null,",,",",,",null,",0,",null,null,"80","N","2021-05-07"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Gessertshausen","Gessertshausen",2023,2023,46,46,"2023-11-16","20:15:00","2023-11-16","23:15:00","0d, 3h","continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",2,2",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Dinkelscherben","Gessertshausen",2023,2023,45,45,"2023-11-10","02:20:00","2023-11-10","05:15:00","0d, 2h","continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<","Augsb Hirbl Str","Augsb-Oberhausen",2023,2023,47,48,"2023-11-26","22:50:00","2023-11-29","05:10:00","2d, 6h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Augsburg Hbf","Gessertshausen",2023,2023,48,48,"2023-11-29","23:00:00","2023-12-01","05:20:00","1d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N"]
[null,80,"Augsburg Hbf - Buchloe","<>","Augsburg Hbf","Augsburg Hbf",2023,2023,45,45,"2023-11-10","00:30:00","2023-11-11","04:30:00","1d, 4h","periodical continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,"80","N","2022-07-19"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Bad Endorf (Obb)","Rosenheim",2023,2023,47,47,"2023-11-26","04:30:00","2023-11-26","06:00:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",3,",null,null,"80","N","2021-07-23"]
[null,80,"Bft Rosenheim Ost - Bft Rosenheim Süd","<>","Rosenheim Süd","Rosenheim Ost",2023,2023,48,48,"2023-11-27","04:10:00","2023-11-27","05:30:00","0d, 1h","continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Bad Endorf (Obb)","Rosenheim",2023,2023,47,48,"2023-11-26","23:40:00","2023-11-27","05:30:00","0d, 5h","continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2021-04-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Prien a Chiemsee","Rottau",2023,2023,48,48,"2023-11-28","22:35:00","2023-11-29","01:00:00","0d, 2h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-04-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rottau","Bad Endorf (Obb)",2023,2023,48,48,"2023-11-29","02:30:00","2023-11-29","03:30:00","0d, 1h","continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-04-25"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Geislingen (St)","Geislingen (St)",2023,2023,44,44,"2023-11-05","04:45:00","2023-11-05","05:35:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Amstetten(Württ)","Amstetten(Württ)",2023,2023,44,44,"2023-11-05","04:45:00","2023-11-05","05:35:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-11-08"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Beimerstetten","Beimerstetten",2023,2023,44,44,"2023-11-04","00:30:00","2023-11-04","01:25:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Teisendorf","Freilassing",2023,2023,45,46,"2023-11-09","23:30:00","2023-11-13","04:00:00","3d, 4h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2021-10-13"]
[null,80,"Ulm Hbf, W 101 - Friedrichshafen Stadt, W 262","<>","Ulm Hbf","Ulm Hbf",2023,2023,45,45,"2023-11-06","03:30:00","2023-11-06","03:50:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Ulm-Örlingen","Ulm Hbf",2023,2023,45,45,"2023-11-06","02:55:00","2023-11-06","03:30:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Amstetten(Württ)","Amstetten(Württ)",2023,2023,44,44,"2023-11-04","22:55:00","2023-11-05","00:00:00","0d, 1h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf","Ulm Hbf",2023,2023,45,45,"2023-11-06","00:15:00","2023-11-06","00:50:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Geislingen (St)","Amstetten(Württ)",2023,2023,44,44,"2023-11-03","22:30:00","2023-11-03","23:18:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Amstetten(Württ)","Amstetten(Württ)",2023,2023,44,44,"2023-11-03","22:30:00","2023-11-03","23:18:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Amstetten(Württ)","Amstetten(Württ)",2023,2023,44,44,"2023-11-04","05:28:00","2023-11-04","05:38:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Geislingen (St)","Geislingen (St)",2023,2023,44,44,"2023-11-04","05:38:00","2023-11-04","06:00:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N","2021-11-08"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Westheim/Schwab","Augsburg Hbf",2023,2023,45,45,"2023-11-06","21:55:00","2023-11-09","04:40:00","2d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Augsburg Hbf, W 910 - Bft Au-Hirblingerstr., W 277","<","Augsb Hirbl Str","Augsb Hirbl Str",2023,2023,45,45,"2023-11-06","21:55:00","2023-11-09","04:40:00","2d, 6h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Beimerstetten","Amstetten(Württ)",2023,2023,44,44,"2023-11-05","00:00:00","2023-11-05","01:05:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267","<","Augsb Hirbl Str","Augsburg Hbf",2023,2023,46,46,"2023-11-14","02:40:00","2023-11-14","04:40:00","0d, 2h","continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf","Ulm Hbf",2023,2023,45,45,"2023-11-06","01:05:00","2023-11-06","01:45:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,45,45,"2023-11-06","00:50:00","2023-11-06","01:05:00","0d, 0h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Amstetten(Württ)","Amstetten(Württ)",2023,2023,44,44,"2023-11-04","22:00:00","2023-11-04","22:55:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Beimerstetten","Westerst Bstg",2023,2023,44,44,"2023-11-05","02:25:00","2023-11-05","03:10:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Geislingen (St)","Geislingen (St)",2023,2023,44,44,"2023-11-04","21:40:00","2023-11-04","22:00:00","0d, 0h","continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<","Westerstetten","Amstetten(Württ)",2023,2023,44,44,"2023-11-05","03:40:00","2023-11-05","04:45:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643","<>","Ulm-Örlingen","Ulm Hbf",2023,2023,45,45,"2023-11-06","01:05:00","2023-11-06","03:50:00","0d, 2h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Baden-Baden","Bühl (Baden) F",2023,2023,44,45,"2023-11-03","22:00:00","2023-11-10","05:00:00","6d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-04-30"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25","<","München-Giesing","München Ost Pbf",2023,2023,48,48,"2023-11-27","22:30:00","2023-12-01","04:30:00","3d, 6h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,2",null,null,"80","N"]
[null,80,"München Ost - Bft Mü-Leuchtenbergring - Abzw Mü-Berg am Laim - Mü Riem West W 53W707","<","Mü Leuchtenberg","München Ost Pbf",2023,2023,48,48,"2023-11-27","22:30:00","2023-12-01","04:30:00","3d, 6h","periodical continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,1",null,null,"80","N"]
[null,80,"Appenweier, W 222 - Bad Griesbach","<>","Appenweier Nord","Bad Griesbach",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-04-12"]
[null,80,"Appenweier-Muhrhaag, W 236 - Appenweier Kurve, W 263","<>","Appenweier Kurve","RAP Muhrhaag",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-04-12"]
[null,80,"Schirnding (DB-Grenze) - Cheb/SZDC","<>","Schirnding Grenz","Cheb",2023,2023,48,49,"2023-11-29","22:50:00","2023-12-09","04:50:00","9d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80,54,80,54","N","2021-11-26"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Hösbach","Aburg-Goldbach",2023,2023,47,48,"2023-11-25","09:00:00","2023-12-02","17:00:00","7d, 8h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-01-31"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Karlsr-Durlach","Ettlingen West",2023,2023,46,47,"2023-11-18","23:00:00","2023-11-20","04:30:00","1d, 5h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Karlsruhe Hbf, W 113 - Mühlacker, W 2","<>","Karlsruhe Hbf","Karlsr-Durlach",2023,2023,46,47,"2023-11-18","23:00:00","2023-11-20","04:30:00","1d, 5h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Winden (Pfalz), W 36 - Karlsruhe Hbf, Gl 101/102","<>","Karlsruhe West","Karlsruhe Hbf",2023,2023,46,47,"2023-11-18","23:00:00","2023-11-20","04:30:00","1d, 5h","periodical continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-04-30"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,47,47,"2023-11-25","16:00:00","2023-11-26","06:00:00","0d, 14h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,47,47,"2023-11-26","06:00:00","2023-11-26","19:30:00","0d, 13h","continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,44,45,"2023-11-05","00:00:00","2023-11-06","04:30:00","1d, 4h","periodical continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rastatt, W 21 - Freudenstadt Hbf, Gl 2","<>","Rastatt DB/AVG","Rastatt",2023,2023,45,47,"2023-11-12","00:00:00","2023-11-20","04:30:00","8d, 4h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rastatt, W 21 - Freudenstadt Hbf, Gl 2","<>","Rastatt DB/AVG","Rastatt",2023,2023,45,47,"2023-11-12","00:00:00","2023-11-20","04:30:00","8d, 4h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Rastatt","Rastatt",2023,2023,47,49,"2023-11-26","00:00:00","2023-12-04","04:30:00","8d, 4h","periodical continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N"]
[null,80,"Stg-Untertürkheim, W 54 - Abzw Stuttgart Nürnberger Str., W 304","<>","Nürnbg Str Abzw","Stg-Untertürkhm",2023,2023,48,48,"2023-11-27","22:00:00","2023-11-29","04:00:00","1d, 6h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-07-25"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Süßen","Ulm Hbf Em Nord",2023,2023,47,48,"2023-11-20","23:00:00","2023-12-01","04:30:00","10d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,"80","N","2022-06-14"]
[null,80,"Stuttgart Hbf - Neu-Ulm, W 643",">","Ulm Hbf Em Nord","Ulm Rbf",2023,2023,46,46,"2023-11-13","23:00:00","2023-11-17","04:30:00","3d, 5h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,"80","N","2021-05-20"]
[null,80,"Augsburg Hbf - RB-Grenze km 54,788 - Ulm Hbf, W 267",">","Neu-Ulm","Ulm Hbf",2023,2023,46,46,"2023-11-13","22:40:00","2023-11-18","04:40:00","4d, 6h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2021-12-07"]
[null,80,"Regensburg Hbf, W 48 - Nürnberg Hbf","<>","Etterzhausen","Feucht Ost",2023,2023,47,47,"2023-11-26","00:00:00","2023-11-26","04:00:00","0d, 4h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,44,44,"2023-11-04","00:00:00","2023-11-04","02:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Freilassing",2023,2023,44,44,"2023-11-04","01:00:00","2023-11-04","03:00:00","0d, 2h","continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-04-26"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)","<>","Offenburg","Baden-Baden",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-04-12"]
[null,80,"Appenweier, W 207 - Kehl (DB-Grenze)","<>","Appenweier","Appenweier Nord",2023,2023,44,44,"2023-11-02","22:00:00","2023-11-03","06:00:00","0d, 8h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2020-09-30"]
[null,80,"Augsburg Hbf - Nördlingen","<>","Gersthofen","Augsburg Hbf",2023,2023,48,48,"2023-12-02","23:29:00","2023-12-03","04:30:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Molzau","Graben-Neudorf",2023,2023,49,49,"2023-12-04","22:50:00","2023-12-05","05:50:00","0d, 7h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-06-08"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Mannheim-Rheinau","Schwetzingen",2023,2023,48,49,"2023-12-02","22:00:00","2023-12-09","05:00:00","6d, 7h","periodical continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-06-01"]
[null,80,"Augsburg Hbf - Gleis 970 - Bft Au-Oberhausen","<>","Augsburg Hbf","Augsb-Oberhausen",2023,2023,48,48,"2023-12-02","23:29:00","2023-12-03","04:30:00","0d, 5h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-12-17"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Rumgraben",2023,2023,48,48,"2023-12-01","01:00:00","2023-12-01","02:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Übersee","Traunstein",2023,2023,48,48,"2023-12-01","02:50:00","2023-12-01","03:30:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Übersee","Prien a Chiemsee",2023,2023,48,48,"2023-12-01","23:40:00","2023-12-02","01:00:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2021-11-25"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Rottau","Traunstein",2023,2023,48,48,"2023-12-01","22:30:00","2023-12-02","06:05:00","0d, 7h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<>","Freilassing","Traunstein",2023,2023,48,48,"2023-12-02","23:20:00","2023-12-03","06:30:00","0d, 7h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Rückstetten","Traunstein",2023,2023,49,49,"2023-12-04","00:20:00","2023-12-04","01:50:00","0d, 1h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Teisendorf","Lauter",2023,2023,49,49,"2023-12-04","01:50:00","2023-12-04","04:20:00","0d, 2h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,"80","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze","<","Salzburg Grenze","Freilassing",2023,2023,49,49,"2023-12-05","02:20:00","2023-12-05","02:50:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,"80,81","N","2022-07-20"]
[null,80,"Rosenheim - Freilassing - Salzburg Grenze",">","Teisendorf","Freilassing",2023,2023,49,49,"2023-12-05","03:25:00","2023-12-05","04:00:00","0d, 0h","continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,"80","N","2022-07-20"]
[null,80,"Freilassing - Bad Reichenhall","<>","Freilassing","Freilassing",2023,2023,49,49,"2023-12-04","23:00:00","2023-12-05","05:30:00","0d, 6h","continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,"80","N","2022-07-20"]
[null,80,"München Ost Pbf, W 41 - Deisenhofen, W 25",">","München Ost Pbf","München-Giesing",2023,2023,49,49,"2023-12-07","00:30:00","2023-12-08","04:30:00","1d, 4h","periodical continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,1",null,null,"80","N"]
[null,80,"Darmstadt Hbf, W 333 - Darmstadt Nord, W 766","<>","Darmstadt Gbf","Darmstadt Gbf",2023,2023,48,49,"2023-12-01","23:00:00","2023-12-04","18:00:00","2d, 19h","continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2021-05-21"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensburg Hbf","Obertraubling",2023,2023,48,48,"2023-12-02","22:20:00","2023-12-03","04:10:00","0d, 5h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,"80","N","2022-06-08"]
[null,80,"Regensburg Ost, W 3 - Bft Regensburg Hafenbrücke Abzw, W 1","<>","Regensbg Ost","Regensbg Ost",2023,2023,48,48,"2023-12-02","22:20:00","2023-12-03","05:10:00","0d, 6h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"München Hbf - Regensburg Hbf, W 106","<","Regensburg Hbf","Obertraubling",2023,2023,48,49,"2023-12-03","23:20:00","2023-12-04","04:15:00","0d, 4h","continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,"80","N","2022-06-08"]
[null,80,"München Hbf - Regensburg Hbf, W 106",">","Regensbg Ost","Regensbg Ost",2023,2023,49,49,"2023-12-04","00:25:00","2023-12-04","04:15:00","0d, 3h","continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,"80","N","2022-06-08"]
[null,80,"Mannheim Hbf - Basel - Konstanz (DB-Grenze)",">","Ettlingen West","Rastatt",2024,2024,11,12,"2024-03-15","21:00:00","2024-03-22","05:00:00","6d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-14"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 1 - Schwetzingen, W 193/182",">","Ziehbrunnen","Schwetzingen",2024,2024,11,12,"2024-03-15","21:00:00","2024-03-22","05:00:00","6d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-15"]
[null,80,"Appenweier, W 207 - Kehl (DB-Grenze)",">","Appenweier Kurve","Kehl",2024,2024,18,20,"2024-05-03","22:00:00","2024-05-17","05:00:00","13d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-13"]
[null,80,"Augsburg Hbf - Buchloe",">","Augsburg Hbf","Bobingen",2024,2024,15,17,"2024-04-12","22:00:00","2024-04-23","06:00:00","10d, 8h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,"80","N","2022-06-13"]
[null,80,"Augsburg Hbf - Buchloe",">","Augsburg Hbf","Bobingen",2024,2024,18,18,"2024-05-02","22:00:00","2024-05-05","06:00:00","2d, 8h","periodical continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,"80","N","2022-06-13"]
[null,80,"Augsburg Hbf - Buchloe","<","Bobingen","Augsburg Hbf",2024,2024,18,19,"2024-05-03","18:00:00","2024-05-11","06:00:00","7d, 12h","continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",0,0",null,null,"80","N","2022-06-13"]
[null,80,"Weiden (Oberpf) - Oberkotzau, W 444","<","Marktredwitz","Pechbrunn",2024,2024,16,17,"2024-04-21","20:00:00","2024-04-28","06:00:00","6d, 10h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,"80","N","2022-06-08"]
[null,80,"Weiden (Oberpf) - Oberkotzau, W 444","<","Marktredwitz","Wiesau (Oberpf)",2024,2024,18,18,"2024-05-02","20:00:00","2024-05-04","06:00:00","1d, 10h","periodical continuous","Signal",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,"80","N","2022-06-08"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2024,2024,2,3,"2024-01-14","21:00:00","2024-01-19","05:00:00","4d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-02-16"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -","<>","Rastatt-Süd","Baden-Baden",2024,2024,3,4,"2024-01-21","21:00:00","2024-01-26","05:00:00","4d, 8h","periodical continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-02-16"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2024,2024,9,10,"2024-03-01","21:00:00","2024-03-04","05:00:00","2d, 8h","periodical continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-09"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf",">","Wiesthal","Wiesthal",2024,2024,24,29,"2024-06-11","21:00:00","2024-07-19","05:00:00","37d, 8h","continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2022-06-09"]
[null,80,"Appenweier, W 207 - Kehl (DB-Grenze)",">","Appenweier Kurve","Kehl",2024,2024,44,46,"2024-11-01","22:00:00","2024-11-15","05:00:00","13d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-13"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Ötigheim","Rastatt",2024,2024,32,33,"2024-08-09","21:00:00","2024-08-16","05:00:00","6d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-15"]
[null,80,"Neu-Edingen/Friedrichsfeld, W 5 - Bft Mannheim-Friedrichsfeld Südeinfahrt/Ausfahrt Abzw., W 907",">","N-Edingen/F-feld","M-Fr Südein/Ausf",2024,2024,33,34,"2024-08-16","21:00:00","2024-08-23","05:00:00","6d, 8h","periodical continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-10-16"]
[null,80,"Mannheim Hbf, W 2 - Rastatt, W 15/16",">","Graben-Neudorf","Karlsr-Hagsfeld",2024,2024,38,39,"2024-09-22","21:00:00","2024-09-29","05:00:00","6d, 8h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,"80","N","2021-10-15"]
[null,80,"Karlsruhe Gbf, W 118 - Karlsruhe-Durlach , W 52",">","Karlsruhe Gbf","Karlsr-Durlach",2024,2024,42,43,"2024-10-18","21:00:00","2024-10-25","05:00:00","6d, 8h","periodical continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2021-10-14"]
[null,80,"(Karlsruhe) - Rastatt-Süd - Offenburg        - Fernbahn -           Schliengen - Haltingen     - Fernbahn -",">","Rastatt-Süd","Appenweier Nord",2024,2024,48,49,"2024-11-29","22:00:00","2024-12-06","05:00:00","6d, 7h","periodical continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,"80","N","2021-10-13"]
[null,80,"Nürnberg Hbf - Schirnding Grenze","<>","Kirchenlaibach","Marktredwitz",2024,2024,40,40,"2024-10-02","23:59:00","2024-10-03","12:00:00","0d, 12h","continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-02-16"]
[null,80,"Würzburg Hbf - RB-Grenze (79,625) - Aschaffenburg Hbf","<>","Wiesthal","Wiesthal",2024,2024,49,50,"2024-12-06","21:00:00","2024-12-09","05:00:00","2d, 8h","continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,"80","N","2022-06-09"]
[null,81,"Wels - Traun - Linz","< >","Linz Wegscheid","",2022,2022,10,10,"07.03.2022","07:00","11.03.2022","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","Gleisaltlage","","N","14.12.2021"]
[null,81,"Wels - Traun - Linz","< >","Linz Hbf","Linz Hbf Westbrücke",2022,2022,11,12,"18.03.2022","22:30","21.03.2022","20:00","2 days + 21,5 h","cont.","SP","","LT","","","","","","","","","Anbindung Gleis 2 (Gleis 4Neu)","","N","14.12.2021"]
[null,81,"Regensburg - Wels","< >","Üst Lz 2","Sbl We 2",2022,2022,12,49,"27.03.2022","00:00","10.12.2022","24:00","259 days","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 1 - 4","","N","14.12.2021"]
[null,81,"Salzburg - Wels",">","Sbl We 1","Abzww Lambach-West",2022,2022,19,49,"15.05.2022","00:00","10.12.2022","24:00","210 days + 1,0 h","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 5 - 6","","N","14.12.2021","N","",1015,1018,"","","","","","","",""]
[null,81,"Wels - Traun - Linz","< >","Wels Vbf-Terminal","",2022,2022,28,29,"16.07.2022","18:00","18.07.2022","12:00","1 day + 18,0 h","cont.","GES","T","ST","","","","C","","","","","Sperre Berggleis (Einfahrt Wels-Verschiebebahnhof) Errichtung Bohrpfähle für MA5.3, Einbau Hilfsbrücke zwischen Weichenverbindung ½ Wels Verschiebeb., Einbau einer Durchfahrt unter Berggleis östlich der Autobahnbrücke","","Y","14.12.2021","N","",1015,"","","","","","","","",""]
[null,81,"Wels - Traun - Linz","< >","Wels Vbf-Terminal","",2022,2022,29,30,"23.07.2022","18:00","25.07.2022","12:00","1 day + 18,0 h","cont.","GES","T","ST","","","","C","","","","","Sperre Berggleis (Einfahrt Wels-Verschiebebahnhof) Errichtung Bohrpfähle für MA5.3, Einbau Hilfsbrücke zwischen Weichenverbindung ½ Wels Verschiebeb., Einbau einer Durchfahrt unter Berggleis östlich der Autobahnbrücke","","Y","14.12.2021","N","",1015,"","","","","","","","",""]
[null,81,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"","","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Unter Purkersdorf","",2022,2022,31,34,"06.08.2022","01:30","22.08.2022","04:00","16 days + 2,5 h","cont.","SP","","ST","","","","C","","B","","","Migration Estw Up neu:\n06.08.22: Softwaretausch Hf/Hdd, EstwUpneu; BFZ\nes stehen nur die Gleise 2+4 im Bf. Up zur Verfügung\nSignalabhängigkeit aufgehoben!\nSchluss/Freimelder erforderlich!\nStr. 123 nicht befahrbar!","","N","14.12.2021",null,null,null,null,null,null,"","","","","","Medium"]
[null,81,"Wels - Traun - Linz",">","Hörsching","Wels Hbf",2022,2022,32,32,"10.08.2022","08:00","15.08.2022","24:00","5 days + 16,0 h","cont.","SP","","LT","","","","","","","","","Migration Marchtrenk","","N","14.12.2021",null,null,null,null,null,null,"","","","","",""]
[null,81,"Wels - Traun - Linz","< >","Marchtrenk","",2022,2022,32,32,"11.08.2022","21:00","12.08.2022","05:00","8,0 h","cont.","SP","","ST","","","","","","","","","Phase 3 - IB Sig. Elemente Gleis 103 zw. AS H3 und ES C\n(Traunerschleife)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Traun - Linz",">","Sbl Hoe 2","Abzw Mak 1",2022,2022,32,32,"14.08.2022","01:00","14.08.2022","03:00","2,0 h","cont.","SP","","LT","","","","","","","","","IBN Marchtrenk SWT","","N","14.12.2021"]
[null,81,"Wels - Traun - Linz","<","Wels Hbf","Marchtrenk",2022,2022,33,33,"15.08.2022","21:00","16.08.2022","05:00","8,0 h","cont.","SP","","LT","","","","","","",10,"","Phase 6 - IB Sig. Elemente  Gleis 1 von ES Z bis AS R1","","N","14.12.2021"]
[null,81,"Wien - Sopron","< >","Wampersdorf","Ebenfurth",2022,2022,33,34,"21.08.2022","22:10","22.08.2022","04:30","6,3 h","cont.","RES","T","LT","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","01.02.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,33,34,"21.08.2022","23:10","22.08.2022","04:30","5,3 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,34,34,"27.08.2022","23:10","28.08.2022","06:00","6,8 h","cont.","GES-N","","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,34,35,"28.08.2022","22:10","29.08.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,35,35,"29.08.2022","01:00","29.08.2022","05:00","4,0 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,null,"Wien - Parndorf","< >","Gramatneusiedl","",2022,2023,35,36,"01.09.2022","08:00","04.09.2023","04:30","368 days","cont.","SP","","ST","","","","","","","","","Fahrleitungsumbau","","N","01.05.2022"]
[null,81,"Salzburg - Wels",">","Abzww Lambach-West","Sbl Sas 1",2022,2022,35,49,"04.09.2022","00:00","10.12.2022","24:00","98 days + 1,0 h","cont.","SP","","LT","S","","","","","","","","Abschaltung der LZB-Schleifen 7 - 8","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","",2022,2022,35,36,"04.09.2022","22:10","05.09.2022","04:30","6,3 h","cont.","GES","T","ST","","","","C","","B","","","Arbeiten an Weichenverbindungen Südkopf Bf Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Sbl Zur 1","Himberg",2022,2022,36,40,"09.09.2022","05:00","03.10.2022","05:00","24 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Lanzendorf-Rannersdorf","Himberg",2022,2022,36,37,"09.09.2022","22:00","12.09.2022","05:00","2 days + 7,0 h","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung W 2 in Himberg","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","< >","Linz Gaumberg","Marchtrenk",2022,2022,37,37,"12.09.2022","00:00","12.09.2022","04:00","4,0 h","cont.","GES-N","","LT","","","","","","",5,"","Schutzgerüstes bei LM 02 (Überfahrtsbrücke vor der Haltestelle Leonding)","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Abzww Zur","Wien Zvbf",2022,2022,37,38,"12.09.2022","07:00","25.09.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Lambach","",2022,2022,37,38,"16.09.2022","19:00","19.09.2022","04:00","2 days + 9,0 h","cont.","SP","","ST","","","","C","","","","","Ausbau DKW67/68, Einbau EW67","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Wels Hbf","Lambach",2022,2022,37,38,"16.09.2022","19:00","19.09.2022","04:00","2 days + 9,0 h","cont.","RES","","LT","","","","C","","","","","Ausbau DKW67/68, Einbau EW67","","Y","05.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Pöchlarn","Ybbs a.d.Donau",2022,2022,38,38,"19.09.2022","22:00","23.09.2022","05:00","4x 7,0 h","period.","GES-N","","LT","","","","C","","B","","","Drainagespülen \nRobel mit Niederflurwagen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,38,38,"25.09.2022","01:10","25.09.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Einfahrgr","",2022,2022,39,41,"02.10.2022","07:00","13.10.2022","17:00","11 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf",">","Lanzendorf-Rannersdorf","Himberg",2022,2022,40,43,"03.10.2022","05:00","24.10.2022","05:00","21 days","cont.","SP","","LT","","","","C","","B",30,"","Unterbausanierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Tfd 2","Abzww Knoten Wagram Nord",2022,2022,40,42,"03.10.2022","23:30","21.10.2022","05:30","18x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,40,40,"09.10.2022","01:10","09.10.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Traun - Linz","<","Marchtrenk","Sbl Hoe 2",2022,2022,41,42,"14.10.2022","22:00","17.10.2022","04:00","2 days + 6,0 h","cont.","SP","","LT","","","","","","","","","LM 22 - Einbau  Hib","","N","14.12.2021"]
[null,81,"Salzburg - Wels","< >","Lambach","",2022,2022,42,42,"20.10.2022","18:00","23.10.2022","04:30","2 days + 10,5 h","cont.","SP","","ST","","","","","","","","","WN W 89","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,42,42,"23.10.2022","01:10","23.10.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (NRZ)",">","St.Peter-Seitenstetten","Abzw Knoten St.Peter-Seitenstetten West",2022,2022,43,47,"24.10.2022","07:00","25.11.2022","17:00","32 days + 11,0 h","cont.","SP","","LT","","","","","","","","","Entwässerungsanlagen, Brückensanierung, Kabelwege","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Tullnerbach-Pressbaum","Rekawinkel",2022,2022,43,44,"26.10.2022","01:00","02.11.2022","04:00","7 days + 4,0 h","cont.","GES","T","LT","","","","C","","B","","","Bauphase 1.2:\nAusbau Hilfsbrücke km 20,406;\nErrichten prov. Bahnsteig Gl2\nVerlängerung Bstg. Gl3 (160m)\nEinbau Hilfsbrücke Gl1 (Personentunnel)\nErrichten Oberleitungsfundamente Ostkopf","","N","14.12.2021"]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,43,44,"28.10.2022","23:30","31.10.2022","05:30","3x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Tullnerbach-Pressbaum","",2022,2023,44,27,"03.11.2022","00:00","09.07.2023","04:00","248 days + 3,0 h","cont.","SP","","ST","","","","","","","","","Bauphase 2.1+2.2+2.3:\nUmbau Nordhälfte;\nAbtrag EK km 19,577; Ausrüstung Technikgebäude, Schaltgerüst neu, Teilerrichtung Inselbahnsteig, Teilerrichtung Personendurchgang\nInbetriebnahme ESTW neu und SWT in der BFZ 18.06.2023","","N","29.03.2022"]
[null,81,"Linz - Wien (NRZ)","< >","Loosdorf","Sbl Los 4",2022,2022,44,44,"05.11.2022","22:00","06.11.2022","05:00","7,0 h","cont.","GES-N","","LT","","","","C","","B","","","Sonderinspektion \nTUF","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[]
[null,81,"Wels - Linz","<","Linz Hbf","Linz Hbf Westbrücke",2022,2022,47,47,"27.11.2022","01:00","27.11.2022","03:00","2,0 h","cont.","SP","","LT","","","","","","","","","Linz Hbf SWT 3 - aufgehobene Signalabhängigkeit mit Sicherheitserprobung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Zvbf","Abzww Zur",2022,2022,45,46,"07.11.2022","07:00","20.11.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,45,45,"07.11.2022","23:30","12.11.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","< >","Lambach","",2022,2022,46,47,"18.11.2022","23:00","21.11.2022","04:00","2 days + 5,0 h","cont.","SP","","ST","","","","C","","B","","","WN 1 und 4","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,46,46,"20.11.2022","01:10","20.11.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Linz - Wien (GZ)",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,47,47,"21.11.2022","23:30","26.11.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Abzww Zur","Wien Zvbf",2022,2022,48,49,"28.11.2022","07:00","11.12.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Abzww Zur","Wien Zvbf",2022,2022,48,49,"28.11.2022","07:00","11.12.2022","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,48,48,"28.11.2022","23:30","03.12.2022","05:30","5x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","Üst Hdd 1","Tullnerfeld-Ost",2022,2022,49,49,"05.12.2022","23:30","07.12.2022","05:30","2x 6,0 h","period.","WF","","LT","","","","C","","B","","","Darainagespülen\nRobel+Niederflurwagen+Steuerwagen","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Hdd 1","Abzw Knoten Hetzendorf",2022,2022,50,50,"18.12.2022","01:10","18.12.2022","05:00","3,8 h","cont.","GES-N","","LT","","","","C","","B","","","periodische Erhaltung und Inspektion","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Medium"]
[null,81,"Wels - Linz",">","Üst Lz 2","Linz Hbf",2023,2023,7,8,"17.02.2023","22:00","22.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 01 km 191,248\nschlagen dukdiler Phäle","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz",">","Marchtrenk","Sbl Hoe 2",2023,2023,7,8,"17.02.2023","22:00","22.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 19, LM 21, \nAusbau Hib LM 22\nAnheben Oberleitung\nEinbau Weiche 5","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","St.Valentin","",2023,2023,10,10,"06.03.2023","07:00","10.03.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GA","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Wels - Linz","< >","Linz Hbf Westbrücke","",2023,2023,11,12,"13.03.2023","17:00","24.03.2023","17:00","11 days","cont.","SP","","ST","","","","","","","","","WN W 401-409","","N","06.02.2022"]
[null,81,"Linz - Wien (GZ)",">","Sbl Spw 5","Sbl Spw 2",2023,2023,12,14,"20.03.2023","22:30","05.04.2023","05:00","16x 6,5 h","period.","GES-N","","LT","","","","C","","B",6,"","Kanalspülen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,12,12,"24.03.2023","22:45","26.03.2023","05:00","2x 6,2 h","period.","SP","","LT","","","","","","",7,"","Errichtung Joche","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Linz Hbf","",2023,2023,13,50,"27.03.2023","00:00","12.12.2023","24:00","261 days + 1,0 h","cont.","SP","","ST","","","","","","","","","WN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Wels - Linz","< >","Linz Vbf-Durchfahrgr","",2023,2023,15,16,"13.04.2023","07:00","17.04.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","EK 0,915 Scharlinz \n(Umsetzung zeitgleich mit Gl 1 km 0,862 - 1,010 0 (115lf)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels",">","Üst Fm 2","Ederbauer",2023,2023,13,14,"02.04.2023","22:45","03.04.2023","05:00","6,2 h","cont.","SP","","LT","","","","","","",15,"","OL-Querungen aufziehen","","N","14.12.2021"]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Durchfahrgr","",2023,2023,15,16,"13.04.2023","07:00","17.04.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","EK 0,915 Scharlinz \n(Umsetzung zeitgleich mit Gl 1 km 0,862 - 1,010 0 (115lf)","","N","14.12.2021"]
[null,81,"Wien - Sopron","< >","Kledering","",2023,2023,14,15,"08.04.2023","09:00","11.04.2023","05:00","2 days + 20,0 h","cont.","SP","T","ST","","","","","","","","","Weichenneulage DKW 453/454 und DKW 455/456","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Straßwalchen","Üst Fm 2",2023,2023,14,15,"09.04.2023","22:45","10.04.2023","07:00","8,2 h","cont.","SP","","LT","","","","","","",5,"","IB neues Schaltgerüst","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Durchfahrgr","",2023,2023,15,16,"13.04.2023","07:00","17.04.2023","17:00","4 days + 10,0 h","cont.","SP","","ST","","","","","","","","","EK 0,915 Scharlinz \n(Umsetzung zeitgleich mit Gl 1 km 0,862 - 1,010 0 (115lf)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Regensburg - Wels","<","Üst Wa 1","Üst Had 2",2023,2023,15,16,"14.04.2023","20:00","17.04.2023","05:00","2 days + 9,0 h","cont.","SP","","LT","","","","","","",3,"","Sanierung UF / Bstg","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Abzww Knoten Rohr West","Pöchlarn",2023,2023,18,21,"01.05.2023","00:00","22.05.2023","04:00","21 days + 4,0 h","cont.","GES","T","LT","","","","C","","B",10,"","Weichentausch ÜSt Rohr 3 und 6\nWest 200\nErneuerung Löschwasserleitung Melker Tunnel Gl 3 (Sperren zum Tunnelspülen werden mitgenutzt.)","","N","07.02.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Lambach","",2023,2023,18,22,"02.05.2023","23:00","02.06.2023","05:00","23x 6,0 h","period.","GES","","ST","","","","","","","","","Kalvarienbergtunnel Strahlerkabeltauschprojekt","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Linz","<","Marchtrenk","Sbl Hoe 2",2023,2023,21,21,"22.05.2023","22:00","26.05.2023","22:00","4 days","cont.","SP","","LT","","","","","","","","","Ausbau Hib LM 19, LM 21,","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Parndorf - Hegyeshalom","<","Nickelsdorf","",2023,2023,21,22,"26.05.2023","09:00","30.05.2023","04:00","3 days + 19,0 h","cont.","SP","","ST","S","","","","","",30,"","Gründliche Durcharbeitung, sowie Sanierung der EK in km 66,641","","N","06.06.2022"]
[null,81,"Linz - Wien (GZ)","< >","Abzww Zur","Wien Zvbf",2023,2023,24,25,"12.06.2023","07:00","25.06.2023","17:00","13 days + 10,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)","< >","Üst Up 2","Tullnerbach-Pressbaum",2023,2023,23,26,"08.06.2023","02:00","30.06.2023","20:00","22 days + 18,0 h","cont.","SP","","LT","","","","","","","","","Bauphase 2.2.1:\nUmbau Weichenkopf OST Ri Up! Umbau Fahrleitung, Fundamente herstellen für OBerleitung und Maste.","","N","14.12.2021"]
[null,81,"Linz - Wien (NRZ)","< >","Abzw Ams 11","Waidhofen a.d.Ybbs",2023,2023,26,36,"30.06.2023","23:00","04.09.2023","04:30","65 days + 5,5 h","cont.","GES","T","LT","","","Do","C","","B","","","Bahnhof Ul: Montage Schaltgerüst\nAbzw. Ams 11 - Ul und Bf. Ul:, Aufziehen der Spitzenleitungen,  Aufziehen und Ausfertigen der Oberleitung\nStrecke UI bis Hk:  Gleisneulage km 12,925 - km 15,032 im Zeitraum 07.08 bis 25.08.2023","","N","03.07.2022",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Wien - Parndorf","< >","Gramatneusiedl","",2023,2023,26,27,"02.07.2023","06:00","09.07.2023","06:00","7 days","cont.","SP","","ST","","","","","","","","","Neuerrichtung Bypassgleis zwischen W63 und W92 (Bauphase 7b - Bahnhofumbau Gramatneusiedl)","","N","01.05.2022"]
[null,81,"Wien - Sopron","< >","Münchendorf","Wampersdorf",2023,2023,26,36,"01.07.2023","22:00","04.09.2023","04:30","64 days + 6,5 h","cont.","GES","T","LT","","","","C","","B","","","Anbindung Bf Ebreichdorf neu an Münchendorf und Wampersdorf","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Wien - Sopron",">","Wampersdorf","Sbl Wp 1",2023,2023,26,32,"02.07.2023","06:00","07.08.2023","06:00","36 days","cont.","SP","","LT","S","","","C","","B",30,"","Planumsverbesserung mit UGV, sowie Einbau der Weichen 2+3 in der Hst Pottendorf-L.","","Y","16.05.2022"]
[null,81,"Linz - Wien (NRZ)","< >","Amstetten","",2023,2023,27,28,"03.07.2023","00:00","14.07.2023","24:00","12 days","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Parndorf - Hegyeshalom",">","Zurndorf","Nickelsdorf",2023,2023,27,30,"04.07.2023","08:00","30.07.2023","16:00","26 days + 8,0 h","cont.","SP","","LT","","","","C","","B",20,"","Gleisneulage mit Untergrundverstärkung","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","","Minor"]
[null,null,"Linz - Wien (NRZ)","<","Tullnerbach-Pressbaum","",2023,2023,27,49,"09.07.2023","04:00","09.12.2023","04:00","153 days + 1,0 h","cont.","SP","","ST","","","","C","","B","","","Bauphase 3.2+3.3+3.4:\nSchwenk von Nord auf Südseiten! Umbau Südseite. Umbau Weichenkopf OST Ri Up! Umbau Fahrleitung; Umbau Signalstandorte!\nDoppelgleissperren in den Nächten!","","N","29.03.2022"]
[null,81,"Salzburg - Wels",">","Seekirchen am Wallersee","Sbl See 1",2023,2023,29,30,"21.07.2023","19:00","24.07.2023","05:00","2 days + 10,0 h","cont.","SP","","LT","","","","C","","B",5,"","Errichtung neuer Hast Seekirchen Süd - \nEinbau Hib Gl 1+2","","Y","11.01.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,30,30,"29.07.2023","23:10","30.07.2023","05:45","6,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,30,31,"30.07.2023","23:10","31.07.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Abzw Pb 1","Prinzersdorf",2023,2023,32,33,"12.08.2023","01:00","18.08.2023","18:00","6 days + 17,0 h","cont.","SP","","LT","","","","C","","B",1,"","Weichenneulage Weichen 3,6,9 (Gl 204)","","Y","13.06.2022",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,33,34,"20.08.2023","23:10","21.08.2023","04:45","5,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","<","St.Valentin-Ennskanalbrücke","",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","ST","","","","","","","","","UGV Weiche  152, 154, 155, 156","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)",">","St.Valentin","Linz Kleinmünchen",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","LT","","","","","","","","","Schotterbetttausch SAZ (Ennsbrücke)","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","St.Valentin-Ennskanalbrücke","",2023,2023,35,37,"28.08.2023","08:00","11.09.2023","05:00","13 days + 21,0 h","cont.","GES","","ST","","","","","","","","","UGV Weiche  160, 161","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Zvbf","Kledering",2023,2023,36,37,"09.09.2023","10:00","15.09.2023","17:00","6 days + 7,0 h","cont.","SP","","LT","","","","","","","","","Gleisneulage","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Abzw Knoten Hetzendorf","Oberlaa",2023,2023,37,37,"11.09.2023","01:30","11.09.2023","03:55","2,4 h","cont.","RES","","LT","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","02.11.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,38,38,"18.09.2023","01:30","18.09.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Matzleinsdorf","",2023,2023,39,43,"25.09.2023","07:00","25.10.2023","12:00","30 days + 5,0 h","cont.","SP","","ST","","","","","","","","","Gleisneulage mit Untergrundstabilisierung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Meidling","",2023,2023,40,40,"02.10.2023","01:30","02.10.2023","03:55","2,4 h","cont.","SP","","ST","","","Do","C","","B","","","Tausch von 15 KV Kabel","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf",">","Himberg","Gramatneusiedl",2023,2023,41,43,"13.10.2023","22:00","25.10.2023","22:00","12 days","cont.","SP","","LT","","","","C","","B",30,"","Anschwenkungen","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Sopron","< >","Wampersdorf","Pottendorf-Landegg",2023,2023,41,41,"14.10.2023","23:10","15.10.2023","05:45","6,6 h","cont.","GES-N","","LT","","","","C","","B","","","Sanierung und Umbau Überfahrtsbrücke","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,null,"Wien - Parndorf","< >","Gramatneusiedl","",2023,2023,42,42,"16.10.2023","00:00","22.10.2023","24:00","7 days","cont.","SP","","ST","","","","","","","","","Abtrag Bgl 11, sowie der Weiche 51 [alt], Einbau Weichen 31 [neu]  (Bauphase 9 - Bahnhofumbau Gramatneusiedl)","","N","01.05.2022"]
[null,null,"Wien - Parndorf","<","Gramatneusiedl","",2023,2023,43,45,"23.10.2023","00:00","12.11.2023","24:00","21 days + 1,0 h","cont.","SP","","ST","S","","","","","",10,"","Bahnsteigneubau (Bauphase 10a - Bahnhofumbau Gramatneusiedl)","","N","01.05.2022"]
[null,81,"Linz - Wien (GZ)","< >","Linz Vbf-Ost Einfahrgr","",2023,2023,44,45,"30.10.2023","07:00","10.11.2023","17:00","11 days + 10,0 h","cont.","SP","","ST","","","","","","","","","GN","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Lanzendorf-Rannersdorf","Gramatneusiedl",2023,2023,44,44,"01.11.2023","06:00","03.11.2023","05:00","1 day + 23,0 h","cont.","SP","","LT","","","","C","","B",30,"","Einbau W 1-neu und anbinden an Bgl 2","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wien - Parndorf","<","Himberg","Gramatneusiedl",2023,2023,45,46,"06.11.2023","05:00","18.11.2023","17:30","12 days + 12,5 h","cont.","SP","","LT","","","","C","","B",30,"","Hauptverkabelung","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Neumarkt am Wallersee",2023,2023,49,50,"08.12.2023","21:00","11.12.2023","05:00","2 days + 8,0 h","cont.","SP","","LT","","","","C","","B",5,"","Tausch Schotterbett in der ÜSt Steindorf b.Stw 3","","Y","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Wels - Traun - Linz","<","Marchtrenk","Sbl Hoe 2",2023,2023,8,9,"22.02.2023","22:00","27.02.2023","04:00","4 days + 6,0 h","cont.","SP","","LT","","","","","","","","","Einbau Hib LM 19, LM 21, \nAusbau Hib LM 22\nAnheben Oberleitung","","N","11.07.2022",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"Wels - Traun - Linz","< >","Linz Hbf Westbrücke","",2023,2023,11,12,"17.03.2023","22:00","24.03.2023","17:00","6 days + 19,0 h","cont.","SP","","ST","","","","","","","","","WN W 401-405","","N","14.12.2021",null,null,null,null,null,null,null,"","","","","Minor"]
[null,81,"Wels - Traun - Linz","< >","Marchtrenk","",2023,2023,22,23,"01.06.2023","22:00","05.06.2023","04:00","3 days + 6,0 h","cont.","GES","T","ST","","","","","","","","","Hib Ausbau LM 21","","N","14.12.2021",null,null,null,null,null,null,null,"","","","",""]
[null,81,"Linz - Wien (NRZ)",">","Enns","",2024,2024,12,13,"22.03.2024","22:00","25.03.2024","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Ausbau Weiche 66 und 67 für Ein- und Ausbau Hib (21.10.24)","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Linz","< >","Linz Hbf","Selzthal",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Hütteldorf","Knoten Wagram",2024,2024,14,17,"06.04.2024","00:00","28.04.2024","24:00","23 days","cont.","RES","","LT","","","","C","","B","","","Sperre Semmering","","N","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (NRZ)",">","Enns","",2024,2024,18,19,"03.05.2024","22:00","06.05.2024","05:00","2 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","HIB Einbau\nBf Enns\nUf – km 171,932\nDL 171,886","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wels - Linz","<","Marchtrenk","",2024,2024,22,23,"29.05.2024","22:00","03.06.2024","05:00","4 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Verschwenkung Gleis 1alt / 3neu / 1alt im Bahnhof Marchtrenk","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,25,26,"22.06.2024","05:00","24.06.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (GZ)","< >","Wien Hbf-Südosttangente (in Wbf)","Gramatneusiedl",2024,2024,26,36,"29.06.2024","09:00","02.09.2024","04:00","64 days + 19,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","23.09.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Wien - Sopron","< >","Wien Hbf-Südosttangente (in Wbf)","Gramatneusiedl",2024,2024,26,36,"29.06.2024","09:00","02.09.2024","04:00","64 days + 19,0 h","cont.","RES","","LT","","","","C","","B","","","Reinvestitionsarbeiten in verschiedenen Abschnitten","","Y","23.09.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,31,32,"03.08.2024","05:00","05.08.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Salzburg - Wels","<","Seekirchen am Wallersee","Sbl See 1",2024,2024,34,35,"24.08.2024","05:00","26.08.2024","05:00","2 days","cont.","SP","","LT","","","","C","","B","","","Errichtung Bahnsteig","","Y","11.01.2022",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (NRZ)",">","Linz Hbf","Sbl Kue 2",2024,2024,35,35,"31.08.2024","00:00","01.09.2024","24:00","2 days","cont.","SP","","LT","","","","","","",10,"","Anschwenkung Gleis 2 (Weststrecke) an Gleis 2We","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,81,"Linz - Wien (NRZ)","<","Sbl Kue 2","Linz Hbf",2024,2024,48,48,"30.11.2024","00:00","01.12.2024","24:00","2 days","cont.","SP","","LT","","","","","","",10,"","Anschwenkung Gleis  (Weststrecke) an Gleis 4 (neu)","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","","Medium"]
[null,81,"Wels - Traun - Linz","<","Marchtrenk","",2024,2024,22,23,"29.05.2024","22:00","03.06.2024","05:00","4 days + 7,0 h","cont.","SP","","ST","","","","C","","B","","","Verschwenkung Gleis 1alt / 3neu / 1alt im Bahnhof Marchtrenk","","Y","14.12.2021",null,null,null,null,null,null,null,null,"","","",""]
[null,87,"Strasbourg",">","Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Neudorf - Jonction Ouest",2022,2022,50,50,"2022-12-12","22:00:00","2022-12-17",0.25,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 3, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg",">","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Entrée Lavage",2023,2023,36,49,"2023-09-04","22:40:00","2023-12-09",0.19444444444444445,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg",">","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Entrée Lavage",2023,2023,9,9,"2023-02-28","00:15:00","2023-03-03",0.25347222222222221,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 05:45, Nuit non passe-minuit, MA,ME,JE,VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Neudorf - Jonction Est",2023,2023,38,43,"2023-09-18","22:40:00","2023-10-24",0.19444444444444445,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","< >","Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Port-du-Rhin - Poste 1",2022,2022,50,50,"2022-12-12","22:00:00","2022-12-17",0.25,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","<","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2023,2023,10,10,"2023-03-06","22:55:00","2023-03-10",0.18055555555555555,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE",null,"Y","2022-01-06"]
[null,87,"Strasbourg-Kehl","<","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2023,2023,13,42,"2023-03-27","22:40:00","2023-10-21",0.19444444444444445,null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Gen, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA",null,"Y","2022-01-06"]
[]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Dětmarovice","Bohumín",2022,2022,28,35,"2022-07-15","17:00","2022-08-31","17:00","47 days + 0 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Louky nad Olší","Karviná hlavní nádraží",2022,2022,37,37,"2022-09-15","17:30","2022-09-16","7:30","0 days + 14 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. obnovení šuntové citlivosti 0/2.","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Dětmarovice","Karviná hlavní nádraží",2022,2022,35,35,"2022-09-01","7:30","2022-09-02","16:30","2 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Dětmarovice","Dětmarovice",2022,2022,33,34,"2022-08-21","23:40","2022-08-24","4:10","3 x 5 hours","Periodical","Catenary","","ST","","","X","","","","","","1.,3.,3a jen TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Louky nad Olší","Karviná hlavní nádraží",2022,2022,40,41,"2022-10-04","18:00","2022-10-13","17:00","8 days + 23 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. vypnutí  PZZ v km 328,670 (P8290) a TZZ v 1/1.","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Karviná hlavní nádraží","Koukolná odb.",2022,2022,40,40,"2022-10-05","0:10","2022-10-05","1:00","1 x 1 hours","Periodical","Signal","T","LT","","","","","","","","","zab. zař. vypnutí TZZ v 1. a 2..","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Český Těšín","Český Těšín",2022,2022,44,44,"2022-11-01","7:30","2022-11-01","13:00","1 x 6 hours","Periodical","Catenary","","ST","","","X","","","","","","2.,6.,6a,8.,8a,10. jen TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Český Těšín","Český Těšín",2022,2022,44,44,"2022-11-03","7:30","2022-11-03","13:00","1 x 6 hours","Periodical","Catenary","","ST","","","X","","","","","","100.,101.-107.,101a jen TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Český Těšín","Český Těšín",2022,2022,47,47,"2022-11-22","7:40","2022-11-22","15:15","1 x 8 hours","Periodical","Switch","","ST","","","","",""," ,X,X","","","zhlaví od nám. výh. č. 27 po nám. výh. č. 29.","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Dětmarovice","Bohumín",2022,2022,46,46,"2022-11-15","7:20","2022-11-16","16:00","2 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Cesky Tesin - Zilina","< >","Třinec (Trzyniec)","Bystřice (Bystrzyca)",2022,2022,37,37,"2022-09-13","7:50","2022-09-13","13:10","1 x 6 hours","Periodical","Catenary","","LT","","","X","","","","","","1. + TV. ","","","2022-08-02"]
[null,null,"Cesky Tesin - Zilina","< >","Návsí (Nawsie)","Návsí (Nawsie)",2022,2022,41,41,"2022-10-10","13:00","2022-10-10","15:00","1 x 2 hours","Periodical","Switch","","ST","","","","",""," ,X,X","","","záhlaví a zhlaví ze směru Mosty u Jablunkova od náv. 1L po náv. S1.","","","2022-08-02"]
[null,54,"Cesky Tesin - Zilina","< >","Český Těšín","Třinec (Trzyniec)",2022,2022,44,44,"2022-10-31","1:00","2022-10-31","6:00","1 x 5 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. aktivace PZZ v km 317,026 (P8287).","","","2022-08-02"]
[null,54,"Cesky Tesin - Zilina","< >","Bystřice (Bystrzyca)","Návsí (Nawsie)",2022,2022,45,45,"2022-11-08","0:10","2022-11-08","1:00","2 x 1 hours","Periodical","Signal","T","LT","","","","","","","","","zab. zař. vypnutí TZZ v 1. a 2. TK.","","","2022-08-02"]
[null,54,"Cesky Tesin - Zilina","< >","Mosty u Jabl. (Mosty koło Jabł.)","Návsí (Nawsie)",2022,2022,46,46,"2022-11-15","0:20","2022-11-15","1:20","1 x 1 hours","Periodical","Signal","T","LT","","","","","","","","","zab. zař. vypnutí PZZ v km 290,925 (P8267) a PZZv km 291,194 (P8268).","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Jistebník","Studénka",2022,2022,37,37,"2022-09-14","7:15","2022-09-14","17:00","1 x 10 hours","Periodical","Switch","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Ostrava hlavní nádraží","Ostrava hlavní nádraží",2022,2022,36,36,"2022-09-05","7:30","2022-09-05","16:00","1 x 9 hours","Periodical","Catenary","","ST","","","X","","","","","","101a + TV. \nzáhlaví a zhlaví 1. traťové koleje ze směru Ostrava-Svinov od náv. 1S po náv. L101a .","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Ostrava hlavní nádraží","Ostrava hlavní nádraží",2022,2022,38,38,"2022-09-23","23:50","2022-09-24","2:00","1 x 3 hours","Periodical","Catenary","","ST","","","X","","","","","","101a jen TV, 102a + TV. \nzáhlaví a zhlaví 2. traťové koleje ze směru Ostrava – Svinov od náv. 2S po náv. L102a .","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2022,2022,40,40,"2022-10-08","7:05","2022-10-08","14:00","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Polanka nad Odrou výh.","Ostrava-Svinov",2022,2022,40,40,"2022-10-05","7:00","2022-10-05","13:00","1 x 6 hours","Periodical","Switch","","LT","","","","","","","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Polanka nad Odrou","Suchdol nad Odrou",2022,2022,44,44,"2022-10-31","7:00","2022-10-31","13:00","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Jistebník","Studénka",2022,2022,41,41,"2022-10-11","7:50","2022-10-11","14:50","1 x 7 hours","Periodical","Switch","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Valašská Polanka","Horní Lideč",2022,2022,4,49,"2022-01-24","8:00","2022-12-10","23:59","320 days + 16 hours","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Horní Lideč",2022,2022,35,35,"2022-09-01","7:00","2022-09-01","14:00","2 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,35,35,"2022-09-03","22:35","2022-09-04","6:25","0 days + 8 hours","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,36,36,"2022-09-05","22:35","2022-09-06","6:25","0 days + 8 hours","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,36,37,"2022-09-11","22:35","2022-09-12","6:25","0 days + 8 hours","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2022,2022,28,49,"2022-07-11","12:05","2022-12-10","23:59","152 days + 12 hours","Continuous","Miscellaneous","","ST","","","","",""," ,X,X","","","zhlaví část koleje od začátku výh. č. 1 po námezník výh. č. 2.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2022,2022,40,41,"2022-10-04","8:00","2022-10-12","14:00","9 x 6 hours","Periodical","Catenary","","ST","","","X","","","","","","1.,2.,4.,4a,5.,7.,9.,11.,13.,15.,17.,17b jen TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2022,2022,42,43,"2022-10-18","8:00","2022-10-26","14:00","9 x 6 hours","Periodical","Catenary","","ST","","","X","","","","","","1.,2.,4.,4a,5.,7.,9.,11.,13.,15.,17.,17b jen TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,41,41,"2022-10-13","22:35","2022-10-14","6:25","0 days + 8 hours","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,43,43,"2022-10-27","22:35","2022-10-28","6:25","0 days + 8 hours","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Lúky pod Makytou","Valašská Polanka",2022,2022,12,44,"2022-03-22","8:00","2022-11-01","13:00","2 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. vypne se napájení 6 kV.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Horní Lideč","Vsetín",2022,2022,10,44,"2022-03-09","8:00","2022-11-02","13:00","3 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. vypne se napájení 6kV.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,48,48,"2022-11-30","23:00","2022-12-01","3:00","1 x 4 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín bývalá Odb Bečva","Valašská Polanka",2022,2022,48,48,"2022-12-03","23:25","2022-12-04","3:50","1 x 5 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2022,2022,49,51,"2022-12-11","0:00","2022-12-22","17:00","11 days + 17 hours","Continuous","Miscellaneous","","ST","","","","",""," ,X,X","","","zhlaví část koleje od začátku výh. č. 1 po námezník výh. č. 2.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín",2022,2022,49,51,"2022-12-11","0:00","2022-12-22","17:00","11 days + 17 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Hoštejn","Česká Třebová",2022,2022,36,36,"2022-09-05","6:30","2022-09-09","13:30","5 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Prosenice","Hranice na Moravě",2022,2022,35,35,"2022-08-29","7:00","2022-08-29","14:00","2 x 7 hours","Periodical","Maintenance","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Červenka","Červenka",2022,2022,35,35,"2022-08-29","8:20","2022-08-29","12:40","1 x 5 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Olomouc přednádraží","Štěpánov",2022,2022,14,35,"2022-04-10","8:00","2022-08-31","13:00","3 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Brodek u Přerova","Dluhonice výhybna",2022,2022,9,37,"2022-03-03","8:00","2022-09-13","13:00","2 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájení 6 kV pro PZS v km 189,194.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Mohelnice","Lukavice na Moravě",2022,2022,16,37,"2022-04-24","8:00","2022-09-12","13:00","3 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Česká Třebová","Choceň",2022,2022,25,49,"2022-06-22","1:50","2022-12-10","23:59","171 days + 23 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2022,2022,25,49,"2022-06-22","1:50","2022-12-10","23:59","171 days + 23 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Dluhonice výhybna","Brodek u Přerova",2022,2022,38,38,"2022-09-23","8:20","2022-09-23","12:20","1 x 4 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Hranice na Moravě","Drahotuše",2022,2022,15,42,"2022-04-14","8:00","2022-10-20","13:00","2 x 5 hours","Periodical","Maintenance","","LT","","","","","","","","","zab. zař. napájecího kabelového vedení 6 kV.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2022,2022,48,48,"2022-12-01","7:00","2022-12-01","13:45","1 x 7 hours","Periodical","Catenary","","LT","","","X","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Štěpánov","Olomouc přednádraží",2022,2022,48,48,"2022-12-02","7:00","2022-12-02","14:00","1 x 7 hours","Periodical","Catenary","","LT","","","X","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Lukavice na Moravě","Mohelnice",2022,2022,45,45,"2022-11-09","7:00","2022-11-09","19:00","1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Mohelnice","Moravičany",2022,2022,45,45,"2022-11-11","7:00","2022-11-11","10:00","1 x 3 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Dluhonice výhybna","Prosenice",2022,2022,40,40,"2022-10-04","8:15","2022-10-04","12:15","1 x 4 hours","Periodical","Others","","LT","","","","","","","","","1S bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Prosenice","Dluhonice výhybna",2022,2022,40,40,"2022-10-05","8:15","2022-10-05","12:15","1 x 4 hours","Periodical","Others","","LT","","","","","","","","","2S bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Dluhonice výhybna","Prosenice",2022,2022,43,43,"2022-10-24","8:15","2022-10-25","17:55","2 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","1S + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Hoštejn","Česká Třebová",2022,2022,42,42,"2022-10-17","6:30","2022-10-17","13:30","1 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Svitavy","Česká Třebová",2022,2022,41,41,"2022-10-14","6:30","2022-10-14","12:30","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Česká Třebová","Parník odb.",2022,2022,43,43,"2022-10-24","12:40","2022-10-24","14:40","1 x 2 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Česká Třebová","Česká Třebová",2022,2022,42,42,"2022-10-21","18:30","2022-10-22","6:30","0 days + 12 hours","Continuous","Catenary","","ST","","","X","","","","","","6. bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Choceň","Brandýs n. Orlicí předjízdné koleje",2022,2022,40,41,"2022-10-07","22:45","2022-10-15","4:35","14 x 6 hours","Periodical","Catenary","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Přerov","Dluhonice výhybna",2022,2022,32,34,"2022-08-09","1:00","2022-08-26","17:00","17 days + 16 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. traťové - 2. TK.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Dluhonice výhybna","Brodek u Přerova",2022,2022,37,37,"2022-09-12","8:00","2022-09-16","15:00","4 days + 7 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. přejezdové - PZS P6527 (km 189,194) v úseku.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Prosenice",2022,2022,44,44,"2022-11-03","8:00","2022-11-03","16:00","1 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Červenka","Moravičany",2022,2022,44,44,"2022-11-04","7:00","2022-11-04","13:00","1 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Choceň","Brandýs n. Orlicí předjízdné koleje",2022,2022,47,48,"2022-11-25","22:45","2022-12-01","4:35","10 x 6 hours","Periodical","Track & Rail","T","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Hoštejn","Česká Třebová",2022,2022,45,45,"2022-11-09","6:30","2022-11-09","13:30","1 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Třebovice v Čechách","Třebovice v Čechách",2022,2022,47,47,"2022-11-21","8:00","2022-11-24","16:00","4 x 8 hours","Periodical","Track & Rail","","ST","","","","",""," ,X,X","","","záhlaví směr Mladějov na Moravě, jeho část od návěstidla ML po návěstidlo Se6 ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Česká Třebová","Dlouhá Třebová",2022,2022,46,46,"2022-11-15","7:30","2022-11-15","14:30","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Brandýs n. Orlicí předjízdné koleje","Choceň",2022,2022,47,47,"2022-11-25","7:00","2022-11-27","19:00","2 days + 12 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Odb Bezpráví","Brandýs nad Orlicí",2022,2022,29,49,"2022-07-21","22:45","2022-12-10","23:59","142 days + 2 hours","Continuous","Miscellaneous","","LT","","","","",""," ,X,X","","","2. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2022,2022,40,40,"2022-10-03","23:00","2022-10-05","4:30","2 x 6 hours","Periodical","Miscellaneous","","ST","","","X","","","","","","202. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,34,35,"2022-08-28","7:30","2022-08-31","17:30","4 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","202. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,34,34,"2022-08-23","7:30","2022-08-23","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","102. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Hostivař","Praha-Zahradní Město",2022,2022,34,34,"2022-08-23","7:30","2022-08-23","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Plzeň hlavní nádraží","Ejpovice",2022,2022,34,34,"2022-08-22","23:15","2022-08-23","4:15","1 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Zdice","Lochovice",2022,2022,39,39,"2022-09-28","8:00","2022-09-28","18:00","1 x 10 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. přejezdové v km 99,175 (P564).","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Beroun","Karlštejn",2022,2022,35,35,"2022-09-03","9:45","2022-09-04","19:30","2 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Beroun","Karlštejn",2022,2022,36,36,"2022-09-05","9:45","2022-09-05","19:30","1 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Závodiště odbočka","Praha-Radotín",2022,2022,36,37,"2022-09-06","7:30","2022-09-14","17:30","8 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Závodiště odbočka","Praha-Radotín",2022,2022,38,39,"2022-09-23","21:00","2022-09-26","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","4. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Odb Barrandov","Závodiště odbočka",2022,2022,36,37,"2022-09-09","21:00","2022-09-12","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Odb Barrandov","Závodiště odbočka",2022,2022,36,37,"2022-09-09","21:00","2022-09-12","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Závodiště odbočka","Tunel odb.",2022,2022,37,37,"2022-09-15","7:30","2022-09-15","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","3. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Eden","Praha-Zahradní Město",2022,2022,36,36,"2022-09-09","7:30","2022-09-10","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","201. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Hostivař","Praha-Zahradní Město",2022,2022,36,37,"2022-09-11","7:30","2022-09-12","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,36,37,"2022-09-11","7:30","2022-09-12","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","102. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Hostivař",2022,2022,37,37,"2022-09-13","23:00","2022-09-14","5:00","1 x 6 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,38,38,"2022-09-21","7:30","2022-09-22","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","202. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Hostivař",2022,2022,38,38,"2022-09-23","21:00","2022-09-25","17:30","1 days + 21 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[]
[null,54,"Plzen - Praha","< >","Praha-Eden","Praha-Zahradní Město",2022,2022,39,39,"2022-09-28","7:30","2022-09-28","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","201. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2022,2022,38,39,"2022-09-25","23:00","2022-09-26","4:00","1 x 5 hours","Periodical","Miscellaneous","","ST","","","X","","","","","","záhlaví 2. traťové koleje směr Plzeň-Koterov mezi návěstidly 2KL - Se204","","","2022-08-02"]
[]
[null,54,"Plzen - Praha","< >","Plzeň hlavní nádraží","Ejpovice",2022,2022,7,42,"2022-02-17","23:15","2022-10-21","4:15","2 x 5 hours","Periodical","Signal","","LT","","","","","","","","","ost. zař.: technologie 1.traťové koleje.","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Malešice","Praha-Malešice",2022,2022,39,39,"2022-10-01","22:00","2022-10-02","5:00","1 x 7 hours","Periodical","Catenary","","ST","","","X","","","","","","zhlaví ve směru Praha-Hostivař na 3. SK, tedy od návěstidela L3 po návěstidlo HSc.","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha jih",2022,2022,42,42,"2022-10-20","0:50","2022-10-20","4:00","1 x 4 hours","Periodical","Miscellaneous","T","LT","","","X","","","","","","","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,40,40,"2022-10-08","7:30","2022-10-09","17:30","2 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","102. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Krč",2022,2022,41,41,"2022-10-12","7:30","2022-10-12","17:30","1 x 10 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Zdice","Hořovice",2022,2022,41,41,"2022-10-12","8:00","2022-10-14","18:00","3 x 10 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Hostivař","Praha-Zahradní Město",2022,2022,46,46,"2022-11-15","7:30","2022-11-15","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Hostivař",2022,2022,46,46,"2022-11-17","23:00","2022-11-18","5:00","1 x 6 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Zahradní Město","Praha-Eden",2022,2022,46,46,"2022-11-19","7:30","2022-11-19","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","102. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Eden","Praha-Zahradní Město",2022,2022,47,47,"2022-11-22","7:30","2022-11-22","17:30","1 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","201. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Praha-Radotín","Závodiště odbočka",2022,2022,45,46,"2022-11-11","21:00","2022-11-14","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","3. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Závodiště odbočka","Praha-Radotín",2022,2022,46,47,"2022-11-18","21:00","2022-11-21","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","4. jen TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Závodiště odbočka","Praha-Radotín",2022,2022,46,47,"2022-11-18","21:00","2022-11-21","5:00","2 days + 8 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Ejpovice","Plzeň hlavní nádraží",2022,2022,45,45,"2022-11-10","23:15","2022-11-11","4:15","1 x 5 hours","Periodical","Tunnel","","LT","","","","","","","","","ost. zař.: technologie 2. traťové koleje.","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Borohrádek","Týniště nad Orlicí",2022,2022,36,36,"2022-09-05","7:10","2022-09-09","18:10","4 days + 11 hours","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Babín odb.","Nymburk předjízdné nádraží",2022,2022,35,35,"2022-09-04","8:30","2022-09-04","18:15","1 x 10 hours","Periodical","Switch","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Libice nad Cidlinou","Poděbrady",2022,2022,38,39,"2022-09-25","23:30","2022-09-28","4:20","3 x 5 hours","Periodical","Catenary","T","LT","","","","",""," ,X,X","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Libice nad Cidlinou","Poděbrady",2022,2022,45,47,"2022-11-07","7:30","2022-11-21","17:30","14 days + 10 hours","Continuous","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Hradec Králové hlavní nádraží","Hradec Králové hlavní nádraží",2022,2022,43,43,"2022-10-24","10:10","2022-10-24","11:50","1 x 2 hours","Periodical","Catenary","","ST","","","X","","","","","","13c,19c,29,31,33,51,53,55,57,59 jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Nymburk město","Sadská",2022,2022,35,35,"2022-09-04","7:30","2022-09-04","12:30","1 x 5 hours","Periodical","Miscellaneous","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Hradec Králové hlavní nádraží","Hradec Králové-Slez. Předměstí",2022,2022,37,37,"2022-09-12","23:45","2022-09-14","4:10","2 x 5 hours","Periodical","Others","T","LT","","","","","","","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Hradec Králové hlavní nádraží","Hradec Králové hlavní nádraží",2022,2022,46,46,"2022-11-14","10:10","2022-11-14","11:00","1 x 1 hours","Periodical","Catenary","","ST","","","X","","","","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Převýšov","Choťovice",2022,2022,45,45,"2022-11-08","11:30","2022-11-08","12:30","1 x 1 hours","Periodical","Catenary","","LT","","","X","","","","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Praskačka","Praskačka",2022,2022,47,47,"2022-11-22","2:10","2022-11-22","3:10","1 x 1 hours","Periodical","Catenary","","ST","","","X","","","","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Český Brod","Úvaly",2022,2022,35,35,"2022-09-04","6:00","2022-09-04","20:00","1 x 14 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Velim","Kolín",2022,2022,33,34,"2022-08-19","23:00","2022-08-27","4:05","8 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Choceň","Zámrsk",2022,2022,38,38,"2022-09-19","7:35","2022-09-19","14:20","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Poříčany","Odb Tatce",2022,2022,37,38,"2022-09-16","19:00","2022-09-19","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","",""," ,X,X","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Poříčany","Odb Tatce",2022,2022,36,37,"2022-09-09","19:00","2022-09-12","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Odb Tatce","Pečky",2022,2022,37,38,"2022-09-16","19:00","2022-09-19","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Kostěnice",2022,2022,39,43,"2022-09-29","3:50","2022-10-30","6:00","31 days + 3 hours","Continuous","Miscellaneous","","LT","","","","",""," ,X,X","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pečky","Odb Tatce",2022,2022,38,39,"2022-09-23","19:00","2022-09-26","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Odb Tatce","Poříčany",2022,2022,38,39,"2022-09-23","19:00","2022-09-26","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Úvaly","Český Brod",2022,2022,41,41,"2022-10-15","6:00","2022-10-15","14:00","1 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Kutná Hora hlavní nádraží","Kolín seřaďovací nádraží",2022,2022,40,40,"2022-10-08","7:00","2022-10-09","15:00","2 x 8 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pečky","Pečky",2022,2022,41,42,"2022-10-14","19:00","2022-10-17","5:00","2 days + 10 hours","Continuous","Miscellaneous","","ST","","","","",""," ,X,X","","","záhlaví tatské od návěstidla 2S po návěstidlo Se39","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pečky","Odb Tatce",2022,2022,41,42,"2022-10-14","19:00","2022-10-17","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","",""," ,X,X","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pečky","Poříčany",2022,2022,41,42,"2022-10-14","19:00","2022-10-17","5:00","2 days + 10 hours","Continuous","Miscellaneous","","LT","","","","","","","","","","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Velim","Velim",2022,2022,43,44,"2022-10-27","23:00","2022-10-31","4:05","3 days + 6 hours","Continuous","Miscellaneous","","ST","","","","",""," ,X,X","","","5. bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Pardubice hlavní nádraží",2022,2022,38,38,"2022-09-20","23:40","2022-09-21","3:50","1 x 5 hours","Periodical","Miscellaneous","","ST","","","","",""," ,X,X","","","1c bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Kostěnice","Pardubice hlavní nádraží",2022,2022,44,45,"2022-10-31","18:00","2022-11-11","18:00","11 days + 0 hours","Continuous","Miscellaneous","","LT","","","","",""," ,X,X","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Choceň","Choceň",2022,2022,40,41,"2022-10-07","22:45","2022-10-15","4:35","7 x 6 hours","Periodical","Catenary","","ST","","","","",""," ,X,X","","","záhlaví 1. TK směr Brandýs nad Orlicí","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Úvaly","Český Brod",2022,2022,35,35,"2022-09-03","8:00","2022-09-03","16:00","1 x 8 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Zámrsk","Uhersko",2022,2022,37,37,"2022-09-16","7:50","2022-09-16","14:50","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Moravany","Uhersko",2022,2022,37,37,"2022-09-17","7:50","2022-09-17","14:50","1 x 7 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Poříčany","Odb Tatce",2022,2022,46,46,"2022-11-17","19:00","2022-11-20","5:00","6 x 10 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Velim","Kolín",2022,2022,47,47,"2022-11-21","23:00","2022-11-22","5:00","1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Praha-Běchovice","Praha-Libeň",2022,2022,44,44,"2022-11-01","8:50","2022-11-01","13:20","1 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","0. + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Choceň","Choceň",2022,2022,47,48,"2022-11-25","22:45","2022-12-01","4:35","5 x 6 hours","Periodical","Track & Rail","","ST","","","","",""," ,X,X","","","záhlaví 1. TK směr Brandýs nad Orlicí","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Choceň","Choceň",2022,2022,47,48,"2022-11-27","22:45","2022-12-01","4:35","4 x 6 hours","Periodical","Miscellaneous","","ST","","","","",""," ,X,X","","","záhlaví 2. TK směr Brandýs nad Orlicí","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Kostěnice","Pardubice hlavní nádraží",2022,2022,45,45,"2022-11-10","23:40","2022-11-13","4:35","2 x 5 hours","Periodical","Switch","T","LT","","","","",""," ,X,X","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Kostěnice","Pardubice hlavní nádraží",2021,2022,49,49,"2021-12-12","0:00","2022-12-10","23:59","363 days + 24 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami .","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Přelouč",2021,2022,49,49,"2021-12-12","0:00","2022-12-10","23:59","363 days + 24 hours","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami .","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň-Koterov","Plzeň hlavní nádraží",2022,2022,38,38,"2022-09-22","23:00","2022-09-25","4:30","3 x 6 hours","Periodical","Miscellaneous","T","LT","","","X","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Staňkov bývalá Odb Vránov","Domažlice",2022,2022,40,43,"2022-10-09","7:30","2022-10-24","14:00","15 days + 7 hours","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Ostrava-Kunčice","Ostrava-Bartovice",2022,2022,36,36,"2022-09-06","23:30","2022-09-07","4:30","1 x 5 hours","Periodical","Switch","T","LT","","","","",""," ,X,X","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Ostrava-Vítkovice","Ostrava-Kunčice",2022,2022,36,36,"2022-09-05","22:45","2022-09-06","4:45","1 x 6 hours","Periodical","Switch","T","LT","","","","",""," ,X,X","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Český Těšín","Albrechtice u Českého Těšína",2022,2022,43,43,"2022-10-24","1:00","2022-10-24","6:00","1 x 5 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. aktivace PZZ v km 321,086/ 1,820 (P8288).","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Ostrava-Kunčice","Ostrava-Vítkovice",2022,2022,40,40,"2022-10-06","12:15","2022-10-06","16:00","1 x 4 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. bez TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Albrechtice u Českého Těšína","Havířov",2022,2022,48,48,"2022-11-28","7:10","2022-11-28","15:00","1 x 8 hours","Periodical","Others","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Havířov","Albrechtice u Českého Těšína",2022,2022,48,48,"2022-11-29","7:10","2022-11-30","15:00","2 x 8 hours","Periodical","Others","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Ostrava-Vítkovice","Odra odb.",2022,2022,46,46,"2022-11-15","22:00","2022-11-16","2:00","1 x 4 hours","Periodical","Others","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Albrechtice u Českého Těšína","Havířov",2022,2022,38,38,"2022-09-19","7:15","2022-09-21","19:00","3 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Ostrava-Vítkovice","Odra odb.",2022,2022,35,35,"2022-08-29","7:10","2022-08-31","13:50","3 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2022,2022,36,36,"2022-09-10","8:00","2022-09-10","16:00","1 x 8 hours","Periodical","Catenary","","ST","","","","",""," ,X,X","","","801.,803.,805. + TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Brod nad Tichou","Planá u Mariánských Lázní",2022,2022,37,37,"2022-09-17","23:10","2022-09-18","5:10","1 x 6 hours","Periodical","Track & Rail","T","LT","","","","","","","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2022,2022,37,37,"2022-09-17","7:30","2022-09-17","13:10","1 x 6 hours","Periodical","Others","","LT","","","X","","","","","","1. jen TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2022,2022,45,45,"2022-11-07","7:40","2022-11-10","13:10","4 x 6 hours","Periodical","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2022,2022,47,47,"2022-11-23","7:30","2022-11-23","9:30","1 x 2 hours","Periodical","Switch","","ST","","","","",""," ,X,X","","","zhlaví směr Františkovy Lázně, část od návěstidla Se74 po námezník výhybky č. 88.","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Brod nad Tichou","Planá u Mariánských Lázní",2022,2022,34,34,"2022-08-24","7:15","2022-08-24","14:45","1 x 8 hours","Periodical","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Valašské Meziříčí","Kunovice-Loučka",2023,2023,38,40,"2023-09-18",null,"2023-10-02",null,"15 days","Continuous","Miscellaneous","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín bývalá Odb Bečva",2023,2023,30,32,"2023-07-25",null,"2023-08-08",null,"15 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ - úvazka.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2023,2023,30,51,"2023-07-25",null,"2023-12-18",null,"147 days","Continuous","Signal","","ST","","","","","","","","","zab. zař. SZZ - aktivace def. ZZ ve vyloučené  SKS.","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Jablůnka","Valašské Meziříčí",2023,2023,31,32,"2023-08-01",null,"2023-08-10",null,"10 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Hranice na Moravě město","Hustopeče nad Bečvou",2023,2023,22,23,"2023-06-01",null,"2023-06-05",null,"5 days","Continuous","Miscellaneous","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Zilina","< >","Vsetín","Vsetín",2023,2023,30,43,"2023-07-26",null,"2023-10-27",null,"94 days","Continuous","Miscellaneous","","ST","","","","","","","","","výh.: 52/M1. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Odb Bezpráví","Ústí nad Orlicí",2023,2023,5,10,"2023-02-01",null,"2023-03-07",null,"35 days","Continuous","Track & Rail","","LT","","","","",""," ,X,X","","","1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Ústí nad Orlicí","Odb Bezpráví",2023,2023,15,20,"2023-04-12",null,"2023-05-16",null,"35 days","Continuous","Track & Rail","","LT","","","","",""," ,X,X","","","2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Zábřeh na Moravě","Postřelmov",2023,2023,48,48,"2023-11-27",null,"2023-12-01",null,"5 days","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2023,2023,16,16,"2023-04-17",null,"2023-04-21",null,"5 days","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Třebovice v Čechách","Rudoltice v Čechách",2023,2023,40,40,"2023-10-02",null,"2023-10-06",null,"5 days","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Hradec Králové hlavní nádraží","Hradec Králové-Slez. Předměstí",2023,2023,30,30,"2023-07-24",null,"2023-07-28",null,"5 days","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Opočno pod Orlickými horami",2023,2023,19,20,"2023-05-09",null,"2023-05-18",null,"10 days","Continuous","Switch","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Chlumec nad Cidlinou","Smidary",2023,2023,25,25,"2023-06-19",null,"2023-06-23",null,"5 x 8 hours","Periodical","Switch","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Choceň","Újezd u Chocně",2023,2023,12,13,"2023-03-24",null,"2023-04-02",null,"20 x 8 hours","Periodical","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Nymburk seřaďovací nádraží","Nymburk seřaďovací nádraží",2023,2023,26,34,"2023-07-01",null,"2023-08-24",null,"55 days","Continuous","Switch","","ST","","","","","","","","","22.-34. jen TV, výh.: 220,221,223,224,225,229,231,234,235,236,244,245,246,247,248,249,251,256,257,258,261,262. ","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Blížejov","Domažlice",2023,2023,31,33,"2023-07-31",null,"2023-08-18",null,"19 days","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň hlavní nádraží","Dobřany",2023,2023,38,40,"2023-09-22",null,"2023-10-06",null,"15 days","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2023,2023,48,48,"2023-12-01",null,"2023-12-02",null,"1 x 6 hours","Periodical","Catenary","","ST","","","","",""," ,X,X","","","201.,202. + TV. \nzáhlaví a zhlaví směr Plzeň-Koterov 1. a 2. traťové koleje.","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Uhersko","Uhersko",2023,2023,23,23,"2023-06-08",null,"2023-06-10",null,"3 days","Continuous","Track & Rail","","ST","","","","","","","","","1,3 + TV, výh.: 12,14,15. ","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2023,2023,41,42,"2023-10-09",null,"2023-10-20",null,"12 days","Continuous","Miscellaneous","","ST","","","X","","","","","","záhlaví směr Plzeň-Koterov 2. traťové koleje mezi návěstidly 2KL - Se204","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2023,2023,42,42,"2023-10-18",null,"2023-10-20",null,"3 days","Continuous","Miscellaneous","","ST","","","","",""," ,X,X","","","záhlaví směr Plzeň-Koterov 1. traťové koleje mezi návěstidly 1KL - Se203","","","2022-08-02"]
[null,54,"Regensburg - Plzen","< >","Plzeň hlavní nádraží","Plzeň hlavní nádraží",2023,2023,20,20,"2023-05-15",null,"2023-05-19",null,"5 days","Continuous","Miscellaneous","","ST","","","","","","","","","201. bez TV. \nzhlaví směr Plzeň-Koterov, jeho část od návěstidla Se203 po návěstidlo Se208.","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2023,2023,15,17,"2023-04-11",null,"2023-04-25",null,"15 days","Continuous","Switch","","ST","","","","","","","","","2,4a,4b,6 jen TV, výh.: 28, 29, 33. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2023,2023,28,30,"2023-07-11",null,"2023-07-27",null,"17 days","Continuous","Switch","","ST","","","","","","","","","2.,4b,6. jen TV, výh.: 64, 77. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2023,2023,52,22,"2023-01-01",null,"2023-05-31",null,"151 days","Continuous","Bridge","","ST","","","","","","","","","140.,142.,144. jen TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Cheb",2023,2023,52,22,"2023-01-01",null,"2023-05-31",null,"151 days","Continuous","Bridge","","ST","","","","","","","","","132.,134. bez TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2023,2023,6,6,"2023-02-06",null,"2023-02-10",null,"5 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ 1.,2..","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2023,2023,14,14,"2023-04-03",null,"2023-04-04",null,"2 x 2 hours","Periodical","Track & Rail","","LT","","","","","","","","","1. bez TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Ošelín","Ošelín",2023,2023,44,45,"2023-10-30",null,"2023-11-09",null,"11 days","Continuous","Track & Rail","","ST","","","","","","","","","2 bez TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","< >","Pňovany","Planá u Mariánských Lázní",2023,2023,41,49,"2023-10-11",null,"2023-12-09",null,"60 days","Continuous","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Ostrava - Detmarovice - Cesky Tesin","< >","Bohumín","Bohumín st.hr.",2023,2023,20,22,"2023-05-15",null,"2023-06-03",null,"20 days","Continuous","Others","","LT","","","X","","","","","","traťová jen TV. ","","","2022-08-02"]
[null,54,"Ostrava - Cesky Tesin","< >","Albrechtice u Českého Těšína","Havířov",2024,2024,35,35,"2024-08-30",null,"2024-08-31",null,"1 x 3 hours","Periodical","Track & Rail","T","LT","","","","","","","","","2 bez TV. ","","","2022-08-02"]
[null,54,"Nürnberg - Plzen","<>","Tršnice","Cheb",2024,2024,27,48,"2024-07-01",null,"2024-11-30T23:59:59.997",null,"153 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Český Brod","Úvaly",2024,2024,32,33,"2024-08-10",null,"2024-08-13T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","1. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Běchovice","Úvaly",2024,2024,29,30,"2024-07-21",null,"2024-07-24T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","0. + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Praha-Libeň","Praha-Běchovice",2024,2024,27,27,"2024-07-01",null,"2024-07-04T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Nýřany","Chotěšov výh.",2024,2024,27,48,"2024-07-04",null,"2024-11-27T23:59:59.997",null,"147 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Nýřany","",2024,2024,27,48,"2024-07-04",null,"2024-11-27T23:59:59.997",null,"147 days","Continuous","Miscellaneous","","ST","","","","","","B","","","1,2,3,4,6,8,10 bez TV. \nzáhlaví domažlické",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Plzeň hl.n.Nová Hospoda","Nýřany",2024,2024,9,27,"2024-02-28",null,"2024-07-03T23:59:59.997",null,"127 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Regensburg - Plzen","<>","Stod","Domažlice",2024,2024,27,30,"2024-07-04",null,"2024-07-22T23:59:59.997",null,"19 days","Continuous","Track & Rail","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Zilina","<>","Horní Lideč","Horní Lideč st.hr.",2024,2024,14,28,"2024-04-01",null,"2024-07-09T23:59:59.997",null,"100 days","Continuous","Track & Rail","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Studénka","",2024,2024,47,48,"2024-11-18T18:00:00",null,"2024-11-25T06:00:00",null,"7 x 6 hours","Periodical","Bridge","","ST","","","D","","","","","","lichá jen TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Jistebník","Studénka",2024,2024,10,11,"2024-03-09",null,"2024-03-16T23:59:59.997",null,"8 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ TK 1 a 2.",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,16,17,"2024-04-17",null,"2024-04-24T23:59:59.997",null,"8 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","< >","Studénka","Studénka",2024,2024,11,12,"2024-03-17",null,"2024-03-24",null,"7 x 6 hours","Periodical","Bridge","","ST","","","X","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","< >","Studénka","Studénka",2024,2024,47,48,"2024-11-18",null,"2024-11-25",null,"7 x 6 hours","Periodical","Bridge","","ST","","","X","","","","","","lichá jen TV. ","","","2022-08-02"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Odry",2024,2024,27,31,"2024-07-05",null,"2024-07-31T23:59:59.997",null,"27 days","Continuous","Bridge","T","LT","","","","","","B","","","traťová bez TV. ",null,null,"2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Svojšín","",2024,2024,17,20,"2024-04-24",null,"2024-05-13T23:59:59.997",null,"20 days","Continuous","Track & Rail","","ST","","","","","","B","","","záhlaví směr Bor (od BL k Se3)",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","< >","Beroun","Karlštejn",2024,2024,18,19,"2024-04-30",null,"2024-05-07",null,"7 x 3 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1 bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Beroun","Karlštejn",2024,2024,22,24,"2024-05-31",null,"2024-06-16",null,"16 x 6 hours","Periodical","Miscellaneous","T","LT","","","","",""," ,X,X","","","1 + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Karlštejn","Beroun",2024,2024,43,44,"2024-10-26",null,"2024-11-02",null,"7 x 3 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2 bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Beroun","Karlštejn",2024,2024,25,28,"2024-06-23",null,"2024-07-14",null,"21 x 3 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1 bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Karlštejn","Beroun",2024,2024,48,51,"2024-11-30",null,"2024-12-21",null,"21 x 3 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2 bez TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","< >","Karlštejn","Beroun",2024,2024,11,11,"2024-03-15",null,"2024-03-16",null,"1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","",""," ,X,X","","","2 + TV. ","","","2022-08-02"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,25,28,"2024-06-23T18:00:00",null,"2024-07-14T06:00:00",null,"21 x 3 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","1 bez TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Beroun",2024,2024,43,44,"2024-10-26T18:00:00",null,"2024-11-02T06:00:00",null,"7 x 3 hours","Periodical","Miscellaneous","","LT","","","","","","","","","2 bez TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,48,51,"2024-11-30",null,"2024-12-21T23:59:59.997",null,"22 days","Continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Beroun",2024,2024,11,11,"2024-03-15T18:00:00",null,"2024-03-16T06:00:00",null,"1 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Beroun",2024,2024,24,48,"2024-06-16",null,"2024-11-29T23:59:59.997",null,"167 days","Continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Ostrava - Cesky Tesin","<>","Ostrava-Vítkovice","Odra odb.",2024,2024,35,41,"2024-09-01",null,"2024-10-10T23:59:59.997",null,"40 days","Continuous","Miscellaneous","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Nürnberg - Plzen","<>","Chodová Planá","Mariánské Lázně",2024,2024,14,31,"2024-04-03",null,"2024-07-31T23:59:59.997",null,"120 days","Continuous","Track & Rail","T","LT","","","","","","B","","","traťová + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Beroun",2024,2024,48,51,"2024-11-30T18:00:00",null,"2024-12-21T06:00:00",null,"21 x 3 hours","Periodical","Miscellaneous","T","LT","","","","","","","","","2 bez TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Zadní Třebaň","Liteň",2024,2024,36,37,"2024-09-02",null,"2024-09-11T23:59:59.997",null,"10 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. SZZ.",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2024,2024,18,19,"2024-05-04",null,"2024-05-09T23:59:59.997",null,"6 days","Continuous","Track & Rail","T","LT","","","","","","B","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice-Rosice nad Labem","Pardubice hlavní nádraží",2024,2024,13,13,"2024-03-27",null,"2024-03-31T23:59:59.997",null,"5 days","Continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2024,2024,14,15,"2024-04-05",null,"2024-04-11T23:59:59.997",null,"7 days","Continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Karlštejn","Beroun",2024,2024,22,24,"2024-05-31T18:00:00",null,"2024-06-16T06:00:00",null,"16 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,22,24,"2024-05-31T18:00:00",null,"2024-06-16T06:00:00",null,"16 x 6 hours","Periodical","Miscellaneous","T","LT","","","","","","B","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","< >","Kostěnice","Pardubice hlavní nádraží",2024,2024,9,9,"2024-03-02",null,"2024-03-02",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Kostěnice","Pardubice hlavní nádraží",2024,2024,22,22,"2024-05-29",null,"2024-05-30",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Kostěnice",2024,2024,9,9,"2024-03-01",null,"2024-03-01",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Kostěnice",2024,2024,22,22,"2024-05-27",null,"2024-05-28",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Přelouč",2024,2024,21,21,"2024-05-24",null,"2024-05-24",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","",""," ,X,X","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Přelouč",2024,2024,22,22,"2024-05-30",null,"2024-05-31",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Přelouč","Pardubice hlavní nádraží",2024,2024,21,21,"2024-05-25",null,"2024-05-25",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","",""," ,X,X","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Přelouč","Pardubice hlavní nádraží",2024,2024,22,22,"2024-05-28",null,"2024-05-29",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Přelouč nákladní nádraží","Heřmanův Městec",2024,2024,14,26,"2024-04-01",null,"2024-06-30",null,"91 x 10 hours","Periodical","Miscellaneous","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Heřmanův Městec","Přelouč nákladní nádraží",2024,2024,40,44,"2024-10-01",null,"2024-10-31",null,"31 x 8 hours","Periodical","Miscellaneous","T","LT","","","","",""," ,X,X","","","traťová bez TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Kostěnice",2024,2024,22,23,"2024-06-01",null,"2024-06-03",null,"3 x 11 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Pardubice hlavní nádraží",2024,2024,28,28,"2024-07-08",null,"2024-07-12",null,"4 x 6 hours","Periodical","Catenary","","ST","","","","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Přelouč","Pardubice hlavní nádraží",2024,2024,23,23,"2024-06-04",null,"2024-06-06",null,"3 x 11 hours","Periodical","Catenary","","LT","","","","",""," ,X,X","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Přelouč",2024,2024,24,24,"2024-06-10",null,"2024-06-12",null,"3 x 11 hours","Periodical","Catenary","","LT","","","","",""," ,X,X","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice hlavní nádraží","Pardubice-Rosice nad Labem",2024,2024,32,32,"2024-08-10",null,"2024-08-11",null,"2 x 11 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","< >","Pardubice-Rosice nad Labem","Pardubice hlavní nádraží",2024,2024,26,26,"2024-06-28",null,"2024-06-29",null,"2 x 11 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Kostěnice",2024,2024,22,22,"2024-05-27T18:00:00",null,"2024-05-29T06:00:00",null,"2 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Přelouč","Pardubice hlavní nádraží",2024,2024,21,21,"2024-05-25",null,"2024-05-25T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","B","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2024,2024,21,21,"2024-05-25",null,"2024-05-25T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 1. TK směr Přelouč po výh. 81.",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2024,2024,22,22,"2024-05-29T18:00:00",null,"2024-05-31T06:00:00",null,"2 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Přelouč",2024,2024,21,21,"2024-05-24",null,"2024-05-24T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","B","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","",2024,2024,21,21,"2024-05-24",null,"2024-05-24T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","ST","","","","","","B","","","záhlaví a zhlaví 2. TK směr Přelouč po výh. 80.",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice hlavní nádraží",2024,2024,20,20,"2024-05-18",null,"2024-05-19T23:59:59.997",null,"2 days","Continuous","Track & Rail","","LT","","","","","","","","","95 bez TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Pardubice hlavní nádraží",2024,2024,17,18,"2024-04-24",null,"2024-05-03T23:59:59.997",null,"10 days","Continuous","Track & Rail","","LT","","","","","","","","","91 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Kostěnice",2024,2024,9,9,"2024-03-01",null,"2024-03-01T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,18,19,"2024-04-30T18:00:00",null,"2024-05-07T06:00:00",null,"7 x 3 hours","Periodical","Miscellaneous","","LT","","","","","","","","","1 bez TV. ",null,null,"2021-12-23"]
[null,54,"Plzen - Praha","<>","Beroun","Karlštejn",2024,2024,9,22,"2024-03-01",null,"2024-05-30T23:59:59.997",null,"91 days","Continuous","Miscellaneous","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2024,2024,9,9,"2024-03-02",null,"2024-03-02T23:59:59.997",null,"1 x 12 hours","Periodical","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Pardubice hlavní nádraží","Přelouč nákladní nádraží",2024,2024,1,44,"2024-01-01",null,"2024-10-30T23:59:59.997",null,"304 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami.",null,null,"2021-12-23"]
[null,54,"Praha - Chocen","<>","Kostěnice","Pardubice hlavní nádraží",2024,2024,1,44,"2024-01-01",null,"2024-10-30T23:59:59.997",null,"304 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. ETCS mezi dopravnami.",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Kostomlaty nad Labem","Nymburk hlavní nádraží",2024,2024,41,42,"2024-10-07",null,"2024-10-16",null,"10 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Kostomlaty nad Labem","Nymburk hlavní nádraží",2024,2024,43,44,"2024-10-22",null,"2024-10-31",null,"10 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Kostomlaty nad Labem","Nymburk hlavní nádraží",2024,2024,48,49,"2024-12-01",null,"2024-12-04",null,"4 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Nymburk hlavní nádraží","Kostomlaty nad Labem",2024,2024,35,37,"2024-09-01",null,"2024-09-10",null,"10 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Nymburk hlavní nádraží","Kostomlaty nad Labem",2024,2024,38,39,"2024-09-16",null,"2024-09-29",null,"14 x 9 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,15,17,"2024-04-12",null,"2024-04-23",null,"11 x 6 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,17,17,"2024-04-26",null,"2024-04-27",null,"1 x 6 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,30,30,"2024-07-23",null,"2024-07-24",null,"1 x 6 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,40,40,"2024-10-02",null,"2024-10-04",null,"2 x 6 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,46,46,"2024-11-11",null,"2024-11-12",null,"1 x 6 hours","Periodical","Catenary","","ST","","","X","",""," ,X,X","","","celá + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,17,17,"2024-04-26",null,"2024-04-28",null,"3 x 6 hours","Periodical","Miscellaneous","","ST","","","X","","","","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,21,22,"2024-05-26",null,"2024-05-27",null,"2 x 6 hours","Periodical","Miscellaneous","","ST","","","X","","","","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,27,27,"2024-07-03",null,"2024-07-03",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","X","","","","","","celá jen TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Chlumec nad Cidlinou","Dobšice nad Cidlinou",2024,2024,27,27,"2024-07-04",null,"2024-07-07",null,"8 x 8 hours","Periodical","Track & Rail","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Hradec Králové hlavní nádraží","Týniště nad Orlicí",2024,2024,22,22,"2024-05-28",null,"2024-05-30",null,"3 x 8 hours","Periodical","Switch","T","LT","","","","",""," ,X,X","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Týniště nad Orlicí","Týniště nad Orlicí",2024,2024,31,31,"2024-07-29",null,"2024-07-31",null,"3 x 8 hours","Periodical","Switch","","ST","","","","",""," ,X,X","","","výh.: 2. \nzáhlaví a zhlaví častolovické.","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Velký Osek","Libice nad Cidlinou",2024,2024,14,14,"2024-04-06",null,"2024-04-06",null,"1 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Libice nad Cidlinou","Velký Osek",2024,2024,14,14,"2024-04-07",null,"2024-04-07",null,"1 x 10 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Velký Osek","Velký Osek-Kanín",2024,2024,15,16,"2024-04-14",null,"2024-04-16",null,"2 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","201.,202. + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Velký Osek-Kanín","Dobšice nad Cidlinou",2024,2024,16,16,"2024-04-16",null,"2024-04-18",null,"2 x 5 hours","Periodical","Catenary","","LT","","","","","","","","","traťová + TV. ","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","< >","Velký Osek","Nymburk hlavní nádraží",2024,2024,16,17,"2024-04-19",null,"2024-04-26",null,"18 x 4 hours","Periodical","Catenary","","LT","","","X","","","","","","","","","2022-08-02"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,4,5,"2024-01-24",null,"2024-01-29T23:59:59.997",null,"6 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,5,7,"2024-02-01",null,"2024-02-12T23:59:59.997",null,"12 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,12,13,"2024-03-24",null,"2024-03-26T23:59:59.997",null,"3 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,15,15,"2024-04-10",null,"2024-04-11T23:59:59.997",null,"2 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,20,20,"2024-05-19",null,"2024-05-19T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,23,23,"2024-06-08",null,"2024-06-08T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,33,34,"2024-08-18",null,"2024-08-19T23:59:59.997",null,"2 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,38,38,"2024-09-19",null,"2024-09-19T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,39,39,"2024-09-27",null,"2024-09-27T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,43,43,"2024-10-25",null,"2024-10-25T23:59:59.997",null,"1 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,44,44,"2024-10-28",null,"2024-10-29T23:59:59.997",null,"2 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","",2024,2024,49,50,"2024-12-04",null,"2024-12-10T23:59:59.997",null,"7 x 6 hours","Periodical","Miscellaneous","","ST","","","D","","","","","","celá jen TV. ",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Borohrádek","Týniště nad Orlicí",2024,2024,33,38,"2024-08-18",null,"2024-09-18T23:59:59.997",null,"32 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2024,2024,33,38,"2024-08-18",null,"2024-09-18T23:59:59.997",null,"32 days","Continuous","Signal","","LT","","","","","","","","","zab. zař. TZZ.",null,null,"2021-12-23"]
[null,54,"Praha - Hradec Kralove - Chocen","<>","Týniště nad Orlicí","Třebechovice pod Orebem",2024,2024,11,11,"2024-03-15",null,"2024-03-17T23:59:59.997",null,"3 days","Continuous","Miscellaneous","T","LT","","","","","","B","","","traťová + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2024,2024,1,7,"2024-01-02",null,"2024-02-15",null,"44 x 6 hours","Periodical","Track & Rail","T","LT","","","X","","","","","","1,2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2024,2024,23,25,"2024-06-05",null,"2024-06-21",null,"16 x 3 hours","Periodical","Track & Rail","T","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2024,2024,48,50,"2024-11-27",null,"2024-12-09",null,"12 x 3 hours","Periodical","Track & Rail","T","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Olomouc hlavní nádraží","Grygov",2024,2024,16,17,"2024-04-17",null,"2024-04-24",null,"8 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,17,18,"2024-04-24",null,"2024-04-30",null,"7 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,22,22,"2024-05-30",null,"2024-05-31",null,"2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Olomouc hlavní nádraží","Grygov",2024,2024,22,22,"2024-05-28",null,"2024-05-29",null,"2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,22,23,"2024-06-01",null,"2024-06-03",null,"2 x 4 hours","Periodical","Catenary","T","LT","","","","","","","","","2,1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,23,23,"2024-06-05",null,"2024-06-06",null,"1 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,25,26,"2024-06-22",null,"2024-06-29",null,"7 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,30,30,"2024-07-23",null,"2024-07-26",null,"3 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Olomouc hlavní nádraží","Grygov",2024,2024,30,31,"2024-07-28",null,"2024-07-29",null,"2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,30,30,"2024-07-26",null,"2024-07-27",null,"2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,41,41,"2024-10-07",null,"2024-10-08",null,"1 x 16 hours","Periodical","Signal","","LT","","","","","","","","","zab. zař. SZZ, TZZ, PZZ.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Grygov","Olomouc hlavní nádraží",2024,2024,41,41,"2024-10-07",null,"2024-10-08",null,"1 x 4 hours","Periodical","Signal","T","LT","","","","","","","","","zab. zař. SZZ, TZZ, PZZ.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,24,25,"2024-06-15",null,"2024-06-22T23:59:59.997",null,"8 days","Continuous","Bridge","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,23,24,"2024-06-07",null,"2024-06-14T23:59:59.997",null,"8 days","Continuous","Bridge","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","< >","Hoštejn předjízdné koleje","Zábřeh na Moravě",2024,2024,9,9,"2024-02-28",null,"2024-02-28",null,"1 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","< >","Zábřeh na Moravě","Hoštejn předjízdné koleje",2024,2024,9,9,"2024-02-29",null,"2024-02-29",null,"1 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ","","","2022-08-02"]
[null,54,"Cesky Tesin - Zilina","< >","Mosty u Jabl. (Mosty koło Jabł.)","Mosty u Jabl. (Mosty koło Jabł.)",2024,2024,41,41,"2024-10-08",null,"2024-10-08",null,"1 x 4 hours","Periodical","Tunnel","","ST","","","","",""," ,X,X","","","celá + TV. \nzáhlaví a zhlaví ze směru Čadca.","","","2022-08-02"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,30,30,"2024-07-26",null,"2024-07-27T23:59:59.997",null,"2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,30,31,"2024-07-28",null,"2024-07-29T23:59:59.997",null,"2 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,23,23,"2024-06-05T18:00:00",null,"2024-06-06T06:00:00",null,"1 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,25,26,"2024-06-22T18:00:00",null,"2024-06-29T06:00:00",null,"7 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,30,30,"2024-07-23T18:00:00",null,"2024-07-26T06:00:00",null,"3 x 4 hours","Periodical","Bridge","T","LT","","","","","","","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,22,23,"2024-06-01T18:00:00",null,"2024-06-03T06:00:00",null,"2 x 4 hours","Periodical","Catenary","T","LT","","","","","","","","","2,1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Olomouc hlavní nádraží","Grygov",2024,2024,22,22,"2024-05-28",null,"2024-05-29T23:59:59.997",null,"2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,22,22,"2024-05-30",null,"2024-05-31T23:59:59.997",null,"2 x 8 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Grygov","Olomouc hlavní nádraží",2024,2024,17,18,"2024-04-24",null,"2024-04-30T23:59:59.997",null,"7 x 6 hours","Periodical","Catenary","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Polom",2024,2024,13,14,"2024-03-29",null,"2024-04-01T23:59:59.997",null,"4 days","Continuous","Track & Rail","","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Polom","Suchdol nad Odrou",2024,2024,44,46,"2024-11-01",null,"2024-11-16T23:59:59.997",null,"16 days","Continuous","Track & Rail","","LT","","","","","","","","","1 + TV. ",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Polom",2024,2024,13,13,"2024-03-25",null,"2024-03-26T23:59:59.997",null,"2 days","Continuous","Signal","","LT","","","","","","","","","zab. a sděl. zař. TZZ.",null,null,"2021-12-23"]
[null,54,"Hranice na Morave - Ostrava","<>","Suchdol nad Odrou","Polom",2024,2024,10,10,"2024-03-04",null,"2024-03-05T23:59:59.997",null,"2 x 2 hours","Periodical","Catenary","T","LT","","","","","","","","","2 + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Hoštejn předjízdné koleje","Zábřeh na Moravě",2024,2024,9,9,"2024-02-28",null,"2024-02-28T23:59:59.997",null,"2 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","1. + TV. ",null,null,"2021-12-23"]
[null,54,"Chocen - Hranice na Morave","<>","Zábřeh na Moravě","Hoštejn předjízdné koleje",2024,2024,9,9,"2024-02-29",null,"2024-02-29T23:59:59.997",null,"1 x 7 hours","Periodical","Catenary","","LT","","","","","","","","","2. + TV. ",null,null,"2021-12-23"]
[null,56,"Žilina - Košice",">","Žilina","Varín",2022,2022,35,50,"2022-08-30",null,"2022-12-15",null,"107 days","continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Rekonštrukcia 1 TK a v.č.3, 4, 9, 10.",null,"Y"]
[null,56,"Žilina - Košice",">","Žilina","Odb. Váh",2022,2023,50,17,"2022-12-15",null,"2023-04-28",null,"134 days","continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Rekonštrukcia 1 TK a v.č.11, 12, 13.",null,"Y"]
[null,56,"Žilina - Košice","< >","Žilina","Žilina",2021,2023,25,31,"2021-06-21",null,"2023-07-31",null,"754 days","continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"Demontáž psk, rekonštrukcia mostu km 250, 586, budovanie podchodov. 2K, č. 12-48.",null,"Y"]
[null,56,"Žilina - Košice","< >","Žilina","Žilina",2022,2022,1,52,"2022-01-01",null,"2022-12-31",null,"365 days","continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"Uzol Žilina, modernizácia.",null,"Y"]
[null,56,"Hranice na Moravě - Žilina","< >","Dolný Hričov","Žilina",2022,2022,40,40,null,null,null,null,"6 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"OGPK, TK 1/2.",null,"N"]
[null,56,"Hranice na Moravě - Žilina","< >","Dolný Hričov","Dolný Hričov",2022,2022,41,41,null,null,null,null,"6 days","periodical","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"OGPK, OGPV, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Žilina","Kysucké Nové Mesto",2022,2022,45,45,null,null,null,null,"4 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Brúsenie koľajníc, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Kysucké Nové Mesto","Krásno nad Kysucou",2022,2022,39,39,null,null,null,null,"6 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"OGPK, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Krásno nad Kysucou","Čadca",2022,2022,35,35,null,null,null,null,"6 days","periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia v km 271,359, TK 1/2.",null,"N"]
[null,56,"Český Těšín - Žilina","< >","Krásno nad Kysucou","Čadca",2022,2022,17,22,null,null,null,null,"30 days","continuous","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia v km 276,050 - 274,950, TK 1.",null,"N"]
[null,56,"Hranice na Moravě - Žilina","< >","Púchov","Lúky pod Makytou št. hr.",2022,2022,17,26,null,null,null,null,"60 days","continuous","Catenary",null,"LT+ST","S",null,null,null,null,null,null,null,"KRTV",null,"N"]
[null,54,"Cesky Tesin - Zilina","<>","Mosty u Jabl. (Mosty koło Jabł.)","",2024,2024,41,41,"2024-10-08",null,"2024-10-08T23:59:59.997",null,"1 x 4 hours","Periodical","Tunnel","","ST","","","","","","B","","","celá + TV. \nzáhlaví a zhlaví ze směru Čadca.",null,null,"2021-12-23"]
[null,56,"Žilina - Košice","< >","Ružomberok",null,2022,2022,40,43,"2022-10-03",null,"2022-10-28",null,"15 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"KRŽZ užitý mat., koľ. č. 4 a 6.",null,"N"]
[null,56,"Žilina - Košice","< >","Ružomberok","Ľubochňa",2022,2022,35,36,"2022-09-02",null,"2022-09-11",null,"6 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"SVK k. č. 1, 2, TK 1, 2.",null,"N"]
[null,56,"Žilina - Košice","< >","Ružomberok","Ľubochňa",2022,2022,37,38,"2022-09-12",null,"2022-09-23",null,"7 days","periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia km 282,567.",null,"N"]
[null,56,"Žilina - Košice","< >","Ružomberok","Ľubochňa",2022,2022,40,41,"2022-10-03",null,"2022-10-15",null,"6 days","periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia km 291,997.",null,"N"]
[null,56,"Žilina - Košice","< >","Vrútky","Varín",2022,2022,39,39,"2022-09-26",null,"2022-09-30",null,"5 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"SVK k. č. 1,2",null,"N"]
[null,56,"Žilina - Košice","< >","Varín",null,2022,2022,17,50,"2022-04-29",null,"2022-12-15",null,"231 days","continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"NSK, rekonštrukcia k.č.1, 3 a výhybiek",null,"Y"]
[null,56,"Košice - Čierna nad Tisou",">","Michaľany","Slovenské Nové Mesto",2022,2022,33,34,"2022-08-18",null,"2022-08-26",null,"10 days","periodical","Switch",null,"LT+ST","S",null,null,null,null,null,null,null,"TK 1, OKLV výh. č. 1, 3, 6, ( koľ. č. 1 + stred DKS ).",null,"N"]
[null,56,"Košice - Čierna nad Tisou","<","Ruskov","Nižná Myšľa",2022,2022,38,39,"2022-09-19",null,"2022-09-28",null,"9 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 1, výmena podvalov a koľajnic .",null,"N"]
[null,56,"Košice - Čierna nad Tisou","< >","Nižná Myšľa",null,2022,2022,40,41,"2022-10-03",null,"2022-10-14",null,"11 days","periodical","Others",null,"ST","S",null,null,null,null,null,null,null,"Oprava nástupíšť medzi k.č.1 -2,1 - 3.",null,"N"]
[null,56,"Košice - Čierna nad Tisou","<","Nižná Myšľa","Krásna nad Hornádom",2022,2022,40,41,"2022-10-03",null,"2022-10-14",null,"11 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, OGPK + SVK Km 85,500 - 89,500.",null,"N"]
[null,56,"Košice - Čierna nad Tisou","< >","Nižná Myšľa","Krásna nad Hornádom",2022,2022,26,26,null,null,null,null,"20 days","periodical continuous","Bridge",null,"LT","S",null,null,null,null,null,null,null,"Oprava OK mosta km 86,952.",null,"N"]
[null,56,"Žilina - Košice","< >","Margecany",null,2022,2022,22,35,null,null,null,null,"92 days","periodical","Bridge",null,"ST","S",null,null,null,null,null,null,null,"Koľ. č. 1, oprava priepustu v km 131,496.",null,"N"]
[null,56,"Žilina - Košice","< >","Margecany",null,2022,2022,40,41,"2022-10-03",null,"2022-10-14",null,"11 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"Koľ. č. 2., výmena podvalov koľ.č. 2 km 131,350-131,787 / 133,100-133,470.",null,"N"]
[null,56,"Žilina - Košice","< >","Košice",null,2022,2022,1,52,"2022-01-01",null,"2022-12-31",null,"365 days","periodical","Others",null,"ST","S",null,null,null,null,null,null,null,"KR nástupíšť 1, 2, 3 a koľají 1,1b,3a,5,7,9,11, noc.",null,"Y"]
[null,56,"Žilina - Košice","< >","Markušovce","Spišské Vlachy",2022,2022,33,34,"2022-08-15",null,"2022-08-26",null,"11 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2, SVP.",null,"N"]
[null,56,"Haniska pri Košic. - Maťovce","< >","Vojany","Drahňov",2022,2022,17,18,null,null,null,null,"10 days","continuous","Bridge",null,"LT","S",null,null,null,null,null,null,null,"Výmena mostníc MO km 27,020.",null,"N"]
[null,56,null,null,"Púchov","Lúky pod Makytou št. hr.",2022,2022,35,44,"2022-09-01",null,"2022-10-31",null,"60 days","continuous","Catenary",null,"LT+ST","S",null,null,null,null,null,null,null,"KRTV",null,"N"]
[null,56,null,null,"Ružomberok",null,2022,2022,40,43,"2022-10-03",null,"2022-10-28",null,"15 days","periodical","Track & Rail",null,"ST","S",null,null,null,null,null,null,null,"KRŽZ užitý mat., koľ. č. 4 a 6.",null,"N"]
[null,56,null,null,"Ružomberok","Ľubochňa",2022,2022,35,36,"2022-09-02",null,"2022-09-11",null,"6 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"SVK k. č. 1, 2, TK 1, 2.",null,"N"]
[null,56,null,null,"Ružomberok","Ľubochňa",2022,2022,37,38,"2022-09-12",null,"2022-09-23",null,"7 days","periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia km 282,567.",null,"N"]
[null,56,null,null,"Ružomberok","Ľubochňa",2022,2022,40,41,"2022-10-03",null,"2022-10-15",null,"6 days","periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia km 291,997.",null,"N"]
[null,56,null,null,"Vrútky","Varín",2022,2022,39,39,"2022-09-26",null,"2022-09-30",null,"5 days","periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"SVK k. č. 1,2",null,"N"]
[null,56,null,null,"Žilina","Varín",2022,2023,28,9,"2022-07-11","00:00:00","2023-03-02",1,235,"continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Rekonštrukcia 1 TK a v.č.3, 4, 9, 10.",null,"Y"]
[null,56,null,null,"Žilina","Odb. Váh",2022,2023,28,9,"2022-07-11","00:00:00","2023-03-02",1,235,"continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"Rekonštrukcia 1 TK a v.č.11, 12, 13.",null,"Y"]
[null,56,null,null,"Žilina","Žilina",2022,2023,11,40,"2022-03-18","00:00:00","2023-10-08",1,570,"continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"Demontáž psk, rekonštrukcia mostu km 250, 586, budovanie podchodov. 2K, č. 12-48.",null,"Y"]
[null,56,null,null,"Žilina","Žilina",2022,2023,8,40,"2022-02-23","00:00:00","2023-10-08",1,542,"continuous","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"Uzol Žilina, modernizácia.",null,"Y"]
[null,56,null,null,"Dolný Hričov","Žilina",2022,2022,40,40,"2022-10-03","00:00:00","2022-10-08",1,6,"periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"OGPK, TK 1/2.",null,"N"]
[null,56,null,null,"Dolný Hričov","Dolný Hričov",2022,2022,41,41,"2022-10-10","00:00:00","2022-10-15",1,6,"periodical","Miscellaneous",null,"ST","S",null,null,null,null,null,null,null,"OGPK, OGPV, TK 1/2.",null,"N"]
[null,56,null,null,"Žilina","Kysucké Nové Mesto",2022,2022,45,45,"2022-11-07","00:00:00","2022-11-10",1,4,"periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Brúsenie koľajníc, TK 1/2.",null,"N"]
[null,56,null,null,"Čadca","Čadca št. hr.",2022,2023,28,17,"2022-07-11","00:00:00","2023-04-30",1,293,"continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Modernisation","54","Y"]
[null,56,null,null,"Kysucké Nové Mesto","Krásno nad Kysucou",2022,2022,39,39,"2022-09-26","00:00:00","2022-10-01",1,6,"periodical","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"OGPK, TK 1/2.",null,"N"]
[null,56,null,null,"Krásno nad Kysucou","Čadca",2022,2022,35,35,"2022-08-29","00:00:00","2022-09-03",1,6,"periodical","Signal",null,"LT","S",null,null,null,null,null,null,null,"KR priecestia v km 271,359, TK 1/2.",null,"N"]
[null,56,null,null,"Michaľany","Slovenské Nové Mesto",2022,2022,32,35,"2022-08-01","00:00:00","2022-08-26",1,"26 days","continuous","Switch",null,"LT+ST",null,null,null,null,null,null,null,null,"OKLV výh. č. 2, 4, 5, 7, 8 ( koľ. č. 2 ), výh. č. 1, 3, 6, ( koľ. č. 1 + stred DKS ) ",null,"Y"]
[null,56,null,null,"Ruskov","Nižná Myšľa",2022,2022,36,36,"2022-08-30","00:00:00","2022-09-04",1,"6 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 1, Oprava geometrickej polohy koľaje km 77,500 - 84,000.",null,"N"]
[null,56,null,null,"Výh. Lučivná","Svit",2022,2022,28,48,"2022-07-12","00:00:00","2022-11-30","00:00:00","142 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"Modernizácia, TK 1.",null,"Y"]
[null,56,null,null,"Ruskov","Nižná Myšľa",2022,2022,39,40,"2022-09-19","00:00:00","2022-09-28",1,"10 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 1, výmena podvalov a koľajnic .",null,"N"]
[null,56,null,null,"Ruskov","Nižná Myšľa",2022,2022,33,34,"2022-08-08","00:00:00","2022-08-19",1,"12 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"TK 2,OKLK, oprava geometrickej polohy koľaje km 77,500 - 84,000",null,"N"]
[null,56,null,null,"Nižná Myšľa","Nižná Myšľa",2022,2022,41,42,"2022-10-03","00:00:00","2022-10-14",1,"12 days","continuous","Others",null,"ST","S",null,null,null,null,null,null,null,"Koľ. č. 2, súvisla výmena koľajníc km 84,300 - 84,500",null,"N"]
[null,43,"Wien - Ebenfurth - Sopron","< >","Baumgarten","Sopron",2022,2022,32,35,"2022-08-13","07:00:00","2022-09-03","23:30:00",21.6875,"continuous","Track & Rail","T"]
[null,43,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2023,2023,20,20,"2023-05-08","08:30:00","2023-05-14","18:30:00",6.4166666666666661,"continuous","Track & Rail","T"]
[null,43,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2023,2023,20,23,"2023-05-08","08:30","2023-05-31","18:30",23.416666666666664,"continuous","Catenary","T"]
[null,43,"Sopron - Győr","< >","Csorna","Győr",2023,2023,38,40,"2023-09-17","06:40","2023-09-30","20:30",13.576388888888888,"continuous","Maintenance","T"]
[null,43,"Sopron - Győr","< >","Fertőendréd","Kapuvár",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Kapuvár","Rábatamási",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Sopron","Fertőszentmiklós",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Track & Rail","T"]
[null,43,"Sopron - Győr","< >","Pinnye","Fertőszentmiklós",2023,2023,42,45,"2023-10-09","07:30","2023-10-31","15:40",22.340277777777779,"continuous","Catenary","T"]
[null,55,"Györ - Budapest","<","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-01","22:00:00","2022-09-02","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-02","22:00:00","2022-09-03","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Ferencváros","Kelenföld",2022,2022,35,35,"2022-09-03","22:00:00","2022-09-04","05:30:00",0.31250000000000011,"Night","Bridge",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Budapest-Kelenföld","Budaörs",2022,2022,36,36,"2022-09-09","22:00:00","2022-09-12","05:00:00",2.2916666666666665,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest","<","Budapest-Kelenföld","Budaörs",2022,2022,37,37,"2022-09-16","22:00:00","2022-09-19","05:00:00",2.2916666666666665,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Györ - Budapest",">","Komárom","Ács",2022,2022,40,41,"2022-10-07","22:00:00","2022-10-10","04:00:00",2.25,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,44112]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Vecsés",2022,2022,24,25,"2022-06-17","23:00:00","2022-06-20","04:00:00",{"$f":"M4865-K4865+N4865-L4865","v":2.208333333333333},"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,24,"2022-06-17","23:50:00","2022-06-18","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,24,"2022-06-18","23:50:00","2022-06-19","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Vecsés",2022,2022,24,25,"2022-06-19","23:50:00","2022-06-20","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Vecsés","Üllő",2022,2022,25,25,"2022-06-20","04:00:00","2022-06-24","23:00:00",4.7916666666666661,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-20","23:50:00","2022-06-21","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-21","23:50:00","2022-06-22","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-22","23:50:00","2022-06-23","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-23","23:50:00","2022-06-24","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,25,26,"2022-06-24","23:00:00","2022-06-27","04:00:00",2.208333333333333,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-24","23:50:00","2022-06-25","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,25,"2022-06-25","23:50:00","2022-06-26","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,25,26,"2022-06-26","23:50:00","2022-06-27","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Vecsés","Üllő",2022,2022,26,26,"2022-06-27","04:00:00","2022-06-29","03:40:00",1.9861111111111109,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-27","23:50:00","2022-06-28","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-28","23:50:00","2022-06-29","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Vecsés","Üllő",2022,2022,26,26,"2022-06-29","03:40:00","2022-07-01","23:00:00",2.8055555555555558,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-29","23:50:00","2022-06-30","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-06-30","23:50:00","2022-07-01","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,26,27,"2022-07-01","23:00:00","2022-07-04","04:00:00",2.208333333333333,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-07-01","23:50:00","2022-07-02","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,26,"2022-07-02","23:50:00","2022-07-03","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,26,27,"2022-07-03","23:50:00","2022-07-04","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Vecsés","Üllő",2022,2022,27,27,"2022-07-04","03:40:00","2022-07-08","23:00:00",4.8055555555555554,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-04","23:50:00","2022-07-05","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-05","23:50:00","2022-07-06","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-06","23:50:00","2022-07-07","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","< >","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-07","23:50:00","2022-07-08","03:40:00",0.15972222222222221,"Night","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok","<","Pestszentlőrinc","Üllő",2022,2022,27,28,"2022-07-08","23:00:00","2022-07-11","23:00:00",3,"Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-08","23:50:00","2022-07-09","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,27,"2022-07-09","23:50:00","2022-07-10","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Budapest - Cegléd - Szolnok",">","Pestszentlőrinc","Üllő",2022,2022,27,28,"2022-07-10","23:50:00","2022-07-11","03:40:00",0.15972222222222221,"Night","Track & Rail",null,"LT",null,null,null,null,null,null,"D",null,"Single line operation\n(closure of one track of a double track line)",null,"N",null,43910]
[null,55,"Szolnok - Cluj","< >","Sáp","Biharkeresztes",2022,2022,24,44,"2022-06-18","00:00:00","2022-11-06","23:59:00",141.99930555555557,"Continuous","Track & Rail","T","LT","S",null,null,null,null,null,"D",null,"Total closure",null,"N",null,44112]
[null,53,"Arad - Simeria","< >","Barzava","Milova",2022,2023,null,null,"2022-06-14","00:00:00","2023-03-08","00:00:00",267,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Milova","Radna",2018,2023,null,null,"2018-03-06","00:00:00","2023-03-08","00:00:00",1828,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Radna","Paulis",2022,2023,null,null,"2022-06-14","00:00:00","2023-03-08","00:00:00",267,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Savarsin","Barzava Noua",2021,2023,null,null,"2021-08-19","00:00:00","2023-02-20","00:00:00",550,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Gurasada "," Campuri Surduc",2020,2022,null,null,"2020-04-03","00:00:00","2022-12-20","00:00:00",991,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Arad - Simeria","< >","Campuri Surduc"," Zam",2022,2022,null,null,"2022-12-15","00:00:00","2022-12-20","00:00:00",5,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Vanatori ","Cristur",2023,2023,null,null,"05.10.2023","00:00:00","2023-10-16","00:00:00",11,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Cata","Rupea",2022,2025,null,null,"01.06.2022","00:00:00","21.03.2025","00:00:00",1024,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Beia","Mureni",2023,2025,null,null,"12.05.2023","00:00:00","21.03.2025","00:00:00",679,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Mureni","Vanatori",2022,2025,null,null,"01.05.2022","00:00:00","21.03.2025","00:00:00",1055,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Vanatori","Albesti",2021,2024,null,null,"19.04.2021","00:00:00","01.10.2024","00:00:00",1261,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Albesti","Sighisoara",2021,2023,null,null,"19.04.2021","00:00:00","10.02.2023","00:00:00",662,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Apata","Augustin",2021,2023,null,null,"2021-04-15","00:00:00","2023-08-11","00:00:00",848,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Augustin","Rupea",2022,2024,null,null,"2022-03-01","00:00:00","2024-06-25","00:00:00",847,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Rupea","Cata",2022,2023,null,null,"2022-11-16","00:00:00","2023-10-09","00:00:00",327,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Brasov","Stupini",2020,2022,null,null,"01.09.2020","00:00:00","25.07.2022","00:00:00",692,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Brasov","Stupini",2024,2025,null,null,"28.08.2024","00:00:00","06.03.2025","00:00:00",190,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2020,2023,null,null,"26.08.2020","00:00:00","17.08.2023","00:00:00",1086,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Stupini","Bod",2023,2023,null,null,"15.05.2023","00:00:00","2023-06-15","00:00:00",31,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2022,2025,null,null,"26.05.2022","00:00:00","06.03.2025","00:00:00",1015,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2022,2022,null,null,"22.09.2022","00:00:00","2022-09-25","00:00:00",3,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Bod","Feldioara",2023,2023,null,null,"15.05.2023","00:00:00","2023-06-15","00:00:00",31,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Simeria - Brasov","< >","Feldioara","Apata",2022,2025,null,null,"25.04.2022","00:00:00","06.03.2025","00:00:00",1046,"Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Simeria - Brasov","< >","Feldioara","Apata",2024,2024,null,null,"15.07.2024","00:00:00","2024-07-19","00:00:00",4,"Continuous","Track & Rail","T","LT",null,null,null,"C,,","R,,",null,null,null,"Total closure. Re-reouting necessary."]
[null,53,"Biharkeresztes - Coslariu","< >","Valea Florilor","Boju",2022,2022,null,null,"2022-06-01","00:00:00","2022-12-31","00:00:00",213,"Continuous","Track & Rail",null,"LT","S",null,"x",null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,53,"Biharkeresztes - Coslariu","< >","Cluj Napoca","Episcopia Bihor",2022,2025,null,null,"2022-07-01","00:00:00","2025-12-31","00:00:00",1279,"Continuous","Track & Rail"]

{"sheet":"Graphic Overview","index":2,"n_rows":1063,"n_cols":375,"rows_kept":1063,"cut":false,"hidden":false,"merged":[[3,362,3,368],[3,369,3,373],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,341,3,347],[3,348,3,354],[3,355,3,361],[3,313,3,319],[3,236,3,242],[3,243,3,249],[3,250,3,256],[3,257,3,263],[3,264,3,270],[3,271,3,277],[3,278,3,284],[3,285,3,291],[3,292,3,298],[3,299,3,305],[3,306,3,312],[3,229,3,235],[3,152,3,158],[3,159,3,165],[3,166,3,172],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,194,3,200],[3,201,3,207],[3,208,3,214],[3,215,3,221],[3,222,3,228],[3,145,3,151],[3,68,3,74],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,103,3,109],[3,110,3,116],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,138,3,144],[2,343,2,373],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,33,3,39],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,282,2,312],[2,313,2,342],[2,129,2,159],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128]]}
[null,"Rhine-Danube, Overview"]
[]
[null,null,null,null,null,null,2021,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-12-12","2022-07-29T18:00:00","229 d, 18 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-09-26T22:00:00","2021-09-27T05:00:00","7 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-09-30T08:00:00","2021-10-05T08:59:00","5 d, 01 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Lohr Bahnhof - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-01T22:00:00","2021-10-05T05:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Aschaffenburg Hbf Ausfahrt - Kleinostheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Frankfurt - Aschaffenburg","continuous","2021-10-01T22:00:00","2021-10-08T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Partenstein - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Nantenbach - Lohr Bahnhof",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-02T01:00:00","2021-10-04T05:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Rohrbach - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Nantenbach - Partenstein",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Aschaffenburg - Gemünden","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Weinheim (Bergstr) - Weinheim (Bergstr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-01T01:00:00","2021-02-05T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-08T05:00:00","2021-02-12T21:00:00","4 d, 16 h","DB Netz AG"]
[]
[null,"Heddesheim/Hirschberg - Hemsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-02-15T01:00:00","2021-02-19T21:00:00","4 d, 20 h","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Neu-Edingen/Mhm-Friedrichsfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-05-27","2021-06-18T23:59:00","23 d","DB Netz AG"]
[]
[null,"Neu-Edingen/Mhm-Friedrichsfeld - Heidelberg-Wieblingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Bruchsal - Mannheim","continuous","2021-06-04T21:00:00","2021-06-08T04:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Nord - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-01-15T23:30:00","2021-01-18T01:30:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-13T00:30:00","2021-02-15T13:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-02-15T13:00:00","2021-11-09T23:45:00","267 d, 11 h","DB Netz AG"]
[]
[null,"Dieburg - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-22T09:00:00","2021-11-15T23:59:00","10 d, 15 h","DB Netz AG"]
[]
[null,"Dieburg - Messel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Messel - Dieburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-10-23T23:50:00","2021-11-15T05:20:00","22 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt-Kranichstein - Babenhausen (Hess)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","periodical","2021-10-24T23:30:00","2021-11-07T05:30:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-01T08:00:00","2021-11-16T06:00:00","14 d, 22 h","DB Netz AG"]
[]
[null,"Mainaschaff Abzw - Aschaffenburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T21:00:00","2021-11-16T05:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Stockstadt (Main) - Stockstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T22:00:00","2021-11-16T06:00:00","6 d, 08 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-09T23:45:00","2021-11-17T04:45:00","7 d, 05 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-15T06:00:00","2021-11-30T06:00:00","15 d","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-19T22:00:00","2021-11-22T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-22T05:00:00","2021-11-26T22:00:00","4 d, 17 h","DB Netz AG"]
[]
[null,"Darmstadt Hbf - Darmstadt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Darmstadt Gbf - Darmstadt Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Darmstadt - Aschaffenburg","continuous","2021-11-26T22:00:00","2021-11-29T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Stuttgart Hbf - Stuttgart-Zuffenhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Ebersbach (Fils) - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-25T22:00:00","2021-01-26T04:30:00","7 h","DB Netz AG"]
[]
[null,"Stuttgart-Bad Cannstatt - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-04T21:00:00","2021-02-08T05:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Geislingen (Steige) - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-02-09T21:00:00","2021-02-12T05:00:00","1 d","DB Netz AG"]
[]
[null,"Ulm Hbf - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-02-28T23:30:00","2021-03-02T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-02T23:30:00","2021-03-14T04:30:00","11 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm-Örlingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-14T23:00:00","2021-03-25T04:30:00","10 d, 05 h","DB Netz AG"]
[]
[null,"Beimerstetten - Beimerstetten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-15T22:00:00","2021-03-22T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Ulm-Örlingen - Ulm Hbf Em Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-25T23:30:00","2021-03-27T04:30:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19","2021-08-09T04:00:00","21 d, 04 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-02T01:00:00","2021-08-13T22:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Ulm Hbf Em Nord - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T20:00:00","2021-08-16T04:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Amstetten (Württ) - Geislingen (Steige)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-16T22:00:00","3 d","DB Netz AG"]
[]
[null,"Göppingen - Eislingen (Fils)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-08-27T04:00:00","13 d, 06 h","DB Netz AG"]
[]
[null,"Geislingen West - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Göppingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-13T22:00:00","2021-09-03T04:00:00","20 d, 06 h","DB Netz AG"]
[]
[null,"Uhingen - Göppingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-26T22:00:00","2021-08-27T04:00:00","6 h","DB Netz AG"]
[]
[null,"Eislingen (Fils) - Gingen (Fils) Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-27T22:00:00","2021-09-03T22:00:00","7 d","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-01-29T22:30:00","2021-02-02T05:15:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:00:00","2021-04-24T05:20:00","14 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-09T22:20:00","2021-04-12T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:00:00","2021-05-10T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-07T22:30:00","2021-05-10T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-05-14T22:30:00","2021-05-17T04:50:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Ulm Hbf - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-07","2021-08-09T04:00:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Burgau (Schwab)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:00:00","2021-12-11T04:00:00","14 d, 05 h","DB Netz AG"]
[]
[null,"Günzburg - Neuoffingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Unterfahlheim - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-26T23:30:00","2021-11-29T05:30:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Nersingen - Ulm Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-11-29","2021-12-04T05:00:00","5 d, 05 h","DB Netz AG"]
[]
[null,"Neuoffingen - Günzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Günzburg - Unterfahlheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-12-03T22:30:00","2021-12-06T05:20:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Mannheim Hbf Ost - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-02-06T02:35:00","2021-02-08T04:35:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Mannheim-Rheinau - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-06-20T22:00:00","2021-08-03T04:00:00","43 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-07-28T22:00:00","2021-08-03T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Mannheim-Rheinau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-08-03T04:00:00","2021-09-13T04:00:00","41 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-07T21:00:00","2021-08-23T05:00:00","2 d","DB Netz AG"]
[]
[null,"Philippsburg Molzau - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-08-09T23:00:00","2021-08-21T05:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Schwetzingen - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-06","2021-10-06T23:59:00","31 d","DB Netz AG"]
[]
[null,"Oftersheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-08T22:00:00","2021-09-16T06:00:00","7 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-09-08T22:00:00","2021-09-16T06:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Schwetzingen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-18T22:00:00","2021-09-20T06:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Schwetzingen - Oftersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Schwetzingen - Hockenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-09-25","2021-09-27T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Waghäusel - Waghäusel",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Hockenheim - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-10-02T22:00:00","2021-10-05T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Graben-Neudorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","continuous","2021-03-08","2021-03-23T23:59:00","16 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Forchheim (b Karlsruhe) - Durmersheim Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-05-13T00:01:00","2021-05-17T04:30:00","4 d, 04 h","DB Netz AG"]
[]
[null,"Karlsruhe Hbf Bft Südeinfahrt - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Graben-Neudorf - Philippsburg Molzau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Mannheim","periodical","2021-07-19T23:00:00","2021-08-07T05:00:00","3 d, 18 h","DB Netz AG"]
[]
[null,"Durmersheim Nord - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-20T23:00:00","2021-08-23T05:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bashaide - Karlsruhe Hbf Bft Südeinfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-08-30T23:00:00","2021-11-08T04:30:00","69 d, 05 h","DB Netz AG"]
[]
[null,"Durmersheim - Bashaide",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-03T22:00:00","2021-10-29T05:00:00","25 d, 07 h","DB Netz AG"]
[]
[null,"Durmersheim - Durmersheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-10-29T23:00:00","2021-11-02T04:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Pforzheim Hbf - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-02-06T02:00:00","2021-02-08T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Vaihingen (Enz) - Vaihingen (Enz)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-03-18","2021-05-03T23:59:00","47 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Wilferdingen-Singen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-07","2021-05-11T23:59:00","5 d","DB Netz AG"]
[]
[null,"Wilferdingen-Singen - Pforzheim Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-08T02:00:00","2021-05-10T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Sachsenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-02-13T21:00:00","2021-02-18T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Sachsenheim - Tamm (Württ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","periodical","2021-03-02T22:00:00","2021-03-06T04:30:00","1 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Karlshöhe - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-22T01:45:00","2021-06-07T04:00:00","16 d, 02 h","DB Netz AG"]
[]
[null,"Kornwestheim Pbf - Kornwestheim Karlshöhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-07T08:00:00","2021-09-07T16:00:00","8 h","DB Netz AG"]
[]
[null,"Stuttgart-Zuffenhausen - Kornwestheim Pbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-10-23T01:45:00","2021-10-25T04:00:00","2 d, 02 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-06T23:00:00","2021-12-11T23:59:00","308 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-02-22T08:00:00","2021-12-11T23:59:00","292 d, 16 h","DB Netz AG"]
[]
[null,"Appenweier-Muhrhaag - Appenweier Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-12T23:35:00","2021-03-15T04:15:00","2 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-03-29T00:15:00","2021-04-02T00:15:00","4 d","DB Netz AG"]
[]
[null,"Rastatt - Rastatt-Süd",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T00:15:00","2021-04-06T03:00:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-05-23T04:30:00","50 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-04-02T23:00:00","2021-08-30","149 d, 01 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-05-24T23:00:00","2021-07-01T04:30:00","37 d, 05 h","DB Netz AG"]
[]
[null,"Rastatt - Rastatt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rastatt - Basel Grenze","continuous","2021-08-30","2021-11-08T04:30:00","70 d, 04 h","DB Netz AG"]
[]
[null,"Appenweier Nord - Appenweier Kurve",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Strasbourg - Karlsruhe","continuous","2021-03-27T00:30:00","2021-03-29T04:30:00","2 d, 04 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-04-23T07:00:00","2021-05-05T17:00:00","12 d, 10 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-04T00:45:00","2021-07-04T06:45:00","6 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-09T23:00:00","2021-07-17T05:00:00","7 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-10T22:00:00","2021-07-11T06:45:00","9 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Karlstadt (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-07-11T22:00:00","2021-07-14T04:40:00","20 h","DB Netz AG"]
[]
[null,"Karlstadt (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-07-25T00:45:00","2021-07-25T06:45:00","6 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-09-27T07:00:00","2021-10-25T18:00:00","28 d, 11 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T07:00:00","2021-10-05T17:00:00","4 d, 10 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-01T22:00:00","2021-10-04T04:50:00","21 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-04T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-01T22:00:00","2021-10-14T05:00:00","12 d, 07 h","DB Netz AG"]
[]
[null,"Langenprozelten - Nantenbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-04T05:00:00","2021-10-05T05:00:00","1 d","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-04T22:00:00","2021-10-12T04:50:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Langenprozelten",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-16","2021-10-18T06:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Gemünden (Main) - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","continuous","2021-10-20T05:00:00","2021-10-25T05:00:00","5 d","DB Netz AG"]
[]
[null,"Langenprozelten - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Würzburg - Nürnberg","periodical","2021-10-20T22:00:00","2021-10-25T05:00:00","21 h","DB Netz AG"]
[]
[null,"München-Lochhausen - München-Pasing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-03-22T22:00:00","2021-03-27T05:40:00","4 d, 08 h","DB Netz AG"]
[]
[null,"München-Pasing - München-Lochhausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-03-22T22:45:00","2021-03-27T05:20:00","1 d, 09 h","DB Netz AG"]
[]
[null,"München-Pasing - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Rosenheim - Rosenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-03-10T00:40:00","2021-03-14T02:40:00","4 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-09T02:00:00","2021-11-23T04:00:00","14 d, 02 h","DB Netz AG"]
[]
[null,"München Hbf - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","continuous","2021-11-23T04:00:00","2021-12-11T23:59:00","18 d, 20 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-05","2021-02-08T04:50:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-12T00:25:00","2021-02-15T05:00:00","3 d, 05 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-02-14T19:10:00","2021-02-15T04:10:00","9 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Seubersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical continuous","2021-02-21T00:25:00","2021-03-01T04:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-06T22:20:00","2021-03-07T05:20:00","7 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-07T22:00:00","2021-03-08T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-11T21:40:00","2021-03-12T04:00:00","6 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg-Prüfening               (NRH)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-13T22:20:00","2021-03-15T04:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-03-19T16:00:00","2021-03-21T16:00:00","2 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-03-20T22:20:00","2021-03-21T05:10:00","7 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-04-01T23:30:00","2021-04-06T06:00:00","4 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-04-09T23:30:00","2021-05-17T06:00:00","13 d, 15 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-21T23:30:00","2021-05-25T06:00:00","3 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-05-26T21:00:00","2021-06-05T05:00:00","9 d, 08 h","DB Netz AG"]
[]
[null,"Postbauer-Heng - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-05-27T01:00:00","2021-06-21T05:00:00","25 d, 04 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-05T21:00:00","2021-06-26T05:00:00","20 d, 08 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-07T21:00:00","2021-06-19T04:00:00","2 d, 22 h","DB Netz AG"]
[]
[null,"Neumarkt (Oberpf) - Postbauer-Heng",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","periodical","2021-06-07T22:00:00","2021-06-10T05:00:00","21 h","DB Netz AG"]
[]
[null,"Osterhofen (Niederbay) - Girching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical","2021-06-12T20:30:00","2021-06-20T04:30:00","1 d","DB Netz AG"]
[]
[null,"Seubersdorf - Neumarkt (Oberpf)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Regensburg","continuous","2021-06-19","2021-07-04T23:50:00","16 d","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-06-26T23:30:00","2021-06-28T06:00:00","1 d, 07 h","DB Netz AG"]
[]
[null,"Girching - Vilshofen (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","periodical continuous","2021-07-02T23:30:00","2021-08-02T06:00:00","11 d, 09 h","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-07-29T23:00:00","2021-08-02T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Hbf - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-08-02T23:00:00","2021-08-06T23:00:00","4 d","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Ost",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Regensburg Ost - Regensburg Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-06T00:30:00","2021-11-11T00:30:00","5 d","DB Netz AG"]
[]
[null,"Sünching - Mangolding",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - Wels","continuous","2021-11-07T01:30:00","2021-11-11T00:30:00","3 d, 23 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-05T09:00:00","2021-03-07T12:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-03-12T09:00:00","2021-03-15T12:00:00","3 d, 03 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T01:00:00","2021-05-02T05:00:00","6 d, 04 h","DB Netz AG"]
[]
[null,"Köfering - Köfering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-04-26T04:00:00","2021-05-02T02:00:00","5 d, 22 h","DB Netz AG"]
[]
[null,"Köfering - Eggmühl",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-28T01:00:00","2021-05-29T13:00:00","1 d, 12 h","DB Netz AG"]
[]
[null,"Eggmühl - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-05-29T13:00:00","2021-05-31T05:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-04T23:00:00","2021-06-08T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-05T03:00:00","2021-06-05T17:00:00","14 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-10T23:00:00","2021-06-14T05:00:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-06-11T03:00:00","2021-06-11T17:00:00","14 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-16T14:00:00","2021-06-18T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-18T22:00:00","2021-06-21T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-23T14:00:00","2021-06-25T22:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-06-25T22:00:00","2021-06-28T06:00:00","2 d, 08 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Regensburg - München","continuous","2021-07-04T01:00:00","2021-07-04T11:00:00","10 h","DB Netz AG"]
[]
[null,"München Kanal - München Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","periodical","2021-07-24T22:50:00","2021-09-06T04:50:00","3 d, 12 h","DB Netz AG"]
[]
[null,"Köfering - Obertraubling",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-09-19T01:00:00","2021-10-03T05:00:00","14 d, 04 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T08:00:00","2021-10-23T05:00:00","11 d, 21 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-11T22:00:00","2021-10-23T05:00:00","11 d, 07 h","DB Netz AG"]
[]
[null,"Landshut (Bay) Hbf - Neufahrn (Niederbay)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-10-23T22:00:00","2021-11-01T04:00:00","8 d, 06 h","DB Netz AG"]
[]
[null,"Neufahrn (Niederbay) - Landshut (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Regensburg - München","continuous","2021-11-01T22:00:00","2021-11-07T05:00:00","5 d, 07 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-01T15:00:00","2021-04-05T14:00:00","3 d, 23 h","DB Netz AG"]
[]
[null,"München Nord Richtungsgruppe Süd - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-05T14:00:00","2021-04-06T09:00:00","19 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-10T12:00:00","2021-04-12T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-04-12T15:00:00","2021-04-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-04-17T12:00:00","2021-05-31T15:00:00","14 d, 21 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-04-19T15:00:00","2021-05-04T06:00:00","1 d, 21 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-05-10T15:00:00","2021-06-01T06:00:00","2 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-05T12:00:00","2021-06-14T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-07T15:00:00","2021-06-15T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-06-19T12:00:00","2021-06-28T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical","2021-06-21T15:00:00","2021-06-29T06:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-03T12:00:00","2021-07-05T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-05T15:00:00","2021-07-06T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-10T12:00:00","2021-07-19T15:00:00","4 d, 06 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-12T15:00:00","2021-07-13T06:00:00","15 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-19T15:00:00","2021-07-20T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-24T12:00:00","2021-07-26T15:00:00","2 d, 03 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-26T15:00:00","2021-07-27T06:00:00","15 h","DB Netz AG"]
[]
[null,"München Nord Rbf Lassallestraße - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-07-31T12:00:00","2021-08-09T15:00:00","2 d, 20 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München Nord Rbf Lassallestraße",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-07-31T12:00:00","2021-08-10T06:00:00","5 d, 12 h","DB Netz AG"]
[]
[null,"München-Milbertshofen - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-08-14T12:00:00","2021-09-13T15:00:00","7 d, 02 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Milbertshofen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","periodical continuous","2021-08-14T12:00:00","2021-09-14T06:00:00","13 d, 18 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-07","2021-10-11T22:00:00","4 d, 22 h","DB Netz AG"]
[]
[null,"München-Johanneskirchen - München-Freimann",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-11T22:00:00","2021-10-17T04:00:00","5 d, 06 h","DB Netz AG"]
[]
[null,"München-Freimann - München-Johanneskirchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Stuttgart - München","continuous","2021-10-30T00:30:00","2021-11-03T03:30:00","4 d, 03 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-01-25T22:30:00","2021-05-24T05:00:00","118 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T15:00:00","2021-04-03T20:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-02T22:30:00","2021-04-05T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-03T20:00:00","2021-04-04T10:00:00","14 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-04T10:00:00","2021-04-05T15:00:00","1 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:00:00","2021-04-10T04:00:00","6 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-09T22:30:00","2021-04-12T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-10T04:00:00","2021-04-11T10:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-11T10:00:00","2021-04-12T16:00:00","1 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-16T22:30:00","2021-04-19T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-04-17T05:00:00","2021-04-17T20:00:00","15 h","DB Netz AG"]
[]
[null,"Haßfurt - Haßfurt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-05-25T22:30:00","2021-08-13T05:00:00","79 d, 07 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-02T05:00:00","9 d, 11 h","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-23T18:00:00","2021-09-03T18:00:00","11 d","DB Netz AG"]
[]
[null,"Schweinfurt Hbf - Waigolshausen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:00:00","2021-09-02T05:00:00","6 d, 07 h","DB Netz AG"]
[]
[null,"Waigolshausen - Schweinfurt Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:30:00","2021-09-02T04:00:00","6 d, 05 h","DB Netz AG"]
[]
[null,"Waigolshausen - Seligenstadt (b Würzburg)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-26T22:45:00","2021-08-30T04:15:00","3 d, 06 h","DB Netz AG"]
[]
[null,"Zeil - Gädheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-08-27T22:30:00","2021-08-30T05:00:00","2 d, 07 h","DB Netz AG"]
[]
[null,"Wernfeld - Gemünden (Main)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-16T08:00:00","2021-02-23T16:00:00","1 d, 16 h","DB Netz AG"]
[]
[null,"Eußenheim - Wernfeld",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-24T08:00:00","2021-03-04T16:00:00","2 d","DB Netz AG"]
[]
[null,"Eußenheim - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-08T08:00:00","2021-03-09T16:00:00","16 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Eußenheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-10T08:00:00","2021-03-16T16:00:00","1 d, 08 h","DB Netz AG"]
[]
[null,"Thüngen (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-17T08:00:00","2021-03-18T16:00:00","16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Thüngen (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-03-22T08:00:00","2021-04-01T16:00:00","2 d, 16 h","DB Netz AG"]
[]
[null,"Arnstein (Unterfr) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-06T08:00:00","2021-04-08T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Arnstein (Unterfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-12T08:00:00","2021-04-14T16:00:00","1 d","DB Netz AG"]
[]
[null,"Mühlhausen (Wern) - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-15T08:00:00","2021-04-19T16:00:00","16 h","DB Netz AG"]
[]
[null,"Waigolshausen - Mühlhausen (Wern)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-04-20T08:00:00","2021-04-22T16:00:00","1 d","DB Netz AG"]
[]
[null,"Nürnberg Rbf Einfahrt - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-02-22T06:00:00","2021-12-11T23:59:00","292 d, 18 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-13T06:00:00","2021-03-14T04:00:00","22 h","DB Netz AG"]
[]
[null,"Nürnberg-Langwasser - Nürnberg Rbf Einfahrt",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-20T06:00:00","2021-03-21T04:00:00","22 h","DB Netz AG"]
[]
[null,"Bamberg - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-27T22:00:00","2021-03-01T05:00:00","14 h","DB Netz AG"]
[]
[null,"Hirschaid - Forchheim (Oberfr)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","periodical","2021-02-28T22:00:00","2021-03-01T05:00:00","7 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Vach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-22T23:00:00","2021-03-26T23:00:00","4 d","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T04:00:00","2021-03-29T04:00:00","3 d","DB Netz AG"]
[]
[null,"Vach - Fürth (Bay) Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-26T22:00:00","2021-03-29T04:00:00","2 d, 06 h","DB Netz AG"]
[]
[null,"Bad Staffelstein - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T21:00:00","2021-03-28T06:00:00","9 h","DB Netz AG"]
[]
[null,"Hirschaid - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-03-27T23:00:00","2021-04-01T04:00:00","4 d, 05 h","DB Netz AG"]
[]
[null,"Fürth (Bay) Hbf - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-04T04:00:00","7 h","DB Netz AG"]
[]
[null,"Forchheim (Oberfr) - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-14T04:00:00","10 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Strullendorf - Strullendorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-03T21:00:00","2021-09-21T04:00:00","17 d, 07 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Bamberg - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-09-14T07:00:00","2021-11-18T18:00:00","65 d, 11 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-10-05T22:00:00","2021-12-01T01:00:00","56 d, 03 h","DB Netz AG"]
[]
[null,"Breitengüßbach - Bamberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-01T01:00:00","2021-12-06T04:00:00","5 d, 03 h","DB Netz AG"]
[]
[null,"Bamberg - Unterleiterbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Gemünden - Bamberg - Nürnberg","continuous","2021-12-05T21:00:00","2021-12-06T04:00:00","7 h","DB Netz AG"]
[]
[null,"Bodenwöhr Nord - Bodenwöhr Nord",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Nürnberg - Plzen","continuous","2021-03-23T07:00:00","2021-05-10T07:00:00","48 d","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-05-10T07:00:00","2021-06-18T21:00:00","39 d, 14 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe-Dammerstock",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-07-02T23:00:00","2021-08-30T05:00:00","58 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-08-30T23:00:00","2021-11-08T05:00:00","69 d, 06 h","DB Netz AG"]
[]
[null,"Karlsruhe Gbf - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-08","2021-09-29T23:59:00","22 d","DB Netz AG"]
[]
[null,"Karlsruhe-Dammerstock - Karlsruhe Gbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Karlsruhe - Stuttgart","continuous","2021-09-25T06:00:00","2021-09-27T04:00:00","1 d, 22 h","DB Netz AG"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,"f","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","30.11.2020","10.07.2021","221 days + 22,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Linz - Wien","cont.","20.02.2021","22.02.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","08.03.2021","16.03.2021","8 days + 9,5 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.03.2021","15.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","12 days","ÖBB Infra"]
[]
[null,"Sbl Spw 2 - St.Valentin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","15.03.2021","26.03.2021","11 days + 12,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","19.03.2021","22.03.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","22.03.2021","03.04.2021","12 days + 8,5 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","26.03.2021","29.03.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","12.04.2021","16.04.2021","4 days","ÖBB Infra"]
[]
[null,"St.Valentin - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","12.04.2021","21.04.2021","9 days + 9,5 h","ÖBB Infra"]
[]
[null,"Linz Hbf Westbrücke - Untergaumberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","16.04.2021","03.05.2021","16 days + 6,5 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","21.05.2021","25.05.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","22.05.2021","24.05.2021","2 days + 4,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","04.06.2021","07.06.2021","2 days + 5,5 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Lambach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","09.07.2021","12.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Üst Ams 2 - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","7 days + 4,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","10.07.2021","17.07.2021","6 days + 5,0 h","ÖBB Infra"]
[]
[null,"Gunskirchen - Sbl Gun 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","16.07.2021","19.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Amstetten - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","17.07.2021","22.07.2021","5 days","ÖBB Infra"]
[]
[null,"Gunskirchen - Wels Hbf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","23.07.2021","26.07.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Ybbs a.d.Donau - Abzw Knoten Karlsbach",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","03.08.2021","23.08.2021","20 days","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Hörsching - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","20.08.2021","23.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Hörsching",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","27.08.2021","30.08.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"St.Peter-Seitenstetten - Abzw Knoten St.Peter-Seitenstetten West",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Linz - Wien","cont.","11.09.2021","20.09.2021","9 days + 4,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","17.09.2021","20.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Attnang-Puchheim - Sbl At 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.09.2021","27.09.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","01.10.2021","04.10.2021","2 days + 19,0 h","ÖBB Infra"]
[]
[null,"Sbl Mak 1P - Marchtrenk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","15.10.2021","18.10.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Wels Hbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wels - Linz","cont.","18.10.2021","22.10.2021","4 days + 10,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","23.10.2021","26.10.2021","3 days + 6,0 h","ÖBB Infra"]
[]
[null,"Salzburg Liefering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: München - Rosenheim - Salzburg ","cont.","30.10.2021","02.11.2021","3 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","30.10.2021","02.11.2021","2 days + 7,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wels - Linz","cont.","05.11.2021","08.11.2021","2 days + 6,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","06.11.2021","19.11.2021","13 days + 9,0 h","ÖBB Infra"]
[]
[null,"Seekirchen am Wallersee - Steindorf bei Straßwalchen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","20.11.2021","24.11.2021","4 days","ÖBB Infra"]
[]
[null,"Steindorf bei Straßwalchen - Seekirchen am Wallersee",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Salzburg - Wels","cont.","24.11.2021","29.11.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Meidling - W.Mat.-Oswaldgasse",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Linz - Wien","cont.","12.12.2021","16.04.2023","491 days","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","26.02.2021","01.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - Obertrattnach-M Hofk",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","05.03.2021","08.03.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.03.2021","15.03.2021","3 days + 16,0 h","ÖBB Infra"]
[]
[null,"Üst Neu 1 - Riedau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.03.2021","22.03.2021","3 days + 17,0 h","ÖBB Infra"]
[]
[null,"Andorf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.05.2021","15.05.2021","7 days + 10,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","08.10.2021","11.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Sbl Af 1 - Taufkirchen a d Pram",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","15.10.2021","18.10.2021","2 days + 5,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","12.11.2021","15.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Grieskirchen-Gallspach - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Regensburg - Wels","cont.","19.11.2021","22.11.2021","2 days + 9,0 h","ÖBB Infra"]
[]
[null,"Parndorf Ort - Zurndorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Parndorf - Hegyeshalom","cont.","12.04.2021","16.04.2021","4 days + 4,7 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","08.03.2021","12.03.2021","4 days + 7,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.03.2021","14.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x"]
[null,"Section: Wien - Parndorf","cont.","19.03.2021","21.03.2021","2 days + 11,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","03.04.2021","06.04.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - Abzww Zur",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","10.04.2021","11.04.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - Lanzendorf-Rannersdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","12.04.2021","18.04.2021","6 days + 10,0 h","ÖBB Infra"]
[]
[null,"Kledering - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","13.05.2021","16.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","22.05.2021","25.05.2021","3 days + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf-Einfgr - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x"]
[null,"Section: Wien - Parndorf","cont.","29.05.2021","30.05.2021","1 day + 10,0 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.06.2021","20.06.2021","13 days + 10,0 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","26.06.2021","20.08.2021","55 days + 9,0 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","05.07.2021","16.07.2021","10 days + 20,5 h","ÖBB Infra"]
[]
[null,"Götzendorf - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","16.07.2021","06.08.2021","21 days + 12,5 h","ÖBB Infra"]
[]
[null,"Abzww Str 11815 - Üst Goe 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","07.08.2021","16.09.2021","39 days + 20,5 h","ÖBB Infra"]
[]
[null,"Grillgasse - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","20.08.2021","05.09.2021","15 days + 23,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Wien - Parndorf","cont.","01.09.2021","31.12.2022","487 days","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","15.10.2021","18.10.2021","2 days + 5,2 h","ÖBB Infra"]
[]
[null,"Wien Zvbf - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","18.10.2021","31.10.2021","13 days + 11,0 h","ÖBB Infra"]
[]
[null,"Himberg - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Wien - Parndorf","cont.","23.10.2021","27.10.2021","3 days + 5,2 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","28.05.2021","02.06.2021","5 days + 15,0 h","ÖBB Infra"]
[]
[null,"Abzww Ebenfurth Nord - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Inzersdorf Ort-Ost - Oberlaa",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","22.03.2021","29.03.2021","6 days + 20,0 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","02.06.2021","07.06.2021","4 days + 6,5 h","ÖBB Infra"]
[]
[null,"Münchendorf - Ebreichsdorf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x"]
[null,"Section: Wien - Sopron","cont.","29.10.2021","03.11.2021","4 days + 7,5 h","ÖBB Infra"]
[]
[null,"Linz Oed - Linz Wegscheid",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-26","2021-08-01","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-07-19","2021-07-25","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-02","2021-08-08","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Linz Wegscheid - Linz Oed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-08-09","2021-08-15","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Marchtrenk - Rutzing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]
[]
[null,"Rutzing - ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x"]
[null,"Section: Wels - Traun - Linz","cont.","2021-10-23","2021-10-29","6 Tage + 10,0 h","ÖBB Infra"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":62,"n_cols":21,"rows_kept":62,"cut":false,"hidden":false,"merged":[[0,2,0,3],[0,0,0,1]]}
["IM",null,"Section",null,"Direction","Duration","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","International Coordination","In yearly timetable","Classification","Status","Automatic process"]
["GySEV",43,"Strasbourg - Karlsruhe",1,"< >","continuous","Signal","T","LT","S","W","D","C,,","R,,",",B,","O,,",43,"Y","Major","Planned","Y"]
["CFR",53,"Appenweier - Karlsruhe (div.)",2,">","periodical","Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,",53,"N","High","Coordination","N"]
["SŽCZ",54,"Karlsruhe - Bruchsal",3,"<","periodical continuous","Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",54,null,"Medium","Consultation"]
["MÁV",55,"Bruchsal - Mannheim",4,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",55,null,"Minor","Published"]
["ŽSR",56,"Karlsruhe - Mannheim",5,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",56,null,"Unclassified","Canceled"]
["DB Netz AG",80,"Mannheim - Darmstadt",6,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",80]
["ÖBB-Infra",81,"Mannheim - Gr. Gerau - Fr.",7,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",81]
["SNCF Reseau",87,"Darmstadt - Frankfurt",8,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,87]
[null,null,"Frankfurt - Aschaffenburg",9,null,null,"Others",null,null,null,null,null,null,null,null,null,54.81]
[null,null,"Darmstadt - Aschaffenburg",10,null,null,null,null,null,null,null,null,null,null,null,null,80.81]
[null,null,"Aschaffenburg - Gemünden",11,null,null,null,null,null,null,null,null,null,null,null,null,"54,80"]
[null,null,"Gemünden - Bamberg - Nürnberg",12,null,null,null,null,null,null,null,null,null,null,null,null,"55,56"]
[null,null,"Gemünden - Würzburg - Nürnberg",13,null,null,null,null,null,null,null,null,null,null,null,null,"54,81"]
[null,null,"Nürnberg - Regensburg",14,null,null,"Signal",null,null,null,null,null,null,null,null,null,"56,81"]
[null,null,"Regensburg - München",15,null,null,"Switch",null,null,null,null,null,null,null,null,null,"55,81"]
[null,null,"Regensburg - Wels",16,null,null,"Catenary",null,null,null,null,null,null,null,null,null,"43,55"]
[null,null,"Bruchsal - Mühlacker",17,null,null,"Track & Rail",null,null,null,null,null,null,null,null,null,"43,81"]
[null,null,"Karlsruhe - Stuttgart",18,null,null,"Tunnel"]
[null,null,"Stuttgart - München",19,null,null,"Bridge"]
[null,null,"München - Rosenheim - Salzburg ",20,null,null,"Miscellaneous*"]
[null,null,"München - Mühld. - Freilassing",21,null,null,"Maintenance"]
[null,null,"Nürnberg - Plzen",22,null,null,"Others**"]
[null,null,"Regensburg - Plzen",23]
[null,null,"Plzen - Praha",24]
[null,null,"Praha - Choceň",25]
[null,null,"Praha - Hr. Králové - Choceň",26]
[null,null,"Choceň - Hranice na Moravě",27]
[null,null,"Hranice na Moravě - Žilina",28]
[null,null,"Hranice na Moravě - Ostrava",29]
[null,null,"Ostrava - Český Těšín",30]
[null,null,"Ostr. - Dětmarovice - Č. Těšín",31]
[null,null,"Český Těšín - Žilina",32]
[null,null,"Žilina - Košice",33]
[null,null,"Košice - Čierna nad Tisou",34]
[null,null,"Čierna nad Tisou - Chop",35]
[null,null,"Košice - Haniska pri Košiciach",36]
[null,null,"Haniska pri Košic. - Maťovce",37]
[null,null,"Salzburg - Wels",38]
[null,null,"Wels - Linz",39]
[null,null,"Wels - Traun - Linz",40]
[null,null,"Linz - Wien",41]
[null,null,"Wien - Parndorf",42]
[null,null,"Parndorf - Bratislava",43]
[null,null,"Parndorf - Hegyeshalom",44]
[null,null,"Wien - Sopron",45]
[null,null,"Sopron - Győr",46]
[null,null,"Bratislava - Hegyeshalom",47]
[null,null,"Hegyeshalom - Györ",48]
[null,null,"Györ - Budapest",49]
[null,null,"Budapest - Újszász - Szolnok",50]
[null,null,"Budapest - Cegléd - Szolnok",51]
[null,null,"Szolnok - Arad",52]
[null,null,"Szolnok - Cluj",53]
[null,null,"Cluj - Coșlariu",54]
[null,null,"Arad - Brașov",55]
[null,null,"Brașov - Bucuresti",56]
[null,null,"Arad - Craiova",57]
[null,null,"Craiova - Bucuresti",58]
[null,null,"Bucuresti - Constanţa",59]
[null,null,"Ploiești triaj - Fetești",60]
[null,null,"Simeria - Filiasi",61]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}