{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2027,52]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":12477,"n_cols":37,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,34,2,34],[1,30,2,30],[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Weekdays","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"DB InfraGO","2FA1-020","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf Bft Südeinfahrt","Kar Hbf DB/Stadt",2024,2024,44,45,"2024-10-31","22:00:00","2024-11-04","04:00:00","3d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-02-07",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO","2FDD-010","Karlsruhe - Strasbourg","< >","Baden-Baden","Sandweier",2024,2024,32,37,"2024-08-11","22:00:00","2024-09-09","05:00:00","28d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FDD-011","Karlsruhe - Strasbourg","< >","Baden-Baden","Sandweier",2024,2024,32,37,"2024-08-11","22:00:00","2024-09-09","05:00:00","28d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FDD-012","Karlsruhe - Strasbourg","< >","Sandweier","Baden-Baden",2024,2024,37,37,"2024-09-09","05:00:00","2024-09-10","05:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2023-12-14",null,null,"1,2",1]
[null,"DB InfraGO","2FDD-013","Karlsruhe - Strasbourg","< >","Sandweier","Baden-Baden",2024,2024,37,37,"2024-09-10","05:00:00","2024-09-13","05:00:00","3d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-14",null,null,"2,3,4,5",1]
[null,"DB InfraGO","2FDD-014","Karlsruhe - Strasbourg","< >","Sandweier","Baden-Baden",2024,2024,37,40,"2024-09-13","05:00:00","2024-09-30","05:00:00","17d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FDD-015","Karlsruhe - Strasbourg","< >","Sandweier","Baden-Baden",2024,2024,48,49,"2024-11-30","23:00:00","2024-12-02","23:00:00","2d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-02-24",null,null,"1,6,7",1]
[null,"DB InfraGO","2FE8-027","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Sandweier",2024,2024,37,38,"2024-09-14","23:00:00","2024-09-20","04:00:00","5d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO","2FE8-029","Karlsruhe - Strasbourg",">","Rastatt-Süd","Baden-Baden",2024,2024,37,38,"2024-09-14","23:00:00","2024-09-20","04:00:00","5d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO","2FE8-031","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,39,40,"2024-09-25","23:00:00","2024-10-04","05:00:00","8d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"6,7",1]
[null,"DB InfraGO","2FE8-036","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,35,37,"2024-08-30","21:00:00","2024-09-09","05:00:00","9d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FE8-038","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Sandweier",2024,2024,41,42,"2024-10-10","23:00:00","2024-10-16","04:00:00","5d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"1,2,4,5,6,7",1]
[null,"DB InfraGO","2FE8-040","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,35,37,"2024-08-30","21:00:00","2024-09-09","05:00:00","9d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FE8-042","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,41,42,"2024-10-10","23:00:00","2024-10-16","04:00:00","5d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"1,2,4,5,6,7",1]
[null,"DB InfraGO","2FE8-046","Karlsruhe - Strasbourg",">","Rastatt-Süd","Baden-Baden",2024,2024,43,43,"2024-10-22","23:00:00","2024-10-25","04:00:00","2d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"2,3,4",1]
[null,"DB InfraGO","2FE8-048","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Sandweier",2024,2024,43,43,"2024-10-22","23:00:00","2024-10-25","04:00:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"2,3,4",1]
[null,"DB InfraGO","2FE8-050","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,48,49,"2024-11-30","21:00:00","2024-12-02","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"6,7",1]
[null,"DB InfraGO","2FE8-052","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,48,49,"2024-11-30","21:00:00","2024-12-02","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"6,7",1]
[null,"DB InfraGO","2FE8-076","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Sandweier",2024,2024,39,40,"2024-09-25","23:00:00","2024-10-04","05:00:00","8d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"6,7",1]
[null,"DB InfraGO","3119-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Appenweier Nord",2024,2024,48,49,"2024-11-29","22:30:00","2024-12-06","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2023-05-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-001","Karlsruhe - Strasbourg","<","Bühl (Baden) F","Rastatt-Süd",2023,2024,50,44,"2023-12-12","23:00:00","2024-10-31","05:00:00","323d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2023-10-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-002","Karlsruhe - Strasbourg",">","Rastatt-Süd","Bühl (Baden) F",2023,2024,50,44,"2023-12-12","23:00:00","2024-10-31","05:00:00","323d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2023-10-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-020","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,32,37,"2024-08-09","23:30:00","2024-09-09","05:00:00","30d, 5h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-028","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Ottersweier",2024,2024,32,37,"2024-08-11","22:00:00","2024-09-09","05:00:00","28d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-033","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,48,50,"2024-12-01","22:00:00","2024-12-12","05:00:00","10d, 7h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-09",null,null,"6,7",1]
[null,"DB InfraGO","314B-035","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,48,50,"2024-12-01","22:00:00","2024-12-12","05:00:00","10d, 7h","Periodical","Signal","T",null,null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-06",null,null,"4,5",1]
[null,"DB InfraGO","5B0B-016","Karlsruhe - Strasbourg","< >","Sandweier","Rastatt-Süd",2024,2024,36,36,"2024-09-06","21:00:00","2024-09-07","21:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-30",null,null,"5,6",1]
[null,"DB InfraGO","5B0B-017","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,36,36,"2024-09-06","21:00:00","2024-09-07","21:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-30",null,null,"5,6",1]
[null,"DB InfraGO","5B0B-019","Karlsruhe - Strasbourg","< >","Baden-Baden","Rastatt-Süd",2024,2024,36,50,"2024-09-07","21:00:00","2024-12-14","23:59:00","98d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-10-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","5B0B-020","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,36,50,"2024-09-07","21:00:00","2024-12-14","23:59:00","98d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","5F22-002","Karlsruhe - Strasbourg",">","Rastatt-Süd","Sandweier",2024,2024,40,40,"2024-10-02","22:45:00","2024-10-03","03:45:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2023-07-20",null,null,"3,4",1]
[null,"DB InfraGO","190DC-002","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2023,2024,49,50,"2023-12-10","00:00:00","2024-12-14","23:59:00","370d, 23h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2023-09-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2FE8-082","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2024,2024,36,37,"2024-09-08","04:30:00","2024-09-09","04:30:00","1d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,7",1]
[null,"DB InfraGO","314B-056","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2024,2024,1,50,"2024-01-01","00:00:00","2024-12-14","23:59:00","348d, 23h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2023-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","314B-057","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2024,2024,1,50,"2024-01-01","00:00:00","2024-12-14","23:59:00","348d, 23h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2023-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","24556-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24556-003","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24556-006","Karlsruhe - Strasbourg","< >","Ottersweier","Rastatt-Süd",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","2469F-001","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,37,37,"2024-09-13","21:00:00","2024-09-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","2469F-003","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,37,37,"2024-09-13","21:00:00","2024-09-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","2469F-004","Karlsruhe - Strasbourg","< >","Appenweier Nord","Ottersweier",2024,2024,37,37,"2024-09-13","21:00:00","2024-09-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","246D0-003","Karlsruhe - Strasbourg",">","Appenweier Nord","Offenburg",2024,2024,37,37,"2024-09-14","21:00:00","2024-09-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","246D0-005","Karlsruhe - Strasbourg","< >","Offenburg","Appenweier Nord",2024,2024,37,37,"2024-09-14","21:00:00","2024-09-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","24798-007","Karlsruhe - Strasbourg","< >","Appenweier","Appenweier",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO","24F74-001","Karlsruhe - Strasbourg","<","Önsbach","Baden-Baden",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-12",null,null,"2,3",1]
[null,"DB InfraGO","24F74-002","Karlsruhe - Strasbourg","<","Önsbach","Ottersweier",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-12",null,null,"2,3",1]
[null,"DB InfraGO","24F74-004","Karlsruhe - Strasbourg","< >","Ottersweier","Önsbach",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-02-12",null,null,"2,3",1]
[null,"DB InfraGO","250B5-001","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-12",null,null,"3,4",1]
[null,"DB InfraGO","250B5-002","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-12",null,null,"3,4",1]
[null,"DB InfraGO","250B5-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-02-12",null,null,"3,4",1]
[null,"DB InfraGO","25A7C-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","25A7C-003","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","25A7C-006","Karlsruhe - Strasbourg","< >","Ottersweier","Rastatt-Süd",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","26181-002","Karlsruhe - Strasbourg",">","Sandweier","Ottersweier",2024,2024,41,41,"2024-10-07","23:35:00","2024-10-08","04:10:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-21",null,null,"1,2",1]
[null,"DB InfraGO","26181-005","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2024,2024,41,41,"2024-10-07","23:35:00","2024-10-08","05:25:00","0d, 5h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-21",null,null,"1,2",1]
[null,"DB InfraGO","26181-006","Karlsruhe - Strasbourg","<","Ottersweier","Sandweier",2024,2024,41,41,"2024-10-08","04:15:00","2024-10-08","05:20:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-21",null,null,2,1]
[null,"DB InfraGO","26181-008","Karlsruhe - Strasbourg",">","Sandweier","Ottersweier",2024,2024,41,41,"2024-10-08","23:35:00","2024-10-09","00:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","26181-011","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2024,2024,41,41,"2024-10-08","23:35:00","2024-10-09","06:05:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","26181-012","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2024,2024,41,41,"2024-10-09","00:40:00","2024-10-09","03:45:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,3,1]
[null,"DB InfraGO","26181-014","Karlsruhe - Strasbourg","<","Ottersweier","Sandweier",2024,2024,41,41,"2024-10-09","03:50:00","2024-10-09","06:10:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-21",null,null,3,1]
[null,"DB InfraGO","26181-017","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2024,2024,41,41,"2024-10-10","00:00:00","2024-10-10","03:00:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-21",null,null,4,1]
[null,"DB InfraGO","265F6-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265F6-003","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265F6-006","Karlsruhe - Strasbourg","< >","Ottersweier","Rastatt-Süd",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265F7-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-04-26",null,null,"4,5",1]
[null,"DB InfraGO","265F7-003","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"4,5",1]
[null,"DB InfraGO","265F7-006","Karlsruhe - Strasbourg","< >","Ottersweier","Rastatt-Süd",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-04-26",null,null,"4,5",1]
[null,"DB InfraGO","266C7-001","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,45,45,"2024-11-08","21:00:00","2024-11-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","266C7-003","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,45,45,"2024-11-08","21:00:00","2024-11-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","266C7-004","Karlsruhe - Strasbourg","< >","Appenweier Nord","Ottersweier",2024,2024,45,45,"2024-11-08","21:00:00","2024-11-09","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","266C8-001","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,49,49,"2024-12-06","21:00:00","2024-12-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","266C8-003","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,49,49,"2024-12-06","21:00:00","2024-12-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","266C8-004","Karlsruhe - Strasbourg","< >","Appenweier Nord","Ottersweier",2024,2024,49,49,"2024-12-06","21:00:00","2024-12-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","2679A-003","Karlsruhe - Strasbourg",">","Appenweier Nord","Offenburg",2024,2024,45,45,"2024-11-09","21:00:00","2024-11-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","2679A-005","Karlsruhe - Strasbourg","< >","Offenburg","Appenweier Nord",2024,2024,45,45,"2024-11-09","21:00:00","2024-11-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","2679B-003","Karlsruhe - Strasbourg",">","Appenweier Nord","Offenburg",2024,2024,49,49,"2024-12-07","21:00:00","2024-12-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"6,7",1]
[null,"DB InfraGO","2679B-005","Karlsruhe - Strasbourg","< >","Offenburg","Appenweier Nord",2024,2024,49,49,"2024-12-07","21:00:00","2024-12-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-28",null,null,"6,7",1]
[null,"DB InfraGO","26898-003","Karlsruhe - Strasbourg","< >","Sandweier","Rastatt",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-08",null,null,"1,2",1]
[null,"DB InfraGO","26899-003","Karlsruhe - Strasbourg","< >","Sandweier","Rastatt",2024,2024,50,50,"2024-12-09","21:00:00","2024-12-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-06",null,null,"1,2",1]
[null,"DB InfraGO","26B80-007","Karlsruhe - Strasbourg","< >","Appenweier","Appenweier",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","26B81-007","Karlsruhe - Strasbourg","< >","Appenweier","Appenweier",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,",null,null,null,"N",null,"2024-04-12",null,null,"4,5",1]
[null,"DB InfraGO","26F70-001","Karlsruhe - Strasbourg","<","Önsbach","Baden-Baden",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","26F70-002","Karlsruhe - Strasbourg","<","Önsbach","Ottersweier",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","26F70-004","Karlsruhe - Strasbourg","< >","Ottersweier","Önsbach",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","27059-001","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,47,47,"2024-11-20","21:00:00","2024-11-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","27059-002","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,47,47,"2024-11-20","21:00:00","2024-11-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","27059-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2024,2024,47,47,"2024-11-20","21:00:00","2024-11-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","27842-001","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,41,41,"2024-10-11","21:00:00","2024-10-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-23",null,null,"5,6",1]
[null,"DB InfraGO","27842-003","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier Nord",2024,2024,41,41,"2024-10-11","21:00:00","2024-10-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"5,6",1]
[null,"DB InfraGO","27842-004","Karlsruhe - Strasbourg","< >","Appenweier Nord","Ottersweier",2024,2024,41,41,"2024-10-11","21:00:00","2024-10-12","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-02-23",null,null,"5,6",1]
[null,"DB InfraGO","2788C-003","Karlsruhe - Strasbourg",">","Appenweier Nord","Offenburg",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"6,7",1]
[null,"DB InfraGO","2788C-005","Karlsruhe - Strasbourg","< >","Offenburg","Appenweier Nord",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-02-23",null,null,"6,7",1]
[null,"DB InfraGO","2793D-003","Karlsruhe - Strasbourg","< >","Sandweier","Rastatt",2024,2024,42,42,"2024-10-14","21:00:00","2024-10-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-04",null,null,"1,2",1]
[null,"DB InfraGO","27A4F-007","Karlsruhe - Strasbourg","< >","Appenweier","Appenweier",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","28273-001","Karlsruhe - Strasbourg","<","Önsbach","Baden-Baden",2024,2024,43,43,"2024-10-22","21:00:00","2024-10-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-11",null,null,"2,3",1]
[null,"DB InfraGO","28273-002","Karlsruhe - Strasbourg","<","Önsbach","Ottersweier",2024,2024,43,43,"2024-10-22","21:00:00","2024-10-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-11",null,null,"2,3",1]
[null,"DB InfraGO","28273-004","Karlsruhe - Strasbourg","< >","Ottersweier","Önsbach",2024,2024,43,43,"2024-10-22","21:00:00","2024-10-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-03-11",null,null,"2,3",1]
[null,"DB InfraGO","28A1D-001","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-03-11",null,null,"3,4",1]
[null,"DB InfraGO","28A1D-002","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-11",null,null,"3,4",1]
[null,"DB InfraGO","28A1D-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-03-11",null,null,"3,4",1]
[null,"DB InfraGO","28A33-003","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2024,2024,42,42,"2024-10-19","23:00:00","2024-10-20","02:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","28A33-004","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2024,2024,42,42,"2024-10-19","23:00:00","2024-10-20","02:00:00","0d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","28A33-005","Karlsruhe - Strasbourg",">","Baden-Baden","Ottersweier",2024,2024,42,42,"2024-10-20","02:00:00","2024-10-20","05:20:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-29",null,null,7,1]
[null,"DB InfraGO","28A33-008","Karlsruhe - Strasbourg","< >","Ottersweier","Baden-Baden",2024,2024,42,42,"2024-10-20","02:00:00","2024-10-20","05:20:00","0d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-29",null,null,7,1]
[null,"DB InfraGO","2A292-001","Karlsruhe - Strasbourg","<","Offenburg","Appenweier Nord",2024,2024,47,47,"2024-11-18","23:00:00","2024-11-19","05:00:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"SNCF-R",8124498,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Krimmen-Meinau/00",2024,2024,37,46,"2024-09-09","22:40:00","2024-11-15","04:30:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124499,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,39,39,"2024-09-23","22:40:00","2024-09-28","04:40:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124500,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,41,41,"2024-10-07","22:40:00","2024-10-09","04:40:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124503,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,50,51,"2024-12-13","10:55:00","2024-12-19","12:03:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124506,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,34,50,"2024-08-19","11:00:00","2024-12-13","12:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124507,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,39,39,"2024-09-24","00:15:00","2024-09-28","06:05:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124508,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/J1","Strasbourg-Port du-Rhin/XD",2024,2024,41,41,"2024-10-08","00:15:00","2024-10-09","06:05:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"SNCF-R",8124509,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville/BV","Strasbourg-Neudorf/JO",2025,2025,35,40,"2025-08-31","00:00:00","2025-10-04","23:59:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"264.8 Corridors européens ETCS niveau1, Corridor 2 - Axe Longuyon - Bettembourg Bâle. PHASE 1 à 5",null,null,null,"2022-11-22"]
[null,"SNCF-R",8124510,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2024,2025,51,50,"2024-12-16","11:20:00","2025-12-12","12:28:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main courante n°15 SA2023)  SA2024 Main Courante 18 : vibration de + 10 minutes des horaires  SA2025 - Main courante 105 : vibration de -10 minutes des horaires",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124511,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2024,2025,51,50,"2024-12-16","11:02:00","2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124512,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2025,2025,13,14,"2025-03-25","00:15:00","2025-04-05","06:05:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Création de fenêtres génériques de 6h avec simultanée de 4h pour passage trains internationaux Pk début 2,500                         ",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124513,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2025,2025,13,14,"2025-03-24","22:40:00","2025-04-05","04:40:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Recommandation de non activation entre avril et octobre Modification de fenêtre : 6h dont 4 de simultanée pour passage trains internationaux      ",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124514,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2025,2026,51,50,"2025-12-15","09:54:00","2026-12-11","11:02:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main courante n°15 SA2023)  SA2024 Main Courante 18 : vibration de + 10 minutes des horaires  SA2026 : Modification des horaires suite à Concertation sur le Système Capacitaire (14/11/2023 XSE",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124515,"Karlsruhe - Strasbourg","< >","Accès à Faisceau Strasbourg-Ville V22 à V24","Strasbourg/Kehl border",2025,2026,51,50,"2025-12-15","11:02:00","2026-12-11","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,null,null,"2024-01-10"]
[null,"SNCF-R",8124516,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2024,2025,51,50,"2024-12-16","10:56:00","2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main courante n°15 SA2023)  SA2024 Main Courante 18 : vibration de + 10 minutes des horaires  SA2025 - Main courante 105 : vibration de -10 minutes des horaires // SA2025 - Main courante 172 :",null,"Y",null,"2024-06-11",null,null,"1,2,3,4,5"]
[null,"SNCF-R",8124517,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2024,2025,51,50,"2024-12-16","11:02:00","2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,"Y",null,"2024-06-11",null,null,"1,2,3,4,5"]
[null,"SNCF-R",8124518,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2025,2025,13,14,"2025-03-24","22:40:00","2025-04-05","04:40:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Recommandation de non activation entre avril et octobre Modification de fenêtre : 6h dont 4 de simultanée pour passage trains internationaux      ",null,"Y",null,"2024-06-11",null,null,"1,2,3,4,6"]
[null,"SNCF-R",8124519,"Karlsruhe - Strasbourg","< >","Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2025,2025,13,14,"2025-03-25","00:15:00","2025-04-05","06:05:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Création de fenêtres génériques de 6h avec simultanée de 4h pour passage trains internationaux Pk début 2,500                         ",null,"Y",null,"2024-06-11",null,null,"2,3,4,5,7"]
[null,"DB InfraGO","2BB9-003","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,32,36,"2024-08-11","21:00:00","2024-09-02","21:00:00","22d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2CAF-002","München - Salzburg","< >","München-Daglfing","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"1,6,7",1]
[null,"DB InfraGO","692F-002","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,46,46,"2024-11-13","22:40:00","2024-11-14","04:40:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,"3,4",1]
[null,"DB InfraGO","692F-004","München - Salzburg",">","München-Trudering","München-Waldtrudering",2024,2024,46,46,"2024-11-14","07:00:00","2024-11-14","11:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,4,1]
[null,"DB InfraGO","692F-005","München - Salzburg","< >","München-Daglfing","München-Trudering",2024,2024,46,46,"2024-11-14","07:00:00","2024-11-14","11:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-18",null,null,4,1]
[null,"DB InfraGO","692F-007","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,46,46,"2024-11-14","11:00:00","2024-11-14","13:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,4,1]
[null,"DB InfraGO","692F-012","München - Salzburg",">","München-Trudering","München-Waldtrudering",2024,2024,46,47,"2024-11-17","23:00:00","2024-11-18","03:00:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,"1,7",1]
[null,"DB InfraGO","692F-013","München - Salzburg","< >","München-Daglfing","München-Trudering",2024,2024,46,47,"2024-11-17","23:00:00","2024-11-18","03:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-18",null,null,"1,7",1]
[null,"DB InfraGO","692F-017","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-18","23:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,1,1]
[null,"DB InfraGO","692F-019","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,47,47,"2024-11-18","22:40:00","2024-11-19","04:40:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-07-18",null,null,"1,2",1]
[null,"DB InfraGO","B5AB-002","München - Salzburg",">","München-Trudering","Haar",2024,2024,50,50,"2024-12-13","23:00:00","2024-12-14","00:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO","B5AB-004","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,50,50,"2024-12-14","01:00:00","2024-12-14","02:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","B5AB-005","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,50,50,"2024-12-14","03:20:00","2024-12-14","04:20:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","2BDE-045","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,43,43,"2024-10-25","00:00:00","2024-10-25","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-08-30",null,null,5,1]
[null,"DB InfraGO","2BDE-046","München - Salzburg",">","München-Trudering","München-Waldtrudering",2024,2024,43,43,"2024-10-26","00:00:00","2024-10-27","05:00:00","1d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-08-30",null,null,"6,7",1]
[null,"DB InfraGO","2BDE-047","München - Salzburg",">","München-Trudering","München-Waldtrudering",2024,2024,43,45,"2024-10-27","23:00:00","2024-11-04","04:00:00","7d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2BDE-048","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,45,45,"2024-11-04","23:00:00","2024-11-05","04:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-08-30",null,null,"1,2",1]
[null,"DB InfraGO","2291B-001","München - Salzburg","<","München Nord Rbf Forstweg","Mering Üst",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","2291B-002","München - Salzburg","<","München Nord Rbf Forstweg","Olching",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","22C61-003","München - Salzburg",">","km 3,6/6,8 (MOL)","Mering Üst",2024,2024,37,37,"2024-09-09","21:10:00","2024-09-10","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO","23096-003","München - Salzburg",">","München Nord Rbf Forstweg","Augsburg-Hochzoll Abzweig",2024,2024,37,37,"2024-09-10","21:15:00","2024-09-11","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-01-30",null,null,"2,3",1]
[null,"DB InfraGO","236EF-004","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,36,36,"2024-09-07","21:10:00","2024-09-08","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-13",null,null,"6,7",1]
[null,"DB InfraGO","23FEA-001","München - Salzburg","<","München Nord Rbf Forstweg","Mering Üst",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-02-19",null,null,"1,2",1]
[null,"DB InfraGO","23FEA-002","München - Salzburg","<","München Nord Rbf Forstweg","Olching",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-02-19",null,null,"1,2",1]
[null,"DB InfraGO","2423A-004","München - Salzburg","<","München-Trudering","München-Waldtrudering",2024,2024,38,38,"2024-09-16","21:10:00","2024-09-17","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","24482-003","München - Salzburg",">","München Nord Rbf Forstweg","Augsburg-Hochzoll Abzweig",2024,2024,41,41,"2024-10-08","21:15:00","2024-10-09","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-02-23",null,null,"2,3",1]
[null,"DB InfraGO","25697-004","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,40,40,"2024-10-05","21:15:00","2024-10-06","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-02-17",null,null,"6,7",1]
[null,"DB InfraGO","25C9D-001","München - Salzburg","<","München Nord Rbf Forstweg","Mering Üst",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","25C9D-002","München - Salzburg","<","München Nord Rbf Forstweg","Olching",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","25E13-002","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,44,44,"2024-11-02","21:15:00","2024-11-03","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","2638F-003","München - Salzburg",">","km 3,6/6,8 (MOL)","Mering Üst",2024,2024,45,45,"2024-11-04","21:10:00","2024-11-05","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","26390-003","München - Salzburg",">","km 3,6/6,8 (MOL)","Mering Üst",2024,2024,49,49,"2024-12-02","21:10:00","2024-12-03","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","2648F-003","München - Salzburg",">","München Nord Rbf Forstweg","Augsburg-Hochzoll Abzweig",2024,2024,45,45,"2024-11-05","21:15:00","2024-11-06","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","26490-003","München - Salzburg",">","München Nord Rbf Forstweg","Augsburg-Hochzoll Abzweig",2024,2024,49,49,"2024-12-03","21:15:00","2024-12-04","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","2692D-002","München - Salzburg","<","München-Trudering","München-Waldtrudering",2024,2024,46,46,"2024-11-11","21:15:00","2024-11-12","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-03-24",null,null,"1,2",1]
[null,"DB InfraGO",26.92,"München - Salzburg","<","München-Trudering","München-Waldtrudering",2024,2024,50,50,"2024-12-09","21:10:00","2024-12-10","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-03-24",null,null,"1,2",1]
[null,"DB InfraGO","2746F-001","München - Salzburg","<","München Nord Rbf Forstweg","Mering Üst",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","2746F-002","München - Salzburg","<","München Nord Rbf Forstweg","Olching",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","27728-002","München - Salzburg","<","München-Waldtrudering","München-Trudering",2024,2024,48,48,"2024-11-30","21:15:00","2024-12-01","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-03-24",null,null,"6,7",1]
[null,"DB InfraGO","27848-001","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,6,7",1]
[null,"DB InfraGO","27848-003","München - Salzburg","< >","München-Daglfing","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,6,7",1]
[null,"DB InfraGO","27848-006","München - Salzburg","< >","München-Daglfing","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,6,7",1]
[null,"DB InfraGO","27992-003","München - Salzburg","< >","München-Trudering","München-Waldtrudering",2024,2024,28,38,"2024-07-08","06:20:00","2024-09-16","11:20:00","70d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-20",null,null,1,1]
[null,"DB InfraGO","2B2C0-013","München - Salzburg","< >","München-Trudering","München-Waldtrudering",2024,2024,44,44,"2024-11-02","21:15:00","2024-11-03","05:15:00","0d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-05-15",null,null,6,1]
[null,"DB InfraGO","2CAF-014","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"1,6,7",1]
[null,"DB InfraGO","2CAF-015","München - Salzburg","<","München-Trudering","München-Waldtrudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-08-30",null,null,"1,6,7",1]
[null,"DB InfraGO","27B47-002","Darmstadt - Aschaffenburg","< >","Aburg-Goldbach","Aschaffenburg Hbf",2024,2024,44,44,"2024-11-03","00:05:00","2024-11-03","06:05:00","0d, 6h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,7,1]
[null,"DB InfraGO","27B47-005","Darmstadt - Aschaffenburg","< >","Aburg-Goldbach","Aschaffenburg Hbf",2024,2024,44,44,"2024-11-03","00:05:00","2024-11-03","06:05:00","0d, 6h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,7,1]
[null,"DB InfraGO","2BB9-038","München - Salzburg","< >","München-Trudering","Haar",2024,2024,34,36,"2024-08-24","00:45:00","2024-09-02","04:45:00","9d, 4h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2BB9-039","München - Salzburg","< >","München-Trudering","Haar",2024,2024,34,36,"2024-08-24","00:45:00","2024-09-02","04:45:00","9d, 4h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2BB9-042","München - Salzburg","<","München-Trudering","München-Berg am Laim Abzw",2024,2024,35,35,"2024-08-31","00:45:00","2024-09-01","04:45:00","1d, 4h","Periodical",null,null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","2BB9-048","München - Salzburg","< >","Haar","München-Trudering",2024,2024,36,36,"2024-09-02","04:45:00","2024-09-04","04:45:00","2d, 0h","Continuous",null,null,null,"S",null,null,",,",",,",null,",,2",null,null,null,"N",null,null,null,null,"1,2,3",1]
[null,"DB InfraGO","2BB9-049","München - Salzburg","< >","Haar","Haar",2024,2024,36,36,"2024-09-02","00:45:00","2024-09-02","04:45:00","0d, 4h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO","2BB9-050","München - Salzburg","<","Zorneding","Haar",2024,2024,36,36,"2024-09-02","00:45:00","2024-09-02","04:45:00","0d, 4h","Continuous",null,null,"LT",null,null,null,",,",",,",null,",,10",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO","2BB9-051","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,36,36,"2024-09-02","02:45:00","2024-09-02","04:45:00","0d, 2h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO","2BB9-052","München - Salzburg","<","München-Trudering","München-Berg am Laim Abzw",2024,2024,36,36,"2024-09-02","02:45:00","2024-09-02","04:45:00","0d, 2h","Continuous",null,null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO","2BB9-061","München - Salzburg","<","Haar","München-Trudering",2024,2024,34,36,"2024-08-23","23:00:00","2024-09-02","04:45:00","9d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2BB9-062","München - Salzburg","< >","Haar","München-Trudering",2024,2024,34,36,"2024-08-24","03:00:00","2024-09-02","00:45:00","8d, 21h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2CAF-003","München - Salzburg","<","Haar","München-Berg am Laim Abzw",2024,2024,44,44,"2024-11-01","02:45:00","2024-11-02","04:45:00","1d, 2h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-08-30",null,null,"5,6",1]
[null,"DB InfraGO","2CAF-004","München - Salzburg","<","Haar","München-Berg am Laim Abzw",2024,2024,45,45,"2024-11-05","02:45:00","2024-11-06","04:45:00","1d, 2h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-08-30",null,null,"2,3",1]
[null,"DB InfraGO","2BB9-065","München - Salzburg",">","München-Trudering","Haar",2024,2024,36,36,"2024-09-03","01:00:00","2024-09-06","04:45:00","3d, 3h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-08-30",null,null,"2,3,4,5",1]
[null,"DB InfraGO","2BB9-078","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,35,35,"2024-08-31","00:45:00","2024-09-01","04:45:00","1d, 4h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","692F-003","München - Salzburg",">","München-Trudering","Haar",2024,2024,46,46,"2024-11-13","22:40:00","2024-11-14","04:40:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-07-18",null,null,"3,4",1]
[null,"DB InfraGO","692F-009","München - Salzburg","<","Haar","München-Berg am Laim Abzw",2024,2024,46,46,"2024-11-15","22:00:00","2024-11-15","23:59:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-07-18",null,null,5,1]
[null,"DB InfraGO","692F-011","München - Salzburg","<","Haar","München-Trudering",2024,2024,46,47,"2024-11-16","00:00:00","2024-11-18","05:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-07-18",null,null,"1,6,7",1]
[null,"DB InfraGO","692F-015","München - Salzburg","<","Haar","München-Berg am Laim Abzw",2024,2024,47,47,"2024-11-18","03:00:00","2024-11-18","05:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-07-18",null,null,1,1]
[null,"DB InfraGO","692F-018","München - Salzburg",">","München-Trudering","Haar",2024,2024,47,47,"2024-11-18","22:40:00","2024-11-19","04:40:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-07-18",null,null,"1,2",1]
[null,"DB InfraGO","22ED8-019","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,37,37,"2024-09-12","21:40:00","2024-09-13","04:20:00","0d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,4,1]
[null,"DB InfraGO","22ED8-020","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,37,37,"2024-09-12","21:40:00","2024-09-13","04:20:00","0d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,4,1]
[null,"DB InfraGO","264E2-008","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,46,46,"2024-11-11","21:40:00","2024-11-15","04:20:00","3d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","264E2-020","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,46,46,"2024-11-11","21:40:00","2024-11-15","04:20:00","3d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","264E2-038","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,45,45,"2024-11-09","04:00:00","2024-11-10","15:40:00","1d, 11h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","264E2-041","München - Salzburg","< >","München-Trudering","München-Berg am Laim Abzw",2024,2024,45,45,"2024-11-09","04:00:00","2024-11-10","15:40:00","1d, 11h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","264E2-042","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,45,45,"2024-11-09","04:00:00","2024-11-10","15:40:00","1d, 11h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","277F2-006","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,45,45,"2024-11-04","21:40:00","2024-11-08","04:20:00","3d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","277F2-015","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2024,2024,45,45,"2024-11-04","21:40:00","2024-11-08","04:20:00","3d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","28B37-002","München - Salzburg","<","Zorneding","München-Trudering",2024,2024,45,45,"2024-11-05","22:30:00","2024-11-06","04:30:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,15",null,null,null,"N",null,"2024-04-04",null,null,"2,3",1]
[null,"DB InfraGO","28B4B-003","München - Salzburg",">","München-Berg am Laim Abzw","Zorneding",2024,2024,45,45,"2024-11-04","22:30:00","2024-11-05","04:30:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,12",null,null,null,"N",null,"2024-01-11",null,null,"1,2",1]
[null,"DB InfraGO","28B6E-004","München - Salzburg",">","Zorneding","Grafing Bahnhof",2024,2024,45,45,"2024-11-06","22:00:00","2024-11-07","04:00:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,10",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO","28B6E-005","München - Salzburg","< >","Grafing Bahnhof","Ebersberg (Oberbay)",2024,2024,45,45,"2024-11-06","22:00:00","2024-11-07","04:00:00","0d, 6h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO","28DBC-001","München - Salzburg","<","Grafing Bahnhof","Zorneding",2024,2024,45,45,"2024-11-07","22:30:00","2024-11-08","04:30:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,15",null,null,null,"N",null,"2024-01-16",null,null,"4,5",1]
[null,"DB InfraGO","2BC8E-002","München - Salzburg","<","Haar","Haar",2024,2024,36,36,"2024-09-02","00:45:00","2024-09-02","04:45:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-05-23",null,null,1,1]
[null,"DB InfraGO","31FB-003","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2024,2024,38,39,"2024-09-20","00:01:00","2024-09-23","23:59:00","3d, 23h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,5,6,7",1]
[null,"DB InfraGO","31FB-007","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2024,2024,39,39,"2024-09-23","22:00:00","2024-09-27","04:00:00","3d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,2,3,4",1]
[null,"DB InfraGO","3203-003","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2024,2024,47,48,"2024-11-22","22:00:00","2024-11-30","05:00:00","7d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3203-006","Gemünden - Bamberg - Nürnberg","< >","Höflein","Hallstadt (b Bamberg)",2024,2024,48,49,"2024-11-29","21:00:00","2024-12-02","05:00:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"5,6,7",1]
[null,"DB InfraGO","23D65-002","Gemünden - Bamberg - Nürnberg","< >","Höflein","Hallstadt (b Bamberg)",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","04:45:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","24EB2-003","Gemünden - Bamberg - Nürnberg","< >","Höflein","Hallstadt (b Bamberg)",2024,2024,40,40,"2024-10-02","21:15:00","2024-10-03","05:00:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","26C60-002","Gemünden - Bamberg - Nürnberg","< >","Höflein","Hallstadt (b Bamberg)",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","04:45:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"6,7",1]
[null,"DB InfraGO","27937-002","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","04:45:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"6,7",1]
[null,"DB InfraGO","6537-005","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Waging",2024,2024,36,36,"2024-09-07","22:15:00","2024-09-08","04:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"6,7",1]
[null,"DB InfraGO","6537-006","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Waging",2024,2024,36,36,"2024-09-08","01:00:00","2024-09-08","02:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-14",null,null,7,1]
[null,"DB InfraGO","6597-005","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,47,47,"2024-11-22","03:00:00","2024-11-22","04:20:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-19",null,null,5,1]
[null,"DB InfraGO","65A2-003","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,47,47,"2024-11-22","23:50:00","2024-11-23","03:20:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-19",null,null,"5,6",1]
[null,"DB InfraGO","65A2-006","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,47,47,"2024-11-23","03:20:00","2024-11-23","04:40:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-19",null,null,6,1]
[null,"DB InfraGO","B073-020","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Waging",2024,2024,45,45,"2024-11-08","23:00:00","2024-11-09","00:01:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-20",null,null,"5,6",1]
[null,"DB InfraGO","236EB-002","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,36,36,"2024-09-06","22:30:00","2024-09-07","06:30:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"5,6",1]
[null,"DB InfraGO","253A3-004","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,40,40,"2024-10-04","21:15:00","2024-10-05","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-17",null,null,"5,6",1]
[null,"DB InfraGO","25DD6-002","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,44,44,"2024-11-01","21:15:00","2024-11-02","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"5,6",1]
[null,"DB InfraGO","276B9-002","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,48,48,"2024-11-29","21:15:00","2024-11-30","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-24",null,null,"5,6",1]
[null,"DB InfraGO","2B903-003","Gemünden - Bamberg - Nürnberg","< >","Hufschlag Abzw","Hufschlag",2024,2024,37,37,"2024-09-14","23:50:00","2024-09-15","04:50:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"6,7",1]
[null,"DB InfraGO","942F-007","München - Salzburg","< >","Landl (Oberbay) Abzw","Rohrdorf (Oberbay)",2024,2024,44,44,"2024-11-02","03:30:00","2024-11-02","04:50:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-19",null,null,6,1]
[null,"DB InfraGO","2423D-002","München - Salzburg","< >","Landl (Oberbay) Abzw","Landl (Oberbay)",2024,2024,38,38,"2024-09-16","21:20:00","2024-09-17","05:20:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","26934-002","München - Salzburg","< >","Landl (Oberbay) Abzw","Landl (Oberbay)",2024,2024,50,50,"2024-12-09","21:20:00","2024-12-10","05:20:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-24",null,null,"1,2",1]
[null,"DB InfraGO","27AAB-002","München - Salzburg","< >","Landl (Oberbay) Abzw","Landl (Oberbay)",2024,2024,42,42,"2024-10-14","21:20:00","2024-10-15","05:20:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"1,2",1]
[null,"DB InfraGO","31E0D-006","München - Salzburg","< >","Landl (Oberbay) Abzw","Landl (Oberbay)",2024,2024,46,46,"2024-11-11","21:15:00","2024-11-12","05:15:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO","1FDAC-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Steinerts","Mainaschaff Abzw",2024,2024,38,38,"2024-09-17","21:15:00","2024-09-18","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"2,3",1]
[null,"DB InfraGO","1FDAD-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Steinerts","Mainaschaff Abzw",2024,2024,42,42,"2024-10-15","21:15:00","2024-10-16","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"2,3",1]
[null,"DB InfraGO","1FDAE-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Steinerts","Mainaschaff Abzw",2024,2024,46,46,"2024-11-12","21:15:00","2024-11-13","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,"2,3",1]
[null,"DB InfraGO","1FE20-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Abzw","Mainaschaff Steinerts",2024,2024,39,39,"2024-09-23","20:20:00","2024-09-24","04:40:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"1,2",1]
[null,"DB InfraGO","1FE23-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Abzw","Mainaschaff Steinerts",2024,2024,47,47,"2024-11-18","20:20:00","2024-11-19","04:40:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2",1]
[null,"DB InfraGO","24CC0-002","Darmstadt - Aschaffenburg","< >","Mainaschaff Abzw","Mainaschaff Steinerts",2024,2024,43,43,"2024-10-21","20:20:00","2024-10-22","04:40:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","1FDAE-006","Darmstadt - Aschaffenburg","< >","Mainaschaff Abzw","Mainaschaff Steinerts",2024,2024,46,46,"2024-11-12","21:15:00","2024-11-13","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,"2,3",1]
[null,"DB InfraGO","4D11-006","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,46,46,"2024-11-15","04:30:00","2024-11-15","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-07-18",null,null,5,1]
[null,"DB InfraGO","4DDE-006","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,45,45,"2024-11-09","05:00:00","2024-11-09","06:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-07-18",null,null,6,1]
[null,"DB InfraGO","5473-002","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,43,43,"2024-10-21","23:00:00","2024-10-22","05:30:00","0d, 6h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-07-19",null,null,"1,2",1]
[null,"DB InfraGO","5484-005","Würzburg - Nürnberg",">","Nantenbach","Rohrbach",2024,2024,43,43,"2024-10-23","03:55:00","2024-10-23","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-07-19",null,null,3,1]
[null,"DB InfraGO","552A-005","Würzburg - Nürnberg",">","Nantenbach","Rohrbach",2024,2024,43,43,"2024-10-24","00:00:00","2024-10-24","05:30:00","0d, 5h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-07-19",null,null,4,1]
[null,"DB InfraGO","23892-002","Würzburg - Nürnberg","<","Rohrbach","Lohr Bahnhof",2024,2024,38,38,"2024-09-17","20:50:00","2024-09-18","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-09",null,null,"2,3",1]
[null,"DB InfraGO","23FB5-004","Würzburg - Nürnberg",">","Nantenbach","Rohrbach",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-06",null,null,"4,5",1]
[null,"DB InfraGO","24C32-002","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,39,39,"2024-09-25","21:10:00","2024-09-26","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-02-16",null,null,"3,4",1]
[null,"DB InfraGO","25B11-004","Würzburg - Nürnberg",">","Nantenbach","Rohrbach",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-04",null,null,"4,5",1]
[null,"DB InfraGO","265D6-002","Würzburg - Nürnberg",">","Nantenbach","Rohrbach",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","270E0-002","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,47,47,"2024-11-20","21:10:00","2024-11-21","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-04-15",null,null,"3,4",1]
[null,"DB InfraGO","27B98-002","Würzburg - Nürnberg","<","Rohrbach","Nantenbach",2024,2024,43,43,"2024-10-23","21:10:00","2024-10-24","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-03-15",null,null,"3,4",1]
[null,"DB InfraGO","2F5E7-005","Würzburg - Nürnberg","<","Rohrbach","Lohr Bahnhof",2024,2024,37,37,"2024-09-11","20:00:00","2024-09-12","06:00:00","0d, 10h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-22",null,null,"3,4",1]
[null,"DB InfraGO","2F5E7-006","Würzburg - Nürnberg","<","Rohrbach","Lohr Bahnhof",2024,2024,37,37,"2024-09-12","20:00:00","2024-09-13","06:00:00","0d, 10h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-22",null,null,"4,5",1]
[null,"DB InfraGO","320F-011","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Ingolstadt Nord",2024,2024,46,46,"2024-11-16","23:00:00","2024-11-17","05:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-15",null,null,"6,7",1]
[null,"DB InfraGO","320F-018","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Nürnberg Reichswald",2024,2024,46,46,"2024-11-16","23:00:00","2024-11-17","05:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-15",null,null,"6,7",1]
[null,"DB InfraGO","58AA-004","Nürnberg - Regensburg","<","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,47,48,"2024-11-18","22:15:00","2024-11-29","05:15:00","10d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-02-10",null,null,"1,2,3,4",1]
[null,"DB InfraGO","58AA-007","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,47,48,"2024-11-18","22:15:00","2024-11-29","05:15:00","10d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-02-10",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606B-002","Nürnberg - Regensburg",">","Nürnberg Reichswald","Kinding (Altmühltal)",2024,2024,44,45,"2024-11-03","22:50:00","2024-11-05","04:40:00","1d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",5,",null,null,null,"N",null,"2024-01-26",null,null,"1,7",1]
[null,"DB InfraGO","606F-001","Nürnberg - Regensburg","< >","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,42,43,"2024-10-14","22:05:00","2024-10-23","05:05:00","8d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606F-002","Nürnberg - Regensburg","<","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,42,43,"2024-10-14","22:05:00","2024-10-23","05:05:00","8d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606F-003","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,42,43,"2024-10-14","22:05:00","2024-10-23","05:05:00","8d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606F-004","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,43,44,"2024-10-23","22:15:00","2024-11-01","04:55:00","8d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606F-005","Nürnberg - Regensburg",">","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,43,44,"2024-10-23","22:15:00","2024-11-01","04:55:00","8d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",5,5",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","606F-006","Nürnberg - Regensburg","< >","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,43,44,"2024-10-23","22:15:00","2024-11-01","04:55:00","8d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-12-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO","22A18-009","Nürnberg - Regensburg",">","Kinding (Altmühltal)","Nürnberg Reichswald",2024,2024,36,36,"2024-09-05","09:00:00","2024-09-05","12:00:00","0d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-02-01",null,null,4,1]
[null,"DB InfraGO","22A18-012","Nürnberg - Regensburg",">","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,36,36,"2024-09-05","12:00:00","2024-09-05","15:30:00","0d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-02-01",null,null,4,1]
[null,"DB InfraGO","22D14-001","Nürnberg - Regensburg",">","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,37,37,"2024-09-12","21:50:00","2024-09-13","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","22D14-002","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,37,37,"2024-09-12","21:50:00","2024-09-13","05:00:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","265CA-001","Nürnberg - Regensburg",">","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","265CA-002","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","2705F-001","Nürnberg - Regensburg",">","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,47,47,"2024-11-20","21:15:00","2024-11-21","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2024-04-08",null,null,"3,4",1]
[null,"DB InfraGO","2705F-002","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,47,47,"2024-11-20","21:15:00","2024-11-21","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2024-04-08",null,null,"3,4",1]
[null,"DB InfraGO","2D855-002","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,38,38,"2024-09-22","00:05:00","2024-09-22","02:35:00","0d, 2h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",4,4",null,null,null,"N",null,"2024-06-14",null,null,7,1]
[null,"DB InfraGO","2D855-005","Nürnberg - Regensburg",">","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,38,38,"2024-09-22","00:05:00","2024-09-22","01:20:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-06-14",null,null,7,1]
[null,"DB InfraGO","2D855-007","Nürnberg - Regensburg",">","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,38,38,"2024-09-22","01:20:00","2024-09-22","02:35:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-06-14",null,null,7,1]
[null,"DB InfraGO","2D855-009","Nürnberg - Regensburg",">","Allersberg (Rothsee)","Nürnberg Reichswald",2024,2024,38,38,"2024-09-22","02:35:00","2024-09-22","06:05:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-07-16",null,null,7,1]
[null,"DB InfraGO","2D855-011","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,38,38,"2024-09-22","02:35:00","2024-09-22","06:05:00","0d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",4,4",null,null,null,"N",null,"2024-06-14",null,null,7,1]
[null,"DB InfraGO","5D20-010","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2024,2024,38,38,"2024-09-18","22:50:00","2024-09-19","02:26:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,"3,4",1]
[null,"DB InfraGO","5D20-011","Mannheim - Karlsruhe",">","Philippsburg Molzau","Blankenloch",2024,2024,38,38,"2024-09-19","02:26:00","2024-09-19","04:40:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,4,1]
[null,"DB InfraGO","5D20-012","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,38,38,"2024-09-19","02:26:00","2024-09-19","04:40:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,4,1]
[null,"DB InfraGO","5D20-017","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,38,38,"2024-09-20","00:05:00","2024-09-20","04:40:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,5,1]
[null,"DB InfraGO","5D20-018","Mannheim - Karlsruhe","<","Philippsburg Molzau","Oberhausen",2024,2024,38,38,"2024-09-20","00:05:00","2024-09-20","04:40:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,5,1]
[null,"DB InfraGO","22683-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,35,35,"2024-08-31","21:00:00","2024-09-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-19",null,null,"6,7",1]
[null,"DB InfraGO","22F9B-003","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","22F9B-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","23A77-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Hockenheim",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","23C4F-001","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","23C4F-002","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe Hbf",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","23C4F-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe-Hagsfeld",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","23F90-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Oberhausen",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-23",null,null,"4,5",1]
[null,"DB InfraGO","23F90-006","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-23",null,null,"4,5",1]
[null,"DB InfraGO","23F90-007","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-23",null,null,"4,5",1]
[null,"DB InfraGO",2.4359999999999998E-3,"Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,39,39,"2024-09-27","21:00:00","2024-09-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"5,6",1]
[null,"DB InfraGO","24433-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,39,39,"2024-09-28","21:00:00","2024-09-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-20",null,null,"6,7",1]
[null,"DB InfraGO","25071-003","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","25071-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","25817-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Hockenheim",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-26",null,null,"2,3",1]
[null,"DB InfraGO","25CC7-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Hockenheim",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-20",null,null,"2,3",1]
[null,"DB InfraGO","26129-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Oberhausen",2024,2024,40,40,"2024-10-03","23:40:00","2024-10-04","02:20:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-03-08",null,null,"4,5",1]
[null,"DB InfraGO","262A4-003","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","262A4-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","262A5-003","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO","262A5-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO","2630A-001","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","2630A-002","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe Hbf",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","2630A-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe-Hagsfeld",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","2631A-001","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","2631A-002","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe Hbf",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","2631A-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe-Hagsfeld",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","2631B-001","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO","2631B-002","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe Hbf",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO","2631B-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Karlsruhe-Hagsfeld",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO","271A1-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Oberhausen",2024,2024,47,47,"2024-11-21","21:00:00","2024-11-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-16",null,null,"4,5",1]
[null,"DB InfraGO","271A1-006","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,47,47,"2024-11-21","21:00:00","2024-11-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"4,5",1]
[null,"DB InfraGO","271A1-007","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,47,47,"2024-11-21","21:00:00","2024-11-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-16",null,null,"4,5",1]
[null,"DB InfraGO","272FD-006","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,47,47,"2024-11-22","21:00:00","2024-11-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-16",null,null,"5,6",1]
[null,"DB InfraGO","273B5-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,47,47,"2024-11-23","21:00:00","2024-11-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-16",null,null,"6,7",1]
[null,"DB InfraGO","274BC-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Hockenheim",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO","280FC-005","Mannheim - Karlsruhe",">","Graben-Neudorf","Blankenloch",2024,2024,43,43,"2024-10-26","21:00:00","2024-10-27","05:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-14",null,null,"6,7",1]
[null,"DB InfraGO","281E5-015","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,42,42,"2024-10-19","02:00:00","2024-10-19","04:00:00","0d, 2h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-08",null,null,6,1]
[null,"DB InfraGO","281E5-017","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,42,42,"2024-10-20","02:00:00","2024-10-20","07:00:00","0d, 5h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-08",null,null,7,1]
[null,"DB InfraGO","28433-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Oberhausen",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-14",null,null,"4,5",1]
[null,"DB InfraGO","28433-006","Mannheim - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-14",null,null,"4,5",1]
[null,"DB InfraGO","28433-007","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-14",null,null,"4,5",1]
[null,"DB InfraGO","28453-008","Mannheim - Karlsruhe",">","Waghäusel Saalbach","Philippsburg Molzau",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-003","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-28","23:50:00","2024-11-29","04:40:00","0d, 4h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-08",null,null,"4,5",1]
[null,"DB InfraGO","29E0A-015","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-27","23:50:00","2024-11-28","04:40:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"3,4",1]
[null,"DB InfraGO","29E0A-016","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,48,48,"2024-11-27","23:50:00","2024-11-28","04:40:00","0d, 4h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-08",null,null,"3,4",1]
[null,"DB InfraGO","29E0A-019","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,48,48,"2024-11-28","23:50:00","2024-11-29","04:40:00","0d, 4h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-08",null,null,"4,5",1]
[null,"DB InfraGO","29E0A-023","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-29","22:45:00","2024-11-30","07:45:00","0d, 9h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"5,6",1]
[null,"DB InfraGO","29E0A-025","Mannheim - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2024,2024,48,48,"2024-11-29","22:45:00","2024-11-30","07:45:00","0d, 9h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-08",null,null,"5,6",1]
[null,"DB InfraGO","2F10E-001","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,39,39,"2024-09-27","21:00:00","2024-09-28","06:00:00","0d, 9h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-04",null,null,"5,6",1]
[null,"DB InfraGO","3119-002","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kehl",2024,2024,48,49,"2024-12-01","22:00:00","2024-12-02","05:00:00","0d, 7h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-01",null,null,"1,7",1]
[null,"DB InfraGO","23917-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-01-26",null,null,"2,3",1]
[null,"DB InfraGO","23917-003","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-01-26",null,null,"2,3",1]
[null,"DB InfraGO","23917-005","Karlsruhe - Strasbourg","< >","Kork","Kehl Grenze",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,87,"N",null,"2024-01-26",null,null,"2,3",1]
[null,"DB InfraGO","23935-001","Karlsruhe - Strasbourg","<","Kork","Appenweier Kurve",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-26",null,null,"1,2",1]
[null,"DB InfraGO","23935-003","Karlsruhe - Strasbourg","<","Kork","Appenweier-Muhrhaag",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"1,2",1]
[null,"DB InfraGO","23935-005","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-01-26",null,null,"1,2",1]
[null,"DB InfraGO","24176-001","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-26",null,null,"3,4",1]
[null,"DB InfraGO","24176-003","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"3,4",1]
[null,"DB InfraGO","24176-004","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kehl",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-26",null,null,"3,4",1]
[null,"DB InfraGO","24798-001","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO","24798-002","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO","24798-004","Karlsruhe - Strasbourg",">","Appenweier Nord","Kork",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO","24798-008","Karlsruhe - Strasbourg","< >","Kork","Appenweier-Muhrhaag",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO",248.2,"Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-07",null,null,"5,6",1]
[null,"DB InfraGO",24.82,"Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"5,6",1]
[null,"DB InfraGO",0.2482,"Karlsruhe - Strasbourg","< >","Kehl","Kork",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-07",null,null,"5,6",1]
[null,"DB InfraGO","248BD-001","Karlsruhe - Strasbourg",">","Kehl","Kehl Grenze",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-02-07",null,null,"6,7",1]
[null,"DB InfraGO","248BD-003","Karlsruhe - Strasbourg","< >","Kehl Grenze","Kehl",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-02-07",null,null,"6,7",1]
[null,"DB InfraGO","248BD-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"6,7",1]
[null,"DB InfraGO","252F9-001","Karlsruhe - Strasbourg","<","Kork","Appenweier Kurve",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-23",null,null,"1,2",1]
[null,"DB InfraGO","252F9-003","Karlsruhe - Strasbourg","<","Kork","Appenweier-Muhrhaag",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"1,2",1]
[null,"DB InfraGO","252F9-005","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-23",null,null,"1,2",1]
[null,"DB InfraGO","2532A-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-02-23",null,null,"2,3",1]
[null,"DB InfraGO","2532A-003","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-02-23",null,null,"2,3",1]
[null,"DB InfraGO","2532A-005","Karlsruhe - Strasbourg","< >","Kork","Kehl Grenze",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,87,"N",null,"2024-02-23",null,null,"2,3",1]
[null,"DB InfraGO","25345-001","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-28",null,null,"3,4",1]
[null,"DB InfraGO","25345-003","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"3,4",1]
[null,"DB InfraGO","25345-004","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kehl",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-28",null,null,"3,4",1]
[null,"DB InfraGO","25C91-001","Karlsruhe - Strasbourg","<","Kork","Appenweier Kurve",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","25C91-003","Karlsruhe - Strasbourg","<","Kork","Appenweier-Muhrhaag",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","25C91-005","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","25CB6-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","25CB6-003","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","25CB6-005","Karlsruhe - Strasbourg","< >","Kork","Kehl Grenze",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,87,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","25CF2-001","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","25CF2-003","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","25CF2-004","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kehl",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-22",null,null,"3,4",1]
[null,"DB InfraGO","26B80-001","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","26B80-002","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","26B80-004","Karlsruhe - Strasbourg",">","Appenweier Nord","Kork",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","26B80-008","Karlsruhe - Strasbourg","< >","Kork","Appenweier-Muhrhaag",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","26B81-001","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-12",null,null,"4,5",1]
[null,"DB InfraGO","26B81-002","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-12",null,null,"4,5",1]
[null,"DB InfraGO","26B81-004","Karlsruhe - Strasbourg",">","Appenweier Nord","Kork",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-12",null,null,"4,5",1]
[null,"DB InfraGO","26B81-008","Karlsruhe - Strasbourg","< >","Kork","Appenweier-Muhrhaag",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-12",null,null,"4,5",1]
[null,"DB InfraGO","26BEC-001","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-22",null,null,"5,6",1]
[null,"DB InfraGO","26BEC-002","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"5,6",1]
[null,"DB InfraGO","26BEC-004","Karlsruhe - Strasbourg","< >","Kehl","Kork",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-22",null,null,"5,6",1]
[null,"DB InfraGO","26BED-001","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-12",null,null,"5,6",1]
[null,"DB InfraGO","26BED-002","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-12",null,null,"5,6",1]
[null,"DB InfraGO","26BED-004","Karlsruhe - Strasbourg","< >","Kehl","Kork",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-12",null,null,"5,6",1]
[null,"DB InfraGO","26C81-001","Karlsruhe - Strasbourg",">","Kehl","Kehl Grenze",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","26C81-003","Karlsruhe - Strasbourg","< >","Kehl Grenze","Kehl",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","26C81-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","26C82-001","Karlsruhe - Strasbourg",">","Kehl","Kehl Grenze",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-04-12",null,null,6,1]
[null,"DB InfraGO","26C82-003","Karlsruhe - Strasbourg","< >","Kehl Grenze","Kehl",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-04-12",null,null,6,1]
[null,"DB InfraGO","26C82-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-12",null,null,6,1]
[null,"DB InfraGO","27453-001","Karlsruhe - Strasbourg","<","Kork","Appenweier Kurve",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","27453-003","Karlsruhe - Strasbourg","<","Kork","Appenweier-Muhrhaag",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","27453-005","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","2749B-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-03-28",null,null,"2,3",1]
[null,"DB InfraGO","2749B-003","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-03-28",null,null,"2,3",1]
[null,"DB InfraGO","2749B-005","Karlsruhe - Strasbourg","< >","Kork","Kehl Grenze",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,87,"N",null,"2024-03-28",null,null,"2,3",1]
[null,"DB InfraGO","27512-001","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-28",null,null,"3,4",1]
[null,"DB InfraGO","27512-003","Karlsruhe - Strasbourg","<","Kehl","Appenweier Kurve",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"3,4",1]
[null,"DB InfraGO","27512-004","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kehl",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-28",null,null,"3,4",1]
[null,"DB InfraGO","27A4F-001","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27A4F-002","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27A4F-004","Karlsruhe - Strasbourg",">","Appenweier Nord","Kork",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27A4F-008","Karlsruhe - Strasbourg","< >","Kork","Appenweier-Muhrhaag",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27A63-001","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","27A63-002","Karlsruhe - Strasbourg",">","Kork","Kehl",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","27A63-004","Karlsruhe - Strasbourg","< >","Kehl","Kork",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","27A90-001","Karlsruhe - Strasbourg",">","Kehl","Kehl Grenze",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","27A90-003","Karlsruhe - Strasbourg","< >","Kehl Grenze","Kehl",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","27A90-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","23947-003","Karlsruhe - Strasbourg","< >","Appenweier Nord","Oberkirch",2024,2024,36,36,"2024-09-05","21:00:00","2024-09-06","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","25905-003","Karlsruhe - Strasbourg","< >","Appenweier Nord","Oberkirch",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"4,5",1]
[null,"DB InfraGO","25D49-003","Karlsruhe - Strasbourg","< >","Appenweier Nord","Oberkirch",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","275B5-003","Karlsruhe - Strasbourg","< >","Appenweier Nord","Oberkirch",2024,2024,48,48,"2024-11-28","21:00:00","2024-11-29","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","23935-002","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Appenweier-Muhrhaag",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"1,2",1]
[null,"DB InfraGO","246D0-002","Karlsruhe - Strasbourg","< >","Appenweier-Muhrhaag","Appenweier Kurve",2024,2024,37,37,"2024-09-14","21:00:00","2024-09-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","252F9-002","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Appenweier-Muhrhaag",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"1,2",1]
[null,"DB InfraGO","25C91-002","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Appenweier-Muhrhaag",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","2679A-002","Karlsruhe - Strasbourg","< >","Appenweier-Muhrhaag","Appenweier Kurve",2024,2024,45,45,"2024-11-09","21:00:00","2024-11-10","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","2679B-002","Karlsruhe - Strasbourg","< >","Appenweier-Muhrhaag","Appenweier Kurve",2024,2024,49,49,"2024-12-07","21:00:00","2024-12-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"6,7",1]
[null,"DB InfraGO","27453-002","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Appenweier-Muhrhaag",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","2788C-002","Karlsruhe - Strasbourg","< >","Appenweier-Muhrhaag","Appenweier Kurve",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"6,7",1]
[null,"DB InfraGO","1FE69-003","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Dieburg",2024,2024,39,39,"2024-09-24","20:45:00","2024-09-25","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"48,48,48",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE6A-003","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Dieburg",2024,2024,43,43,"2024-10-22","20:45:00","2024-10-23","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"48,48,48",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE6C-003","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Dieburg",2024,2024,47,47,"2024-11-19","20:45:00","2024-11-20","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"48,48,48",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","B9E4-014","Stuttgart - München","<","Schwabmünchen","Augsburg Hbf",2024,2024,38,38,"2024-09-16","21:00:00","2024-09-19","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3",1]
[null,"DB InfraGO","B9E4-017","Stuttgart - München","<","Bobingen","Augsburg Hbf",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-22","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-27",null,null,"4,5,6",1]
[null,"DB InfraGO","B9E4-018","Stuttgart - München","<","Schwabmünchen","Augsburg Hbf",2024,2024,37,37,"2024-09-12","22:00:00","2024-09-14","04:00:00","1d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2023-01-27",null,null,"4,5",1]
[null,"DB InfraGO","B9E4-019","Stuttgart - München","<","Bobingen","Augsburg Hbf",2024,2024,37,38,"2024-09-14","22:00:00","2024-09-16","04:00:00","1d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-27",null,null,"6,7",1]
[null,"DB InfraGO","2ABE2-002","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,43,43,"2024-10-26","23:00:00","2024-10-27","07:00:00","0d, 9h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"6,7",1]
[null,"DB InfraGO","2ABE2-015","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,45,45,"2024-11-05","06:00:00","2024-11-05","14:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,2,1]
[null,"DB InfraGO","5040-009","Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-13",null,null,"6,7",1]
[null,"DB InfraGO","5040-012","Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,43,44,"2024-10-26","22:00:00","2024-10-28","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-13",null,null,"6,7",1]
[null,"DB InfraGO","CE8F-001","Stuttgart - München","<","Gablingen","Augsburg-Oberhausen",2024,2024,37,37,"2024-09-12","23:20:00","2024-09-13","00:20:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-03-07",null,null,"4,5",1]
[null,"DB InfraGO","CE8F-002","Stuttgart - München","<","Augsburg-Oberhausen","Gablingen",2024,2024,37,37,"2024-09-13","00:20:00","2024-09-13","02:35:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-03-07",null,null,5,1]
[null,"DB InfraGO","1D79E-004","Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,43,44,"2024-10-26","22:00:00","2024-10-28","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-13",null,null,"6,7",1]
[null,"DB InfraGO","1D79E-005","Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-13",null,null,"6,7",1]
[null,"DB InfraGO","24F1F-001","Stuttgart - München","<","Meitingen","Augsburg-Oberhausen",2024,2024,35,35,"2024-08-31","21:00:00","2024-09-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO","24F1F-005","Stuttgart - München","< >","Augsburg-Oberhausen","Meitingen",2024,2024,35,35,"2024-08-31","21:00:00","2024-09-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO","24F58-001","Stuttgart - München",">","Augsburg Hbf","Gersthofen",2024,2024,37,37,"2024-09-09","20:45:00","2024-09-10","04:35:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO","24F58-003","Stuttgart - München","< >","Gersthofen","Augsburg-Oberhausen",2024,2024,37,37,"2024-09-09","20:45:00","2024-09-10","04:35:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO",250.5,"Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,37,37,"2024-09-09","20:45:00","2024-09-10","04:35:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO",2.5049999999999999,"Stuttgart - München","< >","Gablingen","Augsburg-Oberhausen",2024,2024,37,37,"2024-09-09","20:45:00","2024-09-10","04:35:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO","290ED-005","Stuttgart - München","< >","Gersthofen","Augsburg-Oberhausen",2024,2024,30,50,"2024-07-26","23:00:00","2024-12-14","23:59:00","141d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","290ED-026","Stuttgart - München","< >","Augsburg-Oberhausen","Gersthofen",2024,2024,33,36,"2024-08-12","23:00:00","2024-09-03","04:30:00","21d, 5h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","290ED-028","Stuttgart - München","< >","Gersthofen","Augsburg-Oberhausen",2024,2024,33,36,"2024-08-12","23:00:00","2024-09-03","04:30:00","21d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","290ED-029","Stuttgart - München","<","Gersthofen","Augsburg-Oberhausen",2024,2024,33,36,"2024-08-12","23:00:00","2024-09-03","04:30:00","21d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","290ED-032","Stuttgart - München","<","Gersthofen","Augsburg-Oberhausen",2024,2024,36,36,"2024-09-03","23:00:00","2024-09-07","04:30:00","3d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-27",null,null,"2,3,4,5",1]
[null,"DB InfraGO","290ED-033","Stuttgart - München","< >","Gersthofen","Augsburg-Oberhausen",2024,2024,36,36,"2024-09-03","23:00:00","2024-09-07","04:30:00","3d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-27",null,null,"2,3,4,5",1]
[null,"DB InfraGO","290ED-034","Stuttgart - München",">","Augsburg-Oberhausen","Gersthofen",2024,2024,36,37,"2024-09-07","23:00:00","2024-09-11","04:30:00","3d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-27",null,null,"1,2,6,7",1]
[null,"DB InfraGO","290ED-036","Stuttgart - München","< >","Augsburg-Oberhausen","Gersthofen",2024,2024,36,37,"2024-09-07","23:00:00","2024-09-11","04:30:00","3d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,6,7",1]
[null,"DB InfraGO","2AA46-001","Stuttgart - München","<","Gersthofen","Augsburg-Oberhausen",2024,2024,35,36,"2024-08-31","21:00:00","2024-09-02","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-29",null,null,"6,7",1]
[null,"DB InfraGO","2AA46-007","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2024,2024,35,36,"2024-08-31","21:00:00","2024-09-02","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"6,7",1]
[null,"DB InfraGO","2AA46-009","Stuttgart - München","<","Gersthofen","Augsburg-Oberhausen",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO","2AA46-013","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO","28FF-001","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,32,36,"2024-08-07","20:00:00","2024-09-07","05:00:00","30d, 9h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3130-008","Stuttgart - München","<","Günzburg","Neuoffingen",2024,2024,34,37,"2024-08-23","23:00:00","2024-09-10","05:00:00","17d, 6h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3130-009","Stuttgart - München","<","Günzburg","Neuoffingen",2024,2024,43,44,"2024-10-25","23:00:00","2024-10-30","05:00:00","4d, 7h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,null,null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","3130-013","Stuttgart - München","<","Neu-Ulm","Günzburg",2024,2024,34,37,"2024-08-23","23:00:00","2024-09-10","05:00:00","17d, 6h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3130-014","Stuttgart - München","<","Neu-Ulm","Günzburg",2024,2024,43,44,"2024-10-25","23:00:00","2024-10-30","05:00:00","4d, 7h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","28FF-010","Stuttgart - München","< >","Burgau (Schwab)","Neuoffingen",2024,2024,35,36,"2024-08-29","08:00:00","2024-09-07","05:00:00","8d, 21h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","28FF-011","Stuttgart - München",">","Burgau (Schwab)","Neuoffingen",2024,2024,36,37,"2024-09-07","20:30:00","2024-09-12","04:30:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-11",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO","28FF-012","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,36,36,"2024-09-07","05:00:00","2024-09-08","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2023-06-27",null,null,"6,7",1]
[null,"DB InfraGO","28FF-013","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,36,37,"2024-09-08","05:00:00","2024-09-12","04:30:00","3d, 23h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-06-27",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO",0.32200000000000001,"Stuttgart - München",">","Gessertshausen","Dinkelscherben",2024,2024,34,35,"2024-08-24","20:30:00","2024-09-01","04:30:00","7d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO",3.2199999999999999E-2,"Stuttgart - München","< >","Dinkelscherben","Gessertshausen",2024,2024,34,35,"2024-08-24","20:30:00","2024-09-01","04:30:00","7d, 8h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-01-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","4F19-007","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,39,39,"2024-09-23","22:35:00","2024-09-23","23:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-18",null,null,1,1]
[null,"DB InfraGO","5A63-007","Stuttgart - München","<","Westheim (Schwab)","Westheim (Schwab)",2024,2024,41,42,"2024-10-13","00:00:00","2024-10-14","03:00:00","1d, 3h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-07-24",null,null,"1,7",1]
[null,"DB InfraGO","5A63-008","Stuttgart - München","<","Gessertshausen","Augsburg-Oberhausen",2024,2024,41,42,"2024-10-13","03:00:00","2024-10-14","05:00:00","1d, 2h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-24",null,null,"1,7",1]
[null,"DB InfraGO","5A63-009","Stuttgart - München",">","Westheim (Schwab)","Westheim (Schwab)",2024,2024,41,42,"2024-10-13","03:00:00","2024-10-14","05:00:00","1d, 2h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-07-24",null,null,"1,7",1]
[null,"DB InfraGO","5AE2-005","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,43,44,"2024-10-25","20:30:00","2024-10-29","04:30:00","3d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO","4F19-023","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,39,39,"2024-09-24","01:35:00","2024-09-24","02:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2022-10-27",null,null,2,1]
[null,"DB InfraGO","4F19-052","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,39,39,"2024-09-24","21:35:00","2024-09-24","22:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-10-27",null,null,2,1]
[null,"DB InfraGO","4F19-068","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,39,39,"2024-09-25","00:50:00","2024-09-25","02:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-10-27",null,null,3,1]
[null,"DB InfraGO","5AE2-009","Stuttgart - München","<","Burgau (Schwab)","Freihalden Üst",2024,2024,36,36,"2024-09-06","20:00:00","2024-09-06","23:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-27",null,null,5,1]
[null,"DB InfraGO","5AE2-010","Stuttgart - München","< >","Neuoffingen","Freihalden Üst",2024,2024,36,36,"2024-09-06","20:00:00","2024-09-06","21:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,5,1]
[null,"DB InfraGO","5AE2-011","Stuttgart - München",">","Günzburg","Neuoffingen",2024,2024,36,36,"2024-09-06","23:30:00","2024-09-07","04:30:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-27",null,null,"5,6",1]
[null,"DB InfraGO","20417-015","Stuttgart - München","< >","Neu-Ulm","Neu-Ulm",2024,2024,38,38,"2024-09-18","23:00:00","2024-09-19","05:00:00","0d, 6h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","20417-025","Stuttgart - München","< >","Neu-Ulm","Neu-Ulm",2024,2024,40,40,"2024-10-02","23:00:00","2024-10-03","05:00:00","0d, 6h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","20417-030","Stuttgart - München","< >","Neu-Ulm","Neu-Ulm",2024,2024,41,41,"2024-10-09","23:00:00","2024-10-10","05:00:00","0d, 6h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","23278-001","Stuttgart - München","<","Neu-Ulm","Nersingen",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","23278-002","Stuttgart - München","<","Nersingen","Unterfahlheim",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","23278-005","Stuttgart - München","<","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","23278-006","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","23278-008","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","23311-001","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","23311-002","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","23311-004","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","23483-001","Stuttgart - München","<","Günzburg","Neuoffingen",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-01-22",null,null,"3,4",1]
[null,"DB InfraGO","23483-004","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"3,4",1]
[null,"DB InfraGO","23483-006","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"3,4",1]
[null,"DB InfraGO","23D7B-001","Stuttgart - München","<","Burgau (Schwab)","Dinkelscherben",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-16",null,null,"3,4",1]
[null,"DB InfraGO","23D7B-003","Stuttgart - München","< >","Dinkelscherben","Burgau (Schwab)",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"3,4",1]
[null,"DB InfraGO","23F2F-001","Stuttgart - München","<","Gessertshausen","Westheim (Schwab)",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-16",null,null,"2,3",1]
[null,"DB InfraGO","23F2F-003","Stuttgart - München","< >","Westheim (Schwab)","Gessertshausen",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-16",null,null,"2,3",1]
[null,"DB InfraGO","2442A-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2442A-004","Stuttgart - München",">","Nersingen","Neu-Ulm",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2442A-007","Stuttgart - München",">","Unterfahlheim","Nersingen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2442A-008","Stuttgart - München","< >","Günzburg","Neu-Ulm",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2442A-009","Stuttgart - München","< >","Neu-Ulm","Günzburg",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","24444-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","24444-004","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","24444-005","Stuttgart - München","< >","Unterfahlheim","Günzburg",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-06",null,null,"5,6",1]
[null,"DB InfraGO","2444A-001","Stuttgart - München",">","Burgau (Schwab)","Neuoffingen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2444A-004","Stuttgart - München",">","Neuoffingen","Günzburg",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2444A-005","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","2444A-007","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","24588-001","Stuttgart - München",">","Gessertshausen","Freihalden Üst",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24588-003","Stuttgart - München","< >","Gessertshausen","Freihalden Üst",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24588-005","Stuttgart - München","< >","Freihalden Üst","Gessertshausen",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24593-001","Stuttgart - München",">","Augsburg Hbf","Gessertshausen",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"5,6",1]
[null,"DB InfraGO","24593-003","Stuttgart - München","< >","Augsburg Hirblinger Straße","Gessertshausen",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"5,6",1]
[null,"DB InfraGO","24593-004","Stuttgart - München","< >","Gessertshausen","Augsburg Hirblinger Straße",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"5,6",1]
[null,"DB InfraGO","24904-001","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-21",null,null,"4,5",1]
[null,"DB InfraGO","24904-003","Stuttgart - München",">","Burgau (Schwab)","Unterfahlheim",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-21",null,null,"4,5",1]
[null,"DB InfraGO","24904-004","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,"4,5",1]
[null,"DB InfraGO","24F58-006","Stuttgart - München","< >","Augsburg Hbf","Augsburg-Oberhausen",2024,2024,37,37,"2024-09-09","20:45:00","2024-09-10","04:35:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-04",null,null,"1,2",1]
[null,"DB InfraGO",255.3,"Stuttgart - München",">","Dinkelscherben","Burgau (Schwab)",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"5,6",1]
[null,"DB InfraGO",0.25530000000000003,"Stuttgart - München","< >","Burgau (Schwab)","Dinkelscherben",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"5,6",1]
[null,"DB InfraGO","25560-001","Stuttgart - München",">","Westheim (Schwab)","Dinkelscherben",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"6,7",1]
[null,"DB InfraGO","25560-004","Stuttgart - München","< >","Dinkelscherben","Westheim (Schwab)",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"6,7",1]
[null,"DB InfraGO","25569-001","Stuttgart - München",">","Freihalden Üst","Neuoffingen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"6,7",1]
[null,"DB InfraGO","25569-003","Stuttgart - München","< >","Neuoffingen","Freihalden Üst",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"6,7",1]
[null,"DB InfraGO","255D9-001","Stuttgart - München","<","Neu-Ulm","Nersingen",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","255D9-002","Stuttgart - München","<","Nersingen","Unterfahlheim",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","255D9-005","Stuttgart - München","<","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","255D9-006","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","255D9-008","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","25865-001","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","25865-002","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","25865-004","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","255D9-010","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","25A35-001","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-02-20",null,null,"2,3",1]
[null,"DB InfraGO","25A35-002","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"2,3",1]
[null,"DB InfraGO","25A35-004","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"2,3",1]
[null,"DB InfraGO","25A4E-001","Stuttgart - München","<","Günzburg","Neuoffingen",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO","25A4E-004","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous",null,null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO","25A4E-006","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO","25C77-001","Stuttgart - München","<","Neu-Ulm","Nersingen",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25C77-002","Stuttgart - München","<","Nersingen","Unterfahlheim",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25C77-005","Stuttgart - München","<","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25C77-007","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25C77-008","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25C77-010","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"1,2",1]
[null,"DB InfraGO","25CE2-001","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","25CE2-002","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","25CE2-004","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","23278-010","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","26BB3-001","Stuttgart - München",">","Gessertshausen","Freihalden Üst",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-25",null,null,"4,5",1]
[null,"DB InfraGO","26BB3-003","Stuttgart - München","< >","Gessertshausen","Freihalden Üst",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"4,5",1]
[null,"DB InfraGO","26BB3-004","Stuttgart - München","< >","Freihalden Üst","Gessertshausen",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"4,5",1]
[null,"DB InfraGO","26BB4-001","Stuttgart - München",">","Gessertshausen","Freihalden Üst",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","26BB4-003","Stuttgart - München","< >","Gessertshausen","Freihalden Üst",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","26BB4-004","Stuttgart - München","< >","Freihalden Üst","Gessertshausen",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","26BBF-001","Stuttgart - München",">","Burgau (Schwab)","Unterfahlheim",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-10",null,null,"4,5",1]
[null,"DB InfraGO","26BBF-006","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-10",null,null,"4,5",1]
[null,"DB InfraGO","26BBF-008","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-10",null,null,"4,5",1]
[null,"DB InfraGO","26BC0-001","Stuttgart - München",">","Burgau (Schwab)","Unterfahlheim",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","26BC0-006","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","26BC0-008","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","26C2A-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-10",null,null,"5,6",1]
[null,"DB InfraGO","26C2A-004","Stuttgart - München","< >","Unterfahlheim","Günzburg",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-10",null,null,"5,6",1]
[null,"DB InfraGO","26C2A-006","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-10",null,null,"5,6",1]
[null,"DB InfraGO","26C2B-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO","26C2B-004","Stuttgart - München","< >","Unterfahlheim","Günzburg",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO","26C2B-006","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO","26C30-001","Stuttgart - München",">","Augsburg Hbf","Gessertshausen",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-25",null,null,"5,6",1]
[null,"DB InfraGO","26C30-003","Stuttgart - München","< >","Augsburg Hirblinger Straße","Gessertshausen",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"5,6",1]
[null,"DB InfraGO","26C30-004","Stuttgart - München","< >","Gessertshausen","Augsburg Hirblinger Straße",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"5,6",1]
[null,"DB InfraGO","26C31-001","Stuttgart - München",">","Augsburg Hbf","Gessertshausen",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"5,6",1]
[null,"DB InfraGO","26C31-003","Stuttgart - München","< >","Augsburg Hirblinger Straße","Gessertshausen",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"5,6",1]
[null,"DB InfraGO","26C31-004","Stuttgart - München","< >","Gessertshausen","Augsburg Hirblinger Straße",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"5,6",1]
[null,"DB InfraGO","26C33-001","Stuttgart - München",">","Dinkelscherben","Burgau (Schwab)",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-25",null,null,"5,6",1]
[null,"DB InfraGO","26C33-002","Stuttgart - München","< >","Burgau (Schwab)","Dinkelscherben",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"5,6",1]
[null,"DB InfraGO","26C34-001","Stuttgart - München",">","Dinkelscherben","Burgau (Schwab)",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"5,6",1]
[null,"DB InfraGO","26C34-002","Stuttgart - München","< >","Burgau (Schwab)","Dinkelscherben",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"5,6",1]
[null,"DB InfraGO","26C8E-001","Stuttgart - München",">","Westheim (Schwab)","Dinkelscherben",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-25",null,null,"6,7",1]
[null,"DB InfraGO","26C8E-003","Stuttgart - München","< >","Dinkelscherben","Westheim (Schwab)",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"6,7",1]
[null,"DB InfraGO","26C91-001","Stuttgart - München",">","Freihalden Üst","Neuoffingen",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"6,7",1]
[null,"DB InfraGO","26C91-003","Stuttgart - München","< >","Neuoffingen","Freihalden Üst",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"6,7",1]
[null,"DB InfraGO","26C9D-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26C9D-004","Stuttgart - München",">","Nersingen","Neu-Ulm",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26C9D-007","Stuttgart - München",">","Unterfahlheim","Nersingen",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26C9D-008","Stuttgart - München","< >","Neu-Ulm","Günzburg",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26C9D-010","Stuttgart - München","< >","Günzburg","Neu-Ulm",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26C9E-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26C9E-004","Stuttgart - München",">","Nersingen","Neu-Ulm",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26C9E-007","Stuttgart - München",">","Unterfahlheim","Nersingen",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26C9E-008","Stuttgart - München","< >","Neu-Ulm","Günzburg",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26C9E-010","Stuttgart - München","< >","Günzburg","Neu-Ulm",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26CC6-001","Stuttgart - München",">","Burgau (Schwab)","Neuoffingen",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26CC6-004","Stuttgart - München",">","Neuoffingen","Günzburg",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26CC6-005","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26CC6-007","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","26CC7-001","Stuttgart - München",">","Burgau (Schwab)","Neuoffingen",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26CC7-004","Stuttgart - München",">","Neuoffingen","Günzburg",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26CC7-005","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","26CC7-007","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,6,1]
[null,"DB InfraGO","27412-001","Stuttgart - München","<","Dinkelscherben","Gessertshausen",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"1,2",1]
[null,"DB InfraGO","27412-003","Stuttgart - München","< >","Gessertshausen","Dinkelscherben",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"1,2",1]
[null,"DB InfraGO","27427-001","Stuttgart - München","<","Neu-Ulm","Nersingen",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27427-002","Stuttgart - München","<","Nersingen","Unterfahlheim",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27427-005","Stuttgart - München","<","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27427-007","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27427-008","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27427-010","Stuttgart - München","< >","Unterfahlheim","Neu-Ulm",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","274A1-001","Stuttgart - München","<","Neuoffingen","Freihalden Üst",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"2,3",1]
[null,"DB InfraGO","274A1-003","Stuttgart - München","< >","Freihalden Üst","Neuoffingen",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"2,3",1]
[null,"DB InfraGO","274A5-001","Stuttgart - München","<","Gessertshausen","Westheim (Schwab)",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"2,3",1]
[null,"DB InfraGO","274A5-003","Stuttgart - München","< >","Westheim (Schwab)","Gessertshausen",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"2,3",1]
[null,"DB InfraGO","274DA-001","Stuttgart - München","<","Unterfahlheim","Günzburg",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","274DA-005","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","274DA-007","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","274ED-001","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","274ED-002","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","274ED-004","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO","27527-001","Stuttgart - München","<","Burgau (Schwab)","Dinkelscherben",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"3,4",1]
[null,"DB InfraGO","27527-003","Stuttgart - München","< >","Dinkelscherben","Burgau (Schwab)",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"3,4",1]
[null,"DB InfraGO","27559-001","Stuttgart - München","<","Günzburg","Neuoffingen",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-23",null,null,"3,4",1]
[null,"DB InfraGO","27559-004","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"3,4",1]
[null,"DB InfraGO","27559-006","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"3,4",1]
[null,"DB InfraGO","27AB4-001","Stuttgart - München",">","Burgau (Schwab)","Unterfahlheim",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27AB4-006","Stuttgart - München","< >","Günzburg","Neuoffingen",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27AB4-008","Stuttgart - München","< >","Neuoffingen","Günzburg",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","2553A-001","Stuttgart - München",">","Augsburg Hbf","Westheim (Schwab)",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","2553A-003","Stuttgart - München","< >","Westheim (Schwab)","Augsburg Hbf",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","2813F-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","2813F-004","Stuttgart - München","< >","Unterfahlheim","Günzburg",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","2813F-006","Stuttgart - München","< >","Günzburg","Unterfahlheim",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","2817B-002","Stuttgart - München",">","Günzburg","Unterfahlheim",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","2817B-004","Stuttgart - München",">","Nersingen","Neu-Ulm",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","2817B-007","Stuttgart - München",">","Unterfahlheim","Nersingen",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","2817B-008","Stuttgart - München","< >","Neu-Ulm","Günzburg",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","2817B-010","Stuttgart - München","< >","Günzburg","Neu-Ulm",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"6,7",1]
[null,"DB InfraGO","28948-004","Stuttgart - München",">","Neu-Ulm","Ulm Hbf Bft Pbf",2024,2024,43,43,"2024-10-23","00:50:00","2024-10-23","04:20:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-06",null,null,3,1]
[null,"DB InfraGO","28948-007","Stuttgart - München","<","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,43,43,"2024-10-24","00:50:00","2024-10-24","04:20:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-06",null,null,4,1]
[null,"DB InfraGO","28948-008","Stuttgart - München","<","Neu-Ulm","Nersingen",2024,2024,43,43,"2024-10-24","00:50:00","2024-10-24","04:20:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-06",null,null,4,1]
[null,"DB InfraGO","28BD7-001","Stuttgart - München","<","Gessertshausen","Augsburg Hbf",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-20",null,null,"3,4",1]
[null,"DB InfraGO","28BD7-006","Stuttgart - München","< >","Augsburg Hbf","Gessertshausen",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-20",null,null,"3,4",1]
[null,"DB InfraGO","26BAC-001","Stuttgart - München",">","Augsburg Hbf","Westheim (Schwab)",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-25",null,null,"4,5",1]
[null,"DB InfraGO","26BAC-004","Stuttgart - München","< >","Westheim (Schwab)","Augsburg Hbf",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-25",null,null,"4,5",1]
[null,"DB InfraGO","29775-001","Stuttgart - München","< >","Augsburg Hbf","Gessertshausen",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-26",null,null,"3,4",1]
[null,"DB InfraGO","29775-004","Stuttgart - München","<","Gessertshausen","Augsburg Hbf",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"3,4",1]
[null,"DB InfraGO","26C9D-011","Stuttgart - München",">","Neu-Ulm","Ulm Hbf Bft Pbf",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-10",null,null,"6,7",1]
[null,"DB InfraGO","29B38-001","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,47,47,"2024-11-20","00:00:00","2024-11-22","04:00:00","2d, 4h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"3,4,5",1]
[null,"DB InfraGO","29B38-002","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,47,47,"2024-11-20","00:00:00","2024-11-22","04:00:00","2d, 4h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"3,4,5",1]
[null,"DB InfraGO","29B38-004","Stuttgart - München","< >","Burgau (Schwab)","Freihalden Üst",2024,2024,47,48,"2024-11-23","00:00:00","2024-11-25","04:00:00","2d, 4h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,6,7",1]
[null,"DB InfraGO","29B38-005","Stuttgart - München",">","Freihalden Üst","Burgau (Schwab)",2024,2024,47,48,"2024-11-23","00:00:00","2024-11-25","04:00:00","2d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-14",null,null,"1,6,7",1]
[null,"DB InfraGO","29B38-006","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,47,48,"2024-11-23","00:00:00","2024-11-25","04:00:00","2d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,6,7",1]
[null,"DB InfraGO","29B38-007","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,48,48,"2024-11-25","23:00:00","2024-11-26","05:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,2",1]
[null,"DB InfraGO","29B38-008","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,48,48,"2024-11-25","23:00:00","2024-11-26","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,2",1]
[null,"DB InfraGO","29B38-010","Stuttgart - München","<","Burgau (Schwab)","Freihalden Üst",2024,2024,48,48,"2024-11-27","00:00:00","2024-11-30","04:00:00","3d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-14",null,null,"3,4,5,6",1]
[null,"DB InfraGO","29B38-011","Stuttgart - München","< >","Burgau (Schwab)","Freihalden Üst",2024,2024,48,48,"2024-11-27","00:00:00","2024-11-30","04:00:00","3d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"3,4,5,6",1]
[null,"DB InfraGO","29B38-013","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,48,48,"2024-11-27","00:00:00","2024-11-30","04:00:00","3d, 4h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"3,4,5,6",1]
[null,"DB InfraGO","29B38-014","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,48,49,"2024-11-30","22:00:00","2024-12-03","04:00:00","2d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,6,7",1]
[null,"DB InfraGO","29B38-015","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2024,2024,48,49,"2024-11-30","22:00:00","2024-12-03","04:00:00","2d, 6h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,6,7",1]
[null,"DB InfraGO","26BAD-001","Stuttgart - München",">","Augsburg Hbf","Westheim (Schwab)",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","26BAD-004","Stuttgart - München","< >","Westheim (Schwab)","Augsburg Hbf",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"4,5",1]
[null,"DB InfraGO","31E28-001","Stuttgart - München","<","Gessertshausen","Augsburg Hirblinger Straße",2024,2024,37,37,"2024-09-12","22:50:00","2024-09-13","05:10:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","31E28-002","Stuttgart - München","<","Westheim (Schwab)","Augsburg Hirblinger Straße",2024,2024,37,37,"2024-09-12","22:50:00","2024-09-13","05:10:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","2ABF2-011","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,43,43,"2024-10-27","03:00:00","2024-10-27","09:00:00","0d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,7,1]
[null,"DB InfraGO","2ABE2-013","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,44,45,"2024-11-01","06:00:00","2024-11-05","06:00:00","4d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","288D3-018","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg Hirblinger Straße",2024,2024,34,37,"2024-08-25","22:00:00","2024-09-13","04:30:00","18d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-10",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","288D3-019","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg Hirblinger Straße",2024,2024,34,37,"2024-08-25","22:00:00","2024-09-13","04:30:00","18d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-10",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","288D3-021","Stuttgart - München","< >","Augsburg Hirblinger Straße","Augsburg-Oberhausen",2024,2024,35,37,"2024-09-01","22:00:00","2024-09-13","04:30:00","11d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-10",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","2AA46-002","Stuttgart - München",">","Augsburg-Oberhausen","Westheim (Schwab)",2024,2024,35,36,"2024-08-31","21:00:00","2024-09-02","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"6,7",1]
[null,"DB InfraGO","2AA46-006","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2024,2024,35,36,"2024-08-31","21:00:00","2024-09-02","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"6,7",1]
[null,"DB InfraGO","2AA46-012","Stuttgart - München",">","Augsburg-Oberhausen","Westheim (Schwab)",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO","2AA46-014","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO","2ABF2-003","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,43,43,"2024-10-21","00:00:00","2024-10-21","06:00:00","0d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,1,1]
[null,"DB InfraGO","2ABF2-007","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,43,43,"2024-10-21","06:00:00","2024-10-27","03:00:00","5d, 22h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2ABE2-007","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,43,44,"2024-10-27","07:00:00","2024-11-01","06:00:00","4d, 23h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO","2ADFC-001","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,45,45,"2024-11-04","13:00:00","2024-11-04","18:00:00","0d, 5h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,1,1]
[null,"DB InfraGO","2ADFC-009","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,45,45,"2024-11-04","18:00:00","2024-11-08","22:00:00","4d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","2ADFC-012","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,45,46,"2024-11-08","22:00:00","2024-11-12","22:00:00","4d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","2ADFC-015","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2024,2024,46,46,"2024-11-12","22:00:00","2024-11-13","06:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"2,3",1]
[null,"DB InfraGO","31E72-017","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg Hbf",2024,2024,36,36,"2024-09-07","22:00:00","2024-09-08","08:00:00","0d, 10h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO","31E72-020","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg Hbf",2024,2024,38,38,"2024-09-21","14:00:00","2024-09-21","22:00:00","0d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,6,1]
[null,"DB InfraGO","1F7BC-019","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-11-24",null,null,"2,3",1]
[null,"DB InfraGO","1F7BC-020","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,43,43,"2024-10-22","21:00:00","2024-10-23","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-11-24",null,null,"2,3",1]
[null,"DB InfraGO","1F7BC-021","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-11-24",null,null,"2,3",1]
[null,"DB InfraGO","20096-013","Karlsruhe - Stuttgart",">","Freiberg (Neckar)","Ludwigsburg",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-01-31",null,null,"3,4",1]
[null,"DB InfraGO","20096-014","Karlsruhe - Stuttgart",">","Freiberg (Neckar)","Ludwigsburg",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-01-31",null,null,"3,4",1]
[null,"DB InfraGO","20096-015","Karlsruhe - Stuttgart",">","Freiberg (Neckar)","Ludwigsburg",2024,2024,47,47,"2024-11-20","21:00:00","2024-11-21","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-01-31",null,null,"3,4",1]
[null,"DB InfraGO","211EA-011","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,46,47,"2024-11-11","01:00:00","2024-11-18","05:00:00","7d, 4h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-11-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","233BA-002","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,37,37,"2024-09-10","21:00:00","2024-09-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"2,3",1]
[null,"DB InfraGO","233BA-004","Karlsruhe - Stuttgart",">","Benningen (Neckar)","Ludwigsburg",2024,2024,37,37,"2024-09-10","21:00:00","2024-09-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-30",null,null,"2,3",1]
[null,"DB InfraGO","233BA-006","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,37,37,"2024-09-10","21:00:00","2024-09-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"2,3",1]
[null,"DB InfraGO","245BA-005","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,39,39,"2024-09-27","21:00:00","2024-09-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-09",null,null,"5,6",1]
[null,"DB InfraGO","245BA-008","Karlsruhe - Stuttgart","< >","Ludwigsburg","Backnang",2024,2024,39,39,"2024-09-27","21:00:00","2024-09-28","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-09",null,null,"5,6",1]
[null,"DB InfraGO","25E41-002","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"2,3",1]
[null,"DB InfraGO","25E41-004","Karlsruhe - Stuttgart",">","Benningen (Neckar)","Ludwigsburg",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-28",null,null,"2,3",1]
[null,"DB InfraGO","25E41-006","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"2,3",1]
[null,"DB InfraGO","2643F-002","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,49,49,"2024-12-03","21:00:00","2024-12-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-20",null,null,"2,3",1]
[null,"DB InfraGO","2643F-004","Karlsruhe - Stuttgart",">","Benningen (Neckar)","Ludwigsburg",2024,2024,49,49,"2024-12-03","21:00:00","2024-12-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-03-20",null,null,"2,3",1]
[null,"DB InfraGO","2643F-006","Karlsruhe - Stuttgart","< >","Backnang","Ludwigsburg",2024,2024,49,49,"2024-12-03","21:00:00","2024-12-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-20",null,null,"2,3",1]
[null,"DB InfraGO","272D6-004","Karlsruhe - Stuttgart","<","Ludwigsburg","Freiberg (Neckar)",2024,2024,47,47,"2024-11-22","21:00:00","2024-11-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-03",null,null,"5,6",1]
[null,"DB InfraGO","272D6-007","Karlsruhe - Stuttgart","< >","Ludwigsburg","Backnang",2024,2024,47,47,"2024-11-22","21:00:00","2024-11-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"5,6",1]
[null,"DB InfraGO","2889C-002","Karlsruhe - Stuttgart","< >","Freiberg (Neckar)","Ludwigsburg",2024,2024,43,44,"2024-10-26","00:40:00","2024-10-28","03:50:00","2d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,6,7",1]
[null,"DB InfraGO","2889C-003","Karlsruhe - Stuttgart","< >","Freiberg (Neckar)","Ludwigsburg",2024,2024,44,44,"2024-10-28","03:50:00","2024-10-29","23:59:00","1d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,2",1]
[null,"DB InfraGO","2889C-004","Karlsruhe - Stuttgart",">","Freiberg (Neckar)","Ludwigsburg",2024,2024,50,50,"2024-12-09","22:10:00","2024-12-10","04:45:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,2",1]
[null,"DB InfraGO","2889C-005","Karlsruhe - Stuttgart","< >","Freiberg (Neckar)","Ludwigsburg",2024,2024,43,44,"2024-10-26","00:40:00","2024-10-28","03:50:00","2d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,6,7",1]
[null,"DB InfraGO","2889C-006","Karlsruhe - Stuttgart","< >","Freiberg (Neckar)","Ludwigsburg",2024,2024,50,50,"2024-12-09","22:10:00","2024-12-10","04:45:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,2",1]
[null,"DB InfraGO","31FB-001","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,38,39,"2024-09-20","00:01:00","2024-09-23","23:59:00","3d, 23h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,5,6,7",1]
[null,"DB InfraGO","31FB-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,39,39,"2024-09-23","22:00:00","2024-09-27","04:00:00","3d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,2,3,4",1]
[null,"DB InfraGO","3203-001","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,47,48,"2024-11-22","22:00:00","2024-11-30","05:00:00","7d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3203-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,48,49,"2024-11-29","21:00:00","2024-12-02","05:00:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"5,6,7",1]
[null,"DB InfraGO","222FF-003","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2024,2024,38,38,"2024-09-22","03:00:00","2024-09-22","04:30:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-05",null,null,7,1]
[null,"DB InfraGO","222FF-005","Gemünden - Bamberg - Nürnberg","<","Breitengüßbach Süd","Bamberg",2024,2024,38,38,"2024-09-22","00:00:00","2024-09-22","02:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-05",null,null,7,1]
[null,"DB InfraGO","2294A-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Hallstadt (b Bamberg)",2024,2024,38,38,"2024-09-20","01:00:00","2024-09-20","05:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-05",null,null,5,1]
[null,"DB InfraGO","22A45-002","Gemünden - Bamberg - Nürnberg","<","Breitengüßbach Süd","Bamberg",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-24",null,null,"3,4",1]
[null,"DB InfraGO","22A45-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-01-24",null,null,"3,4",1]
[null,"DB InfraGO","23D65-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","23FCE-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Unterleiterbach",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-06",null,null,"4,5",1]
[null,"DB InfraGO","23FCE-003","Gemünden - Bamberg - Nürnberg","< >","Unterleiterbach","Bamberg",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"4,5",1]
[null,"DB InfraGO","24EB2-001","Gemünden - Bamberg - Nürnberg","<","Breitengüßbach Süd","Bamberg",2024,2024,40,40,"2024-10-02","21:15:00","2024-10-03","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","24EB2-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2024,2024,40,40,"2024-10-02","21:15:00","2024-10-03","05:00:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","26C60-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"6,7",1]
[null,"DB InfraGO","27937-004","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"6,7",1]
[null,"DB InfraGO","2FC9-032","Gemünden - Bamberg - Nürnberg","< >","Oberhaid","Oberhaid",2024,2024,47,48,"2024-11-22","22:00:00","2024-11-25","05:00:00","2d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-07-07",null,null,"1,5,6,7",1]
[null,"DB InfraGO","2FC9-033","Gemünden - Bamberg - Nürnberg","< >","Oberhaid","Oberhaid",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-30","05:00:00","4d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-27",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","D7F5-003","Gemünden - Bamberg - Nürnberg",">","Ebelsbach-Eltmann","Zeil",2024,2024,42,42,"2024-10-15","00:00:00","2024-10-15","03:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2023-02-28",null,null,2,1]
[null,"DB InfraGO","D7F5-004","Gemünden - Bamberg - Nürnberg","<","Zeil","Ebelsbach-Eltmann",2024,2024,42,42,"2024-10-15","03:00:00","2024-10-15","06:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2023-02-28",null,null,2,1]
[null,"DB InfraGO","D7F5-006","Gemünden - Bamberg - Nürnberg","<","Haßfurt","Zeil",2024,2024,42,42,"2024-10-15","23:00:00","2024-10-16","01:15:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-03-18",null,null,"2,3",1]
[null,"DB InfraGO","D7F5-007","Gemünden - Bamberg - Nürnberg",">","Zeil","Haßfurt",2024,2024,42,42,"2024-10-16","01:15:00","2024-10-16","03:30:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2023-02-28",null,null,3,1]
[null,"DB InfraGO","D7F5-009","Gemünden - Bamberg - Nürnberg",">","Gädheim","Schweinfurt Stadt",2024,2024,42,42,"2024-10-16","23:30:00","2024-10-17","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2023-02-28",null,null,"3,4",1]
[null,"DB InfraGO","D7F5-010","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Gädheim",2024,2024,42,42,"2024-10-17","23:30:00","2024-10-18","04:30:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2023-02-28",null,null,"4,5",1]
[null,"DB InfraGO","22B5D-001","Gemünden - Bamberg - Nürnberg","<","Rottendorf","Waigolshausen",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-01-30",null,null,"3,4",1]
[null,"DB InfraGO","22EEA-001","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Gädheim",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-01-30",null,null,"2,3",1]
[null,"DB InfraGO","22FA8-001","Gemünden - Bamberg - Nürnberg","<","Oberhaid","Bamberg",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-01-24",null,null,"3,4",1]
[null,"DB InfraGO","22FA8-002","Gemünden - Bamberg - Nürnberg",">","Bamberg","Oberhaid",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-24",null,null,"3,4",1]
[null,"DB InfraGO","2302B-001","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-01-30",null,null,"3,4",1]
[null,"DB InfraGO","230A3-001","Gemünden - Bamberg - Nürnberg","<","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-01-30",null,null,"1,2",1]
[null,"DB InfraGO","230ED-001","Gemünden - Bamberg - Nürnberg","<","Zeil","Oberhaid",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-24",null,null,"2,3",1]
[null,"DB InfraGO","2311A-001","Gemünden - Bamberg - Nürnberg","<","Gädheim","Ebelsbach-Eltmann",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,null,"N",null,"2024-01-30",null,null,"1,2",1]
[null,"DB InfraGO","237FF-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Haßfurt",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-02-09",null,null,"6,7",1]
[null,"DB InfraGO","238C2-001","Gemünden - Bamberg - Nürnberg",">","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2024,2024,38,38,"2024-09-19","21:10:00","2024-09-20","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-02-09",null,null,"4,5",1]
[null,"DB InfraGO","23B6B-001","Gemünden - Bamberg - Nürnberg",">","Haßfurt","Schweinfurt Hbf",2024,2024,38,38,"2024-09-20","21:20:00","2024-09-21","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-02-23",null,null,"5,6",1]
[null,"DB InfraGO","23B6E-001","Gemünden - Bamberg - Nürnberg",">","Gädheim","Waigolshausen",2024,2024,38,38,"2024-09-21","21:15:00","2024-09-22","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-02-09",null,null,"6,7",1]
[null,"DB InfraGO","23CD3-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Ebelsbach-Eltmann",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-09",null,null,"5,6",1]
[null,"DB InfraGO","23CD3-002","Gemünden - Bamberg - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-09",null,null,"5,6",1]
[null,"DB InfraGO","23D65-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Oberhaid",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","23D65-003","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"6,7",1]
[null,"DB InfraGO","23DDD-001","Gemünden - Bamberg - Nürnberg",">","Zeil","Gädheim",2024,2024,38,38,"2024-09-19","21:10:00","2024-09-20","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-02-09",null,null,"4,5",1]
[null,"DB InfraGO","23DE6-001","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Rottendorf",2024,2024,38,38,"2024-09-20","21:15:00","2024-09-21","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-02-09",null,null,"5,6",1]
[null,"DB InfraGO","246A5-001","Gemünden - Bamberg - Nürnberg","<","Waigolshausen","Gädheim",2024,2024,40,40,"2024-10-01","21:10:00","2024-10-02","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-02-19",null,null,"2,3",1]
[null,"DB InfraGO","246D7-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Bamberg",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","04:50:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","246D7-002","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","04:50:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","24A56-001","Gemünden - Bamberg - Nürnberg",">","Zeil","Oberhaid",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-02-19",null,null,"2,3",1]
[null,"DB InfraGO","24A8F-001","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2024,2024,40,40,"2024-10-02","21:15:00","2024-10-03","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-02-19",null,null,"3,4",1]
[null,"DB InfraGO","24AB0-001","Gemünden - Bamberg - Nürnberg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-02-19",null,null,"1,2",1]
[null,"DB InfraGO","24E10-001","Gemünden - Bamberg - Nürnberg","<","Gädheim","Ebelsbach-Eltmann",2024,2024,40,40,"2024-09-30","21:20:00","2024-10-01","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-19",null,null,"1,2",1]
[null,"DB InfraGO","24E9F-001","Gemünden - Bamberg - Nürnberg","<","Rottendorf","Waigolshausen",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-02-19",null,null,"3,4",1]
[null,"DB InfraGO","25C65-001","Gemünden - Bamberg - Nürnberg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-03-18",null,null,"1,2",1]
[null,"DB InfraGO","25CA3-001","Gemünden - Bamberg - Nürnberg","<","Gädheim","Ebelsbach-Eltmann",2024,2024,44,44,"2024-10-28","21:20:00","2024-10-29","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2024-03-18",null,null,"1,2",1]
[null,"DB InfraGO","25CA7-001","Gemünden - Bamberg - Nürnberg",">","Zeil","Oberhaid",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-03-18",null,null,"2,3",1]
[null,"DB InfraGO","25CE5-001","Gemünden - Bamberg - Nürnberg","<","Waigolshausen","Gädheim",2024,2024,44,44,"2024-10-29","21:10:00","2024-10-30","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-18",null,null,"2,3",1]
[null,"DB InfraGO","25CE9-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Bamberg",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","04:50:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-19",null,null,"3,4",1]
[null,"DB InfraGO","25CE9-002","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","04:50:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-19",null,null,"3,4",1]
[null,"DB InfraGO","25CFF-001","Gemünden - Bamberg - Nürnberg","<","Rottendorf","Waigolshausen",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-03-18",null,null,"3,4",1]
[null,"DB InfraGO","25D26-001","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2024,2024,44,44,"2024-10-30","21:15:00","2024-10-31","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-18",null,null,"3,4",1]
[null,"DB InfraGO","261A3-001","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Rottendorf",2024,2024,42,42,"2024-10-18","21:15:00","2024-10-19","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-04",null,null,"5,6",1]
[null,"DB InfraGO","26214-001","Gemünden - Bamberg - Nürnberg",">","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2024,2024,42,42,"2024-10-17","21:10:00","2024-10-18","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-04",null,null,"4,5",1]
[null,"DB InfraGO","26227-001","Gemünden - Bamberg - Nürnberg",">","Haßfurt","Schweinfurt Hbf",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-03-04",null,null,"5,6",1]
[null,"DB InfraGO","26BC2-001","Gemünden - Bamberg - Nürnberg",">","Zeil","Gädheim",2024,2024,46,46,"2024-11-14","21:10:00","2024-11-15","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","26BC5-001","Gemünden - Bamberg - Nürnberg",">","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2024,2024,46,46,"2024-11-14","21:10:00","2024-11-15","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","26BC8-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Ebelsbach-Eltmann",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-04-09",null,null,"5,6",1]
[null,"DB InfraGO","26BC8-002","Gemünden - Bamberg - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","26C57-001","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Rottendorf",2024,2024,46,46,"2024-11-15","21:15:00","2024-11-16","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","26C5A-001","Gemünden - Bamberg - Nürnberg",">","Haßfurt","Schweinfurt Hbf",2024,2024,46,46,"2024-11-15","21:20:00","2024-11-16","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","26C60-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Oberhaid",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-04-03",null,null,"6,7",1]
[null,"DB InfraGO","26C60-003","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"6,7",1]
[null,"DB InfraGO","26C63-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Haßfurt",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-03-28",null,null,"6,7",1]
[null,"DB InfraGO","26CEA-001","Gemünden - Bamberg - Nürnberg",">","Gädheim","Waigolshausen",2024,2024,46,46,"2024-11-16","21:15:00","2024-11-17","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-03-28",null,null,"6,7",1]
[null,"DB InfraGO","27408-001","Gemünden - Bamberg - Nürnberg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","2747B-001","Gemünden - Bamberg - Nürnberg","<","Gädheim","Ebelsbach-Eltmann",2024,2024,48,48,"2024-11-25","21:20:00","2024-11-26","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"15,,",null,null,null,"N",null,"2024-04-11",null,null,"1,2",1]
[null,"DB InfraGO","27485-001","Gemünden - Bamberg - Nürnberg",">","Zeil","Oberhaid",2024,2024,48,48,"2024-11-26","21:00:00","2024-11-27","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","274F3-001","Gemünden - Bamberg - Nürnberg","<","Waigolshausen","Gädheim",2024,2024,48,48,"2024-11-26","21:10:00","2024-11-27","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-28",null,null,"2,3",1]
[null,"DB InfraGO","274FB-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Bamberg",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","04:50:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-04-03",null,null,"3,4",1]
[null,"DB InfraGO","274FB-002","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","04:50:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"3,4",1]
[null,"DB InfraGO","27525-001","Gemünden - Bamberg - Nürnberg","<","Rottendorf","Waigolshausen",2024,2024,48,48,"2024-11-27","21:00:00","2024-11-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-03-28",null,null,"3,4",1]
[null,"DB InfraGO","27570-001","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2024,2024,48,48,"2024-11-27","21:15:00","2024-11-28","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-28",null,null,"3,4",1]
[null,"DB InfraGO","2761C-001","Gemünden - Bamberg - Nürnberg",">","Oberhaid","Ebelsbach-Eltmann",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-04",null,null,"5,6",1]
[null,"DB InfraGO","2761C-002","Gemünden - Bamberg - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-04",null,null,"5,6",1]
[null,"DB InfraGO","27777-001","Gemünden - Bamberg - Nürnberg",">","Gädheim","Waigolshausen",2024,2024,42,42,"2024-10-19","21:15:00","2024-10-20","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,,12",null,null,null,"N",null,"2024-03-04",null,null,"6,7",1]
[null,"DB InfraGO","27937-001","Gemünden - Bamberg - Nürnberg",">","Bamberg","Oberhaid",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","04:45:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-03-06",null,null,"6,7",1]
[null,"DB InfraGO","27937-003","Gemünden - Bamberg - Nürnberg","< >","Bamberg","Oberhaid",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"6,7",1]
[null,"DB InfraGO","298AB-001","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Stadt","Schweinfurt Hbf",2024,2024,47,47,"2024-11-22","22:00:00","2024-11-23","05:00:00","0d, 7h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-02-22",null,null,"5,6",1]
[null,"DB InfraGO","298AB-003","Gemünden - Bamberg - Nürnberg",">","Gädheim","Schweinfurt Hbf",2024,2024,47,47,"2024-11-23","22:00:00","2024-11-24","05:00:00","0d, 7h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-02-22",null,null,"6,7",1]
[null,"DB InfraGO","298AB-006","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Stadt","Schweinfurt Hbf",2024,2024,47,47,"2024-11-23","01:30:00","2024-11-24","05:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-22",null,null,"6,7",1]
[null,"DB InfraGO","3360F-001","Gemünden - Bamberg - Nürnberg","<","Ebelsbach-Eltmann","Oberhaid",2024,2024,36,36,"2024-09-05","02:40:00","2024-09-05","04:40:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,",null,null,null,"N",null,"2024-07-26",null,null,4,1]
[null,"DB InfraGO","3360F-002","Gemünden - Bamberg - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2024,2024,36,36,"2024-09-05","02:40:00","2024-09-05","04:40:00","0d, 2h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,4,1]
[null,"DB InfraGO","320F-026","Nürnberg - Regensburg","< >","Feucht","Feucht",2024,2024,46,46,"2024-11-16","23:00:00","2024-11-17","05:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-15",null,null,"6,7",1]
[null,"DB InfraGO","2B310-005","Nürnberg - Regensburg",">","Nürnberg Frankenstadion","Feucht",2024,2024,37,37,"2024-09-10","01:30:00","2024-09-10","04:30:00","0d, 3h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,20",null,null,null,"N",null,"2024-05-14",null,null,2,1]
[null,"DB InfraGO","2B3D5-002","Nürnberg - Regensburg","< >","Feucht","Feucht",2024,2024,37,37,"2024-09-11","01:30:00","2024-09-11","02:30:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,3,1]
[null,"DB InfraGO","2BE45-001","Nürnberg - Regensburg","< >","Nürnberg-Dutzendteich","Nürnberg Frankenstadion",2024,2024,37,37,"2024-09-11","02:45:00","2024-09-11","04:15:00","0d, 1h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,3,1]
[null,"DB InfraGO","2BE45-002","Nürnberg - Regensburg","< >","Nürnberg-Dutzendteich","Nürnberg Frankenstadion",2024,2024,37,37,"2024-09-11","02:45:00","2024-09-11","04:15:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,3,1]
[null,"DB InfraGO","2BF61-001","Nürnberg - Regensburg","<","Feucht","Nürnberg Frankenstadion",2024,2024,38,38,"2024-09-18","02:00:00","2024-09-18","04:30:00","0d, 2h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,20",null,null,null,"N",null,"2024-05-15",null,null,3,1]
[null,"DB InfraGO","24904-010","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-21",null,null,"4,5",1]
[null,"DB InfraGO","26BBF-009","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-10",null,null,"4,5",1]
[null,"DB InfraGO","26BC0-005","Stuttgart - München","< >","Neuoffingen","Gundelfingen (Bay)",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"4,5",1]
[null,"DB InfraGO","26BC0-009","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,50,50,"2024-12-12","21:00:00","2024-12-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","27AB4-009","Stuttgart - München","< >","Neuoffingen","Neuoffingen",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","18430-034","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,47,48,"2024-11-19","15:00:00","2024-11-26","18:00:00","7d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2CAF-005","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,45,45,"2024-11-07","00:00:00","2024-11-07","05:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,4,1]
[null,"DB InfraGO","2CAF-006","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,44,44,"2024-10-31","00:00:00","2024-10-31","05:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,4,1]
[null,"DB InfraGO","2CAF-007","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"1,6,7",1]
[null,"DB InfraGO","2CAF-008","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,6,7",1]
[null,"DB InfraGO","2CAF-009","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,45,45,"2024-11-04","05:00:00","2024-11-05","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2023-08-30",null,null,"1,2",1]
[null,"DB InfraGO","692F-006","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,46,46,"2024-11-14","07:00:00","2024-11-14","11:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-18",null,null,4,1]
[null,"DB InfraGO","692F-014","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,46,47,"2024-11-17","23:00:00","2024-11-18","03:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-18",null,null,"1,7",1]
[null,"DB InfraGO","27848-002","München - Salzburg","< >","München-Trudering","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,6,7",1]
[null,"DB InfraGO","27848-004","München - Salzburg","< >","München Ost Rbf","München-Trudering",2024,2024,44,45,"2024-11-02","00:00:00","2024-11-04","05:00:00","2d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,6,7",1]
[null,"DB InfraGO","15DEF-009","Stuttgart - München","< >","München Süd","München Süd",2024,2024,42,42,"2024-10-15","07:00:00","2024-10-17","20:00:00","2d, 13h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"2,3,4",1]
[null,"DB InfraGO","15DEF-010","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,43,"2024-10-21","00:00:00","2024-10-21","04:00:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,1,1]
[null,"DB InfraGO","15DEF-013","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,43,"2024-10-21","23:00:00","2024-10-22","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"1,2",1]
[null,"DB InfraGO","15DEF-014","Stuttgart - München",">","München Friedenheimer Brücke","München Süd",2024,2024,43,43,"2024-10-21","23:00:00","2024-10-22","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-04-21",null,null,"1,2",1]
[null,"DB InfraGO","15DEF-017","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,43,"2024-10-23","23:00:00","2024-10-24","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"3,4",1]
[null,"DB InfraGO","15DEF-019","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"4,5",1]
[null,"DB InfraGO","15DEF-020","Stuttgart - München",">","München Friedenheimer Brücke","München Süd",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-04-21",null,null,"4,5",1]
[null,"DB InfraGO","15DEF-023","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,43,"2024-10-25","00:00:00","2024-10-25","03:00:00","0d, 3h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,5,1]
[null,"DB InfraGO","15DEF-025","Stuttgart - München","< >","München Süd","München Süd",2024,2024,43,44,"2024-10-27","23:00:00","2024-10-28","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"1,7",1]
[null,"DB InfraGO","15DEF-026","Stuttgart - München",">","München Friedenheimer Brücke","München Süd",2024,2024,43,44,"2024-10-27","23:00:00","2024-10-28","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-04-21",null,null,"1,7",1]
[null,"DB InfraGO","15DEF-028","Stuttgart - München","< >","München Süd","München Süd",2024,2024,44,44,"2024-10-28","23:00:00","2024-10-29","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"1,2",1]
[null,"DB InfraGO","15DEF-030","Stuttgart - München","< >","München Süd","München Süd",2024,2024,46,47,"2024-11-17","23:00:00","2024-11-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-21",null,null,"1,7",1]
[null,"DB InfraGO","1AD68-002","Stuttgart - München","<","München-Pasing","München-Laim Rbf",2024,2024,41,42,"2024-10-11","22:00:00","2024-10-14","05:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-09-07",null,null,"1,5,6,7",1]
[null,"DB InfraGO","942F-009","München - Salzburg","< >","Rosenheim Süd","Rosenheim Ost",2024,2024,44,44,"2024-11-02","03:30:00","2024-11-02","04:50:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-19",null,null,6,1]
[null,"DB InfraGO","47D1-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,40,41,"2024-10-06","21:00:00","2024-10-07","23:30:00","1d, 2h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-09-20",null,null,"1,7",1]
[null,"DB InfraGO","47D1-003","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,41,41,"2024-10-07","02:30:00","2024-10-08","05:00:00","1d, 2h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-09-20",null,null,"1,2",1]
[null,"DB InfraGO","47D2-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,40,41,"2024-10-06","21:00:00","2024-10-07","23:30:00","1d, 2h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-09-20",null,null,"1,7",1]
[null,"DB InfraGO","47D2-002","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,41,41,"2024-10-07","02:30:00","2024-10-08","05:00:00","1d, 2h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-09-20",null,null,"1,2",1]
[null,"DB InfraGO","505D-013","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,34,39,"2024-08-19","08:00:00","2024-09-28","16:00:00","40d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1EED4-029","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,37,37,"2024-09-10","21:00:00","2024-09-11","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO","1EED4-030","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO","1EED4-031","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,46,46,"2024-11-12","21:00:00","2024-11-13","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO","1EF67-028","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,37,37,"2024-09-11","21:00:00","2024-09-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"3,4",1]
[null,"DB InfraGO","1EF67-029","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-30","21:00:00","2024-10-31","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"3,4",1]
[null,"DB InfraGO","1EF67-030","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"3,4",1]
[null,"DB InfraGO","1F06C-015","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","1F06C-016","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","1F06C-017","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","1F06C-023","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","1F06C-024","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","1F06C-025","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"4,5",1]
[null,"DB InfraGO","25F6F-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,38,38,"2024-09-18","21:00:00","2024-09-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-02-05",null,null,"3,4",1]
[null,"DB InfraGO","25F6F-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,38,38,"2024-09-18","21:00:00","2024-09-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"3,4",1]
[null,"DB InfraGO","25F74-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,42,42,"2024-10-16","21:00:00","2024-10-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-03-01",null,null,"3,4",1]
[null,"DB InfraGO","25F74-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,42,42,"2024-10-16","21:00:00","2024-10-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"3,4",1]
[null,"DB InfraGO","25F7B-001","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,36,36,"2024-09-05","21:00:00","2024-09-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-01-22",null,null,"4,5",1]
[null,"DB InfraGO","25F7B-002","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,36,36,"2024-09-05","21:00:00","2024-09-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"4,5",1]
[null,"DB InfraGO","25F84-001","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-19",null,null,"4,5",1]
[null,"DB InfraGO","25F84-002","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-19",null,null,"4,5",1]
[null,"DB InfraGO","26AB9-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","26AB9-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","26ABA-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,50,50,"2024-12-11","21:00:00","2024-12-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-29",null,null,"3,4",1]
[null,"DB InfraGO","26ABA-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Walheim (Württ)",2024,2024,50,50,"2024-12-11","21:00:00","2024-12-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"3,4",1]
[null,"DB InfraGO","2760C-001","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,48,48,"2024-11-28","21:00:00","2024-11-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","2760C-002","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,48,48,"2024-11-28","21:00:00","2024-11-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","28CC6-002","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-03-18",null,null,"4,5",1]
[null,"DB InfraGO","28CC6-003","Karlsruhe - Stuttgart","<","Walheim (Württ)","Bietigheim-Bissingen",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-18",null,null,"4,5",1]
[null,"DB InfraGO","22B47-001","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","22B47-002","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","22B47-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-02",null,null,"4,5",1]
[null,"DB InfraGO","24461-001","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","24461-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","24461-005","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","2555F-001","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","2555F-002","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","2555F-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO","265E3-001","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265E3-002","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265E3-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","265E4-001","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"4,5",1]
[null,"DB InfraGO","265E4-002","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"4,5",1]
[null,"DB InfraGO","265E4-005","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"4,5",1]
[null,"DB InfraGO","26EA8-001","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"1,2",1]
[null,"DB InfraGO","26EA8-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-16",null,null,"1,2",1]
[null,"DB InfraGO","26EA8-005","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-16",null,null,"1,2",1]
[null,"DB InfraGO","28136-001","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,43,43,"2024-10-21","21:00:00","2024-10-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","28136-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,43,43,"2024-10-21","21:00:00","2024-10-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","28136-005","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,43,43,"2024-10-21","21:00:00","2024-10-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","289D3-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-31","05:00:00","2d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-21",null,null,"1,2,3",1]
[null,"DB InfraGO","28A0C-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2024,2024,47,48,"2024-11-23","21:00:00","2024-11-26","05:00:00","2d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-21",null,null,"1,6,7",1]
[null,"DB InfraGO","29E0A-026","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-30","23:55:00","2024-12-01","07:00:00","0d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-028","Mannheim - Karlsruhe",">","Bruchsal","Graben-Neudorf",2024,2024,48,48,"2024-11-30","23:55:00","2024-12-01","07:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-08",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-029","Mannheim - Karlsruhe","< >","Graben-Neudorf","Philippsburg (Baden)",2024,2024,48,48,"2024-11-30","23:55:00","2024-12-01","07:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-030","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-30","23:55:00","2024-12-01","07:00:00","0d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-032","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,49,"2024-12-01","23:55:00","2024-12-02","04:45:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"1,7",1]
[null,"DB InfraGO","29E0A-034","Mannheim - Karlsruhe","< >","Graben-Neudorf","Philippsburg (Baden)",2024,2024,48,49,"2024-12-01","23:55:00","2024-12-02","04:45:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"1,7",1]
[null,"DB InfraGO","2F10E-003","Mannheim - Karlsruhe","< >","Graben-Neudorf","Philippsburg Molzau",2024,2024,39,39,"2024-09-27","22:00:00","2024-09-28","02:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-04",null,null,"5,6",1]
[null,"DB InfraGO","4AC7-002","Regensburg - Plzen","< >","Cham (Oberpf) Schwedenschanze","Bad Kötzting",2024,2024,42,44,"2024-10-16","02:00:00","2024-11-03","04:40:00","18d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2DB97-002","Regensburg - Plzen","< >","Cham (Oberpf) Schwedenschanze","Chamerau",2024,2024,40,40,"2024-09-30","23:50:00","2024-10-06","04:50:00","5d, 5h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO","1FCF4-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,37,37,"2024-09-12","21:15:00","2024-09-13","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-01-19",null,null,"4,5",1]
[null,"DB InfraGO","1FCF4-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,37,37,"2024-09-12","21:15:00","2024-09-13","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"34,34,34",null,null,null,"N",null,"2024-01-19",null,null,"4,5",1]
[null,"DB InfraGO","1FCF4-003","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Aschaffenburg Hbf",2024,2024,37,37,"2024-09-12","21:15:00","2024-09-13","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"4,5",1]
[null,"DB InfraGO","1FCF5-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,41,41,"2024-10-10","21:15:00","2024-10-11","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCF5-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,41,41,"2024-10-10","21:15:00","2024-10-11","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"34,34,34",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCF5-003","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Aschaffenburg Hbf",2024,2024,41,41,"2024-10-10","21:15:00","2024-10-11","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCF6-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,45,45,"2024-11-07","21:15:00","2024-11-08","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCF6-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,45,45,"2024-11-07","21:15:00","2024-11-08","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"34,34,34",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCF6-003","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Aschaffenburg Hbf",2024,2024,45,45,"2024-11-07","21:15:00","2024-11-08","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","1FCFC-001","Darmstadt - Aschaffenburg",">","Dieburg","Aschaffenburg Hbf",2024,2024,37,37,"2024-09-12","21:10:00","2024-09-13","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"36,36,36",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFC-002","Darmstadt - Aschaffenburg",">","Dieburg","Kleinostheim",2024,2024,37,37,"2024-09-12","21:10:00","2024-09-13","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"42,42,42",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFC-004","Darmstadt - Aschaffenburg","< >","Dieburg","Stockstadt (Main)",2024,2024,37,37,"2024-09-12","21:10:00","2024-09-13","05:10:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFD-001","Darmstadt - Aschaffenburg",">","Dieburg","Stockstadt (Main)",2024,2024,41,41,"2024-10-10","21:10:00","2024-10-11","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"30,30,30",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFD-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,41,41,"2024-10-10","21:10:00","2024-10-11","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"42,42,42",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFD-004","Darmstadt - Aschaffenburg","< >","Dieburg","Stockstadt (Main)",2024,2024,41,41,"2024-10-10","21:10:00","2024-10-11","05:10:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFE-001","Darmstadt - Aschaffenburg",">","Dieburg","Stockstadt (Main)",2024,2024,45,45,"2024-11-07","21:10:00","2024-11-08","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"30,30,30",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFE-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,45,45,"2024-11-07","21:10:00","2024-11-08","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"42,42,42",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFE-004","Darmstadt - Aschaffenburg","< >","Dieburg","Stockstadt (Main)",2024,2024,45,45,"2024-11-07","21:10:00","2024-11-08","05:10:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD21-001","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,37,37,"2024-09-12","20:50:00","2024-09-13","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD21-002","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,37,37,"2024-09-12","20:50:00","2024-09-13","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD22-001","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,41,41,"2024-10-10","20:50:00","2024-10-11","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD22-002","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,41,41,"2024-10-10","20:50:00","2024-10-11","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD23-001","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,45,45,"2024-11-07","20:50:00","2024-11-08","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD23-002","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,45,45,"2024-11-07","20:50:00","2024-11-08","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FE20-001","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Babenhausen (Hess)",2024,2024,39,39,"2024-09-23","20:20:00","2024-09-24","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-05-03",null,null,"1,2",1]
[null,"DB InfraGO","1FE20-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,39,39,"2024-09-23","20:20:00","2024-09-24","04:40:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-19",null,null,"1,2",1]
[null,"DB InfraGO","1FE23-001","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Babenhausen (Hess)",2024,2024,47,47,"2024-11-18","20:20:00","2024-11-19","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-05-03",null,null,"1,2",1]
[null,"DB InfraGO","1FE23-003","Darmstadt - Aschaffenburg","< >","Aschaffenburg Hbf","Babenhausen (Hess)",2024,2024,47,47,"2024-11-18","20:20:00","2024-11-19","04:40:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","1FE4B-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,39,39,"2024-09-25","20:40:00","2024-09-26","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-03-20",null,null,"3,4",1]
[null,"DB InfraGO","1FE4B-003","Darmstadt - Aschaffenburg","<","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,39,39,"2024-09-25","20:40:00","2024-09-26","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","1FE4C-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,43,43,"2024-10-23","20:40:00","2024-10-24","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","1FE4C-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,43,43,"2024-10-23","20:40:00","2024-10-24","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","1FE4D-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,47,47,"2024-11-20","20:40:00","2024-11-21","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","1FE69-001","Darmstadt - Aschaffenburg","< >","Stockstadt (Main)","Dieburg",2024,2024,39,39,"2024-09-24","20:45:00","2024-09-25","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE6A-001","Darmstadt - Aschaffenburg","< >","Stockstadt (Main)","Dieburg",2024,2024,43,43,"2024-10-22","20:45:00","2024-10-23","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE6C-001","Darmstadt - Aschaffenburg","< >","Stockstadt (Main)","Dieburg",2024,2024,47,47,"2024-11-19","20:45:00","2024-11-20","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE1A-008","Darmstadt - Aschaffenburg","< >","Darmstadt-Kranichstein","Darmstadt Hbf",2024,2024,39,39,"2024-09-24","00:50:00","2024-09-24","04:50:00","0d, 4h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,2,1]
[null,"DB InfraGO","1FE1C-007","Darmstadt - Aschaffenburg","< >","Darmstadt-Kranichstein","Darmstadt Gbf",2024,2024,47,47,"2024-11-19","00:50:00","2024-11-19","04:50:00","0d, 4h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,2,1]
[null,"DB InfraGO","24CC0-001","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Babenhausen (Hess)",2024,2024,43,43,"2024-10-21","20:20:00","2024-10-22","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"22,22,22",null,null,null,"N",null,"2024-05-03",null,null,"1,2",1]
[null,"DB InfraGO","24CC0-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,43,43,"2024-10-21","20:20:00","2024-10-22","04:40:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","1FF5E-005","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Kahl (Main)",2024,2024,44,44,"2024-11-02","22:00:00","2024-11-03","06:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"39,39,39",null,null,null,"N",null,"2024-02-05",null,null,"6,7",1]
[null,"DB InfraGO","1FE4D-005","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Darmstadt-Kranichstein",2024,2024,47,47,"2024-11-20","20:40:00","2024-11-21","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","1FE1C-008","Darmstadt - Aschaffenburg","< >","Darmstadt Gbf","Darmstadt-Kranichstein",2024,2024,47,47,"2024-11-19","00:50:00","2024-11-19","04:50:00","0d, 4h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,2,1]
[null,"DB InfraGO","29489-001","Darmstadt - Aschaffenburg",">","Darmstadt Hbf","Darmstadt Nord",2024,2024,47,47,"2024-11-18","23:00:00","2024-11-19","05:00:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-27",null,null,"1,2",1]
[null,"DB InfraGO","29489-004","Darmstadt - Aschaffenburg",">","Darmstadt Hbf","Darmstadt Gbf",2024,2024,47,47,"2024-11-18","23:00:00","2024-11-19","05:00:00","0d, 6h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-27",null,null,"1,2",1]
[null,"DB InfraGO","1FF5F-005","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Kahl (Main)",2024,2024,48,48,"2024-11-30","22:00:00","2024-12-01","06:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"39,39,39",null,null,null,"N",null,"2024-02-02",null,null,"6,7",1]
[null,"DB InfraGO","1FE1A-009","Darmstadt - Aschaffenburg","< >","Darmstadt Gbf","Darmstadt-Kranichstein",2024,2024,39,39,"2024-09-24","00:50:00","2024-09-24","04:50:00","0d, 4h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,2,1]
[null,"DB InfraGO","29BAD-001","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,49,49,"2024-12-05","20:50:00","2024-12-06","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","29BAD-002","Darmstadt - Aschaffenburg",">","Darmstadt Gbf","Dieburg",2024,2024,49,49,"2024-12-05","20:50:00","2024-12-06","04:50:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","29BAE-001","Darmstadt - Aschaffenburg",">","Dieburg","Stockstadt (Main)",2024,2024,49,49,"2024-12-05","21:10:00","2024-12-06","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"30,30,30",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","29BAE-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,49,49,"2024-12-05","21:10:00","2024-12-06","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"42,42,42",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","29BAE-004","Darmstadt - Aschaffenburg","< >","Dieburg","Stockstadt (Main)",2024,2024,49,49,"2024-12-05","21:10:00","2024-12-06","05:10:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","29BAF-001","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Aschaffenburg Hbf",2024,2024,49,49,"2024-12-05","21:15:00","2024-12-06","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","29BAF-002","Darmstadt - Aschaffenburg",">","Babenhausen (Hess)","Kleinostheim",2024,2024,49,49,"2024-12-05","21:15:00","2024-12-06","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"34,34,34",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","29BAF-003","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Aschaffenburg Hbf",2024,2024,49,49,"2024-12-05","21:15:00","2024-12-06","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","30488-001","Darmstadt - Aschaffenburg","< >","Aschaffenburg Hbf","Aschaffenburg Hbf",2024,2024,40,40,"2024-09-30","08:00:00","2024-10-01","10:15:00","1d, 2h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2",1]
[null,"DB InfraGO","1FE4F-014","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2024,2024,43,43,"2024-10-22","21:20:00","2024-10-23","05:20:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FE50-009","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2024,2024,47,47,"2024-11-19","21:20:00","2024-11-20","05:20:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","1FD21-003","Darmstadt - Aschaffenburg","< >","Darmstadt Nord","Darmstadt Ost",2024,2024,37,37,"2024-09-12","20:50:00","2024-09-13","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD22-003","Darmstadt - Aschaffenburg","< >","Darmstadt Nord","Darmstadt Ost",2024,2024,41,41,"2024-10-10","20:50:00","2024-10-11","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FD23-003","Darmstadt - Aschaffenburg","< >","Darmstadt Nord","Darmstadt Ost",2024,2024,45,45,"2024-11-07","20:50:00","2024-11-08","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","29BAD-003","Darmstadt - Aschaffenburg","< >","Darmstadt Nord","Darmstadt Ost",2024,2024,49,49,"2024-12-05","20:50:00","2024-12-06","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","54F2-001","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Hanau Südseite",2024,2024,41,42,"2024-10-11","23:30:00","2024-10-14","05:00:00","2d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,5,6,7",1]
[null,"DB InfraGO","54F2-003","Darmstadt - Aschaffenburg","< >","Groß-Umstadt Mitte","Babenhausen (Hess)",2024,2024,45,46,"2024-11-10","02:00:00","2024-11-11","04:00:00","1d, 2h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,7",1]
[null,"DB InfraGO","1FCFC-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Babenhausen (Hess)",2024,2024,37,37,"2024-09-12","21:10:00","2024-09-13","05:10:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFD-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Babenhausen (Hess)",2024,2024,41,41,"2024-10-10","21:10:00","2024-10-11","05:10:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","1FCFE-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Babenhausen (Hess)",2024,2024,45,45,"2024-11-07","21:10:00","2024-11-08","05:10:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","29BAE-003","Darmstadt - Aschaffenburg","< >","Babenhausen (Hess)","Babenhausen (Hess)",2024,2024,49,49,"2024-12-05","21:10:00","2024-12-06","05:10:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"4,5",1]
[null,"DB InfraGO","221A0-004","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Erlangen",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,2",1]
[null,"DB InfraGO","221DD-001","Gemünden - Bamberg - Nürnberg","<","Forchheim (Oberfr)","Erlangen Gbf",2024,2024,36,36,"2024-09-02","21:05:00","2024-09-03","05:05:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-18",null,null,"1,2",1]
[null,"DB InfraGO","2233B-001","Gemünden - Bamberg - Nürnberg","<","Erlangen","Erlangen Paul-Gossen-Straße",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-18",null,null,"2,3",1]
[null,"DB InfraGO","22367-004","Gemünden - Bamberg - Nürnberg","< >","Erlangen","Forchheim (Oberfr)",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"3,4",1]
[null,"DB InfraGO","223B7-001","Gemünden - Bamberg - Nürnberg","<","Erlangen","Eltersdorf",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-18",null,null,"3,4",1]
[null,"DB InfraGO","22A45-003","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2024,2024,36,36,"2024-09-04","21:00:00","2024-09-05","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-24",null,null,"3,4",1]
[null,"DB InfraGO","22E60-001","Gemünden - Bamberg - Nürnberg",">","Eltersdorf","Forchheim (Oberfr)",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","22E79-004","Gemünden - Bamberg - Nürnberg","< >","Erlangen","Forchheim (Oberfr)",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","22E83-004","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Erlangen",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"6,7",1]
[null,"DB InfraGO","24D52-001","Gemünden - Bamberg - Nürnberg","<","Erlangen","Eltersdorf",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-01",null,null,"3,4",1]
[null,"DB InfraGO","24D81-004","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Erlangen",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"3,4",1]
[null,"DB InfraGO","25294-003","Gemünden - Bamberg - Nürnberg","< >","Erlangen","Eltersdorf",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","252C4-001","Gemünden - Bamberg - Nürnberg","<","Forchheim (Oberfr)","Erlangen",2024,2024,40,40,"2024-09-30","21:05:00","2024-10-01","05:05:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","253D1-001","Gemünden - Bamberg - Nürnberg",">","Eltersdorf","Forchheim (Oberfr)",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-06",null,null,"4,5",1]
[null,"DB InfraGO","253DD-004","Gemünden - Bamberg - Nürnberg","< >","Erlangen","Forchheim (Oberfr)",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"5,6",1]
[null,"DB InfraGO","25926-004","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Erlangen",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-11",null,null,"6,7",1]
[null,"DB InfraGO","320F-010","Gemünden - Bamberg - Nürnberg","< >","Feucht","Altdorf (b Nürnberg)",2024,2024,46,46,"2024-11-16","23:00:00","2024-11-17","05:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-15",null,null,"6,7",1]
[null,"DB InfraGO","2B3D5-003","Gemünden - Bamberg - Nürnberg","< >","Feucht","Feucht",2024,2024,37,37,"2024-09-11","01:30:00","2024-09-11","02:30:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,3,1]
[null,"DB InfraGO","3043-003","Gemünden - Bamberg - Nürnberg",">","Sterbfritz","Gemünden (Main)",2024,2024,44,45,"2024-11-01","22:05:00","2024-11-08","06:00:00","6d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3043-004","Gemünden - Bamberg - Nürnberg","<","Gemünden (Main)","Sterbfritz",2024,2024,43,44,"2024-10-25","22:05:00","2024-11-01","06:00:00","6d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","22E60-004","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Forchheim (Oberfr)",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","253D1-005","Gemünden - Bamberg - Nürnberg","< >","Forchheim (Oberfr)","Forchheim (Oberfr)",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"4,5",1]
[null,"DB InfraGO","5D31-009","Darmstadt - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2024,2024,38,38,"2024-09-17","02:35:00","2024-09-17","04:20:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,2,1]
[null,"DB InfraGO","5D31-012","Darmstadt - Mannheim",">","Ladenburg","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,38,38,"2024-09-17","02:35:00","2024-09-17","04:20:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,2,1]
[null,"DB InfraGO","5D31-026","Darmstadt - Mannheim",">","Ladenburg","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,38,38,"2024-09-18","02:40:00","2024-09-18","04:15:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,3,1]
[null,"DB InfraGO","1FCE2-001","Darmstadt - Mannheim",">","Bickenbach Nord","Bensheim",2024,2024,37,37,"2024-09-13","20:55:00","2024-09-14","04:55:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCE2-002","Darmstadt - Mannheim","< >","Bickenbach Nord","Bensheim",2024,2024,37,37,"2024-09-13","20:55:00","2024-09-14","04:55:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCE3-001","Darmstadt - Mannheim",">","Bickenbach Nord","Bensheim",2024,2024,41,41,"2024-10-11","20:55:00","2024-10-12","04:55:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCE3-002","Darmstadt - Mannheim","< >","Bickenbach Nord","Bensheim",2024,2024,41,41,"2024-10-11","20:55:00","2024-10-12","04:55:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCE4-001","Darmstadt - Mannheim",">","Bickenbach Nord","Bensheim",2024,2024,45,45,"2024-11-08","20:55:00","2024-11-09","04:55:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCEE-001","Darmstadt - Mannheim",">","Darmstadt Hbf","Bickenbach Nord",2024,2024,37,37,"2024-09-13","20:45:00","2024-09-14","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCEE-002","Darmstadt - Mannheim","< >","Darmstadt Hbf","Bickenbach Nord",2024,2024,37,37,"2024-09-13","20:45:00","2024-09-14","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCEF-001","Darmstadt - Mannheim",">","Darmstadt Hbf","Bickenbach Nord",2024,2024,41,41,"2024-10-11","20:45:00","2024-10-12","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCEF-002","Darmstadt - Mannheim","< >","Darmstadt Hbf","Bickenbach Nord",2024,2024,41,41,"2024-10-11","20:45:00","2024-10-12","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FCF0-001","Darmstadt - Mannheim",">","Darmstadt Hbf","Bickenbach Nord",2024,2024,45,45,"2024-11-08","20:45:00","2024-11-09","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-02",null,null,"5,6",1]
[null,"DB InfraGO","1FCF0-002","Darmstadt - Mannheim","< >","Darmstadt Hbf","Bickenbach Nord",2024,2024,45,45,"2024-11-08","20:45:00","2024-11-09","04:45:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"5,6",1]
[null,"DB InfraGO","1FD09-001","Darmstadt - Mannheim",">","Bensheim-Auerbach","Hemsbach",2024,2024,37,37,"2024-09-13","20:40:00","2024-09-14","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FD09-003","Darmstadt - Mannheim","< >","Bensheim-Auerbach","Heppenheim (Bergstr)",2024,2024,37,37,"2024-09-13","20:40:00","2024-09-14","04:40:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FD0A-001","Darmstadt - Mannheim",">","Bensheim-Auerbach","Hemsbach",2024,2024,41,41,"2024-10-11","20:40:00","2024-10-12","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FD0A-003","Darmstadt - Mannheim","< >","Bensheim-Auerbach","Heppenheim (Bergstr)",2024,2024,41,41,"2024-10-11","20:40:00","2024-10-12","04:40:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FD0B-001","Darmstadt - Mannheim",">","Bensheim-Auerbach","Hemsbach",2024,2024,45,45,"2024-11-08","20:40:00","2024-11-09","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","1FD78-001","Darmstadt - Mannheim",">","Darmstadt-Arheilgen","Darmstadt Hbf",2024,2024,41,41,"2024-10-12","21:25:00","2024-10-13","05:10:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-05",null,null,"6,7",1]
[null,"DB InfraGO","1FE48-001","Darmstadt - Mannheim","<","Hemsbach","Bensheim-Auerbach",2024,2024,39,39,"2024-09-24","21:05:00","2024-09-25","04:50:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-06",null,null,"2,3",1]
[null,"DB InfraGO","23074-003","Darmstadt - Mannheim","<","Neu-Edingen/Mhm-Friedrichsfeld","Ladenburg",2024,2024,36,36,"2024-09-02","22:00:00","2024-09-03","05:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-21",null,null,"1,2",1]
[null,"DB InfraGO","23BE5-008","Darmstadt - Mannheim","<","Neu-Edingen/Mhm-Friedrichsfeld","Ladenburg",2024,2024,37,37,"2024-09-14","21:00:00","2024-09-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-05",null,null,"6,7",1]
[null,"DB InfraGO","2427F-001","Darmstadt - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2024,2024,38,38,"2024-09-17","21:00:00","2024-09-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-13",null,null,"2,3",1]
[null,"DB InfraGO","24A3D-001","Darmstadt - Mannheim","<","Neu-Edingen/Mhm-Friedrichsfeld","Ladenburg",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-20",null,null,"3,4",1]
[null,"DB InfraGO",2.616E-5,"Darmstadt - Mannheim",">","Ladenburg","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-04",null,null,"6,7",1]
[null,"DB InfraGO","26177-004","Darmstadt - Mannheim","< >","Heddesheim/Hirschberg","Ladenburg",2024,2024,41,41,"2024-10-10","21:00:00","2024-10-11","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-01",null,null,"4,5",1]
[null,"DB InfraGO",2.6640000000000001,"Darmstadt - Mannheim",">","Heppenheim (Bergstr)","Hemsbach",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"4,5",1]
[null,"DB InfraGO","266D1-003","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Heddesheim/Hirschberg",2024,2024,49,49,"2024-12-06","21:00:00","2024-12-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"5,6",1]
[null,"DB InfraGO","267A7-002","Darmstadt - Mannheim",">","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,49,49,"2024-12-07","21:00:00","2024-12-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"6,7",1]
[null,"DB InfraGO","26A99-005","Darmstadt - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg Hbf",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"3,4",1]
[null,"DB InfraGO","275FC-003","Darmstadt - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2024,2024,48,48,"2024-11-28","21:00:00","2024-11-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-23",null,null,"4,5",1]
[null,"DB InfraGO","27C5B-002","Darmstadt - Mannheim","<","Ladenburg","Weinheim (Bergstr) Hbf",2024,2024,41,41,"2024-10-09","23:00:00","2024-10-10","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-22",null,null,"3,4",1]
[null,"DB InfraGO","28BF6-003","Darmstadt - Mannheim",">","Weinheim (Bergstr) Hbf","Heddesheim/Hirschberg",2024,2024,43,43,"2024-10-22","21:00:00","2024-10-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-18",null,null,"2,3",1]
[null,"DB InfraGO","29BB9-001","Darmstadt - Mannheim",">","Bensheim-Auerbach","Hemsbach",2024,2024,49,49,"2024-12-06","20:40:00","2024-12-07","04:40:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-24",null,null,"5,6",1]
[null,"DB InfraGO","29DDE-002","Darmstadt - Mannheim",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Hbf",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","0d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-11",null,null,1,1]
[null,"DB InfraGO","2AFD7-009","Darmstadt - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Periodical","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-11",null,null,5,1]
[null,"DB InfraGO","1FDAD-001","Darmstadt - Aschaffenburg",">","Kleinostheim","Aschaffenburg Hbf",2024,2024,42,42,"2024-10-15","21:15:00","2024-10-16","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-01-26",null,null,"2,3",1]
[null,"DB InfraGO","1FDAE-005","Darmstadt - Aschaffenburg","< >","Kleinostheim","Aschaffenburg Hbf",2024,2024,46,46,"2024-11-12","21:15:00","2024-11-13","05:15:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,"2,3",1]
[null,"DB InfraGO","2DAE3-016","München - Salzburg","< >","Freilassing","Hammerau",2024,2024,44,45,"2024-11-03","23:00:00","2024-11-04","04:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-24",null,null,"1,7",1]
[null,"DB InfraGO","320F-033","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Cadolzburg",2024,2024,41,42,"2024-10-07","00:45:00","2024-10-18","05:25:00","11d, 4h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-21",null,null,"2,3,4,5",1]
[null,"DB InfraGO","230B2-002","München - Regensburg","< >","Augsburg-Hochzoll","Augsburg-Hochzoll Abzweig",2024,2024,37,37,"2024-09-11","21:00:00","2024-09-12","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"3,4",1]
[null,"DB InfraGO","26531-003","Karlsruhe - Stuttgart","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2024,2024,45,45,"2024-11-06","21:00:00","2024-11-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","5DFF-041","Karlsruhe - Stuttgart","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2024,2024,46,46,"2024-11-13","23:00:00","2024-11-14","01:40:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-21",null,null,"3,4",1]
[null,"DB InfraGO","2643B-004","Karlsruhe - Stuttgart",">","Karlsruhe Gbf","Karlsruhe-Dammerstock",2024,2024,45,45,"2024-11-05","21:00:00","2024-11-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-04-02",null,null,"2,3",1]
[null,"DB InfraGO","2B71-008","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Karlsruhe-Durlach",2023,2024,49,50,"2023-12-10","00:00:00","2024-12-14","23:59:00","370d, 23h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-04-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","5DFF-012","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2024,2024,46,46,"2024-11-11","21:20:00","2024-11-11","23:15:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2023-07-21",null,null,1,1]
[null,"DB InfraGO","6CE2-011","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2024,2024,38,38,"2024-09-17","22:45:00","2024-09-18","01:40:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-06",null,null,"2,3",1]
[null,"DB InfraGO","6CE2-035","Karlsruhe - Stuttgart","<","Wilferdingen-Singen","Söllingen (b Karlsruhe) Abzw",2024,2024,38,38,"2024-09-19","01:40:00","2024-09-19","04:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2022-11-04",null,null,4,1]
[null,"DB InfraGO","7527-002","Karlsruhe - Stuttgart",">","Pforzheim Hbf","Mühlacker Em Süd",2024,2024,39,40,"2024-09-29","22:45:00","2024-09-30","01:40:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-30",null,null,"1,7",1]
[null,"DB InfraGO","23895-002","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Karlsruhe Hbf",2024,2024,36,36,"2024-09-02","09:00:00","2024-09-04","17:00:00","2d, 8h","Periodical","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-21",null,null,"1,2,3",1]
[null,"DB InfraGO",244.5,"Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"1,2",1]
[null,"DB InfraGO","24A50-001","Karlsruhe - Stuttgart","<","Mühlacker","Illingen (Württ)",2024,2024,42,42,"2024-10-16","21:00:00","2024-10-17","05:00:00","0d, 8h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-21",null,null,3,1]
[null,"DB InfraGO","2621A-005","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Söllingen (b Karlsruhe) Abzw",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO","26EC6-001","Karlsruhe - Stuttgart","<","Mühlacker Em Süd","Pforzheim Hbf",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"1,2",1]
[null,"DB InfraGO","26FC7-001","Karlsruhe - Stuttgart","<","Wilferdingen-Singen","Söllingen Reetzstraße",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"2,3",1]
[null,"DB InfraGO","283E9-003","Karlsruhe - Stuttgart","< >","Wilferdingen-Singen","Wilferdingen-Singen",2024,2024,44,44,"2024-10-28","22:00:00","2024-10-29","05:00:00","0d, 7h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO","28820-002","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2024,2024,50,50,"2024-12-09","21:00:00","2024-12-10","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-18",null,null,"1,2",1]
[null,"DB InfraGO","2A608-001","Karlsruhe - Stuttgart","<","Mühlacker","Pforzheim Hbf",2024,2024,46,47,"2024-11-15","23:10:00","2024-11-18","04:00:00","2d, 4h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-05",null,null,"1,5,6,7",1]
[null,"DB InfraGO","29F76-021","Stuttgart - München","<","Neu-Ulm","Neu-Ulm Finninger Straße",2024,2024,46,46,"2024-11-14","22:00:00","2024-11-15","06:00:00","0d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","275BF-001","München - Regensburg","< >","Dingolfing","Plattling",2024,2024,46,46,"2024-11-12","21:00:00","2024-11-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"2,3",1]
[null,"DB InfraGO","2C8C2-001","Darmstadt - Aschaffenburg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2024,2024,37,37,"2024-09-15","01:20:00","2024-09-15","04:20:00","0d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO","2FE8-047","Karlsruhe - Strasbourg",">","Rastatt-Süd","Baden-Baden",2024,2024,43,43,"2024-10-22","23:00:00","2024-10-25","04:00:00","2d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,"2,3,4",1]
[null,"DB InfraGO","314B-036","Karlsruhe - Strasbourg","<","Muggensturm","Baden-Baden",2024,2024,48,50,"2024-12-01","22:00:00","2024-12-12","05:00:00","10d, 7h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-06",null,null,"1,2,3",1]
[null,"DB InfraGO","5F22-006","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt",2024,2024,40,40,"2024-10-03","22:45:00","2024-10-04","03:45:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-20",null,null,"4,5",1]
[null,"DB InfraGO","23190-001","Karlsruhe - Strasbourg","<","Ettlingen West","Karlsruhe Hbf",2024,2024,36,36,"2024-09-07","21:00:00","2024-09-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-23",null,null,"6,7",1]
[null,"DB InfraGO","23947-004","Karlsruhe - Strasbourg","<","Offenburg","Achern",2024,2024,36,36,"2024-09-05","21:00:00","2024-09-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"4,5",1]
[null,"DB InfraGO","24378-001","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt",2024,2024,36,36,"2024-09-07","21:00:00","2024-09-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-23",null,null,"6,7",1]
[null,"DB InfraGO","254FA-001","Karlsruhe - Strasbourg","<","Rastatt","Muggensturm Badesee",2024,2024,40,40,"2024-10-04","21:00:00","2024-10-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-26",null,null,"5,6",1]
[null,"DB InfraGO","2576D-003","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2024,2024,40,40,"2024-10-05","21:00:00","2024-10-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-26",null,null,"6,7",1]
[null,"DB InfraGO","25905-007","Karlsruhe - Strasbourg","< >","Achern","Offenburg",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-02-23",null,null,"4,5",1]
[null,"DB InfraGO","25DB9-002","Karlsruhe - Strasbourg","<","Achern","Ottersweier",2024,2024,44,44,"2024-11-01","21:00:00","2024-11-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,"1,,1",null,null,null,"N",null,"2024-03-22",null,null,"5,6",1]
[null,"DB InfraGO","2686D-003","Karlsruhe - Strasbourg",">","Baden-Baden","Ottersweier",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"1,2",1]
[null,"DB InfraGO","26898-002","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,"1,2",1]
[null,"DB InfraGO","268E7-001","Karlsruhe - Strasbourg",">","Bruchsal","Karlsruhe-Durlach",2024,2024,50,50,"2024-12-09","21:00:00","2024-12-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-06",null,null,"1,2",1]
[null,"DB InfraGO","269DB-004","Karlsruhe - Strasbourg",">","Ottersweier","Offenburg",2024,2024,50,50,"2024-12-10","21:00:00","2024-12-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-12",null,null,"2,3",1]
[null,"DB InfraGO","27684-002","Karlsruhe - Strasbourg","<","Achern","Ottersweier",2024,2024,48,48,"2024-11-29","21:00:00","2024-11-30","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,"1,,1",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","27704-003","Karlsruhe - Strasbourg","<","Heidelberg Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,48,48,"2024-11-30","21:00:00","2024-12-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"6,7",1]
[null,"DB InfraGO","27931-001","Karlsruhe - Strasbourg",">","Baden-Baden","Ottersweier",2024,2024,42,42,"2024-10-14","21:00:00","2024-10-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-02-29",null,null,"1,2",1]
[null,"DB InfraGO","27A37-004","Karlsruhe - Strasbourg",">","Ottersweier","Offenburg",2024,2024,42,42,"2024-10-15","21:00:00","2024-10-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"2,3",1]
[null,"DB InfraGO","298DB-001","Karlsruhe - Strasbourg","<","Rastatt","Muggensturm",2024,2024,43,44,"2024-10-27","00:00:00","2024-10-28","05:00:00","1d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-10",null,null,"1,7",1]
[null,"DB InfraGO","2B1A4-002","Karlsruhe - Strasbourg","<","Rastatt","Ötigheim",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-06","05:00:00","1d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-23",null,null,"1,2",1]
[null,"DB InfraGO","2DBCF-001","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Karlsruhe Hbf",2024,2024,38,39,"2024-09-16","08:00:00","2024-09-23","16:00:00","7d, 8h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2EE30-029","Karlsruhe - Strasbourg",">","Karlsruhe-Durlach","Karlsruhe Hbf",2024,2024,39,39,"2024-09-27","02:15:00","2024-09-27","04:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-26",null,null,5,1]
[null,"DB InfraGO","32FC4-013","Karlsruhe - Strasbourg","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2024,2024,43,45,"2024-10-25","22:00:00","2024-11-07","12:00:00","12d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2351A-001","Mannheim - Karlsruhe","<","Langes Feld","Vaihingen (Enz)",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-01-22",null,null,"1,2",1]
[null,"DB InfraGO","23533-004","Mannheim - Karlsruhe",">","Vaihingen (Enz)","Vaihingen (Enz)",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-19",null,null,"2,3",1]
[null,"DB InfraGO","241A8-002","Mannheim - Karlsruhe",">","Pfingstberg","Hockenheim",2024,2024,38,38,"2024-09-20","21:00:00","2024-09-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-13",null,null,"5,6",1]
[null,"DB InfraGO","24740-003","Mannheim - Karlsruhe",">","Freudenstein","Vaihingen (Enz)",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","24913-001","Mannheim - Karlsruhe","<","Hockenheim","Pfingstberg",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-26",null,null,"2,3",1]
[null,"DB InfraGO","250FF-008","Mannheim - Karlsruhe",">","Vaihingen (Enz)","Vaihingen (Enz)",2024,2024,46,46,"2024-11-12","21:00:00","2024-11-13","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2023-12-18",null,null,"2,3",1]
[null,"DB InfraGO","259C8-001","Mannheim - Karlsruhe","<","Vaihingen (Enz)","Freudenstein",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","25CAF-001","Mannheim - Karlsruhe","<","Langes Feld","Stuttgart-Zazenhausen",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","26B29-003","Mannheim - Karlsruhe","< >","Vaihingen (Enz)","Freudenstein",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-04-02",null,null,"4,5",1]
[null,"DB InfraGO","26BF0-001","Mannheim - Karlsruhe",">","Vaihingen (Enz)","Langes Feld",2024,2024,50,50,"2024-12-13","21:00:00","2024-12-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-05-06",null,null,"5,6",1]
[null,"DB InfraGO","26C85-002","Mannheim - Karlsruhe",">","Glems","Stuttgart-Zazenhausen",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-04-29",null,null,6,1]
[null,"DB InfraGO","26CA7-003","Mannheim - Karlsruhe",">","Hockenheim","Lußhardt",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,6,1]
[null,"DB InfraGO",277.8,"Mannheim - Karlsruhe",">","Brühler Weg","Hockenheim",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"5,6",1]
[null,"DB InfraGO","283D7-004","Mannheim - Karlsruhe",">","Glems","Stuttgart-Zazenhausen",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-03-01",null,null,"6,7",1]
[null,"DB InfraGO","2956A-002","Mannheim - Karlsruhe","<","Glems","Illingen (Württ)",2024,2024,45,48,"2024-11-07","23:00:00","2024-11-29","00:30:00","21d, 1h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-03-13",null,null,4,1]
[null,"DB InfraGO","2BAB6-012","Mannheim - Karlsruhe",">","Vaihingen (Enz)","Glems",2024,2024,41,41,"2024-10-12","23:00:00","2024-10-13","01:00:00","0d, 2h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2023-08-22",null,null,"6,7",1]
[null,"DB InfraGO","2EE36-003","Mannheim - Karlsruhe",">","Freudenstein","Vaihingen (Enz)",2024,2024,39,39,"2024-09-24","03:15:00","2024-09-24","05:15:00","0d, 2h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-03-13",null,null,2,1]
[null,"DB InfraGO","32F24-004","Mannheim - Karlsruhe","<","Glems","Vaihingen (Enz)",2024,2024,43,43,"2024-10-23","01:50:00","2024-10-23","04:50:00","0d, 3h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-03-13",null,null,3,1]
[null,"DB InfraGO","32F24-017","Mannheim - Karlsruhe","<","Vaihingen (Enz)","Vaihingen (Enz)",2024,2024,43,43,"2024-10-21","22:50:00","2024-10-22","04:50:00","0d, 6h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-03-13",null,null,"1,2",1]
[null,"DB InfraGO","3592-001","Karlsruhe - Strasbourg",">","Mannheim-Rheinau","Hockenheim",2024,2024,38,38,"2024-09-17","21:00:00","2024-09-18","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-05-13",null,null,"2,3",1]
[null,"DB InfraGO","5B46-006","Karlsruhe - Strasbourg","<","Ötigheim","Rastatt",2024,2024,39,40,"2024-09-29","23:00:00","2024-09-30","04:30:00","0d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-28",null,null,"1,7",1]
[null,"DB InfraGO","5D7B-005","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2024,2024,44,44,"2024-10-28","22:30:00","2024-10-29","01:30:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,"1,2",1]
[null,"DB InfraGO","5DA4-014","Karlsruhe - Strasbourg","<","Hockenheim","Oftersheim",2024,2024,39,39,"2024-09-29","01:40:00","2024-09-29","04:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-20",null,null,7,1]
[null,"DB InfraGO","230F6-002","Karlsruhe - Strasbourg",">","Schwetzingen","Hockenheim",2024,2024,37,37,"2024-09-11","21:00:00","2024-09-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-05",null,null,"3,4",1]
[null,"DB InfraGO","239FB-002","Karlsruhe - Strasbourg",">","Mannheim Hbf Ost","Schwetzingen",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-02-02",null,null,"1,2",1]
[null,"DB InfraGO","23FD2-005","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Blankenloch",2024,2024,37,37,"2024-09-11","21:00:00","2024-09-12","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-02-02",null,null,"3,4",1]
[null,"DB InfraGO","24398-006","Karlsruhe - Strasbourg",">","Mannheim-Rheinau","Schwetzingen",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-20",null,null,"4,5",1]
[null,"DB InfraGO","24BCC-003","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Blankenloch",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"4,5",1]
[null,"DB InfraGO","250BA-006","Karlsruhe - Strasbourg","<","Waghäusel","Hockenheim",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-01",null,null,"1,2",1]
[null,"DB InfraGO","251C8-005","Karlsruhe - Strasbourg","< >","Ötigheim","Rastatt",2024,2024,39,39,"2024-09-28","21:00:00","2024-09-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-02-20",null,null,"6,7",1]
[null,"DB InfraGO","25649-004","Karlsruhe - Strasbourg",">","Mannheim Hbf Ost","Schwetzingen",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-03-01",null,null,"2,3",1]
[null,"DB InfraGO","25B10-002","Karlsruhe - Strasbourg",">","Durmersheim","Ötigheim",2024,2024,41,41,"2024-10-09","21:00:00","2024-10-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-03-01",null,null,"3,4",1]
[null,"DB InfraGO","262EB-001","Karlsruhe - Strasbourg",">","Schwetzingen","Waghäusel",2024,2024,49,49,"2024-12-02","21:00:00","2024-12-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"1,2",1]
[null,"DB InfraGO","26391-002","Karlsruhe - Strasbourg",">","Bashaide","Durmersheim",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-03-01",null,null,"2,3",1]
[null,"DB InfraGO","26432-004","Karlsruhe - Strasbourg",">","Mannheim Hbf Ost","Schwetzingen",2024,2024,49,49,"2024-12-03","21:00:00","2024-12-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO",26.52,"Karlsruhe - Strasbourg",">","Schwetzingen","Hockenheim",2024,2024,45,45,"2024-11-06","21:00:00","2024-11-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","26531-005","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Blankenloch",2024,2024,45,45,"2024-11-06","21:00:00","2024-11-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","271A1-001","Karlsruhe - Strasbourg",">","Waghäusel","Graben-Neudorf",2024,2024,47,47,"2024-11-21","21:00:00","2024-11-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"4,5",1]
[null,"DB InfraGO","272D3-001","Karlsruhe - Strasbourg","<","Waghäusel","Hockenheim",2024,2024,47,47,"2024-11-22","21:00:00","2024-11-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"5,6",1]
[null,"DB InfraGO","273A2-001","Karlsruhe - Strasbourg","<","Durmersheim","Bashaide",2024,2024,47,47,"2024-11-23","21:00:00","2024-11-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-04-16",null,null,"6,7",1]
[null,"DB InfraGO","273BF-002","Karlsruhe - Strasbourg","<","Ötigheim","Durmersheim",2024,2024,47,47,"2024-11-23","21:00:00","2024-11-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-04-16",null,null,"6,7",1]
[null,"DB InfraGO","28431-002","Karlsruhe - Strasbourg","<","Ötigheim","Bashaide",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-03-14",null,null,"4,5",1]
[null,"DB InfraGO","28467-001","Karlsruhe - Strasbourg","<","Ötigheim","Bashaide",2024,2024,43,43,"2024-10-25","21:00:00","2024-10-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-03-15",null,null,"5,6",1]
[null,"DB InfraGO","28474-004","Karlsruhe - Strasbourg","<","Rastatt","Ötigheim",2024,2024,43,43,"2024-10-26","21:00:00","2024-10-27","05:00:00","0d, 9h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","29E0A-002","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2024,2024,48,48,"2024-11-27","23:50:00","2024-11-28","04:40:00","0d, 4h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-08",null,null,"3,4",1]
[null,"DB InfraGO","2A270-002","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2024,2024,37,39,"2024-09-12","22:35:00","2024-09-24","04:55:00","11d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2A8F5-001","Karlsruhe - Strasbourg",">","Ötigheim","Rastatt-Süd",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-02","05:00:00","1d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-23",null,null,"4,5",1]
[null,"DB InfraGO","2D53F-001","Karlsruhe - Strasbourg",">","Waghäusel","Philippsburg Molzau",2024,2024,37,37,"2024-09-10","23:00:00","2024-09-11","05:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-24",null,null,"2,3",1]
[null,"DB InfraGO","31BCE-002","Karlsruhe - Strasbourg",">","Blankenloch","Karlsruhe Hbf",2024,2024,43,43,"2024-10-21","01:00:00","2024-10-21","03:30:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-23",null,null,1,1]
[null,"DB InfraGO","31D02-001","Karlsruhe - Strasbourg","< >","Durmersheim","Durmersheim Nord",2024,2024,35,36,"2024-08-26","21:00:00","2024-09-05","21:00:00","10d, 0h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","27451-002","Darmstadt - Mannheim","<","Mannheim Ziehbrunnen","Mannheim Rbf Gr M",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2",1]
[null,"DB InfraGO","50F9-014","Regensburg - Plzen","< >","Maxhütte-Haidhof","Maxh-Haidh DB-Gr",2024,2024,43,43,"2024-10-21","20:00:00","2024-10-23","06:00:00","1d, 10h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-19",null,null,"1,2",1]
[null,"DB InfraGO","277F2-018","München - Salzburg","< >","München Leuchtenbergring","München Ost Pbf",2024,2024,45,45,"2024-11-04","21:40:00","2024-11-08","04:20:00","3d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","C03C-012","Stuttgart - München","<","Mering Üst","München-Lochhausen",2024,2024,45,45,"2024-11-04","22:00:00","2024-11-05","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-02-02",null,null,"1,2",1]
[null,"DB InfraGO","1F730-015","Stuttgart - München",">","München Hbf","München-Pasing",2024,2024,38,38,"2024-09-17","00:45:00","2024-09-18","04:35:00","1d, 3h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-12-17",null,null,"2,3",1]
[null,"DB InfraGO","22C68-003","Stuttgart - München","< >","Mering Üst","Olching",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO","236A6-006","Stuttgart - München","< >","Mering Üst","Augsburg Haunstetterstraße",2024,2024,39,39,"2024-09-27","21:00:00","2024-09-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-02-12",null,null,"5,6",1]
[null,"DB InfraGO","24145-008","Stuttgart - München","< >","München-Lochhausen","Olching",2024,2024,39,39,"2024-09-26","21:00:00","2024-09-27","05:00:00","0d, 8h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-27",null,null,"4,5",1]
[null,"DB InfraGO","262C3-006","Stuttgart - München","< >","Olching","Mering Üst",2024,2024,45,45,"2024-11-04","21:00:00","2024-11-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","2648F-004","Stuttgart - München","< >","Augsburg-Hochzoll Abzweig","Mering Üst",2024,2024,45,45,"2024-11-05","21:15:00","2024-11-06","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-22",null,null,"2,3",1]
[null,"DB InfraGO","270F2-003","Stuttgart - München","<","Augsburg Hbf","Augsburg-Hochzoll Abzweig",2024,2024,47,47,"2024-11-21","20:45:00","2024-11-22","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","27243-003","Stuttgart - München","<","Mering Üst","München Nord Rbf Forstweg",2024,2024,47,47,"2024-11-21","21:00:00","2024-11-22","05:00:00","0d, 8h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,null,null,null,"4,5",1]
[null,"DB InfraGO","6454-003","Stuttgart - München","<","Gauting","München-Pasing",2024,2024,36,36,"2024-09-08","01:00:00","2024-09-08","04:00:00","0d, 3h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-09-01",null,null,7,1]
[null,"DB InfraGO","319D-009","München - Regensburg",">","Köfering","Obertraubling",2024,2024,37,38,"2024-09-15","22:40:00","2024-09-16","05:40:00","0d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-27",null,null,"1,7",1]
[null,"DB InfraGO","31A4-008","München - Regensburg","<","Obertraubling","Mangolding",2024,2024,38,38,"2024-09-17","02:20:00","2024-09-17","04:20:00","0d, 2h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-13",null,null,2,1]
[null,"DB InfraGO","288F0-001","München - Regensburg",">","Köfering","Obertraubling",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-03-11",null,null,"4,5",1]
[null,"DB InfraGO","238A-016","München - Salzburg","< >","Gr-Karolinenf  Ü","Rosenheim",2024,2024,44,45,"2024-10-31","00:30:00","2024-11-04","05:30:00","4d, 5h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO","238A-024","München - Salzburg","<","Gr-Karolinenf  Ü","Rosenheim",2024,2024,45,45,"2024-11-04","22:30:00","2024-11-05","05:30:00","0d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-17",null,null,"1,2",1]
[null,"DB InfraGO","2BDE-020","München - Salzburg",">","München-Trudering","Zorneding",2024,2024,43,45,"2024-10-27","23:00:00","2024-11-04","04:00:00","7d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3407-005","München - Salzburg","< >","München Hbf","München Süd",2024,2024,41,41,"2024-10-09","02:30:00","2024-10-09","03:45:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,3,1]
[null,"DB InfraGO","5E16-007","München - Salzburg","<","Kirchseeon","Zorneding",2024,2024,34,36,"2024-08-25","01:00:00","2024-09-07","01:00:00","13d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","692F-022","München - Salzburg","<","Haar","München-Waldtrudering",2024,2024,46,46,"2024-11-14","11:00:00","2024-11-14","13:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-01-03",null,null,4,1]
[null,"DB InfraGO","24246-002","München - Salzburg","< >","München Süd","München Süd",2024,2024,27,50,"2024-07-06","00:00:00","2024-12-14","23:59:00","162d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","25697-003","München - Salzburg","<","Zorneding","München-Trudering",2024,2024,40,40,"2024-10-05","21:15:00","2024-10-06","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"20,20,20",null,null,null,"N",null,"2024-02-17",null,null,"6,7",1]
[null,"DB InfraGO","2613B-002","München - Salzburg","< >","Ostermünchen","Grafing Bahnhof",2024,2024,42,42,"2024-10-16","21:15:00","2024-10-17","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-02-29",null,null,"3,4",1]
[null,"DB InfraGO","27627-002","München - Salzburg","< >","Grafing Bahnhof","Ostermünchen",2024,2024,48,48,"2024-11-28","21:20:00","2024-11-29","05:20:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-03-24",null,null,"4,5",1]
[null,"DB InfraGO","28DAA-004","München - Salzburg","< >","Zorneding","Kirchseeon",2024,2024,44,44,"2024-11-03","06:00:00","2024-11-03","17:00:00","0d, 11h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-03-20",null,null,7,1]
[null,"DB InfraGO","2ACBA-004","München - Salzburg","<","Zorneding","Haar",2024,2024,45,45,"2024-11-04","23:00:00","2024-11-05","04:00:00","0d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-04-25",null,null,"1,2",1]
[null,"DB InfraGO","2BCB7-002","München - Salzburg","<","Aßling (Oberbay)","Grafing Bahnhof",2024,2024,40,40,"2024-10-03","21:20:00","2024-10-04","05:20:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-05-23",null,null,"4,5",1]
[null,"DB InfraGO","2C6E6-002","München - Salzburg",">","Zorneding","Kirchseeon",2024,2024,38,38,"2024-09-17","21:15:00","2024-09-18","05:15:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO","6443-021","München - Salzburg","< >","München Donnersbergerbrücke","München-Pasing",2024,2024,41,42,"2024-10-11","22:40:00","2024-10-14","04:40:00","2d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-04",null,null,"1,5,6,7",1]
[null,"DB InfraGO","5E97-007","München - Salzburg","< >","München Ost Pbf","München Isartor",2024,2024,41,42,"2024-10-11","22:40:00","2024-10-14","04:40:00","2d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-15",null,null,"1,5,6,7",1]
[null,"DB InfraGO","2AD20-005","München - Salzburg",">","München Isartor","München Ost Pbf",2024,2024,41,42,"2024-10-11","22:40:00","2024-10-14","02:30:00","2d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-04-30",null,null,"1,5,6,7",1]
[null,"DB InfraGO","277F2-013","München - Salzburg","< >","München Ost Pbf","München-Riem West",2024,2024,45,45,"2024-11-04","21:40:00","2024-11-08","04:20:00","3d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","261FC-006","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2024,2024,47,48,"2024-11-18","21:40:00","2024-11-29","04:20:00","10d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","264E2-027","München - Salzburg","< >","München Ost Pbf","München Isartor",2024,2024,45,45,"2024-11-09","04:00:00","2024-11-10","15:40:00","1d, 11h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"6,7",1]
[null,"DB InfraGO","2AD20-009","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2024,2024,41,42,"2024-10-11","22:40:00","2024-10-14","02:30:00","2d, 3h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-30",null,null,"1,5,6,7",1]
[null,"DB InfraGO","277F2-002","München - Salzburg","< >","München Ost Pbf","München-Steinhausen",2024,2024,45,45,"2024-11-04","21:40:00","2024-11-08","04:20:00","3d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","325F3-030","Stuttgart - München","< >","München-Pasing Weiche 352","München-Pasing Bbf",2024,2024,45,45,"2024-11-09","09:00:00","2024-11-09","13:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,6,1]
[null,"DB InfraGO","2268F-002","Mannheim - Karlsruhe","<","Schwetzingen","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","24F0D-001","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Schwetzingen",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"6,7",1]
[null,"DB InfraGO","29DDE-004","Mannheim - Karlsruhe","< >","Mannheim Ziehbrunnen","Ladenburg",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","0d, 8h","Periodical","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-11",null,null,1,1]
[null,"DB InfraGO","23CDC-002","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2024,2024,37,37,"2024-09-13","21:00:00","2024-09-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-05",null,null,"5,6",1]
[null,"DB InfraGO","266AD-002","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2024,2024,49,49,"2024-12-06","21:00:00","2024-12-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"5,6",1]
[null,"DB InfraGO","29D95-005","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Hbf Ost",2024,2024,45,46,"2024-11-10","21:00:00","2024-11-11","05:00:00","0d, 8h","Periodical","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,7,1]
[null,"DB InfraGO","214C8-015","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2024,2024,44,45,"2024-11-03","04:00:00","2024-11-04","04:00:00","1d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-08",null,null,"1,7",1]
[null,"DB InfraGO","221A0-003","Gemünden - Bamberg - Nürnberg","< >","Vach","Erlangen",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,2",1]
[null,"DB InfraGO","2233B-003","Gemünden - Bamberg - Nürnberg","< >","Erlangen Paul-Gossen-Straße","Erlangen",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"2,3",1]
[null,"DB InfraGO","22EDC-003","Gemünden - Bamberg - Nürnberg",">","Vach","Eltersdorf",2024,2024,38,38,"2024-09-21","21:00:00","2024-09-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"15,15,15",null,null,null,"N",null,"2024-02-05",null,null,"6,7",1]
[null,"DB InfraGO","25294-006","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Vach",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"1,2",1]
[null,"DB InfraGO","253D1-003","Gemünden - Bamberg - Nürnberg","< >","Eltersdorf","Forchheim (Oberfr)",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,"4,5",1]
[null,"DB InfraGO",6.3500000000000002E-21,"Gemünden - Bamberg - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2024,2024,45,45,"2024-11-09","01:00:00","2024-11-09","05:00:00","0d, 4h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-15",null,null,6,1]
[null,"DB InfraGO","5947-002","Nürnberg - Plzen","<","Rückersdorf (Mittelfr)","Nürnberg Ost",2024,2024,36,37,"2024-09-06","19:00:00","2024-09-09","05:00:00","2d, 10h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2023-07-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO","5B20-001","Nürnberg - Plzen","<","Marktredwitz","Neusorg",2024,2024,40,40,"2024-09-30","08:00:00","2024-09-30","11:00:00","0d, 3h","Continuous","Tunnel",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2023-07-27",null,null,1,1]
[null,"DB InfraGO","309EF-003","Nürnberg - Plzen",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2024,2024,37,37,"2024-09-12","00:10:00","2024-09-12","05:30:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-06-26",null,null,4,1]
[null,"DB InfraGO","2A84C-004","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2024,2024,37,37,"2024-09-14","03:30:00","2024-09-14","04:40:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,6,1]
[null,"DB InfraGO","214C8-010","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2024,2024,42,42,"2024-10-17","06:45:00","2024-10-17","12:20:00","0d, 5h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-08",null,null,4,1]
[null,"DB InfraGO","1FE4C-002","Darmstadt - Aschaffenburg","< >","Dieburg","Darmstadt-Kranichstein",2024,2024,43,43,"2024-10-23","20:40:00","2024-10-24","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-14",null,null,"3,4",1]
[null,"DB InfraGO","22C61-006","Stuttgart - München","< >","Olching","Maisach Abzw",2024,2024,37,37,"2024-09-09","21:10:00","2024-09-10","05:10:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-29",null,null,"1,2",1]
[null,"DB InfraGO","26390-006","Stuttgart - München","< >","Olching","Maisach Abzw",2024,2024,49,49,"2024-12-02","21:10:00","2024-12-03","05:10:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","289DB-006","Stuttgart - München",">","Olching","Mammendorf",2024,2024,43,43,"2024-10-26","21:00:00","2024-10-27","05:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-14",null,null,"6,7",1]
[null,"DB InfraGO","27357-005","Stuttgart - München","< >","Olching","Olching",2024,2024,47,47,"2024-11-23","21:00:00","2024-11-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-03-22",null,null,"6,7",1]
[null,"DB InfraGO","2CFD-004","Regensburg - Wels","<","Straßkirchen","Vilshofen (Niederbay)",2024,2024,37,38,"2024-09-13","21:00:00","2024-09-20","04:55:00","6d, 7h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-01-17",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","319D-002","Regensburg - Wels",">","Mangolding","Regensburg Ost",2024,2024,37,37,"2024-09-14","22:20:00","2024-09-15","03:20:00","0d, 5h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2023-04-27",null,null,"6,7",1]
[null,"DB InfraGO","4714-045","Regensburg - Wels","< >","Radldorf (Niederbay)","Radldorf (Niederbay)",2024,2024,36,36,"2024-09-07","23:00:00","2024-09-08","01:00:00","0d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-07-17",null,null,"6,7",1]
[null,"DB InfraGO","69D8-001","Regensburg - Wels",">","Straubing","Radldorf (Niederbay)",2024,2024,40,40,"2024-10-03","21:50:00","2024-10-04","04:50:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-02-07",null,null,"4,5",1]
[null,"DB InfraGO","6A12-001","Regensburg - Wels","<","Straßkirchen","Plattling",2024,2024,40,40,"2024-10-02","22:50:00","2024-10-03","06:40:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-12-08",null,null,"3,4",1]
[null,"DB InfraGO","2316A-001","Regensburg - Wels","<","Schalding","Passau Gbf",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-19",null,null,"2,3",1]
[null,"DB InfraGO","23DA1-001","Regensburg - Wels","<","Sünching","Straubing",2024,2024,37,38,"2024-09-15","21:00:00","2024-09-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"20,20,20",null,null,null,"N",null,"2023-12-06",null,null,"1,7",1]
[null,"DB InfraGO","24741-002","Regensburg - Wels","< >","Plattling","Straubing",2024,2024,38,39,"2024-09-22","21:00:00","2024-09-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,7",1]
[null,"DB InfraGO","25A40-001","Regensburg - Wels","<","Straubing","Straßkirchen",2024,2024,41,41,"2024-10-09","21:00:00","2024-10-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-02-23",null,null,"3,4",1]
[null,"DB InfraGO","25B85-001","Regensburg - Wels","<","Girching","Vilshofen (Niederbay)",2024,2024,42,42,"2024-10-16","21:00:00","2024-10-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"3,4",1]
[null,"DB InfraGO","25C69-001","Regensburg - Wels",">","Plattling","Straßkirchen",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-15",null,null,"1,2",1]
[null,"DB InfraGO","26AD5-001","Regensburg - Wels","<","Girching","Vilshofen (Niederbay)",2024,2024,50,50,"2024-12-11","21:00:00","2024-12-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-12",null,null,"3,4",1]
[null,"DB InfraGO","26EFD-001","Regensburg - Wels",">","Sünching","Mangolding",2024,2024,47,47,"2024-11-18","21:00:00","2024-11-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"1,2",1]
[null,"DB InfraGO","27AB6-001","Regensburg - Wels",">","Sünching","Mangolding",2024,2024,43,43,"2024-10-21","21:00:00","2024-10-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-11",null,null,"1,2",1]
[null,"DB InfraGO","2B22C-003","Regensburg - Wels","< >","Sünching","Straubing",2024,2024,49,50,"2024-12-08","21:00:00","2024-12-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-23",null,null,"1,7",1]
[null,"DB InfraGO","30E78-008","Regensburg - Wels","< >","Straßkirchen","Plattling",2024,2024,36,36,"2024-09-02","21:00:00","2024-09-03","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO","31669-012","Regensburg - Wels","< >","Sandbach (Niederbay)","Vilshofen (Niederbay)",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO",336.5,"Regensburg - Wels","< >","Mangolding","Sünching",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO","29AE7-020","Regensburg - Wels",">","Plattling","Straßkirchen",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-25","04:55:00","1d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-26",null,null,"1,2",1]
[null,"DB InfraGO","22C63-004","Stuttgart - München","< >","Plochingen","Wendlingen (Neckar)",2024,2024,36,36,"2024-09-05","21:00:00","2024-09-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-01-23",null,null,"4,5",1]
[null,"DB InfraGO","25D65-002","Stuttgart - München","< >","Wendlingen (Neckar)","Plochingen",2024,2024,44,44,"2024-10-31","21:00:00","2024-11-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-20",null,null,"4,5",1]
[null,"DB InfraGO","2A542-025","Stuttgart - München","< >","Plochingen","Plochingen",2024,2024,48,48,"2024-12-01","01:15:00","2024-12-01","04:45:00","0d, 3h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO","244FB-002","München - Salzburg","< >","Prien a Chiemsee","Aschau (Chiemgau)",2024,2024,38,38,"2024-09-17","21:00:00","2024-09-18","04:55:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"2,3",1]
[null,"DB InfraGO","2B5E-005","Nürnberg - Regensburg","< >","Beratzhausen","Undorf",2024,2024,37,37,"2024-09-14","22:00:00","2024-09-15","05:40:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"6,7",1]
[null,"DB InfraGO","2BF3-003","Nürnberg - Regensburg",">","Parsberg","Seubersdorf",2024,2024,37,39,"2024-09-13","05:00:00","2024-09-29","16:59:00","16d, 11h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-03-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","71D2-002","Nürnberg - Regensburg",">","Seubersdorf","Deining Üst",2024,2024,41,41,"2024-10-12","23:00:00","2024-10-13","06:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-11-24",null,null,"6,7",1]
[null,"DB InfraGO","23FF5-001","Nürnberg - Regensburg",">","Parsberg","Seubersdorf",2024,2024,37,37,"2024-09-10","21:00:00","2024-09-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-25",null,null,"2,3",1]
[null,"DB InfraGO","2458F-001","Nürnberg - Regensburg","<","Postbauer-Heng","Deining (Oberpf)",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-02-21",null,null,"2,3",1]
[null,"DB InfraGO","256A2-001","Nürnberg - Regensburg","<","Parsberg","Beratzhausen",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-15",null,null,"4,5",1]
[null,"DB InfraGO","260B6-001","Nürnberg - Regensburg",">","Postbauer-Heng","Feucht",2024,2024,41,41,"2024-10-12","21:00:00","2024-10-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-03-04",null,null,"6,7",1]
[null,"DB InfraGO","26474-001","Nürnberg - Regensburg",">","Parsberg","Seubersdorf",2024,2024,45,45,"2024-11-05","21:00:00","2024-11-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-03",null,null,"2,3",1]
[null,"DB InfraGO","266BE-002","Nürnberg - Regensburg","< >","Postbauer-Heng","Deining Üst",2024,2024,45,45,"2024-11-08","21:00:00","2024-11-09","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-28",null,null,"5,6",1]
[null,"DB InfraGO","269FE-001","Nürnberg - Regensburg","<","Undorf","Regensburg Bbf",2024,2024,50,50,"2024-12-10","21:00:00","2024-12-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-12",null,null,"2,3",1]
[null,"DB InfraGO","29942-001","Nürnberg - Regensburg",">","Regensburg-Prüfening               (NRH)","Beratzhausen",2024,2024,46,47,"2024-11-17","21:00:00","2024-11-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-02-01",null,null,"1,7",1]
[null,"DB InfraGO","30097-001","Regensburg - Plzen",">","Schwandorf","Irrenlohe",2024,2024,36,36,"2024-09-06","00:15:00","2024-09-06","01:20:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-06-27",null,null,5,1]
[null,"DB InfraGO","29489-003","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Bergschneise",2024,2024,47,47,"2024-11-18","23:00:00","2024-11-19","05:00:00","0d, 6h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-27",null,null,"1,2",1]
[null,"DB InfraGO","2B6F-001","München - Salzburg","< >","Prien a Chiemsee","Rottau",2024,2024,43,44,"2024-10-25","23:00:00","2024-10-31","14:00:00","5d, 16h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2D12-004","München - Salzburg","< >","Rumgraben","Traunstein",2024,2024,43,45,"2024-10-25","23:00:00","2024-11-04","04:00:00","9d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2F79-017","München - Salzburg","< >","Teisendorf","Freilassing",2024,2024,42,42,"2024-10-19","22:00:00","2024-10-20","04:00:00","0d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-04-04",null,null,"6,7",1]
[null,"DB InfraGO","64C0-004","München - Salzburg",">","Bad Endorf (Oberbay)","Rottau",2024,2024,47,47,"2024-11-18","02:40:00","2024-11-18","05:40:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-19",null,null,1,1]
[null,"DB InfraGO","65A2-005","München - Salzburg","< >","Traunstein","Lauter",2024,2024,47,47,"2024-11-23","03:20:00","2024-11-23","04:40:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-19",null,null,6,1]
[null,"DB InfraGO","942F-005","München - Salzburg",">","Landl (Oberbay) Abzw","Bad Endorf (Oberbay)",2024,2024,44,44,"2024-11-01","23:00:00","2024-11-02","04:50:00","0d, 5h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-02",null,null,"5,6",1]
[null,"DB InfraGO","B073-002","München - Salzburg",">","Rottau","Übersee",2024,2024,45,45,"2024-11-05","22:40:00","2024-11-06","00:20:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-19",null,null,"2,3",1]
[null,"DB InfraGO","2F79-047","München - Salzburg","< >","Teisendorf","Freilassing",2024,2024,42,43,"2024-10-15","00:00:00","2024-10-25","23:00:00","10d, 23h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-04-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","236EB-001","München - Salzburg","<","Teisendorf","Traunstein",2024,2024,36,36,"2024-09-06","22:30:00","2024-09-07","06:30:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-19",null,null,"5,6",1]
[null,"DB InfraGO","236F9-013","München - Salzburg","< >","Freilassing","Freilassing",2024,2024,38,38,"2024-09-16","07:00:00","2024-09-18","17:00:00","2d, 10h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-26",null,null,"1,2,3",1]
[null,"DB InfraGO",24.55,"München - Salzburg","< >","Freilassing","Teisendorf",2024,2024,38,38,"2024-09-18","21:20:00","2024-09-19","05:20:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-02-02",null,null,"3,4",1]
[null,"DB InfraGO","253A3-001","München - Salzburg","<","Teisendorf","Traunstein",2024,2024,40,40,"2024-10-04","21:15:00","2024-10-05","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-17",null,null,"5,6",1]
[null,"DB InfraGO","25D84-001","München - Salzburg","<","Übersee","Prien a Chiemsee",2024,2024,44,44,"2024-10-31","21:15:00","2024-11-01","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-15",null,null,"4,5",1]
[null,"DB InfraGO","26934-001","München - Salzburg",">","Rosenheim Ost","Simssee",2024,2024,50,50,"2024-12-09","21:20:00","2024-12-10","05:20:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-24",null,null,"1,2",1]
[null,"DB InfraGO","27623-001","München - Salzburg","<","Freilassing","Teisendorf",2024,2024,48,48,"2024-11-28","21:15:00","2024-11-29","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-24",null,null,"4,5",1]
[null,"DB InfraGO","281B4-010","München - Salzburg",">","Teisendorf","Freilassing",2024,2024,35,36,"2024-09-01","22:55:00","2024-09-02","06:00:00","0d, 7h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-27",null,null,"1,7",1]
[null,"DB InfraGO","2A513-005","München - Salzburg","<","Prien a Chiemsee","Bad Endorf (Oberbay)",2024,2024,43,43,"2024-10-21","22:30:00","2024-10-25","05:30:00","3d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO","2A513-019","München - Salzburg","< >","Prien a Chiemsee","Rottau",2024,2024,45,45,"2024-11-04","02:00:00","2024-11-04","04:00:00","0d, 2h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-15",null,null,1,1]
[null,"DB InfraGO","2B903-006","München - Salzburg","< >","Traunstein","Traunstein",2024,2024,37,37,"2024-09-14","23:50:00","2024-09-15","04:50:00","0d, 5h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"6,7",1]
[null,"DB InfraGO","2DAE3-006","München - Salzburg","< >","Freilassing","Salzburg Liefering",2024,2024,43,44,"2024-10-25","23:00:00","2024-10-31","04:00:00","5d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,81,"N",null,"2024-03-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","31CE7-003","München - Salzburg",">","Traunstein","Lauter",2024,2024,50,50,"2024-12-09","21:00:00","2024-12-10","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO","31E0D-007","München - Salzburg","<","Bad Endorf (Oberbay)","Simssee",2024,2024,48,48,"2024-11-30","21:15:00","2024-12-01","05:15:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO","31D9-006","Nürnberg - Plzen","< >","Schirnding Grenz","Marktredwitz",2024,2024,13,39,"2024-03-30","23:05:00","2024-09-24","04:30:00","177d, 4h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","60F3-007","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt-Sennfeld",2024,2024,39,42,"2024-09-27","05:00:00","2024-10-16","08:00:00","19d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3592-012","Mannheim - Karlsruhe","< >","Oftersheim","Oftersheim",2024,2024,38,38,"2024-09-18","21:00:00","2024-09-19","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-16",null,null,"3,4",1]
[null,"DB InfraGO","217B5-006","Mannheim - Karlsruhe",">","Illingen (Württ)","Illingen (Württ)",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"3,4",1]
[null,"DB InfraGO","24FF0-004","Mannheim - Karlsruhe","<","Illingen (Württ)","Vaihingen (Enz)",2024,2024,39,39,"2024-09-24","21:00:00","2024-09-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-02-07",null,null,"2,3",1]
[null,"DB InfraGO","26FBB-002","Mannheim - Karlsruhe","<","Illingen (Württ)","Vaihingen (Enz)",2024,2024,47,47,"2024-11-19","21:00:00","2024-11-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-02",null,null,"2,3",1]
[null,"DB InfraGO","28825-002","Mannheim - Karlsruhe","<","Vaihingen (Enz)","StrWe 4800/4842",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-08",null,null,"3,4",1]
[null,"DB InfraGO","6260-029","Stuttgart - München","< >","Stuttgart Nürnberger Straße Abzw","Stuttgart-Untertürkheim",2024,2024,39,39,"2024-09-24","23:40:00","2024-09-25","04:40:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-20",null,null,"2,3",1]
[null,"DB InfraGO","243DD-003","Stuttgart - München","< >","Stuttgart-Zazenhausen","Stuttgart-Zazenhausen",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-05",null,null,"4,5",1]
[null,"DB InfraGO","258C2-003","Stuttgart - München","<","Stuttgart-Zazenhausen","Glems",2024,2024,40,40,"2024-09-30","21:00:00","2024-10-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-02-21",null,null,"1,2",1]
[null,"DB InfraGO","20E67-040","Stuttgart - München",">","Stuttgart-Zazenhausen","Langes Feld",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2023-11-27",null,null,"4,5",1]
[null,"DB InfraGO","245C4-009","Stuttgart - München","< >","Kornwestheim Rbf Süd-West","Stuttgart-Zazenhausen",2024,2024,49,49,"2024-12-02","08:00:00","2024-12-02","16:00:00","0d, 8h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO","1F083-018","Stuttgart - München","< >","Ludwigsburg","Ludwigsburg",2024,2024,42,43,"2024-10-20","21:00:00","2024-10-21","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-24",null,null,"1,7",1]
[null,"DB InfraGO","4714-040","Regensburg - Wels","< >","Straubing","Bogen",2024,2024,36,36,"2024-09-03","01:00:00","2024-09-04","23:00:00","1d, 22h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-17",null,null,"2,3",1]
[null,"DB InfraGO","20096-016","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2024,2024,39,39,"2024-09-25","21:00:00","2024-09-26","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-31",null,null,"3,4",1]
[null,"DB InfraGO","2026C-015","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-27",null,null,"1,2",1]
[null,"DB InfraGO","211EA-017","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2024,2024,47,47,"2024-11-18","01:00:00","2024-11-18","05:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,1,1]
[null,"DB InfraGO","58A7-008","Karlsruhe - Stuttgart","<","Mühlacker","Illingen (Württ)",2024,2024,41,41,"2024-10-07","01:35:00","2024-10-07","04:25:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-11-10",null,null,1,1]
[null,"DB InfraGO","1F083-013","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2024,2024,38,39,"2024-09-22","21:00:00","2024-09-23","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-24",null,null,"1,7",1]
[null,"DB InfraGO","2056F-018","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2024,2024,38,38,"2024-09-18","21:00:00","2024-09-19","05:00:00","0d, 8h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO","23AB2-001","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","StrWe 4800/4842",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO","24229-003","Karlsruhe - Stuttgart","< >","Ludwigsburg","Bietigheim-Bissingen",2024,2024,38,38,"2024-09-16","21:00:00","2024-09-17","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,"1,2",1]
[null,"DB InfraGO","2541D-005","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Ludwigsburg",2024,2024,40,40,"2024-10-03","21:00:00","2024-10-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-19",null,null,"4,5",1]
[null,"DB InfraGO","26625-002","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Sachsenheim",2024,2024,49,49,"2024-12-05","21:00:00","2024-12-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"4,5",1]
[null,"DB InfraGO","281D0-002","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker Em Nord",2024,2024,43,43,"2024-10-21","21:00:00","2024-10-23","05:00:00","1d, 8h","Periodical","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-18",null,null,"1,2",1]
[null,"DB InfraGO","2880C-002","Karlsruhe - Stuttgart","<","Illingen (Württ)","Mühlacker",2024,2024,50,50,"2024-12-09","21:00:00","2024-12-11","05:00:00","1d, 8h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-14",null,null,"1,2",1]
[null,"DB InfraGO","3176-006","Stuttgart - München",">","Süßen","Ulm Hbf Bft Pbf",2024,2024,41,42,"2024-10-11","23:00:00","2024-10-16","05:00:00","4d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","57B8-009","Stuttgart - München",">","Beimerstetten","Ulm-Örlingen",2024,2024,37,37,"2024-09-09","21:00:00","2024-09-13","05:00:00","3d, 8h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4",1]
[null,"DB InfraGO","5D5A-018","Stuttgart - München","<","Süßen","Eislingen (Fils)",2024,2024,48,48,"2024-11-25","23:55:00","2024-11-26","01:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-21",null,null,"1,2",1]
[null,"DB InfraGO","6610-004","Stuttgart - München",">","Westerstetten","Beimerstetten",2024,2024,46,46,"2024-11-17","21:45:00","2024-11-17","22:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-07-21",null,null,7,1]
[null,"DB InfraGO","659D-088","Stuttgart - München","<","Ulm Hbf Bft Pbf","Beimerstetten",2024,2024,47,47,"2024-11-19","02:10:00","2024-11-19","03:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-06",null,null,2,1]
[null,"DB InfraGO","20417-018","Stuttgart - München","<","Neu-Ulm","Ulm Hbf Bft Pbf",2024,2024,39,39,"2024-09-25","23:00:00","2024-09-26","05:00:00","0d, 6h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","20893-008","Stuttgart - München","< >","Plochingen","Plochingen",2024,2024,43,43,"2024-10-23","21:00:00","2024-10-24","05:00:00","0d, 8h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-27",null,null,"3,4",1]
[null,"DB InfraGO","22E75-002","Stuttgart - München","< >","Ebersbach (Fils)","Göppingen",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-23",null,null,"2,3",1]
[null,"DB InfraGO","23305-002","Stuttgart - München","<","Beimerstetten","Westerstetten",2024,2024,36,36,"2024-09-03","21:00:00","2024-09-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-01-22",null,null,"2,3",1]
[null,"DB InfraGO","23814-013","Stuttgart - München","< >","Beimerstetten","Ulm-Örlingen",2024,2024,36,37,"2024-09-06","22:00:00","2024-09-09","06:00:00","2d, 8h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO","23814-019","Stuttgart - München","< >","Geislingen West","Geislingen West",2024,2024,38,39,"2024-09-20","22:00:00","2024-09-23","06:00:00","2d, 8h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO","248DB-002","Stuttgart - München","< >","Gingen Süd","Amstetten (Württ)",2024,2024,38,38,"2024-09-19","21:00:00","2024-09-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-20",null,null,"4,5",1]
[null,"DB InfraGO","2566B-002","Stuttgart - München","< >","Ebersbach (Fils)","Göppingen",2024,2024,40,40,"2024-10-01","21:00:00","2024-10-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-20",null,null,"2,3",1]
[null,"DB InfraGO","25C7B-003","Stuttgart - München","< >","Beimerstetten","Ulm Hbf Em Nord",2024,2024,44,44,"2024-10-28","21:00:00","2024-10-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"1,2",1]
[null,"DB InfraGO","25CC5-001","Stuttgart - München","<","Göppingen","Ebersbach (Fils)",2024,2024,44,44,"2024-10-29","21:00:00","2024-10-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-20",null,null,"2,3",1]
[null,"DB InfraGO","26BBC-006","Stuttgart - München","< >","Gingen Süd","Amstetten (Württ)",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"4,5",1]
[null,"DB InfraGO","2742F-002","Stuttgart - München","<","Ulm Hbf Bft Pbf","Beimerstetten",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"1,2",1]
[null,"DB InfraGO","27431-006","Stuttgart - München","< >","Göppingen","Gingen Süd",2024,2024,48,48,"2024-11-25","21:00:00","2024-11-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-03",null,null,"1,2",1]
[null,"DB InfraGO","27AA6-002","Stuttgart - München",">","Geislingen (Steige)","Amstetten (Württ)",2024,2024,42,42,"2024-10-17","21:00:00","2024-10-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-29",null,null,"4,5",1]
[null,"DB InfraGO","27C9C-004","Stuttgart - München","< >","Ebersbach (Fils)","Göppingen",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"5,6",1]
[null,"DB InfraGO","27CD8-001","Stuttgart - München","< >","Westerstetten","Ulm-Örlingen",2024,2024,42,42,"2024-10-18","21:00:00","2024-10-19","04:50:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"5,6",1]
[null,"DB InfraGO","2849A-003","Stuttgart - München","< >","Göppingen","Gingen Süd",2024,2024,42,42,"2024-10-19","21:00:00","2024-10-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-01",null,null,"6,7",1]
[null,"DB InfraGO","29F76-019","Stuttgart - München",">","Ulm Hbf Bft Pbf","Neu-Ulm",2024,2024,46,46,"2024-11-13","22:00:00","2024-11-14","06:00:00","0d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-02",null,null,"3,4",1]
[null,"DB InfraGO","2A542-015","Stuttgart - München","< >","Plochingen","Plochingen",2024,2024,48,49,"2024-12-01","04:45:00","2024-12-07","04:45:00","6d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2B616-009","Stuttgart - München","< >","Göppingen","Gingen Süd",2024,2024,50,50,"2024-12-14","21:00:00","2024-12-14","23:59:00","0d, 2h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO","28AD-013","Stuttgart - München","<","Süßen","Eislingen (Fils)",2024,2024,36,50,"2024-09-06","21:00:00","2024-12-14","23:59:00","99d, 3h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","602F-036","Stuttgart - München","<","Plochingen","Esslingen (Neckar)",2024,2024,40,40,"2024-10-05","03:55:00","2024-10-05","05:20:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2023-07-21",null,null,6,1]
[null,"DB InfraGO","1F8FD-007","Stuttgart - München",">","Esslingen (Neckar)","Plochingen",2024,2024,42,43,"2024-10-20","21:00:00","2024-10-21","05:00:00","0d, 8h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-11-27",null,null,"1,7",1]
[null,"DB InfraGO","2C14E-005","Stuttgart - München","< >","Esslingen (Neckar)","Esslingen (Neckar)",2024,2024,38,38,"2024-09-16","07:00:00","2024-09-20","16:00:00","4d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","20584-020","Stuttgart - München","< >","Kornwestheim Pbf","Kornwestheim Pbf",2024,2024,48,48,"2024-11-28","21:00:00","2024-11-29","05:00:00","0d, 8h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"4,5",1]
[null,"DB InfraGO","23FFE-006","Stuttgart - München","< >","Stuttgart-Untertürkheim Pbf","Stuttgart-Untertürkheim",2024,2024,38,38,"2024-09-16","21:00:00","2024-09-17","05:00:00","0d, 8h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2",1]
[null,"DB InfraGO","2A22D-002","Stuttgart - München",">","Nürnberg-Eibach","Nürnberg Hbf",2024,2024,38,38,"2024-09-22","00:01:00","2024-09-22","02:30:00","0d, 2h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-04-23",null,null,7,1]
[null,"DB InfraGO","2A39A-014","Regensburg - Wels","<","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2024,2024,37,37,"2024-09-10","02:30:00","2024-09-10","04:30:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-03-25",null,null,2,1]
[null,"DB InfraGO","2F868-001","Gemünden - Bamberg - Nürnberg","< >","Arnstein (Unterfr)","Arnstein (Unterfr)",2024,2024,37,38,"2024-09-13","05:00:00","2024-09-19","12:00:00","6d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2F868-007","Gemünden - Bamberg - Nürnberg","< >","Eußenheim","Gemünden (Main)",2024,2024,38,39,"2024-09-22","05:00:00","2024-09-23","13:00:00","1d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"1,7",1]
[null,"DB InfraGO","2975D-011","Mannheim - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf Bft Südeinfahrt",2024,2024,45,46,"2024-11-09","21:10:00","2024-11-14","05:10:00","4d, 8h","Periodical","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-21",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO","322C-020","Aschaffenburg - Würzburg",">","Karlstadt (Main)","Gemünden (Main)",2024,2024,39,39,"2024-09-28","23:30:00","2024-09-29","05:30:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2022-05-25",null,null,"6,7",1]
[null,"DB InfraGO","1DEDA-002","Aschaffenburg - Würzburg","< >","Partenstein","Partenstein",2023,2024,49,49,"2023-12-10","00:00:00","2024-12-07","23:59:00","363d, 23h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","23699-001","Aschaffenburg - Würzburg","<","Lohr Bahnhof","Gemünden (Main)",2024,2024,36,36,"2024-09-06","21:15:00","2024-09-07","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-30",null,null,"5,6",1]
[null,"DB InfraGO","23948-001","Aschaffenburg - Würzburg",">","Wiesthal","Laufach",2024,2024,38,38,"2024-09-17","21:00:00","2024-09-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-09",null,null,"2,3",1]
[null,"DB InfraGO","2F5E7-002","Aschaffenburg - Würzburg",">","Langenprozelten","Partenstein",2024,2024,37,37,"2024-09-11","20:00:00","2024-09-12","06:00:00","0d, 10h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-02-22",null,null,"3,4",1]
[null,"DB InfraGO","18400-010","Nürnberg - Plzen","< >","Furth im Wald","Furth im Wald",2025,2025,23,26,"2025-06-06","12:00:00","2025-06-27","12:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9CF1-003","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2025,2025,16,17,"2025-04-18","21:00:00","2025-04-23","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2023-06-14",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","A5CD-009","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2025,2025,15,16,"2025-04-12","23:00:00","2025-04-18","04:00:00","5d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO","A5CF-016","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2025,2025,37,38,"2025-09-13","23:00:00","2025-09-19","04:00:00","5d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-12",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO","A5CD-037","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2025,2025,18,19,"2025-05-04","23:00:00","2025-05-08","04:00:00","3d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,7",1]
[null,"DB InfraGO","A5CF-028","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Baden-Baden",2025,2025,37,38,"2025-09-13","23:00:00","2025-09-19","04:00:00","5d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO","190CC-007","Karlsruhe - Strasbourg","< >","Bühl (Baden) F","Ottersweier",2025,2025,13,13,"2025-03-28","00:05:00","2025-03-28","01:30:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-04-22",null,null,5,1]
[null,"DB InfraGO","16C4F-001","Stuttgart - München","< >","München-Daglfing","München-Trudering",2025,2025,26,26,"2025-06-23","23:00:00","2025-06-24","04:00:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO","1B11C-002","Stuttgart - München","< >","München-Johanneskirchen","München-Trudering",2025,2025,19,19,"2025-05-05","21:00:00","2025-05-06","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-27",null,null,"1,2",1]
[null,"DB InfraGO","1664A-011","Stuttgart - München","<","München-Trudering","München-Berg am Laim Abzw",2025,2025,33,34,"2025-08-17","22:30:00","2025-08-24","04:30:00","6d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","17612-003","Stuttgart - München","< >","Zorneding","Zorneding",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-18","23:30:00","0d, 2h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,3,1]
[null,"DB InfraGO","181F9-002","Stuttgart - München","<","München-Trudering","München-Berg am Laim Abzw",2025,2025,20,20,"2025-05-13","00:00:00","2025-05-14","04:20:00","1d, 4h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO","1864F-011","Stuttgart - München",">","Zorneding","Grafing Bahnhof",2025,2025,12,12,"2025-03-23","02:05:00","2025-03-23","04:45:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,10",null,null,null,"N",null,"2024-05-29",null,null,7,1]
[null,"DB InfraGO","B3D7-005","Gemünden - Bamberg - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2025,2025,49,50,"2025-12-05","00:00:00","2025-12-08","23:59:00","3d, 23h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO","13FBF-004","Aschaffenburg - Würzburg","< >","Nantenbach","Rohrbach",2025,2025,13,13,"2025-03-24","22:45:00","2025-03-24","23:45:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-12",null,null,1,1]
[null,"DB InfraGO","270E1-002","Aschaffenburg - Würzburg","<","Rohrbach","Nantenbach",2024,2024,51,51,"2024-12-18","21:10:00","2024-12-19","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-04-26",null,null,"3,4",1]
[null,"DB InfraGO","9EBD-004","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2025,2025,14,16,"2025-04-04","21:00:00","2025-04-15","21:00:00","11d, 0h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1B666-001","Nürnberg - Regensburg","<","Allersberg (Rothsee)","Nürnberg-Dutzendteich",2025,2025,30,30,"2025-07-21","21:00:00","2025-07-22","06:00:00","0d, 9h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2023-10-27",null,null,"1,2",1]
[null,"DB InfraGO","27060-002","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2024,2024,51,51,"2024-12-18","21:00:00","2024-12-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2024-04-16",null,null,"3,4",1]
[null,"DB InfraGO","EACB-011","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,26,26,"2025-06-25","01:50:00","2025-06-25","05:30:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-04-26",null,null,3,1]
[null,"DB InfraGO","14D10-022","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,31,31,"2025-08-03","01:10:00","2025-08-03","02:45:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-09",null,null,7,1]
[null,"DB InfraGO","17740-014","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,10,11,"2025-03-09","23:25:00","2025-03-10","00:35:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-08",null,null,"1,7",1]
[null,"DB InfraGO","8D12-003","Karlsruhe - Strasbourg","<","Kork","Appenweier Kurve",2025,2025,32,32,"2025-08-04","22:00:00","2025-08-07","04:00:00","2d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-12",null,null,"1,2,3",1]
[null,"DB InfraGO","139FD-008","Karlsruhe - Strasbourg","<","Kehl","Kork",2025,2025,45,47,"2025-11-03","22:00:00","2025-11-21","05:00:00","17d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","139FD-016","Karlsruhe - Strasbourg",">","Kork","Kehl",2025,2025,48,48,"2025-11-24","22:00:00","2025-11-29","05:00:00","4d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-01",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","19697-006","Karlsruhe - Strasbourg","< >","Kork","Kork",2025,2025,43,44,"2025-10-25","23:00:00","2025-10-30","04:00:00","4d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-08-29",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO","190D3-012","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Appenweier-Muhrhaag",2025,2025,13,13,"2025-03-30","00:35:00","2025-03-30","03:10:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO","153B0-021","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,20,20,"2025-05-16","20:00:00","2025-05-17","08:00:00","0d, 12h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO","153B0-034","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,22,22,"2025-05-27","22:30:00","2025-05-29","04:30:00","1d, 6h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-20",null,null,"2,3",1]
[null,"DB InfraGO","153B0-003","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,19,19,"2025-05-06","22:30:00","2025-05-07","04:30:00","0d, 6h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"2,3",1]
[null,"DB InfraGO","153B0-036","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,22,22,"2025-05-28","22:30:00","2025-05-29","04:30:00","0d, 6h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO","27D1C-002","Stuttgart - München",">","Augsburg-Oberhausen","Gablingen",2024,2024,52,52,"2024-12-30","20:45:00","2024-12-31","04:35:00","0d, 7h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-04",null,null,"1,2",1]
[null,"DB InfraGO","86AF-001","Stuttgart - München",">","Dinkelscherben","Freihalden Üst",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-05",null,null,"1,2",1]
[null,"DB InfraGO","86AF-012","Stuttgart - München","< >","Dinkelscherben","Dinkelscherben",2025,2025,16,16,"2025-04-15","21:00:00","2025-04-17","05:00:00","1d, 8h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-06-14",null,null,"2,3",1]
[null,"DB InfraGO","8887-002","Stuttgart - München","< >","Freihalden Üst","Burgau (Schwab)",2025,2025,14,14,"2025-03-31","21:00:00","2025-04-04","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-06",null,null,"1,2,3,4",1]
[null,"DB InfraGO","BB6D-008","Stuttgart - München","< >","Nersingen","Neu-Ulm",2025,2025,23,28,"2025-06-06","21:00:00","2025-07-11","05:00:00","34d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","BBC9-002","Stuttgart - München","< >","Nersingen","Neu-Ulm",2025,2025,15,15,"2025-04-12","00:01:00","2025-04-13","05:00:00","1d, 4h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO","BBE7-001","Stuttgart - München","< >","Günzburg","Unterfahlheim",2025,2025,22,22,"2025-05-31","00:01:00","2025-05-31","04:00:00","0d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,6,1]
[null,"DB InfraGO","7950-001","Stuttgart - München","<","Günzburg","Neuoffingen",2025,2025,19,19,"2025-05-09","22:00:00","2025-05-11","04:00:00","1d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2023-02-02",null,null,"5,6",1]
[null,"DB InfraGO","7950-007","Stuttgart - München","<","Neu-Ulm","Günzburg",2025,2025,19,20,"2025-05-11","22:00:00","2025-05-14","04:00:00","2d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-03",null,null,"1,2,7",1]
[null,"DB InfraGO","7965-003","Stuttgart - München","<","Neuoffingen","Burgau (Schwab)",2025,2025,34,35,"2025-08-22","22:00:00","2025-08-26","04:00:00","3d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-03",null,null,"1,5",1]
[null,"DB InfraGO","15F96-012","Stuttgart - München","<","Günzburg","Neuoffingen",2025,2025,28,28,"2025-07-11","01:20:00","2025-07-11","02:40:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2023-08-01",null,null,5,1]
[null,"DB InfraGO","15FBD-001","Stuttgart - München","< >","Günzburg","Nersingen",2025,2025,28,28,"2025-07-11","23:20:00","2025-07-12","04:45:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-01",null,null,"5,6",1]
[null,"DB InfraGO","15FBD-013","Stuttgart - München","< >","Günzburg","Nersingen",2025,2025,28,28,"2025-07-12","23:20:00","2025-07-13","04:45:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-01",null,null,"6,7",1]
[null,"DB InfraGO","184FD-009","Stuttgart - München","< >","Gessertshausen","Dinkelscherben",2025,2025,27,33,"2025-07-04","00:00:00","2025-08-15","04:00:00","42d, 4h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","184FD-011","Stuttgart - München",">","Kutzenhausen","Dinkelscherben",2025,2025,33,33,"2025-08-15","05:00:00","2025-08-16","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO",2.566E-4,"Stuttgart - München","< >","Dinkelscherben","Dinkelscherben",2025,2025,35,37,"2025-08-29","20:30:00","2025-09-13","20:00:00","14d, 23h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-01-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","25653-005","Stuttgart - München","< >","Westheim (Schwab)","Westheim (Schwab)",2025,2025,37,40,"2025-09-13","20:00:00","2025-10-01","05:00:00","17d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","25653-015","Stuttgart - München","< >","Westheim (Schwab)","Dinkelscherben",2025,2025,40,40,"2025-10-04","23:30:00","2025-10-05","04:30:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-07",null,null,"6,7",1]
[null,"DB InfraGO","27CF9-004","Stuttgart - München","< >","Neuoffingen","Freihalden Üst",2024,2024,50,51,"2024-12-15","21:00:00","2024-12-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"1,7",1]
[null,"DB InfraGO","27D0B-004","Stuttgart - München",">","Neuoffingen","Günzburg",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","05:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-05-06",null,null,7,1]
[null,"DB InfraGO","7E9B-007","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,46,47,"2025-11-12","07:00:00","2025-11-19","17:00:00","7d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","153B0-025","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,20,21,"2025-05-16","20:00:00","2025-05-19","08:00:00","2d, 12h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6,7",1]
[null,"DB InfraGO","108D8-027","Karlsruhe - Stuttgart",">","Freiberg (Neckar)","Ludwigsburg",2025,2025,29,29,"2025-07-16","22:00:00","2025-07-17","01:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO","BE85-010","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2025,2025,27,27,"2025-07-04","21:00:00","2025-07-04","23:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2023-01-31",null,null,5,1]
[null,"DB InfraGO","BE85-017","Gemünden - Bamberg - Nürnberg","<","Gädheim","Gädheim",2025,2025,29,29,"2025-07-17","05:00:00","2025-07-19","05:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,0",null,null,null,"N",null,"2023-01-31",null,null,"4,5,6",1]
[null,"DB InfraGO","BF16-011","Gemünden - Bamberg - Nürnberg",">","Ebelsbach-Eltmann","Ebelsbach-Eltmann",2025,2025,29,29,"2025-07-16","07:00:00","2025-07-16","22:00:00","0d, 15h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,3,1]
[null,"DB InfraGO","BFD5-008","Gemünden - Bamberg - Nürnberg","< >","Schweinfurt Stadt","Oberhaid",2025,2025,30,35,"2025-07-25","21:00:00","2025-08-25","05:00:00","30d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","C0B8-001","Gemünden - Bamberg - Nürnberg",">","Waigolshausen","Waigolshausen",2025,2025,26,28,"2025-06-26","08:00:00","2025-07-08","18:00:00","12d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","C0B8-015","Gemünden - Bamberg - Nürnberg","< >","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2025,2025,27,27,"2025-06-30","01:00:00","2025-07-06","04:00:00","6d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","13AAB-002","Gemünden - Bamberg - Nürnberg","< >","Waigolshausen","Waigolshausen",2025,2025,41,41,"2025-10-12","16:00:00","2025-10-12","19:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,7,1]
[null,"DB InfraGO","18870-006","Gemünden - Bamberg - Nürnberg","< >","Rottendorf","Waigolshausen",2025,2025,20,20,"2025-05-12","03:00:00","2025-05-12","04:00:00","0d, 1h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,1,1]
[null,"DB InfraGO","15037-010","Gemünden - Bamberg - Nürnberg","< >","Feucht","Feucht",2025,2025,16,16,"2025-04-14","01:30:00","2025-04-14","03:00:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO","13D31-020","Stuttgart - München",">","München Süd","München Süd",2025,2025,31,31,"2025-07-29","02:30:00","2025-07-29","05:00:00","0d, 2h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,2,1]
[null,"DB InfraGO","13D31-030","Stuttgart - München","< >","München Süd","München Süd",2025,2025,32,32,"2025-08-06","23:00:00","2025-08-07","04:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO","13D31-036","Stuttgart - München","< >","München Süd","München Süd",2025,2025,33,33,"2025-08-11","22:00:00","2025-08-12","05:30:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO","13D04-020","Stuttgart - München","< >","München Süd","München Süd",2025,2025,38,38,"2025-09-15","08:00:00","2025-09-17","15:30:00","2d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2,3",1]
[null,"DB InfraGO","15567-007","Stuttgart - München","< >","München Süd","München Süd",2025,2025,2,2,"2025-01-07","00:00:00","2025-01-07","01:00:00","0d, 1h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-25",null,null,2,1]
[null,"DB InfraGO","15567-015","Stuttgart - München","< >","München Süd","München Süd",2024,2024,50,52,"2024-12-15","00:00:00","2024-12-23","04:00:00","8d, 4h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","787A-011","Stuttgart - München","< >","München Süd","München Süd",2025,2025,47,48,"2025-11-23","00:00:00","2025-11-25","06:00:00","2d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-29",null,null,"1,2,7",1]
[null,"DB InfraGO","D724-005","Karlsruhe - Stuttgart","< >","Walheim (Württ)","Bietigheim-Bissingen",2025,2025,33,33,"2025-08-15","22:45:00","2025-08-16","03:45:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-28",null,null,"5,6",1]
[null,"DB InfraGO","19B04-018","Karlsruhe - Stuttgart","<","Lauffen (Neckar)","Bietigheim-Bissingen",2025,2025,24,25,"2025-06-13","21:00:00","2025-06-20","21:00:00","7d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","81CC-002","Mannheim - Karlsruhe","< >","Graben-Neudorf","Bruchsal",2025,2025,42,43,"2025-10-17","22:00:00","2025-10-23","04:30:00","5d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-11-30",null,null,"1,2,3,5",1]
[null,"DB InfraGO","117B3-002","Mannheim - Karlsruhe","<","Graben-Neudorf","Bruchsal",2025,2025,50,50,"2025-12-13","01:00:00","2025-12-13","04:00:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-05-17",null,null,6,1]
[null,"DB InfraGO","70B0-003","Darmstadt - Aschaffenburg","<","Stockstadt (Main)","Aschaffenburg Hbf",2025,2025,26,26,"2025-06-29","01:00:00","2025-06-29","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2022-12-16",null,null,7,1]
[null,"DB InfraGO","9FAA-034","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2025,2025,18,19,"2025-05-04","20:00:00","2025-05-05","04:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-12",null,null,"1,7",1]
[null,"DB InfraGO","A58D-012","Darmstadt - Aschaffenburg","<","Darmstadt-Kranichstein","Darmstadt Hbf",2025,2025,18,18,"2025-04-30","23:00:00","2025-05-01","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","9FAA-015","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2025,2025,9,15,"2025-02-27","06:00:00","2025-04-10","04:00:00","41d, 21h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9FAA-040","Darmstadt - Aschaffenburg","< >","Darmstadt Hbf","Darmstadt Hbf",2025,2025,26,26,"2025-06-28","04:00:00","2025-06-28","20:00:00","0d, 16h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-12",null,null,6,1]
[null,"DB InfraGO","1376C-001","Aschaffenburg - Würzburg","< >","Gemünden (Main)","Gemünden (Main)",2025,2025,44,44,"2025-10-31","01:40:00","2025-10-31","04:50:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,5,1]
[null,"DB InfraGO","27250-002","Aschaffenburg - Würzburg",">","Gemünden (Main)","Burgsinn",2024,2024,51,51,"2024-12-19","21:15:00","2024-12-20","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","9A23-016","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Ladenburg",2025,2025,9,13,"2025-03-01","21:00:00","2025-03-30","05:00:00","28d, 7h","Continuous",null,null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9A89-004","Darmstadt - Mannheim",">","Weinheim (Bergstr) Hbf","Heddesheim/Hirschberg",2025,2025,11,12,"2025-03-14","21:00:00","2025-03-22","05:00:00","7d, 8h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9CFB-002","Darmstadt - Mannheim","< >","Ladenburg","Ladenburg",2025,2025,14,16,"2025-04-06","21:00:00","2025-04-18","05:00:00","11d, 8h","Periodical",null,null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9CFB-012","Darmstadt - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,17,19,"2025-04-22","21:00:00","2025-05-09","05:00:00","16d, 8h","Continuous",null,null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","A0ED-004","Darmstadt - Mannheim","< >","Bensheim","Bensheim",2025,2025,12,12,"2025-03-17","21:30:00","2025-03-21","05:00:00","3d, 7h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-06",null,null,"1,2,3,4",1]
[null,"DB InfraGO","9FAA-071","Darmstadt - Mannheim","< >","Darmstadt Hbf","Darmstadt Gbf",2025,2025,27,27,"2025-07-01","09:00:00","2025-07-01","21:00:00","0d, 12h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-02",null,null,2,1]
[null,"DB InfraGO","A6CD-002","Darmstadt - Mannheim","<","Bensheim","Bensheim-Auerbach",2025,2025,37,38,"2025-09-14","23:00:00","2025-09-15","05:00:00","0d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-12",null,null,7,1]
[null,"DB InfraGO","A8F9-011","Darmstadt - Mannheim","< >","Bensheim","Heppenheim Nord",2025,2025,13,16,"2025-03-28","21:00:00","2025-04-14","05:00:00","16d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","EC08-001","Darmstadt - Mannheim","< >","Ladenburg","Ladenburg",2025,2025,23,24,"2025-06-08","22:00:00","2025-06-09","04:00:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-03-23",null,null,"1,7",1]
[null,"DB InfraGO","EC08-010","Darmstadt - Mannheim",">","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,24,24,"2025-06-09","22:00:00","2025-06-10","00:50:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-23",null,null,"1,2",1]
[null,"DB InfraGO","EC08-016","Darmstadt - Mannheim","<","Neu-Edingen/Mhm-Friedrichsfeld","Ladenburg",2025,2025,24,24,"2025-06-10","22:00:00","2025-06-11","00:50:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-23",null,null,"2,3",1]
[null,"DB InfraGO","26E82-004","Darmstadt - Mannheim",">","Heddesheim/Hirschberg","Ladenburg",2024,2024,51,51,"2024-12-16","21:00:00","2024-12-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-13",null,null,"1,2",1]
[null,"DB InfraGO","26F7D-004","Darmstadt - Mannheim","<","Heddesheim/Hirschberg","Weinheim (Bergstr) Hbf",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO","2B7FA-004","Darmstadt - Mannheim","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-21","05:00:00","1d, 8h","Periodical","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"4,5",1]
[null,"DB InfraGO","A58D-002","Darmstadt - Mannheim","< >","Darmstadt Gbf","Darmstadt Gbf",2025,2025,17,17,"2025-04-24","23:00:00","2025-04-25","05:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-11",null,null,"4,5",1]
[null,"DB InfraGO","70B0-017","Darmstadt - Aschaffenburg","<","Kleinostheim","Aschaffenburg Hbf",2025,2025,38,39,"2025-09-20","21:00:00","2025-09-22","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"24,24,24",null,null,null,"N",null,"2022-11-08",null,null,"6,7",1]
[null,"DB InfraGO","15574-005","Würzburg - Nürnberg","< >","Fürth-Burgfarrnbach","Fürth (Bay) Hbf",2025,2025,39,39,"2025-09-27","21:00:00","2025-09-28","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","1A20E-004","Würzburg - Nürnberg","< >","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2025,2025,16,16,"2025-04-14","22:45:00","2025-04-15","04:50:00","0d, 6h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO","1AB4C-004","Würzburg - Nürnberg","< >","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2025,2025,24,25,"2025-06-15","22:00:00","2025-06-16","05:00:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,7",1]
[null,"DB InfraGO","1AE63-001","Würzburg - Nürnberg",">","Fürth (Bay) Hbf","Siegelsdorf",2025,2025,21,21,"2025-05-24","23:10:00","2025-05-25","04:55:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","150C4-004","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2025,2025,28,31,"2025-07-08","06:00:00","2025-08-03","23:00:00","26d, 17h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","A0ED-007","Darmstadt - Mannheim","< >","Lorsch","Bensheim",2025,2025,39,39,"2025-09-23","01:00:00","2025-09-23","04:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-06",null,null,2,1]
[null,"DB InfraGO","7FD2-006","Mannheim - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2025,2025,9,9,"2025-02-24","12:00:00","2025-02-25","12:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2022-12-05",null,null,"1,2",1]
[null,"DB InfraGO",13.66,"Mannheim - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2025,2025,23,23,"2025-06-02","08:00:00","2025-06-02","16:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-12",null,null,1,1]
[null,"DB InfraGO","177AE-005","Mannheim - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Dammerstock",2025,2025,11,11,"2025-03-11","21:50:00","2025-03-11","23:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO","7FD2-019","Karlsruhe - Stuttgart","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2025,2025,9,9,"2025-02-24","01:30:00","2025-02-24","04:00:00","0d, 2h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-07",null,null,1,1]
[null,"DB InfraGO",7.8,"Karlsruhe - Stuttgart","<","Mühlacker","Wilferdingen-Singen",2025,2025,7,7,"2025-02-11","22:00:00","2025-02-12","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-21",null,null,"2,3",1]
[null,"DB InfraGO","F818-005","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2025,2025,15,15,"2025-04-12","23:40:00","2025-04-13","04:50:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO","F818-015","Karlsruhe - Stuttgart","< >","Pforzheim Hbf","Mühlacker",2025,2025,16,16,"2025-04-15","23:00:00","2025-04-16","04:50:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO","F818-023","Karlsruhe - Stuttgart","<","Pforzheim Hbf","Wilferdingen-Singen",2025,2025,16,16,"2025-04-16","23:00:00","2025-04-17","00:15:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO","F843-020","Karlsruhe - Stuttgart","< >","Grötzingen","Grötzingen",2025,2025,29,29,"2025-07-16","22:10:00","2025-07-17","00:10:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO","102E1-003","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker",2025,2025,13,13,"2025-03-26","22:00:00","2025-03-27","00:50:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-18",null,null,"3,4",1]
[null,"DB InfraGO","102E1-017","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker",2025,2025,13,13,"2025-03-29","22:00:00","2025-03-30","04:30:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"6,7",1]
[null,"DB InfraGO","14890-004","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Karlsruhe-Durlach",2025,2025,39,40,"2025-09-28","01:00:00","2025-09-29","04:00:00","1d, 3h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-08",null,null,"1,7",1]
[null,"DB InfraGO","1853F-002","Karlsruhe - Stuttgart","< >","Mühlacker Em Süd","Mühlacker",2025,2025,38,38,"2025-09-20","00:00:00","2025-09-20","06:00:00","0d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,6,1]
[null,"DB InfraGO","26FC8-001","Karlsruhe - Stuttgart","<","Wilferdingen-Singen","Söllingen Reetzstraße",2024,2024,51,51,"2024-12-17","21:00:00","2024-12-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO","117AB-005","Regensburg - Wels","< >","Plattling","Wallersdorf",2025,2025,40,40,"2025-10-03","23:20:00","2025-10-04","04:50:00","0d, 5h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO","15823-004","Regensburg - Wels","< >","Plattling","Plattling",2025,2025,13,14,"2025-03-30","07:00:00","2025-04-02","07:00:00","3d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"1,2,3,7",1]
[null,"DB InfraGO","18B18-010","Regensburg - Wels","< >","Grafling","Plattling",2025,2025,26,26,"2025-06-23","20:00:00","2025-06-24","06:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO","76BA-003","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,26,35,"2025-06-23","04:00:00","2025-08-25","04:00:00","63d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","84AD-020","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,21,21,"2025-05-23","00:01:00","2025-05-23","04:30:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-02",null,null,5,1]
[null,"DB InfraGO","9B66-005","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2025,2025,9,22,"2025-03-01","22:00:00","2025-05-31","05:00:00","90d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-13",null,null,"4,5",1]
[null,"DB InfraGO","9CF1-009","Karlsruhe - Strasbourg","<","Orschweier Nord","Baden-Baden",2025,2025,19,25,"2025-05-10","23:30:00","2025-06-22","07:30:00","42d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2023-01-04",null,null,6,1]
[null,"DB InfraGO","A5CD-019","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2025,2025,18,19,"2025-05-03","21:00:00","2025-05-05","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-11",null,null,"6,7",1]
[null,"DB InfraGO","A5CF-013","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt",2025,2025,37,37,"2025-09-08","22:00:00","2025-09-12","04:00:00","3d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-12",null,null,"1,2,3,4",1]
[null,"DB InfraGO","A5CD-028","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt",2025,2025,14,15,"2025-04-06","23:00:00","2025-04-12","04:00:00","5d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO","A5CF-024","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2025,2025,36,37,"2025-09-06","21:00:00","2025-09-08","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO","A5CD-040","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2025,2025,18,19,"2025-05-03","21:00:00","2025-05-05","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO","8C99-027","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2025,2025,16,17,"2025-04-18","00:00:00","2025-04-22","04:00:00","4d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","1474A-010","Karlsruhe - Strasbourg","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2025,2025,18,19,"2025-05-02","00:00:00","2025-05-05","23:59:00","3d, 23h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-05-24",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1710C-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2025,2025,34,35,"2025-08-24","23:00:00","2025-08-25","01:48:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-05-09",null,null,"1,7",1]
[null,"DB InfraGO","17110-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2025,2025,35,35,"2025-08-26","22:00:00","2025-08-26","23:02:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-09",null,null,2,1]
[null,"DB InfraGO","17776-001","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2025,2025,15,16,"2025-04-11","22:30:00","2025-04-20","04:30:00","8d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-12",null,null,6,1]
[null,"DB InfraGO","17776-016","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2025,2025,15,16,"2025-04-13","23:00:00","2025-04-14","05:00:00","0d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-12",null,null,7,1]
[null,"DB InfraGO","17776-028","Karlsruhe - Strasbourg","< >","Rastatt","Muggensturm Badesee",2025,2025,17,17,"2025-04-21","01:00:00","2025-04-21","03:30:00","0d, 2h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-12",null,null,1,1]
[null,"DB InfraGO","180E7-009","Karlsruhe - Strasbourg","<","Heidelberg-Wieblingen","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,21,21,"2025-05-21","23:00:00","2025-05-22","02:41:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-05-22",null,null,"3,4",1]
[null,"DB InfraGO","184F6-012","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2025,2025,17,17,"2025-04-21","02:14:00","2025-04-21","03:16:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-09",null,null,1,1]
[null,"DB InfraGO","18F10-016","Karlsruhe - Strasbourg",">","Achern","Appenweier Nord",2025,2025,44,44,"2025-10-29","03:10:00","2025-10-29","04:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","1A43F-016","Karlsruhe - Strasbourg","< >","Achern","Achern",2025,2025,36,36,"2025-09-01","04:30:00","2025-09-05","23:30:00","4d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1A443-004","Karlsruhe - Strasbourg","< >","Achern","Achern",2025,2025,49,49,"2025-12-03","02:00:00","2025-12-04","05:00:00","1d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO","7966-001","Mannheim - Karlsruhe",">","Kraichtal","Vaihingen (Enz)",2025,2025,36,37,"2025-09-07","23:00:00","2025-09-14","05:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2023-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","27CF5-002","Mannheim - Karlsruhe",">","Glems","Stuttgart-Zazenhausen",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","05:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-05-06",null,null,7,1]
[null,"DB InfraGO","2AFC5-004","Mannheim - Karlsruhe",">","Vaihingen (Enz)","Vaihingen (Enz)",2024,2024,51,52,"2024-12-19","23:00:00","2024-12-27","00:30:00","7d, 1h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-04-17",null,null,4,1]
[null,"DB InfraGO","7971-001","Mannheim - Karlsruhe",">","Ötigheim","Rastatt",2025,2025,45,45,"2025-11-05","22:30:00","2025-11-07","05:10:00","1d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-30",null,null,"3,4",1]
[null,"DB InfraGO","84AD-016","Mannheim - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,20,21,"2025-05-17","00:01:00","2025-05-23","04:30:00","6d, 4h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","8FE1-002","Mannheim - Karlsruhe","< >","Hockenheim","Hockenheim",2025,2025,31,32,"2025-08-01","23:00:00","2025-08-04","05:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-14",null,null,"1,5,6,7",1]
[null,"DB InfraGO","8FE1-011","Mannheim - Karlsruhe","< >","Schwetzingen","Schwetzingen",2025,2025,32,33,"2025-08-08","23:00:00","2025-08-11","05:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-15",null,null,"1,5,6,7",1]
[null,"DB InfraGO","A5CE-005","Mannheim - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Durmersheim",2025,2025,22,22,"2025-05-28","23:00:00","2025-06-01","04:00:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-11",null,null,"3,4,5,6",1]
[null,"DB InfraGO","A537-007","Mannheim - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Durmersheim",2025,2025,48,49,"2025-11-29","21:00:00","2025-12-01","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-12",null,null,"6,7",1]
[null,"DB InfraGO","799B-003","Mannheim - Karlsruhe",">","Ötigheim","Rastatt",2025,2025,22,23,"2025-06-01","22:00:00","2025-06-03","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-17",null,null,"1,7",1]
[null,"DB InfraGO","79A7-002","Mannheim - Karlsruhe",">","Mannheim-Rheinau","Schwetzingen",2025,2025,33,34,"2025-08-16","22:00:00","2025-08-18","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-03-02",null,null,"6,7",1]
[null,"DB InfraGO","EACB-001","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,26,26,"2025-06-23","23:00:00","2025-06-24","05:30:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-03-22",null,null,"1,2",1]
[null,"DB InfraGO","10D60-001","Mannheim - Karlsruhe","< >","Ötigheim","Ötigheim",2025,2025,19,19,"2025-05-08","22:00:00","2025-05-09","05:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-23",null,null,"4,5",1]
[null,"DB InfraGO","10877-003","Mannheim - Karlsruhe","<","Rastatt","Ötigheim",2025,2025,16,16,"2025-04-16","22:00:00","2025-04-17","00:50:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-08-22",null,null,"3,4",1]
[null,"DB InfraGO","12C2F-026","Mannheim - Karlsruhe","< >","Waghäusel","Hockenheim",2025,2025,40,40,"2025-09-29","01:00:00","2025-09-30","05:30:00","1d, 4h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,2",1]
[null,"DB InfraGO","14D10-005","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,31,31,"2025-08-02","03:40:00","2025-08-02","04:40:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-09",null,null,6,1]
[null,"DB InfraGO","157BD-013","Mannheim - Karlsruhe","< >","Oftersheim","Schwetzingen",2025,2025,37,37,"2025-09-11","02:30:00","2025-09-11","03:40:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-05-25",null,null,4,1]
[null,"DB InfraGO","14D10-024","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2025,2025,31,31,"2025-08-03","01:10:00","2025-08-03","02:45:00","0d, 1h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-05-09",null,null,7,1]
[null,"DB InfraGO","17722-015","Mannheim - Karlsruhe","< >","Waghäusel","Waghäusel",2025,2025,10,10,"2025-03-06","00:30:00","2025-03-06","01:45:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,4,1]
[null,"DB InfraGO","1772F-009","Mannheim - Karlsruhe","< >","Oftersheim","Schwetzingen",2025,2025,10,10,"2025-03-06","22:00:00","2025-03-06","23:10:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,4,1]
[null,"DB InfraGO","1772F-019","Mannheim - Karlsruhe","< >","Waghäusel","Waghäusel",2025,2025,10,10,"2025-03-07","00:10:00","2025-03-07","01:55:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,5,1]
[null,"DB InfraGO",1.7750000000000001E-10,"Mannheim - Karlsruhe","<","Karlsruhe-Dammerstock","Karlsruhe Gbf",2025,2025,11,11,"2025-03-11","00:30:00","2025-03-11","01:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO","177AE-008","Mannheim - Karlsruhe",">","Karlsruhe Hbf Bft Südeinfahrt","Forchheim (b Karlsruhe)",2025,2025,11,11,"2025-03-11","21:50:00","2025-03-11","23:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO","177AE-019","Mannheim - Karlsruhe",">","Karlsruhe Hbf Bft Südeinfahrt","Forchheim (b Karlsruhe)",2025,2025,11,11,"2025-03-12","00:50:00","2025-03-12","02:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-22",null,null,3,1]
[null,"DB InfraGO","177E8-014","Mannheim - Karlsruhe","<","Bashaide","Durmersheim",2025,2025,11,11,"2025-03-13","01:30:00","2025-03-13","02:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-16",null,null,4,1]
[null,"DB InfraGO","13A33-017","Mannheim - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,35,35,"2025-08-31","00:30:00","2025-08-31","05:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,7,1]
[null,"DB InfraGO","17EF1-016","Mannheim - Karlsruhe","< >","Rastatt","Rastatt",2025,2025,17,17,"2025-04-24","00:00:00","2025-04-26","04:00:00","2d, 4h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"4,5,6",1]
[null,"DB InfraGO","12C2F-034","Mannheim - Karlsruhe","< >","Hockenheim","Hockenheim",2025,2025,36,36,"2025-09-01","05:00:00","2025-09-05","21:00:00","4d, 16h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-05-26",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","272D1-002","Mannheim - Karlsruhe","<","Bashaide","Forchheim (b Karlsruhe)",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-13",null,null,"5,6",1]
[null,"DB InfraGO","272FE-002","Mannheim - Karlsruhe","<","Philippsburg Molzau","Graben-Neudorf",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-13",null,null,"5,6",1]
[null,"DB InfraGO","273A3-007","Mannheim - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Bashaide",2024,2024,51,51,"2024-12-21","21:00:00","2024-12-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"6,7",1]
[null,"DB InfraGO","19F34-009","Regensburg - Plzen","< >","Maxhütte-Haidhof","Maxh-Haidh DB-Gr",2025,2025,24,34,"2025-06-15","00:00:00","2025-08-22","00:00:00","68d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","17C7E-006","Mannheim - Karlsruhe","< >","Mühlacker Em Süd","Mühlacker",2025,2025,13,13,"2025-03-26","00:55:00","2025-03-27","04:10:00","1d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO","17C7E-016","Mannheim - Karlsruhe","< >","Mühlacker Em Nord","Mühlacker",2025,2025,14,14,"2025-04-01","00:55:00","2025-04-02","04:10:00","1d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO","2B992-026","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2024,2024,51,51,"2024-12-18","21:40:00","2024-12-20","04:20:00","1d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"3,4",1]
[null,"DB InfraGO","19FE1-020","Stuttgart - München","< >","München-Pasing","München-Pasing",2025,2025,50,50,"2025-12-10","01:10:00","2025-12-10","04:40:00","0d, 3h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,3,1]
[null,"DB InfraGO","19FE1-005","Stuttgart - München","< >","München-Pasing","München-Pasing West",2025,2025,49,49,"2025-12-01","22:45:00","2025-12-02","04:40:00","0d, 5h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,"1,2",1]
[null,"DB InfraGO","1A453-002","München - Salzburg","<","München-Solln","Mü Heimeranplatz",2025,2025,17,18,"2025-04-25","22:00:00","2025-04-29","06:00:00","3d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-04",null,null,"1,5,6,7",1]
[null,"DB InfraGO","173A8-004","Stuttgart - München","<","Mering Üst","Olching",2025,2025,18,18,"2025-05-03","02:00:00","2025-05-03","05:00:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-25",null,null,6,1]
[null,"DB InfraGO","17A54-007","Stuttgart - München","< >","Mering Üst","Augsburg-Hochzoll Abzweig",2025,2025,30,31,"2025-07-27","23:00:00","2025-07-28","05:00:00","0d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"1,7",1]
[null,"DB InfraGO","1A256-007","Stuttgart - München","< >","Olching","Olching",2025,2025,36,36,"2025-09-02","00:01:00","2025-09-02","05:10:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,2,1]
[null,"DB InfraGO","270F3-003","Stuttgart - München","<","Augsburg Hbf","Augsburg-Hochzoll Abzweig",2024,2024,51,51,"2024-12-19","20:45:00","2024-12-20","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-22",null,null,"4,5",1]
[null,"DB InfraGO","272A4-003","Stuttgart - München","<","Augsburg Hbf","Augsburg-Hochzoll",2024,2024,51,51,"2024-12-20","21:00:00","2024-12-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-22",null,null,"5,6",1]
[null,"DB InfraGO","18FB7-002","Stuttgart - München",">","München-Pasing","Gauting",2025,2025,38,38,"2025-09-16","01:00:00","2025-09-16","04:30:00","0d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-06",null,null,2,1]
[null,"DB InfraGO","1C339-002","Stuttgart - München","<","München-Pasing","München Hbf",2025,2025,27,27,"2025-06-30","22:00:00","2025-07-04","05:30:00","3d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4",1]
[null,"DB InfraGO","AFE8-014","München - Regensburg","< >","Obertraubling","Regensburg Ost",2025,2025,17,18,"2025-04-27","21:00:00","2025-04-28","05:00:00","0d, 8h","Continuous","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-20",null,null,"1,7",1]
[null,"DB InfraGO","B46E-005","München - Regensburg","< >","Obertraubling","Regensburg Ost",2025,2025,37,37,"2025-09-12","21:00:00","2025-09-13","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"5,6",1]
[null,"DB InfraGO","1288B-023","München - Regensburg","< >","Regensburg Hbf","Regensburg Hbf",2025,2025,40,40,"2025-10-01","22:00:00","2025-10-02","04:50:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO","1551A-001","München - Regensburg",">","Köfering","Regensburg Ost",2025,2025,44,44,"2025-10-29","22:00:00","2025-10-29","23:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2023-11-13",null,null,3,1]
[null,"DB InfraGO","1679B-005","München - Regensburg","< >","Regensburg Ost","Obertraubling",2025,2025,49,49,"2025-12-07","03:00:00","2025-12-07","04:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,7,1]
[null,"DB InfraGO","168B6-004","München - Regensburg","< >","Regensburg Hbf","Regensburg Hbf",2025,2025,40,40,"2025-10-04","23:30:00","2025-10-05","05:00:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO","155B8-034","München - Regensburg","< >","Regensburg Ost","Regensburg Ost",2025,2025,34,34,"2025-08-20","21:00:00","2025-08-24","05:00:00","3d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4,5,6,7",1]
[null,"DB InfraGO","7F0F-003","München - Salzburg","< >","Haar","Kirchseeon",2025,2025,23,23,"2025-06-03","03:00:00","2025-06-03","04:00:00","0d, 1h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-26",null,null,2,1]
[null,"DB InfraGO","13D31-004","München - Salzburg","< >","München Süd","München Süd",2025,2025,29,29,"2025-07-18","22:40:00","2025-07-19","05:10:00","0d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-08",null,null,"5,6",1]
[null,"DB InfraGO","13D31-010","München - Salzburg",">","München Süd","München Ost Pbf",2025,2025,30,30,"2025-07-24","01:00:00","2025-07-24","05:00:00","0d, 4h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-08",null,null,4,1]
[null,"DB InfraGO","14F94-001","München - Salzburg",">","Zorneding","Zorneding",2025,2025,45,45,"2025-11-09","21:45:00","2025-11-09","23:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO","151D1-002","München - Salzburg","< >","Kirchseeon","Kirchseeon",2025,2025,46,46,"2025-11-10","23:50:00","2025-11-11","04:50:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO","15211-003","München - Salzburg","<","Haar","Haar",2025,2025,46,46,"2025-11-13","00:01:00","2025-11-13","05:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,4,1]
[null,"DB InfraGO","153E3-004","München - Salzburg","< >","Gr-Karolinenf  Ü","Rosenheim",2025,2025,47,47,"2025-11-17","01:50:00","2025-11-17","03:20:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO","15599-007","München - Salzburg","<","Zorneding","Haar",2024,2024,51,51,"2024-12-16","22:45:00","2024-12-17","00:40:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,"1,2",1]
[null,"DB InfraGO","15599-013","München - Salzburg","<","Ostermünchen","Aßling (Oberbay)",2024,2024,51,51,"2024-12-18","00:05:00","2024-12-18","02:10:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,3,1]
[null,"DB InfraGO","15D38-003","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,48,48,"2025-11-28","02:40:00","2025-11-28","04:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,5,1]
[null,"DB InfraGO","15FC3-005","München - Salzburg",">","München Hbf","München Süd",2024,2024,51,51,"2024-12-21","03:50:00","2024-12-21","05:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",12,12",null,null,null,"N",null,"2024-05-14",null,null,6,1]
[null,"DB InfraGO","15FC3-011","München - Salzburg","<","München Süd","München Hbf",2024,2024,51,51,"2024-12-22","03:45:00","2024-12-22","05:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",10,10",null,null,null,"N",null,"2024-05-14",null,null,7,1]
[null,"DB InfraGO","169A1-002","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,24,25,"2025-06-11","22:30:00","2025-06-17","04:30:00","5d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO","18B1D-007","München - Salzburg",">","München Ost Pbf","Haar",2025,2025,46,46,"2025-11-16","01:45:00","2025-11-16","05:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2023-05-27",null,null,7,1]
[null,"DB InfraGO","18B1D-014","München - Salzburg","<","Zorneding","München-Trudering",2025,2025,47,47,"2025-11-17","03:45:00","2025-11-17","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-05-27",null,null,1,1]
[null,"DB InfraGO","18B1D-025","München - Salzburg","<","Rosenheim","Ostermünchen",2025,2025,47,47,"2025-11-20","01:55:00","2025-11-20","05:15:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-05-27",null,null,4,1]
[null,"DB InfraGO","787A-010","München - Salzburg","< >","München Süd","München Süd",2025,2025,47,48,"2025-11-23","00:00:00","2025-11-25","06:00:00","2d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-29",null,null,"1,2,7",1]
[null,"DB InfraGO","17603-001","München - Salzburg",">","München-Pasing","München-Freiham",2025,2025,14,14,"2025-04-01","01:00:00","2025-04-04","05:00:00","3d, 4h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-30",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1B61B-002","München - Salzburg","< >","München-Pasing","München Hbf tief",2025,2025,19,20,"2025-05-09","22:40:00","2025-05-12","04:40:00","2d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-29",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1B63F-005","München - Salzburg","< >","München Hbf tief","München Ost Pbf",2025,2025,42,43,"2025-10-17","22:40:00","2025-10-20","04:40:00","2d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1BDF3-003","München - Salzburg",">","München Isartor","München Ost Pbf",2025,2025,45,48,"2025-11-06","21:40:00","2025-11-28","04:40:00","21d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-06-02",null,null,4,1]
[null,"DB InfraGO","1CD33-014","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,30,30,"2025-07-24","22:40:00","2025-07-26","04:40:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO","168B5-008","München - Salzburg",">","München Ost Pbf","München-Riem West",2025,2025,32,32,"2025-08-06","22:20:00","2025-08-09","04:20:00","2d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-16",null,null,"3,4,5",1]
[null,"DB InfraGO",0.1734,"München - Salzburg",">","München-Riem West","München Ost Pbf",2025,2025,43,43,"2025-10-25","22:30:00","2025-10-26","04:30:00","0d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO","183AF-013","München - Salzburg","<","München-Riem West","München Ost Pbf",2025,2025,23,23,"2025-06-03","22:20:00","2025-06-07","04:20:00","3d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1BDE9-005","München - Salzburg","<","München-Riem West","München Ost Pbf",2025,2025,32,35,"2025-08-07","21:40:00","2025-08-29","04:40:00","21d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-01",null,null,4,1]
[null,"DB InfraGO","2B992-013","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2024,2024,51,51,"2024-12-18","21:40:00","2024-12-20","04:20:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"N",null,"2024-05-17",null,null,"3,4",1]
[null,"DB InfraGO","16558-006","München - Salzburg",">","München Ost Pbf","München-Riem Pbf",2025,2025,36,36,"2025-09-05","01:00:00","2025-09-05","02:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2023-11-06",null,null,5,1]
[null,"DB InfraGO","1C25D-004","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,18,19,"2025-05-02","00:00:00","2025-05-09","23:59:00","7d, 23h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","169A1-004","München - Salzburg","<","München-Giesing","München Ost Pbf",2025,2025,42,43,"2025-10-17","22:30:00","2025-10-20","04:30:00","2d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1B851-013","München - Salzburg","< >","München St-Martin-Straße","München Ost Pbf",2025,2025,14,17,"2025-04-03","21:40:00","2025-04-25","04:40:00","21d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-03",null,null,4,1]
[null,"DB InfraGO","1BDE9-016","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,32,35,"2025-08-07","21:40:00","2025-08-29","04:20:00","21d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-01",null,null,4,1]
[null,"DB InfraGO","1BDF0-006","München - Salzburg","<","München-Giesing","München Ost Pbf",2025,2025,36,38,"2025-09-04","21:40:00","2025-09-19","04:40:00","14d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-02",null,null,4,1]
[null,"DB InfraGO","169CB-010","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2025,2025,25,25,"2025-06-20","22:40:00","2025-06-21","04:40:00","0d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-06-01",null,null,5,1]
[null,"DB InfraGO","1BDE6-008","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,18,20,"2025-05-01","21:40:00","2025-05-16","04:40:00","14d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,4,1]
[null,"DB InfraGO","1C777-001","München - Salzburg","<","München-Steinhausen","München Ost Pbf",2025,2025,41,42,"2025-10-06","22:40:00","2025-10-17","04:40:00","10d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"1,2,3,4",1]
[null,"DB InfraGO","17590-005","Stuttgart - München","< >","Olching","Maisach",2025,2025,19,19,"2025-05-05","01:00:00","2025-05-05","05:00:00","0d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,1,1]
[null,"DB InfraGO","1792F-008","Stuttgart - München","<","Maisach","München-Lochhausen",2025,2025,36,36,"2025-09-03","23:25:00","2025-09-05","04:30:00","1d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-06",null,null,"3,4",1]
[null,"DB InfraGO","19FE1-014","Stuttgart - München",">","München-Pasing","München-Pasing Weiche 352",2025,2025,50,50,"2025-12-09","01:10:00","2025-12-09","04:40:00","0d, 3h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-16",null,null,2,1]
[null,"DB InfraGO","1B59B-011","Stuttgart - München","< >","München-Lochhausen","Mammendorf",2025,2025,50,50,"2025-12-12","22:30:00","2025-12-13","04:30:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-29",null,null,"5,6",1]
[null,"DB InfraGO","1A256-024","Stuttgart - München","<","Maisach","München-Lochhausen",2025,2025,36,36,"2025-09-01","22:00:00","2025-09-02","00:01:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO","19FE1-003","Stuttgart - München","<","Puchheim","München-Pasing",2025,2025,49,49,"2025-12-03","22:45:00","2025-12-05","04:35:00","1d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-16",null,null,"3,4",1]
[null,"DB InfraGO","82E0-003","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2025,2025,38,39,"2025-09-19","21:30:00","2025-09-25","05:30:00","5d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2022-11-30",null,null,"1,2,3,5",1]
[null,"DB InfraGO","82E0-010","Mannheim - Karlsruhe","< >","Schwetzingen","Schwetzingen",2025,2025,41,41,"2025-10-07","21:30:00","2025-10-10","05:30:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-01",null,null,"2,3,4",1]
[null,"DB InfraGO","8FE1-009","Mannheim - Karlsruhe","< >","Schwetzingen","Schwetzingen",2025,2025,31,32,"2025-08-01","23:00:00","2025-08-04","05:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-14",null,null,"1,5,6,7",1]
[null,"DB InfraGO","9A89-008","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,12,19,"2025-03-21","00:00:00","2025-05-11","23:59:00","51d, 22h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9105-011","Nürnberg - Plzen","< >","Neunkirchen a Sand","Neunkirchen a Sand",2025,2025,13,15,"2025-03-24","06:00:00","2025-04-07","00:00:00","13d, 17h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9E83-001","Gemünden - Bamberg - Nürnberg",">","Nürnberg Hbf","Bamberg",2025,2025,14,14,"2025-03-31","21:00:00","2025-04-05","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-19",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","19CAB-007","Gemünden - Bamberg - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Gbf",2025,2025,20,20,"2025-05-13","03:30:00","2025-05-13","05:00:00","0d, 1h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,2,1]
[null,"DB InfraGO","1A20E-005","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2025,2025,16,16,"2025-04-15","03:40:00","2025-04-15","04:40:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,2,1]
[null,"DB InfraGO","1A643-007","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullendorf",2025,2025,45,45,"2025-11-08","21:00:00","2025-11-09","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-04-27",null,null,"6,7",1]
[null,"DB InfraGO","1A6F6-002","Gemünden - Bamberg - Nürnberg","<","Strullendorf","Eggolsheim Süd",2025,2025,43,43,"2025-10-21","21:00:00","2025-10-22","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-04-27",null,null,"2,3",1]
[null,"DB InfraGO","1A6F6-014","Gemünden - Bamberg - Nürnberg","<","Hirschaid","Bamberg",2025,2025,43,43,"2025-10-25","21:00:00","2025-10-26","05:00:00","0d, 9h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO","1A6F6-023","Gemünden - Bamberg - Nürnberg",">","Eggolsheim Süd","Strullendorf",2025,2025,44,44,"2025-11-01","21:00:00","2025-11-02","01:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO","C4FA-010","Gemünden - Bamberg - Nürnberg","< >","Nür Jansenbr","Fürth (Bay) Gbf",2025,2025,11,12,"2025-03-16","22:00:00","2025-03-17","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO","1A391-004","Gemünden - Bamberg - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Dürrenhof",2025,2025,13,13,"2025-03-26","02:00:00","2025-03-26","04:30:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,3,1]
[null,"DB InfraGO","8D9F-003","Nürnberg - Plzen","< >","Arzberg (Oberfr)","Schirnding",2025,2025,34,38,"2025-08-24","22:35:00","2025-09-20","04:35:00","26d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","8D9F-013","Nürnberg - Plzen","< >","Schirnding","Schirnding",2025,2025,39,40,"2025-09-28","06:35:00","2025-09-30","04:20:00","1d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-13",null,null,"1,2,7",1]
[null,"DB InfraGO","9105-009","Nürnberg - Plzen","<","Neunkirchen a Sand","Lauf (rechts Pegnitz)",2025,2025,12,13,"2025-03-20","23:00:00","2025-03-24","05:00:00","3d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-15",null,null,"4,5,6,7",1]
[null,"DB InfraGO","199D2-007","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2025,2025,31,33,"2025-08-01","22:00:00","2025-08-12","05:00:00","10d, 7h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","199D2-013","Nürnberg - Plzen","< >","Schnabelwaid","Kirchenlaibach",2025,2025,33,35,"2025-08-16","05:00:00","2025-08-30","05:00:00","14d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,0",null,null,null,"N",null,"2023-09-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1AEF7-003","Nürnberg - Plzen","< >","Nürnberg Hbf","Nürnberg Hbf",2025,2025,22,24,"2025-05-29","06:00:00","2025-06-10","06:00:00","12d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-04-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1AEF7-013","Nürnberg - Plzen","< >","Nürnberg Hbf","Nürnberg Hbf",2025,2025,23,24,"2025-06-07","22:00:00","2025-06-09","06:00:00","1d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-04-05",null,null,"6,7",1]
[null,"DB InfraGO","C4FA-009","Gemünden - Bamberg - Nürnberg","< >","Nürnberg-Doos","Fürth (Bay) Gbf",2025,2025,11,12,"2025-03-16","22:00:00","2025-03-17","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO","15574-001","Gemünden - Bamberg - Nürnberg","< >","Nürnberg Nordost","Fürth (Bay) Gbf",2025,2025,39,39,"2025-09-27","21:00:00","2025-09-28","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","8F75-021","Nürnberg - Regensburg",">","Nürnberg-Langwasser","Nürnberg Reichswald",2025,2025,17,17,"2025-04-25","22:45:00","2025-04-26","04:45:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2022-12-14",null,null,"5,6",1]
[null,"DB InfraGO","C4FA-002","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Nürnberg Großmarkt",2025,2025,11,11,"2025-03-15","08:00:00","2025-03-15","16:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,6,1]
[null,"DB InfraGO","1A579-002","Gemünden - Bamberg - Nürnberg",">","Nürnberg Großmarkt","Fürth (Bay) Gbf",2025,2025,39,39,"2025-09-24","00:01:00","2025-09-24","02:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","19CED-005","Gemünden - Bamberg - Nürnberg",">","Nürnberg Großmarkt","Fürth (Bay) Gbf",2025,2025,16,16,"2025-04-14","00:30:00","2025-04-14","05:00:00","0d, 4h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-10-30",null,null,1,1]
[null,"DB InfraGO","1575C-003","Stuttgart - München","< >","Olching","Mammendorf",2025,2025,18,18,"2025-04-28","01:00:00","2025-04-28","04:30:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,1,1]
[null,"DB InfraGO","1A256-003","Stuttgart - München",">","Olching","München Nord Rbf Forstweg",2025,2025,36,36,"2025-09-02","00:01:00","2025-09-02","05:10:00","0d, 5h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-06",null,null,2,1]
[null,"DB InfraGO","B8FC-001","Regensburg - Wels","< >","Plattling","Plattling",2025,2025,33,35,"2025-08-14","06:00:00","2025-08-26","18:00:00","12d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","BC27-004","Regensburg - Wels","< >","Osterhofen (Niederbay)","Plattling",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO","BC27-025","Regensburg - Wels","<","Plattling","Osterhofen (Niederbay)",2025,2025,36,36,"2025-09-02","23:00:00","2025-09-03","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-02-09",null,null,"2,3",1]
[null,"DB InfraGO","BE7B-003","Regensburg - Wels","<","Girching","Sandbach (Niederbay)",2025,2025,35,35,"2025-08-25","21:00:00","2025-08-26","05:00:00","0d, 8h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2023-08-24",null,null,"1,2",1]
[null,"DB InfraGO","BE7B-008","Regensburg - Wels","<","Girching","Vilshofen (Niederbay)",2025,2025,38,39,"2025-09-20","21:00:00","2025-09-23","05:00:00","2d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-08-24",null,null,"1,6,7",1]
[null,"DB InfraGO","10DF4-002","Regensburg - Wels","< >","Plattling","Plattling",2025,2025,24,24,"2025-06-12","22:15:00","2025-06-13","05:15:00","0d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-04",null,null,"4,5",1]
[null,"DB InfraGO","117D3-002","Regensburg - Wels",">","Girching","Plattling",2025,2025,39,39,"2025-09-28","00:30:00","2025-09-28","03:30:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO","12CB3-027","Regensburg - Wels","< >","Passau Hbf","Passau Hbf",2025,2025,41,41,"2025-10-08","22:50:00","2025-10-09","00:30:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO","13177-016","Regensburg - Wels","<","Straubing","Straßkirchen",2025,2025,36,36,"2025-09-02","22:30:00","2025-09-03","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2023-09-04",null,null,"2,3",1]
[null,"DB InfraGO","1335D-002","Regensburg - Wels","< >","Radldorf (Niederbay)","Radldorf (Niederbay)",2025,2025,49,49,"2025-12-01","23:20:00","2025-12-02","04:10:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO","1335D-008","Regensburg - Wels","< >","Radldorf (Niederbay)","Radldorf (Niederbay)",2025,2025,49,49,"2025-12-02","23:50:00","2025-12-03","04:30:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO","13657-024","Regensburg - Wels","<","Radldorf (Niederbay)","Straßkirchen",2025,2025,18,18,"2025-04-28","22:00:00","2025-04-29","04:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"20,20,20",null,null,null,"N",null,"2023-06-13",null,null,"1,2",1]
[null,"DB InfraGO","13821-025","Regensburg - Wels","< >","Straubing","Straubing",2025,2025,24,24,"2025-06-12","05:00:00","2025-06-15","02:00:00","2d, 21h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-13",null,null,"4,5,6,7",1]
[null,"DB InfraGO","13821-036","Regensburg - Wels","< >","Straubing","Straubing",2025,2025,28,28,"2025-07-07","21:00:00","2025-07-10","05:00:00","2d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-13",null,null,"1,2,3,4",1]
[null,"DB InfraGO","14D21-002","Regensburg - Wels",">","Straubing","Radldorf (Niederbay)",2025,2025,39,39,"2025-09-28","01:00:00","2025-09-28","03:00:00","0d, 2h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"13,13,13",null,null,null,"N",null,"2023-09-22",null,null,7,1]
[null,"DB InfraGO","14D21-024","Regensburg - Wels","<","Straubing","Straßkirchen",2025,2025,48,48,"2025-11-27","21:00:00","2025-11-29","05:00:00","1d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2023-09-25",null,null,"4,5",1]
[null,"DB InfraGO","14E1F-004","Regensburg - Wels",">","Straubing","Radldorf (Niederbay)",2025,2025,49,49,"2025-12-03","21:00:00","2025-12-04","05:00:00","0d, 8h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"13,13,13",null,null,null,"N",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO","14E1F-015","Regensburg - Wels",">","Sünching","Mangolding",2025,2025,50,50,"2025-12-10","21:00:00","2025-12-12","05:00:00","1d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-13",null,null,"3,4",1]
[null,"DB InfraGO","15256-001","Regensburg - Wels",">","Straubing","Radldorf (Niederbay)",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-17","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3",1]
[null,"DB InfraGO","13445-009","Regensburg - Wels",">","Mangolding","Obertraubling",2025,2025,40,40,"2025-10-04","23:15:00","2025-10-05","01:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO","16FCB-001","Regensburg - Wels","< >","Straßkirchen","Straubing",2025,2025,38,39,"2025-09-21","20:00:00","2025-09-22","05:00:00","0d, 9h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-19",null,null,"1,7",1]
[null,"DB InfraGO","1A0DF-006","Regensburg - Wels","< >","Schalding","Passau Hbf",2025,2025,14,14,"2025-04-04","23:00:00","2025-04-05","05:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,"5,6",1]
[null,"DB InfraGO","1A0DF-014","Regensburg - Wels","<","Schalding","Passau Hbf",2025,2025,19,20,"2025-05-11","23:30:00","2025-05-12","04:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-04-17",null,null,"1,7",1]
[null,"DB InfraGO","12CB3-001","Regensburg - Wels","< >","Passau Gbf","Passau Gbf",2025,2025,40,41,"2025-10-05","21:00:00","2025-10-06","03:10:00","0d, 6h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO","BE48-006","Stuttgart - München",">","Plochingen","Tübingen Gbf",2025,2025,20,20,"2025-05-14","23:00:00","2025-05-15","05:00:00","0d, 6h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO","127F5-001","Stuttgart - München","< >","Plochingen","Wendlingen (Neckar)",2025,2025,42,42,"2025-10-13","01:30:00","2025-10-13","04:30:00","0d, 3h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-05",null,null,1,1]
[null,"DB InfraGO","9070-020","München - Salzburg","< >","Prien a Chiemsee","Aschau (Chiemgau)",2025,2025,26,26,"2025-06-28","00:00:00","2025-06-29","05:00:00","1d, 5h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"6,7",1]
[null,"DB InfraGO","16F51-002","Regensburg - Wels","< >","Regensburg Bbf","Sinzing (b Regensburg)",2025,2025,44,44,"2025-10-28","21:30:00","2025-10-29","00:01:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-26",null,null,"2,3",1]
[null,"DB InfraGO","8701-010","Nürnberg - Regensburg","< >","Feucht","Postbauer-Heng",2025,2025,41,42,"2025-10-11","23:30:00","2025-10-13","04:30:00","1d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-05",null,null,"6,7",1]
[null,"DB InfraGO","8F75-020","Nürnberg - Regensburg","<","Nürnberg-Dutzendteich","Feucht",2025,2025,17,17,"2025-04-25","22:45:00","2025-04-26","04:45:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-12-14",null,null,"5,6",1]
[null,"DB InfraGO","90D9-010","Nürnberg - Regensburg","<","Parsberg","Parsberg",2025,2025,16,16,"2025-04-18","05:00:00","2025-04-18","23:00:00","0d, 18h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-19",null,null,5,1]
[null,"DB InfraGO","8F75-042","Nürnberg - Regensburg","<","Nürnberg Reichswald","Nürnberg Reichswald",2025,2025,16,16,"2025-04-19","04:00:00","2025-04-19","18:00:00","0d, 14h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-19",null,null,6,1]
[null,"DB InfraGO","9E1C-003","Nürnberg - Regensburg",">","Regensburg Bbf","Nürnberg Hbf",2025,2025,41,41,"2025-10-06","21:00:00","2025-10-11","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-09",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","B90E-006","Nürnberg - Regensburg","< >","Ochenbruck","Postbauer-Heng",2025,2025,41,41,"2025-10-08","00:10:00","2025-10-08","04:15:00","0d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-06",null,null,3,1]
[null,"DB InfraGO","12A6A-005","Nürnberg - Regensburg",">","Undorf","Parsberg",2025,2025,39,39,"2025-09-28","04:30:00","2025-09-28","06:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO","12A6A-013","Nürnberg - Regensburg",">","Regensburg Bbf","Beratzhausen",2025,2025,40,40,"2025-09-30","03:15:00","2025-09-30","04:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO","12B6C-004","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg Dörnberg",2025,2025,49,49,"2025-12-04","01:40:00","2025-12-04","02:40:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,4,1]
[null,"DB InfraGO","15360-002","Nürnberg - Regensburg","<","Parsberg","Beratzhausen",2025,2025,41,41,"2025-10-11","22:00:00","2025-10-12","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO","1599C-004","Nürnberg - Regensburg","<","Beratzhausen","Undorf",2025,2025,40,40,"2025-10-04","23:30:00","2025-10-05","01:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO","159C9-001","Nürnberg - Regensburg",">","Regensburg Bbf","Undorf",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","04:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO","159C9-015","Nürnberg - Regensburg",">","Regensburg Hbf","Undorf",2025,2025,15,15,"2025-04-13","03:00:00","2025-04-13","04:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO","1B666-004","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Nürnberg Reichswald",2025,2025,30,30,"2025-07-22","21:00:00","2025-07-23","06:00:00","0d, 9h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2023-11-03",null,null,"2,3",1]
[null,"DB InfraGO","1B6B8-006","Nürnberg - Regensburg","<","Nürnberg-Dutzendteich","Nürnberg Reichswald",2025,2025,31,31,"2025-07-30","21:00:00","2025-07-31","06:00:00","0d, 9h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-10-27",null,null,"3,4",1]
[null,"DB InfraGO","166B1-003","Regensburg - Plzen","< >","Nabburg","Schwandorf",2025,2025,39,41,"2025-09-26","22:00:00","2025-10-10","05:00:00","13d, 7h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","12B6C-023","Regensburg - Plzen",">","Regensburg Hbf","Regensburg Walhallastraße",2025,2025,49,49,"2025-12-01","02:00:00","2025-12-01","02:50:00","0d, 0h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"13,,13",null,null,null,"N",null,"2023-09-29",null,null,1,1]
[null,"DB InfraGO","19F34-006","Regensburg - Plzen","< >","Schwandorf","Schwandorf",2025,2025,24,28,"2025-06-15","00:00:00","2025-07-13","23:59:00","28d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","19C2C-009","Regensburg - Plzen","< >","Regensburg-Wutzlhofen","Regenstauf",2025,2025,34,35,"2025-08-22","05:00:00","2025-08-26","19:00:00","4d, 14h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-30",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","18400-013","Regensburg - Plzen","< >","Schwandorf","Schwandorf",2025,2025,23,24,"2025-06-05","12:00:00","2025-06-14","12:00:00","9d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","19108-006","Regensburg - Plzen","< >","Regensburg Ost","Regensburg Ost",2025,2025,13,14,"2025-03-26","21:00:00","2025-03-31","05:00:00","4d, 7h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4,5,6,7",1]
[null,"DB InfraGO","155B8-021","Regensburg - Plzen","< >","Regensburg Ost","Regensburg Ost",2025,2025,23,25,"2025-06-05","21:00:00","2025-06-20","05:00:00","14d, 8h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","A7C4-001","Darmstadt - Aschaffenburg","< >","Darmstadt Bergschneise","Darmstadt Hbf",2025,2025,36,36,"2025-09-06","22:00:00","2025-09-07","07:00:00","0d, 9h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-12",null,null,"6,7",1]
[null,"DB InfraGO","8DAE-004","München - Salzburg",">","Teisendorf","Freilassing",2025,2025,42,43,"2025-10-19","22:00:00","2025-10-24","05:00:00","4d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2022-12-12",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","8E14-004","München - Salzburg","< >","Übersee","Übersee",2025,2025,19,23,"2025-05-07","21:00:00","2025-06-07","05:00:00","30d, 8h","Periodical",null,null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2022-12-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","8F29-016","München - Salzburg","< >","Teisendorf","Freilassing",2025,2025,46,47,"2025-11-15","23:00:00","2025-11-17","04:00:00","1d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-14",null,null,"6,7",1]
[null,"DB InfraGO","90F3-006","München - Salzburg","<","Rumgraben","Übersee",2025,2025,33,33,"2025-08-11","05:00:00","2025-08-11","23:00:00","0d, 18h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2022-12-15",null,null,1,1]
[null,"DB InfraGO","90F3-009","München - Salzburg",">","Übersee","Rumgraben",2025,2025,33,46,"2025-08-11","23:00:00","2025-11-14","21:00:00","94d, 23h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","B603-015","München - Salzburg","<","Landl (Oberbay) Abzw","Rosenheim Ost",2025,2025,31,32,"2025-08-03","06:00:00","2025-08-04","06:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-06-16",null,null,"1,7",1]
[null,"DB InfraGO","14D5F-009","München - Salzburg","< >","Rosenheim","Landl (Oberbay) Abzw",2025,2025,23,23,"2025-06-04","23:00:00","2025-06-05","06:00:00","0d, 7h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO","158DC-001","München - Salzburg","< >","Bad Endorf (Oberbay)","Simssee",2025,2025,32,32,"2025-08-09","22:30:00","2025-08-10","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"6,7",1]
[null,"DB InfraGO","17F38-003","München - Salzburg","< >","Freilassing","Teisendorf",2025,2025,17,19,"2025-04-27","21:00:00","2025-05-11","05:00:00","13d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","183D3-015","München - Salzburg",">","Prien a Chiemsee","Übersee",2025,2025,45,45,"2025-11-06","23:00:00","2025-11-07","02:20:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-05-27",null,null,"4,5",1]
[null,"DB InfraGO","18639-005","München - Salzburg",">","Übersee","Traunstein",2025,2025,13,13,"2025-03-29","22:15:00","2025-03-30","01:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-28",null,null,"6,7",1]
[null,"DB InfraGO","18E77-013","München - Salzburg","< >","Traunstein","Traunstein",2025,2025,18,19,"2025-05-03","08:00:00","2025-05-09","16:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","9070-013","München - Salzburg","<","Rottau","Prien a Chiemsee",2025,2025,12,14,"2025-03-21","21:00:00","2025-04-04","05:00:00","13d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9070-028","München - Salzburg","< >","Prien a Chiemsee","Rottau",2025,2025,34,34,"2025-08-18","05:00:00","2025-08-22","21:00:00","4d, 16h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","9070-034","München - Salzburg","<","Prien a Chiemsee","Bad Endorf (Oberbay)",2025,2025,38,38,"2025-09-15","00:00:00","2025-09-15","05:00:00","0d, 5h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-09",null,null,1,1]
[null,"DB InfraGO","14D5F-002","München - Salzburg","< >","Rosenheim","Rosenheim",2025,2025,19,19,"2025-05-05","22:00:00","2025-05-06","06:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-09",null,null,"1,2",1]
[null,"DB InfraGO","14D5F-015","München - Salzburg","< >","Rosenheim","Rosenheim",2025,2025,31,31,"2025-07-28","22:00:00","2025-07-30","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-09",null,null,"1,2",1]
[null,"DB InfraGO","18400-008","Regensburg - Plzen","< >","Furth im Wald","Furth im Wald",2025,2025,44,44,"2025-11-01","19:00:00","2025-11-02","09:00:00","0d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-01",null,null,"6,7",1]
[null,"DB InfraGO","BF16-005","Gemünden - Bamberg - Nürnberg",">","Schweinfurt Hbf","Schweinfurt Hbf",2025,2025,27,30,"2025-07-03","07:00:00","2025-07-25","07:00:00","22d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","9827-046","Mannheim - Karlsruhe",">","StrWe 4800/4842","Illingen (Württ)",2025,2025,17,17,"2025-04-23","22:00:00","2025-04-24","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","B9DE-009","Mannheim - Karlsruhe","< >","Illingen (Württ)","Illingen (Württ)",2025,2025,23,23,"2025-06-03","21:00:00","2025-06-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2023-01-26",null,null,"2,3",1]
[null,"DB InfraGO","1216C-003","Mannheim - Karlsruhe","<","Illingen (Württ)","Vaihingen (Enz)",2025,2025,24,24,"2025-06-10","22:30:00","2025-06-10","23:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-07",null,null,2,1]
[null,"DB InfraGO","1216C-015","Mannheim - Karlsruhe","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,24,24,"2025-06-11","03:00:00","2025-06-11","04:35:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-07",null,null,3,1]
[null,"DB InfraGO","1216C-024","Mannheim - Karlsruhe","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,24,24,"2025-06-12","00:20:00","2025-06-12","01:20:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-07",null,null,4,1]
[null,"DB InfraGO","18340-018","Mannheim - Karlsruhe","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,39,40,"2025-09-28","22:45:00","2025-09-29","01:20:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,"1,7",1]
[null,"DB InfraGO","18340-023","Mannheim - Karlsruhe","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,40,40,"2025-09-29","01:20:00","2025-09-29","04:45:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,1,1]
[null,"DB InfraGO","12CB3-020","Regensburg - Wels","< >","Passau Grenze","Passau Hbf",2025,2025,41,41,"2025-10-07","22:30:00","2025-10-08","00:01:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO","108DD-017","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-08","01:00:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO","17D18-014","Karlsruhe - Stuttgart","< >","Kornwestheim Rbf Süd-Ost","Ludwigsburg",2025,2025,38,38,"2025-09-18","02:55:00","2025-09-18","05:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,4,1]
[null,"DB InfraGO","14C0F-026","Regensburg - Wels","< >","Straubing","Straubing",2025,2025,39,39,"2025-09-24","21:00:00","2025-09-25","05:00:00","0d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-06-13",null,null,"3,4",1]
[null,"DB InfraGO","1A6F6-003","Gemünden - Bamberg - Nürnberg","< >","Strullendorf","Strullend DB-Gr",2025,2025,43,43,"2025-10-21","21:00:00","2025-10-22","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-04-27",null,null,"2,3",1]
[null,"DB InfraGO","7943-001","Karlsruhe - Stuttgart",">","Stuttgart Hbf Gw Prag","Ludwigsburg",2025,2025,14,15,"2025-04-04","22:00:00","2025-04-11","04:00:00","6d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","108DD-011","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Ludwigsburg",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-08","01:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO","124BB-011","Karlsruhe - Stuttgart","<","Bietigheim-Bissingen","Ludwigsburg",2025,2025,14,15,"2025-04-04","21:00:00","2025-04-07","03:50:00","2d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"1,5,6,7",1]
[null,"DB InfraGO","162F6-020","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Ludwigsburg",2025,2025,14,14,"2025-04-03","22:25:00","2025-04-04","00:45:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO","16332-003","Karlsruhe - Stuttgart","< >","Ludwigsburg","Bietigheim-Bissingen",2025,2025,13,13,"2025-03-28","22:00:00","2025-03-29","04:50:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-21",null,null,"5,6",1]
[null,"DB InfraGO","16685-015","Karlsruhe - Stuttgart",">","Stuttgart Pragtunnel","Kornwestheim Pbf",2025,2025,40,40,"2025-09-30","22:00:00","2025-10-01","01:25:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO","166C6-019","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2025,2025,40,40,"2025-10-04","22:00:00","2025-10-05","04:30:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-18",null,null,"6,7",1]
[null,"DB InfraGO","108D8-008","Karlsruhe - Stuttgart","<","Ludwigsburg","Kornwestheim Pbf",2025,2025,28,28,"2025-07-13","01:00:00","2025-07-13","04:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-25",null,null,7,1]
[null,"DB InfraGO","10B3B-002","Karlsruhe - Stuttgart","<","Ludwigsburg","Kornwestheim Pbf",2025,2025,28,28,"2025-07-09","22:00:00","2025-07-10","04:00:00","0d, 6h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO","167B6-007","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2025,2025,40,41,"2025-10-05","22:00:00","2025-10-06","04:00:00","0d, 6h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO","167B6-021","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Ludwigsburg",2025,2025,41,41,"2025-10-07","01:25:00","2025-10-07","04:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",8,8",null,null,null,"N",null,"2023-08-21",null,null,2,1]
[null,"DB InfraGO","17D18-019","Karlsruhe - Stuttgart","< >","Stuttgart-Zuffenhausen","Ludwigsburg",2025,2025,38,38,"2025-09-18","22:30:00","2025-09-19","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"4,5",1]
[null,"DB InfraGO","7811-010","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Sersheim Aischbach",2025,2025,42,42,"2025-10-15","22:00:00","2025-10-16","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","9828-017","Karlsruhe - Stuttgart",">","Mühlacker","Bretten Rechberg",2025,2025,17,17,"2025-04-23","22:00:00","2025-04-24","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-10",null,null,"3,4",1]
[null,"DB InfraGO","9829-015","Karlsruhe - Stuttgart",">","Illingen (Württ)","Mühlacker",2025,2025,8,8,"2025-02-19","22:00:00","2025-02-20","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-10",null,null,"3,4",1]
[null,"DB InfraGO","9827-024","Karlsruhe - Stuttgart",">","Sachsenheim","StrWe 4800/4842",2025,2025,30,30,"2025-07-23","22:00:00","2025-07-24","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","9827-034","Karlsruhe - Stuttgart",">","StrWe 4800/4842","Illingen (Württ)",2025,2025,12,12,"2025-03-19","22:00:00","2025-03-20","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","9827-043","Karlsruhe - Stuttgart",">","StrWe 4800/4842","Illingen (Württ)",2025,2025,49,49,"2025-12-03","22:00:00","2025-12-04","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,"3,4",1]
[null,"DB InfraGO","D4BB-010","Karlsruhe - Stuttgart",">","Sachsenheim","Sersheim Aischbach",2025,2025,27,27,"2025-06-30","22:30:00","2025-07-01","01:25:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-27",null,null,"1,2",1]
[null,"DB InfraGO","D6B0-003","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,27,27,"2025-07-03","22:45:00","2025-07-04","04:30:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-28",null,null,"4,5",1]
[null,"DB InfraGO","102E1-005","Karlsruhe - Stuttgart",">","Illingen (Württ)","Mühlacker",2025,2025,13,13,"2025-03-27","00:50:00","2025-03-27","04:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-18",null,null,4,1]
[null,"DB InfraGO","104D1-007","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker",2025,2025,14,14,"2025-04-01","00:50:00","2025-04-01","04:00:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-18",null,null,2,1]
[null,"DB InfraGO","104D1-021","Karlsruhe - Stuttgart","< >","Maulbronn West","Mühlacker",2025,2025,14,14,"2025-04-03","00:50:00","2025-04-03","04:00:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,4,1]
[null,"DB InfraGO","1216C-031","Karlsruhe - Stuttgart",">","Sachsenheim","Illingen (Württ)",2025,2025,24,24,"2025-06-12","03:00:00","2025-06-12","04:35:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-08-07",null,null,4,1]
[null,"DB InfraGO","155D4-003","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,13,14,"2025-03-29","07:00:00","2025-03-31","23:59:00","2d, 15h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,6,7",1]
[null,"DB InfraGO","166C6-007","Karlsruhe - Stuttgart","< >","Kornwestheim Pbf","Kornwestheim Pbf",2025,2025,40,40,"2025-10-03","22:00:00","2025-10-04","03:00:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO","108D8-002","Karlsruhe - Stuttgart",">","Kornwestheim Pbf","Ludwigsburg",2025,2025,28,28,"2025-07-12","22:00:00","2025-07-13","01:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-25",null,null,"6,7",1]
[null,"DB InfraGO","10B3B-011","Karlsruhe - Stuttgart","<","Ludwigsburg","Kornwestheim Pbf",2025,2025,28,28,"2025-07-11","22:00:00","2025-07-12","01:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-25",null,null,"5,6",1]
[null,"DB InfraGO","124BB-044","Karlsruhe - Stuttgart","<","Tamm (Württ)","Tamm (Württ)",2025,2025,37,38,"2025-09-14","22:30:00","2025-09-15","00:30:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO","17C7E-001","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker",2025,2025,13,14,"2025-03-24","00:00:00","2025-04-03","23:59:00","10d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","17D18-008","Karlsruhe - Stuttgart",">","Stuttgart-Zuffenhausen","Ludwigsburg",2025,2025,38,38,"2025-09-18","00:40:00","2025-09-18","02:55:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2023-09-22",null,null,4,1]
[null,"DB InfraGO","17E07-015","Karlsruhe - Stuttgart",">","Bietigheim-Bissingen","Sachsenheim",2025,2025,39,39,"2025-09-22","03:05:00","2025-09-22","04:45:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,1,1]
[null,"DB InfraGO","17E43-017","Karlsruhe - Stuttgart","< >","Sachsenheim","Sachsenheim",2025,2025,39,39,"2025-09-24","21:15:00","2025-09-24","22:55:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,3,1]
[null,"DB InfraGO","18340-005","Karlsruhe - Stuttgart","< >","Sachsenheim","Sachsenheim",2025,2025,39,39,"2025-09-25","21:45:00","2025-09-25","22:45:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,4,1]
[null,"DB InfraGO","186FA-003","Karlsruhe - Stuttgart","< >","Mühlacker","Mühlacker Em Nord",2025,2025,50,50,"2025-12-08","00:45:00","2025-12-08","04:40:00","0d, 3h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,1,1]
[null,"DB InfraGO","1864C-007","Karlsruhe - Stuttgart",">","Mühlacker","Maulbronn West",2025,2025,40,40,"2025-09-30","02:45:00","2025-09-30","04:45:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,2,1]
[null,"DB InfraGO","17E07-022","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,39,39,"2025-09-22","01:50:00","2025-09-22","03:05:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-23",null,null,1,1]
[null,"DB InfraGO","19F12-012","Karlsruhe - Stuttgart","< >","Sachsenheim","Sersheim Aischbach",2025,2025,21,21,"2025-05-21","05:00:00","2025-05-23","21:00:00","2d, 16h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"3,4,5",1]
[null,"DB InfraGO","780D-007","Stuttgart - München",">","Stuttgart-Untertürkheim Pbf","Plochingen",2025,2025,11,11,"2025-03-11","22:00:00","2025-03-12","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-20",null,null,"2,3",1]
[null,"DB InfraGO","780D-013","Stuttgart - München",">","Stuttgart-Untertürkheim Pbf","Plochingen",2025,2025,24,24,"2025-06-10","22:00:00","2025-06-11","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-20",null,null,"2,3",1]
[null,"DB InfraGO","780D-023","Stuttgart - München",">","Stuttgart-Untertürkheim Pbf","Plochingen",2025,2025,46,46,"2025-11-11","22:00:00","2025-11-12","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-20",null,null,"2,3",1]
[null,"DB InfraGO","9526-017","Stuttgart - München",">","Göppingen","Eislingen (Fils)",2025,2025,29,29,"2025-07-16","22:00:00","2025-07-17","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2022-12-21",null,null,"3,4",1]
[null,"DB InfraGO","9CA8-006","Stuttgart - München","< >","Stuttgart-Untertürkheim Pbf","Stuttgart-Untertürkheim Pbf",2025,2025,37,37,"2025-09-14","01:30:00","2025-09-14","02:30:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-04",null,null,7,1]
[null,"DB InfraGO","9EBC-008","Stuttgart - München","< >","Stuttgart-Untertürkheim Pbf","Stuttgart-Untertürkheim Pbf",2025,2025,42,43,"2025-10-17","21:00:00","2025-10-20","21:00:00","3d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-04",null,null,"1,5,6,7",1]
[null,"DB InfraGO","AB6F-008","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2025,2025,10,10,"2025-03-03","11:00:00","2025-03-03","12:00:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-17",null,null,1,1]
[null,"DB InfraGO","AB78-017","Stuttgart - München","< >","Ulm-Örlingen","Beimerstetten",2025,2025,39,41,"2025-09-26","20:00:00","2025-10-10","05:00:00","13d, 9h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-01-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","AB78-009","Stuttgart - München","< >","Ulm-Örlingen","Beimerstetten",2025,2025,41,41,"2025-10-10","04:50:00","2025-10-12","12:50:00","2d, 8h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-01-23",null,null,"5,6,7",1]
[null,"DB InfraGO","B17D-015","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2025,2025,37,39,"2025-09-14","21:00:00","2025-09-24","05:00:00","9d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","7934-002","Stuttgart - München",">","Süßen","Ulm Hbf Em Nord",2025,2025,14,15,"2025-04-06","22:00:00","2025-04-11","04:00:00","4d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","7914-003","Stuttgart - München",">","Süßen","Ulm Hbf Bft Pbf",2025,2025,34,37,"2025-08-22","22:00:00","2025-09-10","04:00:00","18d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","127F5-011","Stuttgart - München","<","Stuttgart-Obertürkheim","Stuttgart-Untertürkheim Pbf",2025,2025,44,44,"2025-10-27","23:00:00","2025-10-28","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-05",null,null,"1,2",1]
[null,"DB InfraGO","12848-006","Stuttgart - München","< >","Ebersbach (Fils)","Ebersbach (Fils)",2025,2025,23,23,"2025-06-03","01:00:00","2025-06-05","04:30:00","2d, 3h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-08-02",null,null,"2,3,4",1]
[null,"DB InfraGO","12848-007","Stuttgart - München","<","Göppingen","Plochingen",2025,2025,22,22,"2025-05-27","01:00:00","2025-05-30","04:30:00","3d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-06-06",null,null,"2,3,4,5",1]
[null,"DB InfraGO","12848-020","Stuttgart - München","< >","Ebersbach (Fils)","Ebersbach (Fils)",2025,2025,23,23,"2025-06-03","01:00:00","2025-06-05","04:30:00","2d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-06",null,null,"2,3,4",1]
[null,"DB InfraGO","12C57-010","Stuttgart - München","< >","Geislingen (Steige)","Geislingen (Steige)",2025,2025,37,39,"2025-09-14","21:00:00","2025-09-24","05:00:00","9d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","12C57-023","Stuttgart - München","<","Amstetten (Württ)","Geislingen (Steige)",2025,2025,39,39,"2025-09-24","21:00:00","2025-09-26","05:00:00","1d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"3,4,5",1]
[null,"DB InfraGO","14C45-006","Stuttgart - München","< >","Amstetten (Württ)","Beimerstetten",2025,2025,17,17,"2025-04-27","01:30:00","2025-04-27","05:00:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-16",null,null,7,1]
[null,"DB InfraGO","15927-006","Stuttgart - München",">","Stuttgart-Untertürkheim Pbf","Stuttgart-Bad Cannstatt",2025,2025,34,34,"2025-08-18","00:25:00","2025-08-18","02:20:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2023-07-26",null,null,1,1]
[null,"DB InfraGO","15927-018","Stuttgart - München","<","Stuttgart-Obertürkheim","Stuttgart-Untertürkheim Pbf",2025,2025,34,34,"2025-08-19","02:20:00","2025-08-19","04:20:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-26",null,null,2,1]
[null,"DB InfraGO","15927-025","Stuttgart - München","< >","Stuttgart-Obertürkheim","Plochingen",2025,2025,34,34,"2025-08-19","22:45:00","2025-08-20","04:40:00","0d, 5h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-26",null,null,"2,3",1]
[null,"DB InfraGO",1.594E-18,"Stuttgart - München",">","Plochingen","Ebersbach (Fils)",2025,2025,35,35,"2025-08-26","03:15:00","2025-08-26","04:25:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-26",null,null,2,1]
[null,"DB InfraGO","15AA5-001","Stuttgart - München","< >","Ebersbach (Fils)","Ebersbach (Fils)",2025,2025,35,35,"2025-08-27","22:45:00","2025-08-28","00:45:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-26",null,null,"3,4",1]
[null,"DB InfraGO","15AA5-007","Stuttgart - München","< >","Uhingen","Uhingen",2025,2025,35,35,"2025-08-28","00:45:00","2025-08-28","04:45:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-18",null,null,4,1]
[null,"DB InfraGO","15AA5-024","Stuttgart - München","< >","Göppingen","Göppingen",2025,2025,36,36,"2025-09-02","03:15:00","2025-09-02","04:45:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-26",null,null,2,1]
[null,"DB InfraGO","15ACA-004","Stuttgart - München","<","Gingen (Fils)","Süßen",2025,2025,36,36,"2025-09-04","00:40:00","2025-09-04","02:15:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-26",null,null,4,1]
[null,"DB InfraGO","16918-003","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2025,2025,39,39,"2025-09-24","03:00:00","2025-09-24","05:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,3,1]
[null,"DB InfraGO","2B61A-005","Stuttgart - München",">","Eislingen (Fils)","Süßen",2024,2024,50,50,"2024-12-15","00:00:00","2024-12-15","05:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-07",null,null,7,1]
[null,"DB InfraGO","2BFC3-008","Stuttgart - München","< >","Esslingen (Neckar)","Stuttgart-Obertürkheim",2024,2024,50,51,"2024-12-15","00:00:00","2024-12-16","05:00:00","1d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,7",1]
[null,"DB InfraGO","AB88-008","Stuttgart - München","< >","Eislingen (Fils)","Eislingen (Fils)",2025,2025,38,39,"2025-09-15","05:00:00","2025-09-26","21:00:00","11d, 16h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","7948-003","Stuttgart - München",">","Stuttgart-Bad Cannstatt","Plochingen",2025,2025,15,16,"2025-04-11","22:00:00","2025-04-18","04:00:00","6d, 6h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","EC13-005","Stuttgart - München","< >","Stuttgart-Obertürkheim","Stuttgart-Obertürkheim",2025,2025,12,13,"2025-03-23","22:45:00","2025-03-24","00:25:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-05-30",null,null,"1,7",1]
[null,"DB InfraGO","EC11-012","Stuttgart - München","< >","Stuttgart-Obertürkheim","Plochingen",2025,2025,13,13,"2025-03-27","00:00:00","2025-03-27","04:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,4,1]
[null,"DB InfraGO","EC11-029","Stuttgart - München","< >","Esslingen (Neckar)","Plochingen",2025,2025,14,14,"2025-04-02","00:15:00","2025-04-02","04:00:00","0d, 3h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,3,1]
[null,"DB InfraGO","12306-004","Stuttgart - München","< >","Esslingen (Neckar)","Esslingen (Neckar)",2025,2025,23,23,"2025-06-03","01:20:00","2025-06-03","04:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2023-06-02",null,null,2,1]
[null,"DB InfraGO","17547-001","Stuttgart - München","< >","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim",2025,2025,13,13,"2025-03-27","08:00:00","2025-03-28","18:00:00","1d, 10h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-26",null,null,"4,5",1]
[null,"DB InfraGO","17F38-002","München - Salzburg","< >","Traunstein","Traunstein",2025,2025,17,22,"2025-04-27","08:00:00","2025-05-29","18:00:00","32d, 10h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","18E77-016","München - Salzburg","< >","Traunstein","Hörpolding",2025,2025,19,19,"2025-05-10","08:00:00","2025-05-10","14:00:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,6,1]
[null,"DB InfraGO","8C5E-001","Gemünden - Bamberg - Nürnberg",">","Eußenheim","Eußenheim",2025,2025,31,36,"2025-08-01","08:00:00","2025-09-05","18:00:00","35d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","15CCF-004","Gemünden - Bamberg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2025,2025,44,44,"2025-10-29","22:20:00","2025-10-30","00:40:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO","9A23-001","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2025,2025,8,13,"2025-02-21","00:00:00","2025-03-30","23:59:00","37d, 22h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","14890-009","Mannheim - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,39,40,"2025-09-28","01:00:00","2025-09-29","04:00:00","1d, 3h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO","8885-009","Aschaffenburg - Würzburg","<","Wiesthal","Partenstein",2025,2025,29,30,"2025-07-19","22:00:00","2025-07-21","05:00:00","1d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-12-06",null,null,"6,7",1]
[null,"DB InfraGO","A3F1-004","Aschaffenburg - Würzburg","<","Gemünden (Main)","Würzburg Hbf",2025,2025,44,44,"2025-10-27","23:00:00","2025-11-01","05:00:00","4d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-08-24",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","13F91-002","Aschaffenburg - Würzburg","<","Lohr Bahnhof","Gemünden (Main)",2025,2025,12,13,"2025-03-23","23:20:00","2025-03-24","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2023-11-06",null,null,"1,7",1]
[null,"DB InfraGO","15BA2-002","Aschaffenburg - Würzburg","<","Laufach","Wiesthal",2025,2025,43,45,"2025-10-26","23:00:00","2025-11-03","05:55:00","7d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO","15C93-001","Aschaffenburg - Würzburg","< >","Langenprozelten","Langenprozelten",2025,2025,44,44,"2025-10-30","22:30:00","2025-10-31","01:20:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO","15CCF-009","Aschaffenburg - Würzburg","<","Langenprozelten","Gemünden (Main)",2025,2025,44,44,"2025-10-30","02:50:00","2025-10-30","03:50:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,4,1]
[null,"DB InfraGO","142E1-005","Aschaffenburg - Würzburg",">","Langenprozelten","Partenstein",2025,2025,41,41,"2025-10-12","02:20:00","2025-10-12","04:50:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-04-15",null,null,7,1]
[null,"DB InfraGO","142E1-027","Aschaffenburg - Würzburg",">","Karlstadt (Main)","Gemünden (Main)",2025,2025,43,43,"2025-10-20","22:00:00","2025-10-21","01:10:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO","27196-003","Aschaffenburg - Würzburg","< >","Karlstadt (Main)","Gemünden (Main)",2024,2024,51,51,"2024-12-19","21:00:00","2024-12-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"4,5",1]
[null,"DB InfraGO","1E034-016","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1E768-008","Karlsruhe - Strasbourg","< >","Appenweier","Offenburg",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,null,null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","32385-014","Karlsruhe - Strasbourg","< >","Achern (F)","Appenweier Nord",2026,2026,41,42,"2026-10-09","21:00:00","2026-10-12","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO","32765-003","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-13","04:00:00","1d, 4h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO","1E15C-010","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,19,19,"2026-05-05","05:00:00","2026-05-06","05:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO","2901F-005","Stuttgart - München","< >","München-Trudering","München-Trudering",2026,2026,3,3,"2026-01-12","08:00:00","2026-01-13","15:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-03-28",null,null,"1,2",1]
[null,"DB InfraGO","32158-007","München - Salzburg","< >","Zorneding","Grafing Bahnhof",2026,2026,37,38,"2026-09-07","22:10:00","2026-09-14","04:10:00","6d, 6h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","218BA-004","Darmstadt - Aschaffenburg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-14","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2",1]
[null,"DB InfraGO","338D7-007","Aschaffenburg - Würzburg","< >","Nantenbach","Rohrbach",2026,2026,13,13,"2026-03-26","08:00:00","2026-03-26","16:00:00","0d, 8h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-03-27",null,null,4,1]
[null,"DB InfraGO","1E95C-009","Nürnberg - Regensburg","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","20C05-029","Darmstadt - Aschaffenburg","<","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,6,7,"2026-02-08","21:00:00","2026-02-13","05:00:00","4d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","1D41F-017","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1D41F-025","Karlsruhe - Strasbourg","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1F00D-006","Karlsruhe - Strasbourg",">","Kork","Kehl",2025,2025,51,52,"2025-12-21","22:00:00","2025-12-23","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"1,7",1]
[null,"DB InfraGO","1F00D-022","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,7,8,"2026-02-13","22:00:00","2026-02-16","05:00:00","2d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"5,6,7",1]
[null,"DB InfraGO","1F0E7-001","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,10,50,"2026-03-04","05:00:00","2026-12-09","05:00:00","280d, 0h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F0E7-007","Karlsruhe - Strasbourg","<","Kehl","Kork",2026,2026,14,16,"2026-04-03","22:00:00","2026-04-14","05:00:00","10d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F0E7-024","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,27,27,"2026-06-29","22:00:00","2026-07-03","05:00:00","3d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4",1]
[null,"DB InfraGO","1F0E7-029","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,29,30,"2026-07-19","22:00:00","2026-07-24","05:00:00","4d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","1F203-007","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,46,50,"2026-11-12","21:00:00","2026-12-09","05:00:00","26d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2C99C-003","Karlsruhe - Strasbourg","< >","Appenweier Nord","Bad Griesbach",2026,2026,47,47,"2026-11-17","23:00:00","2026-11-21","04:00:00","3d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1D705-007","Stuttgart - München","<","Gersthofen","Augsburg-Oberhausen",2026,2026,21,22,"2026-05-22","23:00:00","2026-05-26","05:00:00","3d, 6h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-05",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","25966-001","Stuttgart - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,42,43,"2026-10-18","22:00:00","2026-10-19","07:00:00","0d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-07",null,null,"1,7",1]
[null,"DB InfraGO","1D885-012","Stuttgart - München",">","Gessertshausen","Gessertshausen",2026,2026,23,24,"2026-06-06","07:00:00","2026-06-08","07:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"1,6,7",1]
[null,"DB InfraGO","1DEAC-003","Stuttgart - München","< >","Burgau (Schwab)","Burgau (Schwab)",2026,2026,27,27,"2026-06-29","21:00:00","2026-06-30","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,2",1]
[null,"DB InfraGO","32A52-006","Stuttgart - München","< >","Günzburg","Unterfahlheim",2026,2026,31,34,"2026-07-28","23:30:00","2026-08-17","05:00:00","19d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D705-009","Stuttgart - München",">","Augsburg-Oberhausen","Westheim (Schwab)",2026,2026,22,22,"2026-05-27","00:30:00","2026-05-28","04:30:00","1d, 4h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-05",null,null,"3,4",1]
[null,"DB InfraGO","3050B-002","Stuttgart - München","< >","Augsburg Hbf","Augsburg Hirblinger Straße",2026,2026,15,16,"2026-04-08","23:30:00","2026-04-13","04:30:00","4d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-12",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO","324D6-002","Gemünden - Bamberg - Nürnberg","<","Schweinfurt Hbf","Gädheim",2026,2026,29,29,"2026-07-18","21:00:00","2026-07-19","05:00:00","0d, 8h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","1E7D1-015","Nürnberg - Regensburg","< >","Feucht","Feucht",2026,2026,33,37,"2026-08-10","20:30:00","2026-09-07","04:30:00","27d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2023-12-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","20D1D-007","Stuttgart - München","< >","München Süd","München Süd",2026,2026,15,28,"2026-04-07","22:40:00","2026-07-08","05:00:00","91d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","33005-008","Stuttgart - München","< >","München-Pasing","München-Pasing",2026,2026,11,12,"2026-03-13","22:00:00","2026-03-19","06:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO","33005-031","Stuttgart - München","< >","München-Pasing Ost","München-Pasing",2026,2026,36,37,"2026-09-05","18:00:00","2026-09-07","04:00:00","1d, 10h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"1,6,7",1]
[null,"DB InfraGO","1E622-004","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO","2124F-008","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-30","05:00:00","6d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D41F-012","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"4,5",1]
[null,"DB InfraGO","1C058-002","Darmstadt - Aschaffenburg","< >","Darmstadt Gbf","Darmstadt Nord",2026,2026,10,12,"2026-03-06","21:00:00","2026-03-20","05:00:00","13d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","218BA-006","Darmstadt - Aschaffenburg","<","Aschaffenburg Hbf","Stockstadt (Main)",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-23","05:00:00","9d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-06-06",null,null,"5,6,7",1]
[null,"DB InfraGO","20C05-051","Darmstadt - Aschaffenburg","<","Darmstadt-Kranichstein","Darmstadt Nord",2026,2026,11,11,"2026-03-14","21:00:00","2026-03-15","07:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-06-06",null,null,"6,7",1]
[null,"DB InfraGO","20C05-007","Darmstadt - Aschaffenburg","< >","Darmstadt Nord","Darmstadt-Arheilgen",2026,2026,1,2,"2026-01-02","21:00:00","2026-01-06","05:00:00","3d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","20029-023","Gemünden - Bamberg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,27,27,"2026-06-30","08:00:00","2026-07-01","20:00:00","1d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO","20029-054","Gemünden - Bamberg - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,13,13,"2026-03-28","08:00:00","2026-03-28","20:00:00","0d, 12h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,6,1]
[null,"DB InfraGO","1C91B-004","Darmstadt - Mannheim","< >","Bickenbach Nord","Bickenbach Nord",2026,2026,17,17,"2026-04-20","04:00:00","2026-04-23","18:00:00","3d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4",1]
[null,"DB InfraGO","1F485-003","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F521-005","Darmstadt - Mannheim","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,8,8,"2026-02-18","23:00:00","2026-02-20","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-06",null,null,"3,4",1]
[null,"DB InfraGO","1F521-026","Darmstadt - Mannheim","< >","Ladenburg","Ladenburg",2026,2026,10,10,"2026-03-02","23:00:00","2026-03-05","05:00:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-23",null,null,"1,2,3",1]
[null,"DB InfraGO","1F841-009","Darmstadt - Mannheim","< >","Heddesheim/Hirschberg","Ladenburg",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-06","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F841-021","Darmstadt - Mannheim","< >","Ladenburg","Ladenburg",2026,2026,10,11,"2026-03-06","21:00:00","2026-03-13","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F841-028","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,11,12,"2026-03-13","00:00:00","2026-03-20","05:00:00","7d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F917-018","Darmstadt - Mannheim","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,13,14,"2026-03-27","21:00:00","2026-04-03","05:00:00","6d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1FA57-031","Darmstadt - Mannheim","< >","Ladenburg","Ladenburg",2026,2026,24,25,"2026-06-12","21:00:00","2026-06-15","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-17",null,null,"5,6,7",1]
[null,"DB InfraGO","1FB9B-003","Darmstadt - Mannheim","< >","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,16,17,"2026-04-17","21:00:00","2026-04-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"5,6,7",1]
[null,"DB InfraGO","1F485-043","Darmstadt - Mannheim","< >","Weinheim (Bergstr) Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1E3F6-018","Würzburg - Nürnberg","< >","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2026,2026,43,50,"2026-10-25","00:00:00","2026-12-12","23:59:00","49d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D885-004","Stuttgart - München","< >","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-05","05:00:00","26d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","213D2-010","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Pommelsbrunn",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-10","23:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-15",null,null,"2,3,4",1]
[null,"DB InfraGO","1E550-022","Mannheim - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1DE53-001","Karlsruhe - Stuttgart","< >","Pforzheim Hbf","Mühlacker Em Süd",2026,2026,42,43,"2026-10-16","23:00:00","2026-10-20","04:00:00","3d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO","1E501-023","Karlsruhe - Stuttgart","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F08E-003","Karlsruhe - Stuttgart","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","25BC0-002","Karlsruhe - Stuttgart","< >","Pforzheim Hbf","Pforzheim Hbf",2026,2026,16,17,"2026-04-19","07:00:00","2026-04-22","07:00:00","3d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-11",null,null,"1,2,3,7",1]
[null,"DB InfraGO","1CF23-004","Regensburg - Wels","< >","Plattling","Plattling",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D659-001","Regensburg - Wels","< >","Plattling","Plattling",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1C08E-003","Darmstadt - Aschaffenburg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,18,19,"2026-05-02","21:00:00","2026-05-04","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-30",null,null,"6,7",1]
[null,"DB InfraGO","1E034-025","Karlsruhe - Strasbourg","< >","Achern","Appenweier Nord",2026,2026,22,26,"2026-05-29","21:00:00","2026-06-22","05:00:00","23d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-13",null,null,"5,6,7",1]
[null,"DB InfraGO","1E199-017","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","23:00:00","2026-04-10","05:00:00","3d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO","1E501-002","Karlsruhe - Strasbourg","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3",1]
[null,"DB InfraGO","1F08E-011","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO","1F43D-011","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1E199-027","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","05:00:00","2026-04-07","07:00:00","1d, 2h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-17",null,null,"1,2",1]
[null,"DB InfraGO","2C17A-003","Karlsruhe - Strasbourg","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,19,28,"2026-05-08","21:00:00","2026-07-10","21:00:00","63d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1E81C-003","Karlsruhe - Strasbourg","< >","Kraichtal","Vaihingen (Enz)",2026,2026,10,11,"2026-03-07","23:00:00","2026-03-09","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO","1E81C-014","Karlsruhe - Strasbourg","< >","Vaihingen (Enz)","Langes Feld",2026,2026,16,17,"2026-04-18","23:00:00","2026-04-20","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO","1EEEE-013","Karlsruhe - Strasbourg","< >","Glems","Vaihingen (Enz)",2026,2026,25,27,"2026-06-15","22:30:00","2026-07-02","05:00:00","16d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1F188-010","Karlsruhe - Strasbourg",">","Freudenstein","Vaihingen (Enz)",2026,2026,35,36,"2026-08-24","22:30:00","2026-09-05","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1F6AE-017","Karlsruhe - Strasbourg","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,44,44,"2026-10-26","22:30:00","2026-10-31","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1F6AE-024","Karlsruhe - Strasbourg",">","Vaihingen (Enz)","Langes Feld",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1D41F-014","Mannheim - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1F71F-002","Mannheim - Karlsruhe",">","Blankenloch","Karlsruhe-Hagsfeld",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","292E3-003","Mannheim - Karlsruhe","< >","Schwetzingen","Schwetzingen",2026,2026,14,14,"2026-03-31","23:00:00","2026-04-02","05:00:00","1d, 6h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-10",null,null,"2,3",1]
[null,"DB InfraGO","1DB29-015","Mannheim - Karlsruhe","< >","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO","338F9-001","Mannheim - Karlsruhe","< >","Mühlacker Kurve","Mühlacker Em Süd",2026,2026,16,17,"2026-04-19","23:00:00","2026-04-22","05:00:00","2d, 6h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,7",1]
[null,"DB InfraGO",3.2139999999999997E-17,"Mannheim - Karlsruhe","< >","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1BF05-042","Stuttgart - München","< >","München-Pasing","München-Pasing",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-26","04:00:00","2d, 7h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1BF05-045","Stuttgart - München","< >","München-Pasing","München-Pasing",2026,2026,44,44,"2026-10-26","21:00:00","2026-10-27","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"1,2",1]
[null,"DB InfraGO","1D3DB-010","Stuttgart - München",">","Olching","Augsburg-Hochzoll Abzweig",2026,2026,26,27,"2026-06-25","21:00:00","2026-06-30","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO","1E029-014","Stuttgart - München",">","Mering Üst","Augsburg Hbf",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","33005-020","Stuttgart - München","< >","München-Pasing","München-Pasing",2026,2026,33,33,"2026-08-14","22:00:00","2026-08-16","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"5,6",1]
[null,"DB InfraGO","21014-005","Stuttgart - München","< >","München-Pasing","Starnberg",2026,2026,45,47,"2026-11-06","21:00:00","2026-11-16","04:30:00","9d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"5,6,7",1]
[null,"DB InfraGO","32CAF-049","Stuttgart - München",">","München-Neuhausen","München-Pasing",2026,2026,5,5,"2026-01-26","22:40:00","2026-01-28","04:40:00","1d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO","1DF3E-001","München - Regensburg","< >","Obertraubling","Regensburg Ost",2026,2026,28,29,"2026-07-10","21:00:00","2026-07-15","01:00:00","4d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO","1DD6A-001","München - Salzburg",">","München Ost Pbf","München Ost Pbf",2026,2026,24,50,"2026-06-08","04:30:00","2026-12-12","23:59:00","187d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1DD6A-013","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,25,50,"2026-06-17","04:30:00","2026-12-12","23:59:00","178d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","20D1D-019","München - Salzburg","<","München Süd","München Hbf",2026,2026,26,27,"2026-06-26","08:00:00","2026-06-29","16:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-06-25",null,null,"1,5",1]
[null,"DB InfraGO","32CAF-004","München - Salzburg","< >","München-Pasing","München Donnersbergerbrücke",2026,2026,3,3,"2026-01-12","22:40:00","2026-01-16","04:40:00","3d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2,3,4",1]
[null,"DB InfraGO","33005-016","München - Salzburg","< >","München-Pasing","München-Pasing",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","06:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2024-04-18",null,null,"5,6",1]
[null,"DB InfraGO","1E0DB-004","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2026,2026,45,45,"2026-11-02","22:30:00","2026-11-04","08:00:00","1d, 9h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3",1]
[null,"DB InfraGO","1DD6A-009","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,23,24,"2026-06-03","14:00:00","2026-06-08","04:30:00","4d, 14h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO","1D341-003","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D3F1-019","München - Salzburg","<","München-Giesing","München Ost Pbf",2026,2026,15,16,"2026-04-09","04:00:00","2026-04-13","04:30:00","4d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-05-17",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO","3374A-013","München - Salzburg","< >","München Ost Pbf","München-Steinhausen",2026,2026,7,9,"2026-02-09","21:40:00","2026-02-24","04:20:00","14d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,1,1]
[null,"DB InfraGO","1E851-001","Stuttgart - München",">","München-Lochhausen","Maisach",2026,2026,10,10,"2026-03-03","00:05:00","2026-03-06","05:00:00","3d, 4h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-05-16",null,null,"2,3,4,5",1]
[null,"DB InfraGO","1BF05-035","Stuttgart - München","< >","München-Pasing","München-Pasing Weiche 352",2026,2026,36,37,"2026-09-04","23:00:00","2026-09-07","05:00:00","2d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1FAF2-009","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","27CB6-003","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2026,2026,31,32,"2026-07-31","21:00:00","2026-08-04","05:00:00","3d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1F4F8-031","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,8,50,"2026-02-16","12:00:00","2026-12-12","23:59:00","299d, 11h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1FAF2-022","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1F521-024","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,10,10,"2026-03-02","23:00:00","2026-03-05","05:00:00","2d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"1,2,3",1]
[null,"DB InfraGO","1FA57-009","Mannheim - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1FB9B-035","Mannheim - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,29,30,"2026-07-17","21:00:00","2026-07-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-17",null,null,"5,6,7",1]
[null,"DB InfraGO","1D973-005","München - Regensburg","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2057A-004","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2057A-010","Nürnberg - Plzen",">","Nürnberg Ost","Nürnberg-Erlenstegen",2026,2026,36,36,"2026-09-02","12:00:00","2026-09-06","04:00:00","3d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-11",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO","1FA90-040","Nürnberg - Plzen","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,22,22,"2026-05-26","22:00:00","2026-05-27","08:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-06-25",null,null,"2,3",1]
[null,"DB InfraGO","20ED5-004","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,45,47,"2026-11-04","14:00:00","2026-11-17","14:00:00","13d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-01-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2138A-001","Nürnberg - Plzen","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2026,2026,8,8,"2026-02-21","06:00:00","2026-02-22","14:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-14",null,null,"6,7",1]
[null,"DB InfraGO","21815-010","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,46,46,"2026-11-09","06:00:00","2026-11-10","12:00:00","1d, 6h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-06-06",null,null,"1,2",1]
[null,"DB InfraGO","20DE0-001","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,32,"2026-08-04","00:00:00","2026-08-05","04:35:00","1d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-06-21",null,null,"2,3",1]
[null,"DB InfraGO","20DE0-004","Nürnberg - Plzen","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,32,"2026-08-06","00:00:00","2026-08-07","04:35:00","1d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-06-21",null,null,"4,5",1]
[null,"DB InfraGO","213D2-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,36,37,"2026-09-01","05:00:00","2026-09-08","23:00:00","7d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1FA7F-005","Gemünden - Bamberg - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,14,16,"2026-04-05","00:00:00","2026-04-13","18:00:00","8d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1FA7F-032","Gemünden - Bamberg - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,17,17,"2026-04-26","06:00:00","2026-04-26","14:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,7,1]
[null,"DB InfraGO","1FA90-051","Gemünden - Bamberg - Nürnberg","< >","Nürnberg Hbf","Nür Jansenbr",2026,2026,31,31,"2026-08-01","03:00:00","2026-08-01","13:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,6,1]
[null,"DB InfraGO","1C8BF-012","Nürnberg - Regensburg",">","Nürnberg-Langwasser","Nürnberg Reichswald",2026,2026,7,8,"2026-02-09","06:00:00","2026-02-21","06:00:00","12d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1E7A1-005","Nürnberg - Regensburg",">","Nürnberg-Langwasser","Nürnberg-Dutzendteich",2026,2026,40,40,"2026-09-28","07:00:00","2026-09-29","16:00:00","1d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"12,,",null,null,null,"N",null,"2024-01-18",null,null,"1,2",1]
[null,"DB InfraGO","1E3F6-019","Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2026,2026,43,50,"2026-10-25","00:00:00","2026-12-12","23:59:00","49d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"Y",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO",3.3529999999999997E-2,"Gemünden - Bamberg - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,39,39,"2026-09-24","06:00:00","2026-09-26","23:59:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-28",null,null,"4,5,6",1]
[null,"DB InfraGO","1E029-011","Stuttgart - München","<","Augsburg Hbf","Kissing",2026,2026,36,43,"2026-08-31","21:00:00","2026-10-21","05:00:00","50d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D1F4-001","Regensburg - Wels",">","Osterhofen (Niederbay)","Plattling",2026,2026,47,47,"2026-11-16","08:00:00","2026-11-16","16:00:00","0d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-01",null,null,1,1]
[null,"DB InfraGO","1D5C0-005","Regensburg - Wels","< >","Passau Hbf","Passau Grenze",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO","1CF23-010","Regensburg - Wels","< >","Passau Gbf","Passau Gbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","22ED3-020","Stuttgart - München","<","Wendlingen (Neckar)","Plochingen",2026,2026,30,30,"2026-07-22","22:00:00","2026-07-24","04:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-07",null,null,"3,4",1]
[null,"DB InfraGO","1E010-007","Regensburg - Wels","< >","Regensburg Bbf","Regensburg Bbf",2026,2026,7,8,"2026-02-13","18:00:00","2026-02-19","07:00:00","5d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1DB86-018","Nürnberg - Regensburg","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-10","19:00:00","2026-06-14","05:00:00","3d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-22",null,null,"3,4,5,6",1]
[null,"DB InfraGO","1E164-001","Nürnberg - Regensburg","< >","Ochenbruck","Postbauer-Heng",2025,2026,50,6,"2025-12-14","00:00:00","2026-02-06","21:00:00","54d, 21h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1E18E-005","Nürnberg - Regensburg",">","Undorf","Parsberg",2026,2026,40,41,"2026-10-02","01:00:00","2026-10-05","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1E72F-017","Nürnberg - Regensburg","<","Ochenbruck","Postbauer-Heng",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-18","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO","1DF02-018","Nürnberg - Regensburg","< >","Neumarkt (Oberpf)","Neumarkt (Oberpf)",2026,2026,6,28,"2026-02-06","00:00:00","2026-07-10","06:00:00","154d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1DB86-001","Regensburg - Plzen","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,10,10,"2026-03-06","23:00:00","2026-03-08","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-22",null,null,"5,6",1]
[null,"DB InfraGO","1DA81-002","Regensburg - Plzen","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","07:00:00","2026-08-23","04:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","3203D-002","München - Salzburg","< >","Rosenheim","Rosenheim",2026,2026,20,21,"2026-05-11","08:00:00","2026-05-21","08:00:00","10d, 0h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1DB9A-012","Mannheim - Karlsruhe","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO","1CF23-009","Regensburg - Wels","< >","Passau Hbf","Passau Hbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2BB27-002","Karlsruhe - Stuttgart","< >","Ludwigsburg","Kornwestheim Rbf Nord-Ost",2025,2025,51,51,"2025-12-20","09:30:00","2025-12-21","17:00:00","1d, 7h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO","1C651-004","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1C662-005","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,6,1]
[null,"DB InfraGO","333D2-011","Karlsruhe - Stuttgart","<","Asperg","Asperg",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","16:00:00","0d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"N",null,"2024-06-03",null,null,7,1]
[null,"DB InfraGO","1C651-007","Karlsruhe - Stuttgart","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1D6AE-010","Karlsruhe - Stuttgart","< >","Mühlacker","Maulbronn West",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO","1DAD8-025","Karlsruhe - Stuttgart","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO","1DB9A-005","Karlsruhe - Stuttgart","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO","1DB9A-019","Karlsruhe - Stuttgart","<","Mühlacker","Illingen (Württ)",2026,2026,45,47,"2026-11-02","22:00:00","2026-11-21","05:00:00","18d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1EEEE-021","Karlsruhe - Stuttgart","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,27,29,"2026-07-02","22:30:00","2026-07-18","05:00:00","15d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","33557-012","Karlsruhe - Stuttgart","< >","Ludwigsburg","Ludwigsburg",2026,2026,35,35,"2026-08-25","08:00:00","2026-08-25","16:00:00","0d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-03",null,null,2,1]
[null,"DB InfraGO","1FFF4-005","Stuttgart - München","< >","Süßen","Süßen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO","20BF3-006","Stuttgart - München","< >","Süßen","Süßen",2026,2026,34,35,"2026-08-22","03:00:00","2026-08-24","05:00:00","2d, 2h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO","21C52-007","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2026,2026,3,4,"2026-01-17","12:00:00","2026-01-19","12:00:00","2d, 0h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,"1,6,7",1]
[null,"DB InfraGO","21CBD-002","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2026,2026,11,12,"2026-03-14","12:00:00","2026-03-16","12:00:00","2d, 0h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,6,7",1]
[null,"DB InfraGO","21CBD-014","Stuttgart - München","< >","Beimerstetten","Beimerstetten",2026,2026,14,15,"2026-04-02","21:00:00","2026-04-07","04:50:00","4d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,4,5,6,7",1]
[null,"DB InfraGO","21CCE-007","Stuttgart - München",">","Westerstetten","Ulm-Örlingen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,"1,5,6,7",1]
[null,"DB InfraGO","22527-006","Stuttgart - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,34,37,"2026-08-22","21:00:00","2026-09-07","05:00:00","15d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","222FB-028","Stuttgart - München",">","Amstetten (Württ)","Westerstetten",2026,2026,36,37,"2026-09-01","21:00:00","2026-09-07","05:00:00","5d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","22494-011","Stuttgart - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","22ED4-020","Stuttgart - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,7",1]
[null,"DB InfraGO","2C17C-002","Stuttgart - München","< >","Süßen","Süßen",2026,2026,36,36,"2026-08-31","05:00:00","2026-09-02","05:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3",1]
[null,"DB InfraGO","22ED3-016","Stuttgart - München","< >","Plochingen","Plochingen",2026,2026,29,33,"2026-07-17","22:00:00","2026-08-10","04:00:00","23d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO",2.81E-3,"Stuttgart - München","< >","Stuttgart-Münster","Stuttgart-Untertürkheim",2026,2026,26,26,"2026-06-24","07:00:00","2026-06-24","15:00:00","0d, 8h","Continuous",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO","2AF93-008","Stuttgart - München","< >","Stuttgart-Untertürkheim Pbf","Stuttgart Hafen",2026,2026,13,14,"2026-03-28","06:00:00","2026-03-30","04:00:00","1d, 21h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-06",null,null,"1,6,7",1]
[null,"DB InfraGO","2AA67-001","München - Salzburg","< >","Traunstein","Ruhpolding",2026,2026,40,44,"2026-10-02","18:00:00","2026-10-26","03:00:00","23d, 10h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-02",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","20F04-003","Nürnberg - Plzen","< >","Kirchenlaibach","Kirchenlaibach",2026,2026,37,37,"2026-09-07","04:30:00","2026-09-11","23:30:00","4d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-06-03",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO","1C3FA-002","Aschaffenburg - Würzburg","<","Aschaffenburg Hbf","Laufach",2026,2026,24,25,"2026-06-08","23:00:00","2026-06-15","05:00:00","6d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","1C3FA-008","Aschaffenburg - Würzburg",">","Laufach","Aschaffenburg Hbf",2026,2026,28,29,"2026-07-06","23:00:00","2026-07-13","05:00:00","6d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","20029-001","Aschaffenburg - Würzburg","< >","Gemünden (Main)","Gemünden (Main)",2025,2026,50,13,"2025-12-14","08:00:00","2026-03-27","20:00:00","103d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","2037B-017","Aschaffenburg - Würzburg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,39,40,"2026-09-25","08:00:00","2026-09-28","20:00:00","3d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO","202A2-005","Aschaffenburg - Würzburg","< >","Langenprozelten","Langenprozelten",2026,2026,35,37,"2026-08-28","21:00:00","2026-09-11","05:00:00","13d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","32C56-001","Aschaffenburg - Würzburg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,28,31,"2026-07-09","22:00:00","2026-07-27","17:00:00","17d, 19h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","32D9A-004","Aschaffenburg - Würzburg","< >","Partenstein","Partenstein",2026,2026,36,37,"2026-08-31","22:00:00","2026-09-07","05:00:00","6d, 7h","Periodical",null,null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","32E80-003","Aschaffenburg - Würzburg","< >","Wiesthal","Partenstein",2026,2026,40,43,"2026-10-03","22:00:00","2026-10-24","05:00:00","20d, 7h","Periodical",null,null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO","33786-001","Aschaffenburg - Würzburg","< >","Wiesthal","Aschaffenburg Hbf",2026,2026,17,17,"2026-04-25","21:00:00","2026-04-26","05:00:00","0d, 8h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"ÖBB Infra",8124318,"Wels - Linz","< >","Marchtrenk",null,2024,2025,31,29,"01.08.2024","00:00:00","20.07.2025",1,"354 days","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"Errichtung Gleis 403 neu und Weiche 255",null,null,null,"24.11.2023"]
[null,"ÖBB Infra",8124359,"Wels - Traun - Linz","< >","Traun","Rohr-Bad Hall",2024,2024,44,45,"29.10.2024","22:00:00","04.11.2024","04:30:00","5 days + 6,5 h","Periodical","Others","T","LT","S",null,null,"C",null,"B",null,null,"Inbetriebnahme ESTW Traun und ESTW Nettingsdorf\n- Ausbau der Weichen 31 und 32 Bf. Nettingsdorf \n- Weichenneulage 353, 354 und 356 Bf. Rohr Bad Hall",null,null,null,"07.09.2023"]
[null,"ÖBB Infra",8124384,"Regensburg - Wels","< >","Wels Vbf",null,2024,2024,39,41,"28.09.2024","07:00:00","10.10.2024","17:00:00","12 days + 10,0 h","Periodical","Others",null,"ST",null,null,null,null,null,null,null,null,"GN346",null,null,null,"01.05.2023"]
[null,"ÖBB Infra",8124436,"Linz - Wien (GZ)",">","Amstetten","St.Valentin",2024,2024,31,35,"01.08.2024","00:00:00","30.08.2024",1,"30 days","Periodical","Other","T","LT",null,null,null,"C",null,"B",null,null,"Gleisneulage Gleis 4 km 128,190 - 131,304 ohne Üst Ams2",null,null,null,"03.04.2022"]
[null,"ÖBB Infra",8124464,"Wien - Hegyeshalom","< >","Götzendorf","Abzww Str 11815",2023,2025,26,27,"01.07.2023","00:00:00","30.06.2025",1,"731 days","Periodical","BFUM",null,"LT",null,null,null,null,null,null,null,null,"Bf-Umbau",null,null,null,"14.12.2021"]
[null,"ÖBB Infra",24474,"Wien - Hegyeshalom",null,null,null,null,null,null,null,null,null,null,null,null,"Periodical"]
[null,"ÖBB Infra","81-B-78131","Wels - Linz","< >","Linz Hbf","Abzw Ast 1",2026,2026,2,41,"07.01.2026","00:00:00","11.10.2026",1,"277 days + 23,0 h","Continuous","Miscellaneous","T","LT",null,null,null,null,null,null,0,null,"Viergleisige Durchbindung Weststrecken Linz Vbf, Errichtung Str10102 im Knoten Linz",null,"N",null,"15.05.2024"]
[null,"ÖBB Infra","81-B-79294","Salzburg - Wels","< >","Attnang-Puchheim",null,2025,2025,23,24,"06.06.2025","20:00:00","10.06.2025","05:00:00","3 days + 9,0 h","Continuous","Others","T","ST",null,null,null,"C",null,null,5,null,"Erneuerung der Kreuzung 6",null,"N",null,"31.05.2024"]
[null,"ÖBB Infra","81-B-73458","Salzburg - Wels","< >","Üst Lz 2","Wels Hbf",2024,2025,50,50,"15.12.2024","00:00:00","13.12.2025",1,"364 days","Continuous","Miscellaneous","T","LT","S",null,null,null,null,null,1,null,"ETCS-LA 160 km/h",null,"N",null,"19.12.2023"]
[null,"ÖBB Infra","81-B-78292","Salzburg - Wels","< >","Linz Hbf",null,2026,2026,31,34,"27.07.2026","00:00:00","21.08.2026",1,"26 days","Continuous","Miscellaneous","T","ST",null,null,null,null,null,null,0,null,"Linz Hbf Westseite; Einbindung 4-Gl. Westbahn\n",null,"N","PEI304","13.05.2024"]
[null,"ÖBB Infra","81-B-65081","Linz - Wien (NRZ)","< >","St.Valentin","Abzw Knoten St.Peter-Seitenstetten West",2025,2025,11,13,"10.03.2025","23:50:00","29.03.2025","05:00:00","18 days + 5,2 h","Periodical","Others","T","LT",null,null,null,null,null,null,0,null,"Tunnelnachrüstung und spülen",null,"N",null,"19.12.2023"]
[null,"ÖBB Infra","81-B-75153","Salzburg - Wels","< >","Neumarkt-Kallham","Abzww Str 26101",2026,2026,7,8,"14.02.2026","00:00:00","22.02.2026",1,"9 days","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Inbetriebsetzung der neu Errichteten EStw",null,"N",null,"21.05.2024"]
[null,"ÖBB Infra","81-B-78237","Wien - Hegyeshalom","< >","Kittsee",null,2025,2025,40,50,"03.10.2025","20:00:00","12.12.2025","17:00:00","69 days + 22,0 h","Continuous","Others","T","ST","S",null,null,null,null,null,0,null,"Bahnsteigneuerrichtung neben Gleis 1",null,"N",null,"07.05.2024"]
[null,"ÖBB Infra","81-B-77799","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,34,37,"18.08.2025","04:40:00","12.09.2025","12:00:00","25 days + 7,3 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 11b",null,"Y",null,"29.05.2024"]
[null,"ÖBB Infra","81-B-77890","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,24,25,"10.06.2025","04:40:00","18.06.2025","18:00:00","8 days + 13,3 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 9a/b/c",null,"Y",null,"29.05.2024"]
[null,"ÖBB Infra","81-B-77948","Linz - Wien (GZ)","< >","Abzw Knoten Hadersdorf",null,2026,2026,43,44,"24.10.2026","00:00:00","27.10.2026",1,"4 days + 1,0 h","Continuous","Others","T","ST",null,null,null,"C","R",null,0,null,"Tausch Weichenherz DKW9",null,"N","24-202702","19.07.2024"]
[null,"SZCZ","V-013339/24","Praha - Chocen","< >","Poříčany","Český Brod",2024,2024,48,48,"2024-11-26","07:00:00","2024-11-26","13:00:00","3 x 6 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2024-07-11T10:25:42"]
[null,"SZCZ","V-008448/24","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2024,2024,34,39,"2024-08-22","19:00:00","2024-09-25","18:00:00","33 days + 23 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:46"]
[null,"SZCZ","V-008699/24","Cesky Tesin - Zilina","< >","Návsí","Mosty u Jablunkova",2024,2024,17,37,"2024-04-26","07:20:00","2024-09-11","17:00:00","2 x 10 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:47"]
[null,"SZCZ","V-008865/24","Chocen - Hranice na Morave","< >","Lukavice na Moravě","Mohelnice",2024,2024,36,36,"2024-09-03","07:15:00","2024-09-03","14:15:00","1 x 7 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:47"]
[null,"SZCZ","V-009342/24","Ostrava - Cesky Tesin","< >","Louky nad Olší","Odb Karviná-Darkov z",2024,2024,38,50,"2024-09-20","07:10:00","2024-12-14","23:59:00","85 days + 17 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. bez TV. ",null,null,null,"2024-07-11T10:25:48"]
[null,"SZCZ","V-009344/24","Ostrava - Cesky Tesin","< >","Odb Karviná-Darkov z","Louky nad Olší",2024,2024,38,38,"2024-09-20","17:00:00","2024-09-21","06:00:00","0 days + 13 hours","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. vypnutí TZZ 1. traťové koleje.",null,null,null,"2024-07-11T10:25:48"]
[null,"SZCZ","V-009774/24","Chocen - Hranice na Morave","< >","Prosenice","Přerov os.n.",2024,2024,37,37,"2024-09-10","08:00:00","2024-09-10","16:00:00","1 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:49"]
[null,"SZCZ","V-009817/24","Chocen - Hranice na Morave","< >","Prosenice","Přerov os.n.",2024,2024,38,38,"2024-09-22","06:40:00","2024-09-22","18:25:00","1 x 12 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:50"]
[null,"SZCZ","V-010167/24","Chocen - Hranice na Morave","< >","Česká Třebová","Choceň",2024,2024,38,39,"2024-09-18","07:00:00","2024-09-26","13:00:00","4 x 6 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2024-07-11T10:25:50"]
[null,"SZCZ","V-010376/24","Hranice na Morave - Zilina","< >","Vsetín","Valašské Meziříčí",2024,2024,43,43,"2024-10-22","08:00:00","2024-10-22","13:00:00","1 x 5 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. vypne senapájení 6 kV AB.",null,null,null,"2024-07-11T10:25:51"]
[null,"SZCZ","V-010585/24","Ostrava - Cesky Tesin","< >","Karviná hl.n.","Louky nad Olší",2024,2024,41,41,"2024-10-10","07:00:00","2024-10-12","16:15:00","3 x 10 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:51"]
[null,"SZCZ","V-010641/24","Ostrava - Cesky Tesin","< >","Bohumín os.n.","Bohumín st.hr.",2024,2024,42,43,"2024-10-19","07:00:00","2024-10-24","19:00:00","5 days + 12 hours","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-07-11T10:25:52"]
[null,"SZCZ","V-010994/24","Hranice na Morave - Zilina","< >","Jablůnka","Vsetín",2024,2024,41,41,"2024-10-08","07:10:00","2024-10-09","18:30:00","2 x 12 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:52"]
[null,"SZCZ","V-011065/24","Plzen - Praha","< >","Odb Tunel","Praha-Krč",2024,2024,39,39,"2024-09-26","22:20:00","2024-09-27","04:40:00","1 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2024-07-11T10:25:53"]
[null,"SZCZ","V-011079/24","Plzen - Praha","< >","Odb Tunel","Praha-Krč",2024,2024,42,43,"2024-10-17","07:30:00","2024-10-22","17:30:00","6 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. jen TV. ",null,null,null,"2024-07-11T10:25:53"]
[null,"SZCZ","V-011943/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2024,2024,45,45,"2024-11-08","00:15:00","2024-11-09","04:00:00","2 x 4 hours","Periodical","Catenary",null,"LT",null,null,"X",null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:54"]
[null,"SZCZ","V-011960/24","Praha - Chocen","< >","Kostěnice","Moravany",2024,2024,42,42,"2024-10-16","08:00:00","2024-10-16","15:00:00","1 x 7 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2024-07-11T10:25:54"]
[null,"SZCZ","V-012020/24","Chocen - Hranice na Morave","< >","Brandýs nad Orlicí z","Choceň",2024,2024,41,41,"2024-10-07","20:00:00","2024-10-08","04:00:00","1 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:54"]
[null,"SZCZ","V-012564/24","Ostrava - Cesky Tesin","< >","Karviná hl.n.","Dětmarovice",2024,2024,47,47,"2024-11-19","07:10:00","2024-11-19","13:00:00","1 x 6 hours","Periodical","Switch","T","LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2024-07-11T10:25:55"]
[null,"SZCZ","V-012681/24","Chocen - Hranice na Morave","< >","Brodek u Přerova","Grygov",2024,2024,48,48,"2024-11-28","08:00:00","2024-11-28","13:00:00","1 x 5 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. napájení 6 kV pro indikátor horkoběžnosti v km 193,295.",null,null,null,"2024-07-11T10:25:55"]
[null,"SZCZ","V-012746/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2024,2024,44,44,"2024-10-31","19:00:00","2024-11-02","03:00:00","2 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2024-07-11T10:25:56"]
[null,"SZCZ","V-013212/24","Plzen - Praha","< >","Ejpovice","Plzeň hl.n.os.n.",2024,2024,45,45,"2024-11-07","23:25:00","2024-11-08","04:15:00","1 x 5 hours","Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ost. zař.: technologie 2. traťové koleje.",null,null,null,"2024-07-11T10:25:57"]
[null,"SZCZ","V-013365/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Odb Jezernice B",2024,2024,48,48,"2024-11-27","07:00:00","2024-11-30","17:00:00","4 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2024-07-11T10:25:57"]
[null,"SZCZ","V-013400/24","Praha - Chocen","< >","Zámrsk","Uhersko",2024,2024,45,45,"2024-11-04","08:00:00","2024-11-04","15:00:00","1 x 7 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:57"]
[null,"SZCZ","V-013539/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2024,2024,46,46,"2024-11-16","07:30:00","2024-11-16","17:30:00","1 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-11T10:25:58"]
[null,"SZCZ","V-013624/24","Praha - Chocen","< >","Praha-Libeň","P.-Holeš.-Rokytka",2024,2024,41,41,"2024-10-13","07:00:00","2024-10-13","12:30:00","1 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:25:58"]
[null,"SZCZ","V-013847/24","Praha - Chocen","< >","Český Brod","Úvaly",2024,2024,39,40,"2024-09-29","22:45:00","2024-09-30","04:45:00","1 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. jen TV. ",null,null,null,"2024-07-11T10:26:00"]
[null,"SZCZ","V-003218/23","Hranice na Morave - Zilina","< >","Jablůnka","Valašské Meziříčí",2024,2024,37,38,"2024-09-14","07:20:00","2024-09-17","16:50:00","3 days + 10 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-11T10:26:22"]
[null,"SZCZ","V-005847/24","Chocen - Hranice na Morave","< >","Česká Třebová","Česká Třebová",2025,2025,45,45,"2025-11-08","18:00:00","2025-11-09","06:00:00","1 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK 1-9, 2-16 směr Třebovice v Č. a Odb Zádulka jen TV.",null,null,null,"2024-07-10T07:39:22"]
[null,"SZCZ","V-007143/24","Nürnberg - Plzen","< >","Cheb","Schirnding",2025,2025,45,45,"2025-11-04","00:00:00","2025-11-07","23:59:00","4 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-07-10T07:39:22"]
[null,"SZCZ","V-006740/24","Plzen - Praha","< >","Karlštejn","Beroun os.n.",2025,2025,20,46,"2025-05-15","18:00:00","2025-11-14","06:00:00","183 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-10T07:39:23"]
[null,"SZCZ","V-011447/24","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,34,34,"2025-08-23","00:00:00","2025-08-24","23:59:00","2 x 3 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,12a-18a jen TV, 1,2,6,8,10a + TV. ",null,null,null,"2024-07-10T07:39:23"]
[null,"SZCZ","V-005714/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2025,2025,1,1,"2025-01-03","18:00:00","2025-01-05","06:00:00","2 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-10T07:39:24"]
[null,"SZCZ","V-005697/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2025,2025,3,3,"2025-01-19","00:00:00","2025-01-19","23:59:00","1 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-10T07:39:24"]
[null,"SZCZ","V-005871/23","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,21,22,"2025-05-23","18:00:00","2025-05-27","06:00:00","4 x 6 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s jen TV. ",null,null,null,"2024-07-10T07:39:25"]
[null,"SZCZ","V-006084/24","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,15,15,"2025-04-12","00:00:00","2025-04-12","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a + TV. ",null,null,null,"2024-07-10T07:39:25"]
[null,"SZCZ","V-008923/24","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,18,19,"2025-05-01","00:00:00","2025-05-07","23:59:00","7 x 11 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. PZZ P4001.",null,null,null,"2024-07-10T07:39:25"]
[null,"SZCZ","V-015151/23","Praha - Chocen","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,17,18,"2025-04-25","00:00:00","2025-04-29","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-07-10T07:39:26"]
[null,"SZCZ","V-004389/24","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2025,2025,14,14,"2025-04-03","00:00:00","2025-04-05","23:59:00","3 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-10T07:39:26"]
[null,"SZCZ","V-012660/20","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2025,2025,31,46,"2025-08-02","00:00:00","2025-11-14","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-10T07:39:26"]
[null,"SZCZ","V-007227/20","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2025,2025,40,42,"2025-10-04","00:00:00","2025-10-19","23:59:00","16 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-10T07:39:26"]
[null,"SZCZ","V-005175/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,15,27,"2025-04-07","00:00:00","2025-07-02","23:59:00","7 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-07-10T07:39:27"]
[null,"SZCZ","V-004854/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,9,10,"2025-02-24","00:00:00","2025-03-04","23:59:00","18 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-07-10T07:39:27"]
[null,"SZCZ","V-004840/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,42,48,"2025-10-19","00:00:00","2025-11-25","23:59:00","8 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-07-10T07:39:28"]
[null,"SZCZ","V-005874/24","Chocen - Hranice na Morave","< >","Odb Parník","Č.Třebová odj.sk.",2025,2025,11,11,"2025-03-14","00:00:00","2025-03-14","23:59:00","1 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-07-10T07:39:28"]
[null,"SZCZ","V-003493/23","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2025,2025,10,10,"2025-03-03","00:00:00","2025-03-07","23:59:00","5 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-10T07:39:28"]
[null,"SZCZ","V-003072/24","Hranice na Morave - Zilina","< >","Jablůnka","Valašské Meziříčí",2025,2025,17,17,"2025-04-21","00:00:00","2025-04-25","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-07-10T07:39:28"]
[null,"SZCZ","V-019713/21","Ostrava - Cesky Tesin","< >","Havířov","Albrechtice u Č.T.",2025,2025,7,26,"2025-02-10","00:00:00","2025-06-27","23:59:00","138 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-07-10T07:39:29"]
[null,"SZCZ","V-018420/23","Chocen - Hranice na Morave","< >","Odb Jezernice A","Drahotuše",2025,2025,28,29,"2025-07-12","00:00:00","2025-07-16","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-07-10T07:39:29"]
[null,"SZCZ","V-018274/22","Praha - Hr - Chocen","< >","Borohrádek","Týniště nad Orlicí",2025,2025,10,11,"2025-03-07","00:00:00","2025-03-12","23:59:00","6 x 9 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-07-10T07:39:30"]
[null,"SZCZ","V-018467/22","Praha - Hr - Chocen","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-10T07:40:22"]
[null,"SZCZ","V-006609/24","Praha - Hr - Chocen","< >","Libice nad Cidlinou","Velký Osek",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-07-10T07:40:23"]
[null,"SZCZ","V-006240/24","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,14,53,"2026-04-01","00:00:00","2026-12-31","23:59:00","275 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"25 bez TV. ",null,null,null,"2024-07-10T07:40:23"]
[null,"SZCZ","V-006238/24","Praha - Hr - Chocen","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,8,53,"2026-02-22","00:00:00","2026-12-31","23:59:00","313 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"17 bez TV. ",null,null,null,"2024-07-10T07:40:23"]
[null,"SZCZ","V-015929/23","Praha - Hr - Chocen","< >","Velký Osek","Velký Osek",2026,2026,13,13,"2026-03-25","00:00:00","2026-03-28","23:59:00","4 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"záhlaví a zhlaví 2.traťové koleje směr Kolín.",null,null,null,"2024-07-10T07:40:24"]
[null,"ŽSR",5625270,"Zilina - Cierna nad Tisou","< >","Košice"," Košice",2024,2024,1,52,"2024-01-01","08:00:00","2024-12-31","16:00:00",null,"Periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101, 10",null,null,null,"2022-12-07"]
[null,"ŽSR",5625286,"Zilina - Cierna nad Tisou","< >","Krompachy","Margecany",2024,2024,25,40,"2024-06-17","08:00:00","2024-09-30","18:00:00",105,"Periodical","Track & Rail",null,null,null,null,null,null,null,null,null,null,"TK 1; OKLK km 134,361 -143,361 (9 000 m); OR ",null,null,null,"2023-12-21"]
[null,"ŽSR",5625317,"Zilina - Cierna nad Tisou","< >","Žilina","Žilina",2024,2024,22,42,"2024-06-01","08:00:00","2024-10-15","18:00:00",136,"Periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Modernizácia ; stredová časť podchodu, výstavba časti koľ. č. 303, 302, 301, 901, 902; O220",null,null,null,"2023-12-21"]
[null,"GySEV",5625331,"Rajka - Hegyeshalom","< >","Hegyeshalom","Rajka",2024,2024,42,42,"2024-10-17",null,"2024-10-19",null,"2 days","Continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and level crossing",null,null,null,"2023-11-28"]
[null,"GySEV",5625338,"Sopron - Györ","< >","Győr","Csorna",2025,2025,17,17,"2025-04-23","07:00:00","2025-04-23","15:00:00","8h","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,"]
[null,"MÁV",55009001103,"Hegyeshalom-Ferencváros",">","Öttevény","Győr",2024,2024,42,42,"2024-10-18","22:15:00","2024-10-19","02:15:00","4 h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009001128,"Hegyeshalom-Ferencváros",">","Tatabánya","Almásfüzitő-Felső",2024,2024,43,43,"2024-10-26","22:50:00","2024-10-27","05:05:00","6 h 15 min","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-08-09"]
[null,"MÁV",55009101002,"Szajol - Biharkeresztes","<>","Püspökladány","Báránd",2024,2024,36,36,"2024-09-02","20:40:00","2024-09-03","04:20:00","7 h 40 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120115,"Szajol-Curtici","<","Kétegyháza","Lőkösháza",2024,2024,37,37,"2024-09-12","21:00:00","2024-09-13","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120125,"Szajol-Curtici","<","Békéscsaba","Szabadkígyós",2024,2024,39,39,"2024-09-23","21:00:00","2024-09-24","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120134,"Szajol-Curtici",">","Kétegyháza","Lőkösháza",2024,2024,40,40,"2024-10-02","21:00:00","2024-10-03","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120141,"Szajol-Curtici","<>","Szabadkígyós","Lőkösháza",2024,2024,40,40,"2024-10-05","22:15:00","2024-10-06","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120142,"Szajol-Curtici","<","Kétegyháza","Lőkösháza",2024,2024,40,41,"2024-10-06","21:00:00","2024-10-07","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120143,"Szajol-Curtici","<>","Szabadkígyós","Lőkösháza",2024,2024,40,41,"2024-10-06","22:15:00","2024-10-07","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120224,"Ferencváros-Szajol (120)",">","Gyömrő","Mende",2024,2024,40,41,"2024-10-06","23:45:00","2024-10-07","03:45:00","4 h","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-08-09"]
[null,"MÁV",55009120144,"Szajol-Curtici","<","Kétegyháza","Lőkösháza",2024,2024,41,41,"2024-10-07","21:00:00","2024-10-08","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120146,"Szajol-Curtici","<>","Szabadkígyós","Lőkösháza",2024,2024,41,41,"2024-10-07","22:15:00","2024-10-08","01:30:00","3 h 15 min","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120225,"Ferencváros-Szajol (120)",">","Gyömrő","Mende",2024,2024,41,41,"2024-10-07","23:45:00","2024-10-08","03:45:00","4 h","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-08-09"]
[null,"MÁV",55009120147,"Szajol-Curtici","<>","Kétegyháza","Lőkösháza",2024,2024,41,41,"2024-10-08","21:00:00","2024-10-09","05:00:00","8 h ","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120226,"Ferencváros-Szajol (120)",">","Gyömrő","Mende",2024,2024,41,41,"2024-10-08","23:45:00","2024-10-09","03:45:00","4 h","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-08-09"]
[null,"MÁV",55009120149,"Szajol-Curtici","<>","Kétegyháza","Lőkösháza",2024,2024,41,41,"2024-10-09","21:00:00","2024-10-10","05:00:00","8 h ","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120156,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,43,43,"2024-10-24","21:00:00","2024-10-25","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120157,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,43,43,"2024-10-24","22:10:00","2024-10-25","01:30:00","3 h 20 min","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120158,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,43,43,"2024-10-25","21:00:00","2024-10-26","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120159,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,43,43,"2024-10-25","22:10:00","2024-10-26","01:30:00","3 h 20 min","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120160,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,43,43,"2024-10-26","21:00:00","2024-10-27","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120161,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,43,43,"2024-10-26","22:10:00","2024-10-27","01:30:00","3 h 20 min","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120162,"Szajol-Curtici","<","Békéscsaba","Szabadkígyós",2024,2024,43,44,"2024-10-27","21:00:00","2024-10-28","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120163,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,43,44,"2024-10-27","22:10:00","2024-10-28","01:30:00","3 h 20 min","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120164,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,45,45,"2024-11-07","21:00:00","2024-11-08","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120165,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,45,45,"2024-11-08","21:00:00","2024-11-09","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120166,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,45,45,"2024-11-09","21:00:00","2024-11-10","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120167,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,45,46,"2024-11-10","21:00:00","2024-11-11","05:00:00","8 h ","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120168,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120169,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-11","21:00:00","2024-11-12","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120170,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,46,46,"2024-11-11","22:10:00","2024-11-12","01:30:00","3 h 20 min","Continuous","Track & Rail","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120171,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-12","21:00:00","2024-11-13","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120172,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-12","21:00:00","2024-11-13","05:00:00","8 h ","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120173,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,46,46,"2024-11-12","22:10:00","2024-11-13","01:30:00","3 h 20 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120174,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","01:00:00","4 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120175,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-13","21:00:00","2024-11-14","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120176,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,46,46,"2024-11-13","22:10:00","2024-11-14","01:30:00","3 h 20 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120177,"Szajol-Curtici","<","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-14","01:00:00","2024-11-14","05:00:00","4 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120178,"Szajol-Curtici","<","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120179,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-14","21:00:00","2024-11-15","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120180,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,46,46,"2024-11-14","22:10:00","2024-11-15","01:30:00","3 h 20 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120181,"Szajol-Curtici","<","Békéscsaba","Szabadkígyós",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120182,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-15","21:00:00","2024-11-16","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120183,"Szajol-Curtici","<>","Békéscsaba","Kétegyháza",2024,2024,46,46,"2024-11-15","22:10:00","2024-11-16","01:30:00","3 h 20 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120184,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,46,46,"2024-11-16","21:00:00","2024-11-17","05:00:00","8 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120185,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-18","22:00:00","2024-11-19","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120186,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-18","22:10:00","2024-11-19","01:30:00","3 h 20 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120187,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-19","22:00:00","2024-11-20","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120188,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-19","22:15:00","2024-11-20","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120189,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-20","22:00:00","2024-11-21","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120190,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-20","22:15:00","2024-11-21","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120191,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-21","22:00:00","2024-11-22","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120192,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-21","22:15:00","2024-11-22","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120193,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-22","22:00:00","2024-11-23","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120194,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-22","22:15:00","2024-11-23","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120195,"Szajol-Curtici","<","Lőkösháza","Lőkösháza oh.",2024,2024,47,47,"2024-11-23","22:00:00","2024-11-24","04:30:00","6 h 30 min","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120196,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,47,47,"2024-11-23","22:15:00","2024-11-24","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120197,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-25","22:00:00","2024-11-26","04:30:00","6 h 30 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120198,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-25","22:15:00","2024-11-26","01:30:00","3 h 15 min","Continuous","Others","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120199,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-26","22:00:00","2024-11-27","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120200,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-26","22:15:00","2024-11-27","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120201,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-27","22:00:00","2024-11-28","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120202,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-27","22:15:00","2024-11-28","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120203,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-28","22:00:00","2024-11-29","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120204,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-28","22:15:00","2024-11-29","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120205,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-29","22:00:00","2024-11-30","04:30:00","6 h 30 min","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120206,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-29","22:15:00","2024-11-30","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120207,"Szajol-Curtici","<>","Maglód","Gyömrő",2024,2024,48,48,"2024-11-30","08:00:00","2024-11-30","16:00:00","8 h ","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120208,"Szajol-Curtici",">","Lőkösháza","Lőkösháza oh.",2024,2024,48,48,"2024-11-30","22:00:00","2024-12-01","04:30:00","6 h 30 min","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120209,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,48,48,"2024-11-30","22:15:00","2024-12-01","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120210,"Ferencváros-Szajol (120)","<>","Maglód","Gyömrő",2024,2024,48,48,"2024-12-01","08:00:00","2024-12-01","16:00:00","8 h ","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120211,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-02","22:15:00","2024-12-03","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120212,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-03","22:15:00","2024-12-04","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120213,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-04","22:15:00","2024-12-05","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120214,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-05","22:15:00","2024-12-06","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120215,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-06","22:15:00","2024-12-07","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120216,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,49,49,"2024-12-07","22:15:00","2024-12-08","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120217,"Szajol-Curtici","<>","Mende","Sülysáp",2024,2024,49,49,"2024-12-08","08:00:00","2024-12-08","12:00:00","4 h ","Continuous","Cetenary",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-03-04"]
[null,"MÁV",55009120218,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,50,50,"2024-12-09","22:15:00","2024-12-10","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120219,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,50,50,"2024-12-10","22:15:00","2024-12-11","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120220,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,50,50,"2024-12-11","22:15:00","2024-12-12","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120221,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,50,50,"2024-12-12","22:15:00","2024-12-13","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"MÁV",55009120222,"Szajol-Curtici","<>","Békéscsaba","Lőkösháza",2024,2024,50,50,"2024-12-13","22:15:00","2024-12-14","01:30:00","3 h 15 min","Continuous","Cetenary","T","LT","S",null,null,null,null,null,null,null,"Total closure",null,null,null,"2024-03-04"]
[null,"CFR",5525627,"Arad - Simeria",null,"Savarsin","Varadia",2023,2024,36,36,"2023-09-10","00:00:00","2024-09-04","23:59:00","361d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525628,"Arad - Simeria",null,"Varadia","Batuta",2019,2024,9,36,"2019-02-27","00:00:00","2024-09-06","23:59:00","2019d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525629,"Arad - Simeria",null,"Barzava","Barzava Noua",2019,2024,25,36,"2019-06-19","00:00:00","2024-09-06","23:59:00","1907d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525631,"Arad - Simeria","< >","Varadia","Batuta",2019,2025,9,7,"2019-02-27","00:00:00","2025-02-11","23:59:00","2177d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525632,"Arad - Simeria","< >","Barzava","Barzava Noua",2019,2025,25,7,"2019-06-19","00:00:00","2025-02-11","23:59:00","2065d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525633,"Arad - Simeria","< >"," Bătuța ","Bârzava",2024,2025,30,7,"2024-07-27","00:00:00","2025-02-11","23:59:00","200d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525634,"Arad - Simeria","< >","Vărădia","Bârzava Nouă",2024,2025,32,7,"2024-08-11","00:00:00","2025-02-11","23:59:00","185d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525637,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2024,1,52,"2024-01-01","00:00:00","2024-12-31","23:59:00","567 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525638,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","567 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525639,"Simeria -  Brasov","< >","Feldioara",null,2024,2024,1,52,"2024-01-01","00:00:00","2024-12-31","23:59:00","569 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525640,"Simeria -  Brasov","< >","Feldioara",null,2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","569 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525641,"Simeria -  Brasov","< >","Feldioara","Apata",2024,2024,1,52,"2024-01-01","00:00:00","2024-12-31","23:59:00","458 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525642,"Simeria -  Brasov","< >","Feldioara","Apata",2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","458 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525643,"Simeria -  Brasov","< >","Mureni","Vanatori",2024,2024,1,52,"2024-01-01","00:00:00","2024-12-31","23:59:00","523 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525644,"Simeria -  Brasov","< >","Mureni","Vanatori",2025,2025,1,12,"2025-01-01","00:00:00","2025-03-21","23:59:00","523 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525645,"Simeria -  Brasov","< >","Statia Vanatori",null,2024,2024,1,40,"2024-01-01","00:00:00","2024-10-01","23:59:00","352 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525646,"Simeria -  Brasov","< >","Vanatori","Albesti",2024,2024,1,40,"2024-01-01","00:00:00","2024-10-01","23:59:00","352 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525647,"Simeria -  Brasov","< >","Augustin","Racos",2024,2024,18,51,"2024-04-29","00:00:00","2024-12-16","23:59:00","232 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525648,"Simeria -  Brasov","< >","Racos",null,2024,2024,18,51,"2024-04-29","00:00:00","2024-12-16","23:59:00","232 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525649,"Simeria -  Brasov","< >","Rupea","Racos",2024,2024,18,51,"2024-04-29","00:00:00","2024-12-16","23:59:00","232 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525650,"Simeria -  Brasov","< >","Brașov","Stupini",2021,2025,47,39,"25.11.2021","00:00:00","27.09.2025","23:59:00","1403d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525651,"Simeria -  Brasov","< >","Stupini","Bod",2023,2025,22,48,"01.06.2023","00:00:00","27.11.2025","23:59:00","911d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525652,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,14,48,"03.04.2023","00:00:00","27.11.2025","23:59:00","970d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525653,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,7,48,"15.02.2023","00:00:00","27.11.2025","23:59:00","1017d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525654,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2024,15,30,"14.04.2024","00:00:00","28.07.2024","23:59:00","106d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525655,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2024,24,24,"11.06.2024","00:00:00","16.06.2024","23:59:00","6d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525656,"Simeria -  Brasov","< >","Feldioara","Apața",2025,2025,4,6,"21.01.2025","00:00:00","05.02.2025","23:59:00","16d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525657,"Simeria -  Brasov","< >","Cata","Rupea",2023,2026,5,50,"02.02.2023","00:00:00","12.12.2026","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525658,"Simeria -  Brasov","< >","Cața","Beia",2023,2026,5,9,"02.02.2023","00:00:00","01.03.2026","23:59:00","1124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525659,"Simeria -  Brasov","< >","Beia","Mureni",2023,2026,44,40,"30.10.2023","00:00:00","30.09.2026","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525661,"Simeria -  Brasov","< >","Beia","Mureni",2025,2025,39,39,"22.09.2025","00:00:00","25.09.2025","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525662,"Simeria -  Brasov","< >","Cața","Archita",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525663,"Simeria -  Brasov","< >","Cața","Archita",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525664,"Simeria -  Brasov","< >","Archita ","Vînători ",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525665,"Simeria -  Brasov","< >","Archita","Vînători ",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525666,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2026,45,40,"09.11.2022","00:00:00","30.09.2026","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525667,"Simeria -  Brasov","< >","Vînători","Albești",2023,2026,24,20,"16.06.2023","00:00:00","12.05.2026","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525668,"Simeria -  Brasov","< >","Vînători","Cristur",2024,2024,27,28,"01.07.2024","00:00:00","10.07.2024","23:59:00","10d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525670,"Simeria -  Brasov","< >","Albești","Sighișoara",2023,2025,24,20,"16.06.2023","00:00:00","12.05.2025","23:59:00","697d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525671,"Simeria -  Brasov","< >","Apata","Augustin",2021,2025,15,33,"2021-04-15","00:00:00","2025-08-11","23:59:00","1580d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525672,"Simeria -  Brasov","< >","Augustin","Racos",2023,2025,28,40,"2023-07-14","00:00:00","2025-09-30","23:59:00","810d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525673,"Simeria -  Brasov","< >","Racos","Rupea",2022,2025,10,11,"2022-03-08","00:00:00","2025-03-12","23:59:00","1101d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525674,"Simeria -  Brasov","< >","Rupea-Cata","Rupea-Cata",2024,2024,31,41,"2024-07-29","00:00:00","2024-10-09","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525675,"Simeria -  Brasov","< >","Racos-Rupea","Racos-Rupea",2024,2025,41,43,"2024-10-10","00:00:00","2025-10-25","23:59:00","381d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525677,"Simeria -  Brasov","< >","Brașov","Stupini",2023,2026,22,12,"01.06.2023","00:00:00","16.03.2026","23:59:00","1020d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525678,"Simeria -  Brasov","< >","Brașov","Stupini",2024,2025,35,10,"28.08.2024","00:00:00","06.03.2025","23:59:00","191d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525679,"Simeria -  Brasov","< >","Stupini","Bod",2023,2024,33,27,"18.08.2023","00:00:00","04.07.2024","23:59:00","322d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525680,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,33,10,"18.08.2023","00:00:00","06.03.2025","23:59:00","567d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525681,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2024,22,30,"01.06.2023","00:00:00","28.07.2024","23:59:00","424d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525682,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,33,10,"18.08.2023","00:00:00","06.03.2025","23:59:00","567d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525683,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525684,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,49,10,"05.12.2023","00:00:00","06.03.2025","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525685,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2024,9,29,"02.03.2023","00:00:00","20.07.2024","23:59:00","507d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525686,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2024,29,29,"15.07.2024","00:00:00","18.07.2024","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5525687,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2024,6,30,"06.02.2024","00:00:00","28.07.2024","23:59:00","174d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525688,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2024,15,30,"14.04.2024","00:00:00","28.07.2024","23:59:00","106d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5525689,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525690,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,49,10,"05.12.2023","00:00:00","06.03.2025","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525691,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525692,"Simeria -  Brasov","< >","Apata","Augustin",2021,2024,15,47,"2021-04-15","00:00:00","2024-11-23","23:59:00","1319d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]
[null,"CFR",5525693,"Simeria -  Brasov","< >","Augustin","Racos",2023,2025,28,30,"2023-07-14","00:00:00","2025-07-23","23:59:00","741d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525694,"Simeria -  Brasov","< >","Augustin","Racos",2024,2025,32,21,"2024-08-07","00:00:00","2025-05-23","23:59:00","290d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525695,"Simeria -  Brasov","< >","Racos","Rupea",2022,2025,10,30,"2022-03-08","00:00:00","2025-07-23","23:59:00","1234d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]
[null,"CFR",5525696,"Simeria -  Brasov","< >","Rupea","Cața",2022,2025,22,34,"2022-06-01","00:00:00","2025-08-21","23:59:00","1178d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]
[null,"CFR",5525697,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,25,12,"18.06.2024","00:00:00","21.03.2025","23:59:00","277d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525698,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,3,25,"16.01.2024","00:00:00","16.06.2025","23:59:00","518d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525699,"Simeria -  Brasov","< >","Cața","Beia",2025,2025,25,51,"17.06.2025","00:00:00","20.12.2025","23:59:00","187d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525700,"Simeria -  Brasov","< >","Cața","Beia",2024,2024,10,25,"08.03.2024","00:00:00","17.06.2024","23:59:00","102d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525701,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,25,12,"18.06.2024","00:00:00","21.03.2025","23:59:00","277d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525702,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,3,25,"16.01.2024","00:00:00","16.06.2025","23:59:00","518d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525703,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525704,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525705,"Simeria -  Brasov","< >","Beia","Mureni",2023,2024,44,40,"30.10.2023","00:00:00","30.09.2024","23:59:00","337d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525706,"Simeria -  Brasov","< >","Beia","Mureni",2024,2024,10,29,"08.03.2024","00:00:00","17.07.2024","23:59:00","132d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525707,"Simeria -  Brasov","< >","Beia","Mureni",2023,2024,44,40,"30.10.2023","00:00:00","30.09.2024","23:59:00","337d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525708,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525709,"Simeria -  Brasov","< >","Beia","Archita",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525710,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525711,"Simeria -  Brasov","< >","Archita","Mureni ",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525712,"Simeria -  Brasov","< >","Archita","Vânători ",2025,2026,51,7,"2025-12-21","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525713,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525714,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525715,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525716,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525717,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525718,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525719,"Simeria -  Brasov","< >","Vânători ","Albești",2023,2024,42,40,"16.10.2023","00:00:00","01.10.2024","23:59:00","352d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525720,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525721,"Simeria -  Brasov","< >","Vânători ","Albești",2023,2024,42,40,"16.10.2023","00:00:00","01.10.2024","23:59:00","352d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525722,"Simeria -  Brasov","< >","Albești","Sighisoara",2023,2024,24,49,"16.06.2023","00:00:00","07.12.2024","23:59:00","541d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525723,"Simeria -  Brasov","< >","Albești","Sighișoara",2024,2025,49,51,"08.12.2024","00:00:00","20.12.2025","23:59:00","378d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-16"]
[null,"CFR",5525676,"Coslariu - Cluj Napoca","< >","Valea Florilor","Boju",2024,2024,1,52,"2024-01-01","00:00:00","2024-12-31","23:59:00","580 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction"]
[null,"CFR",5525623,"Coslariu - Cluj Napoca",null,"Valea Florilor ","Boju",2023,2024,22,52,"2023-06-01","00:00:00","2024-12-31","23:59:00","580d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"30.01.2023"]
[null,"CFR",5525726,"Biharkeresztes - Cluj Napoca","< >","Aghires","Poieni",2024,2025,1,52,"2024-01-01","00:00:00","2025-12-31","23:59:00","731d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-07-10"]
[null,"CFR",5525727,"Biharkeresztes - Cluj Napoca","< >","Poieni","Alesd",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-07-10"]
[null,"CFR",5525728,"Biharkeresztes - Cluj Napoca","< >","Alesd","Oradea",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]
[null,"CFR",5525729,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525730,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525731,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525732,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525733,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontiera",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525734,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525735,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525736,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525737,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Tileagd ",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525738,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea Vest",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525739,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525740,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525741,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Biharia",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525742,"Biharkeresztes - Cluj Napoca","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525743,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525744,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525745,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525746,"Biharkeresztes - Cluj Napoca","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525747,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525748,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525749,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525750,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului ","Bulz",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525751,"Biharkeresztes - Cluj Napoca","< >","Bulz ","Bratca",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525752,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525753,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525754,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525755,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525756,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525757,"Biharkeresztes - Cluj Napoca","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525758,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525759,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525760,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525761,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525762,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525763,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525764,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525765,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525766,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525767,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525768,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525769,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525770,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525780,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,27,27,"2025-07-01","00:00:00","2025-07-02","23:59:00","2d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525781,"Arad - Craiova","< >","Lugoj ","Jabăr",2025,2025,30,30,"2025-07-24","00:00:00","2025-07-24","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525782,"Arad - Craiova","< >","Jabăr","Belinț",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525783,"Arad - Craiova","< >","Belinț","Chizătău",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525784,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525786,"Arad - Craiova","< >","Lugoj – Costeiu Mare","Lugoj – Costeiu Mare",2025,2025,27,30,"2025-07-04","00:00:00","2025-07-24","23:59:00","21d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525787,"Arad - Craiova","< >","Timișoara Est ","Remetea Mare",2024,2024,48,49,"2024-12-01","00:00:00","2024-12-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525788,"Arad - Craiova","< >","Timișoara Est","Timișoara Nord",2024,2024,48,49,"2024-12-01","00:00:00","2024-12-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525789,"Arad - Craiova","< >","Timișoara Est","Timișoara Nord",2025,2025,27,28,"2025-07-01","00:00:00","2025-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525790,"Arad - Craiova","< >","Timișoara Est ","Timișoara Nord",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525791,"Arad - Craiova","< >","Ronaț Triaj Gr. D",null,2024,2024,40,41,"2024-10-01","00:00:00","2024-10-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525792,"Arad - Craiova","< >","Ronaț Triaj Gr. D",null,2025,2025,14,15,"2025-04-01","00:00:00","2025-04-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525793,"Arad - Craiova","< >","Ronaț Triaj Gr. D",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525794,"Arad - Craiova","< >","Ronaț Triaj gr.D "," Dudeștii Noi",2024,2024,41,49,"2024-10-08","00:00:00","2024-12-08","23:59:00","62d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525795,"Arad - Craiova","< >","Timișoara Nord",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525796,"Arad - Craiova","< >","Orțișoara",null,2025,2025,18,19,"2025-05-01","00:00:00","2025-05-08",1.9993055555555554,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525798,"Arad - Craiova","< >","Sânandrei",null,2025,2025,18,19,"2025-05-01","02:00:00","2025-05-08",2.0826388888888898,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525799,"Arad - Craiova","< >","Sânandrei ","Hodoni",2025,2025,18,19,"2025-05-01","03:00:00","2025-05-08",2.1243055555555599,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525801,"Arad - Craiova","< >","Șag ","Valea Viilor",2024,2024,44,45,"2024-11-01","00:00:00","2024-11-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525802,"Arad - Craiova","< >","Șag ","Valea Viilor",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525803,"Arad - Craiova","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525804,"Arad - Craiova","< >","Aradul Nou","Zădăreni",2024,2025,32,32,"2024-08-08","00:00:00","2025-08-08","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525805,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525806,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525807,"Arad - Craiova","< >","Aradul Nou","Arad",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525808,"Arad - Craiova","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525809,"Arad - Craiova","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525810,"Arad - Craiova","< >","Ronat Triaj Gr.D ","Vinga",2026,2026,17,19,"2026-04-24","00:00:00","2026-05-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525811,"Arad - Craiova","< >","Ramificație Pod Mureș ","Glogovăț",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525812,"Arad - Craiova","< >","Glogovăț","Arad",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525813,"Arad - Craiova","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525814,"Arad - Craiova","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525816,"Bucuresti-Constanta","< >","Fetesti","Borcea",2024,2024,35,37,"2024-09-01","00:00:00","2024-09-15","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"CFR",5525771,"Bucuresti-Constanta","< >","Ciulnita","Medgidia",2023,2024,26,47,"2023-07-01","00:00:00","2024-11-19","23:59:00","508d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]
[null,"CFR",5525772,"Bucuresti-Constanta","< >","Fetesti","Tandarei",2023,2024,26,47,"2023-07-01","00:00:00","2024-11-19","23:59:00","508d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-07-10"]

{"sheet":"Graphic Overview","index":2,"n_rows":151,"n_cols":374,"rows_kept":151,"cut":false,"hidden":false,"merged":[[3,237,3,243],[3,244,3,250],[3,251,3,257],[3,258,3,264],[3,9,3,12],[3,13,3,19],[3,20,3,26],[3,27,3,33],[3,34,3,40],[3,41,3,47],[3,48,3,54],[3,55,3,61],[3,62,3,68],[3,69,3,75],[3,76,3,82],[3,83,3,89],[3,90,3,96],[3,97,3,103],[3,335,3,341],[3,300,3,306],[3,307,3,313],[3,314,3,320],[3,321,3,327],[3,328,3,334],[3,265,3,271],[3,272,3,278],[3,279,3,285],[3,286,3,292],[3,293,3,299],[3,139,3,145],[3,146,3,152],[3,153,3,159],[3,160,3,166],[3,167,3,173],[3,174,3,180],[3,104,3,110],[3,111,3,117],[3,118,3,124],[3,125,3,131],[3,132,3,138],[2,129,2,159],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[3,223,3,229],[3,181,3,187],[2,282,2,312],[2,313,2,342],[2,343,2,373],[3,188,3,194],[3,195,3,201],[3,202,3,208],[3,209,3,215],[3,216,3,222],[3,342,3,348],[3,349,3,355],[3,356,3,362],[3,363,3,369],[3,370,3,373],[3,230,3,236],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128]]}
[null,"RFC 9 Overview"]
[]
[null,null,null,null,null,null,2026,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Appenweier - Mühlacker"]
[null," "]
[]
[null,"Abzw Nantenbach - Rohrbach"]
[null," "]
[]
[null,"Darmstadt - Aschaffenburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,null,null,null,null,null,2,2,2,null,null,null,null,2,2,2,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,null,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,null,null,null,null,null,null,2,2,5,5,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,2,null,null,null,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,2,2,5,5]
[null," "]
[]
[null,"Darmstadt - Mannheim",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Aschaffenburg - Würzburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Gemünden - Bamberg - Nürnberg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Würzburg - Nürnberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nürnberg - Regensburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nürnberg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,null,null,null,null,null,2,2,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,5,2,2,2,2,2,2,2,2,2,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Regensburg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Regensburg - Wels",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,null,null,null,null,null,null,null,5,5,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Karlsruhe - Strasbourg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Mannheim - Karlsruhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Karlsruhe - Stuttgart",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,2,2,2,2,2,2,2,2,2,2,null,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Stuttgart - München",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"München - Salzburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"München - Regensburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Salzburg - Wels",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wels - Linz",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wels - Traun - Linz",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Linz - Wien (NRZ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5]
[null," "]
[]
[null,"Linz - Wien (GZ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5]
[null," "]
[]
[null,"Wien - Hegyeshalom",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Praha - Hr - Chocen",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Praha - Chocen"]
[null," "]
[]
[null,"Plzen - Praha",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null," "]
[]
[null,"Chocen - Hranice na Morave",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Ostrava",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Zilina",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Ostrava - Cesky Tesin"]
[null," "]
[]
[null,"Zilina - Cierna nad Tisou",null,null,null,null,null,null,null,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6]
[null," "]
[]
[null,"Cesky Tesin - Zilina"]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Sopron - Györ"]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron"]
[null," "]
[]
[null,"Hegyeshalom - Rajka"]
[null," "]
[]
[null,"Hegyeshalom-Ferencváros"]
[null," "]
[]
[null,"Ferencváros-Szajol (100)"]
[null," "]
[]
[null,"Ferencváros-Szajol (120)"]
[null," "]
[]
[null,"Szajol-Curtici"]
[null," "]
[]
[null,"Szajol - Biharkeresztes"]
[null," "]
[]
[null,"Arad - Simeria"]
[null," "]
[]
[null,"Arad - Craiova",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Simeria -  Brasov",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Bucuresti-Constanta"]
[null," "]
[]
[null,"Coslariu - Cluj Napoca"]
[null," "]
[]
[null,"Biharkeresztes - Cluj Napoca",null,null,null,null,null,null,null,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[]
[]
[]
[null,"Error in *All day*, *Day* or *Night*"]
[null,"| 12107 | 12108 | 12110 | 12111 | 12414 "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":53,"n_cols":23,"rows_kept":53,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Appenweier - Mühlacker",1,"< >","Continuous",25831,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Abzw Nantenbach - Rohrbach",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Darmstadt - Aschaffenburg",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Darmstadt - Mannheim",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Aschaffenburg - Würzburg",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Gemünden - Bamberg - Nürnberg",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["SNCF-R",87,"Würzburg - Nürnberg",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["CFR",53,"Nürnberg - Regensburg",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,"Nürnberg - Plzen",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"Regensburg - Plzen",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Regensburg - Wels",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Karlsruhe - Strasbourg",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Mannheim - Karlsruhe",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Karlsruhe - Stuttgart",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Stuttgart - München",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"München - Salzburg",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"München - Regensburg",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Salzburg - Wels",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Wels - Linz",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Wels - Traun - Linz",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Linz - Wien (NRZ)",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Linz - Wien (GZ)",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Wien - Hegyeshalom",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Praha - Hr - Chocen",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Praha - Chocen",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Plzen - Praha",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Chocen - Hranice na Morave",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Hranice na Morave - Ostrava",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Hranice na Morave - Zilina",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Ostrava - Cesky Tesin",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Zilina - Cierna nad Tisou",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Cesky Tesin - Zilina",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Rajka - Hegyeshalom",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Sopron - Györ",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Wien - Ebenfurth - Sopron",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Hegyeshalom - Rajka",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Hegyeshalom-Ferencváros",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Ferencváros-Szajol (100)",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Ferencváros-Szajol (120)",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Szajol-Curtici",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Szajol - Biharkeresztes",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Arad - Simeria",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Arad - Craiova",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Simeria -  Brasov",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Bucuresti-Constanta",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Coslariu - Cluj Napoca",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Biharkeresztes - Cluj Napoca",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]