{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":3,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2027,52]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":17718,"n_cols":37,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,34,2,34],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Weekdays","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"CFR",5326073,"Arad - Craiova","< >","Aradu Nou","Arad",2026,2027,43,17,"2026-10-23","00:00:00","2027-04-26","23:59:00","186d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-22"]
[null,"CFR",5326077,"Arad - Craiova","< >","Aradul Nou","Zădăreni ",2025,2026,2,4,"2025-01-09","00:00:00","2026-01-23","23:59:00","380d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-01-10"]
[null,"CFR",5326146,"Arad - Craiova","< >","Aradul Nou",null,2025,2026,4,4,"2025-01-21","00:00:00","2026-01-23","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5326147,"Arad - Craiova","< >","Aradul Nou",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525804,"Arad - Craiova","< >","Aradul Nou","Zădăreni",2024,2025,32,32,"2024-08-08","00:00:00","2025-08-08","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525807,"Arad - Craiova","< >","Aradul Nou","Arad",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525809,"Arad - Craiova","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525808,"Arad - Craiova","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326134,"Arad - Craiova","< >","Baile Calacea","Orțișoara",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"2,3,4,5,6"]
[null,"CFR",5326132,"Arad - Craiova","< >","Băile Calacea",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326133,"Arad - Craiova","< >","Băile Calacea",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326030,"Arad - Craiova","< >","Belinț",null,2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326039,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326102,"Arad - Craiova","< >","Belinț",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,6]
[null,"CFR",5326103,"Arad - Craiova","< >","Belinț","Chizătău",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"1,2,3"]
[null,"CFR",5326115,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"2,3,4,5,6"]
[null,"CFR",5326117,"Arad - Craiova","< >","Belinț","Topolovat",2026,2027,45,22,"2026-11-03","00:00:00","2027-06-02","23:59:00","212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"2,3,4,5,6"]
[null,"CFR",5525783,"Arad - Craiova","< >","Belinț","Chizătău",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"2,3,4,5,6"]
[null,"CFR",5326031,"Arad - Craiova","< >","Belinț ","Chizătău",2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,1.2]
[null,"CFR",5326019,"Arad - Craiova","< >","Caransebes","Balta Sărată",2026,2026,27,28,"2026-07-03","00:00:00","2026-07-06","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326079,"Arad - Craiova","< >","Caransebes",null,2025,2026,12,28,"2025-03-19","00:00:00","2026-07-06","23:59:00","475d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"1,2,3,4,5"]
[null,"CFR",5326080,"Arad - Craiova","< >","Caransebes",null,2026,2027,28,40,"2026-07-07","00:00:00","2027-10-04","23:59:00","455d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,"2,3,4,5,6"]
[null,"CFR",5326020,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2024,2025,49,49,"2024-12-03","00:00:00","2025-12-02","23:59:00","365d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,"1,2,3"]
[null,"CFR",5326021,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2026,2026,28,44,"2026-07-07","00:00:00","2026-11-01","23:59:00","118d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,1.2]
[null,"CFR",5326023,"Arad - Craiova","< >","Caransebes ","Zăgujeni",2025,2026,31,36,"2025-07-30","00:00:00","2026-09-01","23:59:00","399d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,1.2]
[null,"CFR",5326082,"Arad - Craiova","< >","Caransebes Tj",null,2024,2025,49,12,"2024-12-03","00:00:00","2025-03-18","23:59:00","106d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,7]
[null,"CFR",5326022,"Arad - Craiova","< >","Caransebes Tj ","Zăgujeni",2024,2025,49,31,"2024-12-03","00:00:00","2025-07-29","23:59:00","239d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13",null,null,7]
[null,"CFR",5326089,"Arad - Craiova","< >","Căvăran",null,2024,2026,49,18,"2024-12-03","00:00:00","2026-05-02","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13",null,null,7]
[null,"CFR",5326090,"Arad - Craiova","< >","Căvăran",null,2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326092,"Arad - Craiova","< >","Căvăran","Găvojdia",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08",null,null,"2,4,5",1]
[null,"CFR",5326040,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-24",null,null,"5,6",1]
[null,"CFR",5326104,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25",null,null,"3,4",1]
[null,"CFR",5326116,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25",null,null,"1,2,3,4,5",1]
[null,"CFR",5525784,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-25",null,null,"1,2,3,4,7",1]
[null,"CFR",5326032,"Arad - Craiova","< >","Chizătău ","Topolovat",2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-25",null,null,"1,2,3,4,7",1]
[null,"CFR",5326093,"Arad - Craiova","< >","Găvojdia",null,2026,2026,11,12,"2026-03-14","00:00:00","2026-03-18","23:59:00","5d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25",null,null,"1,2,3,4,5",1]
[null,"CFR",5326094,"Arad - Craiova","< >","Găvojdia",null,2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08",null,null,"1,7",1]
[null,"CFR",5326095,"Arad - Craiova","< >","Găvojdia",null,2026,2026,12,36,"2026-03-19","00:00:00","2026-09-01","23:59:00","167d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25",null,null,"1,2,3",1]
[null,"CFR",5326096,"Arad - Craiova","< >","Găvojdia","Lugoj",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26",null,null,2,1]
[null,"CFR",5326078,"Arad - Craiova","< >","Glogovăț","Arad",2027,2027,39,41,"2027-10-01","00:00:00","2027-10-17","23:59:00","17d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-25",null,null,"2,3",1]
[null,"CFR",5326148,"Arad - Craiova","< >","Glogovăț","Arad",2026,2026,4,38,"2026-01-23","00:00:00","2026-09-18","23:59:00","239d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26",null,null,2,1]
[null,"CFR",5326149,"Arad - Craiova","< >","Glogovăț","Arad",2026,2027,38,2,"2026-09-18","00:00:00","2027-01-17","23:59:00","122d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525812,"Arad - Craiova","< >","Glogovăț","Arad",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28",null,null,1,1]
[null,"CFR",5525813,"Arad - Craiova","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05",null,null,"1,2",1]
[null,"CFR",5326028,"Arad - Craiova","< >","Jabar",null,2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-28",null,null,"1,5,6,7",1]
[null,"CFR",5326038,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326101,"Arad - Craiova","< >","Jabăr","Belinț",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326114,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525782,"Arad - Craiova","< >","Jabăr","Belinț",2025,2025,34,34,"2025-08-19","00:00:00","2025-08-19","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326029,"Arad - Craiova","< >","Jabăr ","Belinț",2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-28",null,null,"1,2,5,6,7",1]
[null,"CFR",5326091,"Arad - Craiova","< >","Jena","Găvojdia",2026,2026,18,18,"2026-04-27","00:00:00","2026-05-02","23:59:00","6d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-29",null,null,"3,4",1]
[null,"CFR",5326027,"Arad - Craiova","< >","Lugoj","Jabăr",2025,2025,28,28,"2025-07-10","00:00:00","2025-07-11","23:59:00","2d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-29",null,null,"2,3",1]
[null,"CFR",5326037,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-29",null,null,"3,4",1]
[null,"CFR",5326041,"Arad - Craiova","< >","Lugoj","Sinia",2025,2025,11,21,"2025-03-12","00:00:00","2025-05-21","23:59:00","71d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326042,"Arad - Craiova","< >","Lugoj","Costeiu Mare",2026,2026,8,14,"2026-02-21","00:00:00","2026-04-02","23:59:00","41d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326098,"Arad - Craiova","< >","Lugoj",null,2025,2025,11,28,"2025-03-12","00:00:00","2025-07-10","23:59:00","121d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326099,"Arad - Craiova","< >","Lugoj",null,2025,2026,28,27,"2025-07-10","00:00:00","2026-07-03","23:59:00","359d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326100,"Arad - Craiova","< >","Lugoj","Jabăr",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326113,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525781,"Arad - Craiova","< >","Lugoj ","Jabăr",2025,2025,30,30,"2025-07-24","00:00:00","2025-07-24","23:59:00","1d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326118,"Arad - Craiova","< >","Lugoj – Belint","Lugoj – Belint",2026,2027,45,14,"2026-11-03","00:00:00","2027-04-06","23:59:00","155d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525786,"Arad - Craiova","< >","Lugoj – Costeiu Mare","Lugoj – Costeiu Mare",2025,2025,27,30,"2025-07-04","00:00:00","2025-07-24","23:59:00","21d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326065,"Arad - Craiova","< >","Orțișoara",null,2025,2025,27,29,"2025-07-04","00:00:00","2025-07-14","23:59:00","11d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326066,"Arad - Craiova","< >","Orțișoara",null,2025,2025,42,43,"2025-10-17","00:00:00","2025-10-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19",null,null,"5,6,7",1]
[null,"CFR",5326067,"Arad - Craiova","< >","Orțișoara",null,2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326068,"Arad - Craiova","< >","Orțișoara",null,2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326076,"Arad - Craiova","< >","Orțișoara","Aradu Nou",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326135,"Arad - Craiova","< >","Orțișoara",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326136,"Arad - Craiova","< >","Orțișoara",null,2025,2027,43,4,"2025-10-24","00:00:00","2027-01-25","23:59:00","459d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326137,"Arad - Craiova","< >","Orțișoara","Vinga",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525796,"Arad - Craiova","< >","Orțișoara",null,2025,2025,18,19,"2025-05-01","00:00:00","2025-05-08",1.9993055555555554,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-05",null,null,"1,2,3",1]
[null,"CFR",5525814,"Arad - Craiova","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05",null,null,"1,2,3",1]
[null,"CFR",5525811,"Arad - Craiova","< >","Ramificație Pod Mureș ","Glogovăț",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-22",null,null,"1,2,3,4,5",1]
[null,"CFR",5326035,"Arad - Craiova","< >","Recaș",null,2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-06",null,null,"2,3,4,5",1]
[null,"CFR",5326036,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-06",null,null,"1,6,7",1]
[null,"CFR",5326108,"Arad - Craiova","< >","Recaș",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06",null,null,"1,6,7",1]
[null,"CFR",5326109,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-07-24",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326111,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326025,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,27,27,"2025-07-02","00:00:00","2025-07-03","23:59:00","2d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-06",null,null,"1,2",1]
[null,"CFR",5326026,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,48,48,"2025-11-24","00:00:00","2025-11-26","23:59:00","3d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-06",null,null,"2,3,4,5",1]
[null,"CFR",5326046,"Arad - Craiova","< >","Remetea Mare","Timișoara Est",2025,2025,22,23,"2025-05-27","00:00:00","2025-06-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-06",null,null,"3,4",1]
[null,"CFR",5326097,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2026,27,43,"2025-07-03","00:00:00","2026-10-23","23:59:00","478d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06",null,null,"1,2",1]
[null,"CFR",5326110,"Arad - Craiova","< >","Remetea Mare",null,2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06",null,null,"3,4",1]
[null,"CFR",5326112,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07",null,null,"1,2,3,4,5,6",1]
[null,"CFR",5326119,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2027,2027,15,18,"2027-04-15","00:00:00","2027-05-04","23:59:00","20d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07",null,null,"1,2,3,4,5,6",1]
[null,"CFR",5525780,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,27,27,"2025-07-01","00:00:00","2025-07-02","23:59:00","2d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-07",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326045,"Arad - Craiova","< >","Ronaț Triaj","Timișoara Sud",2024,2025,35,23,"2024-09-01","00:00:00","2025-06-02","23:59:00","275d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525792,"Arad - Craiova","< >","Ronaț Triaj Gr. D",null,2025,2025,14,15,"2025-04-01","00:00:00","2025-04-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-21",null,null,"1,6,7",1]
[null,"CFR",5525793,"Arad - Craiova","< >","Ronaț Triaj Gr. D",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-21",null,null,"1,6,7",1]
[null,"CFR",5326049,"Arad - Craiova","< >","Ronaț Triaj Gr.A","Ronaț Triaj Gr.A",2025,2025,34,36,"2025-08-18","00:00:00","2025-09-02","23:59:00","16d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326069,"Arad - Craiova","< >","Ronat Triaj Gr.D","Orțișoara",2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"5,6,7",1]
[null,"CFR",5326128,"Arad - Craiova","< >","Ronat Triaj Gr.D","Sânandrei",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07",null,null,"6,7",1]
[null,"CFR",5326050,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Dudeștii Noi",2025,2025,23,31,"2025-06-02","00:00:00","2025-08-01","23:59:00","61d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"1,2,3",1]
[null,"CFR",5326053,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2025,2025,22,23,"2025-05-27","00:00:00","2025-06-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"1,2,3",1]
[null,"CFR",5326054,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2025,2025,30,31,"2025-07-25","00:00:00","2025-08-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07",null,null,"4,5",1]
[null,"CFR",5326062,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2027,2027,1,2,"2027-01-05","00:00:00","2027-01-12","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-03-21",null,null,"1,6,7",1]
[null,"CFR",5326123,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2024,2025,35,23,"2024-09-01","00:00:00","2025-06-02","23:59:00","275d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07",null,null,"1,2,5,6,7",1]
[null,"CFR",5525810,"Arad - Craiova","< >","Ronat Triaj Gr.D ","Vinga",2026,2026,17,19,"2026-04-24","00:00:00","2026-05-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-13",null,null,6,1]
[null,"CFR",5326141,"Arad - Craiova","< >","Sag",null,2024,2026,43,4,"2024-10-23","00:00:00","2026-01-23","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-17",null,null,7,1]
[null,"CFR",5326142,"Arad - Craiova","< >","Sag",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-08",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326072,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2026,4,21,"2026-01-23","00:00:00","2026-05-23","23:59:00","121d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-09",null,null,"5,6",1]
[null,"CFR",5326143,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525802,"Arad - Craiova","< >","Șag ","Valea Viilor",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-09",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525803,"Arad - Craiova","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-09",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326063,"Arad - Craiova","< >","Sânandrei","Sânandrei",2025,2025,42,43,"2025-10-17","00:00:00","2025-10-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"2,3,4",1]
[null,"CFR",5326064,"Arad - Craiova","< >","Sânandrei","Hodoni",2025,2025,34,43,"2025-08-24","00:00:00","2025-10-24","23:59:00","62d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"2,3,4",1]
[null,"CFR",5326129,"Arad - Craiova","< >","Sânandrei",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"3,4,5",1]
[null,"CFR",5326130,"Arad - Craiova","< >","Sânandrei",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"3,4,5",1]
[null,"CFR",5326131,"Arad - Craiova","< >","Sânandrei","Baile Calacea",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"5,6,7",1]
[null,"CFR",5525798,"Arad - Craiova","< >","Sânandrei",null,2025,2025,18,19,"2025-05-01","02:00:00","2025-05-08",2.0826388888888898,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"1,2,3",1]
[null,"CFR",5525799,"Arad - Craiova","< >","Sânandrei ","Hodoni",2025,2025,18,19,"2025-05-01","03:00:00","2025-05-08",2.1243055555555599,"8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"1,2,7",1]
[null,"CFR",5326024,"Arad - Craiova","< >","Tapia ","Lugoj",2025,2025,30,31,"2025-07-25","00:00:00","2025-07-29","23:59:00","5d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-09",null,null,7,1]
[null,"CFR",5326047,"Arad - Craiova","< >","Timișoara Est","Timișoara Nord",2025,2025,22,23,"2025-05-27","00:00:00","2025-06-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-09",null,null,"4,5,6",1]
[null,"CFR",5326048,"Arad - Craiova","< >","Timișoara Est","Remetea Mică",2025,2026,23,36,"2025-06-02","00:00:00","2026-09-02","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13",null,null,"6,7",1]
[null,"CFR",5326120,"Arad - Craiova","< >","Timișoara Est","Timișoara Est",2024,2025,23,23,"2024-06-03","00:00:00","2025-06-02","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"1,7",1]
[null,"CFR",5326124,"Arad - Craiova","< >","Timișoara Est","Timișoara Est",2024,2026,35,45,"2024-09-01","00:00:00","2026-11-02","23:59:00","793d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,1,1]
[null,"CFR",5525789,"Arad - Craiova","< >","Timișoara Est","Timișoara Nord",2025,2025,27,28,"2025-07-01","00:00:00","2025-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"1,2,3,4",1]
[null,"CFR",5525790,"Arad - Craiova","< >","Timișoara Est ","Timișoara Nord",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-12",null,null,"1,5,6,7",1]
[null,"CFR",5326055,"Arad - Craiova","< >","Timișoara Est  ","Timișoara Est  ",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5326043,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2025,2025,5,6,"2025-01-27","00:00:00","2025-02-03","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,2,3,4",1]
[null,"CFR",5326044,"Arad - Craiova","< >","Timișoara Nord","Săcălaz",2024,2025,35,23,"2024-09-01","00:00:00","2025-06-02","23:59:00","275d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,7",1]
[null,"CFR",5326051,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.B",2025,2025,6,23,"2025-02-03","00:00:00","2025-06-02","23:59:00","120d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,2,3,4",1]
[null,"CFR",5326052,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.B",2025,2025,6,23,"2025-02-03","00:00:00","2025-06-06","23:59:00","124d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5326056,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"5,6,7",1]
[null,"CFR",5326057,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2027,18,2,"2026-05-01","00:00:00","2027-01-12","23:59:00","257d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-30",null,null,"1,2,3",1]
[null,"CFR",5326058,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,5,6,7",1]
[null,"CFR",5326061,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,44,45,"2026-10-27","00:00:00","2026-11-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12",null,null,"1,2,3,4",1]
[null,"CFR",5326125,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2025,2026,23,23,"2025-06-02","00:00:00","2026-06-01","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326126,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2027,23,2,"2026-06-01","00:00:00","2027-01-12","23:59:00","226d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-16",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525795,"Arad - Craiova","< >","Timișoara Nord",null,2025,2025,36,37,"2025-09-01","00:00:00","2025-09-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"6,7",1]
[null,"CFR",5326059,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14",null,null,"6,7",1]
[null,"CFR",5326060,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14",null,null,"6,7",1]
[null,"CFR",5326121,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2024,2025,23,6,"2024-06-03","00:00:00","2025-02-03","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"1,2,3,7",1]
[null,"CFR",5326122,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2025,2026,6,23,"2025-02-03","00:00:00","2026-06-01","23:59:00","484d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"3,4,5,6",1]
[null,"CFR",5326127,"Arad - Craiova","< >","Timișoara Nord ",null,2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,7",1]
[null,"CFR",5326033,"Arad - Craiova","< >","Topolovat",null,2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-16",null,null,"1,2,5,6,7",1]
[null,"CFR",5326034,"Arad - Craiova","< >","Topolovat","Recas",2025,2025,37,39,"2025-09-13","00:00:00","2025-09-26","23:59:00","14d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-14",null,null,"2,3,4,5",1]
[null,"CFR",5326105,"Arad - Craiova","< >","Topolovat",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5326106,"Arad - Craiova","< >","Topolovat","Recas",2025,2025,39,48,"2025-09-26","00:00:00","2025-11-26","23:59:00","62d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"3,4,5,6,7",1]
[null,"CFR",5326107,"Arad - Craiova","< >","Topolovat","Recas",2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"3,4",1]
[null,"CFR",5326074,"Arad - Craiova","< >","Valea Viilor","Arad",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,"2,3,4,5",1]
[null,"CFR",5326075,"Arad - Craiova","< >","Valea Viilor","Arad",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-14",null,null,"2,3,4,5",1]
[null,"CFR",5326144,"Arad - Craiova","< >","Valea Viilor",null,2024,2026,32,21,"2024-08-09","00:00:00","2026-05-23","23:59:00","653d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"2,3,4,5",1]
[null,"CFR",5326145,"Arad - Craiova","< >","Valea Viilor","Aradul Nou",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525805,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2025,2025,31,32,"2025-08-01","00:00:00","2025-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5525806,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326071,"Arad - Craiova","< >","Vinga","Sag",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326138,"Arad - Craiova","< >","Vinga",null,2024,2026,26,4,"2024-06-25","00:00:00","2026-01-23","23:59:00","578d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326139,"Arad - Craiova","< >","Vinga",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326140,"Arad - Craiova","< >","Vinga","Sag",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326083,"Arad - Craiova","< >","Zăgujeni","Zăgujeni",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326084,"Arad - Craiova","< >","Zăgujeni","Zăgujeni",2025,2025,31,32,"2025-07-29","00:00:00","2025-08-04","23:59:00","7d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326085,"Arad - Craiova","< >","Zăgujeni","Căvăran",2025,2025,12,31,"2025-03-19","00:00:00","2025-08-03","23:59:00","138d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3",1]
[null,"CFR",5326086,"Arad - Craiova","< >","Zăgujeni","Căvăran",2025,2025,8,9,"2025-02-20","00:00:00","2025-02-24","23:59:00","5d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3",1]
[null,"CFR",5326087,"Arad - Craiova","< >","Zăgujeni","Căvăran",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5326088,"Arad - Craiova","< >","Zăgujeni","Căvăran",2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525633,"Arad - Simeria","< >"," Bătuța ","Bârzava",2024,2025,30,7,"2024-07-27","00:00:00","2025-02-11","23:59:00","200d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525632,"Arad - Simeria","< >","Barzava","Barzava Noua",2019,2025,25,7,"2019-06-19","00:00:00","2025-02-11","23:59:00","2065d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"1,2,3,4,5",1]
[null,"CFR",5325841,"Arad - Simeria","< >","Bârzava",null,2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"6,7",1]
[null,"CFR",5325842,"Arad - Simeria","< >","Bârzava","Bârzava Nouă",2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"6,7",1]
[null,"CFR",5325836,"Arad - Simeria","< >","Barzava Nouă",null,2019,2025,25,32,"2019-06-19","00:00:00","2025-08-08","23:59:00","2243d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"6,7",1]
[null,"CFR",5325840,"Arad - Simeria","< >","Batuta","Bârzava",2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"6,7",1]
[null,"CFR",5325839,"Arad - Simeria","< >","Bătuța",null,2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325851,"Arad - Simeria","< >","Branisca","Mintia",2021,2025,19,20,"2021-05-10","00:00:00","2025-05-15","23:59:00","1467d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"6,7",1]
[null,"CFR",5325852,"Arad - Simeria","< >","Branisca","Ilia",2021,2025,47,26,"2021-11-28","00:00:00","2025-06-29","23:59:00","1310d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13",null,null,"6,7",1]
[null,"CFR",5325844,"Arad - Simeria","< >","Campuri Surduc","Zam",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-12","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325848,"Arad - Simeria","< >","Deva","Mintia",2019,2025,25,26,"2019-06-22","00:00:00","2025-06-29","23:59:00","2200d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325850,"Arad - Simeria","< >","Deva",null,2020,2025,18,26,"2020-04-29","00:00:00","2025-06-29","23:59:00","1888d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"5,6",1]
[null,"CFR",5325859,"Arad - Simeria","< >","Deva",null,2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"5,6",1]
[null,"CFR",5325863,"Arad - Simeria","< >","Deva","Mintia",2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14",null,null,"5,6",1]
[null,"CFR",5325843,"Arad - Simeria","< >","Ilia","Campuri Surduc",2022,2025,30,7,"2022-07-29","00:00:00","2025-02-15","23:59:00","933d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-02-22",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325853,"Arad - Simeria","< >","Ilia",null,2021,2025,47,26,"2021-11-28","00:00:00","2025-06-29","23:59:00","1310d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-02-22",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325856,"Arad - Simeria","< >","Ilia","Gurasada",2024,2025,49,26,"2024-12-04","00:00:00","2025-06-29","23:59:00","208d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-10-18",null,null,"6,7",1]
[null,"CFR",5325861,"Arad - Simeria","< >","Ilia",null,2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-02-22",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325865,"Arad - Simeria","< >","Ilia","Gurasada",2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-02-22",null,null,"6,7",1]
[null,"CFR",5325832,"Arad - Simeria","< >","Ilteu","Savarsin",2023,2025,20,36,"2023-05-15","00:00:00","2025-09-04","23:59:00","844d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"1,2,3,4,7",1]
[null,"CFR",5325831,"Arad - Simeria","< >","Mintia","Branisca",2025,2025,20,21,"2025-05-15","00:00:00","2025-05-25","23:59:00","11d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,"1,2,3,4,7",1]
[null,"CFR",5325855,"Arad - Simeria","< >","Mintia",null,2023,2025,49,26,"2023-12-06","00:00:00","2025-06-29","23:59:00","572d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"6,7",1]
[null,"CFR",5325857,"Arad - Simeria","< >","Mintia","Branisca",2024,2025,46,26,"2024-11-12","00:00:00","2025-06-29","23:59:00","230d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325860,"Arad - Simeria","< >","Mintia",null,2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"5,6",1]
[null,"CFR",5325864,"Arad - Simeria","< >","Mintia","Ilia",2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"5,6",1]
[null,"CFR",5325833,"Arad - Simeria","< >","Savarsin","Varadia",2021,2025,24,30,"2021-06-19","00:00:00","2025-07-25","23:59:00","1498d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3",1]
[null,"CFR",5325849,"Arad - Simeria","< >","Simeria","Deva",2020,2025,17,26,"2020-04-23","00:00:00","2025-06-29","23:59:00","1894d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-08-03",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325854,"Arad - Simeria","< >","Simeria",null,2022,2025,20,26,"2022-05-21","00:00:00","2025-06-29","23:59:00","1136d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325858,"Arad - Simeria","< >","Simeria",null,2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,1,1]
[null,"CFR",5325862,"Arad - Simeria","< >","Simeria","Deva",2025,2025,26,31,"2025-06-29","00:00:00","2025-07-29","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,1,1]
[null,"CFR",5525631,"Arad - Simeria","< >","Varadia","Batuta",2019,2025,9,7,"2019-02-27","00:00:00","2025-02-11","23:59:00","2177d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325838,"Arad - Simeria","< >","Varadia","Batuta",2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525634,"Arad - Simeria","< >","Vărădia","Bârzava Nouă",2024,2025,32,7,"2024-08-11","00:00:00","2025-02-11","23:59:00","185d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-03-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325837,"Arad - Simeria","< >","Vărădia","Bârzava Nouă",2025,2025,5,32,"2025-01-31","00:00:00","2025-08-08","23:59:00","190d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325845,"Arad - Simeria","< >","Zam",null,2024,2025,11,22,"2024-03-15","00:00:00","2025-05-31","23:59:00","443d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325846,"Arad - Simeria","< >","Zam",null,2024,2025,22,35,"2024-06-01","00:00:00","2025-08-31","23:59:00","457d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,3,1]
[null,"CFR",5325847,"Arad - Simeria","< >","Zam","Ilteu",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-12","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,3,1]
[null,"CFR",5525758,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09",null,null,"1,2",1]
[null,"CFR",5525759,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09",null,null,"2,3,4,5,6",1]
[null,"CFR",5525760,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09",null,null,"3,4",1]
[null,"CFR",5525726,"Biharkeresztes - Cluj Napoca","< >","Aghires","Poieni",2024,2025,1,52,"2024-01-01","00:00:00","2025-12-31","23:59:00","731d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-08-09",null,null,"4,5",1]
[null,"CFR",5325964,"Biharkeresztes - Cluj Napoca","< >","Aghireș",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,5,1]
[null,"CFR",5525728,"Biharkeresztes - Cluj Napoca","< >","Alesd","Oradea",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-15",null,null,"6,7",1]
[null,"CFR",5525735,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"6,7",1]
[null,"CFR",5325984,"Biharkeresztes - Cluj Napoca","< >","Alesd",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325985,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325986,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-16",null,null,"1,7",1]
[null,"CFR",5325987,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-16",null,null,"1,7",1]
[null,"CFR",5525742,"Biharkeresztes - Cluj Napoca","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-16",null,null,"1,2",1]
[null,"CFR",5325960,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16",null,null,"1,2",1]
[null,"CFR",5325961,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj","Gârbău",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16",null,null,"2,3",1]
[null,"CFR",5525768,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-16",null,null,"3,4",1]
[null,"CFR",5325966,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16",null,null,"3,4",1]
[null,"CFR",5525752,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-16",null,null,"2,3",1]
[null,"CFR",5325976,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16",null,null,"6,7",1]
[null,"CFR",5325975,"Biharkeresztes - Cluj Napoca","< >","Bratca ",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16",null,null,"6,7",1]
[null,"CFR",5325973,"Biharkeresztes - Cluj Napoca","< >","Bulz",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,"1,6,7",1]
[null,"CFR",5325974,"Biharkeresztes - Cluj Napoca","< >","Bulz","Bratca",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,"1,6,7",1]
[null,"CFR",5525751,"Biharkeresztes - Cluj Napoca","< >","Bulz ","Bratca",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-19",null,null,6,1]
[null,"CFR",5525749,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,6,1]
[null,"CFR",5325979,"Biharkeresztes - Cluj Napoca","< >","Ciucea",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,6,1]
[null,"CFR",5325980,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19",null,null,6,1]
[null,"CFR",5525755,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525756,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325959,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17",null,null,"5,6",1]
[null,"CFR",5525757,"Biharkeresztes - Cluj Napoca","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"5,6",1]
[null,"CFR",5325983,"Biharkeresztes - Cluj Napoca","< >","Cluj Napoca Est","Cluj",2024,2026,27,9,"2024-07-01","00:00:00","2026-02-28","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"5,6",1]
[null,"CFR",5525732,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-17",null,null,"5,6",1]
[null,"CFR",5525733,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontiera",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,"5,6",1]
[null,"CFR",5525739,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,"6,7",1]
[null,"CFR",5525741,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Biharia",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,"6,7",1]
[null,"CFR",5525747,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,"6,7",1]
[null,"CFR",5325982,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Border",2025,2025,5,22,"2025-02-01","00:00:00","2025-06-01","23:59:00","121d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-02",null,null,"3,4,5",1]
[null,"CFR",5326012,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326013,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,19,41,"2025-05-11","00:00:00","2025-10-10","23:59:00","153d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326014,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,19,41,"2025-05-11","00:00:00","2025-10-10","23:59:00","153d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326015,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Episcopia Bihor",2025,2025,18,22,"2025-05-01","00:00:00","2025-06-01","23:59:00","32d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326016,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2025,27,40,"2025-07-01","00:00:00","2025-10-01","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326018,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Border",2025,2025,5,22,"2025-02-01","00:00:00","2025-06-01","23:59:00","121d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326017,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor ","Border",2025,2025,5,22,"2025-02-01","00:00:00","2025-06-01","23:59:00","121d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525764,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525765,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525766,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5325962,"Biharkeresztes - Cluj Napoca","< >","Gârbău",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5325963,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525769,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5325967,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525761,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525762,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525763,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525731,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525734,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5525738,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea Vest",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326007,"Biharkeresztes - Cluj Napoca","< >","Oradea",null,2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326008,"Biharkeresztes - Cluj Napoca","< >","Oradea",null,2025,2025,18,41,"2025-05-01","00:00:00","2025-10-10","23:59:00","163d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20",null,null,"2,3",1]
[null,"CFR",5326009,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea Vest",2026,2026,9,27,"2026-03-01","00:00:00","2026-07-01","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326010,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea",2025,2025,18,41,"2025-05-01","00:00:00","2025-10-10","23:59:00","163d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326011,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea",2025,2027,50,19,"2025-12-11","00:00:00","2027-05-10","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5525746,"Biharkeresztes - Cluj Napoca","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5525745,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326002,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2024,2025,24,19,"2024-06-11","00:00:00","2025-05-10","23:59:00","334d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326003,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2025,2025,19,41,"2025-05-11","00:00:00","2025-10-10","23:59:00","153d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326004,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326005,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326006,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5525729,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2024,2025,5,22,"2024-02-01","00:00:00","2025-06-01","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5525730,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5525740,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5325998,"Biharkeresztes - Cluj Napoca","< >","Osorhei",null,2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5325999,"Biharkeresztes - Cluj Napoca","< >","Osorhei",null,2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"3,4",1]
[null,"CFR",5326000,"Biharkeresztes - Cluj Napoca","< >","Osorhei","Oradea Est",2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5326001,"Biharkeresztes - Cluj Napoca","< >","Osorhei","Oradea Est",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525737,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Tileagd ",2025,2025,21,22,"2025-05-25","00:00:00","2025-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525744,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5325972,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului","Bulz",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5325981,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525750,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului ","Bulz",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525727,"Biharkeresztes - Cluj Napoca","< >","Poieni","Alesd",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525748,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5525767,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5325965,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21",null,null,"2,3",1]
[null,"CFR",5325978,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525770,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325968,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525753,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325969,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2027,16,23,"2024-04-15","00:00:00","2027-06-10","23:59:00","1152d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325977,"Biharkeresztes - Cluj Napoca","< >","Suncuius",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525736,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325988,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2024,2025,24,41,"2024-06-11","00:00:00","2025-10-10","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325989,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525743,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325990,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2024,2025,24,19,"2024-06-11","00:00:00","2025-05-10","23:59:00","334d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325991,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2025,2025,19,41,"2025-05-11","00:00:00","2025-10-10","23:59:00","153d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27",null,null,"4,5",1]
[null,"CFR",5325992,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27",null,null,"4,5",1]
[null,"CFR",5325993,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2025,37,41,"2025-09-11","00:00:00","2025-10-10","23:59:00","30d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27",null,null,"1,2,3",1]
[null,"CFR",5325994,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2024,2025,19,24,"2024-05-11","00:00:00","2025-06-10","23:59:00","396d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27",null,null,"1,2,3",1]
[null,"CFR",5325995,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2027,42,22,"2025-10-19","00:00:00","2027-06-02","23:59:00","592d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27",null,null,"4,5",1]
[null,"CFR",5325996,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2024,2025,19,24,"2024-05-11","00:00:00","2025-06-10","23:59:00","396d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-02",null,null,7,1]
[null,"CFR",5325997,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2025,41,42,"2025-10-11","00:00:00","2025-10-18","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-28",null,null,"2,3,4,5",1]
[null,"CFR",5525754,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-06-13",null,null,"1,6,7",1]
[null,"CFR",5325970,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13",null,null,"1,6,7",1]
[null,"CFR",5325971,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,41,9,"2024-10-10","00:00:00","2026-02-26","23:59:00","505d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13",null,null,"1,6,7",1]
[null,"CFR",5326154,"Bucuresti-Constanta","< >","Ciulnita",null,2024,2025,48,13,"2024-12-01","00:00:00","2025-03-30","23:59:00","120d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-28",null,null,"2,3,4,5",1]
[null,"CFR",5326150,"Bucuresti-Constanta","< >","Fetesti","Baraganu",2025,2025,18,20,"2025-05-01","00:00:00","2025-05-15","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5326151,"Bucuresti-Constanta","< >","Fetesti","Baraganu",2025,2025,20,24,"2025-05-16","00:00:00","2025-06-15","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,1,1]
[null,"CFR",5326152,"Bucuresti-Constanta","< >","Fetesti","Movila",2025,2025,20,24,"2025-05-16","00:00:00","2025-06-15","23:59:00","31d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,1,1]
[null,"CFR",5326153,"Bucuresti-Constanta","< >","Fetesti","Movila",2025,2025,25,25,"2025-06-16","00:00:00","2025-06-22","23:59:00","7d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5326155,"Bucuresti-Constanta","< >","Fetesti",null,2024,2025,50,18,"2024-12-14","00:00:00","2025-04-30","23:59:00","138d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5325949,"Simeria -  Brasov","< >","Albești",null,2023,2025,41,17,"2023-10-11","00:00:00","2025-04-23","23:59:00","561d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5325950,"Simeria -  Brasov","< >","Albești",null,2025,2025,17,35,"2025-04-24","00:00:00","2025-08-29","23:59:00","128d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5325951,"Simeria -  Brasov","< >","Albești","Sighișoara",2023,2025,41,6,"2023-10-11","00:00:00","2025-02-03","23:59:00","482d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5325952,"Simeria -  Brasov","< >","Albești","Sighișoara",2025,2025,6,17,"2025-02-03","00:00:00","2025-04-23","23:59:00","80d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,2,1]
[null,"CFR",5325953,"Simeria -  Brasov","< >","Albești","Sighișoara",2025,2026,17,10,"2025-04-24","00:00:00","2026-03-04","23:59:00","315d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,"1,2,5,6,7",1]
[null,"CFR",5525670,"Simeria -  Brasov","< >","Albești","Sighișoara",2023,2025,24,20,"16.06.2023","00:00:00","12.05.2025","23:59:00","697d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,"1,2,5,6,7",1]
[null,"CFR",5525723,"Simeria -  Brasov","< >","Albești","Sighișoara",2024,2025,49,51,"08.12.2024","00:00:00","20.12.2025","23:59:00","378d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-06-14",null,null,"1,2,5,6,7",1]
[null,"CFR",5325916,"Simeria -  Brasov","< >","Apata","Augustin",2025,2025,3,45,"2025-01-13","00:00:00","2025-11-07","23:59:00","299d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"1,2,3,6,7",1]
[null,"CFR",5325917,"Simeria -  Brasov","< >","Apata","Augustin",2025,2026,46,32,"2025-11-10","00:00:00","2026-08-03","23:59:00","267d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14",null,null,"1,2,3,6,7",1]
[null,"CFR",5525671,"Simeria -  Brasov","< >","Apata","Augustin",2021,2025,15,33,"2021-04-15","00:00:00","2025-08-11","23:59:00","1580d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,"1,2,3,6,7",1]
[null,"CFR",5325910,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,"1,2,3,6,7",1]
[null,"CFR",5325911,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03",null,null,"1,2,3,6,7",1]
[null,"CFR",5325912,"Simeria -  Brasov","< >","Apața",null,2026,2026,17,33,"2026-04-20","00:00:00","2026-08-14","23:59:00","117d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04",null,null,6,1]
[null,"CFR",5325913,"Simeria -  Brasov","< >","Apața",null,2026,2026,33,44,"2026-08-15","00:00:00","2026-10-30","23:59:00","77d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04",null,null,"1,2,7",1]
[null,"CFR",5325914,"Simeria -  Brasov","< >","Apața",null,2026,2027,44,28,"2026-10-31","00:00:00","2027-07-15","23:59:00","258d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325915,"Simeria -  Brasov","< >","Apața",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525665,"Simeria -  Brasov","< >","Archita","Vînători ",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525711,"Simeria -  Brasov","< >","Archita","Mureni ",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525712,"Simeria -  Brasov","< >","Archita","Vânători ",2025,2026,51,7,"2025-12-21","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325938,"Simeria -  Brasov","< >","Archita ","Vînători ",2027,2028,43,8,"2027-10-26","00:00:00","2028-02-26","23:59:00","124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525664,"Simeria -  Brasov","< >","Archita ","Vînători ",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325918,"Simeria -  Brasov","< >","Augustin","Racos",2025,2025,11,34,"2025-03-15","00:00:00","2025-08-22","23:59:00","161d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-26",null,null,"1,2,3,4,5,6",1]
[null,"CFR",5325919,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06",null,null,"1,2,3,4",1]
[null,"CFR",5325921,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06",null,null,"1,2,3,4",1]
[null,"CFR",5525672,"Simeria -  Brasov","< >","Augustin","Racos",2023,2025,28,40,"2023-07-14","00:00:00","2025-09-30","23:59:00","810d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06",null,null,2,1]
[null,"CFR",5525693,"Simeria -  Brasov","< >","Augustin","Racos",2023,2025,28,30,"2023-07-14","00:00:00","2025-07-23","23:59:00","741d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-09",null,null,"1,2",1]
[null,"CFR",5525694,"Simeria -  Brasov","< >","Augustin","Racos",2024,2025,32,21,"2024-08-07","00:00:00","2025-05-23","23:59:00","290d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-09",null,null,"5,6",1]
[null,"CFR",5325936,"Simeria -  Brasov","< >","Beia","Mureni",2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"1,2",1]
[null,"CFR",5325937,"Simeria -  Brasov","< >","Beia","Mureni",2026,2027,10,43,"2026-03-05","00:00:00","2027-10-25","23:59:00","600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"2,3",1]
[null,"CFR",5525659,"Simeria -  Brasov","< >","Beia","Mureni",2023,2026,44,40,"30.10.2023","00:00:00","30.09.2026","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"3,4",1]
[null,"CFR",5525661,"Simeria -  Brasov","< >","Beia","Mureni",2025,2025,39,39,"22.09.2025","00:00:00","25.09.2025","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"6,7",1]
[null,"CFR",5525704,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-09",null,null,"1,2",1]
[null,"CFR",5525708,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-09",null,null,"2,3",1]
[null,"CFR",5525709,"Simeria -  Brasov","< >","Beia","Archita",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325890,"Simeria -  Brasov","< >","Bod",null,2024,2025,11,12,"2024-03-15","00:00:00","2025-03-20","23:59:00","371d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325891,"Simeria -  Brasov","< >","Bod",null,2025,2025,12,43,"2025-03-21","00:00:00","2025-10-23","23:59:00","217d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325892,"Simeria -  Brasov","< >","Bod",null,2025,2027,30,28,"2025-07-23","00:00:00","2027-07-15","23:59:00","723d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325893,"Simeria -  Brasov","< >","Bod",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325894,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2025,46,7,"2024-11-15","00:00:00","2025-02-15","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325895,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2025,7,27,"2025-02-16","00:00:00","2025-07-03","23:59:00","138d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325896,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2026,27,19,"2025-07-04","00:00:00","2026-05-06","23:59:00","307d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325897,"Simeria -  Brasov","< >","Bod","Feldioara",2026,2027,19,48,"2026-05-06","00:00:00","2027-12-05","23:59:00","579d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325898,"Simeria -  Brasov","< >","Bod","Feldioara",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5525638,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","567 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5525652,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,14,48,"03.04.2023","00:00:00","27.11.2025","23:59:00","970d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5525680,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,33,10,"18.08.2023","00:00:00","06.03.2025","23:59:00","567d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5525682,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,33,10,"18.08.2023","00:00:00","06.03.2025","23:59:00","567d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5525683,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325869,"Simeria -  Brasov","< >","Brașov",null,2024,2025,27,12,"2024-07-01","00:00:00","2025-03-20","23:59:00","263d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325870,"Simeria -  Brasov","< >","Brașov",null,2025,2025,12,22,"2025-03-21","00:00:00","2025-05-30","23:59:00","71d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325871,"Simeria -  Brasov","< >","Brașov",null,2025,2025,22,33,"2025-05-31","00:00:00","2025-08-15","23:59:00","77d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325872,"Simeria -  Brasov","< >","Brașov",null,2025,2025,33,34,"2025-08-16","00:00:00","2025-08-22","23:59:00","7d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325873,"Simeria -  Brasov","< >","Brașov",null,2025,2025,34,46,"2025-08-23","00:00:00","2025-11-15","23:59:00","85d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325874,"Simeria -  Brasov","< >","Brașov",null,2025,2027,46,8,"2025-11-16","00:00:00","2027-02-28","23:59:00","470d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325875,"Simeria -  Brasov","< >","Brașov",null,2027,2027,9,28,"2027-03-01","00:00:00","2027-07-15","23:59:00","137d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"3,4",1]
[null,"CFR",5325876,"Simeria -  Brasov","< >","Brașov",null,2027,2027,28,48,"2027-07-16","00:00:00","2027-12-05","23:59:00","143d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325877,"Simeria -  Brasov","< >","Brașov","Stupini",2024,2025,48,22,"2024-11-26","00:00:00","2025-05-30","23:59:00","186d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325878,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2025,22,44,"2025-05-31","00:00:00","2025-10-27","23:59:00","150d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3",1]
[null,"CFR",5325879,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5325880,"Simeria -  Brasov","< >","Brașov","Stupini",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525650,"Simeria -  Brasov","< >","Brașov","Stupini",2021,2025,47,39,"25.11.2021","00:00:00","27.09.2025","23:59:00","1403d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525677,"Simeria -  Brasov","< >","Brașov","Stupini",2023,2026,22,12,"01.06.2023","00:00:00","16.03.2026","23:59:00","1020d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525678,"Simeria -  Brasov","< >","Brașov","Stupini",2024,2025,35,10,"28.08.2024","00:00:00","06.03.2025","23:59:00","191d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325928,"Simeria -  Brasov","< >","Cata","Rupea",2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325929,"Simeria -  Brasov","< >","Cata","Rupea",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325930,"Simeria -  Brasov","< >","Cata",null,2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325931,"Simeria -  Brasov","< >","Cata",null,2026,2026,3,42,"2026-01-15","00:00:00","2026-10-15","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325932,"Simeria -  Brasov","< >","Cata",null,2026,2027,42,7,"2026-10-15","00:00:00","2027-02-16","23:59:00","125d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325933,"Simeria -  Brasov","< >","Cata","Beia",2025,2026,3,3,"2025-01-15","00:00:00","2026-01-14","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325934,"Simeria -  Brasov","< >","Cata","Beia",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5325935,"Simeria -  Brasov","< >","Cata","Beia",2027,2027,7,43,"2027-02-17","00:00:00","2027-10-25","23:59:00","251d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525657,"Simeria -  Brasov","< >","Cata","Rupea",2023,2026,5,50,"02.02.2023","00:00:00","12.12.2026","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525658,"Simeria -  Brasov","< >","Cața","Beia",2023,2026,5,9,"02.02.2023","00:00:00","01.03.2026","23:59:00","1124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-09-24",null,null,"4,5",1]
[null,"CFR",5525662,"Simeria -  Brasov","< >","Cața","Archita",2024,2025,29,12,"17.07.2024","00:00:00","21.03.2025","23:59:00","248d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525663,"Simeria -  Brasov","< >","Cața","Archita",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525697,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,25,12,"18.06.2024","00:00:00","21.03.2025","23:59:00","277d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525698,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,3,25,"16.01.2024","00:00:00","16.06.2025","23:59:00","518d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525699,"Simeria -  Brasov","< >","Cața","Beia",2025,2025,25,51,"17.06.2025","00:00:00","20.12.2025","23:59:00","187d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525701,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,25,12,"18.06.2024","00:00:00","21.03.2025","23:59:00","277d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5525702,"Simeria -  Brasov","< >","Cața","Beia",2024,2025,3,25,"16.01.2024","00:00:00","16.06.2025","23:59:00","518d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"5,6",1]
[null,"CFR",5525703,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525710,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325866,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,6,6,"2026-02-02","00:00:00","2026-02-08","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325867,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,30,33,"2026-07-24","00:00:00","2026-08-14","23:59:00","22d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325899,"Simeria -  Brasov","< >","Feldioara",null,2020,2025,44,21,"2020-10-28","00:00:00","2025-05-19","23:59:00","1665d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325900,"Simeria -  Brasov","< >","Feldioara",null,2025,2025,21,27,"2025-05-19","00:00:00","2025-07-03","23:59:00","46d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325901,"Simeria -  Brasov","< >","Feldioara",null,2025,2026,27,17,"2025-07-04","00:00:00","2026-04-23","23:59:00","294d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325902,"Simeria -  Brasov","< >","Feldioara",null,2026,2027,17,28,"2026-04-23","00:00:00","2027-07-15","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325903,"Simeria -  Brasov","< >","Feldioara",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325904,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,27,27,"2023-07-07","00:00:00","2025-07-03","23:59:00","728d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325905,"Simeria -  Brasov","< >","Feldioara","Apața",2025,2026,27,6,"2025-07-04","00:00:00","2026-02-02","23:59:00","214d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325906,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,7,30,"2026-02-09","00:00:00","2026-07-23","23:59:00","165d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325907,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,33,49,"2026-08-15","00:00:00","2026-11-30","23:59:00","108d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325908,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2027,49,48,"2026-11-30","00:00:00","2027-12-05","23:59:00","371d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325909,"Simeria -  Brasov","< >","Feldioara","Apața",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525640,"Simeria -  Brasov","< >","Feldioara",null,2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","569 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-06-12",null,null,"1,2,3,7",1]
[null,"CFR",5525642,"Simeria -  Brasov","< >","Feldioara","Apata",2025,2025,1,10,"2025-01-01","00:00:00","2025-03-06","23:59:00","458 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,6,7",1]
[null,"CFR",5525653,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,7,48,"15.02.2023","00:00:00","27.11.2025","23:59:00","1017d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,6,7",1]
[null,"CFR",5525656,"Simeria -  Brasov","< >","Feldioara","Apața",2025,2025,4,6,"21.01.2025","00:00:00","05.02.2025","23:59:00","16d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525684,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,49,10,"05.12.2023","00:00:00","06.03.2025","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525689,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525690,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,49,10,"05.12.2023","00:00:00","06.03.2025","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2024-09-24",null,null,"4,5",1]
[null,"CFR",5525691,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5325939,"Simeria -  Brasov","< >","Mureni",null,2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5325940,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2025,45,35,"2022-11-08","00:00:00","2025-08-29","23:59:00","1026d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5325941,"Simeria -  Brasov","< >","Mureni","Vînători",2025,2027,35,43,"2025-08-30","00:00:00","2027-10-25","23:59:00","787d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-23",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525644,"Simeria -  Brasov","< >","Mureni","Vanatori",2025,2025,1,12,"2025-01-01","00:00:00","2025-03-21","23:59:00","523 d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-12",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525666,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2026,45,40,"09.11.2022","00:00:00","30.09.2026","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525713,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525714,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525715,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5525716,"Simeria -  Brasov","< >","Mureni","Vânători ",2023,2025,42,12,"16.10.2023","00:00:00","21.03.2025","23:59:00","523d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-23",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525717,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5325920,"Simeria -  Brasov","< >","Racos",null,2023,2025,29,34,"2023-07-17","00:00:00","2025-08-22","23:59:00","768d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5325922,"Simeria -  Brasov","< >","Racos","Rupea",2024,2025,17,35,"2024-04-25","00:00:00","2025-08-25","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525673,"Simeria -  Brasov","< >","Racos","Rupea",2022,2025,10,11,"2022-03-08","00:00:00","2025-03-12","23:59:00","1101d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525695,"Simeria -  Brasov","< >","Racos","Rupea",2022,2025,10,30,"2022-03-08","00:00:00","2025-07-23","23:59:00","1234d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,2,3,7",1]
[null,"CFR",5525675,"Simeria -  Brasov","< >","Racos-Rupea","Racos-Rupea",2024,2025,41,43,"2024-10-10","00:00:00","2025-10-25","23:59:00","381d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,7",1]
[null,"CFR",5325923,"Simeria -  Brasov","< >","Rupea","Racos",2024,2025,17,14,"2024-04-25","00:00:00","2025-04-01","23:59:00","342d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5,6,7",1]
[null,"CFR",5325924,"Simeria -  Brasov","< >","Rupea","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,5,6,7",1]
[null,"CFR",5325925,"Simeria -  Brasov","< >","Rupea","Cata",2024,2025,6,30,"2024-02-08","00:00:00","2025-07-24","23:59:00","533d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,5,6,7",1]
[null,"CFR",5325926,"Simeria -  Brasov","< >","Rupea","Cata",2025,2026,30,31,"2025-07-25","00:00:00","2026-07-27","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,5,6,7",1]
[null,"CFR",5325927,"Simeria -  Brasov","< >","Rupea","Cata",2026,2026,31,38,"2026-07-28","00:00:00","2026-09-15","23:59:00","50d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4,5,6",1]
[null,"CFR",5525696,"Simeria -  Brasov","< >","Rupea","Cața",2022,2025,22,34,"2022-06-01","00:00:00","2025-08-21","23:59:00","1178d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4,5,6",1]
[null,"CFR",5325954,"Simeria -  Brasov","< >","Sighișoara",null,2024,2027,34,50,"2024-08-21","00:00:00","2027-12-15","23:59:00","1212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5325955,"Simeria -  Brasov","< >","Sighișoara",null,2023,2025,41,17,"2023-10-11","00:00:00","2025-04-23","23:59:00","561d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-03-08",null,null,"1,2,3,4,5",1]
[null,"CFR",5325956,"Simeria -  Brasov","< >","Sighișoara",null,2023,2027,41,43,"2023-10-11","00:00:00","2027-10-25","23:59:00","1476d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-02",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325957,"Simeria -  Brasov","< >","Sighișoara",null,2023,2028,41,8,"2023-10-11","00:00:00","2028-02-26","23:59:00","1600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,7",1]
[null,"CFR",5325958,"Simeria -  Brasov","< >","Sighișoara","Danes",2023,2025,41,17,"2023-10-11","00:00:00","2025-04-23","23:59:00","561d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325881,"Simeria -  Brasov","< >","Stupini",null,2021,2025,47,6,"2021-11-25","00:00:00","2025-02-04","23:59:00","1168d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325882,"Simeria -  Brasov","< >","Stupini",null,2025,2025,6,22,"2025-02-04","00:00:00","2025-05-30","23:59:00","116d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-03-20",null,null,"1,2,3",1]
[null,"CFR",5325883,"Simeria -  Brasov","< >","Stupini",null,2025,2025,22,44,"2025-05-31","00:00:00","2025-10-27","23:59:00","150d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5325884,"Simeria -  Brasov","< >","Stupini",null,2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"6,7",1]
[null,"CFR",5325885,"Simeria -  Brasov","< >","Stupini",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"1,7",1]
[null,"CFR",5325886,"Simeria -  Brasov","< >","Stupini","Bod",2023,2025,43,6,"2023-10-25","00:00:00","2025-02-03","23:59:00","468d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-13",null,null,"1,2",1]
[null,"CFR",5325887,"Simeria -  Brasov","< >","Stupini","Bod",2025,2025,6,14,"2025-02-03","00:00:00","2025-04-01","23:59:00","58d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-13",null,null,"2,3",1]
[null,"CFR",5325888,"Simeria -  Brasov","< >","Stupini","Bod",2025,2026,14,14,"2025-04-01","00:00:00","2026-04-01","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"6,7",1]
[null,"CFR",5325889,"Simeria -  Brasov","< >","Stupini","Bod",2026,2027,14,48,"2026-04-01","00:00:00","2027-12-05","23:59:00","614d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"6,7",1]
[null,"CFR",5525651,"Simeria -  Brasov","< >","Stupini","Bod",2023,2025,22,48,"01.06.2023","00:00:00","27.11.2025","23:59:00","911d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-13",null,null,"2,3,4",1]
[null,"CFR",5525718,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2024-08-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525720,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-13",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325868,"Simeria -  Brasov","< >","Vînători","Cristur",2025,2025,34,35,"2025-08-19","00:00:00","2025-08-29","23:59:00","11d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-16",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325942,"Simeria -  Brasov","< >","Vînători",null,2022,2025,45,33,"2022-11-08","00:00:00","2025-08-15","23:59:00","1012d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-16",null,null,"1,2,3",1]
[null,"CFR",5325943,"Simeria -  Brasov","< >","Vînători",null,2023,2025,41,33,"2023-10-11","00:00:00","2025-08-15","23:59:00","675d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,1,1]
[null,"CFR",5325944,"Simeria -  Brasov","< >","Vînători",null,2025,2025,33,35,"2025-08-15","00:00:00","2025-08-29","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-26",null,null,"1,2,3,4,5",1]
[null,"CFR",5325945,"Simeria -  Brasov","< >","Vînători",null,2025,2026,35,20,"2025-08-30","00:00:00","2026-05-11","23:59:00","255d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-05-31",null,null,"1,2,3,4",1]
[null,"CFR",5325946,"Simeria -  Brasov","< >","Vînători",null,2026,2028,20,8,"2026-05-11","00:00:00","2028-02-26","23:59:00","657d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,5,1]
[null,"CFR",5325947,"Simeria -  Brasov","< >","Vînători","Albești",2024,2025,28,20,"2024-07-11","00:00:00","2025-05-12","23:59:00","306d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"1,6,7",1]
[null,"CFR",5325948,"Simeria -  Brasov","< >","Vînători","Albești",2025,2026,20,20,"2025-05-13","00:00:00","2026-05-12","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-20",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525667,"Simeria -  Brasov","< >","Vînători","Albești",2023,2026,24,20,"16.06.2023","00:00:00","12.05.2026","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-01",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2E3A2-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,6,6,"2025-02-04","21:00:00","2025-02-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-20",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2E3A3-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2E3A4-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-20",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2E3A5-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-20",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2E3A6-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-23",null,null,"5,6,7",1]
[null,"DB InfraGO AG","31792-005","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,8,8,"2025-02-21","21:00:00","2025-02-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-06-01",null,null,"5,6,7",1]
[null,"DB InfraGO AG","31793-005","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-01-20",null,null,"1,6,7",1]
[null,"DB InfraGO AG","31794-005","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,16,16,"2025-04-18","21:00:00","2025-04-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-06-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","31795-005","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-01-17",null,null,"5,6,7",1]
[null,"DB InfraGO AG","31796-005","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,24,24,"2025-06-13","21:00:00","2025-06-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","319AE-001","Berlin - Dresden","<","Baruth (Mark)","Wünsdorf-Waldstadt",2025,2025,8,8,"2025-02-22","21:00:00","2025-02-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","319AF-001","Berlin - Dresden","<","Baruth (Mark)","Wünsdorf-Waldstadt",2025,2025,12,12,"2025-03-22","21:00:00","2025-03-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","319B0-001","Berlin - Dresden","<","Baruth (Mark)","Wünsdorf-Waldstadt",2025,2025,16,16,"2025-04-19","21:00:00","2025-04-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","319B1-001","Berlin - Dresden","<","Baruth (Mark)","Wünsdorf-Waldstadt",2025,2025,20,20,"2025-05-17","21:00:00","2025-05-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-23",null,null,"6,7",1]
[null,"DB InfraGO AG","319B2-001","Berlin - Dresden","<","Baruth (Mark)","Wünsdorf-Waldstadt",2025,2025,24,24,"2025-06-14","21:00:00","2025-06-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-23",null,null,"6,7",1]
[null,"DB InfraGO AG","3270D-001","Berlin - Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"6,7",1]
[null,"DB InfraGO AG","916D-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-02",null,null,"6,7",1]
[null,"DB InfraGO AG","916D-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A794-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,46,46,"2025-11-15","20:00:00","2025-11-16","04:30:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-01-25",null,null,"5,6",1]
[null,"DB InfraGO AG","1A794-006","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,47,47,"2025-11-17","20:00:00","2025-11-19","04:30:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-01-25",null,null,"5,6",1]
[null,"DB InfraGO AG","1A794-011","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,47,47,"2025-11-18","04:00:00","2025-11-19","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"1,7",1]
[null,"DB InfraGO AG","1A794-016","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,47,47,"2025-11-20","04:00:00","2025-11-21","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1A794-017","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,47,47,"2025-11-20","04:00:00","2025-11-21","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D5D4-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D5D4-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D5D5-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-20",null,null,"4,5,6,7",1]
[null,"DB InfraGO AG","2D5D5-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D5D6-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-26",null,null,"5,6",1]
[null,"DB InfraGO AG","2D5D6-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"1,7",1]
[null,"DB InfraGO AG","2D5D7-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-26",null,null,"1,2",1]
[null,"DB InfraGO AG","2D5D7-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"2,3",1]
[null,"DB InfraGO AG","2F29C-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"2,3",1]
[null,"DB InfraGO AG","2F29D-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"3,4",1]
[null,"DB InfraGO AG","2F29E-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,14,14,"2025-04-03","21:00:00","2025-04-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"3,4",1]
[null,"DB InfraGO AG","2F29F-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-26",null,null,"4,5",1]
[null,"DB InfraGO AG","2F2A0-003","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2025,2025,22,22,"2025-05-29","21:00:00","2025-05-30","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","30080-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","30081-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30082-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-13",null,null,"5,6,7",1]
[null,"DB InfraGO AG","30083-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30084-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","30F82-004","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","30F83-004","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30F84-004","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30F85-004","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30F86-004","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Ostendgestell",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","326A4-004","Berlin - Dresden","< >","Berlin Eichgestell","Grünauer Kreuz Süd",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","326DA-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","326DA-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","372A2-001","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","372A2-011","Berlin - Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FCFA-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","207CA-001","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,28,35,"2026-07-10","21:00:00","2026-08-24","21:00:00","45d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20838-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,48,50,"2026-11-27","21:00:00","2026-12-11","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","2078A-007","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,16,16,"2026-04-17","17:00:00","2026-04-19","04:00:00","1d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","30080-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30081-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30082-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30083-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","30084-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","30F82-007","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","30F83-007","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","30F84-007","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3",1]
[null,"DB InfraGO AG","30F85-007","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3",1]
[null,"DB InfraGO AG","30F86-007","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,2,3",1]
[null,"DB InfraGO AG","30F82-012","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F82-013","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F83-011","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F83-012","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30F84-011","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F84-012","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30F85-011","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30F85-012","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F86-011","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","30F86-012","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,7",1]
[null,"DB InfraGO AG","326A4-001","Berlin - Dresden","< >","Berlin Ostendgestell","Berlin Eichgestell",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1310-(MK27)-01","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,3,4,"22.01.2027","21:00:00","29.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1310-(MK27)-02","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2F29C-007","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","2F29D-007","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2F29E-007","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,14,14,"2025-04-03","21:00:00","2025-04-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2F29F-007","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2F2A0-007","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,22,22,"2025-05-29","21:00:00","2025-05-30","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-30",null,null,"5,6,7",1]
[null,"DB InfraGO AG","30080-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30081-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","30082-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","30083-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","30084-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","326A4-003","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","3CCCF-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","3CCCF-004","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","3CF9E-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","3CF9E-006","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","3CF9E-012","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","3D71C-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2025,2025,28,28,"2025-07-07","21:00:00","2025-07-08","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","2078A-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2026,2026,14,28,"2026-04-01","22:40:00","2026-07-10","21:00:00","99d, 22h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-31",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","2078A-002","Berlin - Dresden","< >","Berlin Stadtforst","Eichgestell Nord",2026,2026,14,28,"2026-04-01","22:40:00","2026-07-10","21:00:00","99d, 22h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-31",null,null,"4,5,6,7",1]
[null,"DB InfraGO AG","30080-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"2,3",1]
[null,"DB InfraGO AG","30081-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"1,2",1]
[null,"DB InfraGO AG","30082-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"3,4",1]
[null,"DB InfraGO AG","30083-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,"4,5",1]
[null,"DB InfraGO AG","30084-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","326A4-005","Berlin - Dresden","< >","Berlin Wendenheide","Berlin-Adlershof Abzw",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4,5,6",1]
[null,"DB InfraGO AG","2D639-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,5,5,"2025-01-31","21:00:00","2025-02-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","2D63A-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","2D63B-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"6,7",1]
[null,"DB InfraGO AG","2D63C-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D63D-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","30080-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30081-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","30082-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","30083-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,6,7",1]
[null,"DB InfraGO AG","30084-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,6,7",1]
[null,"DB InfraGO AG","326A4-007","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","373D3-005","Berlin - Dresden","< >","Berlin-Adlershof Abzw","Berlin Wendenheide",2025,2025,25,25,"2025-06-20","21:00:00","2025-06-21","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2CB4A-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,9,9,"2025-02-24","21:00:00","2025-02-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2CB4B-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","2CB4C-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,17,17,"2025-04-21","21:00:00","2025-04-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2CB4D-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,2,5",1]
[null,"DB InfraGO AG","2CCBB-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","2CCBC-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,13,13,"2025-03-25","21:00:00","2025-03-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","2CCBD-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2CCBE-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,3,1]
[null,"DB InfraGO AG","2D663-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,5,5,"2025-02-01","21:00:00","2025-02-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-24",null,null,"6,7",1]
[null,"DB InfraGO AG","2D664-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,9,9,"2025-03-01","21:00:00","2025-03-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-24",null,null,"1,7",1]
[null,"DB InfraGO AG","2D665-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,13,13,"2025-03-29","21:00:00","2025-03-30","05:00:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-24",null,null,"1,2",1]
[null,"DB InfraGO AG","2D666-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,17,17,"2025-04-26","21:00:00","2025-04-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-24",null,null,"2,3",1]
[null,"DB InfraGO AG","2D667-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,21,21,"2025-05-24","21:00:00","2025-05-25","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2F38F-004","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2F390-004","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2F391-004","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2F392-004","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,19,19,"2025-05-05","21:00:00","2025-05-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2F393-004","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,23,23,"2025-06-02","21:00:00","2025-06-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","30080-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","30081-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","30082-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","30083-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","30084-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-31",null,null,"3,4",1]
[null,"DB InfraGO AG","326A4-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"2,3,4,5,6,7",1]
[null,"DB InfraGO AG","36D73-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-24","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","36D73-007","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,21,21,"2025-05-19","23:30:00","2025-05-21","03:30:00","1d, 4h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-24",null,null,"1,6,7",1]
[null,"DB InfraGO AG","37165-003","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,25,25,"2025-06-16","21:00:00","2025-06-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","371FF-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,25,25,"2025-06-17","21:00:00","2025-06-18","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-02-01",null,null,"5,6,7",1]
[null,"DB InfraGO AG","3746A-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2025,2025,25,25,"2025-06-21","21:00:00","2025-06-22","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,7",1]
[null,"DB InfraGO AG","4094D-001","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Catenary Inspection",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,7",1]
[null,"DB InfraGO AG","40975-001","Berlin - Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Catenary Inspection",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,2",1]
[null,"DB InfraGO AG","1CB7B-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-24","04:00:00","3d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1CD5E-003","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-18","04:00:00","1d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1CCA6-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-19","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1CCBC-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CCBC-003","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,5",1]
[null,"DB InfraGO AG","1CCC5-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,5",1]
[null,"DB InfraGO AG","1CCC5-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3982B-001","Berlin - Dresden","< >","Berlin-Lichtenberg","Biesdorfer Kreuz Nord",2025,2025,11,11,"2025-03-14","23:00:00","2025-03-15","04:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3982B-002","Berlin - Dresden","< >","Berlin-Lichtenberg","Biesdorfer Kreuz Nord",2025,2025,11,11,"2025-03-14","23:00:00","2025-03-15","04:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1BA94-003","Berlin - Dresden","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,43,44,"2025-10-23","22:00:00","2025-10-31","05:50:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1BA94-005","Berlin - Dresden","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,43,43,"2025-10-24","08:00:00","2025-10-24","15:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1BA94-007","Berlin - Dresden","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,44,44,"2025-11-01","08:00:00","2025-11-01","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,6,1]
[null,"DB InfraGO AG","1BA97-002","Berlin - Dresden","< >","Biesdf Kr N Strw","Bln-Hohenschhsn",2025,2025,49,49,"2025-12-01","22:00:00","2025-12-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-09",null,null,6,1]
[null,"DB InfraGO AG","2CD89-002","Berlin - Dresden",">","Biesdf Kr N Strw","Karower Kr Strw",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2CD8A-002","Berlin - Dresden",">","Biesdf Kr N Strw","Berlin-Karow Ost",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2CD8B-002","Berlin - Dresden",">","Biesdf Kr N Strw","Karower Kr Strw",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2CD8C-002","Berlin - Dresden",">","Biesdf Kr N Strw","Karower Kr Strw",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FB98-003","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FB99-003","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FB9A-003","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","02:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FB9B-003","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FB9C-003","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FE37-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2FE38-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-02",null,null,"6,7",1]
[null,"DB InfraGO AG","2FE39-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-02",null,null,"2,3",1]
[null,"DB InfraGO AG","2FE3A-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","00:00:00","0d, 3h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-02",null,null,"3,4",1]
[null,"DB InfraGO AG","2FE3B-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-09",null,null,"5,6",1]
[null,"DB InfraGO AG","32710-002","Berlin - Dresden",">","Biesdf Kr N Strw","Karower Kr Strw",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-13",null,null,3,1]
[null,"DB InfraGO AG","2FE3A-014","Berlin - Dresden","< >","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,19,19,"2025-05-10","00:00:00","2025-05-10","05:00:00","0d, 5h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-13",null,null,3,1]
[null,"DB InfraGO AG","2FB9A-014","Berlin - Dresden","< >","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","05:00:00","0d, 3h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-13",null,null,3,1]
[null,"DB InfraGO AG","36D50-002","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-13","23:00:00","2025-02-15","04:00:00","1d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-13",null,null,3,1]
[null,"DB InfraGO AG","36D50-005","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-13","23:00:00","2025-02-15","04:00:00","1d, 5h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-03-23",null,null,"1,7",1]
[null,"DB InfraGO AG","37276-002","Berlin - Dresden",">","Biesdf Kr N Strw","Karower Kr Strw",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-03-23",null,null,"1,2",1]
[null,"DB InfraGO AG","407C7-002","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,6,6,"2025-02-05","22:30:00","2025-02-06","04:30:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-05-30",null,null,"1,7",1]
[null,"DB InfraGO AG","407C7-004","Berlin - Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Nord",2025,2025,6,6,"2025-02-05","22:30:00","2025-02-06","04:30:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,1,1]
[null,"DB InfraGO AG","306DE-003","Berlin - Dresden","< >","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Ost",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,2,1]
[null,"DB InfraGO AG","306DF-003","Berlin - Dresden","< >","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Ost",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-23",null,null,"2,3",1]
[null,"DB InfraGO AG","306E1-003","Berlin - Dresden","< >","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Ost",2025,2025,14,14,"2025-03-31","21:00:00","2025-04-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,3,1]
[null,"DB InfraGO AG","306E2-003","Berlin - Dresden","< >","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Ost",2025,2025,18,18,"2025-04-28","21:00:00","2025-04-29","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,3,1]
[null,"DB InfraGO AG","306E3-003","Berlin - Dresden","< >","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Ost",2025,2025,22,22,"2025-05-26","21:00:00","2025-05-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-03-23",null,null,"3,4",1]
[null,"DB InfraGO AG","18F39-005","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,9,10,"2025-02-24","22:00:00","2025-03-07","04:00:00","10d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,4,1]
[null,"DB InfraGO AG","1AEE8-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,14,14,"2025-03-31","22:00:00","2025-04-01","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,5,1]
[null,"DB InfraGO AG","1A794-012","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,47,47,"2025-11-19","20:00:00","2025-11-21","04:30:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-05-30",null,null,5,1]
[null,"DB InfraGO AG","1B2E5-002","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Karower Kr Strw",2025,2025,18,18,"2025-05-01","22:00:00","2025-05-02","04:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-05-30",null,null,5,1]
[null,"DB InfraGO AG","1B2E5-005","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Karower Kr Strw",2025,2025,18,18,"2025-05-02","21:00:00","2025-05-03","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-05-30",null,null,1,1]
[null,"DB InfraGO AG","1BA94-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,42,42,"2025-10-18","08:00:00","2025-10-19","23:59:00","1d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,1,1]
[null,"DB InfraGO AG","1BA94-002","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,43,44,"2025-10-23","22:00:00","2025-10-31","05:50:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-30",null,null,1,1]
[null,"DB InfraGO AG","1BA94-004","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,43,43,"2025-10-24","08:00:00","2025-10-24","15:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1BA94-006","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,44,44,"2025-11-01","08:00:00","2025-11-01","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1BA94-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,44,44,"2025-11-02","16:00:00","2025-11-02","23:59:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-04-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1BA94-009","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,44,44,"2025-11-02","16:00:00","2025-11-02","23:59:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1B86A-043","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,45,46,"2025-11-08","00:00:00","2025-11-16","06:00:00","8d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1B86A-044","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,45,46,"2025-11-08","00:00:00","2025-11-16","06:00:00","8d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1B86A-046","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,47,47,"2025-11-23","08:00:00","2025-11-23","11:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","1B86A-047","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,47,47,"2025-11-23","08:00:00","2025-11-23","11:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"1,7",1]
[null,"DB InfraGO AG","1B86A-049","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Bln-Hohenschhsn",2025,2025,47,47,"2025-11-23","11:00:00","2025-11-23","16:00:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1BA97-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,49,49,"2025-12-01","22:00:00","2025-12-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1BA97-004","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,50,50,"2025-12-08","08:00:00","2025-12-09","16:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,3,1]
[null,"DB InfraGO AG","2CD89-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","2CD89-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,4,1]
[null,"DB InfraGO AG","2CD8A-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,4,1]
[null,"DB InfraGO AG","2CD8A-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,4,1]
[null,"DB InfraGO AG","2CD8B-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-18",null,null,"2,3",1]
[null,"DB InfraGO AG","2CD8B-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"3,4",1]
[null,"DB InfraGO AG","2CD8C-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-25",null,null,"2,3",1]
[null,"DB InfraGO AG","2CD8C-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"4,5",1]
[null,"DB InfraGO AG","2FAFA-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-05",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFA-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-04",null,null,"4,5",1]
[null,"DB InfraGO AG","2FAFA-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2FAFA-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"4,5,6,7",1]
[null,"DB InfraGO AG","2FAFB-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FAFB-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-09",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2FAFB-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FAFB-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFC-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFC-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FAFC-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFC-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFD-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFD-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-27",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFD-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","2FAFD-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-25",null,null,"4,5",1]
[null,"DB InfraGO AG","2FAFE-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-25",null,null,5,1]
[null,"DB InfraGO AG","2FAFE-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFE-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","2FAFE-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","2FE37-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz West",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","2FE37-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Süd-West",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","2FE38-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz West",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","2FE38-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Süd-West",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2FE39-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz West",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,2,1]
[null,"DB InfraGO AG","2FE39-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Süd-West",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,3,1]
[null,"DB InfraGO AG","2FE3A-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz West",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,3,1]
[null,"DB InfraGO AG","2FE3A-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Süd-West",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,3,1]
[null,"DB InfraGO AG","2FE3B-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz West",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,3,1]
[null,"DB InfraGO AG","2FE3B-008","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Süd-West",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,4,1]
[null,"DB InfraGO AG","326DE-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin-Lichtenberg",2025,2025,6,6,"2025-02-08","07:00:00","2025-02-08","15:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-07",null,null,4,1]
[null,"DB InfraGO AG","326FE-002","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-07",null,null,4,1]
[null,"DB InfraGO AG","326FE-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-18",null,null,"3,5",1]
[null,"DB InfraGO AG","326FE-008","Berlin - Dresden","<","Biesdorfer Kreuz Nord","Berlin Eichgestell",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-18",null,null,"3,4,5",1]
[null,"DB InfraGO AG","326FE-012","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Bln-Rummels Vnk",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-18",null,null,"4,5",1]
[null,"DB InfraGO AG","32710-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-18",null,null,"4,5",1]
[null,"DB InfraGO AG","32710-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","3500B-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin-Lichtenberg",2025,2025,14,14,"2025-04-05","07:00:00","2025-04-05","15:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG",350,"Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin-Lichtenberg",2025,2025,18,18,"2025-05-03","07:00:00","2025-05-03","15:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,6,1]
[null,"DB InfraGO AG","35010-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin-Lichtenberg",2025,2025,22,22,"2025-05-31","07:00:00","2025-05-31","15:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,6,1]
[null,"DB InfraGO AG","355CA-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,13,14,"2025-03-30","23:00:00","2025-03-31","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","355CA-002","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,14,14,"2025-04-01","22:00:00","2025-04-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","37276-001","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","37276-006","Berlin - Dresden",">","Biesdorfer Kreuz Nord","Berlin-Karow West",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","3994D-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,9,9,"2025-03-01","08:00:00","2025-03-02","13:00:00","1d, 5h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3994D-005","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,9,9,"2025-03-01","08:00:00","2025-03-02","13:00:00","1d, 5h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3A3CC-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Ost",2025,2025,8,9,"2025-02-22","19:15:00","2025-02-26","21:00:00","4d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-02",null,null,"2,3,4",1]
[null,"DB InfraGO AG","3AC99-002","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Nord",2025,2025,10,10,"2025-03-03","07:00:00","2025-03-07","16:00:00","4d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3C267-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin-Karow Ost",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","3EC05-002","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,9,9,"2025-02-24","22:00:00","2025-02-28","04:00:00","3d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","3EC05-005","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,10,10,"2025-03-03","22:00:00","2025-03-07","04:00:00","3d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","3FDF5-004","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,30,30,"2025-07-26","12:00:00","2025-07-27","18:00:00","1d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","3FDF5-007","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-11","04:00:00","3d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","3FDF5-015","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,30,30,"2025-07-26","12:00:00","2025-07-27","18:00:00","1d, 6h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","40404-005","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,13,13,"2025-03-29","08:30:00","2025-03-29","13:30:00","0d, 5h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","401FA-011","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,7,7,"2025-02-15","08:30:00","2025-02-15","13:30:00","0d, 5h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3",1]
[null,"DB InfraGO AG","40720-001","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Ahrensfelde",2025,2025,6,6,"2025-02-04","23:00:00","2025-02-05","03:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"4,5",1]
[null,"DB InfraGO AG","40775-004","Berlin - Dresden","< >","Biesdorfer Kreuz Nord","Berlin Nordost",2025,2025,17,17,"2025-04-26","10:10:00","2025-04-26","14:10:00","0d, 4h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D5D4-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3,4",1]
[null,"DB InfraGO AG","2D5D4-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-02",null,null,"4,5,6",1]
[null,"DB InfraGO AG","2D5D5-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-02",null,null,3,1]
[null,"DB InfraGO AG","2D5D5-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-02",null,null,3,1]
[null,"DB InfraGO AG","2D5D6-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-02",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","2D5D6-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","2D5D7-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"6,7",1]
[null,"DB InfraGO AG","2D5D7-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"6,7",1]
[null,"DB InfraGO AG","326DA-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","326DA-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,3,1]
[null,"DB InfraGO AG","372A2-007","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,5,1]
[null,"DB InfraGO AG","372A2-008","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","41242-003","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Nord",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-06-21",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","41242-004","Berlin - Dresden","< >","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"3,4",1]
[null,"DB InfraGO AG","5D54-001","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,11,46,"2025-03-14","21:00:00","2025-11-14","21:00:00","245d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","5D54-002","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,46,50,"2025-11-14","21:00:00","2025-12-13","23:59:00","29d, 2h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1A794-003","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,46,46,"2025-11-15","20:00:00","2025-11-16","04:30:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,6,1]
[null,"DB InfraGO AG","1A794-004","Berlin - Dresden","<","Biesdorfer Kreuz Süd","Berlin Eichgestell",2025,2025,46,47,"2025-11-16","20:00:00","2025-11-17","04:30:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1A794-010","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Berlin Wendenheide",2025,2025,47,47,"2025-11-18","04:00:00","2025-11-19","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1A794-015","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Berlin Eichgestell",2025,2025,47,47,"2025-11-20","04:00:00","2025-11-21","04:30:00","1d, 0h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","2D5D4-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","2D5D5-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2D5D6-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,7,1]
[null,"DB InfraGO AG","2D5D7-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","2FAFA-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-13",null,null,"5,6",1]
[null,"DB InfraGO AG","2FAFB-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FAFC-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-04",null,null,"1,7",1]
[null,"DB InfraGO AG","2FAFD-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-04",null,null,"2,3",1]
[null,"DB InfraGO AG","2FAFE-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-04",null,null,"6,7",1]
[null,"DB InfraGO AG","326DA-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","326FE-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-West",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","5D54-003","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,11,46,"2025-03-14","21:00:00","2025-11-14","21:00:00","245d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,"3,4",1]
[null,"DB InfraGO AG","372A2-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,"4,5",1]
[null,"DB InfraGO AG","3980B-003","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,11,11,"2025-03-13","23:00:00","2025-03-14","04:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,"5,6",1]
[null,"DB InfraGO AG","41242-002","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,6,1]
[null,"DB InfraGO AG","41242-006","Berlin - Dresden","< >","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,"6,7",1]
[null,"DB InfraGO AG","1A794-009","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-Ost","Biesdorfer Kreuz Süd",2025,2025,47,47,"2025-11-17","20:00:00","2025-11-19","04:30:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-08-25",null,null,7,1]
[null,"DB InfraGO AG","1A794-005","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Süd",2025,2025,46,47,"2025-11-16","20:00:00","2025-11-17","04:30:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","1A794-013","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Süd",2025,2025,47,47,"2025-11-19","20:00:00","2025-11-21","04:30:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","2FE37-012","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","2FE38-012","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,3,1]
[null,"DB InfraGO AG","2FE39-012","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-29",null,null,2,1]
[null,"DB InfraGO AG","2FE3A-012","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-29",null,null,2,1]
[null,"DB InfraGO AG","2FE3B-012","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,5,1]
[null,"DB InfraGO AG","37B40-003","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-24","07:00:00","2025-02-28","16:00:00","4d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","37B40-004","Berlin - Dresden","< >","Biesdorfer Kreuz Süd-West","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-24","07:00:00","2025-02-28","16:00:00","4d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","2D5D4-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"2,3,4",1]
[null,"DB InfraGO AG","2D5D4-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,1,1]
[null,"DB InfraGO AG","2D5D5-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,1,1]
[null,"DB InfraGO AG","2D5D5-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2D5D6-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","2D5D6-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D5D7-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D5D7-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","2FAFA-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2FAFB-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"1,2",1]
[null,"DB InfraGO AG","2FAFC-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"1,2",1]
[null,"DB InfraGO AG","2FAFD-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO AG","2FAFE-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"3,4",1]
[null,"DB InfraGO AG","2FE37-011","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO AG","2FE38-011","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"4,5",1]
[null,"DB InfraGO AG","2FE39-011","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-12",null,null,"1,7",1]
[null,"DB InfraGO AG","2FE3A-011","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-12",null,null,"1,7",1]
[null,"DB InfraGO AG","2FE3B-011","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,7",1]
[null,"DB InfraGO AG","326DA-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,7",1]
[null,"DB InfraGO AG","326DA-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,2",1]
[null,"DB InfraGO AG","326FE-010","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"2,3",1]
[null,"DB InfraGO AG","372A2-013","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","372A2-014","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Süd",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","40707-001","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,5,5,"2025-01-31","23:00:00","2025-02-01","03:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-07-25",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","40707-002","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,5,5,"2025-01-31","23:00:00","2025-02-01","03:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-07-25",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","40716-001","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,5,5,"2025-02-01","23:00:00","2025-02-02","03:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,2",1]
[null,"DB InfraGO AG","40716-002","Berlin - Dresden","< >","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2025,2025,5,5,"2025-02-01","23:00:00","2025-02-02","03:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"3,4",1]
[null,"DB InfraGO AG","C323-003","Berlin - Dresden","< >","Blankenfelde (Kr Teltow-Fläming)","Blankenfelde (Kr Teltow-Fläming)",2024,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00","363d, 23h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-07",null,null,"1,2",1]
[null,"DB InfraGO AG","C35C-004","Berlin - Dresden","< >","Blankenfelde (Kr Teltow-Fläming)","Blankenfelde (Kr Teltow-Fläming)",2024,2025,50,22,"2024-12-15","00:00:00","2025-05-30","21:00:00","166d, 20h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"3,4",1]
[null,"DB InfraGO AG","412B6-001","Berlin - Dresden",">","Blankenfelde (Kr Teltow-Fläming)","Rangsdorf",2025,2025,13,14,"2025-03-30","22:00:00","2025-04-04","04:00:00","4d, 6h","Periodical","Catenary Inspection",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-08-05",null,null,"3,4",1]
[null,"DB InfraGO AG","850C-017","Berlin - Dresden","< >","Bln-Hohenschhsn","Berlin-Karow West",2025,2025,8,9,"2025-02-21","22:00:00","2025-02-24","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"3,4",1]
[null,"DB InfraGO AG","2FE37-009","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdorfer Kreuz Mitte",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FE38-009","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdorfer Kreuz Mitte",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","2FE39-009","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdorfer Kreuz Mitte",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","2FE3A-009","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdorfer Kreuz Mitte",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","2FE3B-009","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdorfer Kreuz Mitte",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FE3A-013","Berlin - Dresden","< >","Bln-Hohenschhsn","Biesdf Kr N Strw",2025,2025,19,19,"2025-05-10","00:00:00","2025-05-10","05:00:00","0d, 5h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","36D50-004","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdf Kr N Strw",2025,2025,7,7,"2025-02-13","23:00:00","2025-02-15","04:00:00","1d, 5h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","3994D-007","Berlin - Dresden","< >","Bln-Hohenschhsn","Berlin Nordost",2025,2025,9,9,"2025-03-01","08:00:00","2025-03-02","13:00:00","1d, 5h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","39967-002","Berlin - Dresden","< >","Bln-Hohenschhsn","Berlin Nordost",2025,2025,11,11,"2025-03-16","08:00:00","2025-03-16","14:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","3B325-001","Berlin - Dresden","<","Bln-Hohenschhsn","Berlin-Karow Ost",2025,2025,8,8,"2025-02-22","07:00:00","2025-02-23","15:30:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3B325-002","Berlin - Dresden","<","Bln-Hohenschhsn","Berlin-Karow Ost",2025,2025,8,8,"2025-02-22","07:00:00","2025-02-23","15:30:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3C267-002","Berlin - Dresden","< >","Bln-Hohenschhsn","Berlin Nordost",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","3C267-003","Berlin - Dresden","< >","Bln-Hohenschhsn","Bln-Hohenschhsn",2025,2025,13,13,"2025-03-25","01:00:00","2025-03-25","05:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","3FDF5-009","Berlin - Dresden","< >","Bln-Hohenschhsn","Biesdorfer Kreuz Nord",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-11","04:00:00","3d, 6h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,7",1]
[null,"DB InfraGO AG","3FDF5-010","Berlin - Dresden","< >","Bln-Hohenschhsn","Biesdf Kr N Strw",2025,2025,28,28,"2025-07-07","22:00:00","2025-07-11","04:00:00","3d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-18",null,null,"1,7",1]
[null,"DB InfraGO AG","405BB-004","Berlin - Dresden","< >","Bln-Hohenschhsn","Bln-Hohenschhsn",2025,2025,13,13,"2025-03-27","00:20:00","2025-03-27","02:50:00","0d, 2h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","405BB-005","Berlin - Dresden","< >","Bln-Hohenschhsn","Berlin-Karow Ost",2025,2025,13,13,"2025-03-27","00:20:00","2025-03-27","02:50:00","0d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","407C7-003","Berlin - Dresden","<","Bln-Hohenschhsn","Biesdf Kr N Strw",2025,2025,6,6,"2025-02-05","22:30:00","2025-02-06","04:30:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1A663-009","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,8,8,"2025-02-21","02:00:00","2025-02-21","04:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,6,1]
[null,"DB InfraGO AG","1A6EC-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-24","22:00:00","2025-02-25","01:00:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1A6EC-006","Berlin - Dresden","< >","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-25","01:00:00","2025-02-25","02:30:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","1A6EC-010","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,9,9,"2025-02-25","02:30:00","2025-02-25","05:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-26",null,null,"1,7",1]
[null,"DB InfraGO AG","1A6EC-011","Berlin - Dresden",">","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-25","02:30:00","2025-02-25","05:30:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-07-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A734-004","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,9,9,"2025-02-25","22:00:00","2025-02-26","01:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-01",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1A734-006","Berlin - Dresden","<","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-25","22:00:00","2025-02-26","01:00:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-01",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1A765-002","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,9,9,"2025-02-26","22:00:00","2025-02-26","23:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-01",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1A734-008","Berlin - Dresden","< >","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-26","01:00:00","2025-02-26","02:30:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"5,7",1]
[null,"DB InfraGO AG","1A734-012","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,9,9,"2025-02-26","02:30:00","2025-02-26","05:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-01",null,null,"5,7",1]
[null,"DB InfraGO AG","1A734-013","Berlin - Dresden",">","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-26","02:30:00","2025-02-26","05:30:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-07-10",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1A765-009","Berlin - Dresden","< >","Brenitz-Sonnewalde","Doberlug-K ob Bf",2025,2025,9,9,"2025-02-27","03:00:00","2025-02-27","05:00:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"2,3",1]
[null,"DB InfraGO AG","2E3DA-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,6,6,"2025-02-04","21:00:00","2025-02-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-09-12",null,null,"4,5,6,7",1]
[null,"DB InfraGO AG","2E3DB-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-09-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2E3DC-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-09-12",null,null,"4,5,6,7",1]
[null,"DB InfraGO AG","2E3DD-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-09-12",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2E3DE-004","Berlin - Dresden","<","Brenitz-Sonnewalde","Walddrehna",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-09-22",null,null,"1,7",1]
[null,"DB InfraGO AG","2E63E-001","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"1,2",1]
[null,"DB InfraGO AG","2E63F-001","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,10,10,"2025-03-05","21:00:00","2025-03-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"1,7",1]
[null,"DB InfraGO AG","2E640-001","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,14,14,"2025-04-02","21:00:00","2025-04-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2E641-001","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,18,18,"2025-04-30","21:00:00","2025-05-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"5,6",1]
[null,"DB InfraGO AG","2E642-001","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-Kh Nord",2025,2025,22,22,"2025-05-28","21:00:00","2025-05-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"1,7",1]
[null,"DB InfraGO AG","314E8-005","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-K ob Bf",2025,2025,8,8,"2025-02-20","21:00:00","2025-02-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","314E9-005","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-K ob Bf",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-11-09",null,null,"3,4",1]
[null,"DB InfraGO AG","314EB-005","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-K ob Bf",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-09-22",null,null,"5,6,7",1]
[null,"DB InfraGO AG","314EC-005","Berlin - Dresden",">","Brenitz-Sonnewalde","Doberlug-K ob Bf",2025,2025,24,24,"2025-06-12","21:00:00","2025-06-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-09-22",null,null,"1,2",1]
[null,"DB InfraGO AG","319A9-001","Berlin - Dresden","<","Brenitz-Sonnewalde","Luckau-Uckro",2025,2025,8,8,"2025-02-22","21:00:00","2025-02-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"2,3",1]
[null,"DB InfraGO AG","319AA-001","Berlin - Dresden","<","Brenitz-Sonnewalde","Luckau-Uckro",2025,2025,12,12,"2025-03-22","21:00:00","2025-03-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-25",null,null,"4,5",1]
[null,"DB InfraGO AG","319AC-001","Berlin - Dresden","<","Brenitz-Sonnewalde","Luckau-Uckro",2025,2025,20,20,"2025-05-17","21:00:00","2025-05-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO AG","319AD-001","Berlin - Dresden","<","Brenitz-Sonnewalde","Luckau-Uckro",2025,2025,24,24,"2025-06-14","21:00:00","2025-06-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO AG",402.1,"Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2025,2025,15,15,"2025-04-09","07:00:00","2025-04-10","18:00:00","1d, 11h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-11-09",null,null,"4,5",1]
[null,"DB InfraGO AG",40.21,"Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2025,2025,15,16,"2025-04-13","23:30:00","2025-04-17","05:00:00","3d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1F4BA-003","Berlin - Dresden",">","Cossebaude","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F4BA-010","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-011","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-005","Berlin - Dresden",">","Cossebaude","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB4B-008","Berlin - Dresden",">","Cossebaude","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","20189-001","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","20189-002","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","20D69-003","Berlin - Dresden","<","Cossebaude","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","2CC84-001","Berlin - Dresden","<","Diedersdorf","Glasower Damm Ost",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","2CC85-001","Berlin - Dresden","<","Diedersdorf","Glasower Damm Ost",2025,2025,13,13,"2025-03-25","21:00:00","2025-03-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,7,1]
[null,"DB InfraGO AG","2CC86-001","Berlin - Dresden","<","Diedersdorf","Glasower Damm Ost",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-05",null,null,1,1]
[null,"DB InfraGO AG","2CC87-001","Berlin - Dresden","<","Diedersdorf","Glasower Damm Ost",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","2ED12-002","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,6,7,"2025-02-09","21:00:00","2025-02-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-07",null,null,"2,3",1]
[null,"DB InfraGO AG","2ED13-002","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,10,11,"2025-03-09","21:00:00","2025-03-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-02",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2ED14-002","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,14,15,"2025-04-06","21:00:00","2025-04-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-02",null,null,"3,4,5",1]
[null,"DB InfraGO AG","2ED15-002","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,18,19,"2025-05-04","21:00:00","2025-05-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-06",null,null,"1,2",1]
[null,"DB InfraGO AG","2ED16-002","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,22,23,"2025-06-01","21:00:00","2025-06-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-06",null,null,"1,2",1]
[null,"DB InfraGO AG","2FDBB-001","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","2FDBC-001","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,"2,3",1]
[null,"DB InfraGO AG","2FDBD-001","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,"2,3",1]
[null,"DB InfraGO AG","2FDBE-001","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,"1,2",1]
[null,"DB InfraGO AG","2FDBF-001","Berlin - Dresden",">","Diedersdorf","Genshagener Heide Ost",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,"3,4",1]
[null,"DB InfraGO AG","1B5FB-009","Berlin - Dresden","<","Diepensee C","Glasower Damm Ost",2025,2025,7,7,"2025-02-12","21:00:00","2025-02-14","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2023-09-06",null,null,"3,4",1]
[null,"DB InfraGO AG","1A79C-001","Berlin - Dresden",">","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,9,9,"2025-02-27","22:00:00","2025-02-28","00:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1A79C-006","Berlin - Dresden","< >","Doberlug-K ob Bf","Hohenleipisch Betriebsbahnhof",2025,2025,9,9,"2025-02-28","00:30:00","2025-02-28","02:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-06",null,null,"3,4",1]
[null,"DB InfraGO AG","1A79C-012","Berlin - Dresden","< >","Doberlug-K ob Bf","Hohenleipisch Betriebsbahnhof",2025,2025,9,9,"2025-02-28","04:30:00","2025-02-28","06:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-06",null,null,"3,4",1]
[null,"DB InfraGO AG","1C5B1-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,24,25,"2025-06-15","23:00:00","2025-06-20","05:00:00","4d, 6h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","2E398-001","Berlin - Dresden",">","Doberlug-K ob Bf","Hohenleipisch",2025,2025,6,6,"2025-02-04","21:00:00","2025-02-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","2E398-004","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,6,6,"2025-02-04","21:00:00","2025-02-05","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","2E399-001","Berlin - Dresden",">","Doberlug-K ob Bf","Hohenleipisch",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,2,1]
[null,"DB InfraGO AG","2E399-004","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","2E39A-001","Berlin - Dresden",">","Doberlug-K ob Bf","Hohenleipisch",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,3,1]
[null,"DB InfraGO AG","2E39A-004","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2E39B-001","Berlin - Dresden",">","Doberlug-K ob Bf","Hohenleipisch",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,3,1]
[null,"DB InfraGO AG","2E39B-004","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","2E39C-001","Berlin - Dresden",">","Doberlug-K ob Bf","Hohenleipisch",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,3,1]
[null,"DB InfraGO AG","2E39C-004","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,4,1]
[null,"DB InfraGO AG","2E63E-005","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2E63F-005","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2025,2025,10,10,"2025-03-05","21:00:00","2025-03-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-17",null,null,"2,3,4",1]
[null,"DB InfraGO AG","2E640-005","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2025,2025,14,14,"2025-04-02","21:00:00","2025-04-03","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-16",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2E641-005","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2025,2025,18,18,"2025-04-30","21:00:00","2025-05-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2E642-005","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2025,2025,22,22,"2025-05-28","21:00:00","2025-05-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","31782-003","Berlin - Dresden",">","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,8,8,"2025-02-21","21:00:00","2025-02-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-08-09",null,null,"1,2",1]
[null,"DB InfraGO AG","31783-003","Berlin - Dresden",">","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-08-09",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","31785-003","Berlin - Dresden",">","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-08-09",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","31786-003","Berlin - Dresden",">","Doberlug-K ob Bf","Rückersdorf                    (Niederl)",2025,2025,24,24,"2025-06-13","21:00:00","2025-06-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-08-09",null,null,"3,4",1]
[null,"DB InfraGO AG","40879-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2025,2025,12,13,"2025-03-23","23:15:00","2025-03-28","04:40:00","4d, 5h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","4149C-001","Berlin - Dresden","<","Doberlug-K ob Bf","Doberlug-K ob Bf",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2103F-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,25,28,"2026-06-19","21:00:00","2026-07-10","21:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-08",null,null,5,1]
[null,"DB InfraGO AG","2100C-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,27,28,"2026-07-03","21:00:00","2026-07-10","21:00:00","7d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-06",null,null,"6,7",1]
[null,"DB InfraGO AG","2100C-003","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,27,28,"2026-07-03","21:00:00","2026-07-10","21:00:00","7d, 0h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-08",null,null,7,1]
[null,"DB InfraGO AG","2100C-004","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-14",null,null,7,1]
[null,"DB InfraGO AG","2100C-005","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","2100D-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","2100D-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,1,1]
[null,"DB InfraGO AG","2100D-003","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-19",null,null,6,1]
[null,"DB InfraGO AG","2103F-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,25,28,"2026-06-19","21:00:00","2026-07-10","21:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1A6EC-008","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-25","02:30:00","2025-02-25","05:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1A765-004","Berlin - Dresden","<","Doberlug-Kh Nord","Doberlug-Kh Nord",2025,2025,9,9,"2025-02-26","22:00:00","2025-02-26","23:15:00","0d, 1h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1A765-006","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-26","23:15:00","2025-02-27","03:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","1A765-008","Berlin - Dresden",">","Doberlug-Kh Nord","Doberlug-Kh Nord",2025,2025,9,9,"2025-02-26","23:15:00","2025-02-27","03:00:00","0d, 3h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2023-09-14",null,null,1,1]
[null,"DB InfraGO AG","1A734-010","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,9,9,"2025-02-26","02:30:00","2025-02-26","05:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","314E8-002","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,8,8,"2025-02-20","21:00:00","2025-02-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-13",null,null,3,1]
[null,"DB InfraGO AG","314E8-003","Berlin - Dresden","< >","Doberlug-Kh Nord","Hennersdorf West",2025,2025,8,8,"2025-02-20","21:00:00","2025-02-21","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-13",null,null,3,1]
[null,"DB InfraGO AG","314E9-002","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-13",null,null,4,1]
[null,"DB InfraGO AG","314E9-003","Berlin - Dresden","< >","Doberlug-Kh Nord","Hennersdorf West",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","314EB-002","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-08",null,null,1,1]
[null,"DB InfraGO AG","314EB-003","Berlin - Dresden","< >","Doberlug-Kh Nord","Hennersdorf West",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","314EC-002","Berlin - Dresden","<","Doberlug-Kh Nord","Brenitz-Sonnewalde",2025,2025,24,24,"2025-06-12","21:00:00","2025-06-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","314EC-003","Berlin - Dresden","< >","Doberlug-Kh Nord","Hennersdorf West",2025,2025,24,24,"2025-06-12","21:00:00","2025-06-13","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3178C-001","Berlin - Dresden","<","Doberlug-Kh Nord","Walddrehna",2025,2025,8,8,"2025-02-21","21:00:00","2025-02-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3178D-001","Berlin - Dresden","<","Doberlug-Kh Nord","Walddrehna",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3178F-001","Berlin - Dresden","<","Doberlug-Kh Nord","Walddrehna",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","31790-001","Berlin - Dresden","<","Doberlug-Kh Nord","Walddrehna",2025,2025,24,24,"2025-06-13","21:00:00","2025-06-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-25",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2100C-006","Berlin - Dresden","< >","Doberlug-Kh Nord","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","2100C-007","Berlin - Dresden","< >","Doberlug-Kh Nord","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDD","Berlin - Dresden",">","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3097-(MK27)-01_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,38,46,"20.09.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3DDC3-001","Berlin - Dresden","< >","Dresden Bischofsplatz","Radebeul Ost",2025,2025,12,12,"2025-03-19","21:00:00","2025-03-20","05:00:00","0d, 8h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","17173-007","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO AG","18B70-013","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2025,2025,7,7,"2025-02-13","19:30:00","2025-02-14","02:00:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"3,4",1]
[null,"DB InfraGO AG","18B70-017","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2025,2025,7,7,"2025-02-14","02:00:00","2025-02-14","04:30:00","0d, 2h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"6,7",1]
[null,"DB InfraGO AG","18B70-018","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2025,2025,7,7,"2025-02-14","02:00:00","2025-02-14","04:30:00","0d, 2h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-18",null,null,"1,2,3",1]
[null,"DB InfraGO AG","18C6D-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,43,43,"2025-10-20","19:30:00","2025-10-24","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,6,7",1]
[null,"DB InfraGO AG","18CE6-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,43,44,"2025-10-24","21:00:00","2025-10-27","04:00:00","2d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","18CE6-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,43,44,"2025-10-24","21:00:00","2025-10-27","04:00:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,7",1]
[null,"DB InfraGO AG","18CE6-006","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,43,44,"2025-10-24","21:00:00","2025-10-27","04:00:00","2d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","18D0A-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,45,"2025-11-03","19:30:00","2025-11-07","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","18D23-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,"4,5",1]
[null,"DB InfraGO AG","18D23-006","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","18D23-007","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,45,47,"2025-11-07","21:00:00","2025-11-17","04:00:00","9d, 7h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","18D4A-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,2,1]
[null,"DB InfraGO AG","2D65A-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-18",null,null,2,1]
[null,"DB InfraGO AG","2E315-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2025,2025,14,14,"2025-03-31","21:00:00","2025-04-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-18",null,null,"2,3",1]
[null,"DB InfraGO AG","387BE-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2025,2025,22,22,"2025-05-26","01:05:00","2025-05-26","04:05:00","0d, 3h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","387FD-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2025,2025,8,8,"2025-02-17","01:05:00","2025-02-17","04:00:00","0d, 2h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,6,1]
[null,"DB InfraGO AG","3FA8F-001","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1D63C-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,49,50,"2026-12-04","22:00:00","2026-12-07","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","1DD70-007","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD70-010","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-20","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","1DD70-013","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,4,4,"2026-01-20","21:00:00","2026-01-25","04:00:00","4d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD70-018","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,6,6,"2026-02-02","21:00:00","2026-02-04","04:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","1F4E5-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,2,1]
[null,"DB InfraGO AG","1F4E5-012","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,2,1]
[null,"DB InfraGO AG","1F4E5-014","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1F4E5-016","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","1F50F-002","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","00:00:00","1d, 12h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F548-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1F548-008","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1F58D-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","1F58D-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F59E-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F59E-006","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1F5C3-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","18:00:00","0d, 13h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1F5C3-017","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1F5FE-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-11-06",null,null,6,1]
[null,"DB InfraGO AG","1F5FE-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO AG","1F672-001","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1F672-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F672-012","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,19,19,"2026-05-09","16:00:00","2026-05-10","04:00:00","0d, 12h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-23",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1F722-001","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-10-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1F722-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F722-008","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,43,43,"2026-10-25","00:00:00","2026-10-25","04:00:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F722-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,47,47,"2026-11-16","00:00:00","2026-11-16","04:00:00","0d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F748-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F748-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"6,7",1]
[null,"DB InfraGO AG","1F543-005","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","00:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-10-25",null,null,7,1]
[null,"DB InfraGO AG","1F543-013","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-25",null,null,7,1]
[null,"DB InfraGO AG","20D69-006","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2023-10-25",null,null,7,1]
[null,"DB InfraGO AG","20D69-007","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,7,1]
[null,"DB InfraGO AG","20D69-008","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-10-18",null,null,4,1]
[null,"DB InfraGO AG","3873-(MK27)-01_D","Berlin - Dresden",">","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"04.09.2027","05:00:00","12.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","3873-(MK27)-01_N","Berlin - Dresden","< >","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"03.09.2027","21:00:00","12.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","9C56-002","Berlin - Dresden","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","9C56-006","Berlin - Dresden","< >","Dresden Hbf","Pirna",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","9C86-002","Berlin - Dresden","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2024-04-17",null,null,"4,5,6",1]
[null,"DB InfraGO AG","9C86-006","Berlin - Dresden","< >","Dresden Hbf","Pirna",2025,2025,46,46,"2025-11-14","21:00:00","2025-11-15","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","9CE5-002","Berlin - Dresden","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2024-04-17",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","9CE5-006","Berlin - Dresden","< >","Dresden Hbf","Pirna",2025,2025,49,49,"2025-12-02","22:00:00","2025-12-03","04:00:00","0d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","9CE5-012","Berlin - Dresden","< >","Dresden Hbf","Bad Schandau Gr",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2024-04-22",null,null,3,1]
[null,"DB InfraGO AG","9CE5-016","Berlin - Dresden","< >","Dresden Hbf","Pirna",2025,2025,49,50,"2025-12-07","19:00:00","2025-12-10","05:00:00","2d, 10h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-15",null,null,"6,7",1]
[null,"DB InfraGO AG","A214-005","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2024,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00","363d, 23h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-09-15",null,null,7,1]
[null,"DB InfraGO AG","A214-006","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2024,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00","363d, 23h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,7,1]
[null,"DB InfraGO AG","17173-003","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,4,1]
[null,"DB InfraGO AG","17173-005","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,"1,2",1]
[null,"DB InfraGO AG","18C01-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2025,2025,41,41,"2025-10-07","19:30:00","2025-10-08","04:30:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,6,1]
[null,"DB InfraGO AG","18D4A-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-29",null,null,"6,7",1]
[null,"DB InfraGO AG","2D65A-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC0E-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-17",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1DC42-022","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1F528-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","1F532-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-12","21:00:00","2026-02-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,3,1]
[null,"DB InfraGO AG","1F58D-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1F672-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2026,2026,19,19,"2026-05-08","20:00:00","2026-05-09","04:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","1F722-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1DD70-015","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,5,5,"2026-01-26","21:00:00","2026-01-28","04:00:00","1d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-28",null,null,2,1]
[null,"DB InfraGO AG","18D4A-007","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2025,2025,46,46,"2025-11-10","19:30:00","2025-11-14","04:30:00","3d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,6,1]
[null,"DB InfraGO AG","1F59E-004","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-09-05",null,null,1,1]
[null,"DB InfraGO AG","1F543-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,2,1]
[null,"DB InfraGO AG","3636-(MK27)-02_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,46,49,"19.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","B20B-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,46,46,"2025-11-13","21:00:00","2025-11-14","16:00:00","0d, 19h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4,5,6,7",1]
[null,"DB InfraGO AG","18A73-012","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2025,2025,5,6,"2025-02-01","04:00:00","2025-02-08","20:00:00","7d, 16h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-24",null,null,"2,3,4",1]
[null,"DB InfraGO AG","399B8-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2025,2025,7,7,"2025-02-10","07:00:00","2025-02-11","16:00:00","1d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-19",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D47F-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,44,48,"2026-10-26","08:00:00","2026-11-23","18:00:00","28d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-11-25",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1F4BA-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"1,7",1]
[null,"DB InfraGO AG","1FA4A-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,8,"2026-02-17","04:00:00","2026-02-21","06:00:00","4d, 2h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2,7",1]
[null,"DB InfraGO AG","20997-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20997-026","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,7",1]
[null,"DB InfraGO AG","20997-034","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-07","21:00:00","2026-03-08","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-04-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20C8C-021","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-11","08:00:00","2026-06-11","17:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"1,2",1]
[null,"DB InfraGO AG","2D62B-007","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2025,2025,9,9,"2025-02-27","21:05:00","2025-02-28","04:50:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1F543-021","Berlin - Dresden","< >","Dresden-Neustadt","Coswig (bei Dresden)",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D65A-001","Berlin - Dresden",">","Dresden-Niedersedlitz Güteranlage  (DHD)","Dresden Hbf",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-01",null,null,"1,2",1]
[null,"DB InfraGO AG","916D-001","Berlin - Dresden","< >","Eichgestell Nord","Berlin Wendenheide",2025,2025,49,49,"2025-12-01","21:30:00","2025-12-02","04:30:00","0d, 7h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","2D5D6-015","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-18",null,null,"5,6",1]
[null,"DB InfraGO AG","30084-002","Berlin - Dresden","< >","Eichgestell Nord","Berlin Eichgestell",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","3960D-001","Berlin - Dresden","<","Frauenhain","Großenhain Berl Bf",2025,2025,7,7,"2025-02-10","22:10:00","2025-02-14","04:50:00","3d, 6h","Periodical","Catenary Inspection",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2025-01-20",null,null,"3,4",1]
[null,"DB InfraGO AG","2FAE0-008","Berlin - Dresden",">","Genshagener Heide","Saarmund",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","2FAE2-003","Berlin - Dresden","< >","Genshagener Heide Mitte","Gensh Heide Nord",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","2CB10-001","Berlin - Dresden","<","Genshagener Heide Ost","Glasower Damm West",2025,2025,17,17,"2025-04-21","21:00:00","2025-04-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"5,6",1]
[null,"DB InfraGO AG","2ED14-005","Berlin - Dresden","<","Genshagener Heide Ost","Glasower Damm Ost",2025,2025,14,15,"2025-04-06","21:00:00","2025-04-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2024-07-08",null,null,"5,6",1]
[null,"DB InfraGO AG","2DC4D-002","Berlin - Dresden","<","Glasower Damm Ost","Schönefeld (bei Berlin) F-Bahn",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","2ED13-001","Berlin - Dresden",">","Glasower Damm Ost","Diedersdorf",2025,2025,10,11,"2025-03-09","21:00:00","2025-03-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","30C89-001","Berlin - Dresden","< >","Glasower Damm Ost","Flughafen BER F-Bahn",2025,2025,18,18,"2025-04-28","21:00:00","2025-04-29","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"6,7",1]
[null,"DB InfraGO AG","2CC86-002","Berlin - Dresden","< >","Glasower Damm West","Blankenfelde (Kr Teltow-Fläming)",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO AG","2E3A6-005","Berlin - Dresden","<","Golßen (Niederlausitz)","Baruth (Mark)",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","314D9-005","Berlin - Dresden","<","Großenhain Berl Bf","Weinböhla",2025,2025,8,8,"2025-02-20","21:00:00","2025-02-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","2FE2E-006","Berlin - Dresden","<","Grünauer Kreuz Nord","Schönefeld (bei Berlin) F-Bahn",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"6,7",1]
[null,"DB InfraGO AG","2CB4A-002","Berlin - Dresden","< >","Grünauer Kreuz Süd","Berlin-Grünau",2025,2025,9,9,"2025-02-24","21:00:00","2025-02-25","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,"1,2",1]
[null,"DB InfraGO AG","36D73-001","Berlin - Dresden",">","Grünauer Kreuz Süd","Berlin Eichgestell",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-24","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","2D664-003","Berlin - Dresden",">","Grünauer Kreuz West","Grünauer Kreuz Süd",2025,2025,9,9,"2025-03-01","21:00:00","2025-03-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2FE31-004","Berlin - Dresden",">","Grünauer Kreuz West","Grünauer Kreuz Süd",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1A663-007","Berlin - Dresden","< >","Luckau-Uckro","Brenitz-Sonnewalde",2025,2025,8,8,"2025-02-21","00:30:00","2025-02-21","02:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","2E5E7-005","Berlin - Dresden","<","Luckau-Uckro","Golßen (Niederlausitz)",2025,2025,22,22,"2025-05-28","21:00:00","2025-05-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2025-01-20",null,null,"2,3",1]
[null,"DB InfraGO AG","31B1B-001","Berlin - Dresden","<","Potsdam Wildpark West","Genshagener Heide",2025,2025,8,9,"2025-02-23","21:00:00","2025-02-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","3AAA6-001","Berlin - Dresden",">","Radebeul Abzw Az","Weinböhla",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","39941-001","Berlin - Dresden",">","Radebeul Ost","Coswig (bei Dresden)",2025,2025,8,8,"2025-02-20","23:30:00","2025-02-21","04:30:00","0d, 5h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1FB4B-015","Berlin - Dresden",">","Radebeul-Naundorf","Radebeul-Naundorf                 (Abzw)",2026,2026,10,11,"2026-03-06","06:00:00","2026-03-10","18:00:00","4d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1A79C-013","Berlin - Dresden","< >","Rückersdorf                    (Niederl)","Rückersdorf                    (Niederl)",2025,2025,9,9,"2025-02-28","04:30:00","2025-02-28","06:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","31783-001","Berlin - Dresden","<","Rückersdorf                    (Niederl)","Doberlug-K ob Bf",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","31B18-001","Berlin - Dresden","<","Saarmund","Genshagener Heide",2025,2025,16,17,"2025-04-20","21:00:00","2025-04-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","1CD5E-001","Berlin - Dresden","<","Schönefeld (bei Berlin) F-Bahn","Berlin Wendenheide",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-18","04:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","1A663-011","Berlin - Dresden","<","Walddrehna","Luckau-Uckro",2025,2025,8,8,"2025-02-21","02:00:00","2025-02-21","04:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","3178D-004","Berlin - Dresden",">","Walddrehna","Brenitz-Sonnewalde",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-17",null,null,"6,7",1]
[null,"DB InfraGO AG","3AAA6-004","Berlin - Dresden","< >","Weinböhla","Radebeul Abzw Az",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous",null,null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","6CB5-002","Berlin - Dresden","< >","Zossen","Zossen",2024,2025,50,33,"2024-12-15","00:00:00","2025-08-15","21:00:00","243d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"1,2",1]
[null,"DB InfraGO AG","2CCED-003","Bremen - Hannover","< >","Achim","Langwedel",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","31068-001","Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2025,24,24,"2025-06-10","21:00:00","2025-06-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","2FA5C-003","Bremen - Hannover","< >","Baden (Kr Verden)","Bremen-Sebaldsbrück",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","31465-004","Bremen - Hannover","< >","Bremen Gabelung","Bremen Hbf",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","2D9AB-006","Bremen - Hannover","<","Bremen Hbf","Bremen-Hemelingen",2025,2025,13,13,"2025-03-24","22:00:00","2025-03-25","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","31463-001","Bremen - Hannover","<","Bremen Hbf","Bremen Gabelung",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","3267A-006","Bremen - Hannover","< >","Bremen Hbf","Bremen-Mahndorf",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"2,3",1]
[null,"DB InfraGO AG","372E8-002","Bremen - Hannover","<","Bremen Hbf","Bremen-Sebaldsbrück",2025,2025,25,25,"2025-06-18","23:00:00","2025-06-19","05:00:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-28",null,null,"2,3",1]
[null,"DB InfraGO AG","20849-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-27","09:00:00","2026-07-27","12:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"2,3",1]
[null,"DB InfraGO AG","20849-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,32,"2026-07-31","22:00:00","2026-08-03","16:30:00","2d, 18h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","20BFE-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,13,13,"2026-03-27","01:00:00","2026-03-27","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","20BFF-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-14","07:00:00","2026-07-14","16:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","2FA54-006","Bremen - Hannover","< >","Bremen Hbf","Bremen-Mahndorf",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"3,4",1]
[null,"DB InfraGO AG","2FA58-006","Bremen - Hannover","< >","Bremen Hbf","Bremen-Mahndorf",2025,2025,23,23,"2025-06-05","21:00:00","2025-06-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","356FB-001","Bremen - Hannover","<","Bremen-Oberneuland","Bremen Hbf",2025,2025,21,21,"2025-05-23","23:50:00","2025-05-24","04:50:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","19D0F-001","Bremen - Hannover",">","Bremen-Sebaldsbrück","Bremen Hbf",2025,2025,7,7,"2025-02-11","04:30:00","2025-02-11","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","2FA1A-004","Bremen - Hannover",">","Bremen-Sebaldsbrück","Bremen Hbf",2025,2025,19,19,"2025-05-06","23:00:00","2025-05-07","05:00:00","0d, 6h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","2FA5C-001","Bremen - Hannover","<","Bremen-Sebaldsbrück","Baden (Kr Verden)",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","2FC83-001","Bremen - Hannover","< >","Estorf (Weser)","Nienburg (Weser)",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"4,5",1]
[null,"DB InfraGO AG","2CCEA-004","Bremen - Hannover","< >","Etelsen","Verden (Aller)",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","37535-003","Bremen - Hannover","< >","Eystrup","Nienburg (Weser)",2025,2025,18,18,"2025-05-03","23:00:00","2025-05-04","00:00:00","0d, 1h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","30E0F-001","Bremen - Hannover","<","Gümmerwald","Wunstorf",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,",null,null,null,"N",null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1B1BB-012","Bremen - Hannover","< >","Hannover-Linden","Ahlem",2026,2026,3,3,"2026-01-16","21:00:00","2026-01-17","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","15638-011","Bremen - Hannover","< >","Hannover-Linden Hafen","Empelde                           (Abzw)",2025,2025,13,13,"2025-03-30","05:40:00","2025-03-30","07:10:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","3170A-001","Bremen - Hannover","<","Hannover-Linden/Fischerhof","Hannover Bismarckstraße",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-11-20",null,null,6,1]
[null,"DB InfraGO AG","1B3E9-005","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover-Waldheim",2026,2026,2,2,"2026-01-10","08:00:00","2026-01-10","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"1,7",1]
[null,"DB InfraGO AG","94C7-008","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2025,2025,19,19,"2025-05-05","04:00:00","2025-05-09","04:00:00","4d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2CCED-001","Bremen - Hannover",">","Langwedel","Achim",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2F2DB-002","Bremen - Hannover","< >","Letter                            (Abzw)","Wunstorf",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","2D9EC-006","Bremen - Hannover","<","Lindhorst (Schaumb-Lippe)","Wunstorf",2025,2025,11,11,"2025-03-12","21:00:00","2025-03-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"6,7",1]
[null,"DB InfraGO AG","2FF9A-001","Bremen - Hannover","<","Linsburg","Poggenhagen",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-06-28",null,null,"6,7",1]
[null,"DB InfraGO AG","2FD65-001","Bremen - Hannover","<","Neustadt a Rübenberge","Wunstorf",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","1E7DC-001","Bremen - Hannover","< >","Neustadt a Rübenberge","Hagen (Han)",2026,2026,42,42,"2026-10-17","23:05:00","2026-10-18","06:50:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","2CBCF-001","Bremen - Hannover",">","Nienburg (Weser)","Eystrup",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","2FC81-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","3201A-001","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2025,2025,13,13,"2025-03-25","21:00:00","2025-03-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB6B-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,7,7,"2026-02-13","11:00:00","2026-02-13","15:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB6C-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-03","10:00:00","2026-06-03","11:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB71-004","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,12,12,"2026-03-20","20:00:00","2026-03-22","05:00:00","1d, 9h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB74-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,38,"2026-09-07","14:00:00","2026-09-18","14:00:00","11d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","97F6-006","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2025,2025,20,20,"2025-05-17","22:45:00","2025-05-18","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","2CD6D-001","Bremen - Hannover",">","Poggenhagen","Linsburg",2025,2025,21,21,"2025-05-20","21:15:00","2025-05-21","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-05",null,null,"2,3",1]
[null,"DB InfraGO AG","2FA69-005","Bremen - Hannover","<","Rohrsen (b Nienburg)","Hagen (Han)",2025,2025,11,11,"2025-03-13","21:00:00","2025-03-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","324D5-003","Bremen - Hannover","< >","Rohrsen (b Nienburg)","Langwedel",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",4,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","31A44-001","Bremen - Hannover","<","Seelze Ost","Hannover-Hainholz",2025,2025,8,8,"2025-02-22","21:00:00","2025-02-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","77B6-001","Bremen - Hannover",">","Seelze West","Hannover-Linden Hafen",2025,2025,13,13,"2025-03-25","23:00:00","2025-03-27","01:00:00","1d, 2h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-08-05",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-007","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"3,4",1]
[null,"DB InfraGO AG","94E3-006","Bremen - Hannover",">","Verden (Aller)","Langwedel",2025,2025,21,22,"2025-05-23","23:00:00","2025-05-27","05:00:00","3d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","2CCE8-005","Bremen - Hannover",">","Verden (Aller)","Etelsen",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","2FA61-001","Bremen - Hannover","< >","Verden (Aller)","Rotenburg (Wümme)",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","324D4-003","Bremen - Hannover","< >","Verden (Aller)","Verden (Aller)",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","2FF68-003","Bremen - Hannover","< >","Wahnebergen","Etelsen",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","9820-005","Bremen - Hannover","< >","Wunstorf","Neustadt a Rübenberge",2025,2025,17,18,"2025-04-27","23:05:00","2025-04-28","04:25:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","2D0F5-003","Bremen - Hannover","< >","Wunstorf","Wunstorf",2025,2025,5,5,"2025-02-01","21:00:00","2025-02-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","2E9E2-002","Bremen - Hannover",">","Wunstorf","Gümmerwald",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-12-18",null,null,"4,5",1]
[null,"DB InfraGO AG","346F3-001","Bremen - Hannover",">","Wunstorf","Seelze Mitte",2025,2025,16,16,"2025-04-17","21:00:00","2025-04-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1CAFD-012","Bremen - Hannover","< >","Wunstorf","Letter                            (Abzw)",2026,2026,32,32,"2026-08-08","01:00:00","2026-08-08","03:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1CC41-020","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","04:30:00","2026-07-31","04:30:00","14d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","1CC41-023","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","21:00:00","2026-07-31","21:00:00","14d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","37474-002","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen-Burg",2025,2025,25,25,"2025-06-21","21:00:00","2025-06-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-004","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"5,6",1]
[null,"DB InfraGO AG","2E5A4-003","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Hbf",2025,2025,22,22,"2025-05-27","23:00:00","2025-05-28","05:00:00","0d, 6h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","2F565-002","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2025,2025,19,19,"2025-05-05","23:00:00","2025-05-06","05:00:00","0d, 6h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","37344-002","Bremerhaven - Bremen",">","Bremen Rbf Abzw","Osterholz-Scharmbeck",2025,2025,25,25,"2025-06-19","21:00:00","2025-06-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","214B7-010","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","320D8-003","Bremerhaven - Bremen",">","Bremen Rbf Ausfahrt","Bremen Rbf Abzw",2025,2025,12,12,"2025-03-22","21:00:00","2025-03-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1E35C-004","Bremerhaven - Bremen","<","Bremen Rbf Ausfahrt","Bremen Hbf",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-05","20:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","A467-004","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2025,2025,15,15,"2025-04-07","23:00:00","2025-04-11","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"Y",null,"2024-06-24",null,null,"1,2",1]
[null,"DB InfraGO AG","2F2F4-001","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E8C3-012","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,9,9,"2026-02-23","21:00:00","2026-02-27","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1F8D8-003","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","07:00:00","2026-09-22","15:30:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","18F6A-004","Bremerhaven - Bremen","< >","Bremerhaven-Lehe Abstellbahnhof","Bremerhaven Hbf",2025,2025,5,6,"2025-02-02","01:15:00","2025-02-09","06:15:00","7d, 5h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-002","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven Hbf",2026,2026,44,45,"2026-10-30","23:00:00","2026-11-03","05:00:00","3d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","2F5B9-003","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Stubben",2025,2025,11,11,"2025-03-11","21:00:00","2025-03-12","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-015","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,28,28,"2026-07-09","10:00:00","2026-07-11","05:00:00","1d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-08",null,null,"1,2",1]
[null,"DB InfraGO AG","22261-012","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,34,35,"2026-08-21","22:00:00","2026-08-25","06:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"2,3",1]
[null,"DB InfraGO AG","324DC-001","Bremerhaven - Bremen","<","Brh-Speckenbütt","Bremerhaven-Wulsdorf",2025,2025,20,20,"2025-05-17","21:00:00","2025-05-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","320D6-001","Bremerhaven - Bremen",">","Lübberstedt","Bremerhaven-Wulsdorf",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","A50D-003","Bremerhaven - Bremen","<","Oldenbüttel","Bremen-Burg",2025,2025,10,10,"2025-03-03","22:30:00","2025-03-07","04:30:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"20,20,20",null,null,null,"Y",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","2F831-003","Bremerhaven - Bremen","< >","Oldenbüttel","Stubben",2025,2025,19,19,"2025-05-07","21:00:00","2025-05-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1E70A-040","Bremerhaven - Bremen","<","Oldenbüttel","Bremen-Burg",2026,2026,11,11,"2026-03-09","23:00:00","2026-03-11","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","30D93-001","Bremerhaven - Bremen","<","Osterholz-Scharmbeck","Bremen Rbf Abzw",2025,2025,11,11,"2025-03-12","21:00:00","2025-03-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1E8C3-009","Bremerhaven - Bremen","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-20","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","3EBE0-001","Bremerhaven - Bremen",">","Stubben","Bremerhaven-Wulsdorf",2025,2025,25,25,"2025-06-19","23:00:00","2025-06-20","05:00:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-11",null,null,"6,7",1]
[null,"DB InfraGO AG","31B2A-004","Darmstadt - Nürnberg","< >","Aschaffenburg Hbf","Aschaffenburg Hbf Ausfahrt",2025,2025,8,9,"2025-02-23","21:00:00","2025-02-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","3623A-001","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Babenhausen (Hess)",2025,2025,23,23,"2025-06-02","21:00:00","2025-06-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"40,40,40",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1C34A-006","Darmstadt - Nürnberg","< >","Aschaffenburg Hbf","Aburg-Goldbach",2026,2026,20,21,"2026-05-16","23:00:00","2026-05-24","05:00:00","7d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","15C39-006","Darmstadt - Nürnberg","<","Aschaffenburg Hbf Einfahrt","Laufach",2025,2025,46,46,"2025-11-10","04:30:00","2025-11-10","05:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-01",null,null,"3,4",1]
[null,"DB InfraGO AG","39CE0-003","Darmstadt - Nürnberg","< >","Babenhausen (Hess)","Babenhausen (Hess)",2025,2025,25,25,"2025-06-19","21:00:00","2025-06-20","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","39FB9-016","Darmstadt - Nürnberg",">","Babenhausen (Hess)","Mainaschaff Steinerts",2025,2025,21,21,"2025-05-25","04:00:00","2025-05-25","05:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"28,28,28",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","30CCD-001","Darmstadt - Nürnberg",">","Bamberg","Breitengüßbach Süd",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","30D11-004","Darmstadt - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","30D30-002","Darmstadt - Nürnberg",">","Bamberg","Oberhaid",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","31EE2-004","Darmstadt - Nürnberg","< >","Bamberg","Hallstadt (b Bamberg)",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1FBAC-001","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","18:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","333F2-003","Darmstadt - Nürnberg","< >","Breitengüßbach Süd","Bamberg",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","36058-001","Darmstadt - Nürnberg",">","Darmstadt Gbf","Dieburg",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1C058-001","Darmstadt - Nürnberg","< >","Darmstadt Gbf","Darmstadt Nord",2026,2026,6,8,"2026-02-06","21:00:00","2026-02-20","05:00:00","13d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","A58D-014","Darmstadt - Nürnberg","<","Darmstadt Hbf","Weiterstadt",2025,2025,18,18,"2025-05-01","23:00:00","2025-05-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"21,21,21",null,null,null,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","331F0-002","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Bickenbach Nord",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","3329B-021","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Gbf",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","361CE-001","Darmstadt - Nürnberg",">","Darmstadt Hbf","Bickenbach Nord",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-26",null,null,"2,3",1]
[null,"DB InfraGO AG","36B34-002","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Hbf",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-27","23:00:00","3d, 2h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","3506-(MK26)-05","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,19,21,"14.05.2027","21:00:00","28.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","20C05-010","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt-Kranichstein",2026,2026,2,2,"2026-01-06","21:00:00","2026-01-09","05:00:00","2d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","20C05-011","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt Nord",2026,2026,2,2,"2026-01-06","21:00:00","2026-01-09","05:00:00","2d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","2D19F-004","Darmstadt - Nürnberg","< >","Darmstadt-Arheilgen","Darmstadt Hbf",2025,2025,13,13,"2025-03-29","21:00:00","2025-03-30","05:00:00","0d, 7h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","39BB6-001","Darmstadt - Nürnberg",">","Darmstadt-Arheilgen","Darmstadt Hbf",2025,2025,25,25,"2025-06-21","21:00:00","2025-06-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","184C1-005","Darmstadt - Nürnberg","< >","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2025,2025,14,15,"2025-04-05","13:30:00","2025-04-07","04:30:00","1d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","20C05-041","Darmstadt - Nürnberg",">","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,11,11,"2026-03-11","21:00:00","2026-03-13","07:00:00","1d, 10h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","36061-002","Darmstadt - Nürnberg",">","Dieburg","Kleinostheim",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"48,48,48",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","38E71-002","Darmstadt - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","04:45:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","30D23-001","Darmstadt - Nürnberg",">","Eggolsheim Süd","Strullendorf",2025,2025,6,6,"2025-02-08","21:00:00","2025-02-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-14",null,null,"1,7",1]
[null,"DB InfraGO AG","30C81-004","Darmstadt - Nürnberg","< >","Eltersdorf","Forchheim (Oberfr)",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","30E77-007","Darmstadt - Nürnberg","< >","Eltersdorf","Forchheim (Oberfr)",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"3,4",1]
[null,"DB InfraGO AG","20088-006","Darmstadt - Nürnberg","<","Eltersdorf","Vach",2026,2026,20,21,"2026-05-17","20:00:00","2026-05-18","04:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","30CCA-005","Darmstadt - Nürnberg","< >","Erlangen","Forchheim (Oberfr)",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"3,4",1]
[null,"DB InfraGO AG",0.31159999999999999,"Darmstadt - Nürnberg","< >","Erlangen","Forchheim (Oberfr)",2025,2025,16,16,"2025-04-15","21:00:00","2025-04-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","30C82-005","Darmstadt - Nürnberg","< >","Forchheim (Oberfr)","Forchheim (Oberfr)",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","30D25-003","Darmstadt - Nürnberg",">","Forchheim (Oberfr)","Eggolsheim Süd",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-11",null,null,"3,4",1]
[null,"DB InfraGO AG","31170-001","Darmstadt - Nürnberg","<","Forchheim (Oberfr)","Erlangen",2025,2025,24,24,"2025-06-10","21:00:00","2025-06-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","316BB-001","Darmstadt - Nürnberg","<","Forchheim (Oberfr)","Erlangen",2025,2025,8,8,"2025-02-20","21:05:00","2025-02-21","05:05:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG",3.688E-13,"Darmstadt - Nürnberg","< >","Forchheim (Oberfr)","Forchheim (Oberfr)",2025,2025,16,16,"2025-04-17","20:00:00","2025-04-18","06:00:00","0d, 10h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1DD19-003","Darmstadt - Nürnberg",">","Gädheim","Schweinfurt Hbf",2026,2026,30,30,"2026-07-22","21:00:00","2026-07-24","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","15E07-004","Darmstadt - Nürnberg","< >","Gemünden (Main)","Karlstadt (Main)",2025,2025,43,43,"2025-10-26","02:50:00","2025-10-26","04:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","2FDDB-001","Darmstadt - Nürnberg","<","Gemünden (Main)","Sterbfritz",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","20029-001","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2025,2026,50,13,"2025-12-14","08:00:00","2026-03-27","20:00:00","103d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","20029-023","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,27,27,"2026-06-30","08:00:00","2026-07-01","20:00:00","1d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","2037B-024","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,41,42,"2026-10-09","23:00:00","2026-10-13","20:00:00","3d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","221FC-005","Darmstadt - Nürnberg","< >","Gemünden (Main)","Wernfeld",2026,2026,47,50,"2026-11-21","21:00:00","2026-12-10","05:00:00","18d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","2EA77-001","Darmstadt - Nürnberg",">","Haßfurt","Schweinfurt Hbf",2025,2025,22,22,"2025-05-30","21:00:00","2025-05-31","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-08-08",null,null,"6,7",1]
[null,"DB InfraGO AG","31375-001","Darmstadt - Nürnberg","<","Höflein","Bamberg",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","2E52C-004","Darmstadt - Nürnberg","< >","Kleinostheim","Aschaffenburg Hbf",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-20",null,null,"1,7",1]
[null,"DB InfraGO AG","39174-002","Darmstadt - Nürnberg","<","Langenprozelten","Gemünden (Main)",2025,2025,24,25,"2025-06-15","21:15:00","2025-06-16","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO AG","2E2DA-006","Darmstadt - Nürnberg","< >","Laufach","Aschaffenburg Hbf Einfahrt",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","142E1-030","Darmstadt - Nürnberg","<","Lohr Bahnhof","Gemünden (Main)",2025,2025,43,43,"2025-10-21","03:10:00","2025-10-21","05:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"5,6",1]
[null,"DB InfraGO AG","318DB-001","Darmstadt - Nürnberg","<","Lohr Bahnhof","Gemünden (Main)",2025,2025,24,24,"2025-06-13","21:15:00","2025-06-14","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","319BA-003","Darmstadt - Nürnberg","< >","Lohr Bahnhof","Lohr Stadt",2025,2025,16,16,"2025-04-19","21:00:00","2025-04-20","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"1,7",1]
[null,"DB InfraGO AG","361FC-002","Darmstadt - Nürnberg","< >","Mainaschaff Steinerts","Mainaschaff Abzw",2025,2025,22,22,"2025-05-27","21:00:00","2025-05-28","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"1,2",1]
[null,"DB InfraGO AG","222AD-003","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Wernfeld",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-22","06:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-07",null,null,"3,4",1]
[null,"DB InfraGO AG","30C71-002","Darmstadt - Nürnberg","< >","Nür Jansenbr","Fürth (Bay) Gbf",2025,2025,9,9,"2025-03-01","21:00:00","2025-03-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1E4C5-005","Darmstadt - Nürnberg","< >","Nürnberg Großmarkt","Fürth (Bay) Gbf",2026,2026,31,32,"2026-07-30","05:00:00","2026-08-06","21:00:00","7d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","216FB-007","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nür Jansenbr",2026,2026,19,19,"2026-05-07","22:00:00","2026-05-08","03:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","3293-(MK27)-03","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,41,43,"15.10.2027","21:00:00","29.10.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1A391-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Mögeldorf",2025,2025,13,13,"2025-03-25","23:30:00","2025-03-26","04:50:00","0d, 5h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,",,10",null,null,null,"N",null,"2024-08-01",null,null,"3,4",1]
[null,"DB InfraGO AG","30CDA-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Gbf",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","30DBD-002","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Stein",2025,2025,7,7,"2025-02-13","21:15:00","2025-02-14","05:00:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-06-01",null,null,"1,2",1]
[null,"DB InfraGO AG","3206B-005","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-12",null,null,"2,3",1]
[null,"DB InfraGO AG","33E1D-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Dutzendteich",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","37255-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Schweinau",2025,2025,25,25,"2025-06-17","21:00:00","2025-06-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-05-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1FA7F-017","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,16,16,"2026-04-13","13:00:00","2026-04-13","18:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-021","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,16,17,"2026-04-13","18:00:00","2026-04-26","06:00:00","12d, 12h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-032","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,21,21,"2026-05-22","03:00:00","2026-05-22","07:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,4,1]
[null,"DB InfraGO AG","1FA90-035","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,21,22,"2026-05-22","22:00:00","2026-05-26","16:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-07-23",null,null,4,1]
[null,"DB InfraGO AG","1FA90-058","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","02:00:00","2d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1E5EA-004","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,41,42,"2026-10-08","05:00:00","2026-10-13","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","30E7B-001","Darmstadt - Nürnberg",">","Nürnberg-Reichelsdorf","Nürnberg Hbf",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-16",null,null,4,1]
[null,"DB InfraGO AG","1FA7F-004","Darmstadt - Nürnberg","<","Nürnberg-Schweinau","Nürnberg Hbf",2026,2026,14,14,"2026-04-03","22:00:00","2026-04-04","03:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-01",null,null,"4,5",1]
[null,"DB InfraGO AG","30DC0-001","Darmstadt - Nürnberg","<","Nürnberg-Stein","Nürnberg Hbf",2025,2025,19,19,"2025-05-08","21:15:00","2025-05-09","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-16",null,null,4,1]
[null,"DB InfraGO AG","3A46F-001","Darmstadt - Nürnberg","< >","Rödermark-Ober Roden","Dieburg",2025,2025,17,18,"2025-04-26","01:00:00","2025-04-28","04:30:00","2d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","2F9E8-002","Darmstadt - Nürnberg","<","Rohrbach","Nantenbach",2025,2025,19,19,"2025-05-07","21:10:00","2025-05-08","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","1DA02-008","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-01-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1DCD7-005","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,34,"2026-08-15","09:30:00","2026-08-18","10:30:00","3d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","13AAB-004","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2025,2025,41,42,"2025-10-12","19:00:00","2025-10-13","05:00:00","0d, 10h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","3367D-003","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2025,2025,6,6,"2025-02-08","21:15:00","2025-02-09","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"6,7",1]
[null,"DB InfraGO AG","2DF17-002","Darmstadt - Nürnberg","<","Stockstadt (Main)","Aschaffenburg Hbf",2025,2025,9,9,"2025-02-27","21:00:00","2025-02-28","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"1,7",1]
[null,"DB InfraGO AG","3605D-002","Darmstadt - Nürnberg","<","Stockstadt (Main)","Aschaffenburg Hbf",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","1A6F6-019","Darmstadt - Nürnberg","< >","Strullendorf","Strullend DB-Gr",2025,2025,43,44,"2025-10-26","21:00:00","2025-10-29","05:00:00","2d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","40973-003","Darmstadt - Nürnberg","< >","Strullendorf","Strullend DB-Gr",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","2E89C-004","Darmstadt - Nürnberg","< >","Vach","Fürth (Bay) Hbf",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","222AD-002","Darmstadt - Nürnberg","< >","Waigolshausen","Wernfeld",2026,2026,26,27,"2026-06-26","21:00:00","2026-06-30","06:00:00","3d, 9h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","2EB61-001","Darmstadt - Nürnberg",">","Waigolshausen","Rottendorf",2025,2025,10,10,"2025-03-07","21:15:00","2025-03-08","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1C08E-003","Darmstadt - Nürnberg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,18,19,"2026-05-02","21:00:00","2026-05-04","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-22",null,null,2,1]
[null,"DB InfraGO AG","34AC6-001","Darmstadt - Nürnberg","< >","Wernfeld","Gemünden (Main)",2025,2025,24,24,"2025-06-09","20:45:00","2025-06-10","04:45:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","2E5F7-002","Darmstadt - Nürnberg",">","Wiesthal","Aschaffenburg Hbf",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-08-12",null,null,"4,5",1]
[null,"DB InfraGO AG","38E7D-001","Darmstadt - Nürnberg",">","Zeil","Gädheim",2025,2025,14,14,"2025-04-03","21:10:00","2025-04-04","05:00:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","2E358-002","Darmstadt - Nürnberg","< >","Zollberg","Langenprozelten",2025,2025,14,14,"2025-04-01","20:50:00","2025-04-02","04:50:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","9C67-010","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2025,2025,46,46,"2025-11-13","08:50:00","2025-11-14","18:50:00","1d, 10h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","325FF-006","Dresden - Děčín",">","Bad Schandau","Bad Schandau",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","9A2C-008","Dresden - Děčín","< >","Bad Schandau Gr","Schöna",2025,2025,16,16,"2025-04-14","21:15:00","2025-04-16","04:15:00","1d, 7h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","9CE5-009","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2025,2025,49,50,"2025-12-03","04:00:00","2025-12-10","14:00:00","7d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","2A3A6-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,40,40,"2026-09-30","09:10:00","2026-10-04","17:10:00","4d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","2D627-005","Dresden - Děčín",">","Bad Schandau Ost","Königst (Sä) Üst",2025,2025,13,13,"2025-03-28","21:20:00","2025-03-29","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","20535-007","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau",2026,2026,1,5,"2026-01-03","04:00:00","2026-01-31","20:00:00","28d, 16h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","9C56-007","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2025,2025,45,45,"2025-11-06","21:00:00","2025-11-07","04:00:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","31259-001","Dresden - Děčín","<","Heidenau","Pirna",2025,2025,8,8,"2025-02-19","20:55:00","2025-02-20","04:40:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2025-01-06",null,null,"2,3",1]
[null,"DB InfraGO AG",3.3299999999999997E-11,"Dresden - Děčín","< >","Heidenau","Dresden-Reick",2025,2025,11,11,"2025-03-10","04:00:00","2025-03-13","04:00:00","3d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","36828-001","Dresden - Děčín",">","Kurort Rathen (Kr Pirna)","Pirna",2025,2025,25,25,"2025-06-18","21:15:00","2025-06-19","04:50:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20005-002","Dresden - Děčín","<","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,22,23,"2026-05-31","21:00:00","2026-06-05","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"1,6,7",1]
[null,"DB InfraGO AG","206F2-007","Dresden - Děčín","<","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,16,17,"2026-04-17","04:30:00","2026-04-25","21:00:00","8d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","A518-022","Dresden - Děčín","< >","Pirna","Heidenau",2025,2025,5,5,"2025-02-02","04:00:00","2025-02-02","22:00:00","0d, 18h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2F4D4-002","Dresden - Děčín","<","Pirna","Obervogelgesang",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","36828-005","Dresden - Děčín","<","Pirna","Kurort Rathen (Kr Pirna)",2025,2025,25,25,"2025-06-20","21:15:00","2025-06-21","04:50:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"4,5",1]
[null,"DB InfraGO AG","A518-023","Dresden - Děčín","< >","Pirna Gbf","Heidenau",2025,2025,5,5,"2025-02-02","04:00:00","2025-02-02","22:00:00","0d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1F543-018","Dresden - Děčín","< >","Rathmannsdorf(P)","Bad Schandau",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"5,6",1]
[null,"DB InfraGO AG","9C41-008","Dresden - Děčín",">","Schöna","Schöna",2025,2025,44,45,"2025-11-02","04:00:00","2025-11-06","21:00:00","4d, 17h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","2A2E0-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,16,21,"2026-04-13","09:10:00","2026-05-18","18:50:00","35d, 9h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","31092-004","Falkenberg - Dresden","<","Coswig (bei Dresden)","Priestewitz",2025,2025,8,8,"2025-02-18","21:00:00","2025-02-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","3994F-004","Falkenberg - Dresden","<","Coswig (bei Dresden)","Niederau",2025,2025,8,8,"2025-02-17","23:40:00","2025-02-19","04:20:00","1d, 4h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"2,3",1]
[null,"DB InfraGO AG","315F1-002","Falkenberg - Dresden","<","Elsterwerda","Rückersdorf                    (Niederl)",2025,2025,8,8,"2025-02-20","21:00:00","2025-02-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","41427-003","Falkenberg - Dresden","<","Elsterwerda","Gröditz (b Riesa)",2025,2025,12,12,"2025-03-21","23:30:00","2025-03-23","05:30:00","1d, 6h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","2D677-002","Falkenberg - Dresden","< >","Elsterwerda-Biehla","Falkenberg (Elster) unt Bf Stw W 15",2025,2025,5,5,"2025-02-01","21:00:00","2025-02-02","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1BF59-007","Falkenberg - Dresden","<","Kottewitz","Weinböhla",2026,2026,41,47,"2026-10-05","04:00:00","2026-11-19","20:00:00","45d, 17h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","313D9-003","Falkenberg - Dresden","<","Leckwitz","Zeithain Bogendreieck",2025,2025,8,8,"2025-02-19","21:00:00","2025-02-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","2EC9D-003","Falkenberg - Dresden",">","Oschatz","Riesa",2025,2025,6,6,"2025-02-08","21:00:00","2025-02-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-29",null,null,1,1]
[null,"DB InfraGO AG","2E793-001","Falkenberg - Dresden",">","Riesa","Zeithain Bogendreieck",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1CA98-009","Falkenberg - Dresden","< >","Riesa","Röderau Bogendreieck",2026,2026,21,30,"2026-05-19","09:00:00","2026-07-24","21:00:00","66d, 12h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO AG","8017-011","Falkenberg - Dresden","< >","Röderau","Zeithain Bogendreieck",2025,2025,2,11,"2025-01-06","00:40:00","2025-03-15","01:40:00","68d, 1h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-27",null,null,"3,4",1]
[null,"DB InfraGO AG","17173-015","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Leckwitz",2025,2025,50,50,"2025-12-09","00:01:00","2025-12-10","04:00:00","1d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-07",null,null,"1,7",1]
[null,"DB InfraGO AG","809D-010","Falkenberg - Dresden","< >","Zeithain Bogendreieck","Priestewitz",2025,2025,19,21,"2025-05-05","08:00:00","2025-05-23","16:00:00","18d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"3,4",1]
[null,"DB InfraGO AG","2FE56-005","Frankfurt - Karlsruhe","< >","Bashaide","Durmersheim",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","30061-002","Frankfurt - Karlsruhe","<","Bashaide","Karlsruhe Hbf Bft Südeinfahrt",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","1BAE4-005","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,21,22,"2026-05-24","05:00:00","2026-05-25","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1BAE4-019","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,28,50,"2026-07-10","05:00:00","2026-12-12","23:59:00","155d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","39BF3-003","Frankfurt - Karlsruhe",">","Bensheim-Auerbach","Hemsbach",2025,2025,25,25,"2025-06-20","21:00:00","2025-06-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","332A8-003","Frankfurt - Karlsruhe","< >","Bickenbach (Bergstr)","Darmstadt Hbf",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","2DDC1-002","Frankfurt - Karlsruhe",">","Blankenloch","Karlsruhe Hbf",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","300FB-001","Frankfurt - Karlsruhe","<","Blankenloch","Graben-Neudorf",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"4,5",1]
[null,"DB InfraGO AG","3207D-005","Frankfurt - Karlsruhe","< >","Blankenloch","Karlsruhe Hbf",2025,2025,22,22,"2025-05-26","21:00:00","2025-05-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","2DEEF-001","Frankfurt - Karlsruhe",">","Bruchsal","Graben-Neudorf",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-09",null,null,"4,5",1]
[null,"DB InfraGO AG","1154-(MK27)-02","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,1,6,"08.01.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-03",null,null,"5,6",1]
[null,"DB InfraGO AG","2DE6D-004","Frankfurt - Karlsruhe",">","Durmersheim","Rastatt",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","2E02A-001","Frankfurt - Karlsruhe","<","Ettlingen West","Karlsruhe Hbf",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-07",null,null,"1,7",1]
[null,"DB InfraGO AG","31A04-001","Frankfurt - Karlsruhe","<","Ettlingen West","Karlsruhe Hbf",2025,2025,12,12,"2025-03-22","21:00:00","2025-03-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-20",null,null,"6,7",1]
[null,"DB InfraGO AG","2DBEF-005","Frankfurt - Karlsruhe","<","Graben-Neudorf","Philippsburg Molzau",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"4,5",1]
[null,"DB InfraGO AG","2DEEF-005","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","2FE74-002","Frankfurt - Karlsruhe","<","Graben-Neudorf","Hockenheim",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-13",null,null,"6,7",1]
[null,"DB InfraGO AG","2FEF2-002","Frankfurt - Karlsruhe","<","Graben-Neudorf","Hockenheim",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-01",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-005","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Blankenloch",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"5,6",1]
[null,"DB InfraGO AG","1D4EB-002","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-06",null,null,"3,4",1]
[null,"DB InfraGO AG","2D025-005","Frankfurt - Karlsruhe","<","Heddesheim/Hirschberg","Weinheim (Bergstr) Hbf",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"6,7",1]
[null,"DB InfraGO AG","1E709-005","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1F4F8-019","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,7,7,"2026-02-12","23:00:00","2026-02-13","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4F8-024","Frankfurt - Karlsruhe",">","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,7,8,"2026-02-15","23:00:00","2026-02-17","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1F841-027","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,11,12,"2026-03-13","00:00:00","2026-03-20","05:00:00","7d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","31589-001","Frankfurt - Karlsruhe","<","Heidelberg-Wieblingen","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,24,24,"2025-06-12","21:00:00","2025-06-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","34B61-002","Frankfurt - Karlsruhe","<","Heidelberg-Wieblingen","Ladenburg",2025,2025,24,24,"2025-06-12","21:00:00","2025-06-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","32738-001","Frankfurt - Karlsruhe","<","Hemsbach","Bensheim-Auerbach",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","3625A-001","Frankfurt - Karlsruhe","<","Hemsbach","Bensheim-Auerbach",2025,2025,23,23,"2025-06-03","21:00:00","2025-06-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-20",null,null,"3,4",1]
[null,"DB InfraGO AG","332B2-003","Frankfurt - Karlsruhe","< >","Heppenheim (Bergstr)","Bensheim-Auerbach",2025,2025,15,15,"2025-04-08","21:00:00","2025-04-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,2",1]
[null,"DB InfraGO AG","2CEFF-002","Frankfurt - Karlsruhe",">","Heppenheim Nord","Hemsbach",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-20",null,null,7,1]
[null,"DB InfraGO AG","2DE64-007","Frankfurt - Karlsruhe","<","Hockenheim","Schwetzingen",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-20",null,null,"1,2",1]
[null,"DB InfraGO AG","30062-006","Frankfurt - Karlsruhe","<","Hockenheim","Schwetzingen",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-15",null,null,"1,2",1]
[null,"DB InfraGO AG","30066-002","Frankfurt - Karlsruhe","<","Hockenheim","Schwetzingen",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-20",null,null,"3,4",1]
[null,"DB InfraGO AG",1.7749999999999999E-7,"Frankfurt - Karlsruhe","<","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2025,2025,11,11,"2025-03-10","22:45:00","2025-03-11","00:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-03",null,null,"6,7",1]
[null,"DB InfraGO AG","2CB61-005","Frankfurt - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Dammerstock",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-08-11",null,null,"6,7",1]
[null,"DB InfraGO AG","345E8-006","Frankfurt - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2025,2025,23,23,"2025-06-04","21:00:00","2025-06-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2023-10-12",null,null,"6,7",1]
[null,"DB InfraGO AG","348EB-002","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","7FD2-015","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe-Durlach",2024,2025,50,40,"2024-12-15","00:00:00","2025-09-29","12:00:00","288d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","174F4-019","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Forchheim (b Karlsruhe)",2025,2025,7,7,"2025-02-10","03:55:00","2025-02-10","05:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","2DD3F-003","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Forchheim (b Karlsruhe)",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","2DF67-002","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","2EBCF-002","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,10,10,"2025-03-08","08:00:00","2025-03-08","16:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"1,2",1]
[null,"DB InfraGO AG","2FF24-002","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","30DAD-001","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Blankenloch",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","31A07-006","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Ettlingen West",2025,2025,24,24,"2025-06-14","21:00:00","2025-06-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","7FD2-024","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Durlach",2025,2025,31,31,"2025-07-31","05:00:00","2025-08-03","15:00:00","3d, 10h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","36555-005","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2025,2025,22,22,"2025-05-28","21:00:00","2025-05-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","4024B-005","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1E550-006","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Grötzingen",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"3,4",1]
[null,"DB InfraGO AG","3658-(MK26)-01","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,28,29,"16.07.2027","21:00:00","19.07.2027","05:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WE",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","2CE00-004","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Kar Hbf DB/Stadt",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"6,7",1]
[null,"DB InfraGO AG","30061-006","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf Bft Südeinfahrt","Bashaide",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-08-08",null,null,"1,7",1]
[null,"DB InfraGO AG","8930-001","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Weingarten (Baden)",2025,2025,30,30,"2025-07-21","04:00:00","2025-07-26","23:30:00","5d, 19h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","2E028-005","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-07",null,null,"3,4",1]
[null,"DB InfraGO AG","2E4CA-005","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Weingarten (Baden)",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-10-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","7FD2-026","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2025,2025,30,31,"2025-07-24","21:00:00","2025-07-31","05:00:00","6d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"2,3",1]
[null,"DB InfraGO AG","40766-020","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2025,2025,10,10,"2025-03-06","03:25:00","2025-03-06","04:25:00","0d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1E501-005","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-11-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E550-019","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1F08E-009","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-11",null,null,"1,2,3,5",1]
[null,"DB InfraGO AG","1F71F-004","Frankfurt - Karlsruhe","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2F36C-001","Frankfurt - Karlsruhe","<","Ladenburg","Heddesheim/Hirschberg",2025,2025,19,19,"2025-05-05","21:00:00","2025-05-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1F4F8-004","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,7,7,"2026-02-10","23:00:00","2026-02-11","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","1F55A-012","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,11,11,"2026-03-09","23:00:00","2026-03-10","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-23",null,null,"1,2",1]
[null,"DB InfraGO AG","2E345-003","Frankfurt - Karlsruhe","< >","Langen (Hess)","Darmstadt Hbf",2025,2025,10,10,"2025-03-03","22:00:00","2025-03-04","03:30:00","0d, 5h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-28",null,null,"6,7",1]
[null,"DB InfraGO AG","2D15E-002","Frankfurt - Karlsruhe","< >","Ludwigsburg","Bietigheim-Bissingen",2025,2025,17,17,"2025-04-26","21:00:00","2025-04-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-28",null,null,"6,7",1]
[null,"DB InfraGO AG","2E55E-002","Frankfurt - Karlsruhe","<","Ludwigsburg","Freiberg (Neckar)",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-10-28",null,null,"6,7",1]
[null,"DB InfraGO AG","2F77E-004","Frankfurt - Karlsruhe","< >","Ludwigsburg","Stuttgart-Zuffenhausen",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-28",null,null,"1,2,3",1]
[null,"DB InfraGO AG","31602-002","Frankfurt - Karlsruhe","< >","Ludwigsburg","Kornwestheim Rbf Nord-West",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-006","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,37,37,"2026-09-07","21:00:00","2026-09-11","05:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-009","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","2E86F-003","Frankfurt - Karlsruhe","<","Mannheim Rbf Gr D","Mannheim Ziehbrunnen",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-11",null,null,"3,4",1]
[null,"DB InfraGO AG","2E072-003","Frankfurt - Karlsruhe","<","Mannheim Rbf Gr K/Kn","Mannheim Ziehbrunnen",2025,2025,5,5,"2025-01-31","21:00:00","2025-02-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-11",null,null,"3,4",1]
[null,"DB InfraGO AG","30BC1-003","Frankfurt - Karlsruhe","< >","Mannheim Ziehbrunnen","Mannheim Unterwerk",2025,2025,8,8,"2025-02-18","21:00:00","2025-02-19","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","40DF3-003","Frankfurt - Karlsruhe",">","Mannheim-Rheinau","Schwetzingen",2025,2025,16,16,"2025-04-18","01:00:00","2025-04-18","02:30:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-04",null,null,"6,7",1]
[null,"DB InfraGO AG","2DC13-004","Frankfurt - Karlsruhe","<","M-Fr Südein/Ausf","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1F485-002","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"Y",null,"2024-11-18",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1F521-016","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-25","05:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F917-016","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,13,14,"2026-03-27","21:00:00","2026-04-03","05:00:00","6d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA57-005","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-24",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FAF2-010","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Hbf Ost",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1FAF2-020","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-29",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2CFE8-001","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,"3,4",1]
[null,"DB InfraGO AG","2DBFC-002","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Schwetzingen",2025,2025,5,5,"2025-02-01","21:00:00","2025-02-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-29",null,null,"4,5",1]
[null,"DB InfraGO AG","2E559-006","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-10",null,null,"3,4",1]
[null,"DB InfraGO AG","2E78E-002","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Hbf Ost",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-13",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","31586-003","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,1,1]
[null,"DB InfraGO AG","34B50-005","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-12-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2DBFA-004","Frankfurt - Karlsruhe","<","Philippsburg Molzau","Waghäusel",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-07",null,null,"1,7",1]
[null,"DB InfraGO AG","30BBD-002","Frankfurt - Karlsruhe","<","Philippsburg Molzau","Hockenheim",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-04",null,null,"6,7",1]
[null,"DB InfraGO AG","2DE63-002","Frankfurt - Karlsruhe",">","Schwetzingen","Hockenheim",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-13",null,null,"5,6",1]
[null,"DB InfraGO AG","30BC4-002","Frankfurt - Karlsruhe","<","Schwetzingen","Neu-Edingen/Mhm-Friedrichsfeld",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1772F-017","Frankfurt - Karlsruhe","<","Waghäusel","Hockenheim",2025,2025,10,10,"2025-03-07","01:55:00","2025-03-07","02:55:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-08",null,null,1,1]
[null,"DB InfraGO AG","2F22D-002","Frankfurt - Karlsruhe",">","Waghäusel","Graben-Neudorf",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-16",null,null,5,1]
[null,"DB InfraGO AG","2DBEF-003","Frankfurt - Karlsruhe",">","Waghäusel Saalbach","Graben-Neudorf",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-20",null,null,3,1]
[null,"DB InfraGO AG","1E501-007","Frankfurt - Karlsruhe",">","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-05",null,null,"2,3",1]
[null,"DB InfraGO AG",13.88,"Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe-Durlach",2025,2025,11,13,"2025-03-10","06:00:00","2025-03-28","06:00:00","18d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-12-17",null,null,"1,7",1]
[null,"DB InfraGO AG","1F485-010","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Hemsbach",2026,2026,6,6,"2026-02-03","23:00:00","2026-02-04","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-27",null,null,2,1]
[null,"DB InfraGO AG","1F841-004","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,3",1]
[null,"DB InfraGO AG","2F4CB-003","Frankfurt - Karlsruhe","<","Weinheim (Bergstr) Hbf","Hemsbach",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,7",1]
[null,"DB InfraGO AG","3372D-001","Frankfurt - Karlsruhe",">","Wörth (Rhein) Alte Bahnmeisterei","Karlsruhe Hbf Bft Südeinfahrt",2025,2025,13,13,"2025-03-25","21:00:00","2025-03-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2B42B-011","Hamburg - Magdeburg",">","Bad Bevensen","Deutsch Evern",2025,2025,10,10,"2025-03-04","01:00:00","2025-03-04","03:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-23",null,null,6,1]
[null,"DB InfraGO AG","2D083-001","Hamburg - Magdeburg",">","Bad Bevensen","Deutsch Evern",2025,2025,5,5,"2025-01-31","21:00:00","2025-02-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2C98B-010","Hamburg - Magdeburg","<","Bardowick","Lüneburg Gbf",2025,2025,6,7,"2025-02-07","20:00:00","2025-02-13","04:00:00","5d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-22",null,null,"6,7",1]
[null,"DB InfraGO AG","2ED37-002","Hamburg - Magdeburg",">","Bardowick","Stelle",2025,2025,14,15,"2025-04-06","21:00:00","2025-04-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D147-001","Hamburg - Magdeburg",">","Bienenbüttel","Lüneburg Gbf",2025,2025,9,9,"2025-03-01","21:00:00","2025-03-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-14",null,null,"1,2",1]
[null,"DB InfraGO AG","31AED-002","Hamburg - Magdeburg","< >","Bienenbüttel","Uelzen",2025,2025,8,9,"2025-02-23","21:00:00","2025-02-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-05-14",null,null,"1,2",1]
[null,"DB InfraGO AG","2CDE9-001","Hamburg - Magdeburg",">","Buchholz (Nordheide)","Maschen Rbf (Msof)",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,null,null,null,"1,6,7",1]
[null,"DB InfraGO AG","2DCE6-009","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E54-052","Hamburg - Magdeburg",">","Celle","Uelzen Gbf",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",6,6",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2D1B5-001","Hamburg - Magdeburg",">","Deutsch Evern","Lüneburg",2025,2025,17,17,"2025-04-26","21:00:00","2025-04-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2FA95-001","Hamburg - Magdeburg",">","Fallersleben","Weddel (Braunschw)",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2CDD0-001","Hamburg - Magdeburg",">","Hagen (Han)","Rohrsen (b Nienburg)",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","36C54-005","Hamburg - Magdeburg","< >","Hagen (Han)","Hagen (Han) Hp",2025,2025,18,18,"2025-05-03","21:05:00","2025-05-04","06:55:00","0d, 9h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-18",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2EA8B-004","Hamburg - Magdeburg","< >","Hamburg Unterelbe","Hamburg Unterelbe Seehafen",2025,2025,22,22,"2025-05-30","21:00:00","2025-05-31","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","172A6-004","Hamburg - Magdeburg","< >","Hamburg-Harburg","Hamburg Hbf",2025,2025,23,23,"2025-06-08","00:00:00","2025-06-08","07:00:00","0d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,6,1]
[null,"DB InfraGO AG","2DAAD-024","Hamburg - Magdeburg","<","Hamburg-Harburg","Buchholz (Nordheide)",2025,2025,15,15,"2025-04-07","22:00:00","2025-04-11","00:00:00","3d, 2h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"3,4,5",1]
[null,"DB InfraGO AG","2F91C-001","Hamburg - Magdeburg","<","Hamburg-Harburg","Maschen Pbf",2025,2025,23,23,"2025-06-04","21:00:00","2025-06-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO AG","30175-001","Hamburg - Magdeburg","<","Hamburg-Harburg","Buchholz (Nordheide)",2025,2025,7,8,"2025-02-16","21:00:00","2025-02-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO AG","36BA7-005","Hamburg - Magdeburg","<","Hamburg-Harburg","Maschen Pbf",2025,2025,6,6,"2025-02-09","02:00:00","2025-02-09","03:00:00","0d, 1h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","4036F-001","Hamburg - Magdeburg","<","Hamburg-Harburg","Maschen Pbf",2025,2025,24,24,"2025-06-11","01:00:00","2025-06-11","03:30:00","0d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3134F-002","Hamburg - Magdeburg","<","Hamburg-Hausbruch","Hamburg-Harburg",2025,2025,8,8,"2025-02-19","21:00:00","2025-02-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO AG","31488-001","Hamburg - Magdeburg","<","Hamburg-Rothenburgsort Ro","Hmb-Wlb Abzw",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1A813-004","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,33,"2026-08-03","07:00:00","2026-08-13","17:00:00","10d, 10h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-021","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt Grenze",2026,2026,34,34,"2026-08-22","00:25:00","2026-08-22","06:25:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","2E967-003","Hamburg - Magdeburg","<","Hmb H Schaar Süd","Süderelbbrücke",2025,2025,22,22,"2025-05-29","21:00:00","2025-05-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,7",1]
[null,"DB InfraGO AG","2E494-002","Hamburg - Magdeburg",">","Hmb-Wlb Abzw","Hamburg-Rothenburgsort Ro",2025,2025,10,10,"2025-03-04","21:00:00","2025-03-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","40C58-001","Hamburg - Magdeburg",">","Hoheneggelsen","Groß Gleidingen",2025,2025,22,22,"2025-05-27","23:15:00","2025-05-28","02:15:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-12-13",null,null,"5,6",1]
[null,"DB InfraGO AG","3268F-001","Hamburg - Magdeburg",">","Klein Süstedt","Uelzen",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-22",null,null,"3,4",1]
[null,"DB InfraGO AG","2C98B-015","Hamburg - Magdeburg",">","Lüneburg","Lüneburg Nordkopf",2025,2025,7,7,"2025-02-13","04:00:00","2025-02-13","16:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"5,6",1]
[null,"DB InfraGO AG","2D0C2-003","Hamburg - Magdeburg","< >","Lüneburg","Lüneburg",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","23082-002","Hamburg - Magdeburg","<","Lüneburg","Uelzen Gbf",2026,2026,28,50,"2026-07-10","21:00:00","2026-12-12","23:59:00","155d, 3h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-05-23",null,null,"1,2",1]
[null,"DB InfraGO AG","2D0C2-002","Hamburg - Magdeburg",">","Lüneburg Gbf","Bardowick",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-05-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1B978-018","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Hbf",2026,2026,9,9,"2026-02-26","03:00:00","2026-02-26","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1B992-010","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,12,12,"2026-03-16","03:00:00","2026-03-16","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","850A-007","Hamburg - Magdeburg","< >","Magdeburg Hbf","Dodendorf",2025,2025,32,32,"2025-08-09","12:30:00","2025-08-10","06:30:00","0d, 18h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"3,4",1]
[null,"DB InfraGO AG","1BE35-003","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"3,4",1]
[null,"DB InfraGO AG","1BD9D-005","Hamburg - Magdeburg","<","Magdeburg Südseite","Magdeburg Hbf",2026,2026,15,15,"2026-04-10","21:00:00","2026-04-11","17:00:00","0d, 20h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"3,4",1]
[null,"DB InfraGO AG","1B3F6-003","Hamburg - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2026,50,29,"2025-12-14","00:00:00","2026-07-18","10:00:00","216d, 9h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","86C2-007","Hamburg - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2025,2025,32,50,"2025-08-10","06:30:00","2025-12-13","23:59:00","125d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-24",null,null,"1,2,3",1]
[null,"DB InfraGO AG","40D33-001","Hamburg - Magdeburg",">","Magdeburg-Rothensee Bez Rmf (A-Gruppe)","Glindenberg",2025,2025,14,14,"2025-04-02","08:20:00","2025-04-02","14:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2CF55-004","Hamburg - Magdeburg","< >","Maschen Pbf","Ashausen Abzw",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E2B5-003","Hamburg - Magdeburg","<","Maschen Rbf (Mnwf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","23:00:00","2026-10-30","04:00:00","13d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"3,4",1]
[null,"DB InfraGO AG","93F5-015","Hamburg - Magdeburg","<","Meckelfeld","Stelle",2025,2025,5,5,"2025-02-01","00:00:00","2025-02-01","23:59:00","0d, 23h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","36BA7-001","Hamburg - Magdeburg","<","Meckelfeld","Meckelfeld",2025,2025,6,6,"2025-02-08","23:00:00","2025-02-09","05:00:00","0d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-05-31",null,null,"3,4",1]
[null,"DB InfraGO AG","3B607-035","Hamburg - Magdeburg","< >","Meckelfeld","Meckelfeld",2025,2025,24,24,"2025-06-10","04:00:00","2025-06-10","07:00:00","0d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2",1]
[null,"DB InfraGO AG","22C9E-030","Hamburg - Magdeburg",">","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,28,28,"2026-07-06","21:00:00","2026-07-08","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-18",null,null,"6,7",1]
[null,"DB InfraGO AG","3FF8D-001","Hamburg - Magdeburg","<","Medewitz (Mark)","Meinsdorf",2025,2025,23,23,"2025-06-04","23:00:00","2025-06-05","04:00:00","0d, 5h","Continuous","Catenary Inspection",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","40F48-005","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel Gbf",2025,2025,11,19,"2025-03-10","06:00:00","2025-05-05","05:00:00","55d, 22h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2023-12-14",null,null,3,1]
[null,"DB InfraGO AG","8853-006","Hamburg - Magdeburg","< >","Schnega","Wieren",2025,2025,9,10,"2025-02-28","21:00:00","2025-03-03","05:00:00","2d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"1,7",1]
[null,"DB InfraGO AG","3200C-001","Hamburg - Magdeburg","< >","Schnega","Wieren",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","20B8B-012","Hamburg - Magdeburg","< >","Schönebeck (Elbe) Gbf","Magdeburg-Neustadt",2026,2026,29,29,"2026-07-19","00:00:00","2026-07-19","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","30DEF-002","Hamburg - Magdeburg",">","Stelle","Maschen Rbf (Msof)",2025,2025,24,24,"2025-06-09","06:00:00","2025-06-09","14:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","315EA-001","Hamburg - Magdeburg","< >","Stelle","Lüneburg Nordkopf",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3A84D-010","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-17","02:00:00","0d, 2h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-05-21",null,null,"5,6,7",1]
[null,"DB InfraGO AG","22E54-036","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2026,2026,19,20,"2026-05-09","20:00:00","2026-05-11","06:00:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","B58E-001","Hamburg - Magdeburg","<","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2025,2025,10,10,"2025-03-03","07:30:00","2025-03-03","19:30:00","0d, 12h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"5,6,7",1]
[null,"DB InfraGO AG","14DE3-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Osterburg",2025,2025,14,14,"2025-04-01","08:30:00","2025-04-02","12:30:00","1d, 4h","Periodical",null,null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","21013-005","Hamburg - Magdeburg",">","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","08:00:00","2026-09-12","10:00:00","0d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2D22D-001","Hamburg - Magdeburg",">","Suderburg","Uelzen Gbf",2025,2025,9,10,"2025-03-02","21:00:00","2025-03-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO AG","B87F-007","Hamburg - Magdeburg","< >","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2025,2025,17,18,"2025-04-22","06:30:00","2025-05-02","21:00:00","10d, 14h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","2AE7D-012","Hamburg - Magdeburg","< >","Uelzen","Uelzen",2025,2025,8,10,"2025-02-22","00:00:00","2025-03-03","04:00:00","9d, 4h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO AG","2ED09-002","Hamburg - Magdeburg","< >","Uelzen","Bienenbüttel",2025,2025,14,15,"2025-04-06","21:00:00","2025-04-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO AG","2AE7D-010","Hamburg - Magdeburg","<","Uelzen Gbf","Veerßen",2025,2025,8,10,"2025-02-22","00:00:00","2025-03-03","04:00:00","9d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-06-06",null,null,"3,4",1]
[null,"DB InfraGO AG","348B2-001","Hamburg - Magdeburg",">","Uelzen Gbf","Bad Bevensen",2025,2025,12,13,"2025-03-23","21:00:00","2025-03-24","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-06-06",null,null,"1,7",1]
[null,"DB InfraGO AG","3600B-003","Hamburg - Magdeburg","< >","Uelzen Gbf","Bad Bevensen",2025,2025,6,7,"2025-02-09","21:00:00","2025-02-11","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","22E57-006","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,44,44,"2026-10-31","23:00:00","2026-11-01","05:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"4,5",1]
[null,"DB InfraGO AG","2ECF3-002","Hamburg - Magdeburg","< >","Waldhausen","Hannover-Wülfel",2025,2025,8,8,"2025-02-17","05:30:00","2025-02-17","13:30:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","2F81E-006","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Frellstedt",2025,2025,7,7,"2025-02-12","21:00:00","2025-02-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","8853-007","Hamburg - Magdeburg","< >","Wieren","Veerßen",2025,2025,13,14,"2025-03-29","17:00:00","2025-03-31","05:00:00","1d, 11h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2CF56-002","Hamburg - Magdeburg",">","Winsen (Luhe)","Maschen Pbf",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3AE81-005","Hamburg - Magdeburg","< >","Winsen (Luhe)","Winsen (Luhe)",2025,2025,25,25,"2025-06-17","23:30:00","2025-06-18","03:30:00","0d, 4h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3BC4F-001","Hannover - Magdeburg","< >","Barleben","Glindenberg",2025,2025,12,12,"2025-03-17","00:25:00","2025-03-21","04:00:00","4d, 3h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","7938-001","Hannover - Magdeburg",">","Braunschweig Hbf","Helmstedt",2024,2025,50,50,"2024-12-15","23:05:00","2025-12-13","04:30:00","362d, 5h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2024-05-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","39396-011","Hannover - Magdeburg",">","Braunschweig Hbf","Wolfenbüttel",2025,2025,14,14,"2025-04-02","23:45:00","2025-04-03","05:10:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-05-17",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2D0FC-004","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig-Buchhorst",2025,2025,13,13,"2025-03-29","21:00:00","2025-03-30","05:00:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2F6D1-004","Hannover - Magdeburg","< >","Braunschweig Schmiedekamp","Braunschweig Lünischteich",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6,7",1]
[null,"DB InfraGO AG","2F6D2-001","Hannover - Magdeburg","<","Braunschweig-Buchhorst","Braunschweig Hbf",2025,2025,11,11,"2025-03-11","21:00:00","2025-03-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,2,1]
[null,"DB InfraGO AG","87F2-027","Hannover - Magdeburg","< >","Frellstedt","Frellstedt",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-08","21:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","32523-001","Hannover - Magdeburg","<","Frellstedt","Königslutter",2025,2025,18,18,"2025-04-28","21:00:00","2025-04-29","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-25",null,null,7,1]
[null,"DB InfraGO AG","21340-007","Hannover - Magdeburg",">","Glindenberg","Zielitz",2026,2026,40,40,"2026-10-01","12:00:00","2026-10-01","20:30:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","2E362-003","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2025,2025,14,14,"2025-04-01","21:00:00","2025-04-02","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,7,1]
[null,"DB InfraGO AG","2F2D3-004","Hannover - Magdeburg","<","Groß Gleidingen","Peine",2025,2025,23,23,"2025-06-02","21:00:00","2025-06-03","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO AG","32266-005","Hannover - Magdeburg","< >","Groß Gleidingen","Groß Gleidingen",2025,2025,6,6,"2025-02-05","01:00:00","2025-02-05","05:00:00","0d, 4h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1A7F1-001","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,41,43,"2026-10-09","22:10:00","2026-10-19","05:00:00","9d, 6h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,2,1]
[null,"DB InfraGO AG","1F1C2-005","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2026,2026,37,37,"2026-09-08","06:30:00","2026-09-08","09:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3",1]
[null,"DB InfraGO AG","2FE71-003","Hannover - Magdeburg","< >","Hannover Hbf","Waldhausen",2025,2025,15,16,"2025-04-13","21:00:00","2025-04-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30C35-001","Hannover - Magdeburg",">","Hannover Hbf Pferdeturm","Hämelerwald",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-06-21",null,null,"3,4",1]
[null,"DB InfraGO AG","31ADF-001","Hannover - Magdeburg","<","Hannover-Linden","Waldhausen",2025,2025,12,12,"2025-03-22","22:45:00","2025-03-23","06:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-06-07",null,null,5,1]
[null,"DB InfraGO AG","31708-004","Hannover - Magdeburg",">","Hannover-Waldheim","Hannover-Linden/Fischerhof",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2ECF7-003","Hannover - Magdeburg","< >","Hannover-Wülfel","Hannover-Waldheim",2025,2025,22,22,"2025-05-31","23:30:00","2025-06-01","07:30:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,7",1]
[null,"DB InfraGO AG","87F2-010","Hannover - Magdeburg","<","Helmstedt","Königslutter",2025,2025,18,19,"2025-05-02","21:00:00","2025-05-05","06:10:00","2d, 9h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","2F81E-002","Hannover - Magdeburg","<","Königslutter","Schandelah",2025,2025,7,7,"2025-02-12","21:00:00","2025-02-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2E909-004","Hannover - Magdeburg",">","Lehrte","Hämelerwald",2025,2025,14,14,"2025-04-03","21:00:00","2025-04-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-02-06",null,null,"1,7",1]
[null,"DB InfraGO AG","2F5AB-011","Hannover - Magdeburg","<","Lehrte","Lehrte",2025,2025,19,19,"2025-05-06","21:00:00","2025-05-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30C36-006","Hannover - Magdeburg","< >","Lehrte","Lehrte",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","37424-002","Hannover - Magdeburg",">","Lehrte","Burgdorf",2025,2025,25,25,"2025-06-20","21:00:00","2025-06-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","8224-008","Hannover - Magdeburg","< >","Lehrte Nord","Lehrte West",2025,2025,46,46,"2025-11-14","23:00:00","2025-11-15","04:00:00","0d, 5h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,7",1]
[null,"DB InfraGO AG","2D5F0-001","Hannover - Magdeburg",">","Lehrte Nord","Ehlershausen",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"11,,11",null,null,null,"N",null,"2024-06-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","A633-008","Hannover - Magdeburg","<","Misburg","Hannover-Waldheim",2025,2025,23,23,"2025-06-06","11:00:00","2025-06-06","16:55:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1AA87-010","Hannover - Magdeburg","< >","Misburg","Hannover-Waldheim",2026,2026,20,20,"2026-05-11","21:00:00","2026-05-12","03:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-08",null,null,"1,7",1]
[null,"DB InfraGO AG","1A7F1-003","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,41,41,"2026-10-10","00:55:00","2026-10-10","03:20:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","8A3E-003","Hannover - Magdeburg","<","Peine Gbf","Hämelerwald",2025,2025,20,20,"2025-05-14","23:15:00","2025-05-16","05:10:00","1d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","203FF-019","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-17","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"1,2",1]
[null,"DB InfraGO AG","20409-032","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,38,39,"2026-09-18","21:00:00","2026-09-25","05:00:00","6d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-005","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,33,35,"2026-08-14","22:00:00","2026-08-28","22:00:00","14d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CBF8-010","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,42,43,"2026-10-17","21:30:00","2026-10-19","04:30:00","1d, 7h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","16918-008","Karlsruhe - München","< >","Amstetten (Württ)","Ulm Hbf Em Nord",2025,2025,22,22,"2025-05-26","05:00:00","2025-05-27","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","32068-001","Karlsruhe - München","<","Amstetten (Württ)","Geislingen (Steige)",2025,2025,16,16,"2025-04-17","21:00:00","2025-04-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-15",null,null,"2,3,4",1]
[null,"DB InfraGO AG","33DB7-011","Karlsruhe - München","< >","Amstetten (Württ)","Beimerstetten",2025,2025,10,10,"2025-03-07","21:00:00","2025-03-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,7",1]
[null,"DB InfraGO AG","222FB-040","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-02","05:00:00","2026-09-05","23:00:00","3d, 18h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3",1]
[null,"DB InfraGO AG","3325A-001","Karlsruhe - München",">","Augsburg Hbf","Westheim (Schwab)",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO AG","332CE-003","Karlsruhe - München","<","Augsburg Hbf","Augsburg-Hochzoll Abzweig",2025,2025,7,7,"2025-02-13","20:45:00","2025-02-14","04:45:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","39731-006","Karlsruhe - München","<","Augsburg Hbf","Augsburg-Hochzoll Abzweig",2025,2025,6,6,"2025-02-05","22:00:00","2025-02-05","23:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","3A4A3-001","Karlsruhe - München",">","Augsburg Hbf","Gessertshausen",2025,2025,18,18,"2025-05-02","21:00:00","2025-05-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3FDFA-011","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2025,13,13,"2025-03-25","03:30:00","2025-03-25","05:00:00","0d, 1h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO AG","1E029-015","Karlsruhe - München","< >","Augsburg Hbf","Mering Üst",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","33F06-002","Karlsruhe - München","< >","Augsburg-Hochzoll","Augsburg Hbf",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","2CAEB-001","Karlsruhe - München",">","Augsburg-Oberhausen","Gablingen",2025,2025,13,13,"2025-03-24","20:45:00","2025-03-25","04:35:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","1D705-011","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg Hirblinger Straße",2026,2026,23,25,"2026-06-01","00:30:00","2026-06-19","04:30:00","18d, 4h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E17F-005","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,21,21,"2026-05-20","23:30:00","2026-05-21","04:30:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"5,6,7"]
[null,"DB InfraGO AG","AB78-008","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2025,2025,41,41,"2025-10-06","21:00:00","2025-10-09","04:50:00","2d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2ECD3-008","Karlsruhe - München","< >","Beimerstetten","Ulm Hbf Bft Pbf",2025,2025,18,18,"2025-05-03","21:00:00","2025-05-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","31EAC-008","Karlsruhe - München","< >","Beimerstetten","Ulm Hbf Bft Pbf",2025,2025,24,24,"2025-06-10","21:00:00","2025-06-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21C52-007","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,3,4,"2026-01-17","12:00:00","2026-01-19","12:00:00","2d, 0h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-16",null,null,"1,7",1]
[null,"DB InfraGO AG","21CCE-004","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-28",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","7811-006","Karlsruhe - München",">","Bietigheim-Bissingen","Sersheim Aischbach",2025,2025,25,25,"2025-06-18","22:00:00","2025-06-19","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","124BB-039","Karlsruhe - München","<","Bietigheim-Bissingen","Ludwigsburg",2025,2025,37,37,"2025-09-11","00:20:00","2025-09-12","03:50:00","1d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2022-12-04",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","2F951-001","Karlsruhe - München",">","Bietigheim-Bissingen","Sachsenheim",2025,2025,7,7,"2025-02-12","21:00:00","2025-02-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-05",null,null,"6,7",1]
[null,"DB InfraGO AG","2F9B2-002","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2025,2025,15,15,"2025-04-09","21:00:00","2025-04-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","33C2A-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,18,18,"2025-04-28","21:00:00","2025-04-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-05",null,null,"5,6",1]
[null,"DB InfraGO AG","349E0-008","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","34A2D-002","Karlsruhe - München","<","Bietigheim-Bissingen","Ludwigsburg",2025,2025,24,24,"2025-06-13","21:00:00","2025-06-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"32,32,32",null,null,null,"N",null,"2022-12-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E12D-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"3,4",1]
[null,"DB InfraGO AG","1E622-010","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-12",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2EA6C-002","Karlsruhe - München","< >","Burgau (Schwab)","Dinkelscherben",2025,2025,22,22,"2025-05-30","21:00:00","2025-05-31","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-20",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","2EA6A-001","Karlsruhe - München",">","Dinkelscherben","Burgau (Schwab)",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-12-22",null,null,7,1]
[null,"DB InfraGO AG","2EB74-004","Karlsruhe - München","< >","Ebersbach (Fils)","Göppingen",2025,2025,6,6,"2025-02-07","21:00:00","2025-02-08","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","31306-001","Karlsruhe - München","<","Ebersbach (Fils)","Plochingen",2025,2025,24,24,"2025-06-11","21:00:00","2025-06-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-12-29",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","31405-003","Karlsruhe - München","<","Eislingen (Fils)","Göppingen",2025,2025,20,20,"2025-05-14","21:00:00","2025-05-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2023-01-03",null,null,"4,5",1]
[null,"DB InfraGO AG","A5A0-006","Karlsruhe - München","< >","Esslingen (Neckar)","Stuttgart-Obertürkheim",2025,2025,23,25,"2025-06-04","21:00:00","2025-06-16","16:00:00","11d, 19h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-03",null,null,"5,6",1]
[null,"DB InfraGO AG","31397-005","Karlsruhe - München","< >","Esslingen (Neckar)","Plochingen",2025,2025,12,12,"2025-03-19","21:00:00","2025-03-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-01-03",null,null,"1,7",1]
[null,"DB InfraGO AG","2EBBD-001","Karlsruhe - München",">","Freihalden Üst","Neuoffingen",2025,2025,18,18,"2025-05-03","21:00:00","2025-05-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-15",null,null,"5,6",1]
[null,"DB InfraGO AG","2E843-001","Karlsruhe - München",">","Freudenstein","Vaihingen (Enz)",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-08-30",null,null,7,1]
[null,"DB InfraGO AG","31237-001","Karlsruhe - München","<","Gauting","München-Pasing",2025,2025,12,12,"2025-03-18","21:00:00","2025-03-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","33E0E-001","Karlsruhe - München",">","Geislingen (Steige)","Amstetten (Württ)",2025,2025,14,14,"2025-04-04","21:00:00","2025-04-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-11",null,null,3,1]
[null,"DB InfraGO AG","32068-007","Karlsruhe - München","<","Geislingen West","Süßen",2025,2025,16,16,"2025-04-17","21:00:00","2025-04-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-01-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30FE1-006","Karlsruhe - München","< >","Gerlenhofen","Neu-Ulm",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-17",null,null,1,1]
[null,"DB InfraGO AG","33261-001","Karlsruhe - München",">","Gessertshausen","Freihalden Üst",2025,2025,14,14,"2025-04-03","21:00:00","2025-04-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","33263-001","Karlsruhe - München",">","Gessertshausen","Freihalden Üst",2025,2025,22,22,"2025-05-29","21:00:00","2025-05-30","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-20",null,null,"1,7",1]
[null,"DB InfraGO AG","2E996-006","Karlsruhe - München","< >","Gingen Süd","Amstetten (Württ)",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,1,1]
[null,"DB InfraGO AG","30EE0-003","Karlsruhe - München","<","Gingen Süd","Süßen",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-18",null,null,2,1]
[null,"DB InfraGO AG","1907B-019","Karlsruhe - München","< >","Glems","Vaihingen (Enz)",2025,2025,8,9,"2025-02-23","23:45:00","2025-02-24","01:15:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,7,1]
[null,"DB InfraGO AG","12848-013","Karlsruhe - München","<","Göppingen","Plochingen",2025,2025,22,22,"2025-05-27","01:00:00","2025-05-28","04:30:00","1d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-18",null,null,6,1]
[null,"DB InfraGO AG","2ECA9-005","Karlsruhe - München","< >","Göppingen","Gingen Süd",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,1,1]
[null,"DB InfraGO AG","20B87-008","Karlsruhe - München",">","Göppingen","Süßen",2026,2026,24,24,"2026-06-11","21:00:00","2026-06-12","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-02",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","7965-006","Karlsruhe - München","<","Günzburg","Neuoffingen",2025,2025,35,36,"2025-08-26","22:00:00","2025-09-07","04:00:00","11d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-07-26",null,null,"5,6",1]
[null,"DB InfraGO AG","31383-001","Karlsruhe - München","<","Günzburg","Neuoffingen",2025,2025,12,12,"2025-03-19","21:00:00","2025-03-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2023-07-17",null,null,"2,3",1]
[null,"DB InfraGO AG","32D1A-005","Karlsruhe - München",">","Günzburg","Unterfahlheim",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-17",null,null,"1,7",1]
[null,"DB InfraGO AG","9829-016","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2025,2025,12,12,"2025-03-19","22:00:00","2025-03-20","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-14",null,null,"3,6",1]
[null,"DB InfraGO AG","2F732-001","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-30",null,null,"1,7",1]
[null,"DB InfraGO AG","2F734-002","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2025,2025,15,15,"2025-04-08","21:00:00","2025-04-09","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-08-30",null,null,"5,6,7",1]
[null,"DB InfraGO AG","33900-001","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-08-30",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1DB29-010","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,2,1]
[null,"DB InfraGO AG","1EEEE-016","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2026,2026,25,27,"2026-06-15","22:30:00","2026-07-02","05:00:00","16d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-10-16",null,null,"5,6",1]
[null,"DB InfraGO AG","349B8-009","Karlsruhe - München","< >","km 3,6/6,8 (MOL)","Olching",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-16",null,null,7,1]
[null,"DB InfraGO AG","167B6-006","Karlsruhe - München","< >","Kornwestheim Pbf","Ludwigsburg",2025,2025,40,41,"2025-10-05","22:00:00","2025-10-06","04:00:00","0d, 6h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,2,1]
[null,"DB InfraGO AG","348FD-004","Karlsruhe - München","< >","Kornwestheim Rbf Nord-West","Ludwigsburg",2025,2025,20,20,"2025-05-16","21:00:00","2025-05-17","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1F188-011","Karlsruhe - München","< >","Kraichtal","Vaihingen (Enz)",2026,2026,35,36,"2026-08-29","23:00:00","2026-08-31","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,"4,5",1]
[null,"DB InfraGO AG","390D6-001","Karlsruhe - München","<","Langes Feld","Vaihingen (Enz)",2025,2025,5,6,"2025-02-02","23:00:00","2025-02-03","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-08",null,null,5,1]
[null,"DB InfraGO AG","3001A-002","Karlsruhe - München","<","Mammendorf","Olching",2025,2025,23,23,"2025-06-04","21:00:00","2025-06-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-15",null,null,"1,2,3",1]
[null,"DB InfraGO AG","332D5-003","Karlsruhe - München","< >","Mering","Augsburg Haunstetterstraße",2025,2025,11,11,"2025-03-10","20:45:00","2025-03-11","04:45:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-11-17",null,null,6,1]
[null,"DB InfraGO AG","30018-007","Karlsruhe - München","< >","Mering Üst","Olching",2025,2025,15,15,"2025-04-09","21:00:00","2025-04-10","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","332EC-005","Karlsruhe - München","< >","Mering Üst","Augsburg Haunstetterstraße",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-04-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","332FF-003","Karlsruhe - München","<","Mering Üst","München Nord Rbf Forstweg",2025,2025,23,23,"2025-06-07","21:00:00","2025-06-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-03-27",null,null,"3,4",1]
[null,"DB InfraGO AG","2FD6E-001","Karlsruhe - München",">","Mettertal","Vaihingen (Enz)",2025,2025,7,7,"2025-02-13","21:10:00","2025-02-14","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-05-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D6AE-011","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-25",null,null,"3,4",1]
[null,"DB InfraGO AG","1DB9A-015","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1DAD8-016","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"1,2",1]
[null,"DB InfraGO AG",8026178,"Karlsruhe - München","<","Mühlacker","Wilferdingen-Singen",2025,2025,11,11,"2025-03-11","22:00:00","2025-03-12","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-09",null,null,"1,2",1]
[null,"DB InfraGO AG","17C7E-012","Karlsruhe - München","< >","Mühlacker","Mühlacker",2025,2025,14,14,"2025-04-01","00:55:00","2025-04-02","04:10:00","1d, 3h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1869D-011","Karlsruhe - München",">","Mühlacker","Mühlacker Em Nord",2025,2025,38,38,"2025-09-16","00:45:00","2025-09-17","04:40:00","1d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","2F44D-002","Karlsruhe - München","<","Mühlacker Em Süd","Pforzheim Hbf",2025,2025,19,19,"2025-05-05","21:00:00","2025-05-06","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-27",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-018","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","15307-039","Karlsruhe - München","< >","München Hbf","München-Pasing",2025,2025,5,6,"2025-02-01","22:40:00","2025-02-03","04:40:00","1d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"2,3",1]
[null,"DB InfraGO AG","337D4-001","Karlsruhe - München","< >","München Hbf","Olching",2025,2025,7,7,"2025-02-10","22:40:00","2025-02-11","04:40:00","0d, 6h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","33F00-004","Karlsruhe - München","< >","München Hirschgarten","München-Pasing",2025,2025,16,17,"2025-04-18","22:40:00","2025-04-22","04:40:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","3545C-001","Karlsruhe - München","<","München Nord Rbf Forstweg","Mering Üst",2025,2025,24,24,"2025-06-09","21:00:00","2025-06-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","15307-056","Karlsruhe - München","< >","München-Neuhausen","München-Pasing",2025,2025,6,7,"2025-02-07","22:40:00","2025-02-15","04:40:00","7d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","15710-006","Karlsruhe - München","<","München-Pasing","München Hirschgarten",2025,2025,32,35,"2025-08-10","22:40:00","2025-08-28","04:40:00","17d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","31016-001","Karlsruhe - München",">","München-Pasing","Gauting",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","38D2F-012","Karlsruhe - München","<","München-Pasing","München Hackerbrücke",2025,2025,6,6,"2025-02-04","01:45:00","2025-02-07","03:40:00","3d, 1h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,",,3",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","349C4-002","Karlsruhe - München",">","München-Pasing Weiche 352","Mering Üst",2025,2025,21,21,"2025-05-19","21:10:00","2025-05-20","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-19",null,null,"5,6",1]
[null,"DB InfraGO AG","BBC9-003","Karlsruhe - München",">","Nersingen","Ulm Hbf Bft Pbf",2025,2025,16,23,"2025-04-18","21:00:00","2025-06-06","05:00:00","48d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","BBC9-005","Karlsruhe - München","< >","Nersingen","Neu-Ulm",2025,2025,16,23,"2025-04-18","21:00:00","2025-06-06","05:00:00","48d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1080-(MK27)-01","Karlsruhe - München",">","Neuoffingen","Neu-Ulm",2027,2027,13,19,"02.04.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-06-24",null,null,"5,6",1]
[null,"DB InfraGO AG","1F0BA-002","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,35,36,"2026-08-29","23:00:00","2026-09-04","05:00:00","5d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","2E99D-010","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2025,2025,10,10,"2025-03-06","21:00:00","2025-03-07","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO AG","2E99C-012","Karlsruhe - München",">","Neuoffingen","Günzburg",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO AG","BB6D-004","Karlsruhe - München","<","Neu-Ulm","Nersingen",2025,2025,23,28,"2025-06-06","21:00:00","2025-07-11","05:00:00","34d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-15",null,null,"6,7",1]
[null,"DB InfraGO AG","30FE1-012","Karlsruhe - München","< >","Neu-Ulm","Ulm Hbf Bft Pbf",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"6,7",1]
[null,"DB InfraGO AG","33F37-012","Karlsruhe - München","< >","Neu-Ulm","Ulm Hbf Bft Pbf",2025,2025,22,22,"2025-05-26","21:00:00","2025-05-27","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"1,7",1]
[null,"DB InfraGO AG","1E9AE-003","Karlsruhe - München","<","Olching","München-Lochhausen",2026,2026,25,25,"2026-06-15","23:00:00","2026-06-19","05:10:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","32E0A-004","Karlsruhe - München",">","Olching","Maisach Abzw",2025,2025,9,9,"2025-02-24","21:10:00","2025-02-25","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","34316-002","Karlsruhe - München",">","Olching","Mering Üst",2025,2025,17,17,"2025-04-21","21:10:00","2025-04-22","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","349B8-010","Karlsruhe - München","< >","Olching","Mammendorf",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","349C4-004","Karlsruhe - München",">","Olching","Maisach Abzw",2025,2025,21,21,"2025-05-19","21:10:00","2025-05-20","05:10:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-20",null,null,"3,4",1]
[null,"DB InfraGO AG","116DA-011","Karlsruhe - München","<","Pforzheim Hbf","Wilferdingen-Singen",2025,2025,19,19,"2025-05-09","23:00:00","2025-05-11","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"4,5",1]
[null,"DB InfraGO AG","2F466-001","Karlsruhe - München","<","Pforzheim Hbf","Wilferdingen-Singen",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"5,6",1]
[null,"DB InfraGO AG","337C7-002","Karlsruhe - München",">","Pforzheim Hbf","Mühlacker Em Süd",2025,2025,9,9,"2025-02-27","21:00:00","2025-02-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-13",null,null,"6,7",1]
[null,"DB InfraGO AG","33863-003","Karlsruhe - München","< >","Pforzheim Hbf","Pforzheim Hbf",2025,2025,21,21,"2025-05-23","21:00:00","2025-05-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-011","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3",1]
[null,"DB InfraGO AG","22ED4-001","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-07","20:00:00","13d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","22ED4-020","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"1,2",1]
[null,"DB InfraGO AG","EC11-015","Karlsruhe - München","<","Plochingen","Esslingen (Neckar)",2025,2025,13,13,"2025-03-27","03:00:00","2025-03-27","04:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","2D244-003","Karlsruhe - München",">","Plochingen","Wendlingen (Neckar)",2025,2025,21,22,"2025-05-25","21:00:00","2025-05-26","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","2E876-003","Karlsruhe - München","< >","Plochingen","Ebersbach (Fils)",2025,2025,14,14,"2025-04-03","21:00:00","2025-04-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","30003-006","Karlsruhe - München","< >","Plochingen","Plochingen",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","31410-003","Karlsruhe - München","< >","Plochingen","Plochingen",2025,2025,24,24,"2025-06-11","21:00:00","2025-06-12","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","9827-028","Karlsruhe - München",">","Sachsenheim","StrWe 4800/4842",2025,2025,46,46,"2025-11-12","22:00:00","2025-11-13","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-28",null,null,"1,7",1]
[null,"DB InfraGO AG","2CEDC-002","Karlsruhe - München","< >","Sachsenheim","Vaihingen (Enz)",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","2E567-001","Karlsruhe - München","<","Sachsenheim","Bietigheim-Bissingen",2025,2025,6,6,"2025-02-04","21:00:00","2025-02-05","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","9827-035","Karlsruhe - München",">","StrWe 4800/4842","Illingen (Württ)",2025,2025,17,17,"2025-04-23","22:00:00","2025-04-24","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","9827-049","Karlsruhe - München",">","StrWe 4800/4842","Illingen (Württ)",2025,2025,30,30,"2025-07-23","22:00:00","2025-07-24","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"3,4",1]
[null,"DB InfraGO AG","2EB72-008","Karlsruhe - München","< >","Stuttgart Nürnberger Straße Abzw","Stuttgart-Untertürkheim Pbf",2025,2025,18,18,"2025-05-02","21:00:00","2025-05-03","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","780D-006","Karlsruhe - München",">","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim Pbf",2025,2025,11,11,"2025-03-11","22:00:00","2025-03-12","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-06-26",null,null,"5,6",1]
[null,"DB InfraGO AG","780D-018","Karlsruhe - München",">","Stuttgart-Bad Cannstatt","Plochingen",2025,2025,38,38,"2025-09-16","22:00:00","2025-09-17","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-06-28",null,null,"6,7",1]
[null,"DB InfraGO AG","3574A-010","Karlsruhe - München","<","Stuttgart-Obertürkheim","Stuttgart Neckarpark",2025,2025,7,8,"2025-02-10","23:00:00","2025-02-21","04:00:00","10d, 5h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-11-07",null,null,"1,2",1]
[null,"DB InfraGO AG","2F783-006","Karlsruhe - München","< >","Stuttgart-Untertürkheim Gl 526-528","Stuttgart-Untertürkheim",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","3040-(MK27)-02","Karlsruhe - München",">","Stuttgart-Utürkhm Pbf","Kornwestheim Pbf",2027,2027,24,26,"19.06.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-08-14",null,null,"2,3",1]
[null,"DB InfraGO AG","12340-007","Karlsruhe - München","<","Stuttgart-Zazenhausen","Stuttgart-Münster",2025,2025,15,15,"2025-04-10","08:30:00","2025-04-11","10:30:00","1d, 2h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-05",null,null,"2,3",1]
[null,"DB InfraGO AG","310C0-002","Karlsruhe - München",">","Stuttgart-Zazenhausen","Stuttgart-Zazenhausen",2025,2025,8,8,"2025-02-18","21:00:00","2025-02-19","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2E024-003","Karlsruhe - München","< >","Stuttgart-Zuffenhausen","Ludwigsburg",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","30EDF-002","Karlsruhe - München","<","Süßen","Eislingen (Fils)",2025,2025,8,8,"2025-02-17","21:00:00","2025-02-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","31405-006","Karlsruhe - München","< >","Süßen","Eislingen (Fils)",2025,2025,20,20,"2025-05-14","21:00:00","2025-05-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","339DF-005","Karlsruhe - München","<","Ulm Hbf Bft Pbf","Nersingen",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"3,4",1]
[null,"DB InfraGO AG","36CEC-011","Karlsruhe - München","< >","Ulm Hbf Bft Pbf","Neu-Ulm",2025,2025,12,12,"2025-03-18","21:00:00","2025-03-19","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"4,5",1]
[null,"DB InfraGO AG","21C52-017","Karlsruhe - München","< >","Ulm-Örlingen","Beimerstetten",2026,2026,4,6,"2026-01-25","22:30:00","2026-02-06","04:30:00","11d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","BBEB-029","Karlsruhe - München",">","Unterfahlheim","Nersingen",2025,2025,41,42,"2025-10-11","05:00:00","2025-10-13","05:00:00","2d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","30ED7-010","Karlsruhe - München","< >","Unterfahlheim","Neu-Ulm",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","30ED8-010","Karlsruhe - München","< >","Unterfahlheim","Neu-Ulm",2025,2025,20,20,"2025-05-12","21:00:00","2025-05-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1E81C-014","Karlsruhe - München","< >","Vaihingen (Enz)","Langes Feld",2026,2026,16,17,"2026-04-18","23:00:00","2026-04-20","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","1E81C-015","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,16,17,"2026-04-18","23:00:00","2026-04-20","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-27",null,null,1,1]
[null,"DB InfraGO AG","1F188-008","Karlsruhe - München","<","Vaihingen (Enz)","Freudenstein",2026,2026,33,34,"2026-08-14","22:30:00","2026-08-21","05:00:00","6d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","A272-009","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-12","05:00:00","1d, 8h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-02",null,null,"1,7",1]
[null,"DB InfraGO AG","2CC4D-005","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,9,9,"2025-02-24","21:00:00","2025-02-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-08-02",null,null,"1,7",1]
[null,"DB InfraGO AG","2E842-003","Karlsruhe - München","<","Vaihingen (Enz)","Freudenstein",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",4,",null,null,null,"N",null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","2F99D-002","Karlsruhe - München","<","Vaihingen (Enz)","Sachsenheim",2025,2025,11,11,"2025-03-12","21:00:00","2025-03-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","31005-003","Karlsruhe - München",">","Vaihingen (Enz)","Illingen (Württ)",2025,2025,8,8,"2025-02-17","21:20:00","2025-02-18","05:10:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","331DC-001","Karlsruhe - München",">","Vaihingen (Enz)","Illingen (Württ)",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","33D1C-006","Karlsruhe - München",">","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,21,21,"2025-05-24","21:00:00","2025-05-25","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"1,2",1]
[null,"DB InfraGO AG","34AE8-002","Karlsruhe - München","<","Vaihingen (Enz)","Freudenstein",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"1,2",1]
[null,"DB InfraGO AG","3B021-007","Karlsruhe - München",">","Vaihingen (Enz)","Vaihingen (Enz)",2025,2025,8,8,"2025-02-17","21:20:00","2025-02-18","05:10:00","0d, 7h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-03",null,null,"1,2",1]
[null,"DB InfraGO AG","2E575-007","Karlsruhe - München","< >","Wendlingen (Neckar)","Plochingen",2025,2025,18,18,"2025-04-29","21:00:00","2025-04-30","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","22527-028","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,35,36,"2026-08-25","05:00:00","2026-09-01","21:00:00","7d, 16h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","33DB7-003","Karlsruhe - München",">","Westerstetten","Beimerstetten",2025,2025,10,10,"2025-03-07","21:00:00","2025-03-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-04",null,null,"2,3",1]
[null,"DB InfraGO AG",0.33250000000000002,"Karlsruhe - München","< >","Westheim (Schwab)","Augsburg Hbf",2025,2025,22,22,"2025-05-29","21:00:00","2025-05-30","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1E2B3-009","Karlsruhe - München","< >","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-11","22:00:00","2d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","2DF04-006","Karlsruhe - München","<","Wilferdingen-Singen","Karlsruhe-Durlach",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-09",null,null,"2,3",1]
[null,"DB InfraGO AG","31503-007","Karlsruhe - Strasbourg","< >","Achern","Offenburg",2025,2025,12,12,"2025-03-20","21:00:00","2025-03-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-03",null,null,"2,3",1]
[null,"DB InfraGO AG","39201-013","Karlsruhe - Strasbourg","< >","Achern","Achern DB/SWEG",2025,2025,12,13,"2025-03-23","23:00:00","2025-03-24","05:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","8D12-007","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2025,2025,33,33,"2025-08-11","22:00:00","2025-08-15","04:00:00","3d, 6h","Periodical",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","2E905-001","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2025,2025,18,18,"2025-05-01","21:00:00","2025-05-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","2E0A3-003","Karlsruhe - Strasbourg",">","Appenweier Nord","Offenburg",2025,2025,13,14,"2025-03-30","21:00:00","2025-03-31","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","321C4-004","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2025,2025,5,5,"2025-01-31","21:00:00","2025-02-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","9CE3-008","Karlsruhe - Strasbourg","< >","Appenweier-Muhrhaag","Appenweier Kurve",2025,2025,24,25,"2025-06-10","02:00:00","2025-06-17","04:00:00","7d, 2h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","A5CD-033","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt",2025,2025,16,17,"2025-04-20","23:00:00","2025-04-26","04:00:00","5d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","2E638-003","Karlsruhe - Strasbourg",">","Baden-Baden","Ottersweier",2025,2025,22,22,"2025-05-28","21:00:00","2025-05-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","31F0D-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"5,5,",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1E199-019","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","2CCAC-005","Karlsruhe - Strasbourg",">","Forchheim (b Karlsruhe)","Durmersheim",2025,2025,9,9,"2025-02-25","21:00:00","2025-02-26","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","2EBE8-001","Karlsruhe - Strasbourg",">","Kehl","Kehl Grenze",2025,2025,10,11,"2025-03-09","21:00:00","2025-03-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-008","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,3,4,"2026-01-16","22:00:00","2026-01-19","05:00:00","2d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-002","Karlsruhe - Strasbourg","< >","Kehl","Kork",2026,2026,10,11,"2026-03-04","05:00:00","2026-03-09","08:00:00","5d, 3h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-018","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,23,26,"2026-06-06","22:00:00","2026-06-26","05:00:00","19d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-027","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,29,29,"2026-07-13","22:00:00","2026-07-19","05:00:00","5d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","310E2-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kork",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","139FD-011","Karlsruhe - Strasbourg",">","Kork","Kehl",2025,2025,47,48,"2025-11-22","22:00:00","2025-11-24","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-002","Karlsruhe - Strasbourg","< >","Kork","Kehl",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-029","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,9,9,"2026-02-23","22:00:00","2026-02-25","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","3175A-004","Karlsruhe - Strasbourg","< >","Muggensturm","Rastatt",2025,2025,8,8,"2025-02-21","21:00:00","2025-02-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","339A5-006","Karlsruhe - Strasbourg","< >","Muggensturm Badesee","Karlsruhe Hbf",2025,2025,18,18,"2025-04-28","21:00:00","2025-04-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","31505-001","Karlsruhe - Strasbourg","<","Offenburg","Achern",2025,2025,20,20,"2025-05-15","21:00:00","2025-05-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","190D1-010","Karlsruhe - Strasbourg","<","Önsbach","Ottersweier",2025,2025,13,13,"2025-03-28","22:55:00","2025-03-29","00:05:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","2DE70-001","Karlsruhe - Strasbourg",">","Ötigheim","Rastatt",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","2FE57-001","Karlsruhe - Strasbourg","<","Ötigheim","Bashaide",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E034-017","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1E034-024","Karlsruhe - Strasbourg","< >","Ottersweier","Achern (F)",2026,2026,21,22,"2026-05-22","21:00:00","2026-05-26","05:00:00","3d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","190D1-004","Karlsruhe - Strasbourg","< >","Ottersweier","Offenburg Ülp südl Esig",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"4,4,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","2DEF4-006","Karlsruhe - Strasbourg","< >","Ottersweier","Rastatt-Süd",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"7,7,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","2E637-004","Karlsruhe - Strasbourg","< >","Ottersweier","Baden-Baden",2025,2025,18,18,"2025-04-30","21:00:00","2025-05-01","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","31A09-001","Karlsruhe - Strasbourg","<","Ottersweier","Baden-Baden",2025,2025,12,12,"2025-03-22","21:00:00","2025-03-23","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-05",null,null,"5,6",1]
[null,"DB InfraGO AG","32F2B-003","Karlsruhe - Strasbourg",">","Ottersweier","Appenweier",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"5,6",1]
[null,"DB InfraGO AG","1F43D-011","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","A5CD-019","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2025,2025,18,19,"2025-05-03","21:00:00","2025-05-05","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","17EF1-002","Karlsruhe - Strasbourg","<","Rastatt","Ötigheim",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-18","04:00:00","1d, 7h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","2FC91-001","Karlsruhe - Strasbourg","<","Rastatt","Ötigheim",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-12",null,null,"5,6",1]
[null,"DB InfraGO AG","30C7D-001","Karlsruhe - Strasbourg","<","Rastatt","Sandweier",2025,2025,10,10,"2025-03-03","21:00:00","2025-03-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","33471-001","Karlsruhe - Strasbourg","< >","Rastatt","Kuppenheim",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","36AFF-002","Karlsruhe - Strasbourg","<","Rastatt","Ötigheim",2025,2025,24,25,"2025-06-15","21:00:00","2025-06-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","40033-034","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2025,2025,17,18,"2025-04-27","22:00:00","2025-04-29","04:30:00","1d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","2DEF3-001","Karlsruhe - Strasbourg",">","Rastatt-Süd","Ottersweier",2025,2025,9,9,"2025-02-27","21:00:00","2025-02-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","30C7C-003","Karlsruhe - Strasbourg","< >","Sandweier","Rastatt",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","2F88A-002","Magdeburg - Falkenberg","< >","Annaburg","Falkenberg (Elster) unt Bf Stw W 26",2025,2025,15,15,"2025-04-09","21:00:00","2025-04-10","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"6,7",1]
[null,"DB InfraGO AG","1F22B-001","Magdeburg - Falkenberg","<","Coswig (Anh) Gbf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,14,14,"2026-03-30","22:00:00","2026-04-01","06:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-15",null,null,"6,7",1]
[null,"DB InfraGO AG","2D653-004","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2025,2025,5,5,"2025-01-31","21:00:00","2025-02-01","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"6,7",1]
[null,"DB InfraGO AG","41260-004","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2025,2025,17,17,"2025-04-26","20:00:00","2025-04-27","02:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"6,7",1]
[null,"DB InfraGO AG","80C1-004","Magdeburg - Falkenberg",">","Falkenberg (Elster) unt Bf Stw W 26","Lutherstadt Wittenberg Hbf",2025,2025,18,19,"2025-05-02","21:00:00","2025-05-09","05:00:00","6d, 8h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-04",null,null,"6,7",1]
[null,"DB InfraGO AG","3D9AC-005","Magdeburg - Falkenberg","< >","Güterglück","Rodleben",2025,2025,5,6,"2025-02-02","23:00:00","2025-02-04","05:00:00","1d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","21D6E-001","Magdeburg - Falkenberg","< >","Herzberg (Elster)","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,16,17,"2026-04-17","07:00:00","2026-04-20","15:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,7",1]
[null,"DB InfraGO AG","1F26D-011","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,18,18,"2026-04-28","20:00:00","2026-04-29","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-03",null,null,"1,2",1]
[null,"DB InfraGO AG","2F4B2-002","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Jessen (Elster)",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","2F47A-003","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg-Piesteritz","Lutherstadt Wittenberg Hbf",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"2,3",1]
[null,"DB InfraGO AG","2F35F-002","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2025,2025,7,7,"2025-02-10","21:00:00","2025-02-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-28",null,null,"2,3",1]
[null,"DB InfraGO AG","2FAC7-003","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,1,1]
[null,"DB InfraGO AG","21CBB-004","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,2",1]
[null,"DB InfraGO AG","2D359-004","Magdeburg - Falkenberg","< >","Trebnitz Strw","Lutherstadt Wittenberg-Piesteritz",2025,2025,42,42,"2025-10-18","22:00:00","2025-10-19","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2",1]
[null,"DB InfraGO AG","9070-025","München - Salzburg","< >","Bad Endorf (Oberbay)","Rottau",2025,2025,31,31,"2025-08-01","21:00:00","2025-08-03","05:00:00","1d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","3417D-002","München - Salzburg","< >","Bad Endorf (Oberbay)","Landl (Oberbay) Abzw",2025,2025,14,14,"2025-04-03","21:15:00","2025-04-04","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","32C4B-001","München - Salzburg","<","Freilassing","Teisendorf",2025,2025,8,8,"2025-02-20","21:15:00","2025-02-21","05:15:00","0d, 8h","Continuous",null,null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-15",null,null,"2,3",1]
[null,"DB InfraGO AG","34FFA-001","München - Salzburg",">","Freilassing","Salzburg Liefering",2025,2025,14,14,"2025-04-03","21:20:00","2025-04-04","05:20:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,81,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1E20A-002","München - Salzburg","< >","Freilassing","Salzburg Grenze",2026,2026,6,6,"2026-02-04","23:50:00","2026-02-05","04:15:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,81,"N",null,"2024-07-12",null,null,"3,4",1]
[null,"DB InfraGO AG","14F5F-001","München - Salzburg",">","Grafing Bahnhof","Grafing Bahnhof",2025,2025,45,45,"2025-11-08","23:50:00","2025-11-09","01:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","34FF9-003","München - Salzburg","<","Grafing Bahnhof","Zorneding",2025,2025,17,17,"2025-04-22","21:15:00","2025-04-23","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","35472-003","München - Salzburg",">","Grafing Bahnhof","Ostermünchen",2025,2025,22,22,"2025-05-31","21:15:00","2025-06-01","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"15,15,15",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1D73C-001","München - Salzburg","< >","Haar","Aßling (Oberbay)",2026,2026,2,2,"2026-01-09","22:15:00","2026-01-10","05:15:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","318E0-002","München - Salzburg","< >","Hufschlag Abzw","Hufschlag",2025,2025,24,24,"2025-06-13","21:15:00","2025-06-14","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","350B5-001","München - Salzburg",">","Landl (Oberbay) Abzw","Bad Endorf (Oberbay)",2025,2025,22,22,"2025-05-29","21:15:00","2025-05-30","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E076-015","München - Salzburg",">","Landl (Oberbay) Abzw","Simssee",2026,2026,3,3,"2026-01-12","07:00:00","2026-01-13","21:00:00","1d, 14h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","32C5F-001","München - Salzburg","<","Lauter","Rumgraben",2025,2025,8,8,"2025-02-21","21:00:00","2025-02-22","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-26",null,null,"5,6",1]
[null,"DB InfraGO AG","39BC0-001","München - Salzburg",">","München Isartor","München Ost Pbf",2025,2025,10,10,"2025-03-08","04:00:00","2025-03-09","15:40:00","1d, 11h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-08-08",null,null,"5,6",1]
[null,"DB InfraGO AG","3330B-027","München - Salzburg",">","München Leuchtenbergring","München-Trudering",2025,2025,20,20,"2025-05-13","22:20:00","2025-05-14","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-11",null,null,"6,7",1]
[null,"DB InfraGO AG","39C7A-019","München - Salzburg","< >","München Leuchtenbergring","München Ost Pbf",2025,2025,11,11,"2025-03-10","21:40:00","2025-03-13","04:20:00","2d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"6,7",1]
[null,"DB InfraGO AG","1D73C-011","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,2,3,"2026-01-11","22:30:00","2026-01-12","05:30:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD6A-008","München - Salzburg",">","München Ost Pbf","München Ost Pbf",2026,2026,22,23,"2026-05-29","04:30:00","2026-06-03","14:00:00","5d, 9h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"6,7",1]
[null,"DB InfraGO AG","2C0D3-011","München - Salzburg","< >","München Ost Pbf","München-Giesing",2025,2025,6,8,"2025-02-03","21:40:00","2025-02-21","04:20:00","17d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","2C0D3-019","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,6,8,"2025-02-03","21:40:00","2025-02-21","04:20:00","17d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","329C6-014","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,13,13,"2025-03-27","21:40:00","2025-03-28","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"2,3",1]
[null,"DB InfraGO AG","329C6-025","München - Salzburg","<","München Ost Pbf","München Isartor",2025,2025,13,13,"2025-03-27","21:40:00","2025-03-28","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","32CC1-028","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,14,14,"2025-04-03","21:40:00","2025-04-04","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","32EE3-012","München - Salzburg","< >","München Ost Pbf","München Isartor",2025,2025,22,22,"2025-05-29","21:40:00","2025-05-30","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","32F48-013","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2025,2025,25,25,"2025-06-19","21:40:00","2025-06-20","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","34D11-005","München - Salzburg","<","München Ost Pbf","München Isartor",2025,2025,13,13,"2025-03-25","22:20:00","2025-03-26","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","39A86-021","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2025,2025,10,10,"2025-03-03","21:40:00","2025-03-06","04:20:00","2d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","39C7A-013","München - Salzburg","< >","München Ost Pbf","München Leuchtenbergring",2025,2025,11,11,"2025-03-10","21:40:00","2025-03-13","04:20:00","2d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","3FB26-002","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","3345A-011","München - Salzburg","< >","München Ost Riedenburger Straße","München Ost Pbf",2025,2025,11,12,"2025-03-15","14:00:00","2025-03-17","05:00:00","1d, 15h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","787A-010","München - Salzburg","< >","München Süd","München Süd",2025,2025,47,48,"2025-11-23","00:00:00","2025-11-25","06:00:00","2d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","2C0D3-020","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2025,2025,6,8,"2025-02-03","21:40:00","2025-02-21","04:20:00","17d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","32CC1-038","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2025,2025,14,14,"2025-04-03","21:40:00","2025-04-04","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","39A86-008","München - Salzburg","< >","München-Berg am Laim Abzw","München-Trudering",2025,2025,10,10,"2025-03-03","21:40:00","2025-03-06","04:20:00","2d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2C165-008","München - Salzburg","< >","München-Giesing","München Ost Pbf",2025,2025,7,7,"2025-02-10","21:40:00","2025-02-12","04:20:00","1d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","2FA2E-006","München - Salzburg","<","München-Riem Pbf","München Ost Pbf",2025,2025,15,15,"2025-04-10","20:50:00","2025-04-11","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-08-14",null,null,"1,2",1]
[null,"DB InfraGO AG","2FA2E-005","München - Salzburg","<","München-Riem West","München Ost Pbf",2025,2025,15,15,"2025-04-10","20:50:00","2025-04-11","04:50:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-08-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1A453-001","München - Salzburg","<","München-Solln","Mü Heimeranplatz",2025,2025,17,18,"2025-04-25","22:00:00","2025-04-30","06:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-08-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1BDEC-007","München - Salzburg",">","München-Trudering","München-Berg am Laim Abzw",2025,2025,41,42,"2025-10-09","21:40:00","2025-10-17","04:40:00","7d, 7h","Periodical",null,null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-14",null,null,"5,6",1]
[null,"DB InfraGO AG","3229D-008","München - Salzburg",">","München-Trudering","Grafing Bahnhof",2025,2025,15,15,"2025-04-10","22:00:00","2025-04-11","05:00:00","0d, 7h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","35386-003","München - Salzburg","< >","München-Trudering","Zorneding",2025,2025,24,24,"2025-06-14","21:15:00","2025-06-15","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-08",null,null,"2,3",1]
[null,"DB InfraGO AG","3B4CB-021","München - Salzburg","<","München-Trudering","München Leuchtenbergring",2025,2025,6,8,"2025-02-03","21:40:00","2025-02-21","04:20:00","17d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1DCCA-001","München - Salzburg","< >","Ostermünchen","Ostermünchen",2026,2026,5,5,"2026-01-30","23:50:00","2026-01-31","05:00:00","0d, 5h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","316D1-001","München - Salzburg","<","Ostermünchen","Grafing Bahnhof",2025,2025,12,12,"2025-03-20","21:20:00","2025-03-21","05:20:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","1E132-008","München - Salzburg",">","Prien a Chiemsee","Rottau",2026,2026,6,6,"2026-02-04","07:00:00","2026-02-06","21:00:00","2d, 14h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-19",null,null,"4,5",1]
[null,"DB InfraGO AG","30ABC-002","München - Salzburg","< >","Prien a Chiemsee","Aschau (Chiemgau)",2025,2025,6,6,"2025-02-04","21:15:00","2025-02-05","05:15:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-09",null,null,6,1]
[null,"DB InfraGO AG","1D8FC-002","München - Salzburg","< >","Rosenheim","Rosenheim",2026,2026,3,3,"2026-01-15","23:55:00","2026-01-16","04:50:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,"6,7",1]
[null,"DB InfraGO AG","31432-001","München - Salzburg","<","Rosenheim","Ostermünchen",2025,2025,20,20,"2025-05-14","21:20:00","2025-05-15","05:20:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-02",null,null,"2,3",1]
[null,"DB InfraGO AG","3450C-003","München - Salzburg",">","Rosenheim","Brannenburg",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-05",null,null,"1,6,7",1]
[null,"DB InfraGO AG","39143-001","München - Salzburg",">","Rosenheim","Raubling",2025,2025,25,25,"2025-06-19","21:00:00","2025-06-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-14",null,null,"1,2",1]
[null,"DB InfraGO AG","9070-001","München - Salzburg","<","Rottau","Prien a Chiemsee",2025,2025,31,33,"2025-08-03","05:00:00","2025-08-11","06:00:00","8d, 1h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-06",null,null,"1,7",1]
[null,"DB InfraGO AG","33B5E-001","München - Salzburg","< >","Rückstetten","Freilassing",2025,2025,5,7,"2025-01-29","03:00:00","2025-02-14","04:00:00","16d, 1h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","30AAB-001","München - Salzburg",">","Rumgraben","Lauter",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-09-16",null,null,"1,7",1]
[null,"DB InfraGO AG","183D3-004","München - Salzburg","<","Simssee","Rosenheim",2025,2025,45,45,"2025-11-04","00:40:00","2025-11-04","01:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-20",null,null,1,1]
[null,"DB InfraGO AG","2E342-004","München - Salzburg","< >","Simssee","Rosenheim Ost",2025,2025,18,18,"2025-04-28","21:20:00","2025-04-29","05:20:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-09-27",null,null,7,1]
[null,"DB InfraGO AG","2E590-002","München - Salzburg","< >","Teisendorf","Lauter",2025,2025,18,18,"2025-04-29","21:20:00","2025-04-30","05:20:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-10-09",null,null,6,1]
[null,"DB InfraGO AG","318DE-001","München - Salzburg","<","Teisendorf","Traunstein",2025,2025,16,16,"2025-04-18","21:15:00","2025-04-19","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-10-04",null,null,7,1]
[null,"DB InfraGO AG","34D26-003","München - Salzburg",">","Teisendorf","Freilassing",2025,2025,18,18,"2025-04-30","21:20:00","2025-05-01","05:20:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-10-15",null,null,"1,2",1]
[null,"DB InfraGO AG","90F3-002","München - Salzburg","< >","Übersee","Rumgraben",2025,2025,12,13,"2025-03-21","21:00:00","2025-03-30","05:00:00","8d, 7h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-10-15",null,null,"1,2",1]
[null,"DB InfraGO AG","316CA-001","München - Salzburg","<","Übersee","Prien a Chiemsee",2025,2025,24,24,"2025-06-12","21:15:00","2025-06-13","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-15",null,null,"2,3",1]
[null,"DB InfraGO AG","3158D-002","München - Salzburg","< >","Zorneding","Grafing Bahnhof",2025,2025,8,8,"2025-02-21","21:15:00","2025-02-22","05:15:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-11-19",null,null,"2,3",1]
[null,"DB InfraGO AG","347AC-001","München - Salzburg","<","Zorneding","München-Trudering",2025,2025,16,16,"2025-04-19","21:15:00","2025-04-20","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-10-14",null,null,"3,4",1]
[null,"DB InfraGO AG","35586-001","München - Salzburg",">","Zorneding","Grafing Bahnhof",2025,2025,18,18,"2025-04-29","21:15:00","2025-04-30","05:15:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-10-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1C3FA-006","Nürnberg - Passau",">","Aburg-Goldbach","Aschaffenburg Hbf",2026,2026,27,28,"2026-06-29","23:00:00","2026-07-06","05:00:00","6d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-15",null,null,"4,5",1]
[null,"DB InfraGO AG","16C52-004","Nürnberg - Passau","<","Allersberg (Rothsee)","Nürnberg Reichswald",2025,2025,10,11,"2025-03-09","22:00:00","2025-03-14","05:30:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-10-14",null,null,"4,5",1]
[null,"DB InfraGO AG","90D9-002","Nürnberg - Passau",">","Beratzhausen","Parsberg",2025,2025,14,14,"2025-04-05","23:00:00","2025-04-06","06:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-15",null,null,"6,7",1]
[null,"DB InfraGO AG","12A6A-007","Nürnberg - Passau",">","Beratzhausen","Seubersdorf",2025,2025,39,39,"2025-09-28","21:00:00","2025-09-28","22:40:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-10-15",null,null,"6,7",1]
[null,"DB InfraGO AG","339C4-003","Nürnberg - Passau","< >","Beratzhausen","Undorf",2025,2025,13,13,"2025-03-28","21:00:00","2025-03-29","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-15",null,null,"4,5",1]
[null,"DB InfraGO AG","330CD-004","Nürnberg - Passau","< >","Beratzhausen","Parsberg",2025,2025,19,19,"2025-05-05","21:00:00","2025-05-06","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1E72F-019","Nürnberg - Passau","<","Beratzhausen","Undorf",2026,2026,42,42,"2026-10-15","00:00:00","2026-10-15","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","33093-004","Nürnberg - Passau","< >","Deining Üst","Parsberg",2025,2025,21,21,"2025-05-24","21:00:00","2025-05-25","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","33990-002","Nürnberg - Passau","< >","Dingolfing","Plattling",2025,2025,12,12,"2025-03-21","21:00:00","2025-03-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","2CF30-002","Nürnberg - Passau","<","Feucht","Postbauer-Heng",2025,2025,13,13,"2025-03-27","21:00:00","2025-03-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-07-10",null,null,5,1]
[null,"DB InfraGO AG","30D3F-001","Nürnberg - Passau","<","Feucht","Postbauer-Heng",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1C8BF-007","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-10-21",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","1E95C-011","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,45,45,"2026-11-04","10:00:00","2026-11-07","16:00:00","3d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1A43B-048","Darmstadt - Nürnberg","< >","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2025,2025,42,42,"2025-10-14","05:00:00","2025-10-15","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-01",null,null,5,1]
[null,"DB InfraGO AG","3206B-001","Darmstadt - Nürnberg",">","Fürth (Bay) Gbf","Nürnberg Hbf",2025,2025,17,17,"2025-04-24","21:00:00","2025-04-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1AA5F-001","Darmstadt - Nürnberg",">","Fürth (Bay) Hbf","Fürth-Burgfarrnbach",2025,2025,23,23,"2025-06-07","22:00:00","2025-06-07","23:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-03",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30DA3-002","Darmstadt - Nürnberg","< >","Fürth (Bay) Hbf","Siegelsdorf",2025,2025,7,7,"2025-02-12","21:20:00","2025-02-13","05:05:00","0d, 7h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-04",null,null,"4,5",1]
[null,"DB InfraGO AG","3483F-001","Darmstadt - Nürnberg","<","Fürth (Bay) Hbf","Nürnberg Großmarkt",2025,2025,15,15,"2025-04-09","21:20:00","2025-04-10","05:05:00","0d, 7h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-11-11",null,null,1,1]
[null,"DB InfraGO AG","363B3-005","Darmstadt - Nürnberg",">","Fürth (Bay) Hbf","Fürth-Unterfarrnbach Abzw",2025,2025,15,16,"2025-04-11","21:00:00","2025-04-18","05:00:00","6d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-13",null,null,1,1]
[null,"DB InfraGO AG","1AA7C-002","Darmstadt - Nürnberg","<","Fürth-Unterfarrnbach Abzw","Fürth (Bay) Hbf",2025,2025,23,24,"2025-06-08","22:00:00","2025-06-09","05:00:00","0d, 7h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-05",null,null,"2,3",1]
[null,"DB InfraGO AG","1D973-001","Nürnberg - Passau","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,34,34,"2026-08-21","21:00:00","2026-08-23","21:00:00","2d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-02",null,null,"1,7",1]
[null,"DB InfraGO AG","330A0-003","Nürnberg - Passau","< >","Girching","Osterhofen (Niederbay)",2025,2025,23,23,"2025-06-04","21:00:00","2025-06-05","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-14",null,null,"6,7",1]
[null,"DB InfraGO AG","330F0-002","Nürnberg - Passau","< >","Girching","Plattling",2025,2025,15,16,"2025-04-13","21:00:00","2025-04-14","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,"4,5",1]
[null,"DB InfraGO AG","2E9BB-005","Nürnberg - Passau","< >","Hagelstadt","Obertraubling",2025,2025,6,6,"2025-02-06","21:00:00","2025-02-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-17",null,null,"6,7",1]
[null,"DB InfraGO AG","330BF-006","Nürnberg - Passau",">","Köfering","Obertraubling",2025,2025,22,22,"2025-05-29","23:00:00","2025-05-30","04:00:00","0d, 5h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-02",null,null,"2,3",1]
[null,"DB InfraGO AG","14E1F-014","Nürnberg - Passau","<","Mangolding","Sünching",2025,2025,50,50,"2025-12-08","21:00:00","2025-12-10","05:00:00","1d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-03",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","15037-017","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2025,2025,15,15,"2025-04-12","22:00:00","2025-04-13","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-09",null,null,"1,7",1]
[null,"DB InfraGO AG","2D163-002","Nürnberg - Passau","< >","Neumarkt (Oberpf)","Ochenbruck",2025,2025,17,17,"2025-04-26","21:00:00","2025-04-27","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-12-09",null,null,"6,7",1]
[null,"DB InfraGO AG","8765-010","Nürnberg - Passau","< >","Nürnberg Rbf Ausfahrt","Nürnberg-Dutzendteich",2025,2025,7,9,"2025-02-15","04:00:00","2025-02-24","04:00:00","9d, 0h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","16C52-002","Nürnberg - Passau",">","Nürnberg Reichswald","Allersberg (Rothsee)",2025,2025,9,10,"2025-03-02","22:00:00","2025-03-07","05:30:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-12-11",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","2D165-002","Nürnberg - Passau",">","Nürnberg Reichswald","Nürnberg-Langwasser",2025,2025,5,5,"2025-02-01","21:00:00","2025-02-02","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-12-18",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","30D4A-002","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg Hbf",2025,2025,11,11,"2025-03-10","21:00:00","2025-03-11","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-10",null,null,7,1]
[null,"DB InfraGO AG","3439F-007","Nürnberg - Passau","< >","Nürnberg Reichswald","Feucht",2025,2025,16,17,"2025-04-15","21:00:00","2025-04-25","21:00:00","10d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,"6,7",1]
[null,"DB InfraGO AG","3ABD3-021","Nürnberg - Passau",">","Nürnberg Reichswald","Allersberg (Rothsee)",2025,2025,16,17,"2025-04-18","22:00:00","2025-04-25","21:00:00","6d, 23h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1DF02-011","Nürnberg - Passau","< >","Nürnberg Reichswald","Deining (Oberpf)",2026,2026,28,28,"2026-07-10","06:00:00","2026-07-10","12:00:00","0d, 6h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-12-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","8F75-003","Nürnberg - Passau",">","Nürnberg-Dürrenhof","Feucht",2025,2025,14,14,"2025-04-01","00:01:00","2025-04-04","04:01:00","3d, 4h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3737C-001","Nürnberg - Passau",">","Nürnberg-Dutzendteich","Nürnberg Hbf",2025,2025,25,25,"2025-06-19","21:00:00","2025-06-20","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-04",null,null,"1,7",1]
[null,"DB InfraGO AG","8D38-004","Nürnberg - Passau","< >","Nürnberg-Langwasser","Nürnberg Reichswald",2025,2025,15,15,"2025-04-13","08:00:00","2025-04-13","14:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-13",null,null,"5,6",1]
[null,"DB InfraGO AG","8F75-013","Nürnberg - Passau",">","Nürnberg-Langwasser","Nürnberg Reichswald",2025,2025,15,15,"2025-04-12","22:00:00","2025-04-13","04:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-08-06",null,null,7,1]
[null,"DB InfraGO AG","1F819-002","Nürnberg - Passau","< >","Obertraubling","Regensburg Ost",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-16","21:00:00","8d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,"4,5",1]
[null,"DB InfraGO AG","2E9BB-008","Nürnberg - Passau","<","Obertraubling","Köfering",2025,2025,6,6,"2025-02-06","23:00:00","2025-02-07","04:00:00","0d, 5h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","30C57-001","Nürnberg - Passau","< >","Ochenbruck","Nürnberg Reichswald",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-17",null,null,"1,2",1]
[null,"DB InfraGO AG","BC27-004","Nürnberg - Passau","< >","Osterhofen (Niederbay)","Plattling",2025,2025,14,14,"2025-04-05","21:00:00","2025-04-06","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-23",null,null,2,1]
[null,"DB InfraGO AG","30D88-001","Nürnberg - Passau","<","Osterhofen (Niederbay)","Girching",2025,2025,7,7,"2025-02-12","21:00:00","2025-02-13","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"2,3,4",1]
[null,"DB InfraGO AG","90D9-003","Nürnberg - Passau","<","Parsberg","Beratzhausen",2025,2025,15,16,"2025-04-07","01:00:00","2025-04-18","05:00:00","11d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-12",null,null,6,1]
[null,"DB InfraGO AG","330CC-001","Nürnberg - Passau","<","Parsberg","Beratzhausen",2025,2025,15,15,"2025-04-07","21:00:00","2025-04-08","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-30",null,null,"4,5",1]
[null,"DB InfraGO AG","33084-004","Nürnberg - Passau","< >","Parsberg","Beratzhausen",2025,2025,21,21,"2025-05-22","21:00:00","2025-05-23","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-11-28",null,null,5,1]
[null,"DB InfraGO AG","2E10F-001","Nürnberg - Passau",">","Passau Gbf","Sandbach (Niederbay)",2025,2025,5,6,"2025-02-02","21:00:00","2025-02-03","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO AG","330A1-002","Nürnberg - Passau","< >","Passau Gbf","Sandbach (Niederbay)",2025,2025,13,14,"2025-03-30","21:00:00","2025-03-31","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D710-002","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,20,21,"2026-05-15","07:00:00","2026-05-23","04:00:00","7d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D5C0-001","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,38,39,"2026-09-19","22:00:00","2026-09-21","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","17B86-005","Nürnberg - Passau","<","Plattling","Osterhofen (Niederbay)",2025,2025,49,49,"2025-12-06","04:30:00","2025-12-06","05:30:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-23",null,null,"1,2,3",1]
[null,"DB InfraGO AG","30CAD-002","Nürnberg - Passau","< >","Plattling","Wallersdorf",2025,2025,10,10,"2025-03-06","21:05:00","2025-03-07","05:00:00","0d, 7h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","368E0-002","Nürnberg - Passau",">","Plattling","Straßkirchen",2025,2025,25,25,"2025-06-18","21:00:00","2025-06-19","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-01",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1CF23-018","Nürnberg - Passau","< >","Plattling","Mangolding",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D32E-012","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,15,15,"2026-04-08","22:00:00","2026-04-10","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,"3,4,5",1]
[null,"DB InfraGO AG","2D022-002","Nürnberg - Passau","< >","Postbauer-Heng","Deining Üst",2025,2025,17,17,"2025-04-25","21:00:00","2025-04-26","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","373A7-002","Nürnberg - Passau","< >","Postbauer-Heng","Deining Üst",2025,2025,25,25,"2025-06-20","21:00:00","2025-06-21","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","2F585-001","Nürnberg - Passau","<","Radldorf (Niederbay)","Straßkirchen",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,null,null,null,"4,5,6",1]
[null,"DB InfraGO AG","330F9-001","Nürnberg - Passau",">","Radldorf (Niederbay)","Mangolding",2025,2025,19,20,"2025-05-11","21:00:00","2025-05-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"20,20,20",null,null,null,"N",null,"2024-04-30",null,null,"5,6",1]
[null,"DB InfraGO AG","159C9-001","Nürnberg - Passau",">","Regensburg Bbf","Undorf",2025,2025,16,16,"2025-04-14","21:00:00","2025-04-15","04:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,7,1]
[null,"DB InfraGO AG","33BD4-001","Nürnberg - Passau",">","Regensburg Bbf","Regensburg-Prüfening               (NRH)",2025,2025,17,17,"2025-04-26","21:00:00","2025-04-27","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-29",null,null,"1,2",1]
[null,"DB InfraGO AG","1DE17-010","Nürnberg - Passau","<","Regensburg Bbf","Regensburg Ost",2026,2026,38,38,"2026-09-15","21:00:00","2026-09-16","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-05-24",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1DB86-013","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-09","01:00:00","2026-06-09","05:00:00","0d, 4h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-14",null,null,7,1]
[null,"DB InfraGO AG","12B6C-007","Nürnberg - Passau","<","Regensburg Hbf","Regensburg Ost",2025,2025,48,48,"2025-11-29","22:00:00","2025-11-29","23:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"13,13,13",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DB86-018","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-10","19:00:00","2026-06-14","05:00:00","3d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1DB86-021","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,25,"2026-06-14","21:00:00","2026-06-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-31",null,null,"5,6",1]
[null,"DB InfraGO AG","33CDC-003","Nürnberg - Passau","< >","Regensburg Ost","Mangolding",2025,2025,14,14,"2025-04-05","23:00:00","2025-04-06","04:00:00","0d, 5h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","ACA7-003","Nürnberg - Passau","< >","Regensburg Walhallastraße","Regensburg Hbf",2025,2025,34,36,"2025-08-22","23:00:00","2025-09-03","05:00:00","11d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","9340-019","Nürnberg - Passau","<","Regenstauf","Regensburg Hbf",2025,2025,44,44,"2025-10-31","22:00:00","2025-11-01","04:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,null,"N",null,"2024-05-23",null,null,1,1]
[null,"DB InfraGO AG","157BC-003","Nürnberg - Passau","<","Sandbach (Niederbay)","Passau Gbf",2025,2025,16,17,"2025-04-20","19:00:00","2025-04-21","05:00:00","0d, 10h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-23",null,null,1,1]
[null,"DB InfraGO AG","366CB-003","Nürnberg - Passau","< >","Sandbach (Niederbay)","Vilshofen (Niederbay)",2025,2025,9,11,"2025-03-01","21:00:00","2025-03-11","05:00:00","9d, 8h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-23",null,null,"3,4",1]
[null,"DB InfraGO AG","16F61-003","Nürnberg - Passau",">","Schalding","Sandbach (Niederbay)",2025,2025,17,18,"2025-04-26","20:00:00","2025-04-28","05:00:00","1d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","2F7A2-001","Nürnberg - Passau","<","Seubersdorf","Parsberg",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2DF5E-004","Nürnberg - Passau","< >","Seubersdorf","Beratzhausen",2025,2025,9,9,"2025-02-27","21:00:00","2025-02-28","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-07",null,null,"5,6,7",1]
[null,"DB InfraGO AG","33094-008","Nürnberg - Passau","< >","Seubersdorf","Parsberg",2025,2025,25,25,"2025-06-21","21:00:00","2025-06-22","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-07",null,null,"5,6,7",1]
[null,"DB InfraGO AG","14D21-009","Nürnberg - Passau","< >","Straßkirchen","Straubing",2025,2025,40,41,"2025-10-05","21:00:00","2025-10-06","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-27",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","330B1-003","Nürnberg - Passau","< >","Straßkirchen","Straubing",2025,2025,15,15,"2025-04-08","21:00:00","2025-04-09","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-28",null,null,"1,2",1]
[null,"DB InfraGO AG","14D21-023","Nürnberg - Passau","<","Straubing","Straßkirchen",2025,2025,48,48,"2025-11-25","21:00:00","2025-11-27","05:00:00","1d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-01-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","15256-002","Nürnberg - Passau",">","Straubing","Radldorf (Niederbay)",2025,2025,17,17,"2025-04-22","21:00:00","2025-04-25","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-23",null,null,6,1]
[null,"DB InfraGO AG","1CF23-007","Nürnberg - Passau","< >","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,"1,2",1]
[null,"DB InfraGO AG","14E1F-015","Nürnberg - Passau",">","Sünching","Mangolding",2025,2025,50,50,"2025-12-10","21:00:00","2025-12-12","05:00:00","1d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-02-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","9228-002","Nürnberg - Passau","< >","Undorf","Beratzhausen",2025,2025,40,41,"2025-10-05","11:00:00","2025-10-06","05:00:00","0d, 18h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-05-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2F79D-001","Nürnberg - Passau","<","Undorf","Regensburg Bbf",2025,2025,7,7,"2025-02-11","21:00:00","2025-02-12","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,4,1]
[null,"DB InfraGO AG","330C4-001","Nürnberg - Passau","<","Undorf","Regensburg Bbf",2025,2025,19,19,"2025-05-06","21:00:00","2025-05-07","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","BE7B-006","Nürnberg - Passau",">","Vilshofen (Niederbay)","Girching",2025,2025,37,38,"2025-09-09","21:00:00","2025-09-15","05:00:00","5d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"6,7",1]
[null,"DB InfraGO AG","C0B4-002","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Sandbach (Niederbay)",2025,2025,18,19,"2025-05-04","22:00:00","2025-05-05","05:00:00","0d, 7h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-05-23",null,null,"6,7",1]
[null,"DB InfraGO AG","BCCB-031","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2025,2025,15,16,"2025-04-11","07:00:00","2025-04-19","20:00:00","8d, 13h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","8D9F-006","Nürnberg - Plzen","< >","Arzberg (Oberfr)","Schirnding",2025,2025,35,35,"2025-08-30","04:35:00","2025-08-31","06:35:00","1d, 2h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","20DE0-021","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,34,38,"2026-08-20","04:45:00","2026-09-14","08:00:00","25d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","20DE0-023","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,37,38,"2026-09-12","18:30:00","2026-09-17","11:00:00","4d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","19F34-009","Nürnberg - Plzen","< >","Maxhütte-Haidhof","Maxh-Haidh DB-Gr",2025,2025,24,34,"2025-06-15","00:00:00","2025-08-22","00:00:00","68d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,7,1]
[null,"DB InfraGO AG","22378-002","Nürnberg - Plzen","< >","Neusorg","Marktredwitz",2026,2026,31,32,"2026-07-31","21:00:00","2026-08-06","05:00:00","5d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","40FB2-001","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2025,2025,8,8,"2025-02-23","01:20:00","2025-02-23","06:30:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","9105-007","Nürnberg - Plzen",">","Rückersdorf (Mittelfr)","Neunkirchen a Sand",2025,2025,23,23,"2025-06-04","20:00:00","2025-06-05","06:00:00","0d, 10h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-07",null,null,3,1]
[null,"DB InfraGO AG","2080A-006","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-14","06:00:00","3d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","8D9F-020","Nürnberg - Plzen","< >","Schirnding","Schirnding",2025,2025,46,47,"2025-11-14","23:00:00","2025-11-19","05:00:00","4d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,3,1]
[null,"DB InfraGO AG","2138A-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4,1]
[null,"DB InfraGO AG","20EC7-009","Rostock - Berlin","< >","Bentwisch","Rostock Seehafen Süd",2026,2026,5,18,"2026-01-31","07:00:00","2026-04-30","16:00:00","89d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","331B1-008","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2025,2025,9,9,"2025-02-24","21:00:00","2025-02-25","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,7"]
[null,"DB InfraGO AG","2FE37-010","Rostock - Berlin","< >","Berlin Nordost","Biesdorfer Kreuz Nord",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","39967-004","Rostock - Berlin","< >","Berlin Nordost","Bln-Hohenschhsn",2025,2025,11,11,"2025-03-16","08:00:00","2025-03-16","10:00:00","0d, 2h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","2DF79-005","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2025,2025,9,9,"2025-02-28","21:00:00","2025-03-01","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-002","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4]
[null,"DB InfraGO AG","2CD8A-005","Rostock - Berlin","< >","Berlin-Karow Ost","Berlin-Karow",2025,2025,13,13,"2025-03-26","21:00:00","2025-03-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2FE37-003","Rostock - Berlin","<","Berlin-Karow Ost","Biesdf Kr N Strw",2025,2025,7,7,"2025-02-14","21:00:00","2025-02-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-14",null,null,3]
[null,"DB InfraGO AG","2FB9A-013","Rostock - Berlin","< >","Berlin-Karow Ost","Biesdf Kr N Strw",2025,2025,15,15,"2025-04-11","02:00:00","2025-04-11","05:00:00","0d, 3h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,7]
[null,"DB InfraGO AG","2FB9B-001","Rostock - Berlin","<","Berlin-Karow West","Karower Kr Strw",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-14",null,null,4]
[null,"DB InfraGO AG","9BBF-019","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuend Sw",2025,2025,6,7,"2025-02-07","22:00:00","2025-02-10","04:00:00","2d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5,6"]
[null,"DB InfraGO AG","331B2-007","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2025,2025,13,13,"2025-03-24","21:00:00","2025-03-25","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2"]
[null,"DB InfraGO AG","3FE74-005","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Birkenwerder (b Berlin)           S-Bahn",2025,2025,28,29,"2025-07-11","22:00:00","2025-07-14","03:00:00","2d, 5h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,5]
[null,"DB InfraGO AG","3FE74-006","Rostock - Berlin","< >","Birkenwerder Nord","Birkenwerder (b Berlin)           S-Bahn",2025,2025,28,29,"2025-07-11","22:00:00","2025-07-14","03:00:00","2d, 5h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40D67-001","Rostock - Berlin","<","Drewin","Seilershof",2025,2025,6,6,"2025-02-03","22:20:00","2025-02-04","03:50:00","0d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,1]
[null,"DB InfraGO AG","2FFDC-002","Rostock - Berlin","<","Fürstenberg (Havel)","Gransee",2025,2025,19,19,"2025-05-10","21:00:00","2025-05-11","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-27",null,null,1]
[null,"DB InfraGO AG","336D6-007","Rostock - Berlin","<","Grabowhöfe","Kargow",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,6]
[null,"DB InfraGO AG","2FDC3-002","Rostock - Berlin","<","Gransee","Nassenheide",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","3001B-005","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2025,2025,7,7,"2025-02-15","21:00:00","2025-02-16","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"2,3,4,5,6"]
[null,"DB InfraGO AG","23B5A-006","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,6]
[null,"DB InfraGO AG","2DDEE-004","Rostock - Berlin",">","Kargow","Grabowhöfe",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"5,6"]
[null,"DB InfraGO AG","30012-002","Rostock - Berlin","<","Kargow","Neustrelitz Hbf",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,"6,7"]
[null,"DB InfraGO AG","332F1-001","Rostock - Berlin","<","Kavelstorf","Plaaz                               Abzw",2025,2025,11,11,"2025-03-14","21:00:00","2025-03-15","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-18",null,null,"5,6"]
[null,"DB InfraGO AG","332F5-001","Rostock - Berlin","<","Kavelstorf","Plaaz                               Abzw",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","1AAC1-003","Rostock - Berlin","< >","Lalendorf Ost","Lalendorf",2025,2025,19,19,"2025-05-07","23:15:00","2025-05-08","02:45:00","0d, 3h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2"]
[null,"DB InfraGO AG","332F8-001","Rostock - Berlin","<","Langhagen","Waren (Müritz)",2025,2025,15,15,"2025-04-11","21:00:00","2025-04-12","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-07",null,null,"2,3,4"]
[null,"DB InfraGO AG","2D5B0-003","Rostock - Berlin","< >","Löwenberg (Mark)","Zehdenick (Mark)",2025,2025,13,13,"2025-03-25","21:00:00","2025-03-26","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3270A-005","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg DB-Gr",2025,2025,20,20,"2025-05-13","21:00:00","2025-05-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","24036-009","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg DB-Gr",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"5,6"]
[null,"DB InfraGO AG","2D5B2-001","Rostock - Berlin",">","Nassenheide","Gransee",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-03",null,null,"5,6"]
[null,"DB InfraGO AG","2D5D9-004","Rostock - Berlin","< >","Neustrelitz Hbf","Neustrelitz Gr",2025,2025,9,9,"2025-02-26","21:00:00","2025-02-27","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"5,6"]
[null,"DB InfraGO AG","2D5DC-004","Rostock - Berlin","< >","Neustrelitz Hbf","Neustrelitz Gr",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3001D-008","Rostock - Berlin","<","Oranienburg","Hohen Neuend Sw",2025,2025,15,15,"2025-04-12","21:00:00","2025-04-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,1]
[null,"DB InfraGO AG","32CC6-001","Rostock - Berlin",">","Oranienburg","Löwenberg (Mark)",2025,2025,9,9,"2025-02-24","21:00:00","2025-02-25","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-14",null,null,1]
[null,"DB InfraGO AG","89BB-004","Rostock - Berlin","< >","Peine","Peine",2025,2025,18,21,"2025-05-03","21:10:00","2025-05-21","05:10:00","17d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1AAC8-006","Rostock - Berlin","< >","Plaaz                               Abzw","Vollrathsruhe",2025,2025,19,19,"2025-05-09","02:45:00","2025-05-09","04:45:00","0d, 2h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41419-002","Rostock - Berlin","< >","Rostock Seehafen","Rostock Seehafen",2025,2025,10,10,"2025-03-05","08:00:00","2025-03-06","15:00:00","1d, 7h","Periodical","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2FB89-004","Rostock - Berlin","< >","Schönfließ West","Hohen Neuend Sw",2025,2025,7,7,"2025-02-13","21:00:00","2025-02-14","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","64C2-001","Rostock - Berlin","< >","Schönfließ West","Hennigsd N (Hdw)",2025,2025,43,46,"2025-10-24","22:00:00","2025-11-14","22:00:00","21d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"06.12.2024",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2FAF1-003","Rostock - Berlin","<","Seilershof","Löwenberg (Mark)",2025,2025,15,15,"2025-04-10","21:00:00","2025-04-11","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"03.06.2024"]
[null,"DB InfraGO AG","2DD66-008","Rostock - Berlin",">","Vollrathsruhe","Plaaz                               Abzw",2025,2025,21,21,"2025-05-20","21:00:00","2025-05-21","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"31.05.2024"]
[null,"DB InfraGO AG","2FDF7-001","Rostock - Berlin","<","Waren (Müritz)","Kratzeburg",2025,2025,19,19,"2025-05-09","21:00:00","2025-05-10","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"13.05.2024"]
[null,"DB InfraGO AG","33924-004","Rostock - Berlin","< >","Waren DB-Gr","Waren (Müritz)",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"19.12.2023"]
[null,"DB InfraGO AG","A4CE-013","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen-Neustadt",2025,2025,24,24,"2025-06-12","03:00:00","2025-06-12","05:30:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"17.06.2024"]
[null,"DB InfraGO AG","36DF8-003","Wilhelmshaven - Bremen","< >","Bremen Hbf ehem Bwn","Delmenhorst",2025,2025,17,17,"2025-04-23","21:00:00","2025-04-24","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"29.05.2024"]
[null,"DB InfraGO AG","1D066-004","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Delmenhorst Df",2026,2026,46,48,"2026-11-13","22:10:00","2026-11-25","05:00:00","11d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",,2",null,null,null,"N",null,"19.07.2024"]
[null,"DB InfraGO AG","2FC38-003","Wilhelmshaven - Bremen","< >","Delmenhorst","Bremen Hbf ehem Bwn",2025,2025,19,19,"2025-05-08","21:00:00","2025-05-09","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"29.08.2024"]
[null,"DB InfraGO AG","2FD39-001","Wilhelmshaven - Bremen","<","Delmenhorst Df","Hude",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"03.06.2024"]
[null,"DB InfraGO AG","2FD39-003","Wilhelmshaven - Bremen","< >","Hude","Delmenhorst",2025,2025,23,23,"2025-06-06","21:00:00","2025-06-07","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"26.11.2024"]
[null,"DB InfraGO AG",313.89999999999998,"Wilhelmshaven - Bremen","<","Jaderberg","Oldenburg (Oldb) Hbf",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"28.01.2025"]
[null,"DB InfraGO AG","1B7E0-001","Wilhelmshaven - Bremen","< >","Kayhauserfeld","Oldenburg (Oldb) Hbf",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","22:00:00","3d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"20.01.2025"]
[null,"DB InfraGO AG","2D9A5-003","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2025,2025,21,21,"2025-05-19","21:00:00","2025-05-20","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"29.05.2024"]
[null,"DB InfraGO AG","2E733-003","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2025,2025,6,6,"2025-02-05","21:00:00","2025-02-06","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"27.05.2024"]
[null,"DB InfraGO AG","30090-004","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Hude",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"19.12.2023"]
[null,"DB InfraGO AG","371A7-001","Wilhelmshaven - Bremen",">","Oldenburg (Oldb) Hbf","Wüsting",2025,2025,25,25,"2025-06-16","21:00:00","2025-06-17","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"17,17,17",null,null,null,"N",null,"14.08.2024"]
[null,"DB InfraGO AG","395FC-005","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2025,2025,21,21,"2025-05-21","21:00:00","2025-05-22","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"26.03.2024"]
[null,"DB InfraGO AG","1C282-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,8,42,"2026-02-16","00:00:00","2026-10-18","23:59:00","244d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"29.08.2024"]
[null,"DB InfraGO AG","3A46B-002","Wilhelmshaven - Bremen","< >","Oldenburg-Hemmelsberg","Oldenburg (Oldb) Tweelbäke",2025,2025,20,21,"2025-05-16","20:00:00","2025-05-19","04:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:22"]
[null,"DB InfraGO AG","2E30D-002","Wilhelmshaven - Bremen","< >","Sande","Sande",2025,2025,6,6,"2025-02-03","21:00:00","2025-02-04","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:23"]
[null,"DB InfraGO AG","2F97F-003","Wilhelmshaven - Bremen","< >","Sande","Sande",2025,2025,11,11,"2025-03-12","21:00:00","2025-03-13","05:00:00","0d, 8h","Continuous","Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:24"]
[null,"DB InfraGO AG","30E1A-001","Wilhelmshaven - Bremen","<","Sande","Jaderberg",2025,2025,12,12,"2025-03-17","21:00:00","2025-03-18","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-10T07:39:25"]
[null,"DB InfraGO AG","31284-002","Wilhelmshaven - Bremen","<","Schortens Weißer Floh","Sande",2025,2025,16,16,"2025-04-16","21:00:00","2025-04-17","05:00:00","0d, 8h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:25"]
[null,"DB InfraGO AG","33E95-012","Wilhelmshaven - Bremen",">","Varel (Oldb)","Sande",2025,2025,18,18,"2025-04-29","19:00:00","2025-04-29","23:00:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-10T07:39:26"]
[null,"DB InfraGO AG","34AE4-001","Wilhelmshaven - Bremen","<","Wüsting","Oldenburg (Oldb) Hbf",2025,2025,11,11,"2025-03-15","21:00:00","2025-03-16","05:00:00","0d, 8h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-10T07:39:26"]
[null,"GySEV",5625342,"Sopron - Györ","< >","Kapuvár","Kapuvár",2025,2025,41,48,"2025-10-06","06:00:00","2025-11-30","23:59:00","56d","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,null,null,null,null,"2024-07-10T07:39:26"]
[null,"MÁV",55009001010,"Hegyeshalom-Ferencváros",">","Almásfüzitő felső","Komárom",2025,2025,10,10,"2025-03-09","04:00:00","2025-03-09","08:05:00","4h05m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:39:27"]
[null,"MÁV",55009001067,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld",2025,2025,14,14,"2025-04-03","09:30:00","2025-04-03","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:39:28"]
[null,"MÁV",55009001083,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld",2025,2025,18,18,"2025-04-28","09:30:00","2025-04-28","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:39:28"]
[null,"MÁV",55009001114,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld",2025,2025,25,25,"2025-06-16","09:00:00","2025-06-16","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:39:29"]
[null,"MÁV",55009001159,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld",2025,2025,35,35,"2025-08-25","09:30:00","2025-08-25","16:30:00","7h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:40:22"]
[null,"MÁV",55009001163,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld",2025,2025,35,35,"2025-08-29","09:30:00","2025-08-29","16:30:00","7h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:40:22"]
[null,"MÁV",55009001093,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,21,21,"2025-05-20","22:00:00","2025-05-21","04:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:40:22"]
[null,"MÁV",55009001141,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,30,31,"2025-07-27","21:00:00","2025-07-28","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:40:23"]
[null,"MÁV",55009001164,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,35,35,"2025-08-29","22:00:00","2025-08-30","04:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2024-07-10T07:40:23"]
[null,"MÁV",55009001175,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,37,37,"2025-09-09","22:00:00","2025-09-10","04:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001199,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,41,41,"2025-10-08","23:00:00","2025-10-09","04:30:00","5h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001209,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,44,44,"2025-10-28","23:00:00","2025-10-29","04:30:00","5h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001234,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,48,48,"2025-11-27","23:00:00","2025-11-28","04:30:00","5h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001242,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,49,49,"2025-12-06","23:00:00","2025-12-07","04:30:00","5h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009100002,"Szajol - Biharkeresztes","<>","Karcag","Püspökladány",2025,2025,19,19,"2025-05-06","00:00:00","2025-05-06","04:00:00","4h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009100005,"Szajol - Biharkeresztes","<>","Püspökladány","Püspökladány",2025,2025,19,19,"2025-05-08","00:00:00","2025-05-08","04:00:00","4h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009120019,"Szajol-Curtici",">","Kétegyháza","Lökösháza oh",2025,2025,21,22,"2025-05-25","22:55:00","2025-05-26","01:05:00","2h10m","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009120002,"Szajol-Curtici",">","Szabadkígyós","Kétegyháza",2024,2025,50,14,"2024-12-15","00:00:00","2025-04-01","04:40:00","107d4h40m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"ÖBB Infra","81-B-78953","Passau - Wels","< >","Ried im Innkreis","Schärding",2026,2026,13,17,"28.03.2026","00:00:00","24.04.2026",1,"27 days + 23,0 h","Continuous","Miscellaneous","T","LT",null,null,null,"C",null,"T",0,null,"Gleisneulage, EK-Neubau",null,"N",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-77203","Salzburg - Wels","< >","Abzw Knoten Hadersdorf","St.Pölten Hbf",2025,2025,1,50,"01.01.2025","00:00:00","13.12.2025",1,"347 days","Continuous","Maintenance","T","LT",null,null,null,"C","R",null,0,null,"Wartungsnacht ",null,"Y",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-77436","Salzburg - Wels","< >","Bad Schallerbach-Wallern","-",2025,2025,14,18,"04.04.2025","07:00:00","02.05.2025","17:00:00","28 days + 10,0 h","Continuous","Others","T","LT","S",null,null,null,null,null,0,null,"Bad Schallerbach-Wallern, Gleis- und Weichenneulage Gleis 302",null,"N",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-85204","Salzburg - Wels","< >","Grieskirchen-Gallspach","-",2025,2025,11,12,"14.03.2025","22:40:00","17.03.2025","04:30:00","2 days + 5,8 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Bf Grieskirchen-Gallspach, Erneuerung Drainage zw Gl 1 u Gl 2",null,"N",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-77518","Salzburg - Wels","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,10,15,"03.03.2025","04:40:00","07.04.2025","04:40:00","34 days + 23,0 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Umbau Bahnhof Himberg Phase 4a/b/c",null,"Y",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-76441","Salzburg - Wels","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2025,5,6,"01.02.2025","23:15:00","03.02.2025","04:40:00","1 day + 5,4 h","Periodical","Others","T","LT",null,null,null,"C","R","T",0,null,"Vorarbeiten für Bahnhofumbau Himberg (Weichenverbindung auflegen)",null,"Y",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-79417","Salzburg - Wels","< >","Linz Kleinmünchen","Linz Hbf",2026,2026,43,44,"24.10.2026","08:30:00","27.10.2026","03:00:00","2 days + 19,5 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Herstellen Spundwand Raimundstraße",null,"N",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-79703","Salzburg - Wels","< >","Mauer-Öhling","-",2025,2025,12,14,"17.03.2025","08:00:00","04.04.2025","15:00:00","18 days + 6,0 h","Continuous","Others","T","LT","S",null,null,null,null,null,0,null,"Erneuerung der Bahnsteigbeleuchtung Mauer-Öhling",null,"N",null,"2024-07-11"]
[null,"ÖBB Infra","81-B-78277","Salzburg - Wels","< >","Salzburg Hbf",null,2026,2026,31,34,"02.08.2026","07:30:00","22.08.2026","05:00:00","19 days + 21,5 h","Continuous","Others","T","ST",null,null,null,"C","R","T",0,null,"Sanierung Gleis 203 und 205 GN/PLV",null,"N",null,"2024-12-17",null,"3,4,5,6,7"]
[null,"ÖBB Infra","81-B-79314","Salzburg - Wels","< >","Timelkam","Redl-Zipf",2025,2025,21,22,"23.05.2025","20:00:00","26.05.2025","05:00:00","2 days + 9,0 h","Continuous","Others","T","LT",null,null,null,"C",null,null,0,null,"Erneuerung der Weichen 53 + 54 + 59 im Bf Timelkam",null,"N",null,"2024-12-17"]
[null,"ÖBB Infra","81-B-85541","Salzburg - Wels","< >","Üst Spw 13","-",2025,2025,39,43,"27.09.2025","07:00:00","20.10.2025","12:00:00","23 days + 5,0 h","Continuous","Others","T","LT",null,null,null,"C",null,"T",0,null,"Weichenneulage mit PLV, Üst Spw 13\n\nRM 80 Einsatz Km 149,400 bis Km 149,800 + Einzelschwellentausch (am 18. - 20.10.25)",null,"N","SAB411","2024-12-17",null,"2,3"]
[null,"ÖBB Infra","81-B-78308","Salzburg - Wels","< >","Wels Vbf","-",2026,2026,15,17,"10.04.2026","00:00:00","23.04.2026",1,"14 days","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Gleinsneulage Gleis 326",null,"N","AMV6990302","2024-12-17"]
[null,"ÖBB Infra","81-B-83935","Salzburg - Wels","< >","Wien Meidling","Knoten Wagram",2025,2025,20,23,"12.05.2025","02:00:00","06.06.2025","02:00:00","25 days","Continuous","Maintenance","T","LT",null,null,null,"C","R","T",0,null,"Wiederherstellen der Infrastruktur (Hochwasser)",null,"N",null,"2024-12-17",null,"1,2,3,4,5"]
[null,"ÖBB Infra","81-B-65809","Wels - Linz","< >","Linz Hbf","Wels Hbf",2025,2025,43,50,"20.10.2025","04:00:00","13.12.2025",1,"54 days + 21,0 h","Continuous","Miscellaneous","T","LT","S",null,null,null,null,null,2,null,"Viergleisiger Ausbau Linz - Wels",null,"N",null,"2024-12-17"]
[null,"ÖBB Infra","81-B-65230","Wels - Traun - Linz","< >","Wels Vbf",null,2025,2025,11,12,"13.03.2025","07:00:00","17.03.2025","17:00:00","4 days + 10,0 h","Continuous","Others","T","ST",null,null,null,null,null,null,0,null,"Weichenneulage W75,76 ",null,"N",null,"2024-12-17",null,"1,2,3,4,5,6,7"]
[null,"ÖBB Infra","81-B-77847","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2026,50,46,"14.12.2025","00:00:00","14.11.2026","04:40:00","335 days + 4,7 h","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,0,null,"Umbau Bahnhof Himberg",null,"N",null,"2024-12-17"]
[null,"ÖBB Infra","81-B-65705","Wien - Hegyeshalom","< >","Maxing","Wien Meidling",2025,2025,17,22,"26.04.2025","01:30:00","26.05.2025","01:30:00","30 days","Continuous","Others","T","LT",null,null,null,"C","R","T",0,null,"Sanierung Gleis 4 und 6 (Tunnelbereiche)\nGleis4: 5,090-6,060, 6,300-6,800\nGleis6: 5,127-6,060, 6,300-6,800",null,"N",null,"2024-12-17",null,"1,4,5,6,7"]
[null,"ÖBB Infra","81-B-65829","Wien - Hegyeshalom","< >","Zentralfriedhof","Wien Zvbf",2025,2025,16,17,"19.04.2025","07:00:00","22.04.2025","11:00:00","3 days + 4,0 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Weichenneulage Weiche 281+282",null,"N",null,"2024-12-17",null,"1,2,3,4,5,6,7"]
[null,"SNCF-R",8726169,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2026,2026,28,28,"2026-07-06","22:40:00","2026-07-11","04:40:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Recommandation de non activation entre avril et octobre Modification de fenêtre : 6h dont 4 de simultanée pour passage trains internationaux      ",null,"Y",142000,"2024-12-17",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-004553/23","Břeclav - Wien","< >","Břeclav st.hr.","Břeclav os.n.",2025,2025,16,17,"2025-04-14","00:00:00","2025-04-22","23:59:00","9 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003896/24","Brno - Břeclav","< >","Odb B.-Čern.zhl.Táb.","Odb Brno-Židenice z",2026,2026,10,11,"2026-03-07","00:00:00","2026-03-09","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17",null,1]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,45,46,"2026-11-06","00:00:00","2026-11-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005705/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2025,2025,10,11,"2025-03-09","18:00:00","2025-03-12","06:00:00","3 x 9 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-12-17",null,1]
[null,"SZCZ","V-005908/24","Chocen - Hranice na Morave","< >","Č.Třebová odj.sk.","Odb Parník",2025,2025,10,12,"2025-03-07","18:00:00","2025-03-17","06:00:00","10 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,"X",null,null," ,X,X",null,null,"3,4 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005851/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2025,2025,35,39,"2025-08-29","00:00:00","2025-09-27","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ TK 1, 2.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004861/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,28,28,"2025-07-07","00:00:00","2025-07-12","23:59:00","12 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2023-11-22"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,48,51,"2026-11-28","00:00:00","2026-12-14","23:59:00","17 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17",null,"1,2,5,6,7"]
[null,"SZCZ","V-004838/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,37,46,"2025-09-13","00:00:00","2025-11-12","23:59:00","4 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005269/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2026,2026,46,46,"2026-11-11","00:00:00","2026-11-15","23:59:00","10 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004867/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Odb Jezernice B",2025,2025,29,30,"2025-07-18","00:00:00","2025-07-23","23:59:00","4 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005180/24","Chocen - Hranice na Morave","< >","Odb Jezernice A","Drahotuše",2025,2025,32,33,"2025-08-07","00:00:00","2025-08-13","23:59:00","7 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17",null,"6,7"]
[null,"SZCZ","V-006258/24","Chocen - Hranice na Morave","< >","Odb Parník","Česká Třebová",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-13","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-007780/22","Chocen - Hranice na Morave","< >","Polom","Suchdol nad Odrou",2025,2025,17,28,"2025-04-25","00:00:00","2025-07-10","23:59:00","77 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005721/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Odb Les",2025,2025,7,8,"2025-02-14","00:00:00","2025-02-21","23:59:00","8 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005696/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2025,2025,1,52,"2025-01-01","00:00:00","2025-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ost. zař.: ETCS.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-015836/23","Děčín - Kolín","< >","Hoštka","Polepy",2025,2025,16,16,"2025-04-14","00:00:00","2025-04-16","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-11-23","2025-01-29"]
[null,"SZCZ","V-007620/23","Děčín - Kolín","< >","Mělník","Všetaty",2025,2025,42,42,"2025-10-15","00:00:00","2025-10-18","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"03.04.2024."]
[null,"SZCZ","V-015830/23","Děčín - Kolín","< >","Štětí","Liběchov",2025,2025,24,26,"2025-06-09","00:00:00","2025-06-28","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-012194/21","Děčín - Praha-Libeň","< >","Bohušovice nad Ohří","Lovosice",2025,2025,45,45,"2025-11-05","18:00:00","2025-11-08","06:00:00","3 x 5 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018236/23","Děčín - Praha-Libeň","< >","Ústí nad Labem západ","Ústí n.L.hl.n.jih",2025,2025,23,25,"2025-06-02","00:00:00","2025-06-20","23:59:00","19 days","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007198/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,43,48,"2026-10-20","18:00:00","2026-11-27","06:00:00","38 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,"X",null,null,null,null,null,"1,2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013853/24","Hranice na Morave - Zilina","< >","Hranice na M. město","Hranice na Moravě",2027,2027,10,11,"2027-03-08","00:00:00","2027-03-21","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-017869/22","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2026,2026,18,31,"2026-05-01","00:00:00","2026-07-29","23:59:00","90 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1., 2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016660/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,28,43,"2026-07-11","00:00:00","2026-10-19","23:59:00","101 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-004711/23","Kolín - Brno-Maloměřice","< >","Ostrov nad Oslavou","Vlkov u Tišnova",2025,2025,21,21,"2025-05-22","00:00:00","2025-05-23","23:59:00","4 x 7 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2024-12-27"]
[null,"SZCZ","V-015978/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,15,16,"2026-04-08","00:00:00","2026-04-14","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"1,3 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007478/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2025,2025,40,40,"2025-10-01","18:00:00","2025-10-05","06:00:00","4 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-019677/24","Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2025,2025,10,10,"2025-03-03","07:40:00","2025-03-03","15:40:00","2 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-009204/24","Nürnberg - Plzen","< >","Pňovany","Trpísty",2025,2025,18,20,"2025-04-30","00:00:00","2025-05-14","23:59:00","15 days","Continuous","Others","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-022229/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2025,2025,14,14,"2025-04-01","23:30:00","2025-04-04","04:15:00","3 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005622/24","Ostrava - Zilina","< >","Karviná hl.n.","Odb Karviná-Darkov z",2025,2025,13,14,"2025-03-25","00:00:00","2025-04-04","23:59:00","22 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-004798/24","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Vítkovice",2025,2025,37,37,"2025-09-08","00:00:00","2025-09-10","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-021504/24","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2025,2025,10,10,"2025-03-03","23:20:00","2025-03-07","04:30:00","4 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1. bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-008681/24","Plzen - Praha","< >","Karlštejn","Beroun os.n.",2025,2025,1,52,"2025-01-01","00:00:00","2025-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. ETCS (1., 2. TK)."]
[null,"SZCZ","V-021374/24","Plzen - Praha","< >","Karlštejn","Odb Lom",2025,2025,6,7,"2025-02-07","21:00:00","2025-02-13","21:00:00","6 days + 0 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. "]
[null,"SZCZ","V-007536/22","Plzen - Praha","< >","Odb Tunel","Praha-Radotín",2025,2025,27,28,"2025-07-01","00:00:00","2025-07-10","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. "]
[null,"SZCZ","V-004403/24","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-11","23:59:00","8 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. bez TV. "]
[null,"SZCZ","V-019798/24","Plzen - Praha","< >","Praha-Krč","Praha-Kačerov",2025,2025,13,13,"2025-03-26","08:00:00","2025-03-26","16:00:00","1 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"91. bez TV. "]
[null,"SZCZ","V-010376/21","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2026,2026,30,32,"2026-07-20","00:00:00","2026-08-08","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1.,3. + TV. "]
[null,"SZCZ","V-021571/24","Plzen - Praha","< >","Praha-Vršovice","Praha-Kačerov",2025,2025,14,14,"2025-04-03","23:30:00","2025-04-04","04:40:00","1 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-004677/23","Praha - Chocen - Česká Třebová","< >","Borohrádek","Borohrádek",2025,2025,25,25,"2025-06-20","00:00:00","2025-06-22","23:59:00","3 days","Continuous","Switch",null,"ST",null,null,"X",null,null,null,null,null,"2 bez TV, výh.: 9. "]
[null,"SZCZ","V-006259/24","Praha - Chocen - Česká Třebová","< >","Česká Třebová","Odb Parník",2026,2026,7,8,"2026-02-14","00:00:00","2026-02-20","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-022455/24","Praha - Chocen - Česká Třebová","< >","Choceň","Týniště nad Orlicí",2025,2025,14,14,"2025-04-02","07:00:00","2025-04-03","13:00:00","1 days + 6 hours","Continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-16"]
[null,"SZCZ","V-003367/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2026,2026,28,29,"2026-07-06","00:00:00","2026-07-13","23:59:00","8 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"2,4 + TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-005964/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,17,18,"2025-04-25","18:00:00","2025-04-28","06:00:00","3 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005923/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,35,36,"2025-08-31","00:00:00","2025-09-01","23:59:00","2 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5-15,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006103/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,26,26,"2025-06-27","00:00:00","2025-06-29","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005871/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,21,22,"2025-05-23","18:00:00","2025-05-27","06:00:00","4 x 6 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005943/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,17,17,"2025-04-23","18:00:00","2025-04-27","06:00:00","4 x 6 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005984/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,16,17,"2025-04-15","18:00:00","2025-04-23","06:00:00","8 x 6 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005901/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,10,10,"2025-03-04","00:00:00","2025-03-04","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006084/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,15,15,"2025-04-12","00:00:00","2025-04-12","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006085/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,16,16,"2025-04-15","00:00:00","2025-04-15","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006086/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,25,26,"2025-06-22","00:00:00","2025-06-25","23:59:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,6,6s,8,10a,10c,12a,14a,16a,18a + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005856/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,8,9,"2025-02-19","00:00:00","2025-02-27","23:59:00","9 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006059/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,10,10,"2025-03-05","00:00:00","2025-03-08","23:59:00","4 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006063/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,19,20,"2025-05-10","00:00:00","2025-05-14","23:59:00","5 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006068/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,27,27,"2025-07-01","00:00:00","2025-07-02","23:59:00","2 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006070/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,28,28,"2025-07-11","00:00:00","2025-07-11","23:59:00","1 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006071/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,32,32,"2025-08-08","00:00:00","2025-08-08","23:59:00","1 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,2s,3a,3b,5,7,13s + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-008930/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,18,18,"2025-05-01","00:00:00","2025-05-04","23:59:00","4 x 11 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ, 2x PZZ.",null,null,null,"2024-01-05"]
[null,"SZCZ","V-008923/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,18,19,"2025-05-01","00:00:00","2025-05-07","23:59:00","7 x 11 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. PZZ P4001.",null,null,null,"2024-01-05"]
[null,"SZCZ","V-004675/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Opatovice-Pohřebačka",2025,2025,37,37,"2025-09-10","00:00:00","2025-09-13","23:59:00","4 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-004671/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-19","23:59:00","3 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006241/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,14,27,"2026-04-01","00:00:00","2026-06-30","23:59:00","91 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"13,15 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006240/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,14,53,"2026-04-01","00:00:00","2026-12-31","23:59:00","275 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"25 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006239/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,8,14,"2026-02-22","00:00:00","2026-03-31","23:59:00","38 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"23 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006238/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,8,53,"2026-02-22","00:00:00","2026-12-31","23:59:00","313 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"17 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006237/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,1,5,"2026-01-01","00:00:00","2026-01-28","23:59:00","28 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3b bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,32,33,"2026-08-03","00:00:00","2026-08-12","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-005964/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,17,18,"2025-04-25","18:00:00","2025-04-28","06:00:00","3 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-011503/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,21,21,"2025-05-20","00:00:00","2025-05-21","23:59:00","2 x 8 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-011459/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,42,42,"2025-10-14","00:00:00","2025-10-14","23:59:00","1 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"13-33,51-59 jen TV, 1,2-14a + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-011473/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,10,13,"2025-03-03","18:00:00","2025-03-30","06:00:00","19 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-011418/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,19,19,"2025-05-08","00:00:00","2025-05-10","23:59:00","3 x 8 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-011421/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,21,21,"2025-05-19","00:00:00","2025-05-19","23:59:00","1 x 8 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-005841/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,47,47,"2025-11-20","18:00:00","2025-11-22","06:00:00","2 x 8 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null," ,X,X",null,null,"2,6,8,13-33,51-59 jen TV, 1,13-17 + TV. "]
[null,"SZCZ","V-011445/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,34,34,"2025-08-23","00:00:00","2025-08-24","23:59:00","2 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-011447/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,34,34,"2025-08-23","00:00:00","2025-08-24","23:59:00","2 x 3 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"4a,12a-18a jen TV, 1,2,6,8,10a + TV. "]
[null,"SZCZ","V-006151/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2025,2025,18,18,"2025-05-01","00:00:00","2025-05-02","23:59:00","2 x 11 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-011466/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,50,50,"2025-12-14","00:00:00","2025-12-14","23:59:00","1 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,6,8,13,13c,15,19,21,33,51-59 jen TV. "]
[null,"SZCZ","V-004671/23","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2025,2025,25,25,"2025-06-17","00:00:00","2025-06-19","23:59:00","3 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-022550/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,15,15,"2025-04-07","10:10:00","2025-04-07","11:00:00","1 x 1 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-022551/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,16,16,"2025-04-14","10:10:00","2025-04-14","11:00:00","1 x 1 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-022552/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2025,2025,18,18,"2025-04-28","10:10:00","2025-04-28","11:50:00","1 x 2 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null,null,null,null,"1.,2.,2s,3a,3b,5.,5a,7.,7a,9.,11.,13.,13s,15.,17.,19.,21.,23.,25.,27. jen TV. "]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-26","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2027,2027,11,28,"2027-03-16","00:00:00","2027-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L.."]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Předměřice nad Labem",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ."]
[null,"SZCZ","V-002986/24","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2025,2025,23,24,"2025-06-05","18:00:00","2025-06-10","06:00:00","3 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-019613/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2025,2025,9,10,"2025-02-28","00:00:00","2025-03-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-022353/24","Praha - Chocen - Česká Třebová","< >","Kolín","Kolín",2025,2025,15,15,"2025-04-10","22:50:00","2025-04-13","05:00:00","3 x 7 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"108.,108a,110.,110a,110b,112.,112a jen TV. "]
[null,"SZCZ","V-015929/23","Praha - Chocen - Česká Třebová","< >","Kolín","Velký Osek",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-08","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,10,12,"2027-03-08","00:00:00","2027-03-24","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-019613/21","Praha - Chocen - Česká Třebová","< >","Kolín vjezd.náv.L","Záboří nad Labem",2025,2025,9,10,"2025-02-28","08:00:00","2025-03-05","04:00:00","4 days + 20 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-022587/24","Praha - Chocen - Česká Třebová","< >","Kolín vjezd.náv.L","Záboří nad Labem",2025,2025,16,16,"2025-04-15","16:00:00","2025-04-16","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-018571/24","Praha - Chocen - Česká Třebová","< >","Kolín-Hradišťko","Velký Osek",2025,2025,8,8,"2025-02-22","08:00:00","2025-02-23","18:00:00","1 days + 10 hours","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-015288/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2025,2025,48,48,"2025-11-25","00:00:00","2025-11-28","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015288/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2025,2025,48,48,"2025-11-25","00:00:00","2025-11-28","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-002786/24","Praha - Chocen - Česká Třebová","< >","Kostěnice","Kostěnice",2026,2026,43,43,"2026-10-19","00:00:00","2026-10-23","23:59:00","5 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"5.,7. jen TV. "]
[null,"SZCZ","V-015266/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2026,2026,20,21,"2026-05-15","00:00:00","2026-05-21","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015260/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Pardubice hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-015288/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2025,2025,48,48,"2025-11-25","00:00:00","2025-11-28","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015266/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2026,2026,20,21,"2026-05-17","00:00:00","2026-05-21","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015260/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Pardubice hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018463/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-006609/24","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015920/23","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,17,17,"2026-04-21","00:00:00","2026-04-24","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015920/23","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,17,17,"2026-04-21","00:00:00","2026-04-24","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. "]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,41,43,"2027-10-17","00:00:00","2027-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015290/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2025,2025,47,48,"2025-11-21","00:00:00","2025-11-24","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015279/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2025,2025,46,46,"2025-11-11","00:00:00","2025-11-15","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015290/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2025,2025,47,48,"2025-11-21","00:00:00","2025-11-24","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015279/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2025,2025,46,46,"2025-11-11","00:00:00","2025-11-15","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015277/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-07","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015270/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015279/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2025,2025,46,46,"2025-11-11","00:00:00","2025-11-15","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015290/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2025,2025,47,48,"2025-11-21","00:00:00","2025-11-24","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015277/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-07","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015270/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-005933/24","Praha - Chocen - Česká Třebová","< >","Odb Parník","Česká Třebová",2025,2025,12,12,"2025-03-19","18:00:00","2025-03-22","06:00:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-005905/24","Praha - Chocen - Česká Třebová","< >","Odb Parník","Č.Třebová odj.sk.",2025,2025,10,10,"2025-03-04","18:00:00","2025-03-07","06:00:00","3 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. "]
[null,"SZCZ","V-005862/24","Praha - Chocen - Česká Třebová","< >","Odb Parník","Č.Třebová odj.sk.",2025,2025,5,6,"2025-01-29","00:00:00","2025-02-09","23:59:00","12 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. "]
[null,"SZCZ","V-006258/24","Praha - Chocen - Česká Třebová","< >","Odb Parník","Česká Třebová",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-13","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. "]
[null,"SZCZ","V-011487/24","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Hradec Králové hl.n.",2025,2025,18,18,"2025-05-03","00:00:00","2025-05-03","23:59:00","1 x 3 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-011482/24","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Hradec Králové hl.n.",2025,2025,12,12,"2025-03-17","18:00:00","2025-03-21","06:00:00","4 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-011480/24","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Hradec Králové hl.n.",2025,2025,11,12,"2025-03-15","18:00:00","2025-03-17","06:00:00","2 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-008934/24","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Hradec Králové hl.n.",2025,2025,18,19,"2025-05-04","18:00:00","2025-05-05","06:00:00","2 x 2 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"traťová bez TV. "]
[null,"SZCZ","V-008930/24","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Hradec Králové hl.n.",2025,2025,18,18,"2025-05-01","00:00:00","2025-05-04","23:59:00","4 x 11 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ, 4x PZZ."]
[null,"SZCZ","V-004675/23","Praha - Chocen - Česká Třebová","< >","Opatovice-Pohřebačka","Odb Plačice",2025,2025,37,37,"2025-09-10","00:00:00","2025-09-13","23:59:00","4 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-015151/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,17,18,"2025-04-25","00:00:00","2025-04-29","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-015150/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,16,17,"2025-04-20","00:00:00","2025-04-24","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005987/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,18,18,"2025-04-30","00:00:00","2025-05-01","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-005332/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,20,20,"2025-05-17","00:00:00","2025-05-17","23:59:00","1 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-005315/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,18,20,"2025-05-02","00:00:00","2025-05-15","23:59:00","14 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-003004/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,25,25,"2025-06-16","18:00:00","2025-06-17","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-003001/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,24,25,"2025-06-15","18:00:00","2025-06-16","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-015151/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,17,18,"2025-04-25","00:00:00","2025-04-29","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-015150/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,16,17,"2025-04-20","00:00:00","2025-04-24","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005315/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,18,20,"2025-05-02","00:00:00","2025-05-15","23:59:00","14 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015256/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Kostěnice",2026,2026,22,22,"2026-05-27","00:00:00","2026-05-31","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-012789/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,48,50,"2026-11-28","00:00:00","2026-12-09","23:59:00","12 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. TZZ."]
[null,"SZCZ","V-021475/24","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2025,2025,6,6,"2025-02-04","07:50:00","2025-02-04","12:50:00","1 x 5 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-015150/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,16,17,"2025-04-20","00:00:00","2025-04-24","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-015151/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2025,2025,17,18,"2025-04-25","00:00:00","2025-04-29","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015256/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Kostěnice",2026,2026,22,22,"2026-05-27","00:00:00","2026-05-31","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-020522/24","Praha - Chocen - Česká Třebová","< >","Praha M.n.-Sluncová","Praha-Libeň",2025,2025,11,13,"2025-03-12","22:20:00","2025-03-29","04:15:00","17 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"201. bez TV. "]
[null,"SZCZ","V-020312/24","Praha - Chocen - Česká Třebová","< >","Praha-Běchovice","Český Brod",2025,2025,9,9,"2025-02-25","07:00:00","2025-02-26","13:00:00","6 x 6 hours","Periodical","Catenary",null,"LT"]
[null,"SZCZ","V-020508/24","Praha - Chocen - Česká Třebová","< >","Praha-Libeň","Praha M.n.-Sluncová",2025,2025,10,10,"2025-03-03","22:20:00","2025-03-04","04:15:00","1 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"202. + TV. "]
[null,"SZCZ","V-020511/24","Praha - Chocen - Česká Třebová","< >","Praha-Libeň","Praha M.n.-Sluncová",2025,2025,10,31,"2025-03-04","23:50:00","2025-08-01","18:00:00","149 days + 19 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"202. + TV. "]
[null,"SZCZ","V-017598/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,15,"2025-04-05","00:00:00","2025-04-09","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017597/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,14,"2025-03-31","00:00:00","2025-04-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-017594/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,16,16,"2025-04-15","00:00:00","2025-04-19","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017593/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,15,16,"2025-04-10","00:00:00","2025-04-14","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-002999/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,24,24,"2025-06-13","18:00:00","2025-06-14","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-002993/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,24,24,"2025-06-11","18:00:00","2025-06-12","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-002997/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,24,24,"2025-06-14","18:00:00","2025-06-15","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-002995/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,24,24,"2025-06-12","18:00:00","2025-06-13","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017598/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,15,"2025-04-05","00:00:00","2025-04-09","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017597/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,14,"2025-03-31","00:00:00","2025-04-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-017594/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,16,16,"2025-04-15","00:00:00","2025-04-19","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017593/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,15,16,"2025-04-10","00:00:00","2025-04-14","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-017593/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,15,16,"2025-04-10","00:00:00","2025-04-14","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-017598/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,14,15,"2025-04-05","00:00:00","2025-04-09","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-022599/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,17,17,"2025-04-26","16:00:00","2025-04-27","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-022605/24","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,18,18,"2025-04-28","16:00:00","2025-04-29","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017594/22","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2025,2025,16,16,"2025-04-15","00:00:00","2025-04-19","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-005984/24","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2025,2025,20,21,"2025-05-18","00:00:00","2025-05-19","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005314/24","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2025,2025,23,23,"2025-06-04","00:00:00","2025-06-04","23:59:00","1 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005297/24","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2025,2025,21,23,"2025-05-20","00:00:00","2025-06-03","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005297/24","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2025,2025,21,23,"2025-05-20","00:00:00","2025-06-03","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-002989/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,23,24,"2025-06-08","18:00:00","2025-06-11","06:00:00","2 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-002776/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,13,13,"2025-03-26","00:00:00","2025-03-30","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-019610/21","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,11,12,"2025-03-15","00:00:00","2025-03-19","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-002776/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,13,13,"2025-03-26","00:00:00","2025-03-30","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-019610/21","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,11,12,"2025-03-15","00:00:00","2025-03-19","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-019610/21","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,11,12,"2025-03-15","04:00:00","2025-03-20","08:00:00","5 days + 4 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-002776/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,13,14,"2025-03-26","08:00:00","2025-03-31","08:00:00","5 days + 0 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-017597/22","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Přelouč",2025,2025,14,14,"2025-03-31","08:00:00","2025-04-05","04:00:00","4 days + 20 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-022593/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,15,16,"2025-04-12","08:00:00","2025-04-15","02:20:00","2 days + 19 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-022597/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2025,2025,17,17,"2025-04-24","16:00:00","2025-04-25","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-022598/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Přelouč",2025,2025,17,17,"2025-04-25","16:00:00","2025-04-26","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-022600/24","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Přelouč",2025,2025,17,18,"2025-04-27","16:00:00","2025-04-28","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,3,7,"2026-01-14","00:00:00","2026-02-13","23:59:00","31 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-016991/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,13,27,"2026-03-23","00:00:00","2026-07-01","23:59:00","69 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017141/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2027,2027,34,35,"2027-08-26","00:00:00","2027-08-31","23:59:00","6 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-018293/22","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2025,2025,33,33,"2025-08-11","00:00:00","2025-08-12","23:59:00","2 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-018295/22","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2025,2025,37,37,"2025-09-08","00:00:00","2025-09-08","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-006263/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Choceň",2026,2026,25,25,"2026-06-15","00:00:00","2026-06-21","23:59:00","7 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-018293/22","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2025,2025,33,33,"2025-08-11","00:00:00","2025-08-12","23:59:00","2 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-018295/22","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2025,2025,37,37,"2025-09-08","00:00:00","2025-09-08","23:59:00","1 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-022612/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Bolehošť",2025,2025,22,22,"2025-05-29","09:20:00","2025-05-29","12:20:00","1 x 3 hours","Periodical","Bridge","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-020634/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Bolehošť",2025,2025,11,11,"2025-03-10","08:00:00","2025-03-14","16:00:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-016907/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,7,9,"2026-02-14","00:00:00","2026-02-28","23:59:00","15 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-016922/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-016925/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-023240/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Borohrádek",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,3,53,"2026-01-14","00:00:00","2026-12-31","23:59:00","352 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. "]
[null,"SZCZ","V-009151/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-006263/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Choceň",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-10","23:59:00","6 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. "]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2027,2027,48,52,"2027-12-01","00:00:00","2027-12-31","23:59:00","31 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. "]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,18,19,"2027-05-07","00:00:00","2027-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice."]
[null,"SZCZ","V-015280/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2025,2025,46,47,"2025-11-16","00:00:00","2025-11-20","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015280/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2025,2025,46,47,"2025-11-16","00:00:00","2025-11-20","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015278/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2026,2026,19,20,"2026-05-08","00:00:00","2026-05-11","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015274/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-03","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015249/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,16,16,"2026-04-14","00:00:00","2026-04-18","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015280/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2025,2025,46,47,"2025-11-16","00:00:00","2025-11-20","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015278/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2026,2026,19,20,"2026-05-08","00:00:00","2026-05-11","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015274/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-03","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015249/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,16,16,"2026-04-14","00:00:00","2026-04-18","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-022543/24","Praha - Chocen - Česká Třebová","< >","Újezd u Chocně","Čermná nad Orlicí",2025,2025,16,16,"2025-04-18","10:20:00","2025-04-18","11:40:00","1 x 2 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"traťová + TV. "]
[null,"SZCZ","V-022545/24","Praha - Chocen - Česká Třebová","< >","Újezd u Chocně","Čermná nad Orlicí",2025,2025,17,17,"2025-04-24","10:30:00","2025-04-24","13:00:00","1 x 3 hours","Periodical","Catenary",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. "]
[null,"SZCZ","V-018855/24","Praha - Chocen - Česká Třebová","< >","Ústí nad Orlicí","Moravany",2025,2025,7,7,"2025-02-11","08:00:00","2025-02-13","13:00:00","2 days + 5 hours","Continuous","Maintenance",null,"LT"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-018465/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-015931/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-02","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-015929/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Velký Osek",2026,2026,13,13,"2026-03-25","00:00:00","2026-03-28","23:59:00","4 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"záhlaví a zhlaví 2.traťové koleje směr Kolín."]
[null,"SZCZ","V-015921/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Velký Osek",2026,2026,13,14,"2026-03-29","00:00:00","2026-04-01","23:59:00","4 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"záhlaví a zhlaví 1.traťové koleje směr Kolín."]
[null,"SZCZ","V-015931/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-02","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-015921/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Kolín",2026,2026,15,15,"2026-04-09","00:00:00","2026-04-12","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Nymburk hl.n.",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","15 x 4 hours","Periodical","Catenary","T","LT"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,44,45,"2027-11-02","00:00:00","2027-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-002987/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín",2025,2025,23,23,"2025-06-06","18:00:00","2025-06-07","06:00:00","1 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-002775/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,12,13,"2025-03-21","00:00:00","2025-03-25","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-002553/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,20,20,"2025-05-16","18:00:00","2025-05-18","06:00:00","2 x 3 hours","Periodical","Others","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. "]
[null,"SZCZ","V-019614/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín",2025,2025,10,10,"2025-03-05","00:00:00","2025-03-09","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-019609/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,11,11,"2025-03-10","00:00:00","2025-03-14","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-002775/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,12,13,"2025-03-21","00:00:00","2025-03-25","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-019614/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Záboří nad Labem",2025,2025,10,10,"2025-03-05","00:00:00","2025-03-09","23:59:00","5 days","Continuous","Switch",null,"ST",null,null,null,null,null," ,X,X",null,null,"sudá jen TV, výh.: 20,21,22. "]
[null,"SZCZ","V-019609/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,11,11,"2025-03-10","00:00:00","2025-03-14","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-002553/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,20,20,"2025-05-16","18:00:00","2025-05-18","06:00:00","2 x 3 hours","Periodical","Others","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. "]
[null,"SZCZ","V-002775/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,12,13,"2025-03-21","08:00:00","2025-03-26","08:00:00","5 days + 0 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-019614/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín vjezd.náv.L",2025,2025,10,11,"2025-03-05","04:00:00","2025-03-10","08:00:00","5 days + 4 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-019609/21","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,11,11,"2025-03-10","08:00:00","2025-03-15","04:00:00","4 days + 20 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-022592/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,15,15,"2025-04-09","08:00:00","2025-04-12","08:00:00","3 days + 0 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-022591/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín vjezd.náv.L",2025,2025,16,16,"2025-04-16","16:00:00","2025-04-17","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-022596/24","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2025,2025,17,17,"2025-04-23","16:00:00","2025-04-24","02:20:00","0 days + 11 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-005288/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,10,11,"2026-03-08","00:00:00","2026-03-09","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015276/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,17,18,"2026-04-24","00:00:00","2026-04-28","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015251/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,16,17,"2026-04-19","00:00:00","2026-04-23","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015246/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-015241/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,12,13,"2026-03-21","00:00:00","2026-03-27","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-015241/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,12,13,"2026-03-21","00:00:00","2026-03-27","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-005099/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 x 12 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015276/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,17,18,"2026-04-24","00:00:00","2026-04-28","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015251/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,16,17,"2026-04-19","00:00:00","2026-04-23","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015246/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-022486/24","Regensburg - Plzen","< >","Česká Kubice","Furth im Wald",2025,2025,15,15,"2025-04-09","08:00:00","2025-04-11","14:00:00","6 x 6 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-022485/24","Regensburg - Plzen","< >","Domažlice","Furth im Wald",2025,2025,15,15,"2025-04-08","08:00:00","2025-04-11","14:00:00","3 days + 6 hours","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,41,52,"2026-10-07","00:00:00","2026-12-22","23:59:00","77 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,34,42,"2026-08-17","00:00:00","2026-10-18","23:59:00","63 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-13","23:59:00","56 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-007221/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2025,2025,50,52,"2025-12-14","00:00:00","2025-12-31","23:59:00","18 days","Continuous","Signal","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-022483/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Vejprnice",2025,2025,14,14,"2025-04-01","08:00:00","2025-04-04","14:00:00","8 x 6 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-019018/21","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,8,33,"2026-02-16","00:00:00","2026-08-16","23:59:00","182 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-014555/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-13","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-014554/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-18","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015698/23","Regensburg - Plzen","< >","Staňkov","Domažlice",2025,2025,14,15,"2025-03-31","00:00:00","2025-04-11","23:59:00","12 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-022873/24","Regensburg - Plzen","< >","Staňkov-Vránov","Horšovský Týn",2025,2025,16,16,"2025-04-14","08:50:00","2025-04-14","14:50:00","1 x 6 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015698/23","Regensburg - Plzen","< >","Stod","Domažlice",2025,2025,15,15,"2025-04-07","08:10:00","2025-04-11","14:45:00","4 days + 7 hours","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311013","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311003","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Komplexná rekonštrukcia diaľnično-železničného mosta",null,"Y",null,"2024-01-05"]
[null,"ŽSR","56TT2311009","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311002","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,"Y",null,"2024-01-05"]
[null,"ŽSR","56TT2311007","Bratislava - Štúrovo","< >","Dvory nad Žitavou","Dvory nad Žitavou",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 ",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311001","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ETCS",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311012","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311001","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ETCS",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311010","Kúty - Bratislava","< >","Malacky","Kúty",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311011b","Kúty - Galanta","< >","Bratislava-Rača","Trnava",2025,2026,1,9,"2025-01-01T08:00:00",45658.333333333336,"2026-02-28T17:00:00","00:00:00","371 x 23h 59min every week","Periodical","signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava",null,"N",null,"2024-01-05"]
[null,"ŽSR","56TT2311008","Kúty - Galanta","< >","Šelpice","Boleráz",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č.1",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311011a","Kúty - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany",null,null,null,"2024-01-05"]
[null,"ŽSR","A10044.1","Ostrava - Zilina","< >","Čadca","Krásno nad Kysucou",2025,2025,36,44,"1.9.2025","08:00:00","30.10.2025","17:00:00",null,"Periodical","track & rail",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia trate - Stabilizácia zosuvu trate",null,"Y",null,"2024-01-05"]
[null,"ŽSR","A13225","Zilina - Cierna nad Tisou","< >","Bánovce nad Ondavou","Humenné",2025,2026,44,23,"2025-11-01","00:01:00","2026-06-01","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Elektrifikácia a modernizácia staničných koľají a výhybiek a traťovej koľaje",null,"Y",null,"2024-01-05"]
[null,"ŽSR","3317/00/2025","Zilina - Cierna nad Tisou","< >","Košice","Košice",2025,2025,22,52,"2025-06-01","08:00:00","2025-12-31","16:00:00",null,"Periodical","signal&control",null,"LT",null,null,null,null,null,null,null,null,"modernizácia stavadla",null,"Y",null,"2024-01-05"]
[null,"ŽSR","A14256","Zilina - Cierna nad Tisou","< >","Košice","Košice",2025,2025,1,22,"2025-01-01","08:00:00","2025-05-31","16:00:00",null,"Periodical","others",null,"LT",null,null,null,null,null,null,null,null,"platform recostruction",null,"Y",null,"2024-01-05"]
[null,"ŽSR",5625269,"Zilina - Cierna nad Tisou","< >","Nižná Myšľa","Ruskov",2024,2025,22,52,"2024-06-01","08:00:00","2025-12-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,null,null,"2024-01-05"]
[null,"ŽSR",5625271,"Zilina - Cierna nad Tisou","< >","Spišská Nová Ves","Vydrník",2024,2026,31,31,"2024-08-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105,null,null,null,"2024-01-05"]
[null,"ŽSR",5625268,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2024,2025,14,14,"2024-04-01","08:00:00","2025-03-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,null,null,"2024-01-05"]
[null,"ŽSR",5625274,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01","08:00:00","2026-06-30","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101]
[null,"ŽSR",5625274,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01","08:00:00","2026-06-30","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y"]
[null,"ŽSR","056KE2212131","Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01T08:00:00",45778.333333333336,"2026-06-30T16:00:00","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y"]
[null,"ŽSR",5625272,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,1,14,"2024-01-01","08:00:00","2026-03-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105]
[null,"ŽSR",5625275,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,14,31,"2024-04-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"105, TK 1/2, Modernizácia"]
[null,"ŽSR",5626156,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad Tatry",2025,2028,9,4,"2025-03-02","08:00:00","2028-01-29","17:00:00",null,"Continuous","miscellaneous",null,"x","x",null,null,null,null,null,null,null,"Modernisation",null,"Y"]

{"sheet":"Graphic Overview","index":2,"n_rows":196,"n_cols":374,"rows_kept":196,"cut":false,"hidden":false,"merged":[[3,364,3,370],[3,371,3,373],[3,189,3,195],[3,196,3,202],[3,203,3,209],[3,210,3,216],[3,217,3,223],[3,336,3,342],[3,343,3,349],[3,350,3,356],[3,357,3,363],[3,224,3,230],[3,231,3,237],[3,238,3,244],[3,245,3,251],[3,252,3,258],[3,9,3,13],[3,14,3,20],[3,21,3,27],[3,28,3,34],[3,35,3,41],[3,42,3,48],[3,49,3,55],[3,56,3,62],[3,63,3,69],[3,70,3,76],[3,259,3,265],[3,266,3,272],[3,273,3,279],[3,280,3,286],[3,322,3,328],[3,329,3,335],[3,287,3,293],[3,294,3,300],[3,301,3,307],[3,308,3,314],[3,315,3,321],[3,161,3,167],[3,168,3,174],[3,175,3,181],[3,182,3,188],[3,77,3,83],[3,84,3,90],[3,91,3,97],[3,147,3,153],[3,98,3,104],[3,105,3,111],[3,112,3,118],[3,119,3,125],[3,126,3,132],[3,133,3,139],[3,140,3,146],[3,154,3,160],[2,343,2,373],[2,313,2,342],[0,1,1,7],[2,9,2,39],[2,282,2,312],[2,99,2,128],[2,129,2,159],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,40,2,67],[2,68,2,98]]}
[null,"RFC 9 Overview"]
[]
[null,null,null,null,null,null,2025,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Frankfurt - Karlsruhe",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Karlsruhe - Strasbourg",null,null,null,null,null,null,null,1,1,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,5,5,5,5,5,5,5,2,2,2,5,5,5,5,5,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,5,5,5,5,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,2,2,2,2,2,2,5,5,5,5,2,2,2,2,2,2,5,5,5,5,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Darmstadt - Nürnberg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nürnberg - Passau",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nürnberg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,5,5,null,5,5,null,null,null,null,null,null,null,null,null,null,5,5,5,null,5,5,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,2,2,2,2,2,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null," "]
[]
[null,"Regensburg - Plzen",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,null,null,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Passau - Wels",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Karlsruhe - München",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"München - Salzburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"München - Regensburg"]
[null," "]
[]
[null,"Salzburg - Wels",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wels - Linz",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wels - Traun - Linz",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Linz - Wien (NRZ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Linz - Wien (GZ)",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Wien - Hegyeshalom",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5]
[null," "]
[]
[null,"Sopron - Györ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Hegyeshalom - Rajka"]
[null," "]
[]
[null,"Hegyeshalom-Ferencváros",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,null,null,null,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,3,3,null,null,3,3,3,null,null,3,3,null,null,null,null,null,null,null,3,null,3,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,null,null,null,3,3,3,3,3,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,null,null,3,3,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros-Szajol",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,null,null,null,null,null,null,null,null,null,null,3,3,3,3,null,null,null,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros-Szajol (120)"]
[null," "]
[]
[null,"Szajol-Curtici",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Szajol - Biharkeresztes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5]
[null," "]
[]
[null,"Arad - Simeria",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Arad - Craiova",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Simeria -  Brasov",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Bucuresti-Constanta",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Coslariu - Cluj Napoca"]
[null," "]
[]
[null,"Biharkeresztes - Cluj Napoca",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Curtici - Arad"]
[null," "]
[]
[null,"Wilhelmshaven - Bremen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,null,null,null,null,5,5,5,5,5,5,5,5,5,2,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,null,null,5,5,5,5,null,null,null,5,5,5,5,5,null,null,null,null,5,5,5,5,5,5,5,5,5,null,null,null,5,5,5,5,null,null,null,5,5,5,5,5,5,5,5,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,5,5,5,5,5,null,null,null,null,5,5,5,5,5,5,5,5,5,5,null,null,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Bremerhaven - Bremen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,2,5,5,2,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,2,5,5,2,2,2,2,5,5,5,5,5,5,5,2,2,2,5,5,5,5,2,2,2,5,5,5,5,2,5,5,2,2,2,5,5,5,5,5,2,2,2,2,2,2,5,5,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,2,2,2,2,2,5,5,5,5,5,2,5,5,5,5,5,5,null,5,5,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,5,5,5,5,null,null,null,null,null,null,null,null,null,2,2,2,2,2,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Bremen - Hannover",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5]
[null," "]
[]
[null,"Hannover - Magdeburg",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,5,5,2,2,5,5,5,5,5,5,5,5,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,5,5,5,5,5,2,2,2,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Magdeburg - Falkenberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,5,5,5,5,2,2,2,2,2,5,5,5,5,5,5,5,5,5,2,2,2,5,5,null,null,null,null,null,5,5,5,5,null,null,null,null,null,null,null,2,2,2,5,5,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,2,2,2,2,2,null,null,5,5,5,5,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,2,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2]
[null," "]
[]
[null,"Falkenberg - Dresden",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null," "]
[]
[null,"Hamburg - Magdeburg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Rostock - Berlin",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Berlin - Dresden",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Dresden - Děčín",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Děčín - Kolín",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,1,1,1,null,1,1,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Děčín - Praha-Libeň",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Praha - Chocen - Česká Třebová",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,3,4,3,3,3,1,1,2,3,3,3,2,1,1,2,2,2,2,2,3,3,1,1,1,1,3,3,3,4,4,4,4,3,3,3,4,4,4,4,4,3,3,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,4,4,3,3,3,3,4,4,3,3,3,3,3,3,3,3,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,1,1,null,null,null,null,null,null,1,1,null,null,null,null,null,null,1,null,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,null,null,null,null,null,null,null,null,null,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null," "]
[]
[null,"Hranice na Morave - Ostrava"]
[null," "]
[]
[null,"Plzen - Praha",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,3,3,3,4,4,4,4,4,4,4,4,4,4,4,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Zilina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ostrava - Zilina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Zilina - Cierna nad Tisou",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kolín - Brno-Maloměřice",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,3,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,5,5,3,3,3,3,3,3,3,3,3,5,5,5,5,5,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Česká Třebová - Brno",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,1,1,1,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null," "]
[]
[null,"Brno - Břeclav",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Břeclav - Wien",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Břeclav - Kúty",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kúty - Bratislava",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Rajka",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Štúrovo"]
[null," "]
[]
[null,"Nové Zámky - Komárom"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Rajka - Hegyeshalom",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Štúrovo - Ferencváros"]
[null," "]
[]
[null,"Kúty - Galanta",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Chocen - Hranice na Morave",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,4,4,4,4,4,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,3,4,4,3,3,4,4,4,4,4,4,3,3,3,3,3,4,4,3,3,4,4,4,4,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":65,"n_cols":23,"rows_kept":65,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Frankfurt - Karlsruhe",1,"< >","Continuous",26188,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Karlsruhe - Strasbourg",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Darmstadt - Nürnberg",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Nürnberg - Passau",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Nürnberg - Plzen",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Regensburg - Plzen",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["SNCF-R",87,"Passau - Wels",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["CFR",53,"Karlsruhe - München",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,"München - Salzburg",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"München - Regensburg",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Salzburg - Wels",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Wels - Linz",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Wels - Traun - Linz",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Linz - Wien (NRZ)",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Linz - Wien (GZ)",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"Wien - Hegyeshalom",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"Wien - Ebenfurth - Sopron",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Sopron - Györ",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Rajka - Hegyeshalom",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Hegyeshalom - Rajka",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Hegyeshalom-Ferencváros",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Ferencváros-Szajol",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Ferencváros-Szajol (120)",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Szajol-Curtici",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Szajol - Biharkeresztes",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Arad - Simeria",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Arad - Craiova",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Simeria -  Brasov",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Bucuresti-Constanta",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Coslariu - Cluj Napoca",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Biharkeresztes - Cluj Napoca",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Curtici - Arad",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Wilhelmshaven - Bremen",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Bremerhaven - Bremen",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Bremen - Hannover",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Hannover - Magdeburg",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Magdeburg - Falkenberg",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Falkenberg - Dresden",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Hamburg - Magdeburg",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Rostock - Berlin",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Berlin - Dresden",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Dresden - Děčín",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Děčín - Kolín",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Děčín - Praha-Libeň",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Praha - Chocen - Česká Třebová",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Hranice na Morave - Ostrava",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Plzen - Praha",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,"Hranice na Morave - Zilina",48,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,"Ostrava - Zilina",49,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,"Zilina - Cierna nad Tisou",50,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,"Kolín - Brno-Maloměřice",51,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,"Česká Třebová - Brno",52,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]
[null,null,"Brno - Břeclav",53]
[null,null,"Břeclav - Wien",54]
[null,null,"Břeclav - Kúty",55]
[null,null,"Kúty - Bratislava",56]
[null,null,"Bratislava - Rajka",57]
[null,null,"Bratislava - Štúrovo",58]
[null,null,"Nové Zámky - Komárom",59]
[null,null,"Kúty - Galanta",60]
[null,null,"Rajka - Hegyeshalom",61]
[null,null,"Štúrovo - Ferencváros",62]
[null,null,"Kúty - Galanta",63]
[null,null,"Chocen - Hranice na Morave"]