{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":3,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2025,20]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":12190,"n_cols":37,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,34,2,34],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Weekdays","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"CFR",5325844,"Arad - Simeria","< >","Campuri Surduc","Zam",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-12","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-22"]
[null,"CFR",5325847,"Arad - Simeria","< >","Zam","Ilteu",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-12","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5325866,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,6,6,"2026-02-02","00:00:00","2026-02-08","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-01-10"]
[null,"CFR",5325867,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,30,33,"2026-07-24","00:00:00","2026-08-14","23:59:00","22d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-01-10"]
[null,"CFR",5325873,"Simeria -  Brasov","< >","Brașov",null,2025,2025,34,46,"2025-08-23","00:00:00","2025-11-15","23:59:00","85d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5325874,"Simeria -  Brasov","< >","Brașov",null,2025,2027,46,8,"2025-11-16","00:00:00","2027-02-28","23:59:00","470d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325875,"Simeria -  Brasov","< >","Brașov",null,2027,2027,9,28,"2027-03-01","00:00:00","2027-07-15","23:59:00","137d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325876,"Simeria -  Brasov","< >","Brașov",null,2027,2027,28,48,"2027-07-16","00:00:00","2027-12-05","23:59:00","143d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325878,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2025,22,44,"2025-05-31","00:00:00","2025-10-27","23:59:00","150d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325879,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325880,"Simeria -  Brasov","< >","Brașov","Stupini",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325883,"Simeria -  Brasov","< >","Stupini",null,2025,2025,22,44,"2025-05-31","00:00:00","2025-10-27","23:59:00","150d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325884,"Simeria -  Brasov","< >","Stupini",null,2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325885,"Simeria -  Brasov","< >","Stupini",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325888,"Simeria -  Brasov","< >","Stupini","Bod",2025,2026,14,14,"2025-04-01","00:00:00","2026-04-01","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325889,"Simeria -  Brasov","< >","Stupini","Bod",2026,2027,14,48,"2026-04-01","00:00:00","2027-12-05","23:59:00","614d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325892,"Simeria -  Brasov","< >","Bod",null,2025,2027,30,28,"2025-07-23","00:00:00","2027-07-15","23:59:00","723d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325893,"Simeria -  Brasov","< >","Bod",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325896,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2026,27,19,"2025-07-04","00:00:00","2026-05-06","23:59:00","307d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5325897,"Simeria -  Brasov","< >","Bod","Feldioara",2026,2027,19,48,"2026-05-06","00:00:00","2027-12-05","23:59:00","579d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5325898,"Simeria -  Brasov","< >","Bod","Feldioara",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5325901,"Simeria -  Brasov","< >","Feldioara",null,2025,2026,27,17,"2025-07-04","00:00:00","2026-04-23","23:59:00","294d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-24"]
[null,"CFR",5325902,"Simeria -  Brasov","< >","Feldioara",null,2026,2027,17,28,"2026-04-23","00:00:00","2027-07-15","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5325903,"Simeria -  Brasov","< >","Feldioara",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5325905,"Simeria -  Brasov","< >","Feldioara","Apața",2025,2026,27,6,"2025-07-04","00:00:00","2026-02-02","23:59:00","214d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5325906,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,7,30,"2026-02-09","00:00:00","2026-07-23","23:59:00","165d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5325907,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,33,49,"2026-08-15","00:00:00","2026-11-30","23:59:00","108d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5325908,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2027,49,48,"2026-11-30","00:00:00","2027-12-05","23:59:00","371d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5325909,"Simeria -  Brasov","< >","Feldioara","Apața",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5325910,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5325911,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5325912,"Simeria -  Brasov","< >","Apața",null,2026,2026,17,33,"2026-04-20","00:00:00","2026-08-14","23:59:00","117d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5325913,"Simeria -  Brasov","< >","Apața",null,2026,2026,33,44,"2026-08-15","00:00:00","2026-10-30","23:59:00","77d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5325914,"Simeria -  Brasov","< >","Apața",null,2026,2027,44,28,"2026-10-31","00:00:00","2027-07-15","23:59:00","258d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5325915,"Simeria -  Brasov","< >","Apața",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5325916,"Simeria -  Brasov","< >","Apata","Augustin",2025,2025,3,45,"2025-01-13","00:00:00","2025-11-07","23:59:00","299d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5325917,"Simeria -  Brasov","< >","Apata","Augustin",2025,2026,46,32,"2025-11-10","00:00:00","2026-08-03","23:59:00","267d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-29"]
[null,"CFR",5325919,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-29"]
[null,"CFR",5325921,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5325924,"Simeria -  Brasov","< >","Rupea","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5325926,"Simeria -  Brasov","< >","Rupea","Cata",2025,2026,30,31,"2025-07-25","00:00:00","2026-07-27","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5325927,"Simeria -  Brasov","< >","Rupea","Cata",2026,2026,31,38,"2026-07-28","00:00:00","2026-09-15","23:59:00","50d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5325928,"Simeria -  Brasov","< >","Cata","Rupea",2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5325929,"Simeria -  Brasov","< >","Cata","Rupea",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5325930,"Simeria -  Brasov","< >","Cata",null,2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5325931,"Simeria -  Brasov","< >","Cata",null,2026,2026,3,42,"2026-01-15","00:00:00","2026-10-15","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5325932,"Simeria -  Brasov","< >","Cata",null,2026,2027,42,7,"2026-10-15","00:00:00","2027-02-16","23:59:00","125d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5325933,"Simeria -  Brasov","< >","Cata","Beia",2025,2026,3,3,"2025-01-15","00:00:00","2026-01-14","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5325934,"Simeria -  Brasov","< >","Cata","Beia",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5325935,"Simeria -  Brasov","< >","Cata","Beia",2027,2027,7,43,"2027-02-17","00:00:00","2027-10-25","23:59:00","251d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5325936,"Simeria -  Brasov","< >","Beia","Mureni",2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5325937,"Simeria -  Brasov","< >","Beia","Mureni",2026,2027,10,43,"2026-03-05","00:00:00","2027-10-25","23:59:00","600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-22"]
[null,"CFR",5325938,"Simeria -  Brasov","< >","Archita ","Vînători ",2027,2028,43,8,"2027-10-26","00:00:00","2028-02-26","23:59:00","124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5325939,"Simeria -  Brasov","< >","Mureni",null,2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-07-24"]
[null,"CFR",5325941,"Simeria -  Brasov","< >","Mureni","Vînători",2025,2027,35,43,"2025-08-30","00:00:00","2027-10-25","23:59:00","787d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5325945,"Simeria -  Brasov","< >","Vînători",null,2025,2026,35,20,"2025-08-30","00:00:00","2026-05-11","23:59:00","255d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5325946,"Simeria -  Brasov","< >","Vînători",null,2026,2028,20,8,"2026-05-11","00:00:00","2028-02-26","23:59:00","657d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5325948,"Simeria -  Brasov","< >","Vînători","Albești",2025,2026,20,20,"2025-05-13","00:00:00","2026-05-12","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5325953,"Simeria -  Brasov","< >","Albești","Sighișoara",2025,2026,17,10,"2025-04-24","00:00:00","2026-03-04","23:59:00","315d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5325954,"Simeria -  Brasov","< >","Sighișoara",null,2024,2027,34,50,"2024-08-21","00:00:00","2027-12-15","23:59:00","1212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5325956,"Simeria -  Brasov","< >","Sighișoara",null,2023,2027,41,43,"2023-10-11","00:00:00","2027-10-25","23:59:00","1476d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5325957,"Simeria -  Brasov","< >","Sighișoara",null,2023,2028,41,8,"2023-10-11","00:00:00","2028-02-26","23:59:00","1600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5325959,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-03-21"]
[null,"CFR",5325960,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2025-01-13"]
[null,"CFR",5325961,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj","Gârbău",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2025-01-17"]
[null,"CFR",5325962,"Biharkeresztes - Cluj Napoca","< >","Gârbău",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-08"]
[null,"CFR",5325963,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-09"]
[null,"CFR",5325964,"Biharkeresztes - Cluj Napoca","< >","Aghireș",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-07"]
[null,"CFR",5325965,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-09"]
[null,"CFR",5325966,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325967,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325968,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325969,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2027,16,23,"2024-04-15","00:00:00","2027-06-10","23:59:00","1152d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325970,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325971,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,41,9,"2024-10-10","00:00:00","2026-02-26","23:59:00","505d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13"]
[null,"CFR",5325972,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului","Bulz",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325973,"Biharkeresztes - Cluj Napoca","< >","Bulz",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325974,"Biharkeresztes - Cluj Napoca","< >","Bulz","Bratca",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325975,"Biharkeresztes - Cluj Napoca","< >","Bratca ",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325976,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-30"]
[null,"CFR",5325977,"Biharkeresztes - Cluj Napoca","< >","Suncuius",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325978,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5325979,"Biharkeresztes - Cluj Napoca","< >","Ciucea",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-08-13"]
[null,"CFR",5325980,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-16"]
[null,"CFR",5325981,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14"]
[null,"CFR",5325983,"Biharkeresztes - Cluj Napoca","< >","Cluj Napoca Est","Cluj",2024,2026,27,9,"2024-07-01","00:00:00","2026-02-28","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5325984,"Biharkeresztes - Cluj Napoca","< >","Alesd",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5325986,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5325989,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5325992,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5325995,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2027,42,22,"2025-10-19","00:00:00","2027-06-02","23:59:00","592d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5325999,"Biharkeresztes - Cluj Napoca","< >","Osorhei",null,2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326001,"Biharkeresztes - Cluj Napoca","< >","Osorhei","Oradea Est",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326004,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326006,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15"]
[null,"CFR",5326009,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea Vest",2026,2026,9,27,"2026-03-01","00:00:00","2026-07-01","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09"]
[null,"CFR",5326011,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea",2025,2027,50,19,"2025-12-11","00:00:00","2027-05-10","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5326012,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15"]
[null,"CFR",5326019,"Arad - Craiova","< >","Caransebes","Balta Sărată",2026,2026,27,28,"2026-07-03","00:00:00","2026-07-06","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326020,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2024,2025,49,49,"2024-12-03","00:00:00","2025-12-02","23:59:00","365d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326021,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2026,2026,28,44,"2026-07-07","00:00:00","2026-11-01","23:59:00","118d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326023,"Arad - Craiova","< >","Caransebes ","Zăgujeni",2025,2026,31,36,"2025-07-30","00:00:00","2026-09-01","23:59:00","399d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326026,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2025,48,48,"2025-11-24","00:00:00","2025-11-26","23:59:00","3d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326037,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326038,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326039,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326040,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5326042,"Arad - Craiova","< >","Lugoj","Costeiu Mare",2026,2026,8,14,"2026-02-21","00:00:00","2026-04-02","23:59:00","41d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326048,"Arad - Craiova","< >","Timișoara Est","Remetea Mică",2025,2026,23,36,"2025-06-02","00:00:00","2026-09-02","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326055,"Arad - Craiova","< >","Timișoara Est  ","Timișoara Est  ",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326056,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326057,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2027,18,2,"2026-05-01","00:00:00","2027-01-12","23:59:00","257d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326058,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326059,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326060,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17"]
[null,"CFR",5326061,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,44,45,"2026-10-27","00:00:00","2026-11-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17"]
[null,"CFR",5326062,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2027,2027,1,2,"2027-01-05","00:00:00","2027-01-12","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17"]
[null,"CFR",5326063,"Arad - Craiova","< >","Sânandrei","Sânandrei",2025,2025,42,43,"2025-10-17","00:00:00","2025-10-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17"]
[null,"CFR",5326064,"Arad - Craiova","< >","Sânandrei","Hodoni",2025,2025,34,43,"2025-08-24","00:00:00","2025-10-24","23:59:00","62d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326066,"Arad - Craiova","< >","Orțișoara",null,2025,2025,42,43,"2025-10-17","00:00:00","2025-10-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326067,"Arad - Craiova","< >","Orțișoara",null,2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326068,"Arad - Craiova","< >","Orțișoara",null,2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326069,"Arad - Craiova","< >","Ronat Triaj Gr.D","Orțișoara",2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326071,"Arad - Craiova","< >","Vinga","Sag",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326072,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2026,4,21,"2026-01-23","00:00:00","2026-05-23","23:59:00","121d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326073,"Arad - Craiova","< >","Aradu Nou","Arad",2026,2027,43,17,"2026-10-23","00:00:00","2027-04-26","23:59:00","186d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326074,"Arad - Craiova","< >","Valea Viilor","Arad",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326075,"Arad - Craiova","< >","Valea Viilor","Arad",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326076,"Arad - Craiova","< >","Orțișoara","Aradu Nou",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5326077,"Arad - Craiova","< >","Aradul Nou","Zădăreni ",2025,2026,2,4,"2025-01-09","00:00:00","2026-01-23","23:59:00","380d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5326078,"Arad - Craiova","< >","Glogovăț","Arad",2027,2027,39,41,"2027-10-01","00:00:00","2027-10-17","23:59:00","17d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5326079,"Arad - Craiova","< >","Caransebes",null,2025,2026,12,28,"2025-03-19","00:00:00","2026-07-06","23:59:00","475d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326080,"Arad - Craiova","< >","Caransebes",null,2026,2027,28,40,"2026-07-07","00:00:00","2027-10-04","23:59:00","455d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326083,"Arad - Craiova","< >","Zăgujeni","Zăgujeni",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326087,"Arad - Craiova","< >","Zăgujeni","Căvăran",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326088,"Arad - Craiova","< >","Zăgujeni","Căvăran",2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326089,"Arad - Craiova","< >","Căvăran",null,2024,2026,49,18,"2024-12-03","00:00:00","2026-05-02","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326090,"Arad - Craiova","< >","Căvăran",null,2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326091,"Arad - Craiova","< >","Jena","Găvojdia",2026,2026,18,18,"2026-04-27","00:00:00","2026-05-02","23:59:00","6d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326092,"Arad - Craiova","< >","Căvăran","Găvojdia",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326093,"Arad - Craiova","< >","Găvojdia",null,2026,2026,11,12,"2026-03-14","00:00:00","2026-03-18","23:59:00","5d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326094,"Arad - Craiova","< >","Găvojdia",null,2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326095,"Arad - Craiova","< >","Găvojdia",null,2026,2026,12,36,"2026-03-19","00:00:00","2026-09-01","23:59:00","167d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326096,"Arad - Craiova","< >","Găvojdia","Lugoj",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326097,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2026,27,43,"2025-07-03","00:00:00","2026-10-23","23:59:00","478d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326099,"Arad - Craiova","< >","Lugoj",null,2025,2026,28,27,"2025-07-10","00:00:00","2026-07-03","23:59:00","359d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326100,"Arad - Craiova","< >","Lugoj","Jabăr",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326101,"Arad - Craiova","< >","Jabăr","Belinț",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326102,"Arad - Craiova","< >","Belinț",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326103,"Arad - Craiova","< >","Belinț","Chizătău",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326104,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326105,"Arad - Craiova","< >","Topolovat",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326106,"Arad - Craiova","< >","Topolovat","Recas",2025,2025,39,48,"2025-09-26","00:00:00","2025-11-26","23:59:00","62d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326107,"Arad - Craiova","< >","Topolovat","Recas",2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326108,"Arad - Craiova","< >","Recaș",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326109,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326110,"Arad - Craiova","< >","Remetea Mare",null,2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326111,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326112,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326113,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326114,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326115,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326116,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326117,"Arad - Craiova","< >","Belinț","Topolovat",2026,2027,45,22,"2026-11-03","00:00:00","2027-06-02","23:59:00","212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326118,"Arad - Craiova","< >","Lugoj – Belint","Lugoj – Belint",2026,2027,45,14,"2026-11-03","00:00:00","2027-04-06","23:59:00","155d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326119,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2027,2027,15,18,"2027-04-15","00:00:00","2027-05-04","23:59:00","20d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326122,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2025,2026,6,23,"2025-02-03","00:00:00","2026-06-01","23:59:00","484d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326124,"Arad - Craiova","< >","Timișoara Est","Timișoara Est",2024,2026,35,45,"2024-09-01","00:00:00","2026-11-02","23:59:00","793d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326125,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2025,2026,23,23,"2025-06-02","00:00:00","2026-06-01","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326126,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2027,23,2,"2026-06-01","00:00:00","2027-01-12","23:59:00","226d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5326127,"Arad - Craiova","< >","Timișoara Nord ",null,2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5326128,"Arad - Craiova","< >","Ronat Triaj Gr.D","Sânandrei",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5326129,"Arad - Craiova","< >","Sânandrei",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5326130,"Arad - Craiova","< >","Sânandrei",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5326131,"Arad - Craiova","< >","Sânandrei","Baile Calacea",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-28"]
[null,"CFR",5326132,"Arad - Craiova","< >","Băile Calacea",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-13"]
[null,"CFR",5326133,"Arad - Craiova","< >","Băile Calacea",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-13"]
[null,"CFR",5326134,"Arad - Craiova","< >","Baile Calacea","Orțișoara",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-13"]
[null,"CFR",5326135,"Arad - Craiova","< >","Orțișoara",null,2024,2025,26,43,"2024-06-25","00:00:00","2025-10-24","23:59:00","487d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5326136,"Arad - Craiova","< >","Orțișoara",null,2025,2027,43,4,"2025-10-24","00:00:00","2027-01-25","23:59:00","459d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5326137,"Arad - Craiova","< >","Orțișoara","Vinga",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5326138,"Arad - Craiova","< >","Vinga",null,2024,2026,26,4,"2024-06-25","00:00:00","2026-01-23","23:59:00","578d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5326139,"Arad - Craiova","< >","Vinga",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5326140,"Arad - Craiova","< >","Vinga","Sag",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5326141,"Arad - Craiova","< >","Sag",null,2024,2026,43,4,"2024-10-23","00:00:00","2026-01-23","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5326142,"Arad - Craiova","< >","Sag",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5326143,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5326144,"Arad - Craiova","< >","Valea Viilor",null,2024,2026,32,21,"2024-08-09","00:00:00","2026-05-23","23:59:00","653d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5326145,"Arad - Craiova","< >","Valea Viilor","Aradul Nou",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5326146,"Arad - Craiova","< >","Aradul Nou",null,2025,2026,4,4,"2025-01-21","00:00:00","2026-01-23","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5326147,"Arad - Craiova","< >","Aradul Nou",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5326148,"Arad - Craiova","< >","Glogovăț","Arad",2026,2026,4,38,"2026-01-23","00:00:00","2026-09-18","23:59:00","239d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06"]
[null,"CFR",5326149,"Arad - Craiova","< >","Glogovăț","Arad",2026,2027,38,2,"2026-09-18","00:00:00","2027-01-17","23:59:00","122d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06"]
[null,"CFR",5525651,"Simeria -  Brasov","< >","Stupini","Bod",2023,2025,22,48,"01.06.2023","00:00:00","27.11.2025","23:59:00","911d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525652,"Simeria -  Brasov","< >","Bod","Feldioara",2023,2025,14,48,"03.04.2023","00:00:00","27.11.2025","23:59:00","970d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525653,"Simeria -  Brasov","< >","Feldioara","Apața",2023,2025,7,48,"15.02.2023","00:00:00","27.11.2025","23:59:00","1017d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525657,"Simeria -  Brasov","< >","Cata","Rupea",2023,2026,5,50,"02.02.2023","00:00:00","12.12.2026","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525658,"Simeria -  Brasov","< >","Cața","Beia",2023,2026,5,9,"02.02.2023","00:00:00","01.03.2026","23:59:00","1124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09",null,null,"2,3",1]
[null,"CFR",5525659,"Simeria -  Brasov","< >","Beia","Mureni",2023,2026,44,40,"30.10.2023","00:00:00","30.09.2026","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,6,7",1]
[null,"CFR",5525663,"Simeria -  Brasov","< >","Cața","Archita",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3",1]
[null,"CFR",5525665,"Simeria -  Brasov","< >","Archita","Vînători ",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5525666,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2026,45,40,"09.11.2022","00:00:00","30.09.2026","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525667,"Simeria -  Brasov","< >","Vînători","Albești",2023,2026,24,20,"16.06.2023","00:00:00","12.05.2026","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5525675,"Simeria -  Brasov","< >","Racos-Rupea","Racos-Rupea",2024,2025,41,43,"2024-10-10","00:00:00","2025-10-25","23:59:00","381d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5525677,"Simeria -  Brasov","< >","Brașov","Stupini",2023,2026,22,12,"01.06.2023","00:00:00","16.03.2026","23:59:00","1020d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5525683,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5525689,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"5,6",1]
[null,"CFR",5525691,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"1,7",1]
[null,"CFR",5525699,"Simeria -  Brasov","< >","Cața","Beia",2025,2025,25,51,"17.06.2025","00:00:00","20.12.2025","23:59:00","187d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"4,5",1]
[null,"CFR",5525703,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,2,3,4",1]
[null,"CFR",5525704,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525708,"Simeria -  Brasov","< >","Beia","Mureni",2024,2025,40,51,"01.10.2024","00:00:00","20.12.2025","23:59:00","446d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"4,5,6,7",1]
[null,"CFR",5525710,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525712,"Simeria -  Brasov","< >","Archita","Vânători ",2025,2026,51,7,"2025-12-21","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5525714,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"2,3",1]
[null,"CFR",5525717,"Simeria -  Brasov","< >","Mureni","Vânători ",2024,2025,12,51,"18.03.2024","00:00:00","2025-12-20","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"2,3",1]
[null,"CFR",5525718,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525720,"Simeria -  Brasov","< >","Vânători ","Albești",2024,2025,12,51,"18.03.2024","00:00:00","20.12.2025","23:59:00","643d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5525723,"Simeria -  Brasov","< >","Albești","Sighișoara",2024,2025,49,51,"08.12.2024","00:00:00","20.12.2025","23:59:00","378d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5525726,"Biharkeresztes - Cluj Napoca","< >","Aghires","Poieni",2024,2025,1,52,"2024-01-01","00:00:00","2025-12-31","23:59:00","731d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525727,"Biharkeresztes - Cluj Napoca","< >","Poieni","Alesd",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525728,"Biharkeresztes - Cluj Napoca","< >","Alesd","Oradea",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,5,6,7",1]
[null,"CFR",5525730,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"5,6,7",1]
[null,"CFR",5525734,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-09-24",null,null,"1,5,6,7",1]
[null,"CFR",5525736,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525739,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525740,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525742,"Biharkeresztes - Cluj Napoca","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525743,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525744,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525745,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525746,"Biharkeresztes - Cluj Napoca","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525747,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525748,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525749,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5525750,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului ","Bulz",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5525751,"Biharkeresztes - Cluj Napoca","< >","Bulz ","Bratca",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5525752,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5525753,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3",1]
[null,"CFR",5525754,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525755,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525756,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525757,"Biharkeresztes - Cluj Napoca","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-23",null,null,"6,7",1]
[null,"CFR",5525758,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2024,2025,9,44,"01.03.2024","00:00:00","31.10.2025","23:59:00","610d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5525759,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525760,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,6,7",1]
[null,"CFR",5525761,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525762,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5525763,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525764,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2023,2025,44,44,"01.11.2023","00:00:00","31.10.2025","23:59:00","731d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525765,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5525766,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-02",null,null,"6,7",1]
[null,"CFR",5525767,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,7",1]
[null,"CFR",5525768,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2",1]
[null,"CFR",5525769,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2025-01-22",null,null,"3,4",1]
[null,"CFR",5525770,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2025-01-22",null,null,"4,5",1]
[null,"CFR",5525790,"Arad - Craiova","< >","Timișoara Est ","Timișoara Nord",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5525803,"Arad - Craiova","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5525806,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-13",null,null,"6,7",1]
[null,"CFR",5525808,"Arad - Craiova","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-28",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525809,"Arad - Craiova","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-13",null,null,"1,2,3,4,5",1]
[null,"CFR",5525810,"Arad - Craiova","< >","Ronat Triaj Gr.D ","Vinga",2026,2026,17,19,"2026-04-24","00:00:00","2026-05-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-05-31",null,null,"1,6,7",1]
[null,"CFR",5525811,"Arad - Craiova","< >","Ramificație Pod Mureș ","Glogovăț",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"1,6,7",1]
[null,"CFR",5525812,"Arad - Craiova","< >","Glogovăț","Arad",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-20",null,null,"1,6,7",1]
[null,"CFR",5525813,"Arad - Craiova","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-01",null,null,"1,4,5,6,7",1]
[null,"CFR",5525814,"Arad - Craiova","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,"5,6"]
[null,"DB InfraGO AG",4.1799999999999997E-3,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Ludwigsburg",2027,2027,11,12,"2027-03-19","21:00:00","2027-03-22","05:00:00","2d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-12-12",null,null,5]
[null,"DB InfraGO AG",4.1800000000000001E-31,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,5,6,7"]
[null,"DB InfraGO AG",3.2139999999999999E-28,"Karlsruhe - Strasbourg","<>","Mühlacker Kurve","Mühlacker Em Süd",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",3.2140000000000001E-25,"Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Kurve",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-17",null,null,"2,3"]
[null,"DB InfraGO AG",3.2139999999999999E-23,"Karlsruhe - München","<>","Mühlacker","Mühlacker",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,6,7"]
[null,"DB InfraGO AG",4.1800000000000001E-23,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,6,7"]
[null,"DB InfraGO AG",4.1799999999999998E-22,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,6,7"]
[null,"DB InfraGO AG",4.1799999999999997E-21,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",4.1800000000000001E-19,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",3.214E-18,"Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",4.1800000000000001E-18,"Karlsruhe - München",">","Kornwestheim Pbf","Ludwigsburg",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",3.2139999999999997E-17,"Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",4.1800000000000003E-17,"Karlsruhe - München",">","Kornwestheim Pbf","Ludwigsburg",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.1799999999999999E-16,"Karlsruhe - München","<>","Stuttgart-Zazenhausen","Kornwestheim Pbf",2027,2027,12,12,"2027-03-23","01:30:00","2027-03-26","04:30:00","3d, 3h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.2140000000000002E-15,"Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",4.1800000000000001E-15,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,12,12,"2027-03-22","05:00:00","2027-03-26","04:30:00","3d, 23h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",4.1800000000000002E-14,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,12,"2027-03-20","01:30:00","2027-03-22","04:30:00","2d, 3h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.1799999999999999E-13,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Ludwigsburg",2027,2027,11,12,"2027-03-20","01:30:00","2027-03-22","04:30:00","2d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.1800000000000004E-12,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Ludwigsburg",2027,2027,11,12,"2027-03-20","01:30:00","2027-03-22","04:30:00","2d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.3599999999999999E-11,"Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,47,47,"2026-11-17","23:00:00","2026-11-18","04:00:00","0d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.6820000000000002E-11,"Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,37,37,"2026-09-10","03:00:00","2026-09-10","05:30:00","0d, 2h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.18E-11,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,12,"2027-03-20","01:30:00","2027-03-22","04:30:00","2d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.6819999999999998E-10,"Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,37,37,"2026-09-10","03:00:00","2026-09-10","05:30:00","0d, 2h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.18E-10,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,12,"2027-03-19","21:00:00","2027-03-22","05:00:00","2d, 8h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.6819999999999999E-9,"Frankfurt - Karlsruhe","<>","Glems","Vaihingen (Enz)",2026,2026,37,37,"2026-09-09","23:00:00","2026-09-10","05:30:00","0d, 6h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",4.18E-9,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,12,"2027-03-19","21:00:00","2027-03-22","05:00:00","2d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.6820000000000001E-8,"Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,37,37,"2026-09-09","23:00:00","2026-09-10","03:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-06-09",null,null,"1,7"]
[null,"DB InfraGO AG",4.1799999999999997E-8,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,12,"2027-03-19","21:00:00","2027-03-22","05:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-09",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",2.8099999999999999E-7,"Karlsruhe - München","<>","Stuttgart-Untertürkheim","Stuttgart-Münster",2026,2026,26,26,"2026-06-25","07:00:00","2026-06-25","15:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.2140000000000001E-7,"Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Kurve",2026,2026,34,35,"2026-08-17","08:00:00","2026-08-28","17:00:00","11d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.3599999999999999E-7,"Nürnberg - Plzen","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,47,47,"2026-11-16","02:00:00","2026-11-16","06:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.6819999999999998E-7,"Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,37,37,"2026-09-09","01:00:00","2026-09-09","05:30:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-12-12",null,null,"1,2"]
[null,"DB InfraGO AG",3.9569999999999998E-7,"Darmstadt - Nürnberg","<","Nürnberg Hbf","Nürnberg-Reichelsdorf",2027,2027,14,15,"2027-04-05","21:00:00","2027-04-12","05:00:00","6d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"5,6,7"]
[null,"DB InfraGO AG",4.1800000000000001E-7,"Karlsruhe - München","<>","Stuttgart-Zazenhausen","Kornwestheim Pbf",2027,2027,11,12,"2027-03-19","21:00:00","2027-03-22","05:00:00","2d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-01",null,null,"5,6,7"]
[null,"DB InfraGO AG",2.8100000000000002E-6,"Karlsruhe - München","<>","Stuttgart-Münster","Stuttgart-Münster",2026,2026,26,26,"2026-06-25","07:00:00","2026-06-25","15:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-05",null,null,"5,6,7"]
[null,"DB InfraGO AG",3.36E-6,"Nürnberg - Plzen","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,47,47,"2026-11-16","01:00:00","2026-11-16","03:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-07-01",null,null,"1,5,6,7"]
[null,"DB InfraGO AG",3.6820000000000001E-6,"Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Glems",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-09","05:30:00","0d, 6h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2025-08-05",null,null,"6,7"]
[null,"DB InfraGO AG",4.1799999999999998E-6,"Karlsruhe - München","<>","Stuttgart-Zazenhausen","Kornwestheim Pbf",2027,2027,11,11,"2027-03-17","01:30:00","2027-03-19","04:30:00","2d, 3h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,7"]
[null,"DB InfraGO AG",2.8099999999999999E-5,"Karlsruhe - München",">","Stuttgart-Untertürkheim","Stuttgart-Zazenhausen",2026,2026,26,26,"2026-06-25","07:00:00","2026-06-25","15:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3"]
[null,"DB InfraGO AG",3.3599999999999997E-5,"Nürnberg - Plzen","<>","Neunkirchen a Sand","Hersbruck (rechts Pegnitz) Ost",2026,2026,47,47,"2026-11-16","01:00:00","2026-11-16","01:30:00","0d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"3,4,5"]
[null,"DB InfraGO AG",3.6820000000000003E-5,"Frankfurt - Karlsruhe","<","Langes Feld","Vaihingen (Enz)",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-09","01:00:00","0d, 2h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-08-05",null,null,6.7]
[null,"DB InfraGO AG",3.9140000000000001E-5,"Darmstadt - Nürnberg","<>","Hallstadt (b Bamberg)","Höflein",2027,2027,12,12,"2027-03-23","21:00:00","2027-03-25","05:00:00","1d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG",4.18E-5,"Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,11,11,"2027-03-17","01:30:00","2027-03-19","04:30:00","2d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-20",null,null,6.7]
[null,"DB InfraGO AG",2.81E-4,"Karlsruhe - München","<>","Stuttgart-Untertürkheim","Stuttgart-Untertürkheim",2026,2026,26,26,"2026-06-25","07:00:00","2026-06-25","15:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-10",null,null,"5,6,7"]
[null,"DB InfraGO AG",3.3599999999999998E-4,"Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,47,47,"2026-11-16","01:00:00","2026-11-16","03:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",3.9140000000000003E-4,"Darmstadt - Nürnberg",">","Bamberg","Oberhaid",2027,2027,12,12,"2027-03-23","21:00:00","2027-03-25","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.0259999999999997E-4,"München - Salzburg","<>","München Ost Pbf","München Ost Riedenburger Straße",2027,2027,2,5,"2027-01-16","22:40:00","2027-02-01","04:40:00","15d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",2.81E-3,"Karlsruhe - München","<>","Stuttgart-Münster","Stuttgart-Untertürkheim",2026,2026,26,26,"2026-06-24","07:00:00","2026-06-24","15:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",3.2139999999999998E-3,"Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-17","08:00:00","2026-08-28","17:00:00","11d, 9h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",3.3530000000000001E-3,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,39,40,"2026-09-27","00:01:00","2026-09-28","04:30:00","1d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",3.3600000000000001E-3,"Nürnberg - Plzen",">","Neunkirchen a Sand","Hersbruck (rechts Pegnitz) Ost",2026,2026,46,47,"2026-11-15","22:00:00","2026-11-16","01:30:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.1799999999999997E-3,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Ludwigsburg",2027,2027,11,11,"2027-03-17","01:30:00","2027-03-19","04:30:00","2d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.4099999999999999E-3,"Darmstadt - Nürnberg","<>","Erlangen Paul-Gossen-Straße","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6,7"]
[null,"DB InfraGO AG",2.81E-2,"Karlsruhe - München","<>","Stuttgart-Münster","Stuttgart-Münster",2026,2026,26,26,"2026-06-24","07:00:00","2026-06-24","15:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-09",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG",3.3529999999999997E-2,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,39,39,"2026-09-24","06:00:00","2026-09-26","23:59:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,1.7]
[null,"DB InfraGO AG",3.9140000000000001E-2,"Darmstadt - Nürnberg","<","Oberhaid","Bamberg",2027,2027,11,12,"2027-03-21","21:00:00","2027-03-23","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.1799999999999997E-2,"Karlsruhe - München",">","Stuttgart-Zuffenhausen","Ludwigsburg",2027,2027,11,11,"2027-03-17","01:30:00","2027-03-19","04:30:00","2d, 3h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",8,8",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.41E-2,"Darmstadt - Nürnberg","<>","Forchheim (Oberfr)","Eltersdorf",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,6.7]
[null,"DB InfraGO AG",0.28100000000000003,"Karlsruhe - München","<","Stuttgart-Zazenhausen","Stuttgart-Untertürkheim",2026,2026,26,26,"2026-06-24","07:00:00","2026-06-24","15:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",0.32140000000000002,"Karlsruhe - Strasbourg","<>","Mühlacker Kurve","Mühlacker Em Süd",2026,2026,34,35,"2026-08-17","08:00:00","2026-08-28","17:00:00","11d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",0.33529999999999999,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,39,40,"2026-09-23","06:00:00","2026-09-28","23:59:00","5d, 17h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",0.39140000000000003,"Darmstadt - Nürnberg","<>","Hallstadt (b Bamberg)","Höflein",2027,2027,11,11,"2027-03-15","21:00:00","2027-03-18","05:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",0.40260000000000001,"München - Salzburg","<>","München Ost Pbf","München-Trudering",2026,2026,51,51,"2026-12-14","22:40:00","2026-12-19","04:40:00","4d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",0.441,"Darmstadt - Nürnberg","<>","Eltersdorf","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",2.81,"Frankfurt - Karlsruhe",">","Langes Feld","Stuttgart-Zazenhausen",2026,2026,26,26,"2026-06-23","07:00:00","2026-06-23","15:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",3.3530000000000002,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,38,39,"2026-09-18","06:00:00","2026-09-23","06:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG",3.9140000000000001,"Darmstadt - Nürnberg",">","Bamberg","Oberhaid",2027,2027,11,11,"2027-03-15","21:00:00","2027-03-18","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.0259999999999998,"München - Salzburg","<","München-Riem West","München Ost Pbf",2026,2026,51,51,"2026-12-14","22:40:00","2026-12-19","04:40:00","4d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",4.41,"Darmstadt - Nürnberg","<>","Eltersdorf","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",28.1,"Karlsruhe - München","<","Stuttgart-Zazenhausen","Stuttgart-Münster",2026,2026,26,26,"2026-06-23","07:00:00","2026-06-23","15:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",32.14,"Karlsruhe - Strasbourg","<>","Mühlacker Kurve","Mühlacker Em Süd",2026,2026,34,35,"2026-08-17","08:00:00","2026-08-28","17:00:00","11d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",33.53,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,37,38,"2026-09-08","06:00:00","2026-09-18","06:00:00","10d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",33.6,"Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,47,47,"2026-11-18","22:00:00","2026-11-19","05:00:00","0d, 7h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",40.26,"München - Salzburg",">","München Ost Pbf","München-Trudering",2026,2026,51,51,"2026-12-14","22:40:00","2026-12-19","04:40:00","4d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",44.1,"Darmstadt - Nürnberg","<>","Eltersdorf","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",47.65,"Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Durlach",2025,2026,50,37,"2025-12-14","00:00:00","2026-09-11","21:00:00","271d, 20h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",281,"Karlsruhe - München","<>","Stuttgart-Zazenhausen","Stuttgart-Münster",2026,2026,26,26,"2026-06-23","07:00:00","2026-06-23","15:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",321.39999999999998,"Karlsruhe - Strasbourg","<>","Mühlacker Em Süd","Mühlacker Em Süd",2026,2026,34,35,"2026-08-17","08:00:00","2026-08-28","17:00:00","11d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",335.3,"Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Gbf",2026,2026,37,39,"2026-09-07","06:00:00","2026-09-24","06:00:00","17d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",336,"Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,46,47,"2026-11-13","00:00:00","2026-11-21","06:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,1.7]
[null,"DB InfraGO AG",391.4,"Darmstadt - Nürnberg","<","Oberhaid","Bamberg",2027,2027,10,10,"2027-03-08","21:00:00","2027-03-11","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-26",null,null,4.5]
[null,"DB InfraGO AG",441,"Darmstadt - Nürnberg",">","Eltersdorf","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG",476.5,"Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2025,2026,50,37,"2025-12-14","00:00:00","2026-09-11","21:00:00","271d, 20h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1B99A-010","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,41,42,"2026-10-09","21:00:00","2026-10-12","05:00:00","2d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1B99A-011","Frankfurt - Karlsruhe","<","Aschaffenburg Hbf","Laufach",2026,2026,41,42,"2026-10-09","21:00:00","2026-10-12","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1B99A-012","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,41,42,"2026-10-09","21:00:00","2026-10-12","05:00:00","2d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1B99A-013","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,41,41,"2026-10-10","05:00:00","2026-10-11","21:00:00","1d, 16h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-06-09",null,null,1.2]
[null,"DB InfraGO AG","1B99A-016","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,45,45,"2026-11-08","05:00:00","2026-11-08","09:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-08-05",null,null,"5,6,7"]
[null,"DB InfraGO AG","1B99A-018","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,45,45,"2026-11-07","21:00:00","2026-11-08","05:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,6.7]
[null,"DB InfraGO AG","1B99A-019","Frankfurt - Karlsruhe","<","Aschaffenburg Hbf","Laufach",2026,2026,45,45,"2026-11-07","21:00:00","2026-11-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3"]
[null,"DB InfraGO AG","1B99A-020","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2026,2026,45,45,"2026-11-07","21:00:00","2026-11-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-08-05",null,null,6.7]
[null,"DB InfraGO AG","1BAE4-001","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,16,16,"2026-04-17","21:00:00","2026-04-19","05:00:00","1d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1BAE4-002","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,21,21,"2026-05-22","21:00:00","2026-05-24","05:00:00","1d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-01",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1BAE4-003","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,16,17,"2026-04-19","05:00:00","2026-04-20","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-01",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1BAE4-004","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,29,30,"2026-07-13","21:00:00","2026-07-20","05:00:00","6d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1BAE4-005","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,21,22,"2026-05-24","05:00:00","2026-05-25","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1BAE4-006","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,16,17,"2026-04-19","05:00:00","2026-04-20","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-007","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,21,22,"2026-05-24","05:00:00","2026-05-25","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1BAE4-008","Frankfurt - Karlsruhe","<","Heppenheim (Bergstr)","Bensheim-Auerbach",2026,2026,17,17,"2026-04-20","21:00:00","2026-04-21","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1BAE4-009","Frankfurt - Karlsruhe",">","Bensheim-Auerbach","Heppenheim (Bergstr)",2026,2026,17,17,"2026-04-21","21:00:00","2026-04-24","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-010","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-011","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,30,30,"2026-07-20","05:00:00","2026-07-22","21:00:00","2d, 16h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-012","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-013","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,28,29,"2026-07-10","21:00:00","2026-07-13","21:00:00","3d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-014","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,29,30,"2026-07-13","21:00:00","2026-07-20","05:00:00","6d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-015","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,30,30,"2026-07-20","05:00:00","2026-07-22","21:00:00","2d, 16h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-016","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,28,28,"2026-07-10","05:00:00","2026-07-10","21:00:00","0d, 16h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-017","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,30,50,"2026-07-22","21:00:00","2026-12-12","23:59:00","143d, 3h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-14",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1BAE4-018","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,28,29,"2026-07-10","21:00:00","2026-07-13","21:00:00","3d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-019","Karlsruhe - Strasbourg","<>","Bensheim","Bensheim",2026,2026,28,50,"2026-07-10","05:00:00","2026-12-12","23:59:00","155d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-020","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,29,50,"2026-07-17","21:00:00","2026-12-12","23:59:00","148d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1BAE4-021","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,29,50,"2026-07-17","21:00:00","2026-12-12","23:59:00","148d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-16",null,null,"5,6,7"]
[null,"DB InfraGO AG","1BAE4-022","Frankfurt - Karlsruhe","<","Heppenheim (Bergstr)","Bensheim-Auerbach",2026,2026,36,36,"2026-09-01","21:00:00","2026-09-02","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,6.7]
[null,"DB InfraGO AG","1BAE4-023","Frankfurt - Karlsruhe",">","Bensheim-Auerbach","Heppenheim (Bergstr)",2026,2026,36,36,"2026-09-02","21:00:00","2026-09-03","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"1,2,3"]
[null,"DB InfraGO AG","1BAE4-024","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2026,36,36,"2026-09-03","21:00:00","2026-09-04","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1C08E-001","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,15,16,"2026-04-11","21:00:00","2026-04-13","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2025-01-14",null,null,"1,2,3"]
[null,"DB InfraGO AG","1C08E-002","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,19,20,"2026-05-09","21:00:00","2026-05-11","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2025-01-14",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-003","Frankfurt - Karlsruhe",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,18,19,"2026-05-02","21:00:00","2026-05-04","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-14",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-004","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,23,23,"2026-06-05","21:00:00","2026-06-06","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2025-01-14",null,null,5]
[null,"DB InfraGO AG","1C08E-005","Frankfurt - Karlsruhe",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,23,23,"2026-06-06","21:00:00","2026-06-07","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-14",null,null,"5,6,7"]
[null,"DB InfraGO AG","1C08E-007","Frankfurt - Karlsruhe",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,24,24,"2026-06-08","21:00:00","2026-06-10","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-14",null,null,2]
[null,"DB InfraGO AG","1C08E-008","Frankfurt - Karlsruhe",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,24,24,"2026-06-09","21:00:00","2026-06-10","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1C08E-010","Frankfurt - Karlsruhe",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,26,32,"2026-06-26","21:00:00","2026-08-07","21:00:00","42d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1C08E-011","Frankfurt - Karlsruhe",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,34,35,"2026-08-23","21:00:00","2026-08-24","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-25",null,null,1.2]
[null,"DB InfraGO AG","1C08E-012","Frankfurt - Karlsruhe",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-14","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-25",null,null,2]
[null,"DB InfraGO AG","1C08E-016","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,26,28,"2026-06-26","21:00:00","2026-07-12","21:00:00","16d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-017","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-10","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-018","Frankfurt - Karlsruhe","<","Darmstadt Gbf","Weiterstadt",2026,2026,34,34,"2026-08-22","21:00:00","2026-08-23","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-019","Frankfurt - Karlsruhe",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,28,32,"2026-07-12","21:00:00","2026-08-07","21:00:00","26d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C08E-020","Frankfurt - Karlsruhe",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,37,37,"2026-09-12","21:00:00","2026-09-13","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,3,4,5,6,7"]
[null,"DB InfraGO AG","1C651-001","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,3,4,5,6,7"]
[null,"DB InfraGO AG","1C651-002","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,3,4,5,6,7"]
[null,"DB InfraGO AG","1C651-003","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","1C651-004","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","1C651-005","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,37,37,"2026-09-07","21:00:00","2026-09-11","05:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","1C651-006","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,37,37,"2026-09-07","21:00:00","2026-09-11","05:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1C651-007","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1C651-008","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1C651-009","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,6]
[null,"DB InfraGO AG","1C651-010","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,6]
[null,"DB InfraGO AG","1C662-001","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-28","05:00:00","6d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1C662-002","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-28","05:00:00","6d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1C662-004","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1C662-005","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1CD61-001","Nürnberg - Passau","<>","Passau Gbf","Plattling",2026,2026,24,28,"2026-06-14","21:00:00","2026-07-10","21:00:00","26d, 0h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1CD61-002","Nürnberg - Passau","<>","Passau Gbf","Plattling",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CD61-003","Nürnberg - Passau","<>","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2026,2026,24,28,"2026-06-14","21:00:00","2026-07-10","21:00:00","26d, 0h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CD61-004","Nürnberg - Passau","<>","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CD61-005","Nürnberg - Passau","<>","Plattling","Obertraubling",2026,2026,28,38,"2026-07-10","21:00:00","2026-09-20","21:00:00","72d, 0h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CD61-009","Nürnberg - Passau","<>","Plattling","Obertraubling",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CDDE-001","Karlsruhe - Strasbourg","<>","Appenweier Nord","Bad Griesbach",2026,2026,31,37,"2026-07-29","23:00:00","2026-09-09","23:00:00","42d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CF23-003","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CF23-004","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,5]
[null,"DB InfraGO AG","1CF23-005","Nürnberg - Passau","<>","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,1.6]
[null,"DB InfraGO AG","1CF23-006","Nürnberg - Passau","<>","Regensburg Ost","Regensburg Ost",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","1CF23-007","Nürnberg - Passau","<>","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","1CF23-008","Nürnberg - Passau","<>","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,1.6]
[null,"DB InfraGO AG","1CF23-009","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,4.5]
[null,"DB InfraGO AG","1CF23-010","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,4.5]
[null,"DB InfraGO AG","1CF23-011","Nürnberg - Passau","<>","Regensburg Bbf","Regensburg Bbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,4.5]
[null,"DB InfraGO AG","1CF23-012","Nürnberg - Passau","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","1CF23-013","Regensburg - Plzen","<>","Regensburg Ost","Regensburg Ost",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","1CF23-014","Nürnberg - Passau","<>","Mangolding","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2025-08-04",null,null,5.6]
[null,"DB InfraGO AG","1CF23-015","Nürnberg - Passau","<>","Passau Hbf","Vilshofen (Niederbay)",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"11,11,11",null,null,null,"N",null,"2025-08-04",null,null,5.6]
[null,"DB InfraGO AG","1CF23-016","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-04",null,null,1]
[null,"DB InfraGO AG","1CF23-017","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-04",null,null,2]
[null,"DB InfraGO AG","1CF23-018","Nürnberg - Passau","<>","Plattling","Mangolding",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2024-06-04",null,null,3.4]
[null,"DB InfraGO AG","1CF23-019","Nürnberg - Passau","<>","Plattling","Vilshofen (Niederbay)",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-06-04",null,null,3.4]
[null,"DB InfraGO AG","1CF23-020","Nürnberg - Passau","<>","Vilshofen (Niederbay)","Passau Hbf",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"11,11,11",null,null,null,"N",null,"2024-06-04",null,null,3.4]
[null,"DB InfraGO AG","1CF23-021","Nürnberg - Passau","<>","Vilshofen (Niederbay)","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-07-28",null,null,5.6]
[null,"DB InfraGO AG","1CF23-022","Nürnberg - Passau","<>","Mangolding","Pleinting",2026,2026,50,50,"2026-12-12","06:00:00","2026-12-12","23:59:00","0d, 17h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-07-28",null,null,5.6]
[null,"DB InfraGO AG","1CF23-023","Nürnberg - Passau","<>","Pleinting","Mangolding",2026,2026,50,50,"2026-12-12","06:00:00","2026-12-12","23:59:00","0d, 17h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-07-28",null,null,6.7]
[null,"DB InfraGO AG","1D0F3-001","Nürnberg - Passau","<>","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,50,"2026-10-28","07:00:00","2026-12-11","23:59:00","44d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-28",null,null,6.7]
[null,"DB InfraGO AG","1D0F3-003","Nürnberg - Passau","<>","Ingolstadt Nord","Nürnberg Reichswald",2026,2026,44,50,"2026-10-30","23:50:00","2026-12-11","04:50:00","41d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2025-08-04",null,null,1]
[null,"DB InfraGO AG","1D1F4-001","Nürnberg - Passau",">","Osterhofen (Niederbay)","Plattling",2026,2026,47,47,"2026-11-16","08:00:00","2026-11-16","16:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","1D1F4-002","Nürnberg - Passau",">","Plattling","Straßkirchen",2026,2026,47,47,"2026-11-17","08:00:00","2026-11-18","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,2]
[null,"DB InfraGO AG","1D1F4-003","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,47,47,"2026-11-19","08:00:00","2026-11-20","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,3]
[null,"DB InfraGO AG","1D1F4-004","Nürnberg - Passau","<","Straßkirchen","Plattling",2026,2026,48,48,"2026-11-23","08:00:00","2026-11-24","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,3.4]
[null,"DB InfraGO AG","1D1F4-005","Nürnberg - Passau","<","Plattling","Osterhofen (Niederbay)",2026,2026,48,48,"2026-11-25","08:00:00","2026-11-25","16:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,4.5]
[null,"DB InfraGO AG","1D1F4-006","Nürnberg - Passau","<>","Wallersdorf","Plattling",2026,2026,48,48,"2026-11-26","08:00:00","2026-11-27","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,4.5]
[null,"DB InfraGO AG","1D41F-001","Frankfurt - Karlsruhe","<>","Schwetzingen","Schwetzingen",2026,2026,43,47,"2026-10-20","22:00:00","2026-11-16","22:00:00","27d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","1D41F-005","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Blankenloch",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,4.5]
[null,"DB InfraGO AG","1D41F-006","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,4.5]
[null,"DB InfraGO AG","1D41F-008","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-13",null,null,4.5]
[null,"DB InfraGO AG","1D41F-009","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-13",null,null,"1,6,7"]
[null,"DB InfraGO AG","1D41F-010","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,6,7"]
[null,"DB InfraGO AG","1D41F-011","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-13",null,null,"1,6,7"]
[null,"DB InfraGO AG","1D41F-012","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D41F-013","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-06",null,null,4.5]
[null,"DB InfraGO AG","1D41F-014","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-06",null,null,4.5]
[null,"DB InfraGO AG","1D41F-015","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Blankenloch",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,5.6]
[null,"DB InfraGO AG","1D41F-016","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,6]
[null,"DB InfraGO AG","1D41F-017","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,6]
[null,"DB InfraGO AG","1D41F-018","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","1D41F-019","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,2]
[null,"DB InfraGO AG","1D41F-020","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1D41F-021","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1D41F-022","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1D41F-023","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1D41F-024","Karlsruhe - Strasbourg",">","Philippsburg Molzau","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1D41F-025","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"5,6,7"]
[null,"DB InfraGO AG","1D41F-026","Nürnberg - Passau","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-23",null,null,6.7]
[null,"DB InfraGO AG","1D41F-027","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7]
[null,"DB InfraGO AG","1D41F-028","Karlsruhe - Strasbourg","<>","Waghäusel Saalbach","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,6.7]
[null,"DB InfraGO AG","1D41F-029","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-05",null,null,5.6]
[null,"DB InfraGO AG","1D41F-030","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-15",null,null,5.6]
[null,"DB InfraGO AG","1D41F-031","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-05",null,null,6.7]
[null,"DB InfraGO AG","1D4EB-001","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-04","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-15",null,null,6.7]
[null,"DB InfraGO AG","1D4EB-002","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-01-05",null,null,1.7]
[null,"DB InfraGO AG","1D4EB-003","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-15",null,null,1.7]
[null,"DB InfraGO AG","1D4EB-004","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-17",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1D4EB-005","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D4EB-006","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-04","04:00:00","2026-11-06","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-05",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1D4EB-007","Karlsruhe - Strasbourg","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-07","06:00:00","2026-11-08","22:00:00","1d, 16h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1D552-001","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,39,40,"2026-09-25","05:00:00","2026-10-04","05:00:00","9d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1D552-002","Nürnberg - Passau","<>","Passau Hbf","Passau Gbf",2026,2026,41,42,"2026-10-05","05:00:00","2026-10-12","05:00:00","7d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-02-05",null,null,"2,3,4"]
[null,"DB InfraGO AG","1D552-003","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,42,43,"2026-10-13","05:00:00","2026-10-22","05:00:00","9d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-06-10",null,null,5.6]
[null,"DB InfraGO AG","1D552-004","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,43,44,"2026-10-23","05:00:00","2026-11-01","05:00:00","9d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,5.6]
[null,"DB InfraGO AG","1D552-005","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,43,44,"2026-10-23","05:00:00","2026-11-01","05:00:00","9d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,6.7]
[null,"DB InfraGO AG","1D587-006","München - Salzburg","<>","Rosenheim","Rosenheim",2026,2026,15,17,"2026-04-11","00:30:00","2026-04-20","05:00:00","9d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1D5C0-001","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,38,39,"2026-09-19","22:00:00","2026-09-21","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","1D5C0-002","Nürnberg - Passau","<>","Passau Hbf","Passau Grenze",2026,2026,39,40,"2026-09-26","22:00:00","2026-09-28","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","1D5C0-003","Nürnberg - Passau","<>","Passau Hbf","Passau Gbf",2026,2026,39,40,"2026-09-26","22:00:00","2026-09-28","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1D5C0-004","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,40,41,"2026-10-03","22:00:00","2026-10-05","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1D5C0-005","Nürnberg - Passau","<>","Passau Hbf","Passau Grenze",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1D5C0-006","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1D5C0-007","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,38,39,"2026-09-19","22:00:00","2026-09-21","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1D5C0-008","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,40,41,"2026-10-03","22:00:00","2026-10-05","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1D5C0-009","Nürnberg - Passau","<>","Passau Hbf","Passau Grenze",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1D5C0-010","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1D5C0-011","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,43,44,"2026-10-24","22:00:00","2026-10-26","05:00:00","1d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1D5C0-012","Nürnberg - Passau","<>","Passau Hbf","Passau Hbf",2026,2026,43,44,"2026-10-24","22:00:00","2026-10-26","05:00:00","1d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-28",null,null,3.4]
[null,"DB InfraGO AG","1D5C3-018","Karlsruhe - Strasbourg","<>","Appenweier","Offenburg",2026,2026,40,41,"2026-10-04","03:00:00","2026-10-07","04:30:00","3d, 1h","Continuous","Switch",null,null,null,null,null,",,",",,",null,",3,",null,null,null,"N",null,"2025-05-28",null,null,3.4]
[null,"DB InfraGO AG","1D659-001","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1D659-002","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,5.6]
[null,"DB InfraGO AG","1D659-003","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,6.7]
[null,"DB InfraGO AG","1D659-004","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,1.7]
[null,"DB InfraGO AG","1D659-005","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-05-01","22:00:00","2026-05-04","05:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,1.2]
[null,"DB InfraGO AG","1D659-006","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-05-01","22:00:00","2026-05-04","05:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,"5,6,7"]
[null,"DB InfraGO AG","1D659-007","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,5.6]
[null,"DB InfraGO AG","1D659-008","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,1.7]
[null,"DB InfraGO AG","1D6AE-002","Karlsruhe - Strasbourg","<>","Mühlacker","Maulbronn West",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,6.7]
[null,"DB InfraGO AG","1D6AE-005","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-24",null,null,4.5]
[null,"DB InfraGO AG","1D6AE-007","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1D6AE-010","Karlsruhe - Strasbourg","<>","Mühlacker","Maulbronn West",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,5]
[null,"DB InfraGO AG","1D6AE-011","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-24",null,null,5]
[null,"DB InfraGO AG","1D6AE-014","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-24",null,null,5]
[null,"DB InfraGO AG","1D6BF-001","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","1D6BF-002","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2025,2026,50,21,"2025-12-14","00:00:00","2026-05-22","04:30:00","159d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,null,null,null,6.7]
[null,"DB InfraGO AG","1D6BF-003","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2025,2026,50,21,"2025-12-14","00:00:00","2026-05-22","04:30:00","159d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","1D6BF-004","Karlsruhe - Strasbourg","<","Augsburg Hbf","Augsburg-Hochzoll Abzweig",2026,2026,21,21,"2026-05-21","22:00:00","2026-05-22","04:30:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","1D6BF-005","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,21,21,"2026-05-21","22:00:00","2026-05-22","04:30:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","1D6BF-006","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1D6BF-007","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1D6BF-008","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1D6BF-009","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D710-001","Karlsruhe - Strasbourg","<>","Plattling","Plattling",2026,2026,20,21,"2026-05-15","07:00:00","2026-05-23","04:00:00","7d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D710-002","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,20,21,"2026-05-15","07:00:00","2026-05-23","04:00:00","7d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D710-003","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,20,21,"2026-05-15","22:00:00","2026-05-23","04:00:00","7d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-21",null,null,1.2]
[null,"DB InfraGO AG","1D710-004","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,20,21,"2026-05-15","22:00:00","2026-05-23","04:00:00","7d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,3,4,5,7"]
[null,"DB InfraGO AG","1D710-005","Karlsruhe - Strasbourg","<>","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,6.7]
[null,"DB InfraGO AG","1D73C-001","Karlsruhe - Strasbourg","<>","Haar","Aßling (Oberbay)",2026,2026,2,2,"2026-01-09","22:15:00","2026-01-10","05:15:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"2,3,4"]
[null,"DB InfraGO AG","1D73C-002","Karlsruhe - Strasbourg",">","Haar","Zorneding",2026,2026,2,2,"2026-01-09","22:15:00","2026-01-10","01:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-14",null,null,"1,4,5,6,7"]
[null,"DB InfraGO AG","1D73C-003","Karlsruhe - Strasbourg",">","Zorneding","Grafing Bahnhof",2026,2026,2,2,"2026-01-10","01:00:00","2026-01-10","03:45:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-17",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1D73C-004","Karlsruhe - Strasbourg",">","Grafing Bahnhof","Aßling (Oberbay)",2026,2026,2,2,"2026-01-10","03:45:00","2026-01-10","05:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","1D73C-005","Karlsruhe - Strasbourg","<>","München Hbf","Haar",2026,2026,2,2,"2026-01-10","22:30:00","2026-01-11","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","1D73C-006","Karlsruhe - Strasbourg",">","München Hbf","München Süd",2026,2026,2,2,"2026-01-10","22:30:00","2026-01-11","00:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","1D73C-007","Karlsruhe - Strasbourg",">","München Süd","München Ost Pbf",2026,2026,2,2,"2026-01-11","00:15:00","2026-01-11","01:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D73C-008","Karlsruhe - Strasbourg",">","München Ost Pbf","Haar",2026,2026,2,2,"2026-01-11","01:45:00","2026-01-11","05:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D73C-009","Karlsruhe - Strasbourg",">","München-Trudering","München-Waldtrudering",2026,2026,2,2,"2026-01-11","01:45:00","2026-01-11","05:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D73C-010","Karlsruhe - Strasbourg","<>","München Hbf","Haar",2026,2026,2,3,"2026-01-11","22:30:00","2026-01-12","05:30:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D73C-011","Karlsruhe - Strasbourg","<>","München Ost Pbf","München Ost Pbf",2026,2026,2,3,"2026-01-11","22:30:00","2026-01-12","05:30:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D73C-012","Karlsruhe - Strasbourg","<","München Süd","München Hbf",2026,2026,2,3,"2026-01-11","22:30:00","2026-01-12","00:15:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-013","Karlsruhe - Strasbourg","<","München Ost Pbf","München Süd",2026,2026,3,3,"2026-01-12","00:15:00","2026-01-12","02:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-014","Karlsruhe - Strasbourg","<","Haar","München Ost Pbf",2026,2026,3,3,"2026-01-12","02:00:00","2026-01-12","03:45:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-015","Karlsruhe - Strasbourg","<","Zorneding","München-Trudering",2026,2026,3,3,"2026-01-12","03:45:00","2026-01-12","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-016","Karlsruhe - Strasbourg","<","München-Waldtrudering","München-Trudering",2026,2026,3,3,"2026-01-12","03:45:00","2026-01-12","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-017","Karlsruhe - Strasbourg","<>","Haar","Aßling (Oberbay)",2026,2026,3,3,"2026-01-12","22:30:00","2026-01-13","05:10:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,6.7]
[null,"DB InfraGO AG","1D73C-018","Karlsruhe - Strasbourg","<","Zorneding","Haar",2026,2026,3,3,"2026-01-12","22:30:00","2026-01-13","00:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,6.7]
[null,"DB InfraGO AG","1D73C-019","Karlsruhe - Strasbourg","<","Grafing Bahnhof","Zorneding",2026,2026,3,3,"2026-01-13","00:30:00","2026-01-13","03:40:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,6.7]
[null,"DB InfraGO AG","1D73C-020","Karlsruhe - Strasbourg","<","Aßling (Oberbay)","Grafing Bahnhof",2026,2026,3,3,"2026-01-13","03:40:00","2026-01-13","05:10:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,6.7]
[null,"DB InfraGO AG","1D73C-021","Karlsruhe - Strasbourg","<>","Grafing Bahnhof","Ostermünchen",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,6.7]
[null,"DB InfraGO AG","1D73C-022","Karlsruhe - Strasbourg","<","Aßling (Oberbay)","Grafing Bahnhof",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-13","23:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,6.7]
[null,"DB InfraGO AG","1D73C-023","Karlsruhe - Strasbourg","<","Ostermünchen","Aßling (Oberbay)",2026,2026,3,3,"2026-01-13","23:30:00","2026-01-14","01:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D73C-024","Karlsruhe - Strasbourg",">","Grafing Bahnhof","Ostermünchen",2026,2026,3,3,"2026-01-14","01:35:00","2026-01-14","05:00:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D73C-025","Karlsruhe - Strasbourg","<>","Ostermünchen","Rosenheim",2026,2026,3,3,"2026-01-14","22:30:00","2026-01-15","05:15:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D73C-026","Karlsruhe - Strasbourg",">","Ostermünchen","Rosenheim",2026,2026,3,3,"2026-01-14","22:30:00","2026-01-15","01:50:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D73C-027","Karlsruhe - Strasbourg","<","Rosenheim","Ostermünchen",2026,2026,3,3,"2026-01-15","01:55:00","2026-01-15","05:15:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D7C2-011","Karlsruhe - Strasbourg","<>","Mannheim Hbf","Hockenheim",2026,2026,14,15,"2026-04-05","22:00:00","2026-04-06","06:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D7C2-015","Karlsruhe - Strasbourg","<>","Mannheim Hbf","Hockenheim",2026,2026,15,15,"2026-04-06","21:00:00","2026-04-07","04:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1D885-001","Karlsruhe - Strasbourg","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,19,24,"2026-05-07","07:00:00","2026-06-09","17:00:00","33d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-19",null,null,4.5]
[null,"DB InfraGO AG","1D885-002","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-05","05:00:00","26d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,5.6]
[null,"DB InfraGO AG","1D885-003","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-05","05:00:00","26d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,4.5]
[null,"DB InfraGO AG","1D885-004","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-05","05:00:00","26d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,6.7]
[null,"DB InfraGO AG","1D885-005","Karlsruhe - Strasbourg",">","Westheim (Schwab)","Dinkelscherben",2026,2026,19,19,"2026-05-09","22:00:00","2026-05-10","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-16",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","1D885-006","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,19,19,"2026-05-09","22:00:00","2026-05-10","05:00:00","0d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-16",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","1D885-007","Karlsruhe - Strasbourg",">","Westheim (Schwab)","Dinkelscherben",2026,2026,19,20,"2026-05-10","21:00:00","2026-05-11","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-16",null,null,4.5]
[null,"DB InfraGO AG","1D885-008","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,20,20,"2026-05-11","22:00:00","2026-05-13","05:00:00","1d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-16",null,null,4.5]
[null,"DB InfraGO AG","1D885-009","Karlsruhe - Strasbourg","<>","Westheim (Schwab)","Dinkelscherben",2026,2026,22,23,"2026-05-31","22:00:00","2026-06-05","05:00:00","4d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"5,6,7"]
[null,"DB InfraGO AG","1D885-010","Karlsruhe - Strasbourg","<","Gessertshausen","Gessertshausen",2026,2026,23,23,"2026-06-05","05:00:00","2026-06-06","07:00:00","1d, 2h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-23",null,null,6.7]
[null,"DB InfraGO AG","1D885-011","Karlsruhe - Strasbourg",">","Gessertshausen","Gessertshausen",2026,2026,23,23,"2026-06-05","05:00:00","2026-06-06","07:00:00","1d, 2h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-08",null,null,"1,2,7"]
[null,"DB InfraGO AG","1D885-012","Karlsruhe - Strasbourg",">","Gessertshausen","Gessertshausen",2026,2026,23,24,"2026-06-06","07:00:00","2026-06-08","07:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-05",null,null,"5,6,7"]
[null,"DB InfraGO AG","1D885-013","Karlsruhe - Strasbourg","<","Gessertshausen","Gessertshausen",2026,2026,23,24,"2026-06-06","07:00:00","2026-06-08","07:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-05",null,null,"5,6,7"]
[null,"DB InfraGO AG","1D885-014","Karlsruhe - Strasbourg","<>","Westheim (Schwab)","Dinkelscherben",2026,2026,45,46,"2026-11-07","22:00:00","2026-11-09","05:00:00","1d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1D885-015","Karlsruhe - Strasbourg","<>","Gessertshausen","Gessertshausen",2026,2026,45,46,"2026-11-07","22:00:00","2026-11-09","05:00:00","1d, 7h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1D885-016","Karlsruhe - München","<>","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-07","05:00:00","28d, 7h","Continuous","Track & Rail",null,null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1D885-017","Karlsruhe - München","<>","Westheim (Schwab)","Dinkelscherben",2026,2026,19,19,"2026-05-10","21:00:00","2026-05-10","22:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1D885-018","München - Salzburg","<>","Gessertshausen","Gessertshausen",2026,2026,19,19,"2026-05-10","21:00:00","2026-05-10","22:00:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-31",null,null,6.7]
[null,"DB InfraGO AG","1D885-019","Karlsruhe - München","<>","Westheim (Schwab)","Dinkelscherben",2026,2026,20,20,"2026-05-11","04:00:00","2026-05-11","05:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,1.7]
[null,"DB InfraGO AG","1D885-020","München - Salzburg","<>","Gessertshausen","Gessertshausen",2026,2026,20,20,"2026-05-11","04:00:00","2026-05-11","05:00:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,1.7]
[null,"DB InfraGO AG","1D973-001","Karlsruhe - Strasbourg","<>","Geiselhöring","Radldorf (Niederbay)",2026,2026,34,34,"2026-08-21","21:00:00","2026-08-23","21:00:00","2d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-31",null,null,6.7]
[null,"DB InfraGO AG","1D973-002","Karlsruhe - Strasbourg","<>","Straubing","Bogen",2026,2026,34,38,"2026-08-21","21:00:00","2026-09-20","20:59:00","29d, 23h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,6.7]
[null,"DB InfraGO AG","1D973-003","Karlsruhe - Strasbourg","<>","Straubing","Bogen",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-06",null,null,6.7]
[null,"DB InfraGO AG","1D973-004","Karlsruhe - Strasbourg","<>","Geiselhöring","Radldorf (Niederbay)",2026,2026,34,39,"2026-08-23","21:00:00","2026-09-23","21:00:00","31d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,1.7]
[null,"DB InfraGO AG","1D973-005","Karlsruhe - Strasbourg","<>","Geiselhöring","Radldorf (Niederbay)",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,1.7]
[null,"DB InfraGO AG","1D9A9-010","Karlsruhe - Strasbourg","<>","Mannheim Hbf","Hockenheim",2026,2026,22,24,"2026-05-29","22:45:00","2026-06-08","05:00:00","9d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,1.2]
[null,"DB InfraGO AG","1DA02-001","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-03","07:00:00","2026-08-28","17:00:00","25d, 10h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-03",null,null,1.2]
[null,"DB InfraGO AG","1DA02-002","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,32,"2026-08-08","00:00:00","2026-08-08","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-03",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DA02-003","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,33,34,"2026-08-11","23:00:00","2026-08-18","23:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DA02-004","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,34,"2026-08-11","23:00:00","2026-08-18","23:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-03",null,null,5.6]
[null,"DB InfraGO AG","1DA02-005","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","18:00:00","2026-08-22","05:00:00","3d, 11h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,5.6]
[null,"DB InfraGO AG","1DA02-006","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-04-03",null,null,1.7]
[null,"DB InfraGO AG","1DA02-007","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-02-14",null,null,1.7]
[null,"DB InfraGO AG","1DA02-008","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1DA02-009","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-23","06:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1DA02-010","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-22","00:00:00","2026-08-22","05:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DA02-011","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-22","00:00:00","2026-08-22","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DA02-012","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,40,40,"2026-10-02","20:00:00","2026-10-02","22:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-05-16",null,null,6.7]
[null,"DB InfraGO AG","1DA02-013","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-02","22:00:00","2026-10-02","23:50:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DA02-014","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,40,40,"2026-10-02","23:55:00","2026-10-03","06:45:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2]
[null,"DB InfraGO AG","1DA02-023","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,40,40,"2026-10-03","23:45:00","2026-10-04","01:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-04-02",null,null,2]
[null,"DB InfraGO AG","1DA02-024","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-03","23:45:00","2026-10-04","01:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-02",null,null,2]
[null,"DB InfraGO AG","1DA02-025","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2]
[null,"DB InfraGO AG","1DA02-026","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DA02-027","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DA02-028","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,41,41,"2026-10-09","21:00:00","2026-10-10","00:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DA02-029","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,41,41,"2026-10-10","00:00:00","2026-10-10","06:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-03-21",null,null,1.2]
[null,"DB InfraGO AG","1DA02-030","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,41,41,"2026-10-10","00:00:00","2026-10-10","06:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-03-21",null,null,1.2]
[null,"DB InfraGO AG","1DA02-031","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,41,41,"2026-10-11","04:20:00","2026-10-11","06:45:00","0d, 2h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-21",null,null,1.2]
[null,"DB InfraGO AG","1DA02-032","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,41,41,"2026-10-11","04:20:00","2026-10-11","06:45:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DA02-035","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-02","23:55:00","2026-10-03","06:45:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DA02-036","Darmstadt - Nürnberg","<","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-02","22:00:00","2026-10-02","23:50:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DA02-037","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-20","22:00:00","2026-08-21","00:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DA02-038","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-19","23:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,3,4,5,7"]
[null,"DB InfraGO AG","1DA02-039","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-21","00:00:00","2026-08-21","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,5.6]
[null,"DB InfraGO AG","1DA02-040","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-21","04:00:00","2026-08-21","06:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,5.6]
[null,"DB InfraGO AG","1DA02-041","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-21","00:00:00","2026-08-21","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,5.6]
[null,"DB InfraGO AG","1DA02-042","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-07","23:00:00","2026-08-28","23:00:00","21d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,6.7]
[null,"DB InfraGO AG","1DA02-043","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-07","23:00:00","2026-08-28","23:00:00","21d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,6.7]
[null,"DB InfraGO AG","1DA02-044","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,35,"2026-08-11","08:00:00","2026-08-28","23:00:00","17d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,7"]
[null,"DB InfraGO AG","1DA02-045","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,35,"2026-08-13","08:00:00","2026-08-28","23:00:00","15d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,7"]
[null,"DB InfraGO AG","1DA81-001","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,33,34,"2026-08-14","07:00:00","2026-08-23","04:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,7"]
[null,"DB InfraGO AG","1DA81-002","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","07:00:00","2026-08-23","04:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"2,3,4"]
[null,"DB InfraGO AG","1DA81-003","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"2,3,4"]
[null,"DB InfraGO AG","1DA81-004","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,4,5,6,7"]
[null,"DB InfraGO AG","1DA81-005","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1DA81-006","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","23:00:00","2026-08-23","03:00:00","8d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-20",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DA81-007","Karlsruhe - Strasbourg","<>","Regensburg Ost","Regensburg Ost",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","04:00:00","1d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-20",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DABD-001","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-29","22:00:00","2026-08-30","08:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DABD-002","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,37,"2026-08-29","22:00:00","2026-09-07","03:00:00","8d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DABD-003","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,37,"2026-08-29","22:00:00","2026-09-07","03:00:00","8d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DABD-004","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","13:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1DABD-005","Karlsruhe - Strasbourg","<","Westheim (Schwab)","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","13:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1DABD-006","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,36,"2026-08-30","13:00:00","2026-09-03","20:00:00","4d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,6.7]
[null,"DB InfraGO AG","1DABD-007","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-03","20:00:00","2026-09-05","09:00:00","1d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DABD-008","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-05","09:00:00","2026-09-06","22:00:00","1d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DABD-009","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1DABD-010","Karlsruhe - Strasbourg","<","Westheim (Schwab)","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1DABD-012","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1DABD-016","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,37,37,"2026-09-09","14:00:00","2026-09-11","04:00:00","1d, 14h","Continuous",null,null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,"2,3,4"]
[null,"DB InfraGO AG","1DABD-017","Karlsruhe - Strasbourg","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1DABD-021","Karlsruhe - München","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-03","20:00:00","2026-09-06","22:00:00","3d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DAD8-001","Karlsruhe - Strasbourg","<>","Mühlacker","Illingen (Württ)",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2025-04-08",null,null,1.2]
[null,"DB InfraGO AG","1DAD8-002","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2025-04-08",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DAD8-003","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-26","20:00:00","2026-08-14","06:00:00","48d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-04-08",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DAD8-005","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-26","20:00:00","2026-08-14","06:00:00","48d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-04-08",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DAD8-007","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,26,28,"2026-06-26","22:00:00","2026-07-11","05:00:00","14d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1DAD8-008","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,26,28,"2026-06-26","22:00:00","2026-07-11","05:00:00","14d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1DAD8-010","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,26,33,"2026-06-27","20:00:00","2026-08-10","06:00:00","43d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","1DAD8-012","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","1DAD8-016","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","1DAD8-018","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-08",null,null,6.7]
[null,"DB InfraGO AG","1DAD8-019","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,6.7]
[null,"DB InfraGO AG","1DAD8-020","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,3.4]
[null,"DB InfraGO AG","1DAD8-021","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,3.4]
[null,"DB InfraGO AG","1DAD8-022","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,1.2]
[null,"DB InfraGO AG","1DAD8-024","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-03-17",null,null,1.2]
[null,"DB InfraGO AG","1DAD8-025","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1DAD8-026","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","1DAD8-027","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,29,29,"2026-07-13","22:00:00","2026-07-18","05:00:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,3,4,5,6,7"]
[null,"DB InfraGO AG","1DAD8-028","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,29,29,"2026-07-13","22:00:00","2026-07-18","05:00:00","4d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-03-17",null,null,"1,3,4,5,6,7"]
[null,"DB InfraGO AG","1DAD8-029","Frankfurt - Karlsruhe","<>","Mühlacker","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-03-17",null,null,1.2]
[null,"DB InfraGO AG","1DAD8-030","Frankfurt - Karlsruhe","<>","Mühlacker","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-001","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,30,31,"2026-07-20","00:00:00","2026-07-31","05:00:00","11d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1DB29-002","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,30,31,"2026-07-20","00:00:00","2026-07-31","05:00:00","11d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-003","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,30,31,"2026-07-20","00:00:00","2026-07-31","05:00:00","11d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-005","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,30,31,"2026-07-20","22:00:00","2026-08-01","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,2]
[null,"DB InfraGO AG","1DB29-006","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,30,31,"2026-07-20","22:00:00","2026-08-01","05:00:00","11d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-08",null,null,6.7]
[null,"DB InfraGO AG","1DB29-007","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-08","05:00:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,4.5]
[null,"DB InfraGO AG","1DB29-008","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-08","05:00:00","4d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-009","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-08",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB29-010","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB29-011","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB29-012","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1DB29-013","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1DB29-015","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","1DB29-016","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"2,3,4"]
[null,"DB InfraGO AG","1DB29-017","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,"1,2,3"]
[null,"DB InfraGO AG","1DB29-019","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-18","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1DB29-020","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:00:00","2026-10-02","06:00:00","11d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1DB29-022","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:45:00","2026-10-02","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-023","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:45:00","2026-10-02","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-11-30",null,null,6.7]
[null,"DB InfraGO AG","1DB29-024","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,42,50,"2026-10-16","20:00:00","2026-12-11","06:00:00","55d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-11-30",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB29-025","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,42,50,"2026-10-16","20:00:00","2026-12-11","06:00:00","55d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-07-18",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DB29-027","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,42,44,"2026-10-16","22:00:00","2026-10-31","05:00:00","14d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-07-18",null,null,1.7]
[null,"DB InfraGO AG","1DB29-028","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,42,44,"2026-10-16","22:00:00","2026-10-31","05:00:00","14d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-18",null,null,1.7]
[null,"DB InfraGO AG","1DB29-029","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker Rößlesweg",2026,2026,30,31,"2026-07-20","00:00:00","2026-07-31","05:00:00","11d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB3C-008","Karlsruhe - Strasbourg",">","Rosenheim","Brannenburg",2026,2026,15,15,"2026-04-10","22:00:00","2026-04-11","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-003","Karlsruhe - Strasbourg","<>","Offenburg Ülp südl Esig","Rastatt-Süd",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-004","Karlsruhe - Strasbourg","<>","Appenweier Nord","Kehl Grenze",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,87,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-005","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf Bft Südeinfahrt","Rastatt",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-006","Karlsruhe - Strasbourg","<>","Bashaide","Rastatt Tunnel Anschluss",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-007","Karlsruhe - Strasbourg","<>","Karlsruhe-Dammerstock","Karlsruhe-Dammerstock",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB50-013","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt DB/AVG",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB50-015","Karlsruhe - Strasbourg","<>","Appenweier Nord","Appenweier Nord",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB50-016","Karlsruhe - Strasbourg","<>","Achern","Achern DB/SWEG",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB50-019","Karlsruhe - Strasbourg","<>","Appenweier-Muhrhaag","Appenweier Kurve",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB50-020","Karlsruhe - Strasbourg","<>","Karlsruhe-Dammerstock","Karlsruhe-Dammerstock",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB50-023","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt Industrie-Stammgl",2026,2026,40,40,"2026-10-04","01:30:00","2026-10-04","04:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.2]
[null,"DB InfraGO AG","1DB53-001","Karlsruhe - Strasbourg","<>","Ebelsbach-Eltmann","Oberhaid",2026,2026,29,29,"2026-07-16","21:00:00","2026-07-17","05:00:00","0d, 8h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",,0",null,null,null,"N",null,"2025-06-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB53-002","Karlsruhe - Strasbourg","<>","Oberhaid","Ebelsbach-Eltmann",2026,2026,29,29,"2026-07-16","21:00:00","2026-07-17","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB53-003","Karlsruhe - Strasbourg",">","Oberhaid","Ebelsbach-Eltmann",2026,2026,29,29,"2026-07-16","21:00:00","2026-07-17","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB63-001","Karlsruhe - Strasbourg",">","Zeil","Haßfurt",2026,2026,23,23,"2026-06-01","21:00:00","2026-06-05","05:00:00","3d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB63-002","Karlsruhe - Strasbourg","<","Haßfurt","Zeil",2026,2026,28,29,"2026-07-12","21:00:00","2026-07-16","05:00:00","3d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB67-001","Karlsruhe - Strasbourg",">","Haßfurt","Gädheim",2026,2026,23,24,"2026-06-05","21:00:00","2026-06-13","05:00:00","7d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB67-002","Karlsruhe - Strasbourg","<","Gädheim","Haßfurt",2026,2026,27,28,"2026-07-04","21:00:00","2026-07-12","05:00:00","7d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-002","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,42,50,"2026-10-17","20:00:00","2026-12-07","06:00:00","50d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-004","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-005","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-007","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Mühlacker",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-008","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Mühlacker",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-03-20",null,null,"5,6,7"]
[null,"DB InfraGO AG","1DB9A-009","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,5.6]
[null,"DB InfraGO AG","1DB9A-010","Karlsruhe - Strasbourg","<>","Vaihingen (Enz)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,5.6]
[null,"DB InfraGO AG","1DB9A-011","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,5.6]
[null,"DB InfraGO AG","1DB9A-012","Karlsruhe - Strasbourg","<>","Illingen (Württ)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,5.6]
[null,"DB InfraGO AG","1DB9A-014","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-01",null,null,1.7]
[null,"DB InfraGO AG","1DB9A-015","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB9A-016","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-12-12",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB9A-018","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,45,47,"2026-11-02","22:00:00","2026-11-21","05:00:00","18d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB9A-019","Karlsruhe - Strasbourg","<","Mühlacker","Illingen (Württ)",2026,2026,45,47,"2026-11-02","22:00:00","2026-11-21","05:00:00","18d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DB9A-020","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-01",null,null,3]
[null,"DB InfraGO AG","1DB9A-022","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-01",null,null,1.7]
[null,"DB InfraGO AG","1DB9A-023","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,48,50,"2026-11-23","22:00:00","2026-12-11","05:00:00","17d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,3]
[null,"DB InfraGO AG","1DB9A-024","Karlsruhe - Strasbourg",">","Illingen (Württ)","Mühlacker",2026,2026,48,50,"2026-11-23","22:00:00","2026-12-11","05:00:00","17d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,3]
[null,"DB InfraGO AG","1DB9A-025","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,48,49,"2026-11-23","22:00:00","2026-12-05","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-01",null,null,3]
[null,"DB InfraGO AG","1DB9A-026","Karlsruhe - Strasbourg","<>","Mühlacker Rößlesweg","Mühlacker",2026,2026,48,49,"2026-11-23","22:00:00","2026-12-05","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-01",null,null,5.6]
[null,"DB InfraGO AG","1DBAD-001","Karlsruhe - Strasbourg",">","Zeil","Gädheim",2026,2026,30,31,"2026-07-25","08:00:00","2026-07-27","16:00:00","2d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2025-08-01",null,null,1.7]
[null,"DB InfraGO AG","1DBAD-002","Karlsruhe - Strasbourg","<>","Zeil","Gädheim",2026,2026,31,31,"2026-07-27","10:00:00","2026-07-29","11:00:00","2d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-01",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DBAD-003","Karlsruhe - Strasbourg","<","Gädheim","Zeil",2026,2026,31,31,"2026-07-28","08:00:00","2026-07-29","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2024-12-12",null,null,3]
[null,"DB InfraGO AG","1DBB2-001","Karlsruhe - Strasbourg",">","Gädheim","Schweinfurt Stadt",2026,2026,24,25,"2026-06-13","23:00:00","2026-06-21","05:30:00","7d, 6h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","1DBB2-002","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Gädheim",2026,2026,26,27,"2026-06-26","23:00:00","2026-07-04","05:30:00","7d, 6h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DBBC-001","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,32,33,"2026-08-03","08:00:00","2026-08-10","16:00:00","7d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1DBBC-002","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,21,22,"2026-05-23","08:00:00","2026-05-29","16:30:00","6d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2024-03-25",null,null,6.7]
[null,"DB InfraGO AG","1DCD7-001","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,33,"2026-08-12","08:00:00","2026-08-14","16:00:00","2d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-03-25",null,null,1.7]
[null,"DB InfraGO AG","1DCD7-002","Karlsruhe - Strasbourg","<>","Waigolshausen","Mühlhausen (Wern)",2026,2026,33,33,"2026-08-12","08:00:00","2026-08-14","16:00:00","2d, 8h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1DCD7-003","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,33,"2026-08-12","09:30:00","2026-08-14","10:30:00","2d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1DCD7-004","Karlsruhe - Strasbourg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2026,2026,33,34,"2026-08-15","08:00:00","2026-08-18","16:00:00","3d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2025-05-28",null,null,1.7]
[null,"DB InfraGO AG","1DCD7-005","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,34,"2026-08-15","09:30:00","2026-08-18","10:30:00","3d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.2]
[null,"DB InfraGO AG","1DCD7-006","Karlsruhe - Strasbourg","<>","Waigolshausen","Mühlhausen (Wern)",2026,2026,34,34,"2026-08-19","08:00:00","2026-08-20","16:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.2]
[null,"DB InfraGO AG","1DD19-001","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Gädheim",2026,2026,29,30,"2026-07-19","21:00:00","2026-07-22","05:00:00","2d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-05-28",null,null,2]
[null,"DB InfraGO AG","1DD19-002","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Gädheim",2026,2026,30,30,"2026-07-20","01:30:00","2026-07-22","03:30:00","2d, 2h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,2]
[null,"DB InfraGO AG","1DD19-003","Karlsruhe - Strasbourg",">","Gädheim","Schweinfurt Hbf",2026,2026,30,30,"2026-07-22","21:00:00","2026-07-24","05:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-05-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD26-001","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Haßfurt",2026,2026,31,31,"2026-07-30","08:00:00","2026-07-31","15:30:00","1d, 7h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2025-05-28",null,null,3.4]
[null,"DB InfraGO AG","1DD26-004","Karlsruhe - Strasbourg",">","Haßfurt","Schweinfurt Stadt",2026,2026,31,31,"2026-08-01","08:00:00","2026-08-02","15:30:00","1d, 7h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1DD2B-001","Karlsruhe - Strasbourg",">","Gädheim","Schweinfurt Hbf",2026,2026,43,44,"2026-10-25","22:00:00","2026-10-27","05:00:00","1d, 7h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1DD2B-002","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,43,44,"2026-10-25","22:00:00","2026-10-27","05:00:00","1d, 7h","Periodical","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,",,0",null,null,null,"N",null,"2025-05-28",null,null,4.5]
[null,"DB InfraGO AG","1DD2B-003","Karlsruhe - Strasbourg","<>","Schweinfurt Stadt","Schweinfurt Hbf",2026,2026,44,44,"2026-10-26","02:00:00","2026-10-26","04:00:00","0d, 2h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","1DD2B-004","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,44,44,"2026-10-26","02:00:00","2026-10-26","04:00:00","0d, 2h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,",,0",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1DD2B-005","Karlsruhe - Strasbourg","<","Schweinfurt Hbf","Schweinfurt Stadt",2026,2026,44,44,"2026-10-27","22:30:00","2026-10-28","05:20:00","0d, 6h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","1DD2B-006","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,44,44,"2026-10-28","22:30:00","2026-10-29","05:20:00","0d, 6h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-05-28",null,null,7]
[null,"DB InfraGO AG","1DD2B-007","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,44,44,"2026-10-28","22:30:00","2026-10-29","05:20:00","0d, 6h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-05-28",null,null,7]
[null,"DB InfraGO AG","1DD36-001","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,48,49,"2026-11-28","22:30:00","2026-11-30","05:00:00","1d, 6h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-05-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-002","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Waigolshausen",2026,2026,48,49,"2026-11-29","02:00:00","2026-11-30","03:30:00","1d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-003","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,48,49,"2026-11-29","02:00:00","2026-11-30","03:30:00","1d, 1h","Periodical","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-004","Karlsruhe - Strasbourg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,49,49,"2026-11-30","22:10:00","2026-12-01","05:20:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-005","Karlsruhe - Strasbourg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-11-30","22:10:00","2026-12-01","05:20:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-006","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-12-01","21:30:00","2026-12-02","05:00:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DD36-007","Karlsruhe - Strasbourg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-03","05:20:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE17-001","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,25,25,"2026-06-17","21:00:00","2026-06-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE17-002","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,25,25,"2026-06-17","21:00:00","2026-06-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DE17-003","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Bbf",2026,2026,25,25,"2026-06-20","21:00:00","2026-06-21","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DE17-004","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Bbf",2026,2026,25,26,"2026-06-21","23:00:00","2026-06-22","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DE17-005","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Bbf",2026,2026,26,26,"2026-06-22","23:00:00","2026-06-23","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DE17-006","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,26,37,"2026-06-23","21:00:00","2026-09-13","04:55:00","81d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DE17-008","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-15","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-02",null,null,3.4]
[null,"DB InfraGO AG","1DE17-009","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-15","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE17-010","Karlsruhe - Strasbourg","<","Regensburg Bbf","Regensburg Ost",2026,2026,38,38,"2026-09-15","21:00:00","2026-09-16","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2025-03-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE17-011","Karlsruhe - Strasbourg","<","Regensburg Bbf","Regensburg Hbf",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-20","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE17-012","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Bbf",2026,2026,38,39,"2026-09-20","21:00:00","2026-09-21","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","1DE17-013","Karlsruhe - Strasbourg","<>","Regensburg Hbf","Regensburg Bbf",2026,2026,38,38,"2026-09-16","23:00:00","2026-09-18","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1DE53-001","Karlsruhe - Strasbourg","<>","Pforzheim Hbf","Mühlacker Em Süd",2026,2026,42,43,"2026-10-16","23:00:00","2026-10-20","04:00:00","3d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3.4]
[null,"DB InfraGO AG","1DEAC-001","Karlsruhe - Strasbourg",">","Freihalden Üst","Neuoffingen",2026,2026,27,27,"2026-06-29","21:00:00","2026-06-30","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,4.5]
[null,"DB InfraGO AG","1DEAC-002","Karlsruhe - Strasbourg","<>","Freihalden","Neuoffingen",2026,2026,27,27,"2026-06-30","02:00:00","2026-06-30","04:00:00","0d, 2h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1DEAC-003","Karlsruhe - Strasbourg","<>","Burgau (Schwab)","Burgau (Schwab)",2026,2026,27,27,"2026-06-29","21:00:00","2026-06-30","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1DFAD-001","Karlsruhe - Strasbourg",">","München Ost Pbf","Haar",2026,2026,50,50,"2026-12-07","23:00:00","2026-12-11","05:00:00","3d, 6h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1E076-001","Karlsruhe - Strasbourg",">","Rosenheim","Landl (Oberbay) Abzw",2026,2026,2,2,"2026-01-05","05:00:00","2026-01-06","13:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1E076-002","Karlsruhe - Strasbourg","<>","Rosenheim Ost","Rosenheim Süd",2026,2026,2,2,"2026-01-05","05:00:00","2026-01-06","13:00:00","1d, 8h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2]
[null,"DB InfraGO AG","1E076-003","Karlsruhe - Strasbourg",">","Rosenheim","Simssee",2026,2026,2,2,"2026-01-05","21:00:00","2026-01-06","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-004","Karlsruhe - Strasbourg","<>","Landl (Oberbay) Abzw","Rohrdorf (Oberbay)",2026,2026,2,2,"2026-01-05","21:00:00","2026-01-06","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-005","Karlsruhe - Strasbourg","<>","Rosenheim Ost","Rosenheim Süd",2026,2026,2,2,"2026-01-05","21:00:00","2026-01-06","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-006","Karlsruhe - Strasbourg","<>","Rosenheim","Simssee",2026,2026,2,2,"2026-01-06","02:30:00","2026-01-07","04:00:00","1d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-007","Karlsruhe - Strasbourg","<","Simssee","Rosenheim",2026,2026,2,2,"2026-01-06","21:00:00","2026-01-07","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E076-008","Karlsruhe - Strasbourg","<>","Landl (Oberbay) Abzw","Rohrdorf (Oberbay)",2026,2026,2,2,"2026-01-06","23:50:00","2026-01-07","04:00:00","0d, 4h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E076-009","Karlsruhe - Strasbourg","<","Landl (Oberbay) Abzw","Rosenheim",2026,2026,2,2,"2026-01-07","05:00:00","2026-01-07","13:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E076-010","Karlsruhe - Strasbourg",">","Landl (Oberbay) Abzw","Bad Endorf (Oberbay)",2026,2026,2,2,"2026-01-07","21:00:00","2026-01-08","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E076-011","Karlsruhe - Strasbourg","<>","Bad Endorf (Oberbay)","Landl (Oberbay) Abzw",2026,2026,2,2,"2026-01-08","02:30:00","2026-01-09","04:00:00","1d, 1h","Periodical","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E076-012","Karlsruhe - Strasbourg",">","Simssee","Bad Endorf (Oberbay)",2026,2026,2,2,"2026-01-08","05:00:00","2026-01-08","12:00:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-013","Karlsruhe - Strasbourg","<","Bad Endorf (Oberbay)","Landl (Oberbay) Abzw",2026,2026,2,2,"2026-01-08","21:00:00","2026-01-09","05:00:00","0d, 8h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-02",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-014","Karlsruhe - Strasbourg","<","Bad Endorf (Oberbay)","Simssee",2026,2026,2,2,"2026-01-09","05:00:00","2026-01-09","12:00:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E076-015","Karlsruhe - Strasbourg",">","Landl (Oberbay) Abzw","Simssee",2026,2026,3,3,"2026-01-12","07:00:00","2026-01-13","21:00:00","1d, 14h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,6.7]
[null,"DB InfraGO AG","1E076-016","Karlsruhe - Strasbourg",">","Landl (Oberbay) Abzw","Simssee",2026,2026,3,3,"2026-01-14","07:00:00","2026-01-14","14:00:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-11",null,null,6.7]
[null,"DB InfraGO AG","1E076-017","Karlsruhe - Strasbourg","<","Simssee","Landl (Oberbay) Abzw",2026,2026,3,3,"2026-01-14","14:00:00","2026-01-14","21:00:00","0d, 7h","Continuous","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-11",null,null,6.7]
[null,"DB InfraGO AG","1E076-018","Karlsruhe - Strasbourg","<","Simssee","Landl (Oberbay) Abzw",2026,2026,3,3,"2026-01-15","07:00:00","2026-01-16","21:00:00","1d, 14h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-019","Karlsruhe - Strasbourg","<","Bad Endorf (Oberbay)","Simssee",2026,2026,4,4,"2026-01-19","07:00:00","2026-01-20","21:00:00","1d, 14h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-11",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E076-020","Karlsruhe - Strasbourg",">","Simssee","Bad Endorf (Oberbay)",2026,2026,4,4,"2026-01-21","07:00:00","2026-01-22","21:00:00","1d, 14h","Periodical","Oberleitungsvollinspektion",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-21",null,null,1.2]
[null,"DB InfraGO AG","1E07D-003","Karlsruhe - Strasbourg","<","Bietigheim-Bissingen","Ludwigsburg",2026,2026,35,37,"2026-08-29","05:00:00","2026-09-07","05:00:00","9d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E12D-001","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","01:00:00","2026-08-17","07:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,4.5]
[null,"DB InfraGO AG","1E12D-002","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","01:00:00","2026-08-17","07:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","1E12D-004","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","07:00:00","2026-08-21","21:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-10-11",null,null,"2,3,4"]
[null,"DB InfraGO AG","1E12D-005","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","07:00:00","2026-08-21","21:00:00","4d, 14h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,7]
[null,"DB InfraGO AG","1E12D-006","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-06-16",null,null,7]
[null,"DB InfraGO AG","1E12D-007","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,5.6]
[null,"DB InfraGO AG","1E12D-011","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-26","16:00:00","4d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-10-11",null,null,"2,3,4"]
[null,"DB InfraGO AG","1E12D-012","Karlsruhe - Strasbourg","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-26","16:00:00","4d, 19h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"2,3,4"]
[null,"DB InfraGO AG","1E18E-001","Karlsruhe - Strasbourg","<>","Beratzhausen","Seubersdorf",2026,2026,35,36,"2026-08-28","01:00:00","2026-08-31","04:00:00","3d, 3h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,5.7]
[null,"DB InfraGO AG","1E18E-002","Karlsruhe - Strasbourg","<>","Beratzhausen","Beratzhausen",2026,2026,37,40,"2026-09-07","20:00:00","2026-09-29","06:00:00","21d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E18E-003","Karlsruhe - Strasbourg","<>","Parsberg","Parsberg",2026,2026,41,44,"2026-10-05","20:00:00","2026-10-26","06:00:00","20d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E18E-004","Karlsruhe - Strasbourg","<>","Seubersdorf","Seubersdorf",2026,2026,45,48,"2026-11-03","00:00:00","2026-11-23","06:00:00","20d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E18E-005","Karlsruhe - Strasbourg",">","Undorf","Parsberg",2026,2026,40,41,"2026-10-02","01:00:00","2026-10-05","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E18E-006","Karlsruhe - Strasbourg",">","Beratzhausen","Seubersdorf",2026,2026,44,45,"2026-10-30","01:00:00","2026-11-02","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E18E-007","Karlsruhe - Strasbourg",">","Parsberg","Deining Üst",2026,2026,48,49,"2026-11-27","01:00:00","2026-11-30","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-15",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-002","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt-Süd",2026,2026,14,14,"2026-03-30","23:00:00","2026-04-03","05:00:00","3d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E199-004","Karlsruhe - Strasbourg","<","Baden-Baden","Baden-Baden",2026,2026,14,15,"2026-03-30","23:00:00","2026-04-06","05:00:00","6d, 6h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-03-24",null,null,1]
[null,"DB InfraGO AG","1E199-005","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,14,14,"2026-03-30","23:00:00","2026-04-03","05:00:00","3d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-10",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E199-008","Karlsruhe - Strasbourg","<","Ottersweier","Rastatt-Süd",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"5,6,7"]
[null,"DB InfraGO AG","1E199-009","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-011","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-014","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","23:00:00","2026-04-10","05:00:00","3d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-015","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,14,14,"2026-03-30","23:00:00","2026-04-03","05:00:00","3d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-02-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-016","Karlsruhe - Strasbourg",">","Rastatt","Ottersweier",2026,2026,15,15,"2026-04-06","23:00:00","2026-04-10","05:00:00","3d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-22",null,null,3.4]
[null,"DB InfraGO AG","1E199-017","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","23:00:00","2026-04-10","05:00:00","3d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-13",null,null,1.7]
[null,"DB InfraGO AG","1E199-018","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-06","23:00:00","2026-04-13","07:00:00","6d, 8h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-08-01",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E199-019","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1E199-020","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-021","Karlsruhe - Strasbourg","<","Ottersweier","Rastatt",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1E199-022","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,16,16,"2026-04-13","05:00:00","2026-04-13","07:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E199-023","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,16,16,"2026-04-13","05:00:00","2026-04-13","07:00:00","0d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3"]
[null,"DB InfraGO AG","1E199-024","Karlsruhe - Strasbourg",">","Rastatt","Ottersweier",2026,2026,16,16,"2026-04-13","05:00:00","2026-04-13","07:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-05",null,null,5]
[null,"DB InfraGO AG","1E199-025","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-05",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-026","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-05",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E199-027","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","05:00:00","2026-04-07","07:00:00","1d, 2h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-028","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-07","07:00:00","2026-04-08","07:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E199-029","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,16,16,"2026-04-13","05:00:00","2026-04-15","07:00:00","2d, 2h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E2B3-002","Karlsruhe - Strasbourg","<>","Pforzheim Hbf","Pforzheim Hbf",2026,2026,36,38,"2026-09-01","22:00:00","2026-09-14","22:00:00","13d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-08-04",null,null,"3,4,5,6"]
[null,"DB InfraGO AG","1E2B3-003","Karlsruhe - Strasbourg","<>","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,36,38,"2026-09-01","22:00:00","2026-09-14","22:00:00","13d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E2B3-005","Karlsruhe - Strasbourg","<>","Grötzingen","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"3,4,5,6"]
[null,"DB InfraGO AG","1E2B3-007","Karlsruhe - Strasbourg","<>","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E2B3-008","Karlsruhe - Strasbourg","<>","Söllingen (b Karlsruhe) Abzw","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E2B3-009","Karlsruhe - Strasbourg","<>","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-11","22:00:00","2d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E2B3-010","Karlsruhe - Strasbourg","<>","Kleinsteinbach","Kleinsteinbach",2026,2026,37,37,"2026-09-11","22:00:00","2026-09-12","22:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E4C5-005","Darmstadt - Nürnberg","<>","Nürnberg Großmarkt","Fürth (Bay) Gbf",2026,2026,31,32,"2026-07-30","05:00:00","2026-08-06","21:00:00","7d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E4C5-008","Darmstadt - Nürnberg","<","Fürth (Bay) Gbf","Nürnberg Hohe Marter",2026,2026,32,34,"2026-08-08","05:00:00","2026-08-17","21:00:00","9d, 16h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E4C5-009","Darmstadt - Nürnberg","<>","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,32,34,"2026-08-08","05:00:00","2026-08-17","21:00:00","9d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,1]
[null,"DB InfraGO AG","1E501-001","Karlsruhe - Strasbourg",">","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E501-002","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-06-24",null,null,4]
[null,"DB InfraGO AG","1E501-003","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,4]
[null,"DB InfraGO AG","1E501-004","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-06-24",null,null,4]
[null,"DB InfraGO AG","1E501-005","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,17,17,"2026-04-20","23:00:00","2026-04-23","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-06-24",null,null,5]
[null,"DB InfraGO AG","1E501-007","Karlsruhe - Strasbourg",">","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-07-18",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E501-008","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-12",null,null,6]
[null,"DB InfraGO AG","1E501-009","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-12",null,null,2]
[null,"DB InfraGO AG","1E501-010","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-011","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-07-30",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-017","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,35,37,"2026-08-29","00:00:00","2026-09-11","23:59:00","13d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-019","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,37,"2026-08-29","18:00:00","2026-09-12","12:00:00","13d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-020","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-021","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-30",null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E501-022","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3]
[null,"DB InfraGO AG","1E501-023","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-30",null,null,3]
[null,"DB InfraGO AG","1E501-024","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,3]
[null,"DB InfraGO AG","1E501-025","Frankfurt - Karlsruhe","<","Grötzingen","Karlsruhe Hbf",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,3]
[null,"DB InfraGO AG","1E501-026","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,3]
[null,"DB InfraGO AG","1E501-027","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3]
[null,"DB InfraGO AG","1E550-001","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,1.2]
[null,"DB InfraGO AG","1E550-002","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,1.2]
[null,"DB InfraGO AG","1E550-004","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-09",null,null,2]
[null,"DB InfraGO AG","1E550-005","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,2]
[null,"DB InfraGO AG","1E550-006","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Grötzingen",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-08",null,null,2]
[null,"DB InfraGO AG","1E550-007","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-07-29",null,null,2]
[null,"DB InfraGO AG","1E550-008","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,5]
[null,"DB InfraGO AG","1E550-009","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,5]
[null,"DB InfraGO AG","1E550-010","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,5]
[null,"DB InfraGO AG","1E550-011","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E550-012","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-18",null,null,5]
[null,"DB InfraGO AG","1E550-013","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,4]
[null,"DB InfraGO AG","1E550-014","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-19",null,null,1.2]
[null,"DB InfraGO AG","1E550-015","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-19",null,null,1.2]
[null,"DB InfraGO AG","1E550-016","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","1E550-017","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-018","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-019","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-020","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Grötzingen",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-021","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-022","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-023","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-024","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-025","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7]
[null,"DB InfraGO AG","1E550-026","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Grötzingen",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-14",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E550-027","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Grötzingen",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5BF-001","Karlsruhe - Strasbourg","<>","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5BF-002","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5BF-003","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5BF-004","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,37,37,"2026-09-11","15:00:00","2026-09-11","21:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5BF-005","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-11","15:00:00","2026-09-11","21:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5BF-007","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,38,"2026-09-11","21:00:00","2026-09-16","08:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-13",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5BF-008","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,38,"2026-09-11","21:00:00","2026-09-16","08:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-28",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5EA-001","Darmstadt - Nürnberg","<","Fürth (Bay) Gbf","Nürnberg Hohe Marter",2026,2026,40,41,"2026-10-02","05:00:00","2026-10-07","21:00:00","5d, 16h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2023-11-28",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E5EA-002","Darmstadt - Nürnberg","<>","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,40,41,"2026-10-02","05:00:00","2026-10-07","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,7"]
[null,"DB InfraGO AG","1E5EA-004","Darmstadt - Nürnberg","<>","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,41,42,"2026-10-08","05:00:00","2026-10-13","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-029","Nürnberg - Passau","<","Undorf","Regensburg Dörnberg",2026,2026,44,44,"2026-10-30","21:00:00","2026-10-31","00:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-030","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,44,44,"2026-10-31","01:00:00","2026-10-31","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-031","Nürnberg - Passau",">","Seubersdorf","Neumarkt (Oberpf)",2026,2026,44,45,"2026-11-01","22:00:00","2026-11-02","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","1E5FD-032","Nürnberg - Passau",">","Parsberg","Seubersdorf",2026,2026,45,45,"2026-11-02","21:00:00","2026-11-06","05:00:00","3d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","1E5FD-033","Nürnberg - Passau",">","Deining Üst","Neumarkt (Oberpf)",2026,2026,45,45,"2026-11-02","21:00:00","2026-11-05","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-034","Nürnberg - Passau","<","Neumarkt (Oberpf)","Deining (Oberpf)",2026,2026,46,46,"2026-11-09","21:00:00","2026-11-12","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-035","Nürnberg - Passau","<","Deining Üst","Seubersdorf",2026,2026,46,46,"2026-11-09","21:00:00","2026-11-14","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-036","Nürnberg - Passau","<","Neumarkt (Oberpf)","Seubersdorf",2026,2026,46,46,"2026-11-12","21:00:00","2026-11-13","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-037","Nürnberg - Passau","<","Undorf","Regensburg Hbf",2026,2026,47,47,"2026-11-16","19:00:00","2026-11-16","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-038","Nürnberg - Passau","<","Beratzhausen","Undorf",2026,2026,47,47,"2026-11-16","19:00:00","2026-11-16","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-07",null,null,4.5]
[null,"DB InfraGO AG","1E5FD-039","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,47,47,"2026-11-16","22:00:00","2026-11-17","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,4.5]
[null,"DB InfraGO AG","1E5FD-040","Nürnberg - Passau",">","Undorf","Beratzhausen",2026,2026,47,47,"2026-11-16","22:00:00","2026-11-17","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-041","Nürnberg - Passau","<>","Regensburg-Prüfening               (NRH)","Beratzhausen",2026,2026,47,47,"2026-11-17","01:00:00","2026-11-17","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-042","Nürnberg - Passau",">","Beratzhausen","Parsberg",2026,2026,47,47,"2026-11-17","19:00:00","2026-11-17","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-043","Nürnberg - Passau","<","Deining Üst","Seubersdorf",2026,2026,47,47,"2026-11-17","19:00:00","2026-11-17","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-044","Nürnberg - Passau","<","Parsberg","Beratzhausen",2026,2026,47,47,"2026-11-17","22:00:00","2026-11-18","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-045","Nürnberg - Passau",">","Seubersdorf","Deining Üst",2026,2026,47,47,"2026-11-17","22:00:00","2026-11-18","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E5FD-046","Nürnberg - Passau","<>","Beratzhausen","Deining Üst",2026,2026,47,47,"2026-11-18","01:00:00","2026-11-18","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-047","Nürnberg - Passau","<","Neumarkt (Oberpf)","Deining Üst",2026,2026,47,47,"2026-11-18","19:00:00","2026-11-18","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-048","Nürnberg - Passau","<","Postbauer-Heng","Neumarkt (Oberpf)",2026,2026,47,47,"2026-11-18","19:00:00","2026-11-18","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-16",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1E5FD-049","Nürnberg - Passau",">","Deining Üst","Neumarkt (Oberpf)",2026,2026,47,47,"2026-11-18","22:00:00","2026-11-19","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","1E5FD-050","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,47,47,"2026-11-18","22:00:00","2026-11-19","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","1E5FD-051","Nürnberg - Passau","<>","Deining Üst","Postbauer-Heng",2026,2026,47,47,"2026-11-19","01:00:00","2026-11-19","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,6]
[null,"DB InfraGO AG","1E5FD-052","Nürnberg - Passau","<","Ochenbruck","Postbauer-Heng",2026,2026,47,47,"2026-11-19","19:00:00","2026-11-19","22:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,6]
[null,"DB InfraGO AG","1E5FD-053","Nürnberg - Passau",">","Postbauer-Heng","Ochenbruck",2026,2026,47,47,"2026-11-19","22:00:00","2026-11-20","01:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","1E5FD-054","Nürnberg - Passau","<>","Ochenbruck","Postbauer-Heng",2026,2026,47,47,"2026-11-20","01:00:00","2026-11-20","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","1E622-001","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","00:00:00","2026-08-31","06:00:00","5d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","1E622-003","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","1E622-004","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","1E622-010","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1E622-011","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-28",null,null,1.7]
[null,"DB InfraGO AG","1E622-012","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,1.7]
[null,"DB InfraGO AG","1E622-013","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E622-014","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E622-016","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E622-017","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-09-05","04:00:00","2026-09-05","06:00:00","0d, 2h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E622-018","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-09-05","04:00:00","2026-09-05","06:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","1E709-002","Frankfurt - Karlsruhe","<>","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,15,15,"2026-04-06","00:00:00","2026-04-08","23:59:00","2d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,1]
[null,"DB InfraGO AG","1E709-003","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-29",null,null,1]
[null,"DB InfraGO AG","1E709-004","Frankfurt - Karlsruhe",">","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-13",null,null,1]
[null,"DB InfraGO AG","1E709-005","Frankfurt - Karlsruhe","<>","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,1]
[null,"DB InfraGO AG","1E709-006","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,1.2]
[null,"DB InfraGO AG","1E709-007","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,1.2]
[null,"DB InfraGO AG","1E709-008","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E709-009","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2]
[null,"DB InfraGO AG","1E709-010","Frankfurt - Karlsruhe","<","Neu-Edingen/Mhm-Friedrichsfeld","Heddesheim/Hirschberg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E709-011","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E709-012","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,2]
[null,"DB InfraGO AG","1E709-013","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E709-014","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E709-015","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,2]
[null,"DB InfraGO AG","1E709-016","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,6.7]
[null,"DB InfraGO AG","1E72E-003","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,6.7]
[null,"DB InfraGO AG","1E72E-004","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","1E72E-005","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","22:00:00","2026-10-02","04:00:00","6d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-13",null,null,3]
[null,"DB InfraGO AG","1E72E-006","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-26","00:30:00","2026-10-02","05:00:00","6d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,3.4]
[null,"DB InfraGO AG","1E72E-007","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,39,"2026-09-25","21:00:00","2026-09-25","22:00:00","0d, 1h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,3.4]
[null,"DB InfraGO AG","1E72E-008","Karlsruhe - München","<","Walheim (Württ)","Bietigheim-Bissingen",2026,2026,39,39,"2026-09-25","21:00:00","2026-09-25","22:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,4]
[null,"DB InfraGO AG","1E72E-010","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,39,"2026-09-25","21:00:00","2026-09-25","22:00:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-07-03",null,null,1.7]
[null,"DB InfraGO AG","1E72E-012","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,40,40,"2026-10-02","04:00:00","2026-10-02","05:00:00","0d, 1h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-03",null,null,1.2]
[null,"DB InfraGO AG","1E72E-013","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,40,40,"2026-10-02","04:00:00","2026-10-02","05:00:00","0d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-24",null,null,1.7]
[null,"DB InfraGO AG","1E72E-016","Karlsruhe - München","<","Walheim (Württ)","Bietigheim-Bissingen",2026,2026,40,40,"2026-10-02","04:00:00","2026-10-02","05:00:00","0d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-24",null,null,1.2]
[null,"DB InfraGO AG","1E72F-001","Nürnberg - Passau","<>","Neumarkt (Oberpf)","Neumarkt (Oberpf)",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","1E72F-002","Nürnberg - Passau","<>","Regensburg Bbf","Regensburg Bbf",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E72F-003","Nürnberg - Passau","<>","Feucht","Feucht",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-004","Nürnberg - Passau","<","Nürnberg Reichswald","Feucht",2026,2026,40,41,"2026-10-04","21:00:00","2026-10-05","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-24",null,null,5.6]
[null,"DB InfraGO AG","1E72F-005","Nürnberg - Passau",">","Nürnberg-Langwasser","Nürnberg Reichswald",2026,2026,40,41,"2026-10-04","21:00:00","2026-10-05","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2025-03-24",null,null,5.6]
[null,"DB InfraGO AG","1E72F-006","Nürnberg - Passau",">","Ochenbruck","Nürnberg Reichswald",2026,2026,41,41,"2026-10-05","21:00:00","2026-10-07","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-24",null,null,"1,6,7"]
[null,"DB InfraGO AG","1E72F-007","Nürnberg - Passau",">","Ochenbruck","Nürnberg Reichswald",2026,2026,41,41,"2026-10-06","01:00:00","2026-10-06","03:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-24",null,null,"1,6,7"]
[null,"DB InfraGO AG","1E72F-008","Nürnberg - Passau",">","Nürnberg-Dürrenhof","Feucht",2026,2026,41,41,"2026-10-06","01:00:00","2026-10-06","03:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,15",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-009","Nürnberg - Passau","<>","Seubersdorf","Parsberg",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","01:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-010","Nürnberg - Passau",">","Parsberg","Seubersdorf",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","01:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-011","Nürnberg - Passau","<>","Feucht","Feucht",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","01:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,6.7]
[null,"DB InfraGO AG","1E72F-012","Nürnberg - Passau","<>","Feucht","Feucht",2026,2026,41,41,"2026-10-08","01:00:00","2026-10-08","03:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"N",null,"2025-08-13",null,null,4.5]
[null,"DB InfraGO AG","1E72F-013","Nürnberg - Passau","<","Parsberg","Beratzhausen",2026,2026,41,42,"2026-10-08","21:00:00","2026-10-13","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-13",null,null,"1,6,7"]
[null,"DB InfraGO AG","1E72F-014","Nürnberg - Passau","<","Nürnberg Reichswald","Feucht",2026,2026,41,41,"2026-10-08","21:00:00","2026-10-10","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-015","Nürnberg - Passau",">","Postbauer-Heng","Feucht",2026,2026,42,42,"2026-10-12","01:00:00","2026-10-12","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,6]
[null,"DB InfraGO AG","1E72F-016","Nürnberg - Passau",">","Beratzhausen","Parsberg",2026,2026,41,41,"2026-10-08","01:00:00","2026-10-08","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-17",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-017","Nürnberg - Passau","<","Ochenbruck","Postbauer-Heng",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-18","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-018","Nürnberg - Passau",">","Undorf","Parsberg",2026,2026,42,42,"2026-10-14","00:00:00","2026-10-14","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"2,3,4,5,6"]
[null,"DB InfraGO AG","1E72F-019","Nürnberg - Passau","<","Beratzhausen","Undorf",2026,2026,42,42,"2026-10-15","00:00:00","2026-10-15","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","1E72F-020","Nürnberg - Passau",">","Undorf","Beratzhausen",2026,2026,42,43,"2026-10-18","21:00:00","2026-10-24","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-021","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,43,43,"2026-10-20","21:00:00","2026-10-23","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-17",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","1E72F-022","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,43,43,"2026-10-24","00:00:00","2026-10-24","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-17",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","1E72F-023","Nürnberg - Passau",">","Deining Üst","Postbauer-Heng",2026,2026,44,44,"2026-10-27","19:00:00","2026-10-28","05:00:00","0d, 10h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-024","Nürnberg - Passau",">","Regensburg Bbf","Beratzhausen",2026,2026,44,44,"2026-10-28","00:00:00","2026-10-28","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-025","Nürnberg - Passau","<","Postbauer-Heng","Neumarkt (Oberpf)",2026,2026,44,44,"2026-10-28","21:00:00","2026-10-29","02:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-026","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,44,44,"2026-10-28","21:00:00","2026-10-29","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-027","Nürnberg - Passau","<","Postbauer-Heng","Deining Üst",2026,2026,44,44,"2026-10-29","02:00:00","2026-10-29","05:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-028","Nürnberg - Passau","<","Undorf","Regensburg Dörnberg",2026,2026,44,44,"2026-10-29","21:00:00","2026-10-30","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E72F-029","Nürnberg - Passau","<>","Parsberg","Parsberg",2026,2026,41,41,"2026-10-07","01:00:00","2026-10-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","1E768-008","Karlsruhe - Strasbourg","<>","Appenweier","Offenburg",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,null,null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-06-24",null,null,"5,6,7"]
[null,"DB InfraGO AG","1E768-020","Karlsruhe - Strasbourg","<>","Rastatt-Süd","Appenweier-Muhrhaag",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,6]
[null,"DB InfraGO AG","1E768-021","Karlsruhe - Strasbourg","<>","Appenweier Nord","Appenweier Nord",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-24",null,null,6]
[null,"DB InfraGO AG","1E768-023","Karlsruhe - Strasbourg","<>","Rastatt-Süd","Offenburg Ülp südl Esig",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",7,",null,null,null,"N",null,"2024-06-24",null,null,5]
[null,"DB InfraGO AG","1E768-024","Karlsruhe - Strasbourg","<>","Appenweier Nord","Appenweier Nord",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-06-17",null,null,5]
[null,"DB InfraGO AG","1E768-026","Karlsruhe - Strasbourg","<>","Offenburg Ülp südl Esig","Rastatt-Süd",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",7,",null,null,null,"N",null,"2024-06-17",null,null,5.6]
[null,"DB InfraGO AG","1E81C-001","Frankfurt - Karlsruhe","<","Vaihingen (Enz)","Mettertal",2026,2026,9,11,"2026-02-23","22:30:00","2026-03-14","05:00:00","18d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2025-03-24",null,null,6.7]
[null,"DB InfraGO AG","1E81C-002","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,9,11,"2026-02-23","22:30:00","2026-03-14","05:00:00","18d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-05-16",null,null,6.7]
[null,"DB InfraGO AG","1E81C-003","Frankfurt - Karlsruhe","<>","Kraichtal","Vaihingen (Enz)",2026,2026,10,11,"2026-03-07","23:00:00","2026-03-09","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E81C-004","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,10,11,"2026-03-07","23:00:00","2026-03-09","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-12-11",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1E81C-005","Frankfurt - Karlsruhe",">","Mettertal","Vaihingen (Enz)",2026,2026,12,14,"2026-03-16","22:30:00","2026-04-04","05:00:00","18d, 5h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-05-16",null,null,7]
[null,"DB InfraGO AG","1E81C-011","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,15,17,"2026-04-10","22:30:00","2026-04-22","05:00:00","11d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-16",null,null,1.7]
[null,"DB InfraGO AG","1E81C-018","Frankfurt - Karlsruhe",">","Vaihingen (Enz)","Illingen (Württ)",2026,2026,17,18,"2026-04-22","22:30:00","2026-05-02","05:00:00","9d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1E95C-002","Nürnberg - Passau","<>","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,47,"2026-10-29","08:00:00","2026-11-16","08:00:00","18d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-17",null,null,7]
[null,"DB InfraGO AG","1E95C-013","Nürnberg - Passau","<>","Feucht","Nürnberg-Langwasser",2026,2026,46,46,"2026-11-10","10:00:00","2026-11-12","16:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,6]
[null,"DB InfraGO AG","1E95C-019","Nürnberg - Passau","<>","Nürnberg Reichswald","Nürnberg-Dutzendteich",2026,2026,46,46,"2026-11-13","01:00:00","2026-11-13","02:00:00","0d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,7]
[null,"DB InfraGO AG","1EEEE-008","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,22,24,"2026-05-25","22:30:00","2026-06-13","05:00:00","18d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1EEEE-018","Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,27,29,"2026-07-02","22:30:00","2026-07-18","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-15",null,null,7]
[null,"DB InfraGO AG","1EEEE-024","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Langes Feld",2026,2026,27,28,"2026-07-04","23:00:00","2026-07-06","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,6.7]
[null,"DB InfraGO AG","1F00D-010","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,3,4,"2026-01-16","22:00:00","2026-01-19","05:00:00","2d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1F00D-027","Karlsruhe - Strasbourg","<>","Kork","Kork",2026,2026,8,10,"2026-02-21","08:00:00","2026-03-08","18:00:00","15d, 10h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-07-18",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1F00D-033","Karlsruhe - Strasbourg","<>","Kehl","Kehl Grenze",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-04","05:00:00","4d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2025-08-05",null,null,"1,2,6,7"]
[null,"DB InfraGO AG","1F08E-012","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,1]
[null,"DB InfraGO AG","1F188-001","Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,30,32,"2026-07-20","22:30:00","2026-08-05","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1F188-008","Frankfurt - Karlsruhe","<","Vaihingen (Enz)","Freudenstein",2026,2026,33,34,"2026-08-14","22:30:00","2026-08-21","05:00:00","6d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2025-05-02",null,null,1.7]
[null,"DB InfraGO AG","1F43D-004","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt-Süd",2026,2026,41,41,"2026-10-06","00:01:00","2026-10-09","04:00:00","3d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-01",null,null,1.2]
[null,"DB InfraGO AG","1F6AE-006","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,40,41,"2026-10-03","23:00:00","2026-10-05","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-05-21",null,null,1]
[null,"DB InfraGO AG","1F6AE-024","Frankfurt - Karlsruhe",">","Vaihingen (Enz)","Langes Feld",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-28",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1F71F-001","Frankfurt - Karlsruhe","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2025-07-28",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1F819-010","München - Regensburg","<>","Obertraubling","Regensburg Ost",2026,2026,31,32,"2026-08-01","21:00:00","2026-08-08","21:00:00","7d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1FA7F-009","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-08","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1FA7F-015","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,15,16,"2026-04-12","22:00:00","2026-04-13","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-06-30",null,null,7]
[null,"DB InfraGO AG","1FA7F-025","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,17,17,"2026-04-26","00:00:00","2026-04-26","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-02",null,null,1.7]
[null,"DB InfraGO AG","1FA7F-042","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,18,18,"2026-05-01","21:00:00","2026-05-01","22:00:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-02",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","1FA7F-048","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-02",null,null,1.2]
[null,"DB InfraGO AG","1FA90-035","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,21,22,"2026-05-22","22:00:00","2026-05-26","16:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-08-06",null,null,4.5]
[null,"DB InfraGO AG","1FA90-052","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,31,31,"2026-08-01","03:00:00","2026-08-01","13:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-15",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1FA90-058","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","02:00:00","2d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","1FB9B-025","Frankfurt - Karlsruhe","<>","Ladenburg","Ladenburg",2026,2026,29,30,"2026-07-17","21:00:00","2026-07-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1FBE8-005","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,19,21,"2026-05-09","07:00:00","2026-05-22","05:00:00","12d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-07",null,null,6.7]
[null,"DB InfraGO AG","1FFF4-009","Karlsruhe - München","<","Gingen Süd","Eislingen (Fils)",2026,2026,37,37,"2026-09-07","00:30:00","2026-09-07","04:30:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-07",null,null,6.7]
[null,"DB InfraGO AG","1FFFE-003","Darmstadt - Nürnberg","<>","Nantenbach","Nantenbach",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"1,2,3,7"]
[null,"DB InfraGO AG","2037B-003","Darmstadt - Nürnberg","<>","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998]
[null,"DB InfraGO AG","2037B-018","Darmstadt - Nürnberg","<>","Gemünden (Main)","Gemünden (Main)",2026,2026,40,41,"2026-09-29","23:00:00","2026-10-05","05:00:00","5d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-04",null,null,1.2]
[null,"DB InfraGO AG","2057A-005","Nürnberg - Passau","<>","Nürnberg Ost","Nürnberg Ost",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,3.4]
[null,"DB InfraGO AG","2057A-013","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,41,42,"2026-10-11","23:40:00","2026-10-12","06:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2025-08-11",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","20AD8-007","Darmstadt - Nürnberg",">","Gemünden Zollberg","Gemünden (Main)",2026,2026,29,30,"2026-07-14","21:00:00","2026-07-21","05:00:00","6d, 8h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-11",null,null,2]
[null,"DB InfraGO AG","20BF3-010","Karlsruhe - München",">","Süßen","Gingen Süd",2026,2026,34,35,"2026-08-23","03:00:00","2026-08-24","04:30:00","1d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-04",null,null,3.4]
[null,"DB InfraGO AG","20C05-018","Darmstadt - Nürnberg",">","Darmstadt-Kranichstein","Messel",2026,2026,5,5,"2026-01-31","21:00:00","2026-02-01","09:00:00","0d, 12h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","20C05-025","Darmstadt - Nürnberg",">","Darmstadt Nord","Darmstadt-Kranichstein",2026,2026,6,6,"2026-02-07","21:00:00","2026-02-08","09:00:00","0d, 12h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-28",null,null,"1,2,3,7"]
[null,"DB InfraGO AG","20C05-032","Darmstadt - Nürnberg","<>","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-20","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,6,7"]
[null,"DB InfraGO AG","20DE0-002","Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,38,"2026-08-04","00:00:00","2026-09-16","00:00:00","43d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","20DE0-008","Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,32,33,"2026-08-09","00:00:00","2026-08-15","04:45:00","6d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","20DE0-021","Nürnberg - Plzen","<>","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,34,38,"2026-08-20","04:45:00","2026-09-14","08:00:00","25d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-12-12",null,null,3]
[null,"DB InfraGO AG","2124F-011","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,44,44,"2026-10-30","00:10:00","2026-10-30","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-16",null,null,6.7]
[null,"DB InfraGO AG","216FB-006","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,19,19,"2026-05-04","22:00:00","2026-05-05","02:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-12-01",null,null,4.5]
[null,"DB InfraGO AG","216FB-016","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Jansenbrücke",2026,2026,19,20,"2026-05-08","22:00:00","2026-05-13","22:00:00","5d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","218BA-001","Darmstadt - Nürnberg","<>","Stockstadt (Main)","Mainaschaff",2026,2026,41,42,"2026-10-11","21:00:00","2026-10-12","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-30",null,null,6.7]
[null,"DB InfraGO AG","218BA-007","Darmstadt - Nürnberg","<>","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-23","05:00:00","9d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-02",null,null,1.2]
[null,"DB InfraGO AG","21C52-011","Karlsruhe - München",">","Westerstetten","Ulm-Örlingen",2026,2026,3,4,"2026-01-17","21:00:00","2026-01-23","04:50:00","5d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-11",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","21CCE-014","Karlsruhe - München","<>","Beimerstetten","Ulm-Örlingen",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","04:50:00","3d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-11",null,null,3.4]
[null,"DB InfraGO AG","221FC-001","Darmstadt - Nürnberg","<>","Gemünden (Main)","Gemünden (Main)",2026,2026,46,50,"2026-11-14","21:00:00","2026-12-11","05:00:00","26d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5,7"]
[null,"DB InfraGO AG","222AD-001","Darmstadt - Nürnberg","<>","Gemünden (Main)","Gemünden (Main)",2026,2026,26,34,"2026-06-26","21:00:00","2026-08-21","06:00:00","55d, 9h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","222FB-035","Karlsruhe - München","<>","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,3]
[null,"DB InfraGO AG","222FB-048","Karlsruhe - München",">","Geislingen (Steige)","Westerstetten",2026,2026,36,36,"2026-09-05","23:00:00","2026-09-06","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,7"]
[null,"DB InfraGO AG","22378-002","Nürnberg - Plzen","<>","Neusorg","Marktredwitz",2026,2026,31,32,"2026-07-31","21:00:00","2026-08-06","05:00:00","5d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,2.2999999999999998]
[null,"DB InfraGO AG","22494-011","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-14",null,null,5]
[null,"DB InfraGO AG","22527-008","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,34,36,"2026-08-23","21:00:00","2026-09-01","05:00:00","8d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-03-24",null,null,1.7]
[null,"DB InfraGO AG","22527-015","Karlsruhe - München","<>","Amstetten (Württ)","Amstetten (Württ)",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-03-24",null,null,2.2999999999999998]
[null,"DB InfraGO AG","22527-027","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"9,,9",null,null,null,"N",null,"2025-08-04",null,null,7]
[null,"DB InfraGO AG","22ED3-016","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,29,33,"2026-07-17","22:00:00","2026-08-10","04:00:00","23d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","22ED4-001","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-07","20:00:00","13d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-02",null,null,4]
[null,"DB InfraGO AG","22ED4-014","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,33,33,"2026-08-10","04:00:00","2026-08-12","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998]
[null,"DB InfraGO AG","24B92-002","Frankfurt - Karlsruhe",">","Vaihingen (Enz)","Glems",2026,2026,2,2,"2026-01-08","23:00:00","2026-01-09","05:30:00","0d, 6h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-09-18",null,null,3.4]
[null,"DB InfraGO AG","2524A-004","Frankfurt - Karlsruhe","<>","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,44,44,"2026-10-30","22:00:00","2026-11-01","06:00:00","1d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-05",null,null,5.6]
[null,"DB InfraGO AG","2524A-010","Frankfurt - Karlsruhe","<","Heddesheim/Hirschberg","Weinheim (Bergstr) Hbf",2026,2026,45,45,"2026-11-04","00:45:00","2026-11-04","02:45:00","0d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-13",null,null,6.7]
[null,"DB InfraGO AG","27CB6-005","Frankfurt - Karlsruhe","<","Schwetzingen","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,32,32,"2026-08-04","21:00:00","2026-08-07","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-23",null,null,6.7]
[null,"DB InfraGO AG","27CB6-008","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,43,44,"2026-10-25","23:00:00","2026-10-27","05:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","27CB6-020","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim-Friedrichsfeld Südeinf/Ausf",2026,2026,43,43,"2026-10-23","21:00:00","2026-10-25","05:00:00","1d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-23",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","2A048-003","Darmstadt - Nürnberg","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2026,2026,17,17,"2026-04-20","01:00:00","2026-04-20","04:00:00","0d, 3h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","2A6C6-002","München - Salzburg","<>","Rosenheim","Wasserburg (Inn) Bahnhof",2026,2026,31,37,"2026-07-31","23:00:00","2026-09-07","04:00:00","37d, 5h","Continuous",null,"T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","2A7D2-003","Karlsruhe - Strasbourg",">","Philippsburg Molzau","Graben-Neudorf",2026,2026,50,50,"2026-12-08","22:00:00","2026-12-09","01:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,6.7]
[null,"DB InfraGO AG","2AA67-001","München - Salzburg","<>","Traunstein","Ruhpolding",2026,2026,40,44,"2026-10-02","18:00:00","2026-10-26","03:00:00","23d, 10h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,4.5]
[null,"DB InfraGO AG","2AE76-010","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2026,2026,50,50,"2026-12-12","00:10:00","2026-12-12","02:00:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-30",null,null,1]
[null,"DB InfraGO AG","2AE7A-003","Karlsruhe - München","<>","Stuttgart-Bad Cannstatt","Stuttgart-Untertürkheim",2026,2026,19,20,"2026-05-04","07:00:00","2026-05-12","17:00:00","8d, 10h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,2]
[null,"DB InfraGO AG","2AF93-015","Karlsruhe - München","<>","Stuttgart-Untertürkheim Pbf","Stuttgart Hafen",2026,2026,15,17,"2026-04-11","06:00:00","2026-04-20","04:00:00","8d, 22h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,6.7]
[null,"DB InfraGO AG","2B680-004","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-11","00:00:00","10d, 0h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,2.2999999999999998]
[null,"DB InfraGO AG","2B78B-002","Karlsruhe - München","<>","Kornwestheim Rbf Süd-Ost","Kornwestheim Karlshöhe",2025,2025,51,51,"2025-12-20","09:30:00","2025-12-21","17:00:00","1d, 7h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-31",null,null,3.4]
[null,"DB InfraGO AG","2B8FF-008","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,21,21,"2026-05-19","00:01:00","2026-05-21","04:00:00","2d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-07-31",null,null,3.4]
[null,"DB InfraGO AG","2BEC6-021","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Söllingen (b Karlsruhe)",2026,2026,43,43,"2026-10-21","23:00:00","2026-10-22","01:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-10",null,null,4]
[null,"DB InfraGO AG","2BF59-002","Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2026,2026,39,39,"2026-09-21","04:00:00","2026-09-21","06:00:00","0d, 2h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,1.7]
[null,"DB InfraGO AG","2C03F-004","Frankfurt - Karlsruhe","<>","Karlsruhe Gbf","Karlsruhe-Durlach",2026,2026,50,50,"2026-12-08","22:00:00","2026-12-09","01:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,2.2999999999999998]
[null,"DB InfraGO AG","2C4A0-003","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,49,49,"2026-12-03","23:00:00","2026-12-04","05:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-10",null,null,1.7]
[null,"DB InfraGO AG","2C90A-008","Karlsruhe - Strasbourg","<>","Ottersweier","Ottersweier",2026,2026,27,28,"2026-07-05","22:00:00","2026-07-06","04:00:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-10",null,null,3]
[null,"DB InfraGO AG","2C914-005","Karlsruhe - München","<>","Stuttgart-Untertürkheim","Stuttgart-Bad Cannstatt",2026,2026,13,16,"2026-03-24","21:00:00","2026-04-13","05:00:00","19d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,1.2]
[null,"DB InfraGO AG","2C914-019","Karlsruhe - München","<>","Stuttgart-Untertürkheim","Stuttgart Neckarpark",2026,2026,13,16,"2026-03-24","21:00:00","2026-04-13","05:00:00","19d, 7h","Continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,4]
[null,"DB InfraGO AG","2D74B-008","Karlsruhe - München","<>","Stuttgart-Untertürkheim Pbf","Stuttgart-Zazenhausen Hp",2026,2026,27,28,"2026-07-05","18:00:00","2026-07-06","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","2D85F-005","Karlsruhe - Strasbourg",">","Ottersweier","Önsbach",2026,2026,44,45,"2026-11-01","22:30:00","2026-11-02","01:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,3.4]
[null,"DB InfraGO AG","2F0DA-002","Karlsruhe - Strasbourg","<","Appenweier","Appenweier",2026,2026,26,26,"2026-06-27","22:00:00","2026-06-28","01:00:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-12",null,null,3.4]
[null,"DB InfraGO AG","31D1F-001","Nürnberg - Passau",">","Passau Hbf","Schalding",2026,2026,28,28,"2026-07-07","18:00:00","2026-07-08","06:00:00","0d, 12h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-08-04",null,null,3]
[null,"DB InfraGO AG","31D94-001","Nürnberg - Passau","<>","Plattling","Passau Hbf",2026,2026,28,38,"2026-07-10","21:00:00","2026-09-20","21:00:00","72d, 0h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","31DE3-005","Nürnberg - Passau","<>","Plattling","Plattling",2026,2026,48,48,"2026-11-28","23:00:00","2026-11-29","05:00:00","0d, 6h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","31FEF-002","Frankfurt - Karlsruhe","<>","Aschaffenburg Hbf","Kleinostheim",2026,2026,17,17,"2026-04-25","21:00:00","2026-04-26","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,6.7]
[null,"DB InfraGO AG","320EA-003","Nürnberg - Passau","<>","Girching","Vilshofen (Niederbay)",2026,2026,32,35,"2026-08-09","20:00:00","2026-08-28","05:00:00","18d, 9h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-06",null,null,2.2999999999999998]
[null,"DB InfraGO AG","320EA-009","Nürnberg - Passau","<","Girching","Vilshofen (Niederbay)",2026,2026,35,35,"2026-08-30","09:00:00","2026-08-30","17:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-06",null,null,3]
[null,"DB InfraGO AG","32154-002","Nürnberg - Passau","<","Vilshofen (Niederbay)","Schalding",2026,2026,36,36,"2026-08-31","19:59:00","2026-09-01","02:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-06-10",null,null,1.2]
[null,"DB InfraGO AG","32154-012","Nürnberg - Passau","<","Sandbach (Niederbay)","Schalding",2026,2026,38,38,"2026-09-17","23:00:00","2026-09-20","05:00:00","2d, 6h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-10",null,null,3.4]
[null,"DB InfraGO AG","32328-006","Nürnberg - Passau","<>","Passau Gbf","Schalding",2026,2026,28,30,"2026-07-11","20:00:00","2026-07-21","05:00:00","9d, 9h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,4.5]
[null,"DB InfraGO AG","32328-017","Nürnberg - Passau","<>","Passau Gbf","Passau Gbf",2026,2026,28,28,"2026-07-12","06:00:00","2026-07-12","16:00:00","0d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-10",null,null,1.2]
[null,"DB InfraGO AG","32385-013","Karlsruhe - Strasbourg","<>","Ottersweier","Appenweier Nord",2026,2026,40,42,"2026-10-03","00:00:00","2026-10-12","04:00:00","9d, 4h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3"]
[null,"DB InfraGO AG","323F7-002","Karlsruhe - München","<","km 3,6/6,8 (MOL)","Olching",2026,2026,33,35,"2026-08-12","21:00:00","2026-08-25","05:00:00","12d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-06-30",null,null,7]
[null,"DB InfraGO AG","32765-006","Karlsruhe - Strasbourg","<>","Ottersweier","Ottersweier",2026,2026,27,27,"2026-07-04","05:00:00","2026-07-05","21:00:00","1d, 16h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","32765-013","Karlsruhe - Strasbourg","<>","Baden-Baden","Ottersweier",2026,2026,28,28,"2026-07-11","00:00:00","2026-07-11","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","32765-019","Karlsruhe - Strasbourg","<>","Baden-Baden","Ottersweier",2026,2026,28,28,"2026-07-12","00:00:00","2026-07-12","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998]
[null,"DB InfraGO AG","32A52-010","Karlsruhe - München","<>","Günzburg","Unterfahlheim",2026,2026,31,34,"2026-07-28","23:30:00","2026-08-17","05:00:00","19d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,7"]
[null,"DB InfraGO AG","32D3A-005","Darmstadt - Nürnberg","<>","Lohr Bahnhof","Lohr Bahnhof",2026,2026,48,48,"2026-11-24","05:00:00","2026-11-28","05:00:00","4d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","32DD8-003","Nürnberg - Passau","<>","Regensburg Bbf","Beratzhausen",2026,2026,36,36,"2026-09-02","03:00:00","2026-09-02","05:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","32DD8-009","Nürnberg - Passau","<>","Undorf","Parsberg",2026,2026,37,37,"2026-09-07","02:30:00","2026-09-07","04:30:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,4.5]
[null,"DB InfraGO AG","32EB4-001","Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2026,2026,41,42,"2026-10-05","08:00:00","2026-10-16","17:00:00","11d, 9h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-06-04",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","32EB4-027","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker Kurve",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","32FBE-007","Nürnberg - Plzen","<>","Marktredwitz","Marktredwitz",2026,2026,19,20,"2026-05-10","22:00:00","2026-05-11","06:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","32FD1-042","München - Salzburg","<","München Ost Riedenburger Straße","München Ost Pbf",2026,2026,43,43,"2026-10-24","21:00:00","2026-10-25","05:00:00","0d, 9h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,4.5]
[null,"DB InfraGO AG","331D9-002","Nürnberg - Passau","<>","Feucht","Altdorf (b Nürnberg)",2026,2026,38,38,"2026-09-19","23:30:00","2026-09-20","04:30:00","0d, 5h","Continuous","Oberleitungsvollinspektion","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2.2999999999999998]
[null,"DB InfraGO AG","333D2-009","Karlsruhe - München","<","Bietigheim-Bissingen","Ludwigsburg",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","16:00:00","0d, 8h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-18",null,null,3]
[null,"DB InfraGO AG","333D2-030","Karlsruhe - München","<>","Bietigheim-Bissingen","Ludwigsburg",2026,2026,36,36,"2026-09-04","12:00:00","2026-09-04","16:00:00","0d, 4h","Continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","33557-006","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,34,34,"2026-08-22","08:00:00","2026-08-22","16:00:00","0d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","33557-012","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,35,35,"2026-08-25","08:00:00","2026-08-25","16:00:00","0d, 8h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","336D9-004","Frankfurt - Karlsruhe","<","Pforzheim Hbf","Wilferdingen-Singen",2026,2026,18,19,"2026-04-29","23:00:00","2026-05-04","05:00:00","4d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"5,6,7"]
[null,"DB InfraGO AG","337F3-002","Karlsruhe - Strasbourg","<>","Mühlacker","Mühlacker",2026,2026,13,13,"2026-03-25","23:30:00","2026-03-26","04:30:00","0d, 5h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-23",null,null,3.4]
[null,"DB InfraGO AG","338AB-006","Karlsruhe - München","<","Beimerstetten","Westerstetten",2026,2026,46,46,"2026-11-14","01:30:00","2026-11-14","04:59:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"3,4,5"]
[null,"DB InfraGO AG","33B53-007","München - Salzburg",">","München Ost Pbf","München Leuchtenbergring",2026,2026,18,18,"2026-04-27","21:40:00","2026-05-01","04:20:00","3d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-12-12",null,null,1.2]
[null,"DB InfraGO AG","33C40-001","Karlsruhe - Strasbourg","<","Windschläg","Achern",2026,2026,2,3,"2026-01-11","23:00:00","2026-01-15","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","33C70-005","Frankfurt - Karlsruhe","<>","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,38,39,"2026-09-20","23:00:00","2026-09-25","05:00:00","4d, 6h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-03-20",null,null,2]
[null,"DB InfraGO AG","33E25-014","München - Salzburg","<","München Ost Pbf","München Isartor",2026,2026,21,21,"2026-05-18","21:40:00","2026-05-19","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2025-08-04",null,null,6]
[null,"DB InfraGO AG","33E25-022","München - Salzburg","<>","München Ost Pbf","München-Steinhausen",2026,2026,21,21,"2026-05-18","21:40:00","2026-05-19","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,6.7]
[null,"DB InfraGO AG","33F2E-010","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,16,16,"2026-04-13","00:00:00","2026-04-13","05:00:00","0d, 5h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,5]
[null,"DB InfraGO AG","33F2E-029","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,29,30,"2026-07-19","21:00:00","2026-07-20","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,"1,6,7"]
[null,"DB InfraGO AG","33F2E-039","Darmstadt - Nürnberg","<>","Nürnberg-Eibach","Nürnberg Hbf",2026,2026,39,39,"2026-09-21","23:00:00","2026-09-22","02:00:00","0d, 3h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","33F96-002","Frankfurt - Karlsruhe","<>","Mühlacker","Mühlacker",2026,2026,20,21,"2026-05-17","22:30:00","2026-05-18","01:30:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","3403B-011","Karlsruhe - München","<","Wendlingen (Neckar)","Plochingen",2026,2026,24,24,"2026-06-10","23:20:00","2026-06-11","03:45:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-21",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3404F-021","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,8,8,"2026-02-17","21:20:00","2026-02-17","22:35:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","343FC-001","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Blankenloch",2026,2026,18,19,"2026-05-03","23:00:00","2026-05-05","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-28",null,null,5.6]
[null,"DB InfraGO AG","343FC-011","Karlsruhe - Strasbourg","<>","Blankenloch","Karlsruhe-Hagsfeld",2026,2026,19,19,"2026-05-05","23:00:00","2026-05-07","05:00:00","1d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-21",null,null,1.7]
[null,"DB InfraGO AG","34450-003","Frankfurt - Karlsruhe","<","Schwetzingen","Mannheim Ziehbrunnen",2026,2026,26,27,"2026-06-27","23:00:00","2026-06-29","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-03-21",null,null,"2,3,4"]
[null,"DB InfraGO AG","34464-003","Karlsruhe - Strasbourg","<","Appenweier Nord","Ottersweier",2026,2026,41,41,"2026-10-05","22:00:00","2026-10-09","05:00:00","3d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1.2]
[null,"DB InfraGO AG","344DE-004","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,33,33,"2026-08-10","22:30:00","2026-08-11","01:35:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-28",null,null,6.7]
[null,"DB InfraGO AG","344DE-030","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,34,34,"2026-08-17","22:30:00","2026-08-18","01:20:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","344E8-006","Karlsruhe - München","<>","Mering","Augsburg Hbf",2026,2026,48,48,"2026-11-23","22:00:00","2026-11-24","04:00:00","0d, 6h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","344E8-018","Karlsruhe - München","<>","Augsburg Haunstetterstraße","Mering",2026,2026,48,48,"2026-11-27","01:00:00","2026-11-27","04:00:00","0d, 3h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","34685-008","Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2026,2026,23,23,"2026-06-06","21:00:00","2026-06-07","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,1.7]
[null,"DB InfraGO AG","34685-023","Darmstadt - Nürnberg",">","Fürth (Bay) Hbf","Fürth-Burgfarrnbach",2026,2026,22,22,"2026-05-31","01:00:00","2026-05-31","05:00:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-05-05",null,null,1]
[null,"DB InfraGO AG","34722-011","Darmstadt - Nürnberg","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2026,2026,41,41,"2026-10-09","00:00:00","2026-10-11","10:00:00","2d, 10h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,"2,3,4"]
[null,"DB InfraGO AG","34884-018","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,15,15,"2026-04-10","22:00:00","2026-04-11","04:30:00","0d, 6h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-14",null,null,1]
[null,"DB InfraGO AG","34884-028","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,16,16,"2026-04-13","22:00:00","2026-04-14","00:50:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-14",null,null,3]
[null,"DB InfraGO AG","34884-034","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,16,16,"2026-04-14","22:00:00","2026-04-15","03:30:00","0d, 5h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-14",null,null,5]
[null,"DB InfraGO AG","34884-044","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,16,16,"2026-04-18","22:00:00","2026-04-19","00:50:00","0d, 2h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-05",null,null,"2,3,4"]
[null,"DB InfraGO AG","3488A-010","Karlsruhe - München","<>","Tamm (Württ)","Bietigheim-Bissingen",2026,2026,35,35,"2026-08-24","22:30:00","2026-08-25","04:30:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3488A-016","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,35,"2026-08-25","01:20:00","2026-08-25","04:30:00","0d, 3h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3488A-027","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,35,"2026-08-26","22:30:00","2026-08-27","01:20:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","34962-005","Karlsruhe - Strasbourg","<>","Rastatt-Süd","Baden-Baden",2026,2026,26,27,"2026-06-28","23:00:00","2026-06-30","05:00:00","1d, 6h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-25",null,null,6]
[null,"DB InfraGO AG","34962-013","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,27,27,"2026-06-30","23:00:00","2026-07-02","05:00:00","1d, 6h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-13",null,null,4.5]
[null,"DB InfraGO AG","349D0-012","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt-Süd",2026,2026,13,13,"2026-03-26","23:00:00","2026-03-27","05:00:00","0d, 6h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-12",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","34ADB-018","München - Salzburg",">","München-Pasing","Planegg Üst",2026,2026,47,48,"2026-11-20","22:40:00","2026-11-23","04:40:00","2d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-08-12",null,null,3]
[null,"DB InfraGO AG","34AEC-023","Karlsruhe - München","<>","München-Pasing","Olching",2026,2026,45,46,"2026-11-08","22:40:00","2026-11-09","04:40:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,3]
[null,"DB InfraGO AG","34B0F-004","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,24,24,"2026-06-08","01:00:00","2026-06-08","03:30:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","34B0F-022","Karlsruhe - München",">","Esslingen (Neckar)","Plochingen",2026,2026,25,25,"2026-06-15","02:00:00","2026-06-15","04:00:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-04",null,null,7]
[null,"DB InfraGO AG","34B0F-032","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,25,25,"2026-06-16","23:00:00","2026-06-17","02:00:00","0d, 3h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-23",null,null,5]
[null,"DB InfraGO AG","34B0F-038","Karlsruhe - München","<>","Plochingen","Plochingen",2026,2026,25,25,"2026-06-18","00:30:00","2026-06-18","02:00:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-31",null,null,2.2999999999999998]
[null,"DB InfraGO AG","34C58-003","Darmstadt - Nürnberg","<","Aschaffenburg-Goldbach","Laufach",2026,2026,26,26,"2026-06-23","21:00:00","2026-06-24","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,5]
[null,"DB InfraGO AG","34C9E-005","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-25","04:30:00","3d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-16",null,null,7]
[null,"DB InfraGO AG","34C9E-012","Karlsruhe - München",">","Freiberg (Neckar)","Ludwigsburg",2026,2026,34,34,"2026-08-22","01:30:00","2026-08-22","04:30:00","0d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-17",null,null,4.5]
[null,"DB InfraGO AG","34C9E-026","Karlsruhe - München","<","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-25","04:30:00","3d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2025-04-08",null,null,2.2999999999999998]
[null,"DB InfraGO AG","34CB7-018","Karlsruhe - Strasbourg","<>","Baden-Baden","Baden-Baden",2026,2026,43,43,"2026-10-19","00:00:00","2026-10-19","01:00:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,4.5]
[null,"DB InfraGO AG","34CB7-024","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt-Süd",2026,2026,43,43,"2026-10-19","03:30:00","2026-10-19","05:00:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-08",null,null,5.6]
[null,"DB InfraGO AG","34D04-010","Karlsruhe - Strasbourg","<>","Oftersheim","Oftersheim",2026,2026,17,17,"2026-04-23","22:00:00","2026-04-24","04:00:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-08",null,null,3.4]
[null,"DB InfraGO AG","34D3F-006","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt",2026,2026,46,46,"2026-11-09","22:00:00","2026-11-14","06:00:00","4d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","34D88-029","Frankfurt - Karlsruhe","<>","Karlsruhe Gbf","Blankenloch",2026,2026,45,46,"2026-11-07","16:00:00","2026-11-09","10:00:00","1d, 18h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","34EEB-013","München - Salzburg","<>","München Ost Pbf","München-Steinhausen",2026,2026,24,24,"2026-06-08","21:40:00","2026-06-12","04:20:00","3d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","34F88-002","Karlsruhe - München","<>","München-Pasing","Gauting",2026,2026,23,25,"2026-06-01","22:40:00","2026-06-15","04:40:00","13d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","350E2-005","München - Salzburg","<>","München Ost Pbf","München Leuchtenbergring",2026,2026,30,30,"2026-07-20","21:40:00","2026-07-21","04:20:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","350E2-013","München - Salzburg","<>","München Ost Pbf","München-Steinhausen",2026,2026,30,30,"2026-07-20","21:40:00","2026-07-21","04:20:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"1,2,3,5,6,7"]
[null,"DB InfraGO AG","3510B-020","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,26,26,"2026-06-24","00:45:00","2026-06-24","03:00:00","0d, 2h","Continuous","Oberleitungsvollinspektion",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-02-02",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","351B9-007","München - Salzburg",">","München Ost Pbf","München Leuchtenbergring",2026,2026,36,36,"2026-08-31","21:40:00","2026-09-01","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-11-22",null,null,1.7]
[null,"DB InfraGO AG","351B9-014","München - Salzburg","<","München Ost Pbf","München Isartor",2026,2026,33,33,"2026-08-10","21:40:00","2026-08-11","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-06-13",null,null,"1,6,7"]
[null,"DB InfraGO AG","35335-001","München - Salzburg",">","München Isartor","München Ost Pbf",2026,2026,42,42,"2026-10-12","21:40:00","2026-10-13","04:20:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-10-08",null,null,3.4]
[null,"DB InfraGO AG","35356-005","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,26,26,"2026-06-22","22:00:00","2026-06-23","00:30:00","0d, 2h","Continuous","Oberleitungsvollinspektion",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,1]
[null,"DB InfraGO AG","35408-002","München - Salzburg","<>","München-Pasing","München Hbf tief",2026,2026,42,43,"2026-10-16","22:40:00","2026-10-19","04:40:00","2d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,7]
[null,"DB InfraGO AG","354CE-005","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt",2026,2026,11,11,"2026-03-15","01:00:00","2026-03-15","04:30:00","0d, 3h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,5.6]
[null,"DB InfraGO AG","355DE-010","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2026,2026,26,26,"2026-06-26","03:30:00","2026-06-26","04:30:00","0d, 1h","Continuous","Oberleitungsvollinspektion",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,6]
[null,"DB InfraGO AG","355FB-006","Karlsruhe - München","<>","Geislingen (Steige)","Geislingen (Steige)",2026,2026,15,15,"2026-04-06","21:45:00","2026-04-06","22:45:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3560D-006","Karlsruhe - München",">","Amstetten (Württ)","Westerstetten",2026,2026,15,15,"2026-04-07","22:45:00","2026-04-08","00:05:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-04",null,null,2]
[null,"DB InfraGO AG","357B2-002","Nürnberg - Passau","<>","Nürnberg-Langwasser","Nürnberg-Dutzendteich",2026,2026,44,44,"2026-10-30","00:30:00","2026-10-30","01:30:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3.4]
[null,"DB InfraGO AG","3597A-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-19","02:00:00","0d, 3h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2025-08-04",null,null,3]
[null,"DB InfraGO AG","359C8-001","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,35,36,"2026-08-30","22:30:00","2026-08-31","04:30:00","0d, 6h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-11",null,null,1.7]
[null,"DB InfraGO AG","359C8-014","Karlsruhe - München","<>","Ludwigsburg","Ludwigsburg",2026,2026,36,36,"2026-09-02","22:30:00","2026-09-03","01:20:00","0d, 2h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-23",null,null,2.2999999999999998]
[null,"DB InfraGO AG","359C8-031","Karlsruhe - München","<","Ludwigsburg","Kornwestheim Pbf",2026,2026,36,36,"2026-09-01","01:30:00","2026-09-01","04:30:00","0d, 3h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-16",null,null,5.7]
[null,"DB InfraGO AG","359E8-006","München - Salzburg","<>","München-Pasing","München-Westkreuz",2026,2026,23,23,"2026-06-02","00:40:00","2026-06-02","04:40:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,"5,6,7"]
[null,"DB InfraGO AG","35B71-002","Karlsruhe - München","<","Gauting","München-Pasing",2026,2026,41,42,"2026-10-09","22:40:00","2026-10-12","04:40:00","2d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,"1,2,3"]
[null,"DB InfraGO AG","35B71-013","München - Salzburg","<>","München-Pasing","München-Westkreuz",2026,2026,43,43,"2026-10-24","00:40:00","2026-10-24","04:40:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-09",null,null,4.5]
[null,"DB InfraGO AG","35B71-028","München - Salzburg","<>","München-Pasing","Gauting",2026,2026,48,48,"2026-11-23","00:40:00","2026-11-23","04:40:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-13",null,null,4.5]
[null,"DB InfraGO AG","35BD6-001","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,22,22,"2026-05-26","23:00:00","2026-05-27","05:00:00","0d, 6h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-30",null,null,4.5]
[null,"DB InfraGO AG","35C81-001","Frankfurt - Karlsruhe","<","Langes Feld","Vaihingen (Enz)",2026,2026,32,32,"2026-08-04","23:00:00","2026-08-05","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-08-04",null,null,1]
[null,"DB InfraGO AG","35C9C-006","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Hbf",2026,2026,29,29,"2026-07-15","02:45:00","2026-07-15","04:30:00","0d, 1h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,7]
[null,"DB InfraGO AG","35CFE-001","Karlsruhe - Strasbourg",">","Baden-Baden","Ottersweier",2026,2026,38,39,"2026-09-20","23:00:00","2026-09-21","05:00:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-23",null,null,4.5]
[null,"DB InfraGO AG","35D48-001","Karlsruhe - Strasbourg","<>","Achern","Achern",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-22","05:00:00","3d, 6h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-21",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","35D5E-002","Frankfurt - Karlsruhe",">","Mettertal","Vaihingen (Enz)",2026,2026,7,7,"2026-02-11","23:00:00","2026-02-12","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-08-07",null,null,2.2999999999999998]
[null,"DB InfraGO AG","35D88-011","München - Salzburg","<","München-Steinhausen","München Ost Pbf",2026,2026,15,16,"2026-04-12","21:50:00","2026-04-13","04:50:00","0d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","35D8E-001","Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,19,19,"2026-05-04","23:00:00","2026-05-05","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-06-07",null,null,4]
[null,"DB InfraGO AG","35D8E-011","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,19,19,"2026-05-07","02:00:00","2026-05-07","05:00:00","0d, 3h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-11",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","35DE9-007","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,22,22,"2026-05-25","23:00:00","2026-05-26","05:00:00","0d, 6h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","35DF9-004","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,31,31,"2026-07-27","23:00:00","2026-07-28","05:00:00","0d, 6h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","35DFB-001","Karlsruhe - Strasbourg",">","Rastatt","Baden-Baden",2026,2026,16,17,"2026-04-19","23:00:00","2026-04-20","05:00:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-07-08",null,null,5]
[null,"DB InfraGO AG","35E3C-010","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,34,34,"2026-08-19","02:00:00","2026-08-19","05:00:00","0d, 3h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-06-03",null,null,1]
[null,"DB InfraGO AG","35E41-008","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-20","23:00:00","2026-10-21","02:00:00","0d, 3h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-06-03",null,null,5]
[null,"DB InfraGO AG","35EB4-008","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Mettertal",2026,2026,16,16,"2026-04-16","02:30:00","2026-04-16","04:00:00","0d, 1h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-03",null,null,5]
[null,"DB InfraGO AG","35EED-001","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Mettertal",2026,2026,46,46,"2026-11-09","23:00:00","2026-11-10","05:30:00","0d, 6h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998]
[null,"DB InfraGO AG","35F16-004","Karlsruhe - München","<>","Ulm Hbf Bft Pbf","Neu-Ulm",2026,2026,48,48,"2026-11-27","02:00:00","2026-11-27","05:00:00","0d, 3h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","35F16-014","Karlsruhe - München","<>","Neu-Ulm","Gerlenhofen",2026,2026,48,48,"2026-11-27","02:00:00","2026-11-27","04:00:00","0d, 2h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","35F89-001","Frankfurt - Karlsruhe","<","Vaihingen (Enz)","Freudenstein",2026,2026,32,33,"2026-08-09","23:00:00","2026-08-10","05:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,null,null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","363B9-009","Frankfurt - Karlsruhe","<","Hockenheim","Brühler Weg",2026,2026,22,22,"2026-05-27","01:30:00","2026-05-27","03:30:00","0d, 2h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-03",null,null,6]
[null,"DB InfraGO AG","363B9-015","Frankfurt - Karlsruhe","<>","Hockenheim","Hockenheim",2026,2026,22,22,"2026-05-27","22:00:00","2026-05-27","23:50:00","0d, 1h","Continuous","Maintenance",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-03",null,null,2]
[null,"DB InfraGO AG","363B9-025","Frankfurt - Karlsruhe","<>","Hockenheim","Oberhausen",2026,2026,22,22,"2026-05-28","01:30:00","2026-05-28","03:00:00","0d, 1h","Continuous","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.7]
[null,"DB InfraGO AG","363EF-001","Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,29,29,"2026-07-13","23:00:00","2026-07-14","05:00:00","0d, 6h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-08-04",null,null,5]
[null,"DB InfraGO AG","363EF-008","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Glems",2026,2026,28,29,"2026-07-12","23:00:00","2026-07-13","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","36477-001","Karlsruhe - Strasbourg","<>","Rastatt","Rastatt",2026,2026,15,15,"2026-04-08","23:00:00","2026-04-09","00:00:00","0d, 1h","Continuous","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,4]
[null,"DB InfraGO AG","364BA-007","Frankfurt - Karlsruhe","<","Vaihingen (Enz)","Mettertal",2026,2026,29,29,"2026-07-14","02:30:00","2026-07-14","05:30:00","0d, 3h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","364BA-017","Frankfurt - Karlsruhe","<","Langes Feld","Vaihingen (Enz)",2026,2026,29,29,"2026-07-16","01:00:00","2026-07-16","02:30:00","0d, 1h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-18",null,null,1]
[null,"DB InfraGO AG","364CD-015","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,38,38,"2026-09-16","23:00:00","2026-09-17","01:00:00","0d, 2h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-07-22",null,null,"1,6,7"]
[null,"DB InfraGO AG","36517-013","Frankfurt - Karlsruhe","<","Glems","Vaihingen (Enz)",2026,2026,10,10,"2026-03-05","03:00:00","2026-03-05","05:30:00","0d, 2h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2025-07-22",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","365AC-004","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,33,33,"2026-08-12","23:00:00","2026-08-14","05:00:00","1d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","367B9-001","Karlsruhe - München",">","Sachsenheim","Vaihingen (Enz)",2026,2026,2,3,"2026-01-11","23:00:00","2026-01-13","05:00:00","1d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","36836-015","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,31,31,"2026-07-28","23:00:00","2026-07-29","05:00:00","0d, 6h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","368FC-019","München - Salzburg","<>","München-Steinhausen","München Ost Pbf",2026,2026,45,45,"2026-11-02","21:40:00","2026-11-03","04:20:00","0d, 6h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-20",null,null,1.7]
[null,"DB InfraGO AG","369D6-004","Nürnberg - Passau","<","Regensburg Bbf","Regensburg Hbf",2026,2026,28,28,"2026-07-09","20:30:00","2026-07-09","22:30:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","36C5D-001","Darmstadt - Nürnberg","<>","Waigolshausen","Mühlhausen (Wern)",2027,2027,31,31,"2027-08-08","07:30:00","2027-08-08","15:30:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,5]
[null,"DB InfraGO AG","36D96-010","München - Salzburg","<>","München Ost Pbf","München Ost Pbf",2026,2026,26,26,"2026-06-24","22:20:00","2026-06-27","04:20:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","36E1A-002","Regensburg - Plzen","<>","Regensburg-Wutzlhofen","Schwandorf",2026,2026,38,38,"2026-09-20","01:30:00","2026-09-20","05:00:00","0d, 3h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,1.7]
[null,"DB InfraGO AG","36E6C-007","München - Salzburg","<","München-Riem West","München Ost Pbf",2026,2026,48,49,"2026-11-27","22:20:00","2026-11-30","04:20:00","2d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2025-08-04",null,null,6.7]
[null,"DB InfraGO AG","3703F-007","Darmstadt - Nürnberg","<","Eggolsheim Süd","Forchheim (Oberfr)",2027,2027,24,24,"2027-06-16","23:00:00","2027-06-18","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2025-08-04",null,null,5.6]
[null,"DB InfraGO AG","38BA9-003","Darmstadt - Nürnberg","<>","Gemünden (Main)","Gemünden (Main)",2027,2027,36,49,"2027-09-08","21:00:00","2027-12-11","23:59:00","94d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,6.7]
[null,"DB InfraGO AG","38BAA-006","München - Salzburg","<>","Traunstein","Hörpolding",2027,2027,5,6,"2027-02-05","21:00:00","2027-02-14","04:30:00","8d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,2]
[null,"DB InfraGO AG","38C54-004","Karlsruhe - München","<>","Strullendorf DB-Grenze","Strullendorf",2027,2027,20,20,"2027-05-17","21:00:00","2027-05-21","05:00:00","3d, 8h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,1]
[null,"DB InfraGO AG","38C54-014","Darmstadt - Nürnberg","<>","Fürth (Bay) Hbf","Bamberg",2027,2027,37,37,"2027-09-18","20:00:00","2027-09-19","08:00:00","0d, 12h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-02",null,null,1.7]
[null,"DB InfraGO AG","38C54-020","Darmstadt - Nürnberg","<>","Fürth-Unterfarrnbach Abzw","Fürth (Bay) Hbf",2027,2027,37,37,"2027-09-18","20:00:00","2027-09-19","08:00:00","0d, 12h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-02",null,null,1]
[null,"DB InfraGO AG","38E98-014","Regensburg - Plzen","<>","Furth im Wald","Furth im Wald",2027,2027,23,24,"2027-06-08","00:01:00","2027-06-18","23:59:00","10d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-02",null,null,3]
[null,"DB InfraGO AG","38F2F-003","Nürnberg - Plzen","<>","Furth im Wald","Furth im Wald",2027,2027,26,27,"2027-07-03","00:01:00","2027-07-09","23:59:00","6d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-18",null,null,5]
[null,"DB InfraGO AG","38F2F-009","Nürnberg - Plzen","<>","Furth im Wald","Furth im Wald",2027,2027,28,29,"2027-07-14","00:01:00","2027-07-24","23:59:00","10d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-19",null,null,1.2]
[null,"DB InfraGO AG","38F87-001","Darmstadt - Nürnberg",">","Erlangen","Eggolsheim Süd",2027,2027,26,27,"2027-07-04","21:00:00","2027-07-06","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"Y",null,"2025-05-21",null,null,4.5]
[null,"DB InfraGO AG","390A7-011","Darmstadt - Nürnberg","<>","Schweinfurt Hbf","Schweinfurt Hbf",2027,2027,21,21,"2027-05-25","16:00:00","2027-05-26","04:00:00","0d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998]
[null,"DB InfraGO AG","3911C-003","Darmstadt - Nürnberg","<","Ebelsbach-Eltmann","Bamberg",2027,2027,9,10,"2027-03-06","23:30:00","2027-03-08","05:00:00","1d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-08-04",null,null,4]
[null,"DB InfraGO AG","39157-009","Darmstadt - Nürnberg",">","Nantenbach","Rohrbach",2027,2027,18,19,"2027-05-04","21:00:00","2027-05-12","05:00:00","7d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-08-04",null,null,2]
[null,"DB InfraGO AG","391C1-006","Karlsruhe - München","<>","Dinkelscherben","Dinkelscherben",2027,2027,8,11,"2027-02-24","02:00:00","2027-03-19","21:00:00","23d, 19h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,4]
[null,"DB InfraGO AG","3924B-006","Regensburg - Plzen","<>","Regensburg Walhallastraße","Regensburg Walhallastraße",2027,2027,14,16,"2027-04-09","06:00:00","2027-04-19","06:00:00","10d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-26",null,null,4.5]
[null,"DB InfraGO AG","3924B-012","Regensburg - Plzen","<>","Regensburg Walhallastraße","Regensburg Walhallastraße",2027,2027,47,48,"2027-11-26","22:00:00","2027-12-02","06:00:00","5d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","39352-035","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2027,2027,21,28,"2027-05-30","21:00:00","2027-07-16","05:00:00","46d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-08",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","39498-007","Darmstadt - Nürnberg",">","Nürnberg-Reichelsdorf","Nürnberg Hbf",2027,2027,13,14,"2027-04-02","21:00:00","2027-04-05","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2025-08-04",null,null,1.2]
[null,"DB InfraGO AG","39498-013","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2027,2027,18,47,"2027-05-03","03:00:00","2027-11-23","04:30:00","204d, 2h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-26",null,null,7]
[null,"DB InfraGO AG","3954C-010","Karlsruhe - München","<>","Dinkelscherben","Burgau (Schwab)",2027,2027,17,18,"2027-05-02","05:00:00","2027-05-03","05:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,4.5]
[null,"DB InfraGO AG","395D3-007","Darmstadt - Nürnberg",">","Nürnberg-Reichelsdorf","Nürnberg Hbf",2027,2027,47,48,"2027-11-27","23:00:00","2027-11-29","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2025-01-15",null,null,7]
[null,"DB InfraGO AG","396FE-001","München - Salzburg","<>","Grafing Bahnhof","Ebersberg (Oberbay)",2027,2027,45,46,"2027-11-08","21:00:00","2027-11-15","05:00:00","6d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-13",null,null,4]
[null,"DB InfraGO AG","3977F-010","Darmstadt - Nürnberg",">","Darmstadt Hbf","Darmstadt Nord",2027,2027,25,25,"2027-06-24","21:00:00","2027-06-25","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-17",null,null,1.2]
[null,"DB InfraGO AG","397ED-011","Nürnberg - Passau","<>","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2027,2027,15,16,"2027-04-18","21:00:00","2027-04-19","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","3986A-007","Frankfurt - Karlsruhe","<>","Darmstadt Hbf","Darmstadt Gbf",2027,2027,7,9,"2027-02-19","21:00:00","2027-03-05","21:00:00","14d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3998C-002","Frankfurt - Karlsruhe","<>","Bensheim","Bensheim",2026,2027,50,5,"2026-12-13","00:00:00","2027-02-05","21:00:00","54d, 21h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-26",null,null,3.4]
[null,"DB InfraGO AG","39BE3-002","Frankfurt - Karlsruhe","<>","Darmstadt Hbf","Bickenbach (Bergstr)",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-17",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","39CC7-002","Darmstadt - Nürnberg","<","Darmstadt-Kranichstein","Darmstadt Nord",2025,2025,51,51,"2025-12-16","00:50:00","2025-12-16","05:00:00","0d, 4h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2025-03-17",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","39CCF-003","Darmstadt - Nürnberg","<>","Darmstadt-Kranichstein","Babenhausen (Hess)",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-17",null,null,"2,3,4,5,6,7"]
[null,"DB InfraGO AG","3A3AA-003","Nürnberg - Passau",">","Nürnberg-Dürrenhof","Feucht",2027,2027,30,30,"2027-07-28","00:30:00","2027-07-29","04:30:00","1d, 4h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,25",null,null,null,"N",null,"2024-07-12",null,null,1.7]
[null,"DB InfraGO AG","3A3AA-015","Nürnberg - Passau","<>","Nürnberg-Dutzendteich","Nürnberg Hbf",2027,2027,30,37,"2027-07-31","00:00:00","2027-09-13","05:00:00","44d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-04-17",null,null,1.2]
[null,"DB InfraGO AG","3A3FB-003","Karlsruhe - München","<>","Augsburg-Hochzoll Abzweig","Mering Üst",2027,2027,20,27,"2027-05-21","21:00:00","2027-07-09","06:00:00","48d, 9h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-17",null,null,2.2999999999999998]
[null,"DB InfraGO AG","3A5C7-004","Nürnberg - Plzen","<>","Nürnberg-Dürrenhof","Nürnberg Hbf",2027,2027,37,37,"2027-09-13","00:30:00","2027-09-16","04:30:00","3d, 4h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-09-23",null,null,"3,4,5,6"]
[null,"DB InfraGO AG","3A60A-003","Karlsruhe - München","<>","Gessertshausen","Gessertshausen",2027,2027,23,49,"2027-06-11","01:00:00","2027-12-11","04:00:00","183d, 4h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3"]
[null,"DB InfraGO AG","3A60A-009","Karlsruhe - München","<>","Gessertshausen","Gessertshausen",2027,2027,34,35,"2027-08-28","21:00:00","2027-08-30","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-18",null,null,"1,2,3"]
[null,"DB InfraGO AG","3A7E3-008","Frankfurt - Karlsruhe","<","Darmstadt Hbf","Darmstadt-Arheilgen",2027,2027,19,20,"2027-05-16","21:00:00","2027-05-19","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3"]
[null,"DB InfraGO AG","3A7E3-016","Frankfurt - Karlsruhe","<>","Darmstadt Hbf","Darmstadt Hbf",2027,2027,23,23,"2027-06-07","21:00:00","2027-06-10","05:00:00","2d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-27",null,null,1.2]
[null,"DB InfraGO AG","3A83F-008","Nürnberg - Plzen","<>","Nürnberg-Dutzendteich","Nürnberg-Mögeldorf",2027,2027,35,35,"2027-09-01","23:00:00","2027-09-03","05:00:00","1d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3A96E-003","Frankfurt - Karlsruhe","<>","Darmstadt Hbf","Darmstadt Hbf",2027,2027,26,27,"2027-06-28","08:00:00","2027-07-05","05:00:00","6d, 21h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,2.2999999999999998]
[null,"DB InfraGO AG","3A9AE-006","Nürnberg - Passau","<>","Straßkirchen","Straubing",2027,2027,23,24,"2027-06-13","21:00:00","2027-06-16","05:00:00","2d, 8h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","3A9E8-007","Karlsruhe - München","<>","Mering Üst","Augsburg-Hochzoll Abzweig",2027,2027,7,7,"2027-02-15","22:00:00","2027-02-19","05:00:00","3d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-27",null,null,1.7]
[null,"DB InfraGO AG","3AA84-010","Karlsruhe - München","<>","Augsburg-Hochzoll Abzweig","Mering Üst",2027,2027,16,16,"2027-04-19","22:00:00","2027-04-23","05:00:00","3d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-09-27",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3AABF-005","Nürnberg - Passau","<","Sandbach (Niederbay)","Sandbach (Niederbay)",2027,2027,24,24,"2027-06-14","21:00:00","2027-06-15","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3AABF-020","Nürnberg - Passau","<","Schalding","Passau Gbf",2027,2027,25,25,"2027-06-24","21:00:00","2027-06-25","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-09-27",null,null,7]
[null,"DB InfraGO AG","3AC71-001","Nürnberg - Passau",">","Plattling","Straßkirchen",2027,2027,24,24,"2027-06-16","21:00:00","2027-06-19","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-07-25",null,null,1.3]
[null,"DB InfraGO AG","3AC71-013","Nürnberg - Passau","<>","Plattling","Straßkirchen",2027,2027,25,26,"2027-06-26","20:00:00","2027-06-28","02:00:00","1d, 6h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-11",null,null,7]
[null,"DB InfraGO AG","3AC9A-008","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2027,2027,12,14,"2027-03-26","06:00:00","2027-04-06","06:00:00","10d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-18",null,null,2.2999999999999998]
[null,"DB InfraGO AG","3ACE5-004","Karlsruhe - München","<","Olching","München-Lochhausen",2027,2027,25,25,"2027-06-21","22:00:00","2027-06-25","05:00:00","3d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-20",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3AD76-002","München - Salzburg","<","Raubling","Rosenheim",2027,2027,12,12,"2027-03-22","23:00:00","2027-03-25","05:00:00","2d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-30",null,null,"4,5,6"]
[null,"DB InfraGO AG","3ADFE-002","Darmstadt - Nürnberg","<>","Darmstadt Gbf","Darmstadt Gbf",2027,2027,27,27,"2027-07-08","05:00:00","2027-07-09","21:00:00","1d, 16h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,3.4]
[null,"DB InfraGO AG","3AEC5-016","Nürnberg - Passau","<>","Nürnberg Reichswald","Nürnberg Reichswald",2027,2027,16,17,"2027-04-25","02:00:00","2027-04-26","02:00:00","1d, 0h","Continuous","Switch",null,null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-11",null,null,"5,6,7"]
[null,"DB InfraGO AG","3AF05-002","Karlsruhe - München","<>","Maisach Abzw","Olching",2027,2027,27,34,"2027-07-10","22:00:00","2027-08-23","05:00:00","43d, 7h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-02-14",null,null,1.7]
[null,"DB InfraGO AG","3AF05-022","Karlsruhe - München","<>","Maisach Abzw","Olching",2027,2027,26,40,"2027-07-04","22:00:00","2027-10-06","05:00:00","93d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-31",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3B048-030","München - Salzburg","<>","Freilassing","Freilassing",2027,2027,16,19,"2027-04-23","22:00:00","2027-05-10","05:00:00","16d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","3B048-042","München - Salzburg","<>","Freilassing","Freilassing",2027,2027,17,18,"2027-04-30","22:00:00","2027-05-03","05:00:00","2d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"5,6,7"]
[null,"DB InfraGO AG","3B10B-002","Frankfurt - Karlsruhe","<>","Darmstadt Hbf","Darmstadt Hbf",2027,2027,24,24,"2027-06-14","06:00:00","2027-06-15","05:00:00","0d, 23h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-23",null,null,"1,2,3,4,7"]
[null,"DB InfraGO AG","3B127-009","Karlsruhe - München","<>","Maisach","Olching",2027,2027,31,33,"2027-08-03","01:00:00","2027-08-18","04:20:00","15d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2025-02-11",null,null,"2,3,4"]
[null,"DB InfraGO AG","3B1E9-027","Karlsruhe - Strasbourg","<>","Achern DB/SWEG","Achern",2027,2027,22,22,"2027-05-31","22:30:00","2027-06-03","04:45:00","2d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,6,7"]
[null,"DB InfraGO AG","3B1FE-002","Karlsruhe - München",">","Augsburg Hbf","Augsburg Hbf",2026,2027,50,15,"2026-12-13","00:00:00","2027-04-15","23:59:00","123d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,6,7"]
[null,"DB InfraGO AG","3B1FE-013","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2027,2027,28,28,"2027-07-14","22:00:00","2027-07-16","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,5.6]
[null,"DB InfraGO AG","3B370-002","München - Salzburg","<>","Traunstein","Siegsdorf",2027,2027,13,14,"2027-03-29","21:00:00","2027-04-05","05:00:00","6d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,7"]
[null,"DB InfraGO AG","3B386-010","München - Salzburg","<>","Zorneding","Grafing Bahnhof",2027,2027,40,42,"2027-10-04","21:00:00","2027-10-18","04:10:00","13d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,3.4]
[null,"DB InfraGO AG","3B386-016","München - Salzburg","<>","Grafing Bahnhof","München-Trudering",2027,2027,42,43,"2027-10-22","22:10:00","2027-10-25","04:10:00","2d, 6h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,"2,3,4,5,6"]
[null,"DB InfraGO AG","3B3E9-015","Darmstadt - Nürnberg","<>","Aschaffenburg Hbf","Aschaffenburg Hbf",2027,2027,28,28,"2027-07-12","22:00:00","2027-07-14","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-02-14",null,null,1]
[null,"DB InfraGO AG","3B3E9-029","Darmstadt - Nürnberg","<>","Mainaschaff","Aschaffenburg Hbf",2027,2027,28,29,"2027-07-18","22:00:00","2027-07-22","05:00:00","3d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-10",null,null,1.7]
[null,"DB InfraGO AG","3B3E9-035","Darmstadt - Nürnberg","<>","Mainaschaff Steinerts","Mainaschaff Abzw",2027,2027,29,29,"2027-07-22","22:00:00","2027-07-24","05:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-09-04",null,null,"1,2,3"]
[null,"DB InfraGO AG","3B3E9-062","Frankfurt - Karlsruhe","<","Aschaffenburg Hbf Ausfahrt","Laufach",2027,2027,30,31,"2027-08-01","02:00:00","2027-08-04","04:00:00","3d, 2h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-17",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","3B5BD-001","München - Salzburg","<>","Freilassing","Freilassing",2027,2027,13,16,"2027-04-02","22:00:00","2027-04-19","05:00:00","16d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-02-13",null,null,"1,2,3,5,6,7"]
[null,"DB InfraGO AG","3B5BD-007","München - Salzburg","<>","Freilassing","Freilassing",2027,2027,13,14,"2027-04-02","22:00:00","2027-04-05","05:00:00","2d, 7h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3B5C1-004","München - Salzburg","<>","Salzburg Grenze","Salzburg Liefering",2027,2027,43,44,"2027-10-29","22:00:00","2027-11-01","22:00:00","3d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,81,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3C332-004","Karlsruhe - Strasbourg","<>","Kehl","Kork",2026,2027,50,49,"2026-12-13","00:00:00","2027-12-11","23:59:00","363d, 23h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"Y",null,"2024-11-19",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","3C332-014","Karlsruhe - Strasbourg","<>","Kehl","Kehl",2027,2027,8,12,"2027-02-26","21:00:00","2027-03-22","05:00:00","23d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-26",null,null,1.7]
[null,"DB InfraGO AG","3C332-028","Karlsruhe - Strasbourg","<>","Kehl","Kehl",2027,2027,14,18,"2027-04-05","00:00:00","2027-05-07","23:59:00","32d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-10",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","3C3E3-001","Karlsruhe - Strasbourg","<>","Rastatt","Karlsruhe Brunnenstück",2027,2027,19,27,"2027-05-14","21:00:00","2027-07-09","20:59:00","55d, 23h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-09-24",null,null,"5,6,7"]
[null,"DB InfraGO AG","3C3F0-008","Darmstadt - Nürnberg","<>","Mainaschaff Abzw","Mainaschaff Steinerts",2026,2026,9,9,"2026-02-28","05:00:00","2026-03-01","05:00:00","1d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-18",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","3C3F0-019","Darmstadt - Nürnberg","<>","Mainaschaff Abzw","Mainaschaff Steinerts",2026,2026,10,11,"2026-03-05","05:00:00","2026-03-09","05:00:00","4d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-13",null,null,"1,2,6,7"]
[null,"DB InfraGO AG","3C918-004","Nürnberg - Passau","<>","Feucht","Nürnberg-Dutzendteich",2025,2025,51,51,"2025-12-16","22:00:00","2025-12-17","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-15",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","3C979-006","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2025,2025,51,51,"2025-12-18","21:45:00","2025-12-19","04:45:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-03",null,null,6.7]
[null,"DB InfraGO AG","3CD29-002","Darmstadt - Nürnberg","<>","Darmstadt-Eberstadt Nord","Pfungstadt",2027,2027,5,13,"2027-02-05","21:00:00","2027-04-02","20:59:00","55d, 22h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-14",null,null,6]
[null,"DB InfraGO AG","3D5E8-006","Frankfurt - Karlsruhe","<>","Mühlacker Kurve","Mühlacker Em Süd",2026,2026,51,51,"2026-12-14","08:00:00","2026-12-18","18:00:00","4d, 10h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-18",null,null,"1,2,7"]
[null,"DB InfraGO AG","3D5E8-022","Frankfurt - Karlsruhe","<>","Mühlacker Em Süd","Mühlacker Em Süd",2027,2027,2,2,"2027-01-11","08:00:00","2027-01-15","18:00:00","4d, 10h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,6,7"]
[null,"DB InfraGO AG","3D5E8-029","Karlsruhe - München","<>","Illingen (Württ)","Mühlacker",2027,2027,2,3,"2027-01-15","21:00:00","2027-01-22","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-10",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3D5E8-049","Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2027,2027,3,6,"2027-01-22","22:30:00","2027-02-12","05:00:00","20d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-24",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","3D5E8-088","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2027,2027,6,13,"2027-02-12","22:00:00","2027-04-02","05:00:00","48d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-13",null,null,1.2]
[null,"DB InfraGO AG","3D5E8-094","Karlsruhe - München","<>","Illingen (Württ)","Illingen (Württ)",2027,2027,6,13,"2027-02-12","22:00:00","2027-04-02","05:00:00","48d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-06",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3D626-007","München - Salzburg","<>","Prien a Chiemsee","Aschau (Chiemgau)",2027,2027,20,21,"2027-05-23","13:00:00","2027-05-24","05:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-17",null,null,1.7]
[null,"DB InfraGO AG","3D856-015","Karlsruhe - München","<>","Olching","München-Lochhausen",2027,2027,33,37,"2027-08-22","22:00:00","2027-09-14","05:00:00","22d, 7h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3D856-038","Karlsruhe - München",">","München-Lochhausen","Olching",2027,2027,41,41,"2027-10-11","22:00:00","2027-10-15","05:00:00","3d, 7h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-18",null,null,6.7]
[null,"DB InfraGO AG","3DF11-009","Karlsruhe - Strasbourg","<>","Achern","Appenweier-Muhrhaag",2027,2027,1,10,"2027-01-09","23:00:00","2027-03-14","04:00:00","63d, 5h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3DF11-022","Karlsruhe - Strasbourg","<>","Ottersweier","Offenburg nördl. Esig",2027,2027,14,19,"2027-04-11","23:00:00","2027-05-10","04:00:00","28d, 5h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-09",null,null,"1,2,3,4,6,7"]
[null,"DB InfraGO AG","3E5D5-003","Frankfurt - Karlsruhe","<>","Graben-Neudorf","Graben-Neudorf",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-09",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3E63E-002","Karlsruhe - Strasbourg","<>","Offenburg","Appenweier",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3E8AC-006","Karlsruhe - München","<>","Amstetten (Württ)","Süßen",2025,2025,51,52,"2025-12-21","22:00:00","2025-12-22","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","3ED1D-008","Karlsruhe - Strasbourg",">","Achern","Windschläg",2027,2027,21,22,"2027-05-28","21:00:00","2027-06-01","21:00:00","4d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-25",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","3ED1D-016","Karlsruhe - Strasbourg",">","Achern","Windschläg",2027,2027,22,23,"2027-06-05","21:00:00","2027-06-07","21:00:00","2d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-09",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3ED1D-040","Karlsruhe - Strasbourg","<>","Achern","Achern",2027,2027,26,27,"2027-06-30","21:00:00","2027-07-08","21:00:00","8d, 0h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"3,4,5,6"]
[null,"DB InfraGO AG","3ED7B-003","Nürnberg - Passau","<>","Nürnberg Reichswald","Allersberg (Rothsee)",2027,2027,8,9,"2027-02-28","22:00:00","2027-03-05","05:30:00","4d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3"]
[null,"DB InfraGO AG","3F8A5-002","Karlsruhe - Strasbourg","<>","Appenweier","Appenweier",2027,2027,30,31,"2027-07-26","22:00:00","2027-08-07","04:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-04-11",null,null,7]
[null,"DB InfraGO AG","3FA73-008","Karlsruhe - München","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2027,2027,18,19,"2027-05-09","03:00:00","2027-05-13","23:59:00","4d, 20h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-16",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","3FC77-004","Karlsruhe - München","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2027,2027,25,26,"2027-06-25","23:00:00","2027-06-28","05:00:00","2d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,"1,6,7"]
[null,"DB InfraGO AG","3FC77-010","Karlsruhe - München",">","Augsburg Hirblinger Straße","Westheim (Schwab)",2027,2027,26,26,"2027-06-28","23:00:00","2027-06-30","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-08",null,null,"5,6,7"]
[null,"DB InfraGO AG","3FC77-020","Karlsruhe - München","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2027,2027,26,27,"2027-07-03","07:00:00","2027-07-05","15:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,1.2]
[null,"DB InfraGO AG","3FC77-038","Karlsruhe - München","<>","Augsburg-Oberhausen","Augsburg-Oberhausen",2027,2027,30,31,"2027-08-01","21:00:00","2027-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-20",null,null,1.7]
[null,"DB InfraGO AG","3FC96-009","Karlsruhe - München","<>","Unterfahlheim","Ulm Hbf Bft Pbf",2025,2025,50,50,"2025-12-14","00:00:00","2025-12-14","05:00:00","0d, 5h","Continuous","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-02-20",null,null,3.4]
[null,"DB InfraGO AG","3FCD6-001","München - Salzburg","<>","Rosenheim","Rosenheim",2027,2027,5,27,"2027-02-04","21:00:00","2027-07-10","06:00:00","155d, 8h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,6,7"]
[null,"DB InfraGO AG","3FD50-011","Karlsruhe - Strasbourg","<>","Appenweier","Appenweier",2027,2027,46,46,"2027-11-15","23:00:00","2027-11-17","04:00:00","1d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-09",null,null,1.7]
[null,"DB InfraGO AG","3FD55-005","Karlsruhe - München","<>","Esslingen (Neckar)","Esslingen (Neckar)",2027,2027,10,12,"2027-03-10","07:00:00","2027-03-22","17:00:00","12d, 10h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-09",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3FD55-011","Karlsruhe - München","<>","Plochingen","Wendlingen (Neckar)",2027,2027,10,11,"2027-03-12","21:00:00","2027-03-19","05:00:00","6d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-09",null,null,7]
[null,"DB InfraGO AG","3FDE1-004","Nürnberg - Plzen","<>","Pegnitz","Pegnitz",2027,2027,19,23,"2027-05-14","05:00:00","2027-06-12","05:00:00","29d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-09",null,null,7]
[null,"DB InfraGO AG","3FE17-006","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2027,2027,6,13,"2027-02-13","22:00:00","2027-03-29","05:00:00","43d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3FE17-022","Frankfurt - Karlsruhe","<>","Illingen (Württ)","Illingen (Württ)",2027,2027,6,13,"2027-02-13","22:00:00","2027-03-29","05:00:00","43d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,2.2999999999999998]
[null,"DB InfraGO AG","3FE17-075","Karlsruhe - München","<>","Mühlacker","Maulbronn West",2027,2027,26,27,"2027-06-28","22:30:00","2027-07-09","05:00:00","10d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3FE17-092","Frankfurt - Karlsruhe","<>","Mühlacker","Mühlacker Em Nord",2027,2027,31,33,"2027-08-02","08:00:00","2027-08-20","18:00:00","18d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3"]
[null,"DB InfraGO AG","3FED7-006","Karlsruhe - Strasbourg","<>","Önsbach","Appenweier Nord",2027,2027,2,3,"2027-01-12","23:00:00","2027-01-20","04:00:00","7d, 5h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"5,6,7"]
[null,"DB InfraGO AG","3FF64-002","Frankfurt - Karlsruhe","<>","Neu-Edingen/Mhm-Friedrichsfeld","Schwetzingen",2027,2027,5,9,"2027-02-05","21:00:00","2027-03-05","05:00:00","27d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-20",null,null,1.2]
[null,"DB InfraGO AG","3FF64-009","Frankfurt - Karlsruhe","<>","Mannheim Ziehbrunnen","Schwetzingen",2027,2027,5,9,"2027-02-05","21:00:00","2027-03-05","05:00:00","27d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3FF80-002","Karlsruhe - München","<>","Mühlacker","Mühlacker",2027,2027,33,35,"2027-08-21","23:45:00","2027-09-04","05:00:00","13d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,"2,3,4"]
[null,"DB InfraGO AG","3FF80-026","Frankfurt - Karlsruhe","<>","Illingen (Württ)","Illingen (Württ)",2027,2027,36,39,"2027-09-06","22:00:00","2027-10-02","05:00:00","25d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","3FF80-035","Karlsruhe - München","<>","Mühlacker","Mühlacker",2027,2027,40,42,"2027-10-04","23:45:00","2027-10-22","05:00:00","17d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","3FF80-064","Karlsruhe - München","<>","Mühlacker","Mühlacker Em Nord",2027,2027,46,49,"2027-11-19","22:00:00","2027-12-10","05:00:00","20d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","40040-016","Karlsruhe - Strasbourg","<>","Appenweier","Appenweier-Muhrhaag",2027,2027,32,32,"2027-08-10","23:00:00","2027-08-12","04:00:00","1d, 5h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-27",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40040-031","Karlsruhe - Strasbourg","<>","Appenweier","Appenweier",2027,2027,38,38,"2027-09-21","23:00:00","2027-09-23","04:00:00","1d, 5h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-04",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","40041-005","Nürnberg - Plzen","<>","Schnabelwaid","Kirchenlaibach",2027,2027,18,20,"2027-05-03","05:00:00","2027-05-23","15:00:00","20d, 10h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","40045-014","Frankfurt - Karlsruhe","<>","Schwetzingen","Schwetzingen",2027,2027,7,8,"2027-02-19","21:00:00","2027-02-22","05:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-04",null,null,1.2]
[null,"DB InfraGO AG","40045-042","Karlsruhe - Strasbourg","<","Hockenheim","Schwetzingen",2027,2027,8,8,"2027-02-26","21:00:00","2027-02-28","22:00:00","2d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-04",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","40045-056","Karlsruhe - Strasbourg","<>","Schwetzingen","Schwetzingen",2027,2027,8,8,"2027-02-26","21:00:00","2027-02-28","22:00:00","2d, 1h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","404DB-001","Darmstadt - Nürnberg","<>","Aschaffenburg-Goldbach","Aschaffenburg Hbf Einfahrt",2027,2027,13,13,"2027-03-29","22:00:00","2027-04-03","05:00:00","4d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-19",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","40639-010","Karlsruhe - Strasbourg","<>","Rastatt","Bashaide",2027,2027,30,36,"2027-07-30","21:00:00","2027-09-10","21:00:00","42d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-10",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40745-001","München - Salzburg","<>","München Ost Pbf","München Ost Pbf",2026,2027,50,49,"2026-12-13","00:00:00","2027-12-11","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","40AE6-009","Karlsruhe - München",">","Bietigheim-Bissingen","Sachsenheim",2027,2027,6,7,"2027-02-12","21:00:00","2027-02-15","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3"]
[null,"DB InfraGO AG","40C37-001","München - Salzburg","<>","Landl (Oberbay) Abzw","Rohrdorf (Oberbay)",2027,2027,5,27,"2027-02-05","21:00:00","2027-07-09","21:00:00","153d, 23h","Continuous","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-09-30",null,null,4.5]
[null,"DB InfraGO AG","40CD3-002","Darmstadt - Nürnberg",">","Fürth-Burgfarrnbach","Fürth (Bay) Gbf",2027,2027,41,42,"2027-10-16","21:00:00","2027-10-18","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-12",null,null,5.6]
[null,"DB InfraGO AG","40CFB-017","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,51,52,"2026-12-20","21:00:00","2026-12-21","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-20",null,null,1.6]
[null,"DB InfraGO AG","40CFB-054","Karlsruhe - München","<>","Sachsenheim","Illingen (Württ)",2027,2027,2,3,"2027-01-17","21:00:00","2027-01-18","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40CFB-064","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","StrWe 4800/4842",2027,2027,3,3,"2027-01-18","21:00:00","2027-01-19","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-20",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40CFB-082","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2027,2027,6,6,"2027-02-09","21:00:00","2027-02-10","05:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-13",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","40E13-005","Karlsruhe - München","<>","Eislingen (Fils)","Eislingen (Fils)",2027,2027,9,9,"2027-03-02","21:00:00","2027-03-05","05:00:00","2d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-20",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","40E4A-002","Darmstadt - Nürnberg",">","Nürnberg Großmarkt","Fürth (Bay) Gbf",2027,2027,40,40,"2027-10-06","07:30:00","2027-10-07","14:30:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40E6E-004","Karlsruhe - München",">","Günzburg","Unterfahlheim",2027,2027,12,13,"2027-03-26","21:00:00","2027-03-29","05:00:00","2d, 7h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-25",null,null,3.4]
[null,"DB InfraGO AG","40EFF-008","Darmstadt - Nürnberg","<>","Fürth (Bay) Hbf","Fürth (Bay) Hbf",2027,2027,13,42,"2027-03-29","23:00:00","2027-10-22","04:00:00","206d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-14",null,null,"1,2,3,4,5,6"]
[null,"DB InfraGO AG","40F05-002","Karlsruhe - München","<>","Nersingen","Nersingen",2027,2027,5,5,"2027-02-05","22:00:00","2027-02-06","16:00:00","0d, 18h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-16",null,null,"1,2,3"]
[null,"DB InfraGO AG","40F05-008","Karlsruhe - München","<>","Nersingen","Nersingen",2027,2027,5,6,"2027-02-06","16:00:00","2027-02-08","04:00:00","1d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-16",null,null,1.7]
[null,"DB InfraGO AG","40F05-026","Karlsruhe - München",">","Unterfahlheim","Nersingen",2027,2027,13,13,"2027-04-03","21:00:00","2027-04-04","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-14",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","40F05-036","Karlsruhe - München","<>","Nersingen","Nersingen",2027,2027,22,22,"2027-06-04","05:00:00","2027-06-06","05:00:00","2d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3,4,6,7"]
[null,"DB InfraGO AG","40F9C-001","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2027,2027,6,6,"2027-02-13","21:00:00","2027-02-14","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-23",null,null,1.2]
[null,"DB InfraGO AG","40F9C-011","Frankfurt - Karlsruhe","<>","Illingen (Württ)","Illingen (Württ)",2027,2027,6,7,"2027-02-14","21:00:00","2027-02-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-26",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","40F9C-028","Frankfurt - Karlsruhe","<>","Vaihingen (Enz)","Vaihingen (Enz)",2027,2027,7,7,"2027-02-16","21:00:00","2027-02-18","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","40FF3-001","Darmstadt - Nürnberg","<>","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,51,51,"2026-12-18","21:00:00","2026-12-20","00:00:00","1d, 3h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41094-014","Nürnberg - Plzen","<>","Nürnberg Hbf","Nürnberg Hbf",2027,2027,27,28,"2027-07-09","23:00:00","2027-07-12","04:30:00","2d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,1]
[null,"DB InfraGO AG","411FE-003","Frankfurt - Karlsruhe","<>","StrWe 4800/4842","Vaihingen (Enz)",2027,2027,4,5,"2027-01-29","21:00:00","2027-02-04","05:00:00","5d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41200-002","Karlsruhe - München","<>","Bietigheim-Bissingen","Sachsenheim",2027,2027,4,5,"2027-01-29","21:00:00","2027-02-04","05:00:00","5d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,1.2]
[null,"DB InfraGO AG","41200-009","Karlsruhe - München","<","Sachsenheim","Bietigheim-Bissingen",2027,2027,7,7,"2027-02-15","21:00:00","2027-02-18","05:00:00","2d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","413AB-005","Nürnberg - Passau","<","Nürnberg-Dutzendteich","Nürnberg Rbf Ausfahrt",2027,2027,44,46,"2027-11-07","08:00:00","2027-11-21","16:00:00","14d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"20,,",null,null,null,"N",null,"2024-09-27",null,null,7]
[null,"DB InfraGO AG","41499-010","Karlsruhe - München",">","Stuttgart-Zuffenhausen","Kornwestheim Pbf",2027,2027,20,20,"2027-05-18","21:00:00","2027-05-21","05:00:00","2d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",6,6",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41553-006","Darmstadt - Nürnberg","<>","Fürth (Bay) Gbf","Fürth (Bay) Hbf",2027,2027,30,33,"2027-08-01","00:50:00","2027-08-20","05:00:00","19d, 4h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","415A4-018","München - Salzburg","<>","München-Giesing","München Ost Pbf",2026,2026,26,26,"2026-06-26","01:30:00","2026-06-26","04:30:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-20",null,null,"1,2,3,4,5,7"]
[null,"DB InfraGO AG","415A4-034","München - Salzburg","<>","München-Giesing","München Ost Pbf",2026,2026,26,28,"2026-06-26","01:30:00","2026-07-07","04:00:00","11d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-20",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41706-011","Karlsruhe - München","<>","Süßen","Süßen",2027,2027,31,33,"2027-08-06","23:00:00","2027-08-16","05:00:00","9d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","41769-005","Karlsruhe - München","<>","Göppingen","Göppingen",2027,2027,43,44,"2027-10-27","07:00:00","2027-11-03","17:00:00","7d, 11h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-09-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","417B0-001","Karlsruhe - München","<>","Augsburg Morellstraße","Augsburg Hbf",2027,2027,37,37,"2027-09-17","00:00:00","2027-09-19","05:00:00","2d, 5h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-11-27",null,null,2.2999999999999998]
[null,"DB InfraGO AG","41991-009","Karlsruhe - München","<>","Göppingen","Göppingen",2027,2027,39,40,"2027-10-01","07:00:00","2027-10-08","19:00:00","7d, 12h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-27",null,null,"3,4,5"]
[null,"DB InfraGO AG","41A9A-009","Karlsruhe - München","<>","Göppingen","Süßen",2027,2027,9,11,"2027-03-06","00:30:00","2027-03-15","05:00:00","9d, 4h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-27",null,null,4.5]
[null,"DB InfraGO AG","41B3D-001","Nürnberg - Passau","<","Feucht","Postbauer-Heng",2027,2027,47,47,"2027-11-26","21:00:00","2027-11-28","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","41B3D-007","Nürnberg - Passau",">","Neumarkt (Oberpf)","Ochenbruck",2027,2027,49,49,"2027-12-08","21:00:00","2027-12-09","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3"]
[null,"DB InfraGO AG","41E91-010","Karlsruhe - München","<>","Plochingen","Plochingen",2027,2027,4,5,"2027-01-30","21:00:00","2027-02-01","05:00:00","1d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,1.7]
[null,"DB InfraGO AG","41F83-020","Karlsruhe - München","<>","München-Pasing","München-Pasing",2027,2027,33,33,"2027-08-16","22:00:00","2027-08-18","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,7]
[null,"DB InfraGO AG","41FA3-008","München - Salzburg","<>","München-Giesing","München Ost Pbf",2026,2026,25,25,"2026-06-15","01:30:00","2026-06-17","04:30:00","2d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,4.5]
[null,"DB InfraGO AG","4208D-004","Karlsruhe - München","<>","Kornwestheim Pbf","Kornwestheim Pbf",2027,2027,27,27,"2027-07-06","22:00:00","2027-07-08","03:00:00","1d, 5h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-02-05",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","420AB-035","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2027,2027,43,45,"2027-10-30","00:00:00","2027-11-08","05:00:00","9d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","420E2-012","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2027,2027,12,26,"2027-03-23","00:01:00","2027-06-29","04:30:00","98d, 3h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3"]
[null,"DB InfraGO AG","420E3-001","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2027,2027,40,41,"2027-10-10","21:00:00","2027-10-11","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-30",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","420E3-011","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2027,2027,41,41,"2027-10-13","21:00:00","2027-10-14","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-26",null,null,1.7]
[null,"DB InfraGO AG","4224B-020","Frankfurt - Karlsruhe","<>","Karlsruhe Gbf","Karlsruhe-Dammerstock",2027,2027,18,19,"2027-05-05","22:01:00","2027-05-14","22:00:00","8d, 23h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,1.7]
[null,"DB InfraGO AG","4226D-003","Karlsruhe - München","<>","Augsburg Hbf","Inningen",2027,2027,13,13,"2027-04-03","20:30:00","2027-04-04","04:30:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3"]
[null,"DB InfraGO AG","4226D-014","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Morellstraße",2027,2027,14,15,"2027-04-10","20:00:00","2027-04-12","05:00:00","1d, 9h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","4233D-015","Karlsruhe - München","<>","München-Pasing Ost","München-Pasing",2027,2027,42,42,"2027-10-22","22:00:00","2027-10-23","22:00:00","1d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,6]
[null,"DB InfraGO AG","4233D-025","Karlsruhe - München","<>","München-Pasing","München-Pasing",2027,2027,46,47,"2027-11-19","22:00:00","2027-11-23","04:00:00","3d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,"1,6,7"]
[null,"DB InfraGO AG","4233D-041","Karlsruhe - München",">","München Hbf","München-Pasing Weiche 352",2027,2027,41,42,"2027-10-15","22:00:00","2027-10-18","04:00:00","2d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","42359-008","Karlsruhe - München","<>","Augsburg Hbf","Augsburg Hbf",2027,2027,47,48,"2027-11-28","05:00:00","2027-12-04","05:00:00","6d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","42575-032","Frankfurt - Karlsruhe","<>","Karlsruhe Hbf","Karlsruhe Hbf",2027,2027,29,30,"2027-07-24","22:00:00","2027-07-29","05:00:00","4d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-16",null,null,6.7]
[null,"DB InfraGO AG","42575-041","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe Hbf",2027,2027,31,32,"2027-08-06","01:00:00","2027-08-10","04:30:00","4d, 3h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,6.7]
[null,"DB InfraGO AG","42576-023","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2027,2027,14,18,"2027-04-09","23:30:00","2027-05-08","05:00:00","28d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-09-16",null,null,1.2]
[null,"DB InfraGO AG","42576-043","Karlsruhe - Strasbourg","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2027,2027,18,19,"2027-05-09","00:00:00","2027-05-10","05:00:00","1d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-15",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","42576-049","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2027,2027,18,19,"2027-05-09","05:00:00","2027-05-10","20:00:00","1d, 15h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","42576-081","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe Gbf",2027,2027,29,31,"2027-07-25","23:00:00","2027-08-06","05:00:00","11d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-10",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","42576-097","Frankfurt - Karlsruhe","<>","Karlsruhe-Durlach","Karlsruhe-Durlach",2027,2027,32,33,"2027-08-13","21:00:00","2027-08-16","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-16",null,null,1.7]
[null,"DB InfraGO AG","426E3-008","Karlsruhe - München","<>","Stuttgart-Zuffenhausen","Kornwestheim Pbf",2027,2027,30,31,"2027-07-26","01:00:00","2027-08-06","04:00:00","11d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-15",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","426E3-057","Karlsruhe - München","<>","Stuttgart-Zazenhausen","Stuttgart-Zazenhausen",2027,2027,34,35,"2027-08-23","23:00:00","2027-09-03","05:00:00","10d, 6h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","426E3-066","Karlsruhe - München","<>","Stuttgart-Zazenhausen","Kornwestheim Rbf Süd-Ost",2027,2027,39,40,"2027-10-01","23:00:00","2027-10-04","05:00:00","2d, 6h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","426FF-021","Karlsruhe - Strasbourg",">","Weingarten (Baden)","Karlsruhe Hbf",2027,2027,32,34,"2027-08-13","21:00:00","2027-08-23","12:00:00","9d, 15h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","426FF-035","Frankfurt - Karlsruhe","<>","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,29,30,"2027-07-25","01:00:00","2027-08-01","05:00:00","7d, 4h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","426FF-041","Karlsruhe - Strasbourg",">","Weingarten (Baden)","Karlsruhe Hbf",2027,2027,29,31,"2027-07-25","23:00:00","2027-08-06","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-25",null,null,6.7]
[null,"DB InfraGO AG","440CC-002","Darmstadt - Nürnberg",">","Wiesthal","Aschaffenburg Hbf",2026,2026,2,2,"2026-01-05","22:00:00","2026-01-06","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","440DF-001","München - Salzburg",">","Gr-Karolinenf  Ü","Rosenheim",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","04:00:00","0d, 6h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-16",null,null,1.2]
[null,"DB InfraGO AG","440E8-001","München - Salzburg",">","Straß","Freilassing",2026,2026,2,2,"2026-01-07","23:30:00","2026-01-08","05:30:00","0d, 6h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-16",null,null,1.2]
[null,"DB InfraGO AG","440F1-002","Darmstadt - Nürnberg","<>","Fürth (Bay) Hbf","Eltersdorf",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","44101-002","Darmstadt - Nürnberg",">","Zeil","Gädheim",2026,2026,2,2,"2026-01-08","22:10:00","2026-01-09","05:00:00","0d, 6h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-09-16",null,null,"5,6,7"]
[null,"DB InfraGO AG","44105-002","München - Salzburg","<>","Freilassing","Freilassing",2026,2026,2,2,"2026-01-08","23:00:00","2026-01-09","05:00:00","0d, 6h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-10",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","4410F-006","Darmstadt - Nürnberg","<>","Eggolsheim Süd","Bubenreuth",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-15",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","44124-005","Darmstadt - Nürnberg","<>","Strullendorf","Forchheim (Oberfr)",2026,2026,2,2,"2026-01-10","22:00:00","2026-01-11","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"2,3,4"]
[null,"DB InfraGO AG","44128-002","Darmstadt - Nürnberg","<>","Waigolshausen","Schweinfurt Stadt",2026,2026,2,2,"2026-01-10","22:15:00","2026-01-11","05:00:00","0d, 6h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","441BA-001","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Gbf",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","4645F-007","Darmstadt - Nürnberg","<>","Hallstadt (b Bamberg)","Bamberg",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","04:45:00","0d, 6h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3"]
[null,"DB InfraGO AG","470AD-008","Karlsruhe - Strasbourg",">","Karlsruhe Hbf","Rastatt",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","470AD-014","Karlsruhe - Strasbourg","<>","Karlsruhe Hbf","Karlsruhe-Hagsfeld",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","475B3-004","München - Regensburg","<>","Obertraubling","Eggmühl",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,5.6]
[null,"DB InfraGO AG","49182-007","Nürnberg - Passau","<","Nürnberg Hbf","Nürnberg-Dutzendteich",2026,2026,2,2,"2026-01-07","04:00:00","2026-01-07","05:30:00","0d, 1h","Continuous","Maintenance",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-15",null,null,"1,6,7"]
[null,"DB InfraGO AG","49F90-003","Darmstadt - Nürnberg","<>","Nürnberg Hbf","Nürnberg Rothenburgerstraße",2026,2026,2,2,"2026-01-09","23:15:00","2026-01-10","05:00:00","0d, 5h","Continuous","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","592CA-006","Karlsruhe - München","<>","Bietigheim-Bissingen","Bietigheim-Bissingen",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-24",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","5AF32-003","Karlsruhe - Strasbourg",">","Karlsruhe-Durlach","Karlsruhe Hbf",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Continuous","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","5AF32-009","Karlsruhe - Strasbourg","<","Karlsruhe Hbf","Blankenloch",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","5AFB3-004","Karlsruhe - München","<>","Esslingen (Neckar)","Esslingen (Neckar)",2025,2025,51,51,"2025-12-18","22:00:00","2025-12-19","05:00:00","0d, 7h","Continuous","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-24",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","1E35C-007","Bremen - Hannover",">","Bremen Hbf","Bremen Hbf",2026,2026,37,37,"2026-09-07","05:00:00","2026-09-12","14:00:00","5d, 9h","continuous",null,null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2024-01-17",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","3BEA2-005","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2025,2025,51,51,"2025-12-16","23:00:00","2025-12-17","05:00:00","0d, 6h","continuous","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-24",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4D3E6-006","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,7,7,"2026-02-10","23:00:00","2026-02-11","05:00:00","0d, 6h","continuous","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","50DDF-002","Bremen - Hannover",">","Bremen Rbf Ausfahrt","Bremen Rbf Abzw",2026,2026,3,3,"2026-01-14","23:00:00","2026-01-15","01:00:00","0d, 2h","continuous","Maintenance","T",null,null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","35BE2-002","Bremen - Hannover","<>","Bremen-Vahr","Bremen-Sebaldsbrück",2026,2026,45,46,"2026-11-02","08:00:00","2026-11-09","15:00:00","7d, 7h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-05",null,null,1,1]
[null,"DB InfraGO AG","36E9A-010","Bremen - Hannover","<>","Bremen Rbf Abzw","Bremen Rbf Einfahrt",2026,2026,45,45,"2026-11-02","08:00:00","2026-11-02","11:00:00","0d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO AG","43DFC-002","Bremen - Hannover","<>","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,3,3,"2026-01-12","22:00:00","2026-01-13","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,1.2,1]
[null,"DB InfraGO AG","4A561-002","Bremen - Hannover",">","Bremen-Sebaldsbrück","Bremen Hbf",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-11",null,null,1.2,1]
[null,"DB InfraGO AG","4A7C6-002","Bremen - Hannover",">","Bremen Rbf Abzw","Osterholz-Scharmbeck",2026,2026,5,5,"2026-01-29","22:00:00","2026-01-30","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-16",null,null,4.5,1]
[null,"DB InfraGO AG","4D4D6-002","Bremen - Hannover","<","Bremen Hbf","Bremen-Sebaldsbrück",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-13",null,null,4.5,1]
[null,"DB InfraGO AG","321C8-003","Bremen - Hannover","<>","Haste","Wunstorf",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-02",null,null,"4,5,6",1]
[null,"DB InfraGO AG","43EB9-003","Bremen - Hannover","<>","Wunstorf","Seelze",2026,2026,4,4,"2026-01-20","22:00:00","2026-01-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","46B34-006","Bremen - Hannover","<","Wunstorf","Letter                            (Abzw)",2025,2025,51,51,"2025-12-20","22:50:00","2025-12-21","06:50:00","0d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-04-30",null,null,6.7,1]
[null,"DB InfraGO AG","4A803-002","Bremen - Hannover","<>","Wunstorf","Lindhorst (Schaumb-Lippe)",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2025-06-12",null,null,4.5,1]
[null,"DB InfraGO AG","4D4FA-007","Bremen - Hannover","<>","Nienburg (Weser)","Nienburg (Weser)",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-17",null,null,4.5,1]
[null,"DB InfraGO AG","3BF46-003","Bremen - Hannover","<>","Nienburg (Weser)","Nienburg (Weser)",2025,2025,51,51,"2025-12-18","22:00:00","2025-12-19","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-24",null,null,4.5,1]
[null,"DB InfraGO AG","20849-001","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-27","09:00:00","2026-07-27","12:00:00","0d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","20849-011","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-09","09:00:00","2026-08-09","13:00:00","0d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,7,1]
[null,"DB InfraGO AG","20A9D-005","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,39,40,"2026-09-24","07:00:00","2026-09-30","15:00:00","6d, 8h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","34F7B-003","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-29","08:00:00","2026-07-29","16:00:00","0d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-13",null,null,3,1]
[null,"DB InfraGO AG","3BF93-001","Bremen - Hannover","<>","Sagehorn","Bremen Hbf",2025,2025,51,51,"2025-12-19","22:00:00","2025-12-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-28",null,null,5.6,1]
[null,"DB InfraGO AG","43E7C-001","Bremen - Hannover","<","Sagehorn","Bremen Hbf",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-23",null,null,5.6,1]
[null,"DB InfraGO AG","49464-003","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,6,6,"2026-02-03","23:00:00","2026-02-04","05:00:00","0d, 6h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-05",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4D656-001","Bremen - Hannover","<","Sagehorn","Bremen Hbf",2026,2026,7,7,"2026-02-13","22:00:00","2026-02-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-06-17",null,null,5.6,1]
[null,"DB InfraGO AG","4E566-008","Bremen - Hannover","<>","Bremen Hbf","Bremen Gabelung",2026,2026,8,8,"2026-02-19","23:00:00","2026-02-20","05:00:00","0d, 6h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,4.5,1]
[null,"DB InfraGO AG","1B194-001","Bremen - Hannover","<>","Hannover-Linden Hafen","Seelze Ost",2025,2026,52,3,"2025-12-27","21:00:00","2026-01-13","10:00:00","16d, 13h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3BCA4-002","Bremen - Hannover",">","Wunstorf","Wunstorf",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,1.2,1]
[null,"DB InfraGO AG","43D91-001","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2026,2026,2,2,"2026-01-05","05:30:00","2026-01-05","13:30:00","0d, 8h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,null,"N",null,"2025-04-08",null,null,1,1]
[null,"DB InfraGO AG","43DE8-003","Bremen - Hannover","<>","Hannover-Linden Hafen","Wunstorf",2026,2026,2,2,"2026-01-10","23:30:00","2026-01-11","07:30:00","0d, 8h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,6.7,1]
[null,"DB InfraGO AG","43EF2-002","Bremen - Hannover","<>","Hannover-Waldhausen","Hannover-Linden/Fischerhof",2026,2026,4,5,"2026-01-25","22:00:00","2026-01-26","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-24",null,null,1.7,1]
[null,"DB InfraGO AG","47BEB-002","Bremen - Hannover","<>","Lehrte West","Lehrte West",2026,2026,6,6,"2026-02-05","22:00:00","2026-02-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","47C65-001","Bremen - Hannover","<>","Lehrte West","Lehrte Nord",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-06-10",null,null,5.6,1]
[null,"DB InfraGO AG","48EB5-003","Bremen - Hannover","<>","Seelze West","Wunstorf",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-11",null,null,5.6,1]
[null,"DB InfraGO AG","493B0-003","Bremen - Hannover","<>","Seelze West","Hannover-Linden Hafen",2026,2026,10,10,"2026-03-02","05:30:00","2026-03-02","13:30:00","0d, 8h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,1,1]
[null,"DB InfraGO AG","4A9FA-006","Bremen - Hannover","<>","Seelze Ost","Seelze Ost",2026,2026,5,6,"2026-02-01","22:00:00","2026-02-02","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-11",null,null,1.7,1]
[null,"DB InfraGO AG","4E3C2-001","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,8,8,"2026-02-17","22:00:00","2026-02-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"8,,",null,null,null,"N",null,"2025-06-11",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","43DCF-006","Bremen - Hannover","<>","Wunstorf","Wunstorf",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,4.5,1]
[null,"DB InfraGO AG","43EB5-003","Bremen - Hannover","<>","Wunstorf","Wunstorf",2026,2026,4,4,"2026-01-19","22:00:00","2026-01-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,1.2,1]
[null,"DB InfraGO AG","47CAE-004","Bremen - Hannover","<>","Gümmerwald","Wunstorf",2026,2026,10,10,"2026-03-07","23:30:00","2026-03-08","07:30:00","0d, 8h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,6.7,1]
[null,"DB InfraGO AG","4A4C5-003","Bremen - Hannover","<>","Eystrup","Nienburg (Weser)",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-11",null,null,1.2,1]
[null,"DB InfraGO AG","4A561-007","Bremen - Hannover","<>","Baden (Kr Verden)","Bremen Hbf",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2025-06-11",null,null,1.2,1]
[null,"DB InfraGO AG","4A5D9-004","Bremen - Hannover","<>","Achim","Verden (Aller)",2026,2026,5,5,"2026-01-27","22:00:00","2026-01-28","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2025-06-11",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4A6A5-002","Bremen - Hannover","<>","Rohrsen (b Nienburg)","Hagen (Han)",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","4A766-003","Bremen - Hannover","<>","Stubben","Bremerhaven-Wulsdorf",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2025-06-12",null,null,4.5,1]
[null,"DB InfraGO AG","4A7C6-005","Bremen - Hannover","<>","Bremen Hbf","Osterholz-Scharmbeck",2026,2026,5,5,"2026-01-29","22:00:00","2026-01-30","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2025-06-16",null,null,4.5,1]
[null,"DB InfraGO AG","4A76C-010","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2025,2025,51,51,"2025-12-18","00:00:00","2025-12-18","02:30:00","0d, 2h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-05-12",null,null,4,1]
[null,"DB InfraGO AG","4A923-003","Bremen - Hannover","<>","Wunstorf","Wunstorf",2026,2026,9,9,"2026-02-28","22:00:00","2026-03-01","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,6.7,1]
[null,"DB InfraGO AG","4A76C-023","Bremen - Hannover","<","Oldenbüttel","Osterholz-Scharmbeck",2026,2026,12,12,"2026-03-21","22:00:00","2026-03-22","07:00:00","0d, 9h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-05-12",null,null,6.7,1]
[null,"DB InfraGO AG","4D2DE-003","Bremen - Hannover","<>","Osterholz-Scharmbeck","Lübberstedt",2026,2026,7,7,"2026-02-09","22:00:00","2026-02-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2025-06-16",null,null,1.2,1]
[null,"DB InfraGO AG","4D3CE-001","Bremen - Hannover","<","Oldenbüttel","Bremen-Burg",2026,2026,7,7,"2026-02-14","22:00:00","2026-02-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-07-21",null,null,6.7,1]
[null,"DB InfraGO AG","4D4D6-001","Bremen - Hannover","<","Bremen Hbf","Baden (Kr Verden)",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-13",null,null,4.5,1]
[null,"DB InfraGO AG","4D6AB-004","Bremen - Hannover","<>","Wahnebergen","Etelsen",2026,2026,7,7,"2026-02-14","22:00:00","2026-02-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-17",null,null,6.7,1]
[null,"DB InfraGO AG","4E566-009","Bremen - Hannover","<>","Bremen Hbf","Bremen Hbf",2026,2026,8,8,"2026-02-19","23:00:00","2026-02-20","05:00:00","0d, 6h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,4.5,1]
[null,"DB InfraGO AG","50DDF-003","Bremen - Hannover","<>","Bremen Rbf Abzw","Bremen Rbf Abzw",2026,2026,3,3,"2026-01-14","23:00:00","2026-01-15","01:00:00","0d, 2h","Periodical","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","1F8D6-012","Bremerhaven - Bremen","<>","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,33,"2026-08-16","15:00:00","2026-08-16","16:00:00","0d, 1h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,7,1]
[null,"DB InfraGO AG","1F8D6-019","Bremerhaven - Bremen","<>","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-18","02:00:00","2026-08-18","05:00:00","0d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,2,1]
[null,"DB InfraGO AG","1E8C2-009","Bremerhaven - Bremen","<","Oldenbüttel","Bremen-Burg",2026,2026,4,4,"2026-01-19","23:00:00","2026-01-23","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E8C3-012","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,9,9,"2026-02-23","21:00:00","2026-02-27","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E70A-037","Bremerhaven - Bremen","<>","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,10,10,"2026-03-04","23:00:00","2026-03-06","05:00:00","1d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-23",null,null,3.4,1]
[null,"DB InfraGO AG","1F8D8-003","Bremerhaven - Bremen","<>","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","07:00:00","2026-09-22","15:30:00","0d, 8h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-05-13",null,null,2,1]
[null,"DB InfraGO AG","35825-004","Bremerhaven - Bremen","<","Stubben","Lübberstedt",2026,2026,43,43,"2026-10-20","22:00:00","2026-10-23","05:00:00","2d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-24",null,null,2.4,1]
[null,"DB InfraGO AG","35825-006","Bremerhaven - Bremen","<>","Stubben","Stubben",2026,2026,43,43,"2026-10-20","22:00:00","2026-10-23","05:00:00","2d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,2.4,1]
[null,"DB InfraGO AG","369BD-002","Bremerhaven - Bremen","<>","Bremen-Mahndorf","Bremen-Mahndorf",2026,2026,5,6,"2026-02-01","22:30:00","2026-02-03","04:50:00","1d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-12",null,null,1.7,1]
[null,"DB InfraGO AG","3BEAC-002","Bremerhaven - Bremen","<>","Oldenbüttel","Stubben",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-28",null,null,3.4,1]
[null,"DB InfraGO AG","3BEF6-002","Bremerhaven - Bremen","<>","Baden (Kr Verden)","Bremen-Sebaldsbrück",2025,2025,51,51,"2025-12-18","22:00:00","2025-12-19","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-28",null,null,4.5,1]
[null,"DB InfraGO AG","3BF46-004","Bremerhaven - Bremen","<>","Nienburg (Weser)","Nienburg (Weser)",2025,2025,51,51,"2025-12-18","22:00:00","2025-12-19","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-24",null,null,4.5,1]
[null,"DB InfraGO AG","43DCF-005","Bremerhaven - Bremen","<>","Wunstorf","Wunstorf",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,4.5,1]
[null,"DB InfraGO AG","43E16-003","Bremerhaven - Bremen","<>","Bremerhaven-Wulsdorf","Stubben",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","43E4C-004","Bremerhaven - Bremen","<>","Bremen-Mahndorf","Bremen Hbf",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2025-04-23",null,null,4.5,1]
[null,"DB InfraGO AG","43E72-002","Bremerhaven - Bremen","<>","Nienburg (Weser)","Dörverden",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,5.6,1]
[null,"DB InfraGO AG","46893-007","Bremerhaven - Bremen","<>","Verden (Aller)","Verden (Aller)",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,4.5,1]
[null,"DB InfraGO AG","47BF9-002","Bremerhaven - Bremen","<","Poggenhagen","Wunstorf",2026,2026,6,6,"2026-02-05","22:00:00","2026-02-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2025-06-11",null,null,4.5,1]
[null,"DB InfraGO AG","1DD70-015","Dresden - Děčín","<>","Dresden Mitte","Dresden Hbf",2026,2026,5,5,"2026-01-28","21:00:00","2026-01-30","04:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,3.4,1]
[null,"DB InfraGO AG","20535-008","Dresden - Děčín",">","Bad Schandau","Bad Schandau",2026,2026,1,5,"2026-01-03","04:00:00","2026-01-31","20:00:00","28d, 16h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20535-016","Dresden - Děčín","<>","Bad Schandau Ost","Königst (Sä) Üst",2026,2026,9,9,"2026-02-26","20:00:00","2026-02-28","04:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-08",null,null,4.5,1]
[null,"DB InfraGO AG","206A9-012","Dresden - Děčín","<>","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,9,11,"2026-02-27","00:01:00","2026-03-11","04:00:00","12d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","24097-002","Dresden - Děčín","<>","Pirna Gbf","Dresden-Reick Abstellbahnhof",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","04:50:00","0d, 7h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-19",null,null,6.7,1]
[null,"DB InfraGO AG","24FC1-005","Dresden - Děčín","<>","Dresden Hbf","Dresden-Neustadt",2026,2026,31,31,"2026-07-29","23:40:00","2026-07-31","04:20:00","1d, 4h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3.4,1]
[null,"DB InfraGO AG","2A3A6-005","Dresden - Děčín","<>","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-03","09:10:00","2026-11-05","17:10:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"2,3,4",1]
[null,"DB InfraGO AG","31C8B-004","Dresden - Děčín","<","Obervogelgesang (Kr Pirna)","Königst (Sä) Üst",2026,2026,3,3,"2026-01-15","01:00:00","2026-01-15","05:00:00","0d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-29",null,null,4,1]
[null,"DB InfraGO AG","31E68-001","Dresden - Děčín","<>","Obervogelgesang (Kr Pirna)","Königst (Sä) Üst",2026,2026,4,4,"2026-01-24","21:00:00","2026-01-25","05:00:00","0d, 8h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-29",null,null,6.7,1]
[null,"DB InfraGO AG","31E7F-003","Dresden - Děčín",">","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,4,5,"2026-01-25","21:00:00","2026-01-26","05:00:00","0d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-29",null,null,1.7,1]
[null,"DB InfraGO AG","31F86-003","Dresden - Děčín",">","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,5,5,"2026-01-27","21:00:00","2026-01-27","23:00:00","0d, 2h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-05-29",null,null,2,1]
[null,"DB InfraGO AG","327BA-004","Dresden - Děčín","<","Dresden Hbf","Dresden Hbf",2026,2026,5,6,"2026-02-01","20:00:00","2026-02-02","04:00:00","0d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-06-10",null,null,1.7,1]
[null,"DB InfraGO AG","327C2-007","Dresden - Děčín","<>","Dresden Hbf","Dresden-Niedersedlitz Güteranlage  (DHD)",2026,2026,8,9,"2026-02-22","19:50:00","2026-02-23","04:00:00","0d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-17",null,null,1.7,1]
[null,"DB InfraGO AG","33B25-009","Dresden - Děčín","<","Heidenau","Pirna",2026,2026,33,33,"2026-08-12","21:00:00","2026-08-14","01:00:00","1d, 4h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,3.4,1]
[null,"DB InfraGO AG","1DD70-022","Dresden - Děčín","<>","Dresden Hbf","Dresden Mitte",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","04:00:00","0d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,5.6,1]
[null,"DB InfraGO AG","5108F-004","Dresden - Děčín","<>","Dresden Hbf","Dresden Mitte",2026,2026,5,5,"2026-01-27","08:00:00","2026-01-27","17:00:00","0d, 9h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-29",null,null,2,1]
[null,"DB InfraGO AG","24097-003","Dresden - Děčín","<>","Heidenau","Dohna (Sachs)",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","04:50:00","0d, 7h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-19",null,null,6.7,1]
[null,"DB InfraGO AG","1DC42-019","Dresden - Děčín","<>","Coswig (bei Dresden)","Dresden Hbf",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,1,1]
[null,"DB InfraGO AG","24FC1-003","Dresden - Děčín","<>","Dresden Hbf","Dresden-Neustadt",2026,2026,31,31,"2026-07-30","00:15:00","2026-07-31","04:20:00","1d, 4h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,4.5,1]
[null,"DB InfraGO AG","327C2-014","Dresden - Děčín","<>","Dresden-Reick","Dresden Hbf",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-24","04:30:00","0d, 5h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,1.2,1]
[null,"DB InfraGO AG","1F543-028","Dresden - Děčín","<>","Dresden-Neustadt","Coswig (bei Dresden)",2026,2026,8,8,"2026-02-16","00:00:00","2026-02-16","04:00:00","0d, 4h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-09",null,null,1,1]
[null,"DB InfraGO AG","1D405-008","Falkenberg - Dresden","<","Kottewitz","Leckwitz",2026,2026,39,39,"2026-09-21","05:00:00","2026-09-22","05:00:00","1d, 0h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-28",null,null,1.2,1]
[null,"DB InfraGO AG","3210F-004","Falkenberg - Dresden",">","Leckwitz","Kottewitz",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-23","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","48569-005","Falkenberg - Dresden","<>","Leckwitz","Leckwitz",2026,2026,6,6,"2026-02-05","22:00:00","2026-02-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,4.5,1]
[null,"DB InfraGO AG","33BBB-004","Falkenberg - Dresden",">","Zeithain Bogendreieck","Zeithain Rohrwerk",2026,2026,41,41,"2026-10-06","01:00:00","2026-10-06","05:00:00","0d, 4h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"7,,7",null,null,null,"N",null,"2024-04-18",null,null,2,1]
[null,"DB InfraGO AG","4EF7D-005","Falkenberg - Dresden","<>","Zeithain Rohrwerk","Zeithain Bogendreieck",2026,2026,8,8,"2026-02-16","22:00:00","2026-02-17","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,1.2,1]
[null,"DB InfraGO AG",3.3910000000000003E-2,"Falkenberg - Dresden","<>","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,42,42,"2026-10-13","21:00:00","2026-10-14","05:00:00","0d, 8h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-18",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","3D6FE-003","Falkenberg - Dresden","<","Röderau","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"18,,18",null,null,null,"N",null,"2025-05-20",null,null,1.2,1]
[null,"DB InfraGO AG","443EB-004","Falkenberg - Dresden","<>","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,3,3,"2026-01-14","22:00:00","2026-01-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,3.4,1]
[null,"DB InfraGO AG","4EF7D-002","Falkenberg - Dresden","<>","Röderau","Zeithain Bogendreieck",2026,2026,8,8,"2026-02-16","22:00:00","2026-02-17","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,1.2,1]
[null,"DB InfraGO AG","32427-010","Falkenberg - Dresden",">","Priestewitz","Coswig (bei Dresden) Stw 1",2026,2026,8,8,"2026-02-18","21:30:00","2026-02-20","05:30:00","1d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,3.4,1]
[null,"DB InfraGO AG","336BA-004","Falkenberg - Dresden","<","Priestewitz","Leckwitz",2026,2026,22,22,"2026-05-30","00:10:00","2026-05-30","03:40:00","0d, 3h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-03-21",null,null,6,1]
[null,"DB InfraGO AG","3370C-001","Falkenberg - Dresden","<>","Leckwitz","Niederau",2026,2026,24,24,"2026-06-11","21:00:00","2026-06-12","05:00:00","0d, 8h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-24",null,null,4.5,1]
[null,"DB InfraGO AG",4.4290000000000003E-2,"Falkenberg - Dresden","<>","Priestewitz","Zeithain Bogendreieck",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2025-04-23",null,null,4.5,1]
[null,"DB InfraGO AG","442BD-009","Falkenberg - Dresden","<>","Zeithain Bogendreieck","Riesa Rbf",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4,1]
[null,"DB InfraGO AG","44427-004","Falkenberg - Dresden","<","Zeithain Bogendreieck","Röderau Bogendreieck",2026,2026,4,4,"2026-01-19","22:00:00","2026-01-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-23",null,null,1.2,1]
[null,"DB InfraGO AG","4856B-002","Falkenberg - Dresden",">","Zeithain Bogendreieck","Priestewitz",2026,2026,10,10,"2026-03-05","22:00:00","2026-03-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,4.5,1]
[null,"DB InfraGO AG","43EA2-002","Hamburg - Magdeburg",">","Stelle","Maschen Rbf (Msof)",2026,2026,4,4,"2026-01-19","07:00:00","2026-01-19","14:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,1,1]
[null,"DB InfraGO AG","1FB6A-001","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","203FF-019","Hamburg - Magdeburg","<>","Stendal Gbf","Nahrstedt",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-17","05:00:00","0d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-14",null,null,1.2,1]
[null,"DB InfraGO AG","3BE1A-003","Hamburg - Magdeburg","<>","Lehrte","Lehrte",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-07",null,null,3.4,1]
[null,"DB InfraGO AG","443F6-001","Hamburg - Magdeburg","<>","Stendal Gbf","Nahrstedt",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,4.5,1]
[null,"DB InfraGO AG","48735-003","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Stendal Gbf",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,5.6,1]
[null,"DB InfraGO AG","4C310-006","Hamburg - Magdeburg","<>","Meinersen","Lehrte",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","4D416-003","Hamburg - Magdeburg","<>","Lehrte","Lehrte",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,3.4,1]
[null,"DB InfraGO AG","33905-001","Hamburg - Magdeburg","<>","Maschen Rbf (Mnof)","Maschen Rbf (Mnof)",2026,2026,7,8,"2026-02-09","07:00:00","2026-02-16","07:00:00","7d, 0h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","35B1D-002","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-23","16:00:00","2d, 18h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","3BFA3-002","Hamburg - Magdeburg","<>","Buchholz (Nordheide)","Maschen Rbf (Msof)",2025,2025,51,51,"2025-12-19","22:00:00","2025-12-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,5.6,1]
[null,"DB InfraGO AG","43E66-004","Hamburg - Magdeburg","<","Hamburg-Wilhelmsburg Abzw","Hamburg Oberhafen",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,4.5,1]
[null,"DB InfraGO AG","4D572-003","Hamburg - Magdeburg","<","Hamburg-Rothenburgsort Ro","Hamburg-Wilhelmsburg Abzw",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-25",null,null,4.5,1]
[null,"DB InfraGO AG","4E5C6-001","Hamburg - Magdeburg","<","Hamburg-Veddel","Meckelfeld",2026,2026,8,8,"2026-02-20","22:00:00","2026-02-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-07-04",null,null,5.6,1]
[null,"DB InfraGO AG","50C63-004","Hamburg - Magdeburg","<>","Buchholz (Nordheide)","Maschen Rbf (Msof)",2026,2026,5,5,"2026-01-31","00:20:00","2026-01-31","04:50:00","0d, 4h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,6,1]
[null,"DB InfraGO AG","47C42-003","Hamburg - Magdeburg","<>","Hamburg Unterelbe","Hamburg Unterelbe Seehafen",2026,2026,10,10,"2026-03-06","22:00:00","2026-03-07","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,5.6,1]
[null,"DB InfraGO AG","43E14-006","Hamburg - Magdeburg","<>","Lehrte","Lehrte West",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-25",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","47C65-002","Hamburg - Magdeburg","<>","Lehrte West","Lehrte",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-06-10",null,null,5.6,1]
[null,"DB InfraGO AG","3BC61-002","Hamburg - Magdeburg",">","Bardowick","Stelle",2025,2025,50,51,"2025-12-14","22:00:00","2025-12-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2025-03-29",null,null,1.7,1]
[null,"DB InfraGO AG","3BD22-003","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg-Harburg",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,1.2,1]
[null,"DB InfraGO AG","3BDA8-001","Hamburg - Magdeburg","<","Meckelfeld","Stelle",2025,2025,51,51,"2025-12-16","22:00:00","2025-12-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-03-24",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","3FC0A-003","Hamburg - Magdeburg","<>","Lüneburg Gbf","Lüneburg Gbf",2025,2025,50,50,"2025-12-14","00:00:00","2025-12-14","05:00:00","0d, 5h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,7,1]
[null,"DB InfraGO AG","43DD8-005","Hamburg - Magdeburg","<>","Buxtehude","Hamburg-Harburg",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,5.6,1]
[null,"DB InfraGO AG","43E1E-001","Hamburg - Magdeburg","<","Bardowick","Lüneburg",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-04-22",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","43E9B-003","Hamburg - Magdeburg","<>","Bad Bevensen","Lüneburg Gbf",2026,2026,3,4,"2026-01-18","22:00:00","2026-01-19","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,1.7,1]
[null,"DB InfraGO AG","43EA2-005","Hamburg - Magdeburg","<","Meckelfeld","Meckelfeld",2026,2026,4,4,"2026-01-19","07:00:00","2026-01-19","14:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,1,1]
[null,"DB InfraGO AG","43EFA-004","Hamburg - Magdeburg","<>","Uelzen Gbf","Uelzen",2026,2026,4,4,"2026-01-20","22:00:00","2026-01-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-16",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","467E7-001","Hamburg - Magdeburg",">","Lehrte Nord","Burgdorf",2025,2025,50,50,"2025-12-14","22:00:00","2025-12-14","23:45:00","0d, 1h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-03-25",null,null,7,1]
[null,"DB InfraGO AG","43E92-004","Hamburg - Magdeburg","<>","Klein Süstedt","Uelzen",2026,2026,3,3,"2026-01-17","22:00:00","2026-01-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2025-04-22",null,null,6.7,1]
[null,"DB InfraGO AG","47C41-002","Hamburg - Magdeburg","<>","Hamburg-Hausbruch","Hausbruch Mitte",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-24",null,null,5.6,1]
[null,"DB InfraGO AG","48EF1-001","Hamburg - Magdeburg","<","Bad Bevensen","Uelzen",2026,2026,6,7,"2026-02-08","22:00:00","2026-02-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-06-26",null,null,1.7,1]
[null,"DB InfraGO AG","494DD-002","Hamburg - Magdeburg",">","Lüneburg Gbf","Lüneburg Nordkopf",2026,2026,10,10,"2026-03-07","22:00:00","2026-03-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-03",null,null,6.7,1]
[null,"DB InfraGO AG","4A78B-002","Hamburg - Magdeburg","<>","Winsen (Luhe)","Lüneburg",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-27",null,null,4.5,1]
[null,"DB InfraGO AG","4A893-003","Hamburg - Magdeburg","<>","Lüneburg Gbf","Bad Bevensen",2026,2026,9,10,"2026-03-01","22:00:00","2026-03-02","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-02",null,null,1.7,1]
[null,"DB InfraGO AG","4A90B-004","Hamburg - Magdeburg","<>","Lehrte Nord","Lehrte",2026,2026,9,9,"2026-02-27","22:00:00","2026-02-28","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,5.6,1]
[null,"DB InfraGO AG","4A9E3-001","Hamburg - Magdeburg",">","Suderburg","Uelzen Gbf",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-06-27",null,null,4.5,1]
[null,"DB InfraGO AG","4A9EE-004","Hamburg - Magdeburg","<>","Stelle","Bardowick",2026,2026,5,6,"2026-02-01","22:00:00","2026-02-02","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-26",null,null,1.7,1]
[null,"DB InfraGO AG","4D2BA-002","Hamburg - Magdeburg","<","Lehrte Nord","Lehrte",2026,2026,7,7,"2026-02-09","22:00:00","2026-02-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-06-10",null,null,1.2,1]
[null,"DB InfraGO AG","4D40A-001","Hamburg - Magdeburg","<","Ehlershausen","Lehrte Nord",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-06-10",null,null,3.4,1]
[null,"DB InfraGO AG","4D452-003","Hamburg - Magdeburg",">","Lüneburg","Winsen (Luhe)",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-27",null,null,3.4,1]
[null,"DB InfraGO AG","4E48E-001","Hamburg - Magdeburg","<","Hamburg-Hausbruch","Hamburg-Harburg",2026,2026,8,8,"2026-02-18","22:00:00","2026-02-19","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-23",null,null,3.4,1]
[null,"DB InfraGO AG","4E5F6-003","Hamburg - Magdeburg","<>","Lüneburg Gbf","Lüneburg Gbf",2026,2026,8,8,"2026-02-20","22:00:00","2026-02-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-02",null,null,5.6,1]
[null,"DB InfraGO AG","4E6E6-001","Hamburg - Magdeburg",">","Stelle","Hamburg-Harburg",2026,2026,8,9,"2026-02-22","22:00:00","2026-02-23","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-07-04",null,null,1.7,1]
[null,"DB InfraGO AG","50FA9-007","Hamburg - Magdeburg","<","Stelle","Lüneburg",2025,2025,50,50,"2025-12-14","02:00:00","2025-12-14","03:30:00","0d, 1h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,7,1]
[null,"DB InfraGO AG","5D0D1-002","Hamburg - Magdeburg",">","Uelzen","Uelzen",2025,2025,51,51,"2025-12-16","01:45:00","2025-12-16","04:00:00","0d, 2h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-22",null,null,2,1]
[null,"DB InfraGO AG","3BE1F-003","Hamburg - Magdeburg","<>","Algermissen","Lehrte",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-07",null,null,3.4,1]
[null,"DB InfraGO AG","3BD27-001","Hamburg - Magdeburg","<>","Stelle","Winsen (Luhe)",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-24",null,null,6.7,1]
[null,"DB InfraGO AG","5DC9E-001","Hamburg - Magdeburg",">","Stelle","Stelle",2026,2026,2,3,"2026-01-11","22:00:00","2026-01-12","05:00:00","0d, 7h","Periodical","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-29",null,null,1.7,1]
[null,"DB InfraGO AG","20B8B-004","Hamburg - Magdeburg","<>","Tornitz Seehof","Magdeburg Hbf",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,6.7,1]
[null,"DB InfraGO AG","1B3F6-003","Hamburg - Magdeburg","<>","Magdeburg-Buckau","Magdeburg Hbf",2025,2026,50,29,"2025-12-14","00:00:00","2026-07-18","10:00:00","216d, 9h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21013-008","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-19",null,null,6,1]
[null,"DB InfraGO AG","21013-016","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,37,37,"2026-09-12","12:00:00","2026-09-12","14:00:00","0d, 2h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-22",null,null,6,1]
[null,"DB InfraGO AG","44269-001","Hamburg - Magdeburg","<>","Magdeburg-Neustadt","Magdeburg Hbf",2026,2026,2,2,"2026-01-05","22:00:00","2026-01-06","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-02",null,null,1.2,1]
[null,"DB InfraGO AG","44285-003","Hamburg - Magdeburg","<>","Angern-Rogätz","Angern-Rogätz",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-29",null,null,3.4,1]
[null,"DB InfraGO AG","442BB-003","Hamburg - Magdeburg","<>","Magdeburg Hbf","Magdeburg Hbf",2026,2026,2,2,"2026-01-10","22:00:00","2026-01-11","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-02",null,null,6.7,1]
[null,"DB InfraGO AG","44467-003","Hamburg - Magdeburg","<>","Wolmirstedt","Wolmirstedt",2026,2026,4,4,"2026-01-23","22:00:00","2026-01-24","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,5.6,1]
[null,"DB InfraGO AG","48735-008","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Stendal Gbf",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,5.6,1]
[null,"DB InfraGO AG","49853-005","Hamburg - Magdeburg","<>","Magdeburg Hbf","Magdeburg-Neustadt",2026,2026,6,6,"2026-02-07","22:00:00","2026-02-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,6.7,1]
[null,"DB InfraGO AG","5B60B-003","Hamburg - Magdeburg","<","Magdeburg-Neustadt","Magdeburg Hbf",2025,2025,51,51,"2025-12-16","06:00:00","2025-12-17","04:30:00","0d, 22h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2025-08-18",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","43DCA-006","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg Süderelbbrücke",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,4.5,1]
[null,"DB InfraGO AG","46FA0-004","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg-Wilhelmsburg Abzw",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,5.6,1]
[null,"DB InfraGO AG","47C06-001","Hamburg - Magdeburg","<","Meckelfeld","Maschen Rbf (Mswf)",2026,2026,10,10,"2026-03-06","07:00:00","2026-03-06","14:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-03",null,null,5,1]
[null,"DB InfraGO AG","50C68-001","Hamburg - Magdeburg",">","Hamburg-Harburg","Hamburg Süderelbbrücke",2026,2026,5,5,"2026-01-29","22:00:00","2026-01-30","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-23",null,null,4.5,1]
[null,"DB InfraGO AG","1E2B5-002","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","21:00:00","2026-10-31","05:00:00","14d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","35B1D-009","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,47,47,"2026-11-20","22:00:00","2026-11-21","04:00:00","0d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,5.6,1]
[null,"DB InfraGO AG","43DD0-002","Hamburg - Magdeburg","<>","Maschen Rbf (Mswf)","Meckelfeld",2026,2026,2,2,"2026-01-09","07:00:00","2026-01-09","14:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,5,1]
[null,"DB InfraGO AG","44278-005","Hamburg - Magdeburg","<>","Osterburg","Stendal Gbf",2026,2026,2,2,"2026-01-06","22:00:00","2026-01-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-29",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","48735-002","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Borstel (Kr Stendal)",2026,2026,6,6,"2026-02-06","22:00:00","2026-02-07","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,5.6,1]
[null,"DB InfraGO AG","20EDE-005","Hamburg - Magdeburg","<>","Wieren","Wieren",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","36807-001","Hamburg - Magdeburg","<>","Stendal Gbf","Hohenwulsch",2026,2026,4,6,"2026-01-19","00:50:00","2026-02-08","04:30:00","20d, 3h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","442B0-005","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Stendal Gbf",2026,2026,2,2,"2026-01-09","22:00:00","2026-01-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-29",null,null,5.6,1]
[null,"DB InfraGO AG","44784-003","Hamburg - Magdeburg","<>","Hohenwulsch","Rademin",2026,2026,3,3,"2026-01-14","22:00:00","2026-01-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,3.4,1]
[null,"DB InfraGO AG","4B5A5-003","Hamburg - Magdeburg","<>","Schnega","Schnega",2026,2026,5,5,"2026-01-30","22:00:00","2026-01-31","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,5.6,1]
[null,"DB InfraGO AG","20A85-014","Hamburg - Magdeburg","<>","Stendal Hauptbahnhof","Tangermünde",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,7,1]
[null,"DB InfraGO AG","43F0A-002","Hamburg - Magdeburg","<","Fischerhof","Uelzen",2026,2026,4,4,"2026-01-23","22:00:00","2026-01-24","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-05-15",null,null,5.6,1]
[null,"DB InfraGO AG","35694-002","Hamburg - Magdeburg","<>","Hamburg-Wilhelmsburg Abzw","Hamburg-Veddel",2026,2026,49,49,"2026-12-01","01:00:00","2026-12-03","04:00:00","2d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-23",null,null,"2,3,4",1]
[null,"DB InfraGO AG","43E66-002","Hamburg - Magdeburg",">","Hamburg-Wilhelmsburg Abzw","Hamburg Hbf",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-16",null,null,4.5,1]
[null,"DB InfraGO AG","43EA3-003","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg-Veddel",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-17",null,null,5.6,1]
[null,"DB InfraGO AG","47B3E-002","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg-Harburg",2026,2026,6,6,"2026-02-03","22:00:00","2026-02-04","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4E512-004","Hamburg - Magdeburg",">","Hamburg-Wilhelmsburg Abzw","Hamburg Hbf",2026,2026,8,8,"2026-02-19","22:00:00","2026-02-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-27",null,null,4.5,1]
[null,"DB InfraGO AG","4E6E6-005","Hamburg - Magdeburg","<>","Hamburg-Harburg","Hamburg-Harburg",2026,2026,8,9,"2026-02-22","22:00:00","2026-02-23","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,1.7,1]
[null,"DB InfraGO AG","50C66-004","Hamburg - Magdeburg","<>","Hamburg-Wilhelmsburg Abzw","Hamburg Hbf",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,3.4,1]
[null,"DB InfraGO AG","5C152-001","Hannover - Magdeburg","<>","Magdeburg-Rothensee","Magdeburg-Rothensee",2025,2025,51,51,"2025-12-15","08:00:00","2025-12-15","16:00:00","0d, 8h","Periodical","Signal",null,null,null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-09-01",null,null,1,1]
[null,"DB InfraGO AG","4A92F-008","Hannover - Magdeburg","<>","Braunschweig Schmiedekamp","Braunschweig Rbf",2026,2026,9,9,"2026-02-28","22:00:00","2026-03-01","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,6.7,1]
[null,"DB InfraGO AG","48EDA-002","Hannover - Magdeburg","<>","Hannover-Waldhausen","Hannover-Wülfel",2026,2026,10,10,"2026-03-07","23:30:00","2026-03-08","07:30:00","0d, 8h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,6.7,1]
[null,"DB InfraGO AG","1A813-010","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-09-26",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-001","Hannover - Magdeburg","<>","Schandelah","Braunschweig-Buchhorst",2026,2026,34,34,"2026-08-17","23:10:00","2026-08-18","04:50:00","0d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-05",null,null,1.2,1]
[null,"DB InfraGO AG","3B7EB-005","Hannover - Magdeburg","<>","Schandelah","Schandelah",2026,2026,33,33,"2026-08-15","20:00:00","2026-08-16","08:00:00","0d, 12h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,6.7,1]
[null,"DB InfraGO AG","3BE29-005","Hannover - Magdeburg","<>","Weddel (Braunschw)","Frellstedt",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,3.4,1]
[null,"DB InfraGO AG","460DD-002","Hannover - Magdeburg","<","Frellstedt","Königslutter",2026,2026,3,3,"2026-01-12","22:00:00","2026-01-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-10",null,null,1.2,1]
[null,"DB InfraGO AG","460FC-002","Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2026,2026,3,3,"2026-01-14","22:00:00","2026-01-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-04-10",null,null,3.4,1]
[null,"DB InfraGO AG","4A8F3-003","Hannover - Magdeburg",">","Braunschweig Hbf","Braunschweig Schmiedekamp",2026,2026,9,9,"2026-02-27","22:00:00","2026-02-28","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-13",null,null,5.6,1]
[null,"DB InfraGO AG","4C2D4-002","Hannover - Magdeburg","<","Frellstedt","Königslutter",2026,2026,7,7,"2026-02-09","22:00:00","2026-02-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-06-13",null,null,1.2,1]
[null,"DB InfraGO AG","4C2EC-002","Hannover - Magdeburg","<","Schandelah","Braunschweig Schmiedekamp",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-06-13",null,null,3.4,1]
[null,"DB InfraGO AG","50000-008","Hannover - Magdeburg","<>","Weddel (Braunschw)","Weddel (Braunschw)",2026,2026,3,3,"2026-01-12","00:15:00","2026-01-12","02:30:00","0d, 2h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,1,1]
[null,"DB InfraGO AG","3BD81-004","Hannover - Magdeburg","<>","Braunschweig Lünischteich","Braunschweig Schmiedekamp",2025,2025,51,51,"2025-12-16","22:00:00","2025-12-17","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4C2E0-004","Hannover - Magdeburg","<>","Braunschweig Lünischteich","Braunschweig Schmiedekamp",2026,2026,7,7,"2026-02-10","22:00:00","2026-02-11","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","1A813-029","Hannover - Magdeburg","<>","Helmstedt","Harbke",2026,2026,35,35,"2026-08-28","15:00:00","2026-08-28","21:00:00","0d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,5,1]
[null,"DB InfraGO AG","1C2F9-002","Hannover - Magdeburg","<>","Wefensleben","Wefensleben",2026,2026,33,35,"2026-08-14","23:00:00","2026-08-28","05:00:00","13d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CBF8-005","Hannover - Magdeburg","<>","Wefensleben","Wefensleben",2026,2026,41,42,"2026-10-09","23:59:00","2026-10-12","03:00:00","2d, 3h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-05",null,null,"5,6,7",1]
[null,"DB InfraGO AG","4A65D-004","Hannover - Magdeburg",">","Helmstedt","Harbke",2026,2026,5,5,"2026-01-31","22:00:00","2026-02-01","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2025-06-13",null,null,6.7,1]
[null,"DB InfraGO AG","4C2D4-006","Hannover - Magdeburg","<>","Harbke","Helmstedt",2026,2026,7,7,"2026-02-09","22:00:00","2026-02-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,1.2,1]
[null,"DB InfraGO AG","43DA4-008","Hannover - Magdeburg","<>","Groß Gleidingen Ostkopf","Beddingen",2026,2026,2,2,"2026-01-06","22:00:00","2026-01-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-25",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4E4BE-002","Hannover - Magdeburg","<","Groß Gleidingen","Groß Gleidingen",2026,2026,8,8,"2026-02-19","22:00:00","2026-02-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","4E4BE-006","Hannover - Magdeburg","<>","Groß Gleidingen","Groß Gleidingen",2026,2026,8,8,"2026-02-19","22:00:00","2026-02-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","33429-014","Hannover - Magdeburg","<>","Hamburg Unterelbe Seehafen","Hamburg Unterelbe",2026,2026,50,50,"2026-12-07","03:00:00","2026-12-07","06:00:00","0d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-01",null,null,1,1]
[null,"DB InfraGO AG","1A784-015","Hannover - Magdeburg","<>","Vechelde","Vechelde",2026,2026,35,35,"2026-08-27","05:00:00","2026-08-28","21:00:00","1d, 16h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-04-02",null,null,4.5,1]
[null,"DB InfraGO AG","1A7F1-009","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,42,43,"2026-10-17","23:05:00","2026-10-19","05:00:00","1d, 5h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-12",null,null,6.7,1]
[null,"DB InfraGO AG","3BD08-008","Hannover - Magdeburg","<>","Lehrte","Lehrte",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-07",null,null,1.2,1]
[null,"DB InfraGO AG","43E14-005","Hannover - Magdeburg","<>","Lehrte","Peine Gbf",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-25",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","47BEB-006","Hannover - Magdeburg","<>","Lehrte West","Lehrte",2026,2026,6,6,"2026-02-05","22:00:00","2026-02-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","4A77F-001","Hannover - Magdeburg",">","Vechelde","Groß Gleidingen",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-13",null,null,4.5,1]
[null,"DB InfraGO AG","4A8E6-002","Hannover - Magdeburg",">","Hämelerwald","Peine",2026,2026,5,5,"2026-01-30","22:00:00","2026-01-31","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2025-06-10",null,null,5.6,1]
[null,"DB InfraGO AG","4A93B-001","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,9,9,"2026-02-28","22:00:00","2026-03-01","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-06-11",null,null,6.7,1]
[null,"DB InfraGO AG","4C37C-003","Hannover - Magdeburg","<>","Groß Gleidingen","Peine",2026,2026,7,7,"2026-02-09","22:00:00","2026-02-10","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,1.2,1]
[null,"DB InfraGO AG","4D416-002","Hannover - Magdeburg","<>","Hannover Hbf","Lehrte",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,3.4,1]
[null,"DB InfraGO AG","43E97-003","Hannover - Magdeburg","<>","Hannover Hbf","Hannover-Waldhausen",2026,2026,3,4,"2026-01-18","22:00:00","2026-01-19","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-08",null,null,1.7,1]
[null,"DB InfraGO AG","4E596-001","Hannover - Magdeburg","<","Weetzen","Hannover-Linden",2026,2026,8,9,"2026-02-22","22:00:00","2026-02-23","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-06-16",null,null,1.7,1]
[null,"DB InfraGO AG","4A922-001","Hannover - Magdeburg",">","Hannover Hbf","Wunstorf",2026,2026,5,5,"2026-01-31","22:00:00","2026-02-01","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",7,7",null,null,null,"N",null,"2025-06-11",null,null,6.7,1]
[null,"DB InfraGO AG","43F10-001","Hannover - Magdeburg","<","Seelze Ost","Hannover-Hainholz",2026,2026,4,5,"2026-01-25","22:00:00","2026-01-26","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"10,,",null,null,null,"N",null,"2025-04-08",null,null,1.7,1]
[null,"DB InfraGO AG","48ED9-003","Hannover - Magdeburg","<>","Hannover-Wülfel","Hannover-Waldheim",2026,2026,6,6,"2026-02-07","23:30:00","2026-02-08","07:30:00","0d, 8h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,6.7,1]
[null,"DB InfraGO AG","3BCFC-005","Hannover - Magdeburg","<>","Helmstedt DB-Grenze","Helmstedt",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-10",null,null,1.2,1]
[null,"DB InfraGO AG","3B7EB-003","Hannover - Magdeburg","<","Sandbach","Weddel (Braunschw)",2026,2026,33,33,"2026-08-14","23:35:00","2026-08-15","07:30:00","0d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-04",null,null,5.6,1]
[null,"DB InfraGO AG","4A579-002","Hannover - Magdeburg","<>","Weddel (Braunschw)","Sülfeld",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,1.2,1]
[null,"DB InfraGO AG","50000-003","Hannover - Magdeburg","<>","Fallersleben","Weddel (Braunschw)",2026,2026,2,3,"2026-01-11","22:00:00","2026-01-12","00:15:00","0d, 2h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,1.7,1]
[null,"DB InfraGO AG","4B3B5-002","Magdeburg - Falkenberg","<>","Biederitz","Gommern",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,1.2,1]
[null,"DB InfraGO AG","33951-007","Magdeburg - Falkenberg","<>","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,42,42,"2026-10-14","18:00:00","2026-10-16","06:00:00","1d, 12h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-18",null,null,3.4,1]
[null,"DB InfraGO AG","3D120-007","Magdeburg - Falkenberg","<>","Elsterwerda-Biehla","Falkenberg (Elster) unt Bf Stw W 17",2025,2025,51,51,"2025-12-15","22:00:00","2025-12-16","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-20",null,null,1.2,1]
[null,"DB InfraGO AG","3D199-002","Magdeburg - Falkenberg","<>","Annaburg","Falkenberg (Elster) unt Bf Stw W 26",2025,2025,51,51,"2025-12-17","22:00:00","2025-12-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-17",null,null,3.4,1]
[null,"DB InfraGO AG","442C8-002","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,3,3,"2026-01-12","22:00:00","2026-01-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,1.2,1]
[null,"DB InfraGO AG","442D0-001","Magdeburg - Falkenberg","<","Lutherstadt Wittenberg-Piesteritz","Jessen (Elster)",2026,2026,3,3,"2026-01-12","22:00:00","2026-01-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,1.2,1]
[null,"DB InfraGO AG","443DB-004","Magdeburg - Falkenberg","<>","Fermerswalde","Fermerswalde",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-04",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","442D8-008","Magdeburg - Falkenberg","<>","Lutherstadt Wittenberg-Piesteritz","Lutherstadt Wittenberg-Piesteritz Werkbf",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4B539-005","Magdeburg - Falkenberg","<>","Lutherstadt Wittenberg Hbf","Coswig (Anh) Gbf",2026,2026,5,5,"2026-01-29","22:00:00","2026-01-30","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-25",null,null,4.5,1]
[null,"DB InfraGO AG","4B58D-004","Magdeburg - Falkenberg","<>","Falkenberg (Elster) unt Bf Pbf/Stw B 20","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,5,5,"2026-01-30","22:00:00","2026-01-31","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-27",null,null,5.6,1]
[null,"DB InfraGO AG","51019-003","Magdeburg - Falkenberg","<>","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2025,2025,51,51,"2025-12-19","01:15:00","2025-12-19","04:00:00","0d, 2h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,5,1]
[null,"DB InfraGO AG","5CAD8-012","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,19,19,"2026-05-08","10:00:00","2026-05-08","14:00:00","0d, 4h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-09-03",null,null,5,1]
[null,"DB InfraGO AG","5CAD8-018","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,20,20,"2026-05-11","22:00:00","2026-05-12","04:00:00","0d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-03",null,null,1,1]
[null,"DB InfraGO AG","5CAD8-028","Magdeburg - Falkenberg","<>","Coswig (Anh) Gbf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,32,32,"2026-08-04","06:00:00","2026-08-04","22:00:00","0d, 16h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-09-03",null,null,2,1]
[null,"DB InfraGO AG","22420-008","Magdeburg - Falkenberg","<>","Lu Wittenberg-Piesteritz Werkbf Ostseite","Lu Wittenberg-Piesteritz Werkbf Ostseite",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,5.6,1]
[null,"DB InfraGO AG","1B3BA-001","Magdeburg - Falkenberg","<>","Magdeburg-Sudenburg","Magdeburg-Sudenburg",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","443ED-001","Magdeburg - Falkenberg","<","Magdeburg-Neustadt","Biederitz",2026,2026,3,3,"2026-01-14","22:00:00","2026-01-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-05-02",null,null,3.4,1]
[null,"DB InfraGO AG","49853-001","Magdeburg - Falkenberg","<>","Magdeburg-Neustadt","Magdeburg Hbf",2026,2026,6,6,"2026-02-07","22:00:00","2026-02-08","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,6.7,1]
[null,"DB InfraGO AG","4B55E-001","Magdeburg - Falkenberg",">","Magdeburg-Sudenburg","Wellen (b Magdeburg)",2026,2026,9,9,"2026-02-26","22:00:00","2026-02-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-07-09",null,null,4.5,1]
[null,"DB InfraGO AG","4B629-001","Magdeburg - Falkenberg",">","Wellen (b Magdeburg)","Eilsleben (b Magdeburg)",2026,2026,5,5,"2026-01-31","22:00:00","2026-02-01","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-06-19",null,null,6.7,1]
[null,"DB InfraGO AG","5B60B-001","Magdeburg - Falkenberg","<","Magdeburg Hbf","Magdeburg-Neustadt",2025,2025,51,51,"2025-12-16","06:00:00","2025-12-17","04:30:00","0d, 22h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-08-18",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4447D-004","Magdeburg - Falkenberg","<>","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,4,4,"2026-01-24","22:00:00","2026-01-25","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-02",null,null,6.7,1]
[null,"DB InfraGO AG","49853-004","Magdeburg - Falkenberg","<>","Magdeburg Hbf","Magdeburg-Neustadt",2026,2026,6,6,"2026-02-07","22:00:00","2026-02-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-04",null,null,6.7,1]
[null,"DB InfraGO AG","44419-008","Magdeburg - Falkenberg","<>","Rodleben","Rodleben",2026,2026,3,3,"2026-01-17","22:00:00","2026-01-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,6.7,1]
[null,"DB InfraGO AG","22420-003","Magdeburg - Falkenberg","<>","Meinsdorf","Lutherstadt Wittenberg Hbf",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,5.6,1]
[null,"DB InfraGO AG","1BF59-004","Rostock-Berlin-Dresden","<>","Radebeul Abzw Az","Radebeul Nord",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,4.5,1]
[null,"DB InfraGO AG","3DBB3-014","Rostock-Berlin-Dresden","<>","Bergfelde Ost","Hohen Neuend Sw",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-15",null,null,6.7,1]
[null,"DB InfraGO AG","4FF33-007","Rostock-Berlin-Dresden","<>","Bergfelde Ost","Hohen Neuend Sw",2026,2026,7,7,"2026-02-13","22:00:00","2026-02-14","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,5.6,1]
[null,"DB InfraGO AG","4AB35-015","Rostock-Berlin-Dresden","<>","Eichgestell Nord","Berlin Stadtforst",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,3.4,1]
[null,"DB InfraGO AG","358B0-019","Rostock-Berlin-Dresden","<>","Berlin Ostendgestell","Berlin Eichgestell",2026,2026,25,25,"2026-06-16","02:00:00","2026-06-16","04:00:00","0d, 2h","Periodical","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-10-09",null,null,2,1]
[null,"DB InfraGO AG","4E88A-011","Rostock-Berlin-Dresden","<>","Berlin Ostendgestell","Berlin Eichgestell",2026,2026,8,8,"2026-02-16","22:00:00","2026-02-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-18",null,null,1.2,1]
[null,"DB InfraGO AG","2A199-002","Rostock-Berlin-Dresden","<>","Berlin-Karow Ost","Berlin-Karow",2026,2026,19,21,"2026-05-08","22:00:00","2026-05-18","04:00:00","9d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","47D25-003","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz Ost","Biesdorfer Kreuz Mitte",2026,2026,6,6,"2026-02-03","22:00:00","2026-02-04","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-18",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4AB36-014","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz Süd","Biesdorfer Kreuz Süd-Ost",2026,2026,9,9,"2026-02-25","22:00:00","2026-02-26","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,3.4,1]
[null,"DB InfraGO AG","1DC42-010","Rostock-Berlin-Dresden","<>","Dresden-Neustadt","Dresden-Neustadt Gbf",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-26",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","34E88-003","Rostock-Berlin-Dresden","<>","Glasower Damm Ost","Glasower Damm Ost",2026,2026,2,2,"2026-01-07","00:00:00","2026-01-07","04:00:00","0d, 4h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-26",null,null,3,1]
[null,"DB InfraGO AG","4ABDE-004","Rostock-Berlin-Dresden","<","Glasower Damm Ost","Flughafen BER F-Bahn",2026,2026,9,9,"2026-02-23","22:00:00","2026-02-24","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2025-06-05",null,null,1.2,1]
[null,"DB InfraGO AG","4FB89-004","Rostock-Berlin-Dresden","<>","Glasower Damm Ost","Blankenfelde (Kr Teltow-Fläming)",2026,2026,8,8,"2026-02-19","22:00:00","2026-02-20","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-11",null,null,4.5,1]
[null,"DB InfraGO AG","35014-003","Rostock-Berlin-Dresden","<>","Grünauer Kreuz West","Grünauer Kreuz Süd",2026,2026,9,10,"2026-02-24","22:00:00","2026-03-03","22:00:00","7d, 0h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","4402B-007","Rostock-Berlin-Dresden","<>","Lalendorf Ost","Lalendorf Ost",2026,2026,4,4,"2026-01-19","22:00:00","2026-01-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-14",null,null,1.2,1]
[null,"DB InfraGO AG","1FB4B-010","Rostock-Berlin-Dresden","<","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2026,2026,9,10,"2026-02-28","06:00:00","2026-03-03","18:00:00","3d, 12h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2025-06-02",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG",4.4279999999999998E-4,"Rostock-Berlin-Dresden","<>","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden)",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4,1]
[null,"DB InfraGO AG","5C890-002","Rostock-Berlin-Dresden","<>","Rostock Seehafen","Rostock Seehafen",2025,2026,50,27,"2025-12-14","00:01:00","2026-07-03","23:59:00","201d, 22h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-08-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20EC7-005","Rostock-Berlin-Dresden","<>","Bentwisch","Rostock Seehafen Süd",2026,2026,5,18,"2026-01-31","07:00:00","2026-04-30","16:00:00","89d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2025-09-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20EC7-009","Rostock-Berlin-Dresden","<>","Bentwisch","Rostock Seehafen Süd",2026,2026,5,18,"2026-01-31","07:00:00","2026-04-30","16:00:00","89d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","358B0-008","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Berlin Eichgestell",2026,2026,25,25,"2026-06-15","02:00:00","2026-06-15","04:00:00","0d, 2h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-10-09",null,null,1,1]
[null,"DB InfraGO AG","358B0-018","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Eichgestell Nord",2026,2026,25,25,"2026-06-16","02:00:00","2026-06-16","04:00:00","0d, 2h","Periodical","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-10-09",null,null,2,1]
[null,"DB InfraGO AG","3656D-003","Rostock-Berlin-Dresden","<>","Eichgestell Nord","Berlin Eichgestell",2026,2026,48,48,"2026-11-29","20:00:00","2026-11-29","23:00:00","0d, 3h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-13",null,null,7,1]
[null,"DB InfraGO AG","3656D-033","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Berlin Eichgestell",2026,2026,50,50,"2026-12-07","02:00:00","2026-12-07","04:00:00","0d, 2h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-13",null,null,1,1]
[null,"DB InfraGO AG","3652C-019","Rostock-Berlin-Dresden",">","Biesdorfer Kreuz Mitte","Biesdorfer Kreuz Nord",2026,2026,45,45,"2026-11-05","03:00:00","2026-11-05","04:45:00","0d, 1h","Periodical","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,4,1]
[null,"DB InfraGO AG","3652C-035","Rostock-Berlin-Dresden","<","Biesdorfer Kreuz Nord","Biesdorfer Kreuz Mitte",2026,2026,46,46,"2026-11-09","23:20:00","2026-11-10","05:20:00","0d, 6h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-30",null,null,1.2,1]
[null,"DB InfraGO AG","4AB1D-001","Rostock-Berlin-Dresden",">","Biesdorfer Kreuz Nord","Biesdf Kr N Strw",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-04",null,null,3.4,1]
[null,"DB InfraGO AG","4AB35-018","Rostock-Berlin-Dresden",">","Berlin Eichgestell","Biesdorfer Kreuz Nord",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,3.4,1]
[null,"DB InfraGO AG","4C508-001","Rostock-Berlin-Dresden","<","Biesdf Kr N Strw","Biesdorfer Kreuz Mitte",2026,2026,7,7,"2026-02-13","22:00:00","2026-02-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-16",null,null,5.6,1]
[null,"DB InfraGO AG","4ABEA-002","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Berlin Stadtforst",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","36B38-002","Rostock-Berlin-Dresden",">","Berlin Ostendgestell","Berlin Eichgestell",2026,2026,50,50,"2026-12-07","23:30:00","2026-12-08","03:30:00","0d, 4h","Periodical","Maintenance",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-13",null,null,1.2,1]
[null,"DB InfraGO AG","44296-001","Rostock-Berlin-Dresden","<>","Lutherstadt Wittenberg Hbf","Radis",2026,2026,2,2,"2026-01-08","22:00:00","2026-01-09","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-22",null,null,4.5,1]
[null,"DB InfraGO AG","484FF-001","Rostock-Berlin-Dresden","<>","Lutherstadt Wittenberg Hbf","Radis",2026,2026,10,10,"2026-03-05","22:00:00","2026-03-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-07-01",null,null,4.5,1]
[null,"DB InfraGO AG","48766-001","Rostock-Berlin-Dresden",">","Niedergörsdorf","Lutherstadt Wittenberg Hbf",2026,2026,10,10,"2026-03-07","22:00:00","2026-03-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-25",null,null,6.7,1]
[null,"DB InfraGO AG","4B635-004","Rostock-Berlin-Dresden","<>","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2026,2026,5,5,"2026-01-31","22:00:00","2026-02-01","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-25",null,null,6.7,1]
[null,"DB InfraGO AG","5C944-004","Rostock-Berlin-Dresden","<>","Berlin-Blankenburg","Berlin-Karow West",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","34E8E-001","Rostock-Berlin-Dresden","<>","Oranienburg","Oranienburg",2026,2026,37,39,"2026-09-07","07:00:00","2026-09-25","21:00:00","18d, 14h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3DBB3-012","Rostock-Berlin-Dresden","<>","Nassenheide","Nassenheide",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-15",null,null,6.7,1]
[null,"DB InfraGO AG","44005-001","Rostock-Berlin-Dresden","<>","Gransee","Gransee",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-09",null,null,5.6,1]
[null,"DB InfraGO AG","4AB65-008","Rostock-Berlin-Dresden",">","Birkenwerder (b Berlin)","Oranienburg",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,1.2,1]
[null,"DB InfraGO AG","4AB66-009","Rostock-Berlin-Dresden","<>","Birkenwerder (b Berlin)","Oranienburg",2026,2026,9,9,"2026-02-23","22:00:00","2026-02-24","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,1.2,1]
[null,"DB InfraGO AG","4AD6A-001","Rostock-Berlin-Dresden",">","Nassenheide","Gransee",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-30",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4AD8E-002","Rostock-Berlin-Dresden",">","Fürstenberg (Havel)","Fürstenberg (Havel)",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-30",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4C616-001","Rostock-Berlin-Dresden","<>","Birkenwerder (b Berlin)","Oranienburg",2026,2026,7,7,"2026-02-14","22:00:00","2026-02-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-05",null,null,6.7,1]
[null,"DB InfraGO AG","4C83E-003","Rostock-Berlin-Dresden","<>","Neustrelitz Hbf","Neustrelitz Hbf",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,4.5,1]
[null,"DB InfraGO AG","4C87A-001","Rostock-Berlin-Dresden","<>","Löwenberg (Mark)","Löwenberg (Mark)",2026,2026,7,7,"2026-02-14","22:00:00","2026-02-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,6.7,1]
[null,"DB InfraGO AG","5DB2C-003","Rostock-Berlin-Dresden","<>","Oranienburg","Oranienburg",2026,2026,37,50,"2026-09-07","07:00:00","2026-12-12","21:00:00","96d, 15h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-10-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CCC5-004","Rostock-Berlin-Dresden","<>","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","43FC5-003","Rostock-Berlin-Dresden",">","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,3,3,"2026-01-12","22:00:00","2026-01-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,1.2,1]
[null,"DB InfraGO AG","23B5A-012","Rostock-Berlin-Dresden","<>","Berlin-Karow","Berlin-Karow West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3652C-001","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2026,2026,45,45,"2026-11-03","23:00:00","2026-11-04","05:10:00","0d, 6h","Periodical","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-13",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4C508-010","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz West","Biesdorfer Kreuz Nord",2026,2026,7,7,"2026-02-13","22:00:00","2026-02-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,5.6,1]
[null,"DB InfraGO AG","46E75-003","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz Nord","Berlin-Rummelsburg (Rgbv)",2026,2026,3,3,"2026-01-15","22:00:00","2026-01-16","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,4.5,1]
[null,"DB InfraGO AG","4ABEA-001","Rostock-Berlin-Dresden","<>","Berlin-Adlershof Abzw","Berlin Wendenheide",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","1F548-006","Rostock-Berlin-Dresden","<>","Dresden-Altstadt","Dresden Hbf",2026,2026,8,11,"2026-02-16","04:00:00","2026-03-15","06:00:00","27d, 2h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2025-07-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","4C49C-003","Rostock-Berlin-Dresden","<>","Berlin Nordost","Berlin-Hohenschönhausen",2026,2026,7,7,"2026-02-13","08:00:00","2026-02-13","15:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,5,1]
[null,"DB InfraGO AG","33A3C-002","Rostock-Berlin-Dresden","<>","Biesdf Kr N Strw","Berlin-Hohenschönhausen",2026,2026,8,11,"2026-02-19","23:55:00","2026-03-11","04:00:00","19d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","46A12-002","Rostock-Berlin-Dresden","<","Berlin-Hohenschönhausen","Biesdorfer Kreuz Mitte",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-16",null,null,5.6,1]
[null,"DB InfraGO AG","23B5A-002","Rostock-Berlin-Dresden","<>","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2D3-002","Rostock-Berlin-Dresden","<","Elsterwerda","Elsterwerda",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-15",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1E1BD-001","Rostock-Berlin-Dresden","<>","Zossen","Wünsdorf-Waldstadt",2026,2026,1,2,"2026-01-04","21:00:00","2026-01-05","05:00:00","0d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,1.7,1]
[null,"DB InfraGO AG","2BDB5-005","Rostock-Berlin-Dresden","<>","Brenitz-Sonnewalde","Brenitz-Sonnewalde",2026,2026,2,3,"2026-01-11","22:00:00","2026-01-13","04:50:00","1d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-09-19",null,null,1.7,1]
[null,"DB InfraGO AG","32390-002","Rostock-Berlin-Dresden","<>","Rückersdorf                    (Niederl)","Elsterwerda",2026,2026,6,6,"2026-02-03","01:00:00","2026-02-03","04:00:00","0d, 3h","Periodical","Maintenance","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,2,1]
[null,"DB InfraGO AG","32390-009","Rostock-Berlin-Dresden",">","Hohenleipisch","Hohenleipisch Betriebsbahnhof",2026,2026,6,6,"2026-02-04","04:00:00","2026-02-04","05:00:00","0d, 1h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-06-16",null,null,3,1]
[null,"DB InfraGO AG","337F2-011","Rostock-Berlin-Dresden","<>","Elsterwerda","Elsterwerda",2026,2026,24,24,"2026-06-09","00:00:00","2026-06-10","04:00:00","1d, 4h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-04-30",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4405B-003","Rostock-Berlin-Dresden","<","Wünsdorf-Waldstadt","Wünsdorf-Waldstadt",2026,2026,4,4,"2026-01-24","22:00:00","2026-01-25","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-14",null,null,6.7,1]
[null,"DB InfraGO AG","4405C-004","Rostock-Berlin-Dresden",">","Rangsdorf","Zossen",2026,2026,4,4,"2026-01-23","22:00:00","2026-01-24","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,",2,2",null,null,null,"N",null,"2025-04-14",null,null,5.6,1]
[null,"DB InfraGO AG","4445B-007","Rostock-Berlin-Dresden","<>","Doberlug-Kirchhain ob Bf","Elsterwerda",2026,2026,4,4,"2026-01-22","22:00:00","2026-01-23","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,4.5,1]
[null,"DB InfraGO AG","46D96-005","Rostock-Berlin-Dresden",">","Luckau-Uckro","Luckau-Uckro",2026,2026,2,2,"2026-01-05","22:00:00","2026-01-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-01",null,null,1.2,1]
[null,"DB InfraGO AG","46DAA-006","Rostock-Berlin-Dresden",">","Doberlug-Kirchhain Nord","Doberlug-Kirchhain ob Bf",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-30",null,null,3.4,1]
[null,"DB InfraGO AG","47232-001","Rostock-Berlin-Dresden","<","Blankenfelde (Kr Teltow-Fläming)","Berlin-Marienfelde Gbf",2026,2026,4,4,"2026-01-22","22:00:00","2026-01-23","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-14",null,null,4.5,1]
[null,"DB InfraGO AG","47D62-004","Rostock-Berlin-Dresden",">","Rückersdorf                    (Niederl)","Rückersdorf                    (Niederl)",2026,2026,10,10,"2026-03-04","22:00:00","2026-03-05","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,3.4,1]
[null,"DB InfraGO AG","47D6D-006","Rostock-Berlin-Dresden",">","Baruth (Mark)","Golßen (Niederlausitz)",2026,2026,6,6,"2026-02-03","22:00:00","2026-02-04","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","47DC2-004","Rostock-Berlin-Dresden","<","Doberlug-Kirchhain ob Bf","Walddrehna",2026,2026,10,10,"2026-03-03","22:00:00","2026-03-04","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","49561-001","Rostock-Berlin-Dresden",">","Golßen (Niederlausitz)","Walddrehna",2026,2026,10,10,"2026-03-02","22:00:00","2026-03-03","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-18",null,null,1.2,1]
[null,"DB InfraGO AG","4E956-002","Rostock-Berlin-Dresden","<","Doberlug-Kirchhain Nord","Brenitz-Sonnewalde",2026,2026,8,8,"2026-02-21","22:00:00","2026-02-22","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-17",null,null,6.7,1]
[null,"DB InfraGO AG","4E962-004","Rostock-Berlin-Dresden",">","Luckau-Uckro","Brenitz-Sonnewalde",2026,2026,8,8,"2026-02-19","21:00:00","2026-02-20","05:00:00","0d, 8h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-17",null,null,4.5,1]
[null,"DB InfraGO AG","4FB89-001","Rostock-Berlin-Dresden","<","Blankenfelde (Kr Teltow-Fläming)","Berlin-Marienfelde Gbf",2026,2026,8,8,"2026-02-19","22:00:00","2026-02-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-06-11",null,null,4.5,1]
[null,"DB InfraGO AG","4853D-005","Rostock-Berlin-Dresden","<>","Coswig (bei Dresden) Stw 1","Meißen Triebischtal DB-Grenze",2026,2026,10,10,"2026-03-06","22:00:00","2026-03-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-28",null,null,5.6,1]
[null,"DB InfraGO AG","47D62-009","Rostock-Berlin-Dresden","<>","Doberlug-Kirchhain unt Bf","Doberlug-Kirchhain ob Bf",2026,2026,10,10,"2026-03-04","22:00:00","2026-03-05","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,3.4,1]
[null,"DB InfraGO AG","1F581-007","Rostock-Berlin-Dresden","<>","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-12","21:00:00","2026-03-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-07-08",null,null,4.5,1]
[null,"DB InfraGO AG","1F6CB-001","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden-Altstadt",2026,2026,36,38,"2026-08-31","18:00:00","2026-09-14","05:00:00","13d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F543-011","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden-Altstadt",2026,2026,8,8,"2026-02-16","00:00:00","2026-02-16","04:00:00","0d, 4h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-09",null,null,1,1]
[null,"DB InfraGO AG","1DD70-001","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden Hbf",2026,2026,3,3,"2026-01-12","21:00:00","2026-01-15","04:00:00","2d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,"1,2,3",1]
[null,"DB InfraGO AG","327BA-001","Rostock-Berlin-Dresden","<","Dresden Hbf","Dresden Hbf",2026,2026,5,5,"2026-01-31","20:00:00","2026-02-01","04:00:00","0d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-06-10",null,null,6.7,1]
[null,"DB InfraGO AG","1DD70-023","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden Hbf",2026,2026,5,5,"2026-01-29","04:00:00","2026-01-30","04:30:00","1d, 0h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-04",null,null,4.5,1]
[null,"DB InfraGO AG","1FA4A-006","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG",44.28,"Rostock-Berlin-Dresden",">","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,2,2,"2026-01-07","22:00:00","2026-01-08","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4,1]
[null,"DB InfraGO AG","1F528-009","Rostock-Berlin-Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-14","12:00:00","5d, 8h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-07-09",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","20997-008","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-05-15",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","24FD2-002","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,35,35,"2026-08-24","07:30:00","2026-08-28","14:30:00","4d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,null,null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1BF59-001","Rostock-Berlin-Dresden","<>","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,40,41,"2026-10-04","20:00:00","2026-10-05","04:00:00","0d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,1.7,1]
[null,"DB InfraGO AG","1BF59-010","Rostock-Berlin-Dresden","<>","Weinböhla","Weinböhla",2026,2026,48,50,"2026-11-27","08:00:00","2026-12-11","16:00:00","14d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1FA4A-007","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FB4B-006","Rostock-Berlin-Dresden",">","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-02",null,null,"2,3,4,5,6",1]
[null,"DB InfraGO AG","20997-017","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2025-05-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","32138-008","Rostock-Berlin-Dresden",">","Cossebaude","Cossebaude",2026,2026,5,5,"2026-01-27","21:00:00","2026-01-28","05:00:00","0d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-05-29",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","32168-006","Rostock-Berlin-Dresden","<","Radebeul-Naundorf","Cossebaude",2026,2026,5,5,"2026-01-29","23:30:00","2026-01-30","05:00:00","0d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2025-05-29",null,null,4.5,1]
[null,"DB InfraGO AG","322B2-002","Rostock-Berlin-Dresden",">","Radebeul Abzw Az","Kottewitz",2026,2026,5,6,"2026-02-01","21:00:00","2026-02-02","05:00:00","0d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2025-06-16",null,null,1.7,1]
[null,"DB InfraGO AG","33772-001","Rostock-Berlin-Dresden","<>","Radebeul-Naundorf","Dresden-Friedrichstadt",2026,2026,22,23,"2026-05-31","20:00:00","2026-06-02","04:00:00","1d, 8h","Periodical","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-26",null,null,1.7,1]
[null,"DB InfraGO AG","34531-004","Rostock-Berlin-Dresden",">","Weinböhla","Großenhain Berl Bf",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","05:00:00","0d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-12",null,null,4.5,1]
[null,"DB InfraGO AG","44263-009","Rostock-Berlin-Dresden","<>","Elsterwerda Strw","Kottewitz",2026,2026,2,2,"2026-01-05","22:00:00","2026-01-06","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,1.2,1]
[null,"DB InfraGO AG","483A9-004","Rostock-Berlin-Dresden",">","Frauenhain","Elsterwerda",2026,2026,6,6,"2026-02-02","22:00:00","2026-02-03","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-05-27",null,null,1.2,1]
[null,"DB InfraGO AG","5DAB1-001","Rostock-Berlin-Dresden","<>","Großenhain Berl Bf","Kottewitz",2025,2026,50,36,"2025-12-14","10:00:00","2026-09-04","04:00:00","263d, 17h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-10-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D050-003","Rostock-Berlin-Dresden","<>","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,16,16,"2026-04-15","20:50:00","2026-04-18","04:20:00","2d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-04",null,null,"3,4,5",1]
[null,"DB InfraGO AG","23B5A-003","Rostock-Berlin-Dresden","<>","Hohen Neuend Sw","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-03-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","5C944-006","Rostock-Berlin-Dresden","<>","Schönfließ West","Hohen Neuend Sw",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","32D2F-008","Rostock-Berlin-Dresden","<>","Bergfelde Ost","Hohen Neuend Sw",2026,2026,49,50,"2026-12-06","22:00:00","2026-12-11","04:00:00","4d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","47D0E-006","Rostock-Berlin-Dresden","<>","Rostock Seehafen Süd","Rostock Seehafen",2026,2026,10,10,"2026-03-02","08:00:00","2026-03-02","15:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,1,1]
[null,"DB InfraGO AG","4C77E-007","Rostock-Berlin-Dresden","<>","Kavelstorf","Kavelstorf",2026,2026,7,7,"2026-02-13","23:15:00","2026-02-14","05:15:00","0d, 6h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,5.6,1]
[null,"DB InfraGO AG","4AD6A-003","Rostock-Berlin-Dresden","<>","Löwenberg (Mark)","Zehdenick (Mark)",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-30",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","24036-004","Rostock-Berlin-Dresden","<>","Waren DB-Grenze","Waren (Müritz)",2026,2026,46,50,"2026-11-13","23:00:00","2026-12-11","05:00:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3529F-001","Rostock-Berlin-Dresden",">","Vollrathsruhe","Plaaz                               Abzw",2026,2026,47,47,"2026-11-16","20:30:00","2026-11-17","06:30:00","0d, 10h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-02",null,null,1.2,1]
[null,"DB InfraGO AG","3529F-008","Rostock-Berlin-Dresden","<>","Vollrathsruhe","Lalendorf Ost",2026,2026,47,47,"2026-11-17","20:30:00","2026-11-18","06:30:00","0d, 10h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-02",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","3DE25-003","Rostock-Berlin-Dresden","<>","Vollrathsruhe","Vollrathsruhe",2025,2025,51,51,"2025-12-19","22:00:00","2025-12-20","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-14",null,null,5.6,1]
[null,"DB InfraGO AG","44007-004","Rostock-Berlin-Dresden","<","Waren (Müritz)","Kratzeburg",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-09",null,null,5.6,1]
[null,"DB InfraGO AG","4400F-001","Rostock-Berlin-Dresden","<","Langhagen","Waren (Müritz)",2026,2026,3,3,"2026-01-16","22:00:00","2026-01-17","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-04-14",null,null,5.6,1]
[null,"DB InfraGO AG","44018-004","Rostock-Berlin-Dresden","<","Kargow","Neustrelitz Hbf",2026,2026,3,3,"2026-01-17","22:00:00","2026-01-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-04-09",null,null,6.7,1]
[null,"DB InfraGO AG","4AC79-001","Rostock-Berlin-Dresden",">","Lalendorf Ost","Kavelstorf",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"7,,7",null,null,null,"N",null,"2025-06-10",null,null,3.4,1]
[null,"DB InfraGO AG","4AC85-002","Rostock-Berlin-Dresden",">","Vollrathsruhe","Vollrathsruhe",2026,2026,5,5,"2026-01-27","21:00:00","2026-01-28","05:00:00","0d, 8h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4AC86-003","Rostock-Berlin-Dresden",">","Langhagen","Langhagen",2026,2026,9,9,"2026-02-24","21:00:00","2026-02-25","05:00:00","0d, 8h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-10",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4ADBD-003","Rostock-Berlin-Dresden",">","Kargow","Grabowhöfe",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,3.4,1]
[null,"DB InfraGO AG","4C77E-009","Rostock-Berlin-Dresden","<>","Rostock Hbf","Kavelstorf",2026,2026,7,7,"2026-02-13","23:15:00","2026-02-14","05:15:00","0d, 6h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-09",null,null,5.6,1]
[null,"DB InfraGO AG","4C796-001","Rostock-Berlin-Dresden","<","Laage (Meckl)","Langhagen",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-10",null,null,4.5,1]
[null,"DB InfraGO AG","4C892-003","Rostock-Berlin-Dresden","<>","Kratzeburg","Kratzeburg",2026,2026,7,7,"2026-02-13","22:00:00","2026-02-14","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-23",null,null,5.6,1]
[null,"DB InfraGO AG","33978-002","Rostock-Berlin-Dresden","<>","Riesa","Riesa",2026,2026,33,33,"2026-08-10","07:00:00","2026-08-10","13:00:00","0d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO AG","2F082-002","Rostock-Berlin-Dresden","<>","Berlin Wendenheide","Grünauer Kreuz Nord",2026,2026,2,3,"2026-01-11","22:00:00","2026-01-14","04:00:00","2d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-13",null,null,"1,2,7",1]
[null,"DB InfraGO AG","36B38-012","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Berlin Eichgestell",2026,2026,50,50,"2026-12-09","23:30:00","2026-12-10","03:30:00","0d, 4h","Periodical","Maintenance",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-21",null,null,3.4,1]
[null,"DB InfraGO AG","4C6EE-008","Rostock-Berlin-Dresden","<>","Glasower Damm Ost","Glasower Damm Ost",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-05",null,null,4.5,1]
[null,"DB InfraGO AG","5111B-007","Rostock-Berlin-Dresden","<>","Berlin Eichgestell","Berlin Eichgestell",2026,2026,2,2,"2026-01-05","23:20:00","2026-01-09","04:40:00","3d, 5h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,"2,3,4",1]
[null,"DB InfraGO AG","4FD5C-012","Rostock-Berlin-Dresden",">","Genshagener Heide","Saarmund",2026,2026,3,3,"2026-01-16","04:00:00","2026-01-17","04:00:00","1d, 0h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-06-25",null,null,5.6,1]
[null,"DB InfraGO AG","4D6F3-002","Wilhelmshaven - Bremen",">","Oldenburg-Hemmelsberg","Oldenburg-Hemmelsberg",2026,2026,7,7,"2026-02-14","22:00:00","2026-02-15","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-17",null,null,6.7,1]
[null,"DB InfraGO AG","4A609-004","Wilhelmshaven - Bremen","<>","Delmenhorst","Ganderkesee",2026,2026,5,5,"2026-01-27","22:00:00","2026-01-28","05:00:00","0d, 7h","Periodical","Maintenance Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","3BFD3-002","Wilhelmshaven - Bremen","<","Hude","Hude",2025,2025,51,51,"2025-12-20","22:00:00","2025-12-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-28",null,null,6.7,1]
[null,"DB InfraGO AG","1D066-008","Wilhelmshaven - Bremen","<>","Bremen-Neustadt","Delmenhorst Df",2026,2026,48,50,"2026-11-25","22:10:00","2026-12-11","05:00:00","15d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2025-03-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","34BC1-009","Wilhelmshaven - Bremen","<>","Bookholzberg","Bookholzberg",2026,2026,13,15,"2026-03-25","05:00:00","2026-04-10","05:00:00","15d, 23h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","35DA3-001","Wilhelmshaven - Bremen","<","Wüsting","Oldenburg (Oldb) Hbf",2026,2026,8,9,"2026-02-22","22:10:00","2026-02-23","05:30:00","0d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2024-12-12",null,null,1.7,1]
[null,"DB InfraGO AG","43E25-002","Wilhelmshaven - Bremen","<","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,3,3,"2026-01-13","23:00:00","2026-01-14","05:00:00","0d, 6h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","43E8D-004","Wilhelmshaven - Bremen","<>","Oldenburg (Oldb) Hbf","Hude",2026,2026,3,3,"2026-01-17","22:00:00","2026-01-18","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-04-23",null,null,6.7,1]
[null,"DB InfraGO AG","4A525-004","Wilhelmshaven - Bremen","<>","Oldenburg (Oldb) Hbf","Hude",2026,2026,5,5,"2026-01-26","22:00:00","2026-01-27","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-11",null,null,1.2,1]
[null,"DB InfraGO AG","4A60A-001","Wilhelmshaven - Bremen","<>","Delmenhorst","Wüsting",2026,2026,9,9,"2026-02-24","22:00:00","2026-02-25","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","4A75A-004","Wilhelmshaven - Bremen","<>","Bremen Hbf","Bremen Hbf",2026,2026,9,9,"2026-02-25","23:00:00","2026-02-26","05:00:00","0d, 6h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","4D55A-004","Wilhelmshaven - Bremen","<>","Delmenhorst","Bremen Hbf ehem Bwn",2026,2026,7,7,"2026-02-12","22:00:00","2026-02-13","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-06-17",null,null,4.5,1]
[null,"DB InfraGO AG","1B7E0-002","Wilhelmshaven - Bremen","<","HOFD","Oldenburg (Oldb) Hbf",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","22:00:00","3d, 0h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","36C18-009","Wilhelmshaven - Bremen","<>","Sande","Sande",2026,2026,10,10,"2026-03-07","03:15:00","2026-03-07","08:15:00","0d, 5h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-10-24",null,null,6,1]
[null,"DB InfraGO AG","36C18-015","Wilhelmshaven - Bremen","<>","Sande","Sande",2026,2026,11,11,"2026-03-11","23:00:00","2026-03-13","05:00:00","1d, 6h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-10-24",null,null,3.4,1]
[null,"DB InfraGO AG","43DA8-001","Wilhelmshaven - Bremen",">","Rastede","Varel (Oldb)",2026,2026,2,2,"2026-01-06","22:00:00","2026-01-07","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-04-23",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","48E85-001","Wilhelmshaven - Bremen",">","Oldenburg (Oldb) Hbf","Jaderberg",2026,2026,6,6,"2026-02-04","22:00:00","2026-02-05","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2025-06-05",null,null,3.4,1]
[null,"DB InfraGO AG",4.9989999999999997,"Wilhelmshaven - Bremen","<>","Jaderberg","Wilhelmshaven",2026,2026,6,6,"2026-02-02","22:00:00","2026-02-03","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-05",null,null,1.2,1]
[null,"DB InfraGO AG","4A705-003","Wilhelmshaven - Bremen","<>","Rastede","Oldenburg (Oldb) Hbf",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","4E572-002","Wilhelmshaven - Bremen","<>","Rastede","Varel (Oldb)",2026,2026,8,8,"2026-02-20","22:00:00","2026-02-21","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-18",null,null,5.6,1]
[null,"DB InfraGO AG","4A705-006","Wilhelmshaven - Bremen","<>","Westerstede-Ocholt","Oldenburg (Oldb) Hbf",2026,2026,5,5,"2026-01-28","22:00:00","2026-01-29","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-06-12",null,null,3.4,1]
[null,"DB InfraGO AG","43E42-006","Wilhelmshaven - Bremen","<>","Sande","Sande",2026,2026,3,3,"2026-01-14","22:00:00","2026-01-15","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-23",null,null,3.4,1]
[null,"DB InfraGO AG","4D482-010","Wilhelmshaven - Bremen","<>","Sande","Sande",2026,2026,7,7,"2026-02-11","22:00:00","2026-02-12","05:00:00","0d, 7h","Periodical","Maintenance Container",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-06-16",null,null,3.4,1]
[null,"DB InfraGO AG","41324-002","Bremen - Hannover","<>","Bremen-Sebaldsbrück","Bremen-Sebaldsbrück",2027,2027,32,32,"2027-08-14","22:00:00","2027-08-15","06:00:00","0d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,6.7,1]
[null,"DB InfraGO AG","41055-001","Bremen - Hannover","<","Seelze","Wunstorf",2027,2027,27,28,"2027-07-09","21:00:00","2027-07-14","04:55:00","4d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-18",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","40AFE-002","Bremen - Hannover",">","Bremen-Hastedt","Bremen Hbf",2027,2027,26,26,"2027-06-28","08:00:00","2027-07-01","16:00:00","3d, 8h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-29",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","4106F-016","Bremen - Hannover","<","Bremen Hbf","Bremen-Hastedt",2027,2027,18,19,"2027-05-08","00:00:00","2027-05-14","05:00:00","6d, 5h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","41268-002","Bremen - Hannover","<>","Bremen Hbf","Bremen-Hemelingen",2027,2027,26,26,"2027-06-28","08:00:00","2027-07-02","16:00:00","4d, 8h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-29",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3A3A2-004","Bremen - Hannover","<>","Lehrte West","Lehrte West",2027,2027,41,45,"2027-10-17","05:00:00","2027-11-10","09:00:00","24d, 5h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3A951-001","Bremen - Hannover","<>","Hannover-Waldhausen","Misburg",2027,2027,1,2,"2027-01-09","20:00:00","2027-01-11","08:00:00","1d, 12h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-10",null,null,6.7,1]
[null,"DB InfraGO AG","41053-001","Bremen - Hannover",">","Wunstorf","Seelze West",2027,2027,2,2,"2027-01-12","21:10:00","2027-01-15","05:05:00","2d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-18",null,null,"2,3,4",1]
[null,"DB InfraGO AG","41055-011","Bremen - Hannover",">","Wunstorf","Seelze West",2027,2027,29,29,"2027-07-21","21:10:00","2027-07-23","05:05:00","1d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-18",null,null,3.4,1]
[null,"DB InfraGO AG","38FF1-003","Bremen - Hannover","<","Hagen (Han)","Neustadt a Rübenberge",2027,2027,20,20,"2027-05-17","21:00:00","2027-05-19","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-16",null,null,1.2,1]
[null,"DB InfraGO AG","3909C-001","Bremen - Hannover",">","Neustadt a Rübenberge","Hagen (Han)",2027,2027,19,20,"2027-05-14","20:15:00","2027-05-22","06:15:00","7d, 10h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-27",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO AG","3909C-007","Bremen - Hannover",">","Neustadt a Rübenberge","Hagen (Han)",2027,2027,22,23,"2027-06-01","21:05:00","2027-06-12","05:25:00","10d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-27",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","39305-001","Bremen - Hannover","<>","Wunstorf","Poggenhagen",2027,2027,19,19,"2027-05-14","21:05:00","2027-05-15","22:55:00","1d, 1h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-14",null,null,5.6,1]
[null,"DB InfraGO AG","3C567-002","Bremen - Hannover",">","Poggenhagen","Hagen (Han)",2027,2027,19,20,"2027-05-15","21:05:00","2027-05-17","05:05:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-03",null,null,6.7,1]
[null,"DB InfraGO AG","3C567-009","Bremen - Hannover","<","Hagen (Han)","Poggenhagen",2027,2027,25,25,"2027-06-23","21:00:00","2027-06-25","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-03",null,null,3.4,1]
[null,"DB InfraGO AG","4103D-002","Bremen - Hannover","<","Bremen-Mahndorf","Baden (Kr Verden)",2027,2027,20,21,"2027-05-23","22:00:00","2027-05-24","06:00:00","0d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-09-19",null,null,1.7,1]
[null,"DB InfraGO AG","4103D-008","Bremen - Hannover","<>","Achim","Achim",2027,2027,23,24,"2027-06-11","22:00:00","2027-06-19","06:00:00","7d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","4108D-005","Bremen - Hannover","<>","Eystrup","Eystrup",2027,2027,23,23,"2027-06-10","22:00:00","2027-06-12","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,4.5,1]
[null,"DB InfraGO AG","42464-001","Bremen - Hannover","<","Bremerhaven-Speckenbüttel","Bremerhaven-Lehe Pbf",2027,2027,13,14,"2027-04-04","22:00:00","2027-04-06","06:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-01",null,null,1.7,1]
[null,"DB InfraGO AG","3A010-003","Dresden - Děčín","<>","Dresden Hbf","Dresden Hbf",2027,2027,10,13,"2027-03-12","21:00:00","2027-04-02","21:00:00","20d, 23h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3C2EB-015","Dresden - Děčín","<>","Dresden Hbf","Dresden Hbf",2027,2027,36,41,"2027-09-11","04:00:00","2027-10-12","04:00:00","31d, 0h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3CD83-002","Dresden - Děčín","<>","Bad Schandau Grenze","Bad Schandau",2027,2027,45,45,"2027-11-13","21:00:00","2027-11-14","05:00:00","0d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-09-26",null,null,6.7,1]
[null,"DB InfraGO AG","3DEFB-003","Dresden - Děčín","<>","Pirna Gbf","Pirna Gbf",2027,2027,16,17,"2027-04-19","08:00:00","2027-04-29","05:00:00","9d, 21h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-09-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3E072-010","Dresden - Děčín","<>","Obervogelgesang (Kr Pirna)","Pirna Gbf",2027,2027,41,41,"2027-10-12","20:00:00","2027-10-15","04:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-16",null,null,"2,3,4",1]
[null,"DB InfraGO AG","3B5E7-015","Dresden - Děčín","<>","Dresden Hbf","Dresden Mitte",2027,2027,15,15,"2027-04-15","20:00:00","2027-04-16","04:00:00","0d, 8h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,4.5,1]
[null,"DB InfraGO AG","3DA1D-008","Dresden - Děčín","<>","Heidenau","Dresden Hbf",2027,2027,10,11,"2027-03-11","22:00:00","2027-03-15","04:00:00","3d, 6h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-18",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","3DEFB-015","Dresden - Děčín","<>","Pirna","Heidenau",2027,2027,17,17,"2027-04-27","21:00:00","2027-04-29","05:00:00","1d, 8h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-19",null,null,2.2999999999999998,1]
[null,"DB InfraGO AG","40243-007","Dresden - Děčín","<>","Coswig (bei Dresden)","Coswig (bei Dresden)",2027,2027,21,22,"2027-05-30","20:00:00","2027-05-31","04:00:00","0d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,1.7,1]
[null,"DB InfraGO AG","4023D-001","Falkenberg - Dresden","<>","Coswig (bei Dresden)","Coswig (bei Dresden)",2027,2027,11,13,"2027-03-17","06:00:00","2027-04-03","18:00:00","17d, 11h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-10-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","40245-018","Falkenberg - Dresden","<>","Coswig (bei Dresden)","Coswig (bei Dresden)",2027,2027,23,23,"2027-06-09","08:00:00","2027-06-11","17:00:00","2d, 9h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-01",null,null,"3,4,5",1]
[null,"DB InfraGO AG","40256-002","Falkenberg - Dresden","<","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden)",2027,2027,35,35,"2027-09-01","08:00:00","2027-09-03","17:00:00","2d, 9h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"7,,7",null,null,null,"N",null,"2024-10-30",null,null,"3,4,5",1]
[null,"DB InfraGO AG","40256-024","Falkenberg - Dresden","<>","Coswig (bei Dresden)","Coswig (bei Dresden)",2027,2027,38,38,"2027-09-22","20:00:00","2027-09-23","04:00:00","0d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-10-30",null,null,3.4,1]
[null,"DB InfraGO AG","40269-003","Falkenberg - Dresden","<>","Coswig (bei Dresden)","Coswig (bei Dresden) Stw 1",2027,2027,48,49,"2027-12-02","08:00:00","2027-12-07","17:00:00","5d, 9h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-11-01",null,null,"1,2,4,5",1]
[null,"DB InfraGO AG","3A2D0-006","Falkenberg - Dresden","<>","Elsterwerda","Elsterwerda",2027,2027,44,49,"2027-11-01","08:00:00","2027-12-11","23:59:00","40d, 15h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-09-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3FD0E-006","Falkenberg - Dresden","<>","Priestewitz","Zeithain Bogendreieck",2027,2027,47,47,"2027-11-25","16:00:00","2027-11-26","05:00:00","0d, 13h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,4.5,1]
[null,"DB InfraGO AG","4023D-020","Falkenberg - Dresden","<>","Coswig (bei Dresden)","Coswig (bei Dresden)",2027,2027,17,17,"2027-04-28","22:00:00","2027-04-30","04:00:00","1d, 6h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-30",null,null,3.4,1]
[null,"DB InfraGO AG","40243-008","Falkenberg - Dresden","<>","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden)",2027,2027,21,22,"2027-05-30","20:00:00","2027-05-31","04:00:00","0d, 8h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,1.7,1]
[null,"DB InfraGO AG","424A8-002","Hamburg - Magdeburg","<>","Schnega","Veerßen",2027,2027,1,5,"2027-01-08","21:30:00","2027-02-01","05:00:00","23d, 7h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"5,6,7",1]
[null,"DB InfraGO AG","3994C-001","Magdeburg - Falkenberg",">","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2027,2027,36,36,"2027-09-06","08:00:00","2027-09-07","14:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-28",null,null,1.2,1]
[null,"DB InfraGO AG","39C33-002","Magdeburg - Falkenberg","<","Meinsdorf","Coswig (Anh) Gbf",2027,2027,36,37,"2027-09-08","08:00:00","2027-09-14","14:00:00","6d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","42611-006","Rostock-Berlin-Dresden","<>","Bergfelde Ost","Hohen Neuend Sw",2027,2027,5,5,"2027-02-01","05:00:00","2027-02-05","21:00:00","4d, 16h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-30",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","3928B-003","Rostock-Berlin-Dresden","<>","Genshagener Heide Ost","Birkengrund Süd",2027,2027,42,42,"2027-10-18","22:35:00","2027-10-21","04:30:00","2d, 5h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"1,2,3",1]
[null,"DB InfraGO AG","408DB-001","Rostock-Berlin-Dresden","<>","Bentwisch","Rostock Seehafen Süd",2027,2027,53,1,"2027-01-01","00:00:00","2027-01-04","04:30:00","3d, 4h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-01",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","41F08-002","Rostock-Berlin-Dresden","<>","Ahrensfelde","Biesdorfer Kreuz Nord",2027,2027,28,28,"2027-07-12","20:00:00","2027-07-14","04:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-02",null,null,1.2,1]
[null,"DB InfraGO AG","41507-006","Rostock-Berlin-Dresden","<>","Berlin-Grünau","Grünauer Kreuz Süd",2027,2027,16,18,"2027-04-19","06:00:00","2027-05-05","21:00:00","16d, 15h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-04-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","40AC4-003","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden-Altstadt",2027,2027,42,42,"2027-10-20","08:00:00","2027-10-20","18:00:00","0d, 10h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-14",null,null,3,1]
[null,"DB InfraGO AG","41DA9-042","Rostock-Berlin-Dresden","<>","Biesdorfer Kreuz Nord","Berlin Nordost",2027,2027,37,37,"2027-09-17","20:00:00","2027-09-19","16:00:00","1d, 20h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-09",null,null,"5,6,7",1]
[null,"DB InfraGO AG","3938B-002","Rostock-Berlin-Dresden",">","Brenitz-Sonnewalde","Doberlug-Kirchhain Nord",2027,2027,5,5,"2027-02-03","07:00:00","2027-02-04","14:50:00","1d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-28",null,null,3.4,1]
[null,"DB InfraGO AG","393F6-003","Rostock-Berlin-Dresden","<>","Luckau-Uckro","Golßen (Niederlausitz)",2027,2027,6,6,"2027-02-11","08:00:00","2027-02-12","15:50:00","1d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,4.5,1]
[null,"DB InfraGO AG","396C9-010","Rostock-Berlin-Dresden",">","Hohenleipisch Betriebsbahnhof","Elsterwerda Strw",2027,2027,10,44,"2027-03-08","08:00:00","2027-11-01","08:00:00","238d, 0h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-02",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3DF65-001","Rostock-Berlin-Dresden","<>","Rangsdorf","Wünsdorf-Waldstadt",2027,2027,4,5,"2027-01-29","22:00:00","2027-02-01","04:00:00","2d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-07-02",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","3E04E-001","Rostock-Berlin-Dresden","<>","Rangsdorf","Zossen",2027,2027,5,6,"2027-02-05","21:00:00","2027-02-08","04:50:00","2d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-29",null,null,"5,6,7",1]
[null,"DB InfraGO AG","3DF12-004","Rostock-Berlin-Dresden","<>","Doberlug-Kirchhain ob Bf","Doberlug-Kirchhain ob Bf",2027,2027,44,44,"2027-11-06","08:00:00","2027-11-06","16:00:00","0d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-03",null,null,6,1]
[null,"DB InfraGO AG","3AF76-007","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden-Altstadt",2027,2027,35,44,"2027-09-05","04:00:00","2027-11-06","14:00:00","62d, 11h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"Y",null,"2024-09-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3B081-001","Rostock-Berlin-Dresden","<","Dresden Freiberger Straße","Dresden Hbf",2027,2027,41,41,"2027-10-12","21:00:00","2027-10-15","05:00:00","2d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"2,3,4",1]
[null,"DB InfraGO AG","3C2EB-022","Rostock-Berlin-Dresden","<>","Dresden Hbf","Dresden Hbf",2027,2027,38,41,"2027-09-24","04:00:00","2027-10-11","20:00:00","17d, 16h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","40156-002","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Cotta Bft",2027,2027,28,28,"2027-07-12","18:00:00","2027-07-17","04:00:00","4d, 10h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-09-25",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","40837-022","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Cotta Bft",2027,2027,36,36,"2027-09-08","08:00:00","2027-09-08","16:00:00","0d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-02-18",null,null,3,1]
[null,"DB InfraGO AG","40837-026","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2027,2027,36,36,"2027-09-08","08:00:00","2027-09-08","16:00:00","0d, 8h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-02-18",null,null,3,1]
[null,"DB InfraGO AG","40837-027","Rostock-Berlin-Dresden","<>","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2027,2027,36,36,"2027-09-08","08:00:00","2027-09-08","16:00:00","0d, 8h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-02-18",null,null,3,1]
[null,"DB InfraGO AG","40A91-005","Rostock-Berlin-Dresden","<>","Karower Kr Strw","Berlin-Karow West",2027,2027,1,1,"2027-01-04","05:00:00","2027-01-08","21:00:00","4d, 16h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","4180F-001","Rostock-Berlin-Dresden","<>","Kargow","Waren (Müritz)",2027,2027,44,44,"2027-11-01","22:30:00","2027-11-06","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-26",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","39297-005","Rostock-Berlin-Dresden","<>","Nienburg (Weser)","Nienburg (Weser)",2027,2027,42,44,"2027-10-18","05:00:00","2027-11-03","16:00:00","16d, 12h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3D842-001","Rostock-Berlin-Dresden","<>","Genshagener Heide Ost","Glasower Damm Ost",2027,2027,46,47,"2027-11-21","22:35:00","2027-11-24","04:30:00","2d, 5h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-28",null,null,"1,2,7",1]
[null,"DB InfraGO AG","399CC-002","Rostock-Berlin-Dresden",">","Medewitz (Mark)","Roßlau (Elbe) Gbf",2027,2027,15,15,"2027-04-14","22:00:00","2027-04-16","04:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-28",null,null,3.4,1]
[null,"DB InfraGO AG","3ED37-008","Wilhelmshaven - Bremen","<>","Wilhelmshaven Ölweiche","Wilhelmshaven Nord",2027,2027,9,11,"2027-03-06","08:00:00","2027-03-16","15:55:00","10d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3ED37-006","Wilhelmshaven - Bremen","<>","Wilhelmshaven Ölweiche","Wilhelmshaven JadeWeserPort DB-Grenze",2027,2027,9,9,"2027-03-01","08:00:00","2027-03-04","15:55:00","3d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-17",null,null,"1,2,3,4",1]
[null,"MÁV",55009001211,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,44,44,"2025-10-30","04:30:00","2025-10-30","23:59:00","19h29m","Periodical","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001217,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,45,45,"2025-11-07","23:00:00","2025-11-08","04:30:00","5h30m","Periodical","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001234,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,48,48,"2025-11-27","23:00:00","2025-11-28","04:30:00","5h30m","Periodical","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"MÁV",55009001244,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2025,2025,50,50,"2025-12-09","23:00:00","2025-12-10","04:30:00","5h30m","Periodical","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2023-12-04T08:12:54"]
[null,"ÖBB Infra","81-B-62309","Břeclav - Wien","< >","Wien Floridsdorf","Wien Meidling",2025,2025,1,50,"2025-01-01","00:00:00","2025-12-13",1,"347 days","Periodical","Others","T","LT",null,null,null,"C","R","T",0,null,"Programm Schnellbahn Wien\nErrichten von Bahnsteiglängen 220m; Stromschiene; ETCS L2;\nReinvestitionen ",null,"N",null,"2023-12-04T08:12:54"]
[null,"ÖBB Infra","81-B-65429","Salzburg - Wels","< >","Abzw Bl 1","Neusiedl am See",2025,2025,44,48,"27.10.2025","05:00:00","24.11.2025","05:00:00","28 days","Periodical","Others","T","LT",null,null,null,"C","R","T",0,null,"Brückensanierung in km 35,057 und in km 37,639 sowie Gleisneulage und Bahnsteigsanierung in der Hst Parndorf Ort",null,"N",null,"11.05.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-65802","Salzburg - Wels","< >","Linz Hbf","-",2025,2025,1,50,"01.01.2025","00:00:00","13.12.2025",1,"347 days","Periodical","Miscellaneous","T","LT",null,null,null,"C",null,null,0,null,"Umbau Linz Hbf West",null,"N",null,"30.05.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-65812","Wels - Linz","< >","Linz Hbf","Wels Hbf",2026,2026,1,50,"01.01.2026","00:00:00","12.12.2026",1,"346 days","Periodical","Miscellaneous","T","LT","S",null,null,"C","R",null,7,null,"Viergleisiger Ausbau Linz - Wels",null,"N",null,"06.09.2024",null,null,null,"Y"]
[null,"ÖBB Infra","81-B-73462","Salzburg - Wels","< >","Marchtrenk","Wels Hbf",2024,2025,50,48,"15.12.2024","00:00:00","30.11.2025",1,"351 days","Periodical","Miscellaneous","T","LT","S",null,null,null,null,null,1,null,"Langsamfahren Gleis 1 und 2 mit 100 km/h - Errichtung des neuen Überwerfungsbauwerks und der Autobahnbrücken von km 207,600 bis 208,400",null,"N",null,"30.01.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-77194","Salzburg - Wels","< >","Abzw Knoten Hadersdorf","Unter Purkersdorf",2025,2025,1,50,"01.01.2025","00:00:00","13.12.2025",1,"347 days","Periodical","Maintenance","T","LT",null,null,null,"C","R",null,0,null,"Wartungsnacht ",null,"Y",null,"2024-07-11",null,"1,2,3,4,5,6,7"]
[null,"ÖBB Infra","81-B-77847","Wien - Hegyeshalom","< >","Lanzendorf-Rannersdorf","Gramatneusiedl",2025,2026,50,46,"14.12.2025","00:00:00","14.11.2026","04:40:00","335 days + 4,7 h","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,0,null,"Umbau Bahnhof Himberg",null,"N",null,"2024-07-11",null,"1,2,3,4,5"]
[null,"ÖBB Infra","81-B-78053","Salzburg - Wels","< >","St.Valentin - gesamt","Abzw Knoten St.Peter-Seitenstetten West",2026,2026,13,19,"25.03.2026","00:00:00","09.05.2026",1,"45 days + 23,0 h","Periodical","Others","T","LT",null,null,null,null,null,null,0,null,"Tunnelspülen, Strahlerkabel, Tunnelnotruf",null,"N",null,"2024-07-11",null,"1,2,3,4,5"]
[null,"ÖBB Infra","81-B-78277","Salzburg - Wels","< >","Salzburg Hbf","-",2026,2026,31,34,"02.08.2026","07:30:00","22.08.2026","05:00:00","19 days + 21,5 h","Periodical","Others","T","LT",null,null,null,"C","R","T",0,null,"Sanierung Gleis 203 und 205 GN/PLV",null,"N",null,"2024-07-11",null,"1,2,3,4,5,6,7"]
[null,"ÖBB Infra","81-B-78291","Salzburg - Wels","< >","Linz Hbf","-",2026,2026,13,30,"27.03.2026","23:00:00","24.07.2026","05:00:00","118 days + 5,0 h","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,0,null,"Linz Hbf Westseite; Einbindung 4-Gl. Westbahn\n",null,"Y","PEI304","2024-07-11"]
[null,"ÖBB Infra","81-B-78308","Salzburg - Wels","< >","Wels Vbf","-",2026,2026,15,17,"10.04.2026","00:00:00","23.04.2026",1,"14 days","Periodical","Others","T","LT",null,null,null,null,null,null,0,null,"Gleinsneulage Gleis 326",null,"N","AMV6990302","2024-12-17"]
[null,"ÖBB Infra","81-B-79062","Salzburg - Wels","< >","Wels Hbf","Grünau im Almtal",2026,2026,28,35,"11.07.2026","00:00:00","28.08.2026",1,"49 days","Periodical","Others","T","LT",null,null,null,"C",null,null,0,null,"Gleisneulagen, IB EStw, DL, BR, Bahnsteige",null,"N",null,"2024-12-17",null,"1,2,3,4,5,6"]
[null,"ÖBB Infra","81-B-79436","Salzburg - Wels","< >","Linz Vbf-Ost Reihungsgr","-",2026,2026,37,38,"07.09.2026","00:00:00","18.09.2026",1,"12 days","Periodical","Others","T","LT",null,null,null,null,null,null,0,null,"Schienentausch, Einbau Gleisbremsen, Rollberg",null,"N",null,"2024-12-17",null,3]
[null,"ÖBB Infra","81-B-79735","Salzburg - Wels","< >","Taufkirchen a.d.Pram","-",2026,2026,24,50,"14.06.2026","00:00:00","12.12.2026",1,"182 days + 1,0 h","Periodical","Others","T","LT",null,null,null,"C",null,null,0,null,"Umbau Bahnhof Taufkirchen an der Pram",null,"N","SAB416, SAV431, STA602, SAV431","19.12.2023",null,null,null,"N"]
[null,"ÖBB Infra","81-B-84776","Wels - Linz","< >","Linz Hbf","Üst Lz 2",2027,2027,47,48,"26.11.2027","22:30:00","05.12.2027","01:30:00","8 days + 3,0 h","Periodical","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Viergleisiger Ausbau \n1. Anschwenkung an Gleis 4 neu im Bereich Leonding",null,"N",null,"13.05.2024",null,null,null,"N"]
[null,"ÖBB Infra","81-B-86285","Salzburg - Wels","< >","Linz Hbf","-",2026,2026,34,50,"17.08.2026","05:00:00","12.12.2026",1,"117 days + 20,0 h","Continuous","Miscellaneous","T","LT",null,null,null,"C",null,"T",0,null,"Abtrag Gleis 342 und Abtrag Weiche 313/314",null,"Y","PEI304","2024-12-17",null,"1,2,3,4,5"]
[null,"ÖBB Infra","81-B-86641","Linz - Wien (NRZ)","< >","Wien Meidling","St.Pölten Hbf\nWien Hütteldorf\nUnter Purkersdorf\nInzersdorf Ort",2026,2026,50,53,"13.12.2026","00:00:00","31.12.2026",1,"19 days","Periodical","Maintenance","T","LT",null,null,null,"C","R",null,0,null,"Wartungsfenster Lainzer Tunnel + WWT + Perschlingkette\nSperre von Wien Meidling/Wien Inzersdorf - St. Pölten Hbf",null,"N",null,"2024-12-17",null,"2,3"]
[null,"ÖBB Infra","81-B-89551","Wien - Hegyeshalom","< >","Parndorf","Staatsgrenze nächst Kittsee",2026,2026,38,38,"14.09.2026","07:50:00","18.09.2026","12:30:00","4 days + 4,7 h","Periodical","Maintenance","T","LT",null,null,null,"C","R","T",0,null,"Div. Instandhaltungsarbeiten","Affected Border: 56\nAffected Ims: Bratislava Petrzalka\nDeviation Border(s): Devinska Nova Ves","N",null,"26.05.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-89845","Wien - Ebenfurth - Sopron","< >","Ebenfurth","-",2026,2026,9,10,"28.02.2026","07:00:00","07.03.2026","17:00:00","7 days + 10,0 h","Periodical","Miscellaneous","T","LT",null,null,null,"C","R",null,0,null,"Errichtung der Schleife Ebenfurth",null,"N",null,"27.05.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-90174","Wien - Ebenfurth - Sopron","< >","Üst Wp 1","Abzww Ebenfurth Nord",2026,2026,33,50,"10.08.2026","18:00:00","12.12.2026",1,"124 days + 7,0 h","Continuous","Miscellaneous","T","LT",null,null,null,"C","R","T",0,null,"Errichtung der Schleife Ebenfurth",null,"N",null,"27.05.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-91673","Linz - Wien (NRZ)","< >","Neulengbach","-",2027,2027,22,24,"05.06.2027","07:00:00","14.06.2027","04:00:00","8 days + 21,0 h","Continuous","Others","T","LT",null,null,null,null,null,null,0,null,"Reinvestition Bf. Neulengbach: Gleisneulage und Planumsverbesserung Gl2, Gl5 km37,945 - 38,308; Weichenneulage W10,11,12,34,32",null,"N","16-119623","07.02.2025",null,null,null,"N"]
[null,"ÖBB Infra","81-B-93187","Linz - Wien (NRZ)","< >","Rekawinkel","Hutten",2026,2026,4,27,"24.01.2026","01:10:00","30.06.2026",1,"157 days + 21,8 h","Continuous","Maintenance","T","LT",null,null,null,null,"R",null,0,null,"Drainagen und Tunnelspülen",null,"N",null,"20.05.2025",null,null,null,"N"]
[null,"SNCF-R",8124518,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2024,2025,51,50,"2024-12-16","11:02:00","2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,"Y",null,"2024-12-17"]
[null,"SZCZ","V-001625/24","Hranice na Morave - Zilina","< >","Valašská Polanka","Horní Lideč",2025,2025,1,52,"2025-01-01","00:00:00","2025-12-31","23:59:00","365 days","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-002761/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,9,50,"2026-03-01","00:00:00","2026-12-12","23:59:00","287 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-003373/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2026,2026,30,30,"2026-07-20","00:00:00","2026-07-24","23:59:00","5 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"3,5 bez TV. ",null,null,null,"2025-06-30T07:51:17"]
[null,"SZCZ","V-003647/25","Ostrava - Zilina","< >","Louky nad Olší","hi Louky n.O.",2026,2026,12,13,"2026-03-20","00:00:00","2026-03-23","23:59:00","4 x 10 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"traťová bez TV. ",null,null,null,"2024-12-17",null,"3,4,5,6,7"]
[null,"SZCZ","V-003657/23","Chocen - Hranice na Morave","< >","Studénka","Studénka",2026,2026,31,49,"2026-08-01","00:00:00","2026-11-30","23:59:00","122 days","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. \nzhlaví jistebnické.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003708/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2026,2026,36,36,"2026-08-31","00:00:00","2026-09-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:16"]
[null,"SZCZ","V-003896/24","Brno - Břeclav","< >","Brno-Černov.zhl.Táb.","Odb Brno-Židenice z",2026,2026,10,11,"2026-03-07","00:00:00","2026-03-09","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-003940/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,6,7,"2026-02-08","00:00:00","2026-02-11","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2024-12-17",null,"1,2,3,4,5"]
[null,"SZCZ","V-003978/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,11,11,"2026-03-10","00:00:00","2026-03-13","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004044/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín st.hr.",2026,2026,34,34,"2026-08-17","00:00:00","2026-08-21","23:59:00","5 x 10 hours","Periodical","Others",null,"LT",null,null,"X",null,null," ,X,X",null,null,"traťová jen TV. ",null,null,null,"2024-12-17",null,"1,4,5,6,7"]
[null,"SZCZ","V-004076/25","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2027,2027,43,43,"2027-10-27","00:00:00","2027-10-31","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004340/25","Kolín - Brno-Maloměřice","< >","Brno-Královo Pole","Kuřim",2027,2027,35,48,"2027-09-01","00:00:00","2027-11-30","23:59:00","91 days","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Praha-Radotín",2026,2026,43,44,"2026-10-23","00:00:00","2026-10-27","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004833/25","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2027,2027,14,14,"2027-04-05","00:00:00","2027-04-11","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004839/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2025,2025,38,47,"2025-09-17","00:00:00","2025-11-17","23:59:00","4 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004972/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2026,2026,9,9,"2026-02-24","00:00:00","2026-02-28","23:59:00","5 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005087/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2026,2026,9,46,"2026-03-01","00:00:00","2026-11-14","23:59:00","259 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:34",null,"2,3,4"]
[null,"SZCZ","V-005099/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 x 12 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-005154/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,17,18,"2026-04-23","00:00:00","2026-04-29","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:23",null,"1,6,7"]
[null,"SZCZ","V-005250/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,32,32,"2026-08-05","00:00:00","2026-08-06","23:59:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005474/24","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005696/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2025,2025,1,52,"2025-01-01","00:00:00","2025-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ost. zař.: ETCS.",null,null,null,"2025-06-30T10:22:35"]
[null,"SZCZ","V-006006/25","Plzen - Praha","< >","Dobřichovice","Praha-Radotín",2027,2027,27,30,"2027-07-08","00:00:00","2027-07-27","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-006133/25","Plzen - Praha","< >","Dobřichovice","Praha-Radotín",2027,2027,9,14,"2027-03-05","00:00:00","2027-04-11","23:59:00","6 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:16",null,"1,5,6,7"]
[null,"SZCZ","V-006241/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,14,27,"2026-04-01","00:00:00","2026-06-30","23:59:00","91 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"13,15 bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-006248/24","Česká Třebová - Brno","< >","Odb Zádulka","Česká Třebová",2026,2026,16,16,"2026-04-14","00:00:00","2026-04-16","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-006258/24","Praha - Chocen - Česká Třebová","< >","Odb Parník","Česká Třebová",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-13","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2025-06-30T07:51:13"]
[null,"SZCZ","V-006260/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2026,2026,49,53,"2026-12-05","00:00:00","2026-12-31","23:59:00","27 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2025-06-30T07:51:16"]
[null,"SZCZ","V-006278/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,45,46,"2026-11-06","18:00:00","2026-11-12","06:00:00","6 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-006585/24","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2026,2026,17,17,"2026-04-22","00:00:00","2026-04-25","23:59:00","4 x 12 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:27",null,"1,6,7"]
[null,"SZCZ","V-006665/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,49,51,"2026-11-30","18:00:00","2026-12-15","06:00:00","15 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-006943/24","Plzen - Praha","< >","Hořovice","Kařízek",2026,2026,15,16,"2026-04-07","18:00:00","2026-04-19","06:00:00","7 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007228/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,9,10,"2026-03-01","00:00:00","2026-03-07","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:35"]
[null,"SZCZ","V-007312/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,42,42,"2026-10-14","00:00:00","2026-10-16","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-007519/22","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2025,2025,31,46,"2025-08-01","03:25:00","2025-11-13","04:05:00","104 days + 1 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-008307/25","Děčín - Kolín","< >","Mělník","Všetaty",2027,2027,27,28,"2027-07-06","00:00:00","2027-07-16","23:59:00","4 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-009151/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-010088/19","Děčín - Kolín","< >","Velké Březno","Boletice nad Labem",2026,2026,38,41,"2026-09-17","00:00:00","2026-10-06","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T10:22:38",null,"1,2,3,4,5"]
[null,"SZCZ","V-012062/24","Chocen - Hranice na Morave","< >","Studénka","Studénka",2025,2025,41,43,"2025-10-11","00:00:00","2025-10-24","23:59:00","14 x 4 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. \nzáhlaví a zhlaví 1., 2.TK směr Jistebník.",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-012388/25","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2025,2025,43,44,"2025-10-21","08:10:00","2025-10-29","17:00:00","8 days + 9 hours","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2025-06-30T07:52:53",null,"2,3,4"]
[null,"SZCZ","V-012660/20","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2025,2025,31,46,"2025-08-02","00:00:00","2025-11-14","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-013474/25","Děčín - Kolín","< >","Kostomlaty nad Labem","Nymburk hl.n.",2025,2025,45,45,"2025-11-06","20:00:00","2025-11-07","20:00:00","1 days + 0 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-014084/24","Hranice na Morave - Zilina","< >","Valašská Polanka","Horní Lideč",2024,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00","363 days + 24 hours","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:52:53",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015236/23","Praha - Chocen - Česká Třebová","< >","Choceň","Brandýs n.O.předj.k.",2025,2025,45,46,"2025-11-05","00:00:00","2025-11-10","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015245/23","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,13,14,"2026-03-28","00:00:00","2026-04-03","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015260/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Pardubice hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-015270/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015276/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,17,18,"2026-04-24","00:00:00","2026-04-28","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015288/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2025,2025,48,48,"2025-11-25","00:00:00","2025-11-28","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T10:22:36"]
[null,"SZCZ","V-015392/24","Břeclav - Wien","< >","Břeclav os.n.","Břeclav st.hr.",2026,2026,17,18,"2026-04-20","00:00:00","2026-04-28","23:59:00","9 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:18",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015888/23","Děčín - Kolín","< >","Polepy","Hoštka",2027,2027,19,21,"2027-05-16","00:00:00","2027-05-30","23:59:00","15 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:52:55"]
[null,"SZCZ","V-015923/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,20,21,"2026-05-16","00:00:00","2026-05-19","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015926/23","Kolín - Brno-Maloměřice","< >","Golčův Jeníkov","Čáslav",2026,2026,12,12,"2026-03-17","00:00:00","2026-03-22","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-015929/23","Kolín - Brno-Maloměřice","< >","Kolín","Velký Osek",2026,2026,13,14,"2026-03-25","00:00:00","2026-04-01","23:59:00","8 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015944/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,20,21,"2026-05-15","18:00:00","2026-05-19","06:00:00","4 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015948/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,24,25,"2026-06-14","18:00:00","2026-06-16","06:00:00","2 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015954/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno hl.n.",2027,2027,14,15,"2027-04-10","00:00:00","2027-04-12","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015955/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,3,3,"2026-01-12","18:00:00","2026-01-14","06:00:00","2 x 9 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. "]
[null,"SZCZ","V-015960/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,7,8,"2026-02-12","00:00:00","2026-02-18","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. "]
[null,"SZCZ","V-015961/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,40,42,"2026-10-01","18:00:00","2026-10-18","06:00:00","17 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015961/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,40,42,"2026-10-01","18:00:00","2026-10-18","06:00:00","17 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-015961/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,8,25,"2026-02-20","00:00:00","2026-06-19","23:59:00","120 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-015970/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,34,34,"2026-08-18","18:00:00","2026-08-21","06:00:00","2 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-015973/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,36,37,"2026-09-01","18:00:00","2026-09-13","06:00:00","12 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-015978/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,15,16,"2026-04-08","00:00:00","2026-04-14","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"1,3 + TV. "]
[null,"SZCZ","V-015979/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,30,"2026-06-21","00:00:00","2026-07-21","23:59:00","31 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3 jen TV, 1 + TV. "]
[null,"SZCZ","V-015980/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,26,"2026-06-21","00:00:00","2026-06-27","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3 bez TV. "]
[null,"SZCZ","V-015981/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,31,48,"2026-08-01","00:00:00","2026-11-23","23:59:00","115 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. "]
[null,"SZCZ","V-015982/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,48,49,"2026-11-24","00:00:00","2026-11-30","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá jen TV. "]
[null,"SZCZ","V-015988/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2026,2026,40,41,"2026-10-01","18:00:00","2026-10-11","06:00:00","10 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-015996/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,27,"2026-06-21","18:00:00","2026-06-29","06:00:00","8 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. \nzhlaví 2. TK směr Přibyslav."]
[null,"SZCZ","V-016003/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,4,6,"2026-01-19","00:00:00","2026-02-06","23:59:00","19 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-016004/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,9,10,"2026-03-01","18:00:00","2026-03-03","06:00:00","2 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016006/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,11,12,"2026-03-10","18:00:00","2026-03-16","06:00:00","6 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016007/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,33,"2026-08-11","18:00:00","2026-08-15","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. "]
[null,"SZCZ","V-016015/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,31,33,"2026-08-01","00:00:00","2026-08-14","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-016015/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,31,33,"2026-08-01","00:00:00","2026-08-14","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-016016/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,48,"2026-08-15","00:00:00","2026-11-23","23:59:00","101 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 2. TK směr Havl. Brod, jeho část."]
[null,"SZCZ","V-016016/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,23,23,"2026-06-05","18:00:00","2026-06-07","06:00:00","2 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016018/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,25,25,"2026-06-15","18:00:00","2026-06-19","06:00:00","4 x 9 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016022/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2026,2026,25,45,"2026-06-20","00:00:00","2026-11-06","23:59:00","140 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. "]
[null,"SZCZ","V-016023/24","Kolín - Brno-Maloměřice","< >","Žďár nad Sázavou","Sázava u Žďáru",2027,2027,4,22,"2027-01-25","00:00:00","2027-06-03","23:59:00","130 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-016032/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2027,2027,13,15,"2027-04-04","18:00:00","2027-04-16","06:00:00","12 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016045/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Žďár nad Sázavou",2027,2027,17,19,"2027-04-30","18:00:00","2027-05-11","06:00:00","11 x 7 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016312/23","Brno - Břeclav","< >","Brno jih","Brno jih",2026,2026,38,42,"2026-09-14","00:00:00","2026-10-13","23:59:00","30 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"108a bez TV, 104.,106.,108.,110a jen TV, 110b,110c + TV. "]
[null,"SZCZ","V-016312/23","Brno - Břeclav","< >","Brno jih","Brno jih",2026,2026,38,42,"2026-09-14","00:00:00","2026-10-13","23:59:00","30 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"108a bez TV, 104.,106.,108.,110a jen TV, 110b,110c + TV. "]
[null,"SZCZ","V-016313/23","Brno - Břeclav","< >","Brno-Horní Heršpice","Brno-Horní Heršpice",2026,2026,27,33,"2026-07-01","00:00:00","2026-08-14","23:59:00","45 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"5.,707.,709.,709b,711.,713.,717. bez TV, 3.,3a,3b,5.,7.,9.,90.,603.,707.,709. jen TV. "]
[null,"SZCZ","V-016315/23","Česká Třebová - Brno","< >","Brno-Maloměřice St.6","Odb Svitava",2026,2026,6,6,"2026-02-02","00:00:00","2026-02-04","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016316/23","Česká Třebová - Brno","< >","Odb Svitava","Brno-Maloměřice St.6",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-11","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016317/23","Česká Třebová - Brno","< >","Odb Svitava","Adamov",2026,2026,6,6,"2026-02-07","00:00:00","2026-02-08","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016318/23","Česká Třebová - Brno","< >","Adamov","Odb Svitava",2026,2026,7,7,"2026-02-14","00:00:00","2026-02-15","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016319/23","Česká Třebová - Brno","< >","Adamov","Blansko",2026,2026,8,8,"2026-02-21","00:00:00","2026-02-22","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016320/23","Česká Třebová - Brno","< >","Blansko","Adamov",2026,2026,9,9,"2026-02-28","00:00:00","2026-03-01","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016321/23","Česká Třebová - Brno","< >","Rájec-Jestřebí","Blansko",2026,2026,37,38,"2026-09-12","00:00:00","2026-09-16","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016321/23","Česká Třebová - Brno","< >","Rájec-Jestřebí","Blansko",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016321/24","Děčín - Kolín","< >","Lysá nad Labem","Lysá nad Labem",2026,2026,27,29,"2026-07-01","00:00:00","2026-07-15","23:59:00","15 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"2. bez TV, 2.,2a,4.,4a,6a jen TV. "]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,36,37,"2026-09-05","00:00:00","2026-09-09","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,45,46,"2026-11-06","00:00:00","2026-11-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016327/23","Plzen - Praha","< >","Kařízek","Hořovice",2026,2026,16,17,"2026-04-18","00:00:00","2026-04-20","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016327/23","Plzen - Praha","< >","Kařízek","Hořovice",2026,2026,17,17,"2026-04-20","18:00:00","2026-04-21","06:00:00","1 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. "]
[null,"SZCZ","V-016327/24","Děčín - Praha-Libeň","< >","Hněvice","Roudnice nad Labem",2026,2026,37,39,"2026-09-10","00:00:00","2026-09-21","23:59:00","12 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016329/23","Plzen - Praha","< >","Zdice","Beroun os.n.",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016329/23","Plzen - Praha","< >","Zdice","Beroun os.n.",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016329/23","Plzen - Praha","< >","Zdice","Beroun os.n.",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016331/23","Plzen - Praha","< >","Beroun os.n.","Zdice",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016331/23","Plzen - Praha","< >","Beroun os.n.","Zdice",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016331/23","Plzen - Praha","< >","Beroun os.n.","Zdice",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016331/24","Děčín - Praha-Libeň","< >","Hněvice","Dolní Beřkovice",2026,2026,17,18,"2026-04-25","00:00:00","2026-04-27","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016332/24","Děčín - Praha-Libeň","< >","Dolní Beřkovice","Hněvice",2026,2026,18,18,"2026-04-28","00:00:00","2026-04-30","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-016333/23","Plzen - Praha","< >","Hořovice","Kařízek",2026,2026,16,16,"2026-04-15","00:00:00","2026-04-17","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016333/23","Plzen - Praha","< >","Hořovice","Kařízek",2026,2026,16,16,"2026-04-15","18:00:00","2026-04-16","06:00:00","1 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. "]
[null,"SZCZ","V-016341/24","Česká Třebová - Brno","< >","Skalice nad Svitavou","Letovice",2026,2026,38,38,"2026-09-15","00:00:00","2026-09-20","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. "]
[null,"SZCZ","V-016342/24","Česká Třebová - Brno","< >","Skalice nad Svitavou","Letovice",2026,2026,39,39,"2026-09-21","00:00:00","2026-09-26","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-016388/24","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-12","23:59:00","8 x 9 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016413/24","Děčín - Kolín","< >","Všetaty","Dřísy",2026,2026,20,20,"2026-05-13","00:00:00","2026-05-16","23:59:00","4 x 9 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016429/24","Děčín - Kolín","< >","Štětí","Liběchov",2026,2026,15,15,"2026-04-07","00:00:00","2026-04-09","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016430/24","Děčín - Kolín","< >","Liběchov","Štětí",2026,2026,15,15,"2026-04-10","00:00:00","2026-04-12","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016431/24","Děčín - Kolín","< >","Hoštka","Štětí",2026,2026,17,17,"2026-04-20","00:00:00","2026-04-22","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016432/24","Děčín - Kolín","< >","Štětí","Hoštka",2026,2026,16,16,"2026-04-13","00:00:00","2026-04-17","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016433/24","Děčín - Kolín","< >","Polepy","Hoštka",2026,2026,18,18,"2026-04-27","00:00:00","2026-05-01","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016434/24","Děčín - Kolín","< >","Hoštka","Polepy",2026,2026,17,17,"2026-04-23","00:00:00","2026-04-24","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016435/24","Děčín - Kolín","< >","Polepy","Litoměřice dolní n.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016439/24","Děčín - Kolín","< >","Velké Žernoseky","Litoměřice dolní n.",2026,2026,19,19,"2026-05-07","00:00:00","2026-05-10","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016440/24","Děčín - Kolín","< >","Sebuzín","Velké Žernoseky",2026,2026,20,20,"2026-05-11","00:00:00","2026-05-15","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016441/24","Děčín - Kolín","< >","Velké Žernoseky","Sebuzín",2026,2026,21,21,"2026-05-18","00:00:00","2026-05-22","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016449/24","Děčín - Kolín","< >","Ústí n.L.-Střekov","Sebuzín",2026,2026,22,22,"2026-05-25","00:00:00","2026-05-29","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016450/24","Děčín - Kolín","< >","Sebuzín","Ústí n.L.-Střekov",2026,2026,23,23,"2026-06-01","00:00:00","2026-06-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016454/24","Děčín - Kolín","< >","Velké Březno","Ústí n.L.-Střekov",2026,2026,23,23,"2026-06-04","00:00:00","2026-06-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016455/24","Děčín - Kolín","< >","Ústí n.L.-Střekov","Velké Březno",2026,2026,24,24,"2026-06-08","00:00:00","2026-06-10","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016484/24","Brno - Břeclav","< >","Odb Rajhrad","Hrušovany u Brna",2027,2027,19,32,"2027-05-15","00:00:00","2027-08-12","23:59:00","90 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016485/24","Brno - Břeclav","< >","Odb Rajhrad","Hrušovany u Brna",2027,2027,32,45,"2027-08-12","00:00:00","2027-11-09","23:59:00","90 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016506/24","Děčín - Kolín","< >","Stará Boleslav","Hoštka",2027,2027,26,28,"2027-07-03","00:00:00","2027-07-18","23:59:00","16 days","Continuous","Catenary",null,"LT"]
[null,"SZCZ","V-016515/24","Děčín - Kolín","< >","Děčín východ","Boletice nad Labem",2026,2026,24,25,"2026-06-14","00:00:00","2026-06-16","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-016516/24","Děčín - Kolín","< >","Boletice nad Labem","Děčín východ",2026,2026,25,25,"2026-06-17","00:00:00","2026-06-19","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016541/24","Děčín - Kolín","< >","Hoštka","Polepy",2027,2027,17,19,"2027-04-26","00:00:00","2027-05-15","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-016599/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,43,46,"2027-10-27","00:00:00","2027-11-16","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016599/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,43,46,"2027-10-27","00:00:00","2027-11-16","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-016601/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,13,16,"2027-04-02","18:00:00","2027-04-25","06:00:00","23 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2,1 + TV. "]
[null,"SZCZ","V-016624/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,39,43,"2027-09-27","18:00:00","2027-10-27","06:00:00","30 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2,1 + TV. "]
[null,"SZCZ","V-016654/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,45,45,"2027-11-12","18:00:00","2027-11-14","06:00:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-016656/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,28,38,"2027-07-12","00:00:00","2027-09-26","23:59:00","77 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:39",null,"1,6,7"]
[null,"SZCZ","V-016659/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Kolín",2026,2026,14,28,"2026-04-02","00:00:00","2026-07-10","23:59:00","100 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:13",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016659/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Kolín",2027,2027,8,22,"2027-02-22","00:00:00","2027-06-01","23:59:00","100 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:13"]
[null,"SZCZ","V-016660/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,28,43,"2026-07-11","00:00:00","2026-10-19","23:59:00","101 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:13"]
[null,"SZCZ","V-016660/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2027,2027,22,36,"2027-06-02","00:00:00","2027-09-09","23:59:00","100 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-016733/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,28,37,"2027-07-12","00:00:00","2027-09-17","23:59:00","68 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-016801/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,38,38,"2027-09-20","00:00:00","2027-09-26","23:59:00","7 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-016808/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,17,27,"2027-04-26","00:00:00","2027-07-11","23:59:00","77 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-016885/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,48,49,"2027-12-05","18:00:00","2027-12-07","06:00:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-016899/24","Česká Třebová - Brno","< >","Odb Zádulka","Č.Třebová vjezd.sk.",2026,2026,48,48,"2026-11-23","00:00:00","2026-11-24","23:59:00","2 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. jen TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,3,53,"2026-01-14","00:00:00","2026-12-31","23:59:00","352 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-06-30T07:51:18",null,"1,2,7"]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,24,53,"2026-06-14","00:00:00","2026-12-31","23:59:00","201 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-06-30T07:51:18",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016907/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18",null,"3,4,5,6"]
[null,"SZCZ","V-016907/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,7,9,"2026-02-14","00:00:00","2026-02-28","23:59:00","15 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016922/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,2,7"]
[null,"SZCZ","V-016925/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,6,7"]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,3,7,"2026-01-14","00:00:00","2026-02-13","23:59:00","31 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,2,3,4,6,7"]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,24,44,"2026-06-14","00:00:00","2026-10-27","23:59:00","96 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"2,3"]
[null,"SZCZ","V-016991/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,13,27,"2026-03-23","00:00:00","2026-07-01","23:59:00","69 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19",null,"3,4,5"]
[null,"SZCZ","V-017126/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Odb Les",2027,2027,22,49,"2027-06-03","00:00:00","2027-12-11","23:59:00","192 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"200 + TV. ",null,null,null,"2025-06-30T07:51:20",null,"1,2,3,4,7"]
[null,"SZCZ","V-017126/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Odb Les",2027,2027,22,49,"2027-06-03","00:00:00","2027-12-11","23:59:00","192 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"200 + TV. ",null,null,null,"2025-06-30T07:51:20",null,"1,2,5,6,7"]
[null,"SZCZ","V-017128/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2027,2027,53,22,"2027-01-01","00:00:00","2027-06-02","23:59:00","153 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2025-06-30T07:51:22"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017131/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2027,2027,39,40,"2027-09-27","00:00:00","2027-10-10","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017131/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2027,2027,39,40,"2027-09-27","00:00:00","2027-10-10","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:52:53",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,18,19,"2027-05-07","00:00:00","2027-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice.",null,null,null,"2025-06-30T07:52:53",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,18,19,"2027-05-07","00:00:00","2027-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice.",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2027,2027,48,52,"2027-12-01","00:00:00","2027-12-31","23:59:00","31 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2027,2027,50,52,"2027-12-17","00:00:00","2027-12-31","23:59:00","15 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-06-30T07:52:53"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-06-30T10:22:35"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-06-30T07:51:15",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017141/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2027,2027,34,35,"2027-08-26","00:00:00","2027-08-31","23:59:00","6 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:15",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-03","23:59:00","278 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:16"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,5,48,"2027-02-01","00:00:00","2027-12-03","23:59:00","306 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Předměřice nad Labem",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2027,2027,11,28,"2027-03-16","00:00:00","2027-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L..",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2027,2027,11,28,"2027-03-16","00:00:00","2027-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L..",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017175/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2027,2027,7,8,"2027-02-15","00:00:00","2027-02-28","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017279/20","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Horní Lideč",2026,2026,17,22,"2026-04-21","00:00:00","2026-05-31","23:59:00","41 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017279/20","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Horní Lideč",2026,2026,17,22,"2026-04-21","00:00:00","2026-05-31","23:59:00","41 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017279/20","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Horní Lideč",2026,2026,17,22,"2026-04-21","00:00:00","2026-05-31","23:59:00","41 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Schirnding",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,19,20,"2026-05-10","00:00:00","2026-05-15","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-017869/22","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2026,2026,18,31,"2026-05-01","00:00:00","2026-07-29","23:59:00","90 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1., 2. + TV. ",null,null,null,"2025-06-30T07:51:18",null,"1,4,5,6,7"]
[null,"SZCZ","V-017869/22","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2026,2026,18,31,"2026-05-01","00:00:00","2026-07-29","23:59:00","90 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1., 2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-017869/22","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2026,2026,18,31,"2026-05-01","00:00:00","2026-07-29","23:59:00","90 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-017870/22","Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín-Bečva",2026,2026,18,22,"2026-05-01","00:00:00","2026-05-31","23:59:00","31 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-017870/22","Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín-Bečva",2026,2026,18,22,"2026-05-01","00:00:00","2026-05-31","23:59:00","31 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-017870/22","Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín-Bečva",2026,2026,18,22,"2026-05-01","00:00:00","2026-05-31","23:59:00","31 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-017964/22","Plzen - Praha","< >","Ejpovice","Chrást u Plzně",2026,2026,23,27,"2026-06-01","00:00:00","2026-06-30","23:59:00","30 days","Continuous","Bridge","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018141/22","Česká Třebová - Brno","< >","Rájec-Jestřebí","Skalice nad Svitavou",2026,2026,15,16,"2026-04-06","00:00:00","2026-04-13","23:59:00","8 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. PZS v km 188,870 (P6807).",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018256/22","Česká Třebová - Brno","< >","Skalice nad Svitavou","Letovice",2026,2026,19,20,"2026-05-04","00:00:00","2026-05-11","23:59:00","8 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař.  PZS km 199,369 (P6813).",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018417/22","Děčín - Kolín","< >","Všetaty","Dřísy",2026,2026,23,25,"2026-06-01","00:00:00","2026-06-16","23:59:00","16 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018418/22","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,27,29,"2026-07-01","00:00:00","2026-07-16","23:59:00","16 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018423/23","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2026,2026,3,4,"2026-01-14","00:00:00","2026-01-25","23:59:00","24 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T07:52:52"]
[null,"SZCZ","V-018423/23","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2026,2026,3,4,"2026-01-14","00:00:00","2026-01-25","23:59:00","24 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-06-30T10:22:35"]
[null,"SZCZ","V-018453/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T10:23:08"]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T10:23:08"]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,37,38,"2027-09-16","00:00:00","2027-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:15"]
[null,"SZCZ","V-018463/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:16"]
[null,"SZCZ","V-018463/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-018465/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018465/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018467/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:19"]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,41,43,"2027-10-17","00:00:00","2027-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,41,43,"2027-10-17","00:00:00","2027-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018467/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,6,7,"2026-02-02","00:00:00","2026-02-13","23:59:00","12 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-018467/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,6,7,"2026-02-02","00:00:00","2026-02-13","23:59:00","12 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. "]
[null,"SZCZ","V-018467/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,6,7,"2026-02-02","00:00:00","2026-02-13","23:59:00","12 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018468/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,6,7,"2026-02-07","18:00:00","2026-02-09","06:00:00","2 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018468/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,6,7,"2026-02-07","18:00:00","2026-02-09","06:00:00","2 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018468/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,6,7,"2026-02-07","18:00:00","2026-02-09","06:00:00","2 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018470/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,7,26,"2026-02-14","00:00:00","2026-06-25","23:59:00","132 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:36"]
[null,"SZCZ","V-018470/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,7,28,"2026-02-14","00:00:00","2026-07-09","23:59:00","146 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:16"]
[null,"SZCZ","V-018470/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,7,28,"2026-02-14","00:00:00","2026-07-09","23:59:00","146 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:17"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,26,46,"2026-06-26","00:00:00","2026-11-09","23:59:00","137 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:17"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,28,49,"2026-07-10","00:00:00","2026-12-03","23:59:00","147 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:21"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,28,49,"2026-07-10","00:00:00","2026-12-03","23:59:00","147 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-018472/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,14,16,"2026-03-30","00:00:00","2026-04-17","23:59:00","19 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:52"]
[null,"SZCZ","V-018472/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,46,48,"2026-11-10","00:00:00","2026-11-27","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-018472/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,13,17,"2026-03-27","00:00:00","2026-04-21","23:59:00","26 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,48,51,"2026-11-28","00:00:00","2026-12-14","23:59:00","17 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,35,38,"2026-08-30","00:00:00","2026-09-16","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,35,39,"2026-08-27","00:00:00","2026-09-21","23:59:00","26 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018478/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,44,45,"2027-11-02","00:00:00","2027-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,44,45,"2027-11-02","00:00:00","2027-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018491/22","Děčín - Kolín","< >","Nymburk hl.n.","Velký Osek",2026,2026,47,47,"2026-11-18","00:00:00","2026-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Nymburk hl.n.",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","15 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,null,null,null,null,"2024-01-05"]
[null,"SZCZ","V-018974/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,17,18,"2026-04-25","00:00:00","2026-04-29","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018974/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,17,18,"2026-04-25","00:00:00","2026-04-29","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018975/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,18,19,"2026-04-30","00:00:00","2026-05-04","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018975/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,18,19,"2026-04-30","00:00:00","2026-05-04","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018980/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,27,28,"2026-06-30","00:00:00","2026-07-07","23:59:00","8 x 4 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:12"]
[null,"SZCZ","V-018999/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Sázava u Žďáru",2026,2026,30,30,"2026-07-20","18:00:00","2026-07-21","06:00:00","2 x 6 hours","Periodical","Catenary",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-06-30T10:22:36"]
[null,"SZCZ","V-019000/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Přibyslav",2026,2026,36,37,"2026-09-01","18:00:00","2026-09-13","06:00:00","12 x 6 hours","Periodical","Catenary",null,"LT",null,null,"X",null,null,null,null,null,"1.,2 jen TV. ",null,null,null,"2025-06-30T10:22:36"]
[null,"SZCZ","V-019012/24","Kolín - Brno-Maloměřice","< >","Sázava u Žďáru","Přibyslav",2026,2026,40,41,"2026-10-01","18:00:00","2026-10-09","06:00:00","8 x 6 hours","Periodical","Catenary",null,"LT",null,null,"X",null,null,null,null,null,"1.,2 jen TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-019018/21","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,8,33,"2026-02-16","00:00:00","2026-08-16","23:59:00","182 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:18"]
[null,"SZCZ","V-019018/21","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,27,53,"2026-06-29","00:00:00","2026-12-31","23:59:00","186 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,34,42,"2026-08-17","00:00:00","2026-10-18","23:59:00","63 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:51:23"]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2027,2027,2,17,"2027-01-16","00:00:00","2027-05-02","23:59:00","107 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-019263/24","Břeclav - Kúty","< >","Lanžhot st.hr.","Lanžhot",2025,2025,14,50,"2025-03-31","16:00:00","2025-12-13","12:00:00","256 days + 20 hours","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"část 2. TK bez TV",null,null,null,"2025-06-30T07:52:54"]
[null,"SZCZ","V-019703/21","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2025,2025,26,45,"2025-06-28","00:00:00","2025-11-05","23:59:00","131 days","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:56"]
[null,"SZCZ","V-019703/21","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2025,2025,26,45,"2025-06-28","00:00:00","2025-11-05","23:59:00","131 days","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:56"]
[null,"SZCZ","V-020209/22","Kolín - Brno-Maloměřice","< >","Tišnov","Řikonín",2027,2027,9,44,"2027-03-01","00:00:00","2027-11-01","23:59:00","246 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-06-30T07:52:56"]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:56",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:56",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:52:56",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-020678/19","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2025,2025,48,51,"2025-11-29","00:00:00","2025-12-15","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T07:52:56",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-020678/19","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2025,2025,48,51,"2025-11-29","00:00:00","2025-12-15","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:04",null,"3,4,5"]
[null,"SZCZ","V-020685/19","Plzen - Praha","< >","Praha-Smíchov","Odb Závodiště",2026,2026,34,43,"2026-08-19","00:00:00","2026-10-19","23:59:00","62 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-06-30T10:22:26"]
[null,"SZCZ","V-020763/21","Kolín - Brno-Maloměřice","< >","Vlkov u Tišnova","Křižanov",2027,2027,26,26,"2027-07-01","00:00:00","2027-07-03","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:26"]
[null,"SZCZ","V-020765/21","Kolín - Brno-Maloměřice","< >","Vlkov u Tišnova","Křižanov",2027,2027,45,45,"2027-11-10","00:00:00","2027-11-13","23:59:00","4 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-06-30T10:22:26"]
[null,"SZCZ","V-020814/21","Kolín - Brno-Maloměřice","< >","Křižanov","Vlkov u Tišnova",2027,2027,6,8,"2027-02-10","00:00:00","2027-02-25","23:59:00","16 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-06-30T10:22:28"]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,10,12,"2027-03-08","00:00:00","2027-03-24","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:29"]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,45,47,"2027-11-08","00:00:00","2027-11-24","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:34",null,"1,6,7"]
[null,"SZCZ","V-021006/24","Chocen - Hranice na Morave","< >","Česká Třebová","Česká Třebová",2025,2025,11,46,"2025-03-13","08:00:00","2025-11-11","17:00:00","243 days + 9 hours","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,null,null,null,null,"2025-06-30T10:22:34",null,"2,3,4"]
[null,"SZCZ","V-023240/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Borohrádek",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:51:13",null,"2,3,4,5"]
[null,"SZCZ","V-023240/18","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:51:13",null,"1,2,3,4,5,7"]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:51:13",null,"1,6,7"]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-06-30T07:51:14",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-023794/19","Chocen - Hranice na Morave","< >","Polom","Suchdol nad Odrou",2025,2025,45,48,"2025-11-09","00:00:00","2025-11-29","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:15",null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-023795/19","Chocen - Hranice na Morave","< >","Suchdol nad Odrou","Polom",2025,2025,48,51,"2025-11-30","00:00:00","2025-12-20","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:15",null,"1,2,3,7"]
[null,"SZCZ","V-023797/19","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2026,2026,10,25,"2026-03-08","00:01:00","2026-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:17",null,"1,5,6,7"]
[null,"SZCZ","V-023797/19","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2026,2026,10,25,"2026-03-08","00:00:00","2026-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:17",null,"1,2,3"]
[null,"SZCZ","V-023857/19","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,10,25,"2026-03-08","00:00:00","2026-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,2,7"]
[null,"SZCZ","V-023857/19","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,10,25,"2026-03-08","00:00:00","2026-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-06-30T07:51:19",null,"3,4"]
[null,"SZCZ","V-023891/19","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2026,2026,10,10,"2026-03-03","00:00:00","2026-03-04","23:59:00","2 x 2 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-06-30T07:51:19",null,"1,2,5,6,7"]
[null,"ŽSR",5625269,"Zilina - Cierna nad Tisou","< >","Nižná Myšľa","Ruskov",2024,2025,22,52,"2024-06-01","08:00:00","2025-12-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,null,null,"2025-06-30T07:51:19",null,"1,2,3,6,7"]
[null,"ŽSR",5625271,"Zilina - Cierna nad Tisou","< >","Spišská Nová Ves","Vydrník",2024,2026,31,31,"2024-08-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105,null,null,null,"2025-06-30T07:51:19",null,"1,2,3,4,7"]
[null,"ŽSR",5625272,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,1,14,"2024-01-01","08:00:00","2026-03-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105,null,null,null,"2025-06-30T07:51:19",null,"1,2,3,4,5"]
[null,"ŽSR",5625274,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01","08:00:00","2026-06-30","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y",null,"2025-06-30T07:51:20",null,"1,2,3,4,7"]
[null,"ŽSR",5625275,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,14,31,"2024-04-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"105, TK 1/2, Modernizácia",null,null,null,"2025-06-30T07:51:20",null,"1,2,3,7"]
[null,"ŽSR",5626156,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad Tatry",2025,2028,9,4,"2025-03-02","08:00:00","2028-01-29","17:00:00",null,"Continuous","miscellaneous",null,"x","x",null,null,null,null,null,null,null,"Modernisation",null,"Y",null,"2025-06-30T07:51:20",null,"3,4,5,6"]
[null,"ŽSR","056KE2212131","Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01T08:00:00",45778.333333333336,"2026-06-30T16:00:00","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y",null,"2025-06-30T07:51:21",null,"6,7"]
[null,"ŽSR","3317/00/2025","Zilina - Cierna nad Tisou","< >","Košice","Košice",2025,2025,22,52,"2025-06-01","08:00:00","2025-12-31","16:00:00",null,"Periodical","signal&control",null,"LT",null,null,null,null,null,null,null,null,"modernizácia stavadla",null,"Y",null,"2025-06-30T07:51:21",null,"2,3,4,5"]
[null,"ŽSR","56TT2311001","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ETCS",null,null,null,"2025-06-30T07:51:21",null,"1,5,6,7"]
[null,"ŽSR","56TT2311001","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"ETCS",null,null,null,"2025-06-30T07:51:21",null,"6,7"]
[null,"ŽSR","56TT2311002","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,"Y",null,"2025-06-30T07:51:22"]
[null,"ŽSR","56TT2311003","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2025,2025,1,52,"2025-01-01","08:00:00","2025-12-31","17:00:00",null,"Periodical","Bridge",null,"LT",null,null,null,null,null,null,null,null,"Komplexná rekonštrukcia diaľnično-železničného mosta",null,"Y",null,"2024-01-05"]
[null,"ŽSR","56TT2311007","Bratislava - Štúrovo","< >","Dvory nad Žitavou","Dvory nad Žitavou",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 ",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311008","Kúty - Galanta","< >","Šelpice","Boleráz",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č.1",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311009","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2024-01-05"]
[null,"ŽSR","56TT2311010","Kúty - Bratislava","< >","Malacky","Kúty",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS"]
[null,"ŽSR","56TT2311011a","Kúty - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany"]
[null,"ŽSR","56TT2311011b","Kúty - Galanta","< >","Bratislava-Rača","Trnava",2025,2026,1,9,"2025-01-01T08:00:00",45658.333333333336,"2026-02-28T17:00:00","00:00:00","371 x 23h 59min every week","Periodical","signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava",null,"N"]
[null,"ŽSR","56TT2311012","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves"]
[null,"ŽSR","56TT2311013","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)"]
[null,"ŽSR","A13225","Zilina - Cierna nad Tisou","< >","Bánovce nad Ondavou","Humenné",2025,2026,44,23,"2025-11-01","00:01:00","2026-06-01","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Elektrifikácia a modernizácia staničných koľají a výhybiek a traťovej koľaje",null,"Y"]

{"sheet":"Graphic Overview","index":2,"n_rows":202,"n_cols":374,"rows_kept":202,"cut":false,"hidden":false,"merged":[[3,371,3,373],[3,98,3,104],[3,105,3,111],[3,112,3,118],[3,119,3,125],[3,126,3,132],[3,231,3,237],[3,238,3,244],[3,245,3,251],[3,252,3,258],[3,259,3,265],[3,266,3,272],[3,273,3,279],[3,280,3,286],[3,287,3,293],[3,294,3,300],[3,336,3,342],[3,343,3,349],[3,350,3,356],[3,357,3,363],[3,364,3,370],[3,147,3,153],[3,308,3,314],[3,315,3,321],[3,322,3,328],[3,329,3,335],[3,210,3,216],[3,217,3,223],[3,224,3,230],[3,154,3,160],[3,161,3,167],[3,168,3,174],[3,175,3,181],[3,182,3,188],[0,1,1,7],[2,9,2,39],[2,282,2,312],[2,99,2,128],[2,129,2,159],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,40,2,67],[2,68,2,98],[3,42,3,48],[3,49,3,55],[3,56,3,62],[2,343,2,373],[2,313,2,342],[3,63,3,69],[3,70,3,76],[3,77,3,83],[3,84,3,90],[3,91,3,97],[3,301,3,307],[3,133,3,139],[3,140,3,146],[3,189,3,195],[3,196,3,202],[3,203,3,209],[3,9,3,13],[3,14,3,20],[3,21,3,27],[3,28,3,34],[3,35,3,41]]}
[null,"RFC 9 Overview"]
[]
[null,null,null,null,null,null,2025,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Frankfurt - Karlsruhe",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Karlsruhe - Strasbourg",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Darmstadt - Nürnberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Nürnberg - Passau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5]
[null," "]
[]
[null,"Nürnberg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,5,5,2,2]
[null," "]
[]
[null,"Regensburg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Passau - Wels"]
[null," "]
[]
[null,"Karlsruhe - München",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"München - Salzburg"]
[null," "]
[]
[null,"München - Regensburg"]
[null," "]
[]
[null,"Salzburg - Wels",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Wels - Linz",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Wels - Traun - Linz",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Linz - Wien (NRZ)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Linz - Wien (GZ)",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Wien - Hegyeshalom",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Sopron - Györ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Hegyeshalom - Rajka"]
[null," "]
[]
[null,"Hegyeshalom-Ferencváros",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Ferencváros-Szajol",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Ferencváros-Szajol (120)"]
[null," "]
[]
[null,"Szajol-Curtici"]
[null," "]
[]
[null,"Szajol - Biharkeresztes"]
[null," "]
[]
[null,"Arad - Simeria",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Arad - Craiova",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Simeria -  Brasov",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Bucuresti-Constanta"]
[null," "]
[]
[null,"Coslariu - Cluj Napoca"]
[null," "]
[]
[null,"Biharkeresztes - Cluj Napoca",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Curtici - Arad"]
[null," "]
[]
[null,"Wilhelmshaven - Bremen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Bremerhaven - Bremen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Bremen - Hannover",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,6,6,6,6,6,2,2,2,2,2,2,6,6,6,6,6,6]
[null," "]
[]
[null,"Hannover - Magdeburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,null,null,null,null,null,null,null,2]
[null," "]
[]
[null,"Magdeburg - Falkenberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Falkenberg - Dresden",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Hamburg - Magdeburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Rostock - Berlin"]
[null," "]
[]
[null,"Rostock-Berlin-Dresden",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Dresden - Děčín",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Děčín - Kolín",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,1,1,1,1,1,3,3,1,1,1,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,1,1,1,1,1]
[null," "]
[]
[null,"Děčín - Praha-Libeň",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Praha - Chocen - Česká Třebová",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null," "]
[]
[null,"Hranice na Morave - Ostrava"]
[null," "]
[]
[null,"Plzen - Praha",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Zilina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ostrava - Zilina",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,3,3,3]
[null," "]
[]
[null,"Zilina - Cierna nad Tisou",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kolín - Brno-Maloměřice",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Česká Třebová - Brno",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,null,null,null,null,null,1,1,1,1]
[null," "]
[]
[null,"Brno - Břeclav",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Břeclav - Wien",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Břeclav - Kúty",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kúty - Bratislava",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Rajka",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Bratislava - Štúrovo"]
[null," "]
[]
[null,"Nové Zámky - Komárom"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Rajka - Hegyeshalom",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Štúrovo - Ferencváros"]
[null," "]
[]
[null,"Kúty - Galanta",null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Chocen - Hranice na Morave",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[]
[]
[]
[null,"Error in *All day*, *Day* or *Night*"]
[null,"| 5802 | 5806 | 5821 | 5822 | 5823 | 5835 | 5837 | 5846 "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":65,"n_cols":23,"rows_kept":65,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Frankfurt - Karlsruhe",1,"< >","Continuous",26529,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Karlsruhe - Strasbourg",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Darmstadt - Nürnberg",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Nürnberg - Passau",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Nürnberg - Plzen",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Regensburg - Plzen",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["SNCF-R",87,"Passau - Wels",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["CFR",53,"Karlsruhe - München",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,"München - Salzburg",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"München - Regensburg",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Salzburg - Wels",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Wels - Linz",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Wels - Traun - Linz",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Linz - Wien (NRZ)",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Linz - Wien (GZ)",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"Wien - Hegyeshalom",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"Wien - Ebenfurth - Sopron",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Sopron - Györ",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Rajka - Hegyeshalom",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Hegyeshalom - Rajka",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Hegyeshalom-Ferencváros",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Ferencváros-Szajol",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Ferencváros-Szajol (120)",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Szajol-Curtici",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Szajol - Biharkeresztes",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Arad - Simeria",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Arad - Craiova",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Simeria -  Brasov",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Bucuresti-Constanta",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Coslariu - Cluj Napoca",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Biharkeresztes - Cluj Napoca",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Curtici - Arad",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Wilhelmshaven - Bremen",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Bremerhaven - Bremen",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Bremen - Hannover",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Hannover - Magdeburg",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Magdeburg - Falkenberg",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Falkenberg - Dresden",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Hamburg - Magdeburg",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Rostock - Berlin",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Rostock-Berlin-Dresden",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Dresden - Děčín",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Děčín - Kolín",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Děčín - Praha-Libeň",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Praha - Chocen - Česká Třebová",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Hranice na Morave - Ostrava",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Plzen - Praha",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,"Hranice na Morave - Zilina",48,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,"Ostrava - Zilina",49,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,"Zilina - Cierna nad Tisou",50,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,"Kolín - Brno-Maloměřice",51,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,"Česká Třebová - Brno",52,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]
[null,null,"Brno - Břeclav",53]
[null,null,"Břeclav - Wien",54]
[null,null,"Břeclav - Kúty",55]
[null,null,"Kúty - Bratislava",56]
[null,null,"Bratislava - Rajka",57]
[null,null,"Bratislava - Štúrovo",58]
[null,null,"Nové Zámky - Komárom",59]
[null,null,"Kúty - Galanta",60]
[null,null,"Rajka - Hegyeshalom",61]
[null,null,"Štúrovo - Ferencváros",62]
[null,null,"Kúty - Galanta",63]
[null,null,"Chocen - Hranice na Morave",64]