{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":3,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2026,1]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":4750,"n_cols":37,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,34,2,34],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Weekdays","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"CFR",5326073,"Arad - Craiova","< >","Aradu Nou","Arad",2026,2027,43,17,"2026-10-23","00:00:00","2027-04-26","23:59:00","186d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-22"]
[null,"CFR",5326077,"Arad - Craiova","< >","Aradul Nou","Zădăreni ",2025,2026,2,4,"2025-01-09","00:00:00","2026-01-23","23:59:00","380d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-01-10"]
[null,"CFR",5326146,"Arad - Craiova","< >","Aradul Nou",null,2025,2026,4,4,"2025-01-21","00:00:00","2026-01-23","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5326147,"Arad - Craiova","< >","Aradul Nou",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525809,"Arad - Craiova","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525808,"Arad - Craiova","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326134,"Arad - Craiova","< >","Baile Calacea","Orțișoara",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326133,"Arad - Craiova","< >","Băile Calacea",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326039,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326102,"Arad - Craiova","< >","Belinț",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326103,"Arad - Craiova","< >","Belinț","Chizătău",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326115,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326117,"Arad - Craiova","< >","Belinț","Topolovat",2026,2027,45,22,"2026-11-03","00:00:00","2027-06-02","23:59:00","212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326019,"Arad - Craiova","< >","Caransebes","Balta Sărată",2026,2026,27,28,"2026-07-03","00:00:00","2026-07-06","23:59:00","4d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326079,"Arad - Craiova","< >","Caransebes",null,2025,2026,12,28,"2025-03-19","00:00:00","2026-07-06","23:59:00","475d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326080,"Arad - Craiova","< >","Caransebes",null,2026,2027,28,40,"2026-07-07","00:00:00","2027-10-04","23:59:00","455d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326021,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2026,2026,28,44,"2026-07-07","00:00:00","2026-11-01","23:59:00","118d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326023,"Arad - Craiova","< >","Caransebes ","Zăgujeni",2025,2026,31,36,"2025-07-30","00:00:00","2026-09-01","23:59:00","399d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326089,"Arad - Craiova","< >","Căvăran",null,2024,2026,49,18,"2024-12-03","00:00:00","2026-05-02","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326090,"Arad - Craiova","< >","Căvăran",null,2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5326092,"Arad - Craiova","< >","Căvăran","Găvojdia",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5326040,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-24"]
[null,"CFR",5326104,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326116,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326093,"Arad - Craiova","< >","Găvojdia",null,2026,2026,11,12,"2026-03-14","00:00:00","2026-03-18","23:59:00","5d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326094,"Arad - Craiova","< >","Găvojdia",null,2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5326095,"Arad - Craiova","< >","Găvojdia",null,2026,2026,12,36,"2026-03-19","00:00:00","2026-09-01","23:59:00","167d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326096,"Arad - Craiova","< >","Găvojdia","Lugoj",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5326078,"Arad - Craiova","< >","Glogovăț","Arad",2027,2027,39,41,"2027-10-01","00:00:00","2027-10-17","23:59:00","17d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-25"]
[null,"CFR",5326148,"Arad - Craiova","< >","Glogovăț","Arad",2026,2026,4,38,"2026-01-23","00:00:00","2026-09-18","23:59:00","239d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5326149,"Arad - Craiova","< >","Glogovăț","Arad",2026,2027,38,2,"2026-09-18","00:00:00","2027-01-17","23:59:00","122d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5525812,"Arad - Craiova","< >","Glogovăț","Arad",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5525813,"Arad - Craiova","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5326038,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-28"]
[null,"CFR",5326101,"Arad - Craiova","< >","Jabăr","Belinț",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5326114,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5326091,"Arad - Craiova","< >","Jena","Găvojdia",2026,2026,18,18,"2026-04-27","00:00:00","2026-05-02","23:59:00","6d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-29"]
[null,"CFR",5326037,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-29"]
[null,"CFR",5326042,"Arad - Craiova","< >","Lugoj","Costeiu Mare",2026,2026,8,14,"2026-02-21","00:00:00","2026-04-02","23:59:00","41d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-01"]
[null,"CFR",5326099,"Arad - Craiova","< >","Lugoj",null,2025,2026,28,27,"2025-07-10","00:00:00","2026-07-03","23:59:00","359d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5326100,"Arad - Craiova","< >","Lugoj","Jabăr",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5326113,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5326118,"Arad - Craiova","< >","Lugoj – Belint","Lugoj – Belint",2026,2027,45,14,"2026-11-03","00:00:00","2027-04-06","23:59:00","155d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5326067,"Arad - Craiova","< >","Orțișoara",null,2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19"]
[null,"CFR",5326068,"Arad - Craiova","< >","Orțișoara",null,2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-02"]
[null,"CFR",5326076,"Arad - Craiova","< >","Orțișoara","Aradu Nou",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19"]
[null,"CFR",5326136,"Arad - Craiova","< >","Orțișoara",null,2025,2027,43,4,"2025-10-24","00:00:00","2027-01-25","23:59:00","459d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5326137,"Arad - Craiova","< >","Orțișoara","Vinga",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5525814,"Arad - Craiova","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5525811,"Arad - Craiova","< >","Ramificație Pod Mureș ","Glogovăț",2025,2026,32,19,"2025-08-08","00:00:00","2026-05-08","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-22"]
[null,"CFR",5326108,"Arad - Craiova","< >","Recaș",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326109,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-07-24"]
[null,"CFR",5326111,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326097,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2026,27,43,"2025-07-03","00:00:00","2026-10-23","23:59:00","478d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326110,"Arad - Craiova","< >","Remetea Mare",null,2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326112,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326119,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2027,2027,15,18,"2027-04-15","00:00:00","2027-05-04","23:59:00","20d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326069,"Arad - Craiova","< >","Ronat Triaj Gr.D","Orțișoara",2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07"]
[null,"CFR",5326128,"Arad - Craiova","< >","Ronat Triaj Gr.D","Sânandrei",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326062,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2027,2027,1,2,"2027-01-05","00:00:00","2027-01-12","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-03-21"]
[null,"CFR",5525810,"Arad - Craiova","< >","Ronat Triaj Gr.D ","Vinga",2026,2026,17,19,"2026-04-24","00:00:00","2026-05-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-13"]
[null,"CFR",5326141,"Arad - Craiova","< >","Sag",null,2024,2026,43,4,"2024-10-23","00:00:00","2026-01-23","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-17"]
[null,"CFR",5326142,"Arad - Craiova","< >","Sag",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-08"]
[null,"CFR",5326072,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2026,4,21,"2026-01-23","00:00:00","2026-05-23","23:59:00","121d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-09"]
[null,"CFR",5326143,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-07"]
[null,"CFR",5525803,"Arad - Craiova","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-09"]
[null,"CFR",5326130,"Arad - Craiova","< >","Sânandrei",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326131,"Arad - Craiova","< >","Sânandrei","Baile Calacea",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326048,"Arad - Craiova","< >","Timișoara Est","Remetea Mică",2025,2026,23,36,"2025-06-02","00:00:00","2026-09-02","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13"]
[null,"CFR",5326124,"Arad - Craiova","< >","Timișoara Est","Timișoara Est",2024,2026,35,45,"2024-09-01","00:00:00","2026-11-02","23:59:00","793d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5525790,"Arad - Craiova","< >","Timișoara Est ","Timișoara Nord",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-08","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326055,"Arad - Craiova","< >","Timișoara Est  ","Timișoara Est  ",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5326056,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5326057,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2027,18,2,"2026-05-01","00:00:00","2027-01-12","23:59:00","257d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-30"]
[null,"CFR",5326058,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,22,23,"2026-05-25","00:00:00","2026-06-01","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5326061,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,44,45,"2026-10-27","00:00:00","2026-11-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5326125,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2025,2026,23,23,"2025-06-02","00:00:00","2026-06-01","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326126,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2027,23,2,"2026-06-01","00:00:00","2027-01-12","23:59:00","226d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-16"]
[null,"CFR",5326059,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14"]
[null,"CFR",5326060,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14"]
[null,"CFR",5326122,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2025,2026,6,23,"2025-02-03","00:00:00","2026-06-01","23:59:00","484d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5326127,"Arad - Craiova","< >","Timișoara Nord ",null,2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5326105,"Arad - Craiova","< >","Topolovat",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326107,"Arad - Craiova","< >","Topolovat","Recas",2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22"]
[null,"CFR",5326074,"Arad - Craiova","< >","Valea Viilor","Arad",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5326075,"Arad - Craiova","< >","Valea Viilor","Arad",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-14"]
[null,"CFR",5326144,"Arad - Craiova","< >","Valea Viilor",null,2024,2026,32,21,"2024-08-09","00:00:00","2026-05-23","23:59:00","653d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5326145,"Arad - Craiova","< >","Valea Viilor","Aradul Nou",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5525806,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326071,"Arad - Craiova","< >","Vinga","Sag",2026,2026,3,4,"2026-01-16","00:00:00","2026-01-23","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-08-13"]
[null,"CFR",5326138,"Arad - Craiova","< >","Vinga",null,2024,2026,26,4,"2024-06-25","00:00:00","2026-01-23","23:59:00","578d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5326139,"Arad - Craiova","< >","Vinga",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326140,"Arad - Craiova","< >","Vinga","Sag",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5326083,"Arad - Craiova","< >","Zăgujeni","Zăgujeni",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326087,"Arad - Craiova","< >","Zăgujeni","Căvăran",2025,2026,32,18,"2025-08-04","00:00:00","2026-05-02","23:59:00","272d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5326088,"Arad - Craiova","< >","Zăgujeni","Căvăran",2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5525759,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09"]
[null,"CFR",5525760,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09"]
[null,"CFR",5325964,"Biharkeresztes - Cluj Napoca","< >","Aghireș",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5525728,"Biharkeresztes - Cluj Napoca","< >","Alesd","Oradea",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-15"]
[null,"CFR",5325984,"Biharkeresztes - Cluj Napoca","< >","Alesd",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-15"]
[null,"CFR",5325986,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5525742,"Biharkeresztes - Cluj Napoca","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5325960,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325961,"Biharkeresztes - Cluj Napoca","< >","Baciu Triaj","Gârbău",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5525768,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5325966,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5525752,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5325976,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325975,"Biharkeresztes - Cluj Napoca","< >","Bratca ",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325973,"Biharkeresztes - Cluj Napoca","< >","Bulz",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5325974,"Biharkeresztes - Cluj Napoca","< >","Bulz","Bratca",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5525751,"Biharkeresztes - Cluj Napoca","< >","Bulz ","Bratca",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5525749,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5325979,"Biharkeresztes - Cluj Napoca","< >","Ciucea",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5325980,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5525756,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17"]
[null,"CFR",5325959,"Biharkeresztes - Cluj Napoca","< >","Cluj","Baciu Triaj",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-17"]
[null,"CFR",5525757,"Biharkeresztes - Cluj Napoca","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17"]
[null,"CFR",5325983,"Biharkeresztes - Cluj Napoca","< >","Cluj Napoca Est","Cluj",2024,2026,27,9,"2024-07-01","00:00:00","2026-02-28","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17"]
[null,"CFR",5525739,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525747,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326012,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525765,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525766,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5325962,"Biharkeresztes - Cluj Napoca","< >","Gârbău",null,2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5325963,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2024,2026,27,27,"2024-07-01","00:00:00","2026-06-30","23:59:00","730d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5525769,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325967,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5525762,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2025,2026,44,18,"01.11.2025","00:00:00","30.04.2026","23:59:00","181d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525763,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525734,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326009,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea Vest",2026,2026,9,27,"2026-03-01","00:00:00","2026-07-01","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326011,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea",2025,2027,50,19,"2025-12-11","00:00:00","2027-05-10","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525746,"Biharkeresztes - Cluj Napoca","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525745,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326004,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326006,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525730,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525740,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325999,"Biharkeresztes - Cluj Napoca","< >","Osorhei",null,2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326001,"Biharkeresztes - Cluj Napoca","< >","Osorhei","Oradea Est",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525744,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325972,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului","Bulz",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5325981,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5525750,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului ","Bulz",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525727,"Biharkeresztes - Cluj Napoca","< >","Poieni","Alesd",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5525748,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525767,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325965,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5325978,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5525770,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325968,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5525753,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325969,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2027,16,23,"2024-04-15","00:00:00","2027-06-10","23:59:00","1152d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5325977,"Biharkeresztes - Cluj Napoca","< >","Suncuius",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5525736,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325989,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5525743,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325992,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5325995,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2027,42,22,"2025-10-19","00:00:00","2027-06-02","23:59:00","592d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5525754,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,2,29,"2024-01-10","00:00:00","2026-07-19","23:59:00","922d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-06-13"]
[null,"CFR",5325970,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului",null,2024,2026,16,9,"2024-04-15","00:00:00","2026-02-26","23:59:00","683d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13"]
[null,"CFR",5325971,"Biharkeresztes - Cluj Napoca","< >","Vadul Crisului","Alesd",2024,2026,41,9,"2024-10-10","00:00:00","2026-02-26","23:59:00","505d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13"]
[null,"CFR",5325953,"Simeria -  Brasov","< >","Albești","Sighișoara",2025,2026,17,10,"2025-04-24","00:00:00","2026-03-04","23:59:00","315d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5325917,"Simeria -  Brasov","< >","Apata","Augustin",2025,2026,46,32,"2025-11-10","00:00:00","2026-08-03","23:59:00","267d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5325910,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5325911,"Simeria -  Brasov","< >","Apața",null,2021,2026,18,17,"2021-05-05","00:00:00","2026-04-20","23:59:00","1812d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-03"]
[null,"CFR",5325912,"Simeria -  Brasov","< >","Apața",null,2026,2026,17,33,"2026-04-20","00:00:00","2026-08-14","23:59:00","117d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5325913,"Simeria -  Brasov","< >","Apața",null,2026,2026,33,44,"2026-08-15","00:00:00","2026-10-30","23:59:00","77d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5325914,"Simeria -  Brasov","< >","Apața",null,2026,2027,44,28,"2026-10-31","00:00:00","2027-07-15","23:59:00","258d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5325915,"Simeria -  Brasov","< >","Apața",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5525665,"Simeria -  Brasov","< >","Archita","Vînători ",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5525712,"Simeria -  Brasov","< >","Archita","Vânători ",2025,2026,51,7,"2025-12-21","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-05"]
[null,"CFR",5325938,"Simeria -  Brasov","< >","Archita ","Vînători ",2027,2028,43,8,"2027-10-26","00:00:00","2028-02-26","23:59:00","124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5325919,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06"]
[null,"CFR",5325921,"Simeria -  Brasov","< >","Augustin","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-06"]
[null,"CFR",5325936,"Simeria -  Brasov","< >","Beia","Mureni",2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5325937,"Simeria -  Brasov","< >","Beia","Mureni",2026,2027,10,43,"2026-03-05","00:00:00","2027-10-25","23:59:00","600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525659,"Simeria -  Brasov","< >","Beia","Mureni",2023,2026,44,40,"30.10.2023","00:00:00","30.09.2026","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5325892,"Simeria -  Brasov","< >","Bod",null,2025,2027,30,28,"2025-07-23","00:00:00","2027-07-15","23:59:00","723d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3",1]
[null,"CFR",5325893,"Simeria -  Brasov","< >","Bod",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5325896,"Simeria -  Brasov","< >","Bod","Feldioara",2025,2026,27,19,"2025-07-04","00:00:00","2026-05-06","23:59:00","307d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325897,"Simeria -  Brasov","< >","Bod","Feldioara",2026,2027,19,48,"2026-05-06","00:00:00","2027-12-05","23:59:00","579d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5325898,"Simeria -  Brasov","< >","Bod","Feldioara",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5525683,"Simeria -  Brasov","< >","Bod","Feldioara",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5325874,"Simeria -  Brasov","< >","Brașov",null,2025,2027,46,8,"2025-11-16","00:00:00","2027-02-28","23:59:00","470d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,7",1]
[null,"CFR",5325875,"Simeria -  Brasov","< >","Brașov",null,2027,2027,9,28,"2027-03-01","00:00:00","2027-07-15","23:59:00","137d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"4,5",1]
[null,"CFR",5325876,"Simeria -  Brasov","< >","Brașov",null,2027,2027,28,48,"2027-07-16","00:00:00","2027-12-05","23:59:00","143d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4",1]
[null,"CFR",5325879,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5,6,7",1]
[null,"CFR",5325880,"Simeria -  Brasov","< >","Brașov","Stupini",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5525677,"Simeria -  Brasov","< >","Brașov","Stupini",2023,2026,22,12,"01.06.2023","00:00:00","16.03.2026","23:59:00","1020d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5325928,"Simeria -  Brasov","< >","Cata","Rupea",2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"2,3",1]
[null,"CFR",5325929,"Simeria -  Brasov","< >","Cata","Rupea",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"2,3",1]
[null,"CFR",5325930,"Simeria -  Brasov","< >","Cata",null,2024,2026,6,3,"2024-02-08","00:00:00","2026-01-14","23:59:00","707d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325931,"Simeria -  Brasov","< >","Cata",null,2026,2026,3,42,"2026-01-15","00:00:00","2026-10-15","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325932,"Simeria -  Brasov","< >","Cata",null,2026,2027,42,7,"2026-10-15","00:00:00","2027-02-16","23:59:00","125d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5325933,"Simeria -  Brasov","< >","Cata","Beia",2025,2026,3,3,"2025-01-15","00:00:00","2026-01-14","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325934,"Simeria -  Brasov","< >","Cata","Beia",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325935,"Simeria -  Brasov","< >","Cata","Beia",2027,2027,7,43,"2027-02-17","00:00:00","2027-10-25","23:59:00","251d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,5,6,7",1]
[null,"CFR",5525657,"Simeria -  Brasov","< >","Cata","Rupea",2023,2026,5,50,"02.02.2023","00:00:00","12.12.2026","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"5,6,7",1]
[null,"CFR",5525658,"Simeria -  Brasov","< >","Cața","Beia",2023,2026,5,9,"02.02.2023","00:00:00","01.03.2026","23:59:00","1124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-09-24",null,null,"1,5,6,7",1]
[null,"CFR",5525663,"Simeria -  Brasov","< >","Cața","Archita",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525703,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525710,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325866,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,6,6,"2026-02-02","00:00:00","2026-02-08","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325867,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,30,33,"2026-07-24","00:00:00","2026-08-14","23:59:00","22d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325901,"Simeria -  Brasov","< >","Feldioara",null,2025,2026,27,17,"2025-07-04","00:00:00","2026-04-23","23:59:00","294d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325902,"Simeria -  Brasov","< >","Feldioara",null,2026,2027,17,28,"2026-04-23","00:00:00","2027-07-15","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325903,"Simeria -  Brasov","< >","Feldioara",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325905,"Simeria -  Brasov","< >","Feldioara","Apața",2025,2026,27,6,"2025-07-04","00:00:00","2026-02-02","23:59:00","214d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325906,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,7,30,"2026-02-09","00:00:00","2026-07-23","23:59:00","165d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325907,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,33,49,"2026-08-15","00:00:00","2026-11-30","23:59:00","108d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325908,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2027,49,48,"2026-11-30","00:00:00","2027-12-05","23:59:00","371d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325909,"Simeria -  Brasov","< >","Feldioara","Apața",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5525689,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525691,"Simeria -  Brasov","< >","Feldioara","Apața",2024,2026,30,12,"28.07.2024","00:00:00","16.03.2026","23:59:00","597d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325939,"Simeria -  Brasov","< >","Mureni",null,2024,2026,42,10,"2024-10-15","00:00:00","2026-03-04","23:59:00","506d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325941,"Simeria -  Brasov","< >","Mureni","Vînători",2025,2027,35,43,"2025-08-30","00:00:00","2027-10-25","23:59:00","787d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-23",null,null,"6,7",1]
[null,"CFR",5525666,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2026,45,40,"09.11.2022","00:00:00","30.09.2026","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5325924,"Simeria -  Brasov","< >","Rupea","Racos",2025,2026,35,25,"2025-08-25","00:00:00","2026-06-15","23:59:00","295d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5325926,"Simeria -  Brasov","< >","Rupea","Cata",2025,2026,30,31,"2025-07-25","00:00:00","2026-07-27","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5325927,"Simeria -  Brasov","< >","Rupea","Cata",2026,2026,31,38,"2026-07-28","00:00:00","2026-09-15","23:59:00","50d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325954,"Simeria -  Brasov","< >","Sighișoara",null,2024,2027,34,50,"2024-08-21","00:00:00","2027-12-15","23:59:00","1212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5325956,"Simeria -  Brasov","< >","Sighișoara",null,2023,2027,41,43,"2023-10-11","00:00:00","2027-10-25","23:59:00","1476d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-02",null,null,"6,7",1]
[null,"CFR",5325957,"Simeria -  Brasov","< >","Sighișoara",null,2023,2028,41,8,"2023-10-11","00:00:00","2028-02-26","23:59:00","1600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,7",1]
[null,"CFR",5325884,"Simeria -  Brasov","< >","Stupini",null,2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"3,4",1]
[null,"CFR",5325885,"Simeria -  Brasov","< >","Stupini",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"4,5",1]
[null,"CFR",5325888,"Simeria -  Brasov","< >","Stupini","Bod",2025,2026,14,14,"2025-04-01","00:00:00","2026-04-01","23:59:00","366d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,7",1]
[null,"CFR",5325889,"Simeria -  Brasov","< >","Stupini","Bod",2026,2027,14,48,"2026-04-01","00:00:00","2027-12-05","23:59:00","614d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5325945,"Simeria -  Brasov","< >","Vînători",null,2025,2026,35,20,"2025-08-30","00:00:00","2026-05-11","23:59:00","255d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-05-31",null,null,"1,6,7",1]
[null,"CFR",5325946,"Simeria -  Brasov","< >","Vînători",null,2026,2028,20,8,"2026-05-11","00:00:00","2028-02-26","23:59:00","657d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"1,6,7",1]
[null,"CFR",5325948,"Simeria -  Brasov","< >","Vînători","Albești",2025,2026,20,20,"2025-05-13","00:00:00","2026-05-12","23:59:00","365d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-20",null,null,"1,6,7",1]
[null,"CFR",5525667,"Simeria -  Brasov","< >","Vînători","Albești",2023,2026,24,20,"16.06.2023","00:00:00","12.05.2026","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-01",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","1FCFA-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,7",1]
[null,"DB InfraGO AG","207CA-001","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,28,35,"2026-07-10","21:00:00","2026-08-24","21:00:00","45d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","20838-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,48,50,"2026-11-27","21:00:00","2026-12-11","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"2,3",1]
[null,"DB InfraGO AG","2078A-007","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,16,16,"2026-04-17","17:00:00","2026-04-19","04:00:00","1d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"3,4",1]
[null,"DB InfraGO AG","1310-(MK27)-01","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,3,4,"22.01.2027","21:00:00","29.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1310-(MK27)-02","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"1,2",1]
[null,"DB InfraGO AG","2078A-001","Berlin - Dresden","< >","Berlin Stadtforst","Berlin Eichgestell",2026,2026,14,28,"2026-04-01","22:40:00","2026-07-10","21:00:00","99d, 22h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2078A-002","Berlin - Dresden","< >","Berlin Stadtforst","Eichgestell Nord",2026,2026,14,28,"2026-04-01","22:40:00","2026-07-10","21:00:00","99d, 22h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1CB7B-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-24","04:00:00","3d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,7,1]
[null,"DB InfraGO AG","1CD5E-003","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-18","04:00:00","1d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,1,1]
[null,"DB InfraGO AG","1CCA6-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-19","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,2,1]
[null,"DB InfraGO AG","1CCBC-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1CCBC-003","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1CCC5-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"4,5",1]
[null,"DB InfraGO AG","1CCC5-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F4BA-003","Berlin - Dresden",">","Cossebaude","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-22",null,null,7,1]
[null,"DB InfraGO AG","1F4BA-010","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F4BA-011","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-12",null,null,"2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FB4B-005","Berlin - Dresden",">","Cossebaude","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-12",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1FB4B-008","Berlin - Dresden",">","Cossebaude","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","20189-001","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","20189-002","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","20D69-003","Berlin - Dresden","<","Cossebaude","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","2103F-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,25,28,"2026-06-19","21:00:00","2026-07-10","21:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-08",null,null,"1,2",1]
[null,"DB InfraGO AG","2100C-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,27,28,"2026-07-03","21:00:00","2026-07-10","21:00:00","7d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-06",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","2100C-003","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,27,28,"2026-07-03","21:00:00","2026-07-10","21:00:00","7d, 0h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-08",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","2100C-004","Berlin - Dresden","<","Doberlug-K ob Bf","Brenitz-Sonnewalde",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-14",null,null,"6,7",1]
[null,"DB InfraGO AG","2100C-005","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,7,1]
[null,"DB InfraGO AG","2100D-001","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,6,1]
[null,"DB InfraGO AG","2100D-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2100D-003","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-Kirchhain unt Bf",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-24","21:00:00","14d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-19",null,null,"6,7",1]
[null,"DB InfraGO AG","2103F-002","Berlin - Dresden","< >","Doberlug-K ob Bf","Doberlug-K ob Bf",2026,2026,25,28,"2026-06-19","21:00:00","2026-07-10","21:00:00","21d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","2100C-006","Berlin - Dresden","< >","Doberlug-Kh Nord","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","2100C-007","Berlin - Dresden","< >","Doberlug-Kh Nord","Doberlug-K ob Bf",2026,2026,28,28,"2026-07-07","21:00:00","2026-07-08","05:00:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDD","Berlin - Dresden",">","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3097-(MK27)-01_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,38,46,"20.09.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1D63C-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,49,50,"2026-12-04","22:00:00","2026-12-07","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD70-007","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1DD70-010","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-20","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1DD70-013","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,4,4,"2026-01-20","21:00:00","2026-01-25","04:00:00","4d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1DD70-018","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,6,6,"2026-02-02","21:00:00","2026-02-04","04:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1F4E5-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,3,1]
[null,"DB InfraGO AG","1F4E5-012","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1F4E5-014","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,4,1]
[null,"DB InfraGO AG","1F4E5-016","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,4,1]
[null,"DB InfraGO AG","1F50F-002","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","00:00:00","1d, 12h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-04-17",null,null,4,1]
[null,"DB InfraGO AG","1F548-005","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-19",null,null,4,1]
[null,"DB InfraGO AG","1F548-008","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,4,1]
[null,"DB InfraGO AG","1F58D-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,5,1]
[null,"DB InfraGO AG","1F58D-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1F59E-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-17",null,null,5,1]
[null,"DB InfraGO AG","1F59E-006","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,5,1]
[null,"DB InfraGO AG","1F5C3-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","18:00:00","0d, 13h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,5,1]
[null,"DB InfraGO AG","1F5C3-017","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","1F5FE-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO AG","1F5FE-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO AG","1F672-001","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,7",1]
[null,"DB InfraGO AG","1F672-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,1,1]
[null,"DB InfraGO AG","1F672-012","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,19,19,"2026-05-09","16:00:00","2026-05-10","04:00:00","0d, 12h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-23",null,null,1,1]
[null,"DB InfraGO AG","1F722-001","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-10-25",null,null,1,1]
[null,"DB InfraGO AG","1F722-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F722-008","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,43,43,"2026-10-25","00:00:00","2026-10-25","04:00:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1F722-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,47,47,"2026-11-16","00:00:00","2026-11-16","04:00:00","0d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1F748-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","1F748-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","1F543-005","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","00:00:00","0d, 6h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2023-10-25",null,null,2,1]
[null,"DB InfraGO AG","1F543-013","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-10-25",null,null,2,1]
[null,"DB InfraGO AG","20D69-006","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2023-10-25",null,null,2,1]
[null,"DB InfraGO AG","20D69-007","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","20D69-008","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-10-18",null,null,2,1]
[null,"DB InfraGO AG","3873-(MK27)-01_D","Berlin - Dresden",">","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"04.09.2027","05:00:00","12.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","3873-(MK27)-01_N","Berlin - Dresden","< >","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"03.09.2027","21:00:00","12.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-30",null,null,3,1]
[null,"DB InfraGO AG","1DC0E-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-22",null,null,"1,6",1]
[null,"DB InfraGO AG","1DC0E-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-17",null,null,"1,7",1]
[null,"DB InfraGO AG","1DC0E-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1DC0E-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC0E-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1DC0E-008","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,3,1]
[null,"DB InfraGO AG","1DC42-004","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DC42-005","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC42-006","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-15",null,null,6,1]
[null,"DB InfraGO AG","1DC42-021","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1DC42-022","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1DCB3-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1DCB3-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-31",null,null,4,1]
[null,"DB InfraGO AG","1DCB3-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-30",null,null,7,1]
[null,"DB InfraGO AG","1DCB3-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,3,1]
[null,"DB InfraGO AG","1DCB3-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","1DCB3-008","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","1DD70-001","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,3,"2026-01-12","21:00:00","2026-01-15","04:00:00","2d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-11",null,null,1,1]
[null,"DB InfraGO AG","1DD70-002","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,3,3,"2026-01-12","21:00:00","2026-01-15","04:00:00","2d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DD70-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1DD70-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1DD70-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","1DD70-012","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,4,4,"2026-01-20","21:00:00","2026-01-25","04:00:00","4d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1DD70-016","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,5,5,"2026-01-28","21:00:00","2026-01-30","04:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DD70-017","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,5,5,"2026-01-28","21:00:00","2026-01-30","04:00:00","1d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1F4E5-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4E5-004","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F4E5-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F4E5-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1F4E5-008","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1F4E5-011","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,6,6,"2026-02-07","04:00:00","2026-02-07","12:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4E5-013","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","1F4E5-015","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,6,6,"2026-02-07","08:00:00","2026-02-07","12:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,7,1]
[null,"DB InfraGO AG","1F50F-006","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","04:00:00","1d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1F528-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-22",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1F528-003","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1F528-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1F528-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F528-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F528-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F528-008","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,4,1]
[null,"DB InfraGO AG","1F532-001","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","21:00:00","2026-02-12","05:00:00","2d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,1,1]
[null,"DB InfraGO AG","1F532-002","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","21:00:00","2026-02-12","05:00:00","2d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F532-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-09","21:00:00","2026-02-10","05:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","1F532-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-12","21:00:00","2026-02-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F532-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,7,"2026-02-12","21:00:00","2026-02-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F548-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F548-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F548-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F581-001","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-16","05:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-10-16",null,null,"6,7",1]
[null,"DB InfraGO AG","1F581-002","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,10,10,"2026-03-06","21:00:00","2026-03-08","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-10-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1F581-003","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,10,11,"2026-03-08","21:00:00","2026-03-12","05:00:00","3d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F581-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,10,11,"2026-03-08","21:00:00","2026-03-12","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F581-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-12","21:00:00","2026-03-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,7,1]
[null,"DB InfraGO AG","1F588-001","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-14","07:00:00","2026-03-14","14:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F58D-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,"2,5,6,7",1]
[null,"DB InfraGO AG","1F59E-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,"2,5,6,7",1]
[null,"DB InfraGO AG","1F59E-002","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,11,18,"2026-03-15","06:00:00","2026-05-03","16:00:00","49d, 9h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-02-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1F59E-007","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1F5A4-001","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,12,12,"2026-03-16","06:00:00","2026-03-22","21:00:00","6d, 15h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,2,1]
[null,"DB InfraGO AG","1F5A4-002","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,12,12,"2026-03-16","06:00:00","2026-03-22","21:00:00","6d, 15h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5AB-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,17,18,"2026-04-26","21:00:00","2026-04-30","04:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"7,,7",null,null,null,"N",null,"2024-07-24",null,null,3,1]
[null,"DB InfraGO AG","1F5AB-002","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,17,17,"2026-04-26","21:00:00","2026-04-26","22:30:00","0d, 1h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1F5AB-003","Berlin - Dresden","< >","Dresden Hbf","Freital Ost",2026,2026,17,17,"2026-04-26","21:00:00","2026-04-26","22:30:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,4,1]
[null,"DB InfraGO AG","1F5AB-004","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-04-30","02:30:00","2026-04-30","04:00:00","0d, 1h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-08",null,null,7,1]
[null,"DB InfraGO AG","1F5AB-005","Berlin - Dresden","< >","Dresden Hbf","Freital Ost",2026,2026,18,18,"2026-04-30","02:30:00","2026-04-30","04:00:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,7,1]
[null,"DB InfraGO AG","1F5C3-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","18:00:00","0d, 13h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"7,,7",null,null,null,"N",null,"2024-07-22",null,null,7,1]
[null,"DB InfraGO AG","1F5C3-003","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","18:00:00","0d, 13h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,7,1]
[null,"DB InfraGO AG","1F5C3-005","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","06:30:00","0d, 1h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2023-09-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1F5C3-006","Berlin - Dresden","< >","Dresden Hbf","Freital Ost",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","06:30:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F5C3-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,18,18,"2026-05-03","16:30:00","2026-05-03","18:00:00","0d, 1h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2023-09-22",null,null,5,1]
[null,"DB InfraGO AG","1F5C3-008","Berlin - Dresden","< >","Dresden Hbf","Freital Ost",2026,2026,18,18,"2026-05-03","16:30:00","2026-05-03","18:00:00","0d, 1h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,5,1]
[null,"DB InfraGO AG","1F5C3-012","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,18,18,"2026-05-03","14:00:00","2026-05-03","18:00:00","0d, 4h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-10-02",null,null,"5,6",1]
[null,"DB InfraGO AG","1F5C3-013","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,18,18,"2026-05-03","14:00:00","2026-05-03","18:00:00","0d, 4h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"5,6",1]
[null,"DB InfraGO AG","1F5FE-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-10-02",null,null,5,1]
[null,"DB InfraGO AG","1F5FE-007","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1F5FE-008","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,1,1]
[null,"DB InfraGO AG","1F672-004","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-01-18",null,null,1,1]
[null,"DB InfraGO AG","1F672-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2026,2026,19,19,"2026-05-08","20:00:00","2026-05-09","04:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO AG","1F672-008","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,20,"2026-05-09","03:00:00","2026-05-12","16:00:00","3d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2023-12-12",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F672-009","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,19,"2026-05-09","04:00:00","2026-05-09","16:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-12",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1F672-011","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2026,2026,19,19,"2026-05-09","16:00:00","2026-05-10","04:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-12",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F672-014","Berlin - Dresden","< >","Dresden Hbf","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-09","18:00:00","2026-05-10","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-12",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO AG","1F672-015","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,19,"2026-05-10","00:00:00","2026-05-10","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-12",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO AG","1F672-016","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,19,"2026-05-10","04:00:00","2026-05-10","19:00:00","0d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-16",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F672-018","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2026,2026,19,20,"2026-05-10","19:00:00","2026-05-11","04:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-08-29",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1F672-019","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,20,20,"2026-05-11","17:00:00","2026-05-12","04:00:00","0d, 11h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-16",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F672-020","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,20,20,"2026-05-11","23:00:00","2026-05-12","04:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-16",null,null,"1,2,3,6,7",1]
[null,"DB InfraGO AG","1F6CB-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,36,38,"2026-08-31","18:00:00","2026-09-14","05:00:00","13d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,5,1]
[null,"DB InfraGO AG","1F722-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-10-16",null,null,6,1]
[null,"DB InfraGO AG","1F722-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,2,1]
[null,"DB InfraGO AG","1F722-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,2,1]
[null,"DB InfraGO AG","1F748-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","1F748-007","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1F748-008","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-16",null,null,1,1]
[null,"DB InfraGO AG","1F543-010","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1F543-011","Berlin - Dresden","< >","Dresden Hbf","Klingenberg-Colmnitz",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1F543-012","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F89C-004","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F89C-005","Berlin - Dresden","< >","Dresden Hbf","Dresden-Neustadt",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-26",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","1F89C-009","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,16,17,"2026-04-19","21:00:00","2026-04-25","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-26",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","1655-(MK26)-02_D","Berlin - Dresden",">","Dresden Hbf","Pirna",2027,2027,15,23,"17.04.2027","05:00:00","11.06.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1655-(MK26)-02_N","Berlin - Dresden","< >","Dresden Hbf","Pirna",2027,2027,15,23,"16.04.2027","21:00:00","11.06.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1656-(MK26)-01_D","Berlin - Dresden",">","Dresden Hbf","Pirna",2027,2027,14,17,"10.04.2027","05:00:00","30.04.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1656-(MK26)-01_N","Berlin - Dresden","< >","Dresden Hbf","Pirna",2027,2027,14,17,"09.04.2027","21:00:00","30.04.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3094-(MK27)-02_WDN","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2027,2027,25,27,"21.06.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-05-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3094-(MK27)-02_WDD","Berlin - Dresden",">","Dresden Hbf","Dresden Mitte",2027,2027,25,27,"21.06.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-09-22",null,null,6,1]
[null,"DB InfraGO AG","3094-(MK27)-03","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2027,2027,35,45,"03.09.2027","21:00:00","12.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-09-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD70-015","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,5,5,"2026-01-26","21:00:00","2026-01-28","04:00:00","1d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-28",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1F50F-003","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","04:00:00","1d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1F50F-004","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","04:00:00","1d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F588-004","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,11,11,"2026-03-14","10:00:00","2026-03-14","14:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F58D-001","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1F58D-002","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-04",null,null,5,1]
[null,"DB InfraGO AG","1F672-007","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,19,19,"2026-05-09","00:00:00","2026-05-09","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,5,1]
[null,"DB InfraGO AG","1F672-017","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,19,20,"2026-05-10","19:00:00","2026-05-11","04:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-16",null,null,5,1]
[null,"DB InfraGO AG","1F543-001","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-16",null,null,7,1]
[null,"DB InfraGO AG","1F543-002","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-27",null,null,3,1]
[null,"DB InfraGO AG","1F89C-003","Berlin - Dresden","<","Dresden Mitte","Dresden-Friedrichstadt",2026,2026,14,15,"2026-04-05","21:00:00","2026-04-11","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-08-16",null,null,3,1]
[null,"DB InfraGO AG","1DD70-019","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2026,2026,5,5,"2026-01-26","21:00:00","2026-01-28","04:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-16",null,null,"5,6",1]
[null,"DB InfraGO AG","3868-(MK26)-01_D","Berlin - Dresden",">","Dresden Mitte","Dresden Hbf",2027,2027,14,15,"10.04.2027","05:00:00","16.04.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","3868-(MK26)-01_N","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2027,2027,14,15,"09.04.2027","21:00:00","16.04.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2023-09-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1D5D6-010","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-23","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC0E-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2025,2026,50,2,"2025-12-14","00:00:00","2026-01-09","04:00:00","26d, 4h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,2,1]
[null,"DB InfraGO AG","1DC42-007","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-27",null,null,"2,3",1]
[null,"DB InfraGO AG","1DCB3-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,3,7,"2026-01-12","04:00:00","2026-02-09","04:00:00","28d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1DD70-008","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,3,3,"2026-01-15","21:00:00","2026-01-16","04:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2023-09-22",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1DD70-011","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-20","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD70-014","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,4,4,"2026-01-20","21:00:00","2026-01-25","04:00:00","4d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4E5-003","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,6,6,"2026-02-06","21:00:00","2026-02-07","12:00:00","0d, 15h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","1F50F-001","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","00:00:00","1d, 12h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","1F50F-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,6,7,"2026-02-07","12:00:00","2026-02-09","04:00:00","1d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-09-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1F50F-007","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-09","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1F50F-010","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-09","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1F528-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1F548-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F548-006","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F548-009","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1F581-007","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-12","21:00:00","2026-03-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2023-09-11",null,null,"1,2,7",1]
[null,"DB InfraGO AG","1F588-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-14","07:00:00","2026-03-14","14:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2,7",1]
[null,"DB InfraGO AG","1F58D-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,11,11,"2026-03-14","14:00:00","2026-03-15","06:00:00","0d, 16h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1F59E-004","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-09-05",null,null,7,1]
[null,"DB InfraGO AG","1F59E-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,11,19,"2026-03-15","06:00:00","2026-05-04","04:00:00","49d, 21h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1F5C3-002","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,18,18,"2026-05-03","05:00:00","2026-05-03","08:00:00","0d, 3h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-04",null,null,1,1]
[null,"DB InfraGO AG","1F5C3-011","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,18,18,"2026-05-03","08:00:00","2026-05-03","18:00:00","0d, 10h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,1,1]
[null,"DB InfraGO AG","1F5C3-015","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5C3-016","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5FE-001","Berlin - Dresden","<","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-08-05",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5FE-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5FE-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,6,1]
[null,"DB InfraGO AG","1F672-013","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-09","16:00:00","2026-05-10","04:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2023-09-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1F722-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1F722-004","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F748-001","Berlin - Dresden","<","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F748-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"Y",null,"2024-07-17",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1F748-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-21",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1F543-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,7",1]
[null,"DB InfraGO AG","1F543-004","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","1F543-006","Berlin - Dresden","<","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-14","18:00:00","2026-02-15","04:00:00","0d, 10h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-10-01",null,null,"4,5",1]
[null,"DB InfraGO AG","20189-003","Berlin - Dresden","< >","Dresden-Cotta Bft","Dresden-Kemnitz",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","3096-(MK25)-03_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Dresden Freibg Str",2026,2027,51,27,"14.12.2026","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","3096-(MK25)-03_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Freibg Str",2026,2027,51,27,"14.12.2026","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-10-25",null,null,7,1]
[null,"DB InfraGO AG","3096-(MK27)-02_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Dresden Freibg Str",2027,2027,46,46,"15.11.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-10-15",null,null,3,1]
[null,"DB InfraGO AG","3096-(MK27)-02_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Freibg Str",2027,2027,46,46,"15.11.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-11",null,null,"3,4",1]
[null,"DB InfraGO AG","3097-(MK27)-01_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Mitte",2027,2027,38,46,"20.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-09-12",null,null,4,1]
[null,"DB InfraGO AG","3636-(MK25)-02_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,12,37,"27.03.2027","05:00:00","17.09.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-08-29",null,null,5,1]
[null,"DB InfraGO AG","3636-(MK25)-02_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,12,37,"26.03.2027","21:00:00","17.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-08-29",null,null,5,1]
[null,"DB InfraGO AG","3636-(MK26)-07_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,38,46,"20.09.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-10-16",null,null,6,1]
[null,"DB InfraGO AG","3636-(MK26)-07_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,38,46,"20.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2025-01-08",null,null,2,1]
[null,"DB InfraGO AG","3636-(MK26)-10_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2026,2027,50,10,"12.12.2026","05:00:00","12.03.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,2,1]
[null,"DB InfraGO AG","3636-(MK26)-10_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2026,2027,50,10,"11.12.2026","21:00:00","12.03.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3636-(MK27)-02_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,46,49,"20.11.2027","05:00:00","10.12.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3636-(MK27)-02_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,46,49,"19.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1C092-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,38,41,"2026-09-16","07:00:00","2026-10-05","16:00:00","19d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-11-25",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1D47F-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,44,48,"2026-10-26","08:00:00","2026-11-23","18:00:00","28d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-11-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC42-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC42-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DC42-025","Berlin - Dresden","< >","Dresden-Friedrichstadt","Elsterwerda Strw",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD70-003","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,3,3,"2026-01-12","21:00:00","2026-01-15","04:00:00","2d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD70-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,4,4,"2026-01-19","21:00:00","2026-01-20","04:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-001","Berlin - Dresden",">","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-28",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-002","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-005","Berlin - Dresden",">","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-02","20:00:00","2026-02-06","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-06","20:00:00","2026-02-07","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4BA-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,6,6,"2026-02-06","20:00:00","2026-02-07","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,6,6,"2026-02-06","20:00:00","2026-02-07","04:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-012","Berlin - Dresden","<","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-013","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,7,7,"2026-02-09","20:00:00","2026-02-13","04:00:00","3d, 8h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-015","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4BA-016","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,7,7,"2026-02-13","20:00:00","2026-02-14","04:00:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F50F-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-09","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1F528-009","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-09","04:00:00","2026-02-15","04:00:00","6d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1F548-007","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,11,"2026-02-15","04:00:00","2026-03-15","06:00:00","28d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1F581-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-12","21:00:00","2026-03-14","05:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1F588-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-14","07:00:00","2026-03-14","14:00:00","0d, 7h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"6,7",1]
[null,"DB InfraGO AG","1F672-002","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-08","18:00:00","2026-05-08","20:00:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-25",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F672-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-08","20:00:00","2026-05-09","04:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F672-010","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,19,19,"2026-05-09","04:00:00","2026-05-09","16:00:00","0d, 12h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F672-021","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,20,20,"2026-05-11","23:00:00","2026-05-12","04:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F543-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F543-015","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F543-024","Berlin - Dresden","< >","Dresden-Friedrichstadt","Elsterwerda Strw",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F89C-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F89C-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FA4A-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FA4A-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FA4A-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FA4A-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,7,8,"2026-02-15","22:00:00","2026-02-17","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1FA4A-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1FA4A-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1FA4A-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,11,"2026-02-17","04:00:00","2026-03-12","04:00:00","23d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","1FA4A-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-12","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA4A-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-12","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA4A-010","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-12","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA4A-011","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,11,11,"2026-03-10","22:00:00","2026-03-12","04:00:00","1d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","1FAD6-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,13,"2026-03-14","07:00:00","2026-03-23","17:00:00","9d, 10h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","1FAD6-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,11,13,"2026-03-14","07:00:00","2026-03-23","17:00:00","9d, 10h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","1FAD6-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,13,"2026-03-14","07:00:00","2026-03-23","17:00:00","9d, 10h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","1FAD6-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1FAD6-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1FAD6-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,8,"2026-02-17","04:00:00","2026-02-21","06:00:00","4d, 2h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,8,8,"2026-02-17","04:00:00","2026-02-21","06:00:00","4d, 2h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,8,8,"2026-02-17","04:00:00","2026-02-21","06:00:00","4d, 2h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,8,9,"2026-02-21","06:00:00","2026-02-24","18:00:00","3d, 12h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-006","Berlin - Dresden",">","Dresden-Friedrichstadt","Radebeul-Naundorf",2026,2026,9,9,"2026-02-24","18:00:00","2026-02-28","06:00:00","3d, 12h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-010","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-011","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-012","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-013","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","206A9-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,8,16,"2026-02-21","18:00:00","2026-04-13","18:00:00","50d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","206F2-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,16,20,"2026-04-13","18:00:00","2026-05-12","20:00:00","29d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-08-26",null,null,"1,2",1]
[null,"DB InfraGO AG","207CD-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,20,22,"2026-05-13","08:00:00","2026-05-26","16:00:00","13d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-08-26",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,11,"2026-02-23","08:00:00","2026-03-09","16:00:00","14d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-24","08:00:00","2026-03-02","14:00:00","6d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-011","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-27","07:00:00","2026-03-02","16:00:00","3d, 9h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-012","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-02","14:00:00","2d, 17h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,9,10,"2026-03-01","16:00:00","2026-03-02","14:00:00","0d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"1,2",1]
[null,"DB InfraGO AG","20997-017","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"5,6",1]
[null,"DB InfraGO AG","20997-018","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"5,6",1]
[null,"DB InfraGO AG","20997-020","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"5,6",1]
[null,"DB InfraGO AG","20997-021","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-02","14:00:00","2026-03-08","16:00:00","6d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"5,6",1]
[null,"DB InfraGO AG","20997-023","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-024","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-026","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-027","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-028","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,10,10,"2026-03-05","21:00:00","2026-03-08","16:00:00","2d, 19h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-031","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-05","19:00:00","2026-03-08","18:00:00","2d, 23h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-032","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-05","19:00:00","2026-03-08","18:00:00","2d, 23h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-033","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-07","21:00:00","2026-03-08","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20997-034","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,10,10,"2026-03-07","21:00:00","2026-03-08","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,11,14,"2026-03-13","06:00:00","2026-03-30","08:00:00","17d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-16","09:00:00","2026-03-16","17:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-16","17:00:00","2026-03-28","15:00:00","11d, 22h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-16","08:00:00","2026-03-28","21:00:00","12d, 13h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-17","08:00:00","2026-03-28","15:00:00","11d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-09",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-010","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-17","08:00:00","2026-03-28","15:00:00","11d, 7h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-012","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,13,"2026-03-17","08:00:00","2026-03-28","15:00:00","11d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-09-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-013","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-17","08:00:00","2026-03-17","20:00:00","0d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-09-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,12,12,"2026-03-17","08:00:00","2026-03-17","20:00:00","0d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-09-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-015","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,13,13,"2026-03-26","08:00:00","2026-03-28","15:00:00","2d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-05-17",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-016","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,13,13,"2026-03-26","08:00:00","2026-03-28","15:00:00","2d, 7h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-05-17",null,null,"2,3",1]
[null,"DB InfraGO AG","20BA3-017","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,13,13,"2026-03-28","15:00:00","2026-03-28","21:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-05-02",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,23,24,"2026-06-05","16:00:00","2026-06-12","17:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-08-14",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-08","18:00:00","2026-06-09","04:00:00","0d, 10h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-010","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-011","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-013","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-014","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-015","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","20C8C-017","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","18:00:00","2026-06-10","04:00:00","0d, 10h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-018","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","22:00:00","2026-06-10","04:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-019","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-09","22:00:00","2026-06-10","04:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-020","Berlin - Dresden",">","Dresden-Friedrichstadt","Dresden Freiberger Straße",2026,2026,24,24,"2026-06-09","22:00:00","2026-06-10","04:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-021","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-11","08:00:00","2026-06-11","17:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-023","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-12","08:00:00","2026-06-12","17:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C8C-024","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,24,24,"2026-06-12","08:00:00","2026-06-12","17:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","1D050-001","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,7,7,"2026-02-09","20:50:00","2026-02-11","04:20:00","1d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-002","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,14,16,"2026-04-01","20:50:00","2026-04-15","04:20:00","13d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-003","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,16,16,"2026-04-15","20:50:00","2026-04-18","04:20:00","2d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-005","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,28,29,"2026-07-09","20:50:00","2026-07-15","04:20:00","5d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-006","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,44,44,"2026-10-26","20:50:00","2026-10-28","04:20:00","1d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-007","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,44,44,"2026-10-30","20:50:00","2026-10-31","04:20:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1DC42-020","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-004","Berlin - Dresden","<","Dresden-Neustadt","Dresden-Klotzsche",2026,2026,18,21,"2026-04-30","20:50:00","2026-05-19","04:20:00","18d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1DC42-010","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Neustadt Gbf",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F543-016","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Pieschen                  (Abzw)",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F543-021","Berlin - Dresden","< >","Dresden-Neustadt","Coswig (bei Dresden)",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F543-022","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Klotzsche",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F89C-001","Berlin - Dresden","< >","Dresden-Neustadt","Dresden Mitte",2026,2026,14,15,"2026-04-05","21:00:00","2026-04-11","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F89C-007","Berlin - Dresden","< >","Dresden-Neustadt","Dresden-Neustadt Gbf",2026,2026,15,16,"2026-04-12","21:00:00","2026-04-18","05:00:00","5d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F89C-002","Berlin - Dresden","< >","Dresden-Neustadt Gbf","Dresden-Neustadt",2026,2026,14,15,"2026-04-05","21:00:00","2026-04-11","05:00:00","5d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1DC42-023","Berlin - Dresden","< >","Dresden-Pieschen                  (Abzw)","Dresden-Neustadt",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1F4C3-001","Berlin - Dresden","< >","Dresden-Pieschen                  (Abzw)","Dresden-Neustadt",2026,2026,12,50,"2026-03-16","00:00:00","2026-12-11","23:59:00","270d, 23h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1DC42-001","Berlin - Dresden","< >","Dresden-Reick","Dresden-Neustadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","1DC42-003","Berlin - Dresden","< >","Dresden-Reick Abstellbahnhof","Dresden-Neustadt",2026,2026,2,3,"2026-01-09","04:00:00","2026-01-12","04:00:00","3d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","1FCFA-003","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","20838-003","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,48,50,"2026-11-27","21:00:00","2026-12-11","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","2078A-008","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,16,16,"2026-04-17","17:00:00","2026-04-19","04:00:00","1d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","207CA-006","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,28,35,"2026-07-10","21:00:00","2026-08-24","21:00:00","45d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1C2D3-001","Berlin - Dresden","<","Frauenhain","Elsterwerda",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-01-20",null,null,"6,7",1]
[null,"DB InfraGO AG","1F5C3-014","Berlin - Dresden","< >","Freital Ost","Dresden Hbf",2026,2026,18,19,"2026-05-03","18:00:00","2026-05-04","04:00:00","0d, 10h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"6,7",1]
[null,"DB InfraGO AG","1C573-017","Berlin - Dresden","< >","Görlitz","Dresden-Neustadt",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-10","02:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1653-(MK26)-01","Berlin - Dresden","< >","Großenh Berl Bf","Großenh Cott Bf",2027,2027,26,27,"02.07.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1653-(MK26)-03","Berlin - Dresden","< >","Großenh Berl Bf","Großenh Cott Bf",2027,2027,31,34,"06.08.2027","21:00:00","27.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1C573-023","Berlin - Dresden","< >","Großenhain Cottb Bf","Brieske",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-10","02:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1CA02-002","Berlin - Dresden","<","Grünauer Kreuz Süd","Grünauer Kreuz West",2026,2026,20,21,"2026-05-15","22:00:00","2026-05-18","04:00:00","2d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-06-25",null,null,"4,5",1]
[null,"DB InfraGO AG","1CB7B-002","Berlin - Dresden","< >","Grünauer Kreuz Süd","Grünauer Kreuz Nord",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-24","04:00:00","3d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1CD5E-002","Berlin - Dresden","<","Grünauer Kreuz Süd","Grünauer Kreuz West",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-18","04:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1CCA6-007","Berlin - Dresden","< >","Grünauer Kreuz Süd","Berlin-Grünau",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-19","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1CB7B-003","Berlin - Dresden","< >","Grünauer Kreuz West","Grünauer Kreuz Süd",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-24","04:00:00","3d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1C2D3-004","Berlin - Dresden",">","Hohenleipisch","Elsterwerda",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1E552-001","Berlin - Dresden","< >","Luckau-Uckro","Brenitz-Sonnewalde",2026,2026,48,49,"2026-11-28","22:00:00","2026-12-05","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1C092-009","Berlin - Dresden",">","Niederau","Coswig (bei Dresden)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","1BF3C-002","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,13,13,"2026-03-23","20:00:00","2026-03-26","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-004","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,36,36,"2026-08-31","20:00:00","2026-09-03","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-005","Berlin - Dresden",">","Radebeul Abzw Az","Weinböhla",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-007","Berlin - Dresden","< >","Radebeul Abzw Az","Weinböhla",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-002","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,40,41,"2026-10-04","20:00:00","2026-10-05","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-004","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-006","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,50,50,"2026-12-11","20:00:00","2026-12-12","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1DC42-027","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1F543-023","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1FB4B-009","Berlin - Dresden","<","Radebeul Abzw Az","Cossebaude",2026,2026,9,10,"2026-02-28","06:00:00","2026-03-03","18:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1DC42-024","Berlin - Dresden","< >","Radebeul Nord","Radebeul Abzw Az",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","3648-(MK27)-01","Berlin - Dresden",">","Radebeul-Naundf Abz","Coswig (bei Dre)",2027,2027,30,33,"31.07.2027","05:00:00","20.08.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","3648-(MK27)-02","Berlin - Dresden",">","Radebeul-Naundf Abz","Coswig (bei Dre)",2027,2027,38,46,"25.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1FB4B-012","Berlin - Dresden",">","Radebeul-Naundorf","Radebeul Abzw Az",2026,2026,10,10,"2026-03-04","06:00:00","2026-03-06","06:00:00","2d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1FB4B-015","Berlin - Dresden",">","Radebeul-Naundorf","Radebeul-Naundorf                 (Abzw)",2026,2026,10,11,"2026-03-06","06:00:00","2026-03-10","18:00:00","4d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-001","Berlin - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Kottewitz",2026,2026,13,13,"2026-03-23","20:00:00","2026-03-26","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1BF3C-003","Berlin - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Kottewitz",2026,2026,36,36,"2026-08-31","20:00:00","2026-09-03","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB4B-011","Berlin - Dresden","<","Radebeul-Naundorf                 (Abzw)","Radebeul-Naundorf",2026,2026,9,10,"2026-02-28","06:00:00","2026-03-03","18:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,1,1]
[null,"DB InfraGO AG","1FB4B-013","Berlin - Dresden",">","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2026,2026,10,10,"2026-03-04","06:00:00","2026-03-06","06:00:00","2d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-19",null,null,1,1]
[null,"DB InfraGO AG","1FB4B-014","Berlin - Dresden",">","Radebeul-Naundorf                 (Abzw)","Coswig (bei Dresden)",2026,2026,10,11,"2026-03-06","06:00:00","2026-03-10","18:00:00","4d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-02",null,null,1,1]
[null,"DB InfraGO AG","1CD5E-001","Berlin - Dresden","<","Schönefeld (bei Berlin) F-Bahn","Berlin Wendenheide",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-18","04:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1E552-002","Berlin - Dresden","< >","Walddrehna","Walddrehna",2026,2026,49,49,"2026-12-05","22:00:00","2026-12-06","22:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1E552-003","Berlin - Dresden","< >","Walddrehna","Walddrehna",2026,2026,49,50,"2026-12-06","22:00:00","2026-12-07","22:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-006","Berlin - Dresden","<","Weinböhla","Radebeul Abzw Az",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-008","Berlin - Dresden","<","Weinböhla","Radebeul-Naundorf",2026,2026,13,33,"2026-03-26","08:00:00","2026-08-11","16:00:00","138d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-009","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,13,33,"2026-03-26","08:00:00","2026-08-11","16:00:00","138d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-011","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-008","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,41,47,"2026-10-05","04:00:00","2026-11-19","20:00:00","45d, 17h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-010","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,48,50,"2026-11-27","08:00:00","2026-12-11","16:00:00","14d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-011","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,41,50,"2026-10-05","04:00:00","2026-12-11","20:00:00","67d, 17h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1BD-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,1,2,"2026-01-04","21:00:00","2026-01-05","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1BD-004","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,2,2,"2026-01-06","21:00:00","2026-01-07","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1BD-007","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,2,3,"2026-01-09","21:00:00","2026-01-16","05:00:00","6d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1C2-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,25,25,"2026-06-19","20:00:00","2026-06-20","08:00:00","0d, 12h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1C3-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,33,34,"2026-08-15","21:00:00","2026-08-17","05:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1B194-002","Bremen - Hannover","< >","Ahlem","Hannover Kurve",2025,2026,52,3,"2025-12-27","21:00:00","2026-01-13","10:00:00","16d, 13h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1B194-003","Bremen - Hannover","< >","Ahlem","Seelze Ost",2026,2026,3,3,"2026-01-13","10:00:00","2026-01-14","10:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1B1AC-002","Bremen - Hannover","< >","Ahlem","Seelze Ost",2026,2026,8,8,"2026-02-21","20:00:00","2026-02-22","06:00:00","0d, 10h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1B1BB-004","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2025,2026,52,1,"2025-12-26","22:00:00","2026-01-04","06:00:00","8d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1B1BB-007","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2026,2026,1,3,"2026-01-04","06:00:00","2026-01-16","21:00:00","12d, 15h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1B1BB-011","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2026,2026,3,3,"2026-01-16","21:00:00","2026-01-17","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1B325-001","Bremen - Hannover","< >","Ahlem","Hannover-Linden",2026,2026,7,9,"2026-02-14","21:00:00","2026-02-23","05:00:00","8d, 8h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1E35C-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,36,36,"2026-09-04","22:00:00","2026-09-05","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,36,36,"2026-09-04","22:00:00","2026-09-05","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-003","Bremen - Hannover",">","Bremen Hbf","Bremen Hbf",2026,2026,36,37,"2026-09-05","10:00:00","2026-09-07","05:00:00","1d, 19h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-05","20:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-06","08:00:00","0d, 14h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-007","Bremen - Hannover",">","Bremen Hbf","Bremen Hbf",2026,2026,37,37,"2026-09-07","05:00:00","2026-09-12","14:00:00","5d, 9h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,37,38,"2026-09-12","14:00:00","2026-09-14","05:00:00","1d, 15h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,37,38,"2026-09-12","14:00:00","2026-09-14","05:00:00","1d, 15h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,38,38,"2026-09-14","22:00:00","2026-09-15","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,38,38,"2026-09-14","22:00:00","2026-09-15","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-27","09:00:00","2026-07-27","12:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-27","12:00:00","2026-07-27","15:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-28","07:00:00","2026-07-31","22:00:00","3d, 15h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-004","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-07-28","07:00:00","2026-07-31","17:00:00","3d, 10h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,32,"2026-07-31","22:00:00","2026-08-03","16:30:00","2d, 18h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-08-01","05:00:00","2026-08-01","08:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-007","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,35,"2026-08-03","16:30:00","2026-08-30","18:00:00","27d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-05","04:00:00","2026-08-05","18:00:00","0d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-06","00:00:00","2026-08-06","11:00:00","0d, 11h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","22:00:00","1d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-09","09:00:00","2026-08-09","13:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-012","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,35,35,"2026-08-30","12:00:00","2026-08-30","15:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,38,"2026-09-14","08:00:00","2026-09-14","12:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,38,"2026-09-14","12:00:00","2026-09-14","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,39,"2026-09-17","07:00:00","2026-09-24","07:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-004","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","00:00:00","2026-09-24","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,40,"2026-09-24","07:00:00","2026-09-30","15:00:00","6d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","07:00:00","2026-09-24","09:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-007","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","22:00:00","2026-09-27","05:00:00","2d, 7h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,40,"2026-09-30","10:00:00","2026-09-30","12:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,41,"2026-09-30","15:00:00","2026-10-08","07:00:00","7d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,40,"2026-10-01","00:00:00","2026-10-01","03:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","00:00:00","2026-10-08","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-012","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,42,"2026-10-08","07:00:00","2026-10-13","06:00:00","4d, 23h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-013","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,42,"2026-10-08","07:00:00","2026-10-13","06:00:00","4d, 23h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-014","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","07:00:00","2026-10-08","11:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-015","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","22:00:00","2026-10-11","05:00:00","2d, 7h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-016","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","01:00:00","2026-10-13","04:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-017","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","01:00:00","2026-10-13","05:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-018","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","08:00:00","2026-10-13","12:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-019","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","12:00:00","2026-10-13","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,12,12,"2026-03-20","10:00:00","2026-03-20","13:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,13,14,"2026-03-23","07:00:00","2026-04-01","05:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-004","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,13,13,"2026-03-23","07:00:00","2026-03-27","17:00:00","4d, 10h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,13,13,"2026-03-27","01:00:00","2026-03-27","04:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,14,17,"2026-04-01","05:00:00","2026-04-25","18:00:00","24d, 13h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-012","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,14,17,"2026-04-01","05:00:00","2026-04-25","18:00:00","24d, 13h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-013","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,17,17,"2026-04-25","16:00:00","2026-04-25","18:00:00","0d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-13","07:00:00","2026-07-13","17:30:00","0d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-14","07:00:00","2026-07-14","16:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-004","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-15","07:00:00","2026-07-15","16:30:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-16","07:00:00","2026-07-16","13:30:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,29,29,"2026-07-17","07:00:00","2026-07-17","19:00:00","0d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,30,30,"2026-07-20","07:00:00","2026-07-20","16:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,30,30,"2026-07-21","07:00:00","2026-07-21","13:30:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,30,30,"2026-07-22","07:00:00","2026-07-22","16:30:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFF-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,30,30,"2026-07-23","07:00:00","2026-07-23","17:30:00","0d, 10h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","20BFE-002","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,13,13,"2026-03-23","01:00:00","2026-03-23","04:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-006","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,13,14,"2026-03-27","22:00:00","2026-04-01","05:00:00","4d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-007","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,13,13,"2026-03-27","22:00:00","2026-03-28","02:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-008","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,13,13,"2026-03-28","00:00:00","2026-03-28","02:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-009","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,14,14,"2026-04-01","01:00:00","2026-04-01","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-010","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,14,14,"2026-04-01","01:00:00","2026-04-01","03:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFE-014","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,17,17,"2026-04-26","01:00:00","2026-04-26","04:00:00","0d, 3h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFF-001","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,28,29,"2026-07-12","16:30:00","2026-07-13","04:00:00","0d, 11h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-15",null,null,"5,6",1]
[null,"DB InfraGO AG","20BFF-007","Bremen - Hannover",">","Bremen-Hemelingen","Bremen Hbf",2026,2026,29,30,"2026-07-19","20:00:00","2026-07-20","04:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"5,6",1]
[null,"DB InfraGO AG","1115-(MK27)-01_D","Bremen - Hannover",">","Bremen-Sebaldsbrück","Verden (Aller)",2027,2027,19,26,"15.05.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-19",null,null,6,1]
[null,"DB InfraGO AG","1115-(MK27)-01_N","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Verden (Aller)",2027,2027,19,26,"14.05.2027","21:00:00","02.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-01",null,null,"1,7",1]
[null,"DB InfraGO AG","3632-(MK27)-01_D","Bremen - Hannover",">","Bremen-Sebaldsbrück","Bremen Hbf",2027,2027,19,26,"15.05.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-01",null,null,"1,7",1]
[null,"DB InfraGO AG","3632-(MK27)-01_N","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen Hbf",2027,2027,19,26,"14.05.2027","21:00:00","02.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1CC41-006","Bremen - Hannover","<","Gümmerwald","Wunstorf",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-039","Bremen - Hannover","<","Gümmerwald","Wunstorf",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1B3E9-007","Bremen - Hannover",">","Hannover Bismarckstraße","Hannover-Linden",2026,2026,3,4,"2026-01-17","08:15:00","2026-01-24","15:55:00","7d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1B1BB-012","Bremen - Hannover","< >","Hannover-Linden","Ahlem",2026,2026,3,3,"2026-01-16","21:00:00","2026-01-17","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1B194-001","Bremen - Hannover","< >","Hannover-Linden Hafen","Seelze Ost",2025,2026,52,3,"2025-12-27","21:00:00","2026-01-13","10:00:00","16d, 13h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1B1AC-004","Bremen - Hannover","<","Hannover-Linden Hafen","Seelze West",2026,2026,8,9,"2026-02-22","19:00:00","2026-02-23","05:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"8,8,8",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1B3E9-001","Bremen - Hannover",">","Hannover-Linden/Fischerhof","Waldhausen",2025,2026,52,3,"2025-12-26","08:00:00","2026-01-16","16:00:00","21d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1B3E9-002","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Waldhausen",2025,2026,52,3,"2025-12-26","08:00:00","2026-01-16","20:00:00","21d, 12h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1B3E9-005","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover-Waldheim",2026,2026,2,2,"2026-01-10","08:00:00","2026-01-10","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1B3E9-006","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Waldhausen",2026,2026,3,4,"2026-01-16","18:00:00","2026-01-25","07:00:00","8d, 13h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1B42F-001","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Waldhausen",2026,2026,36,38,"2026-09-05","20:00:00","2026-09-14","06:00:00","8d, 10h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1B42F-002","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover Bismarckstraße",2026,2026,37,38,"2026-09-07","23:45:00","2026-09-17","04:35:00","9d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1C80D-001","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,28,29,"2026-07-10","17:15:00","2026-07-15","05:15:00","4d, 12h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-005","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-007","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-13","19:00:00","4d, 22h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-008","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,33,35,"2026-08-13","19:00:00","2026-08-30","00:30:00","16d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-010","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,35,36,"2026-08-30","00:30:00","2026-09-01","04:25:00","2d, 3h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-007","Bremen - Hannover",">","Letter                            (Abzw)","Seelze West",2026,2026,32,33,"2026-08-07","23:00:00","2026-08-15","05:05:00","7d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1CBAE-002","Bremen - Hannover",">","Letter                            (Abzw)","Seelze West",2026,2026,41,42,"2026-10-05","23:10:00","2026-10-14","04:45:00","8d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1E7DC-001","Bremen - Hannover","< >","Neustadt a Rübenberge","Hagen (Han)",2026,2026,42,42,"2026-10-17","23:05:00","2026-10-18","06:50:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB6B-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,7,7,"2026-02-13","07:00:00","2026-02-13","11:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,7,7,"2026-02-13","11:00:00","2026-02-13","15:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,7,7,"2026-02-13","11:00:00","2026-02-13","15:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,8,8,"2026-02-16","01:00:00","2026-02-16","05:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,8,8,"2026-02-16","03:00:00","2026-02-16","05:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,8,11,"2026-02-16","05:00:00","2026-03-13","05:00:00","25d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,8,9,"2026-02-20","14:00:00","2026-02-23","05:00:00","2d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-008","Bremen - Hannover","< >","Nienburg (Weser)","Langendamm (Han)",2026,2026,8,9,"2026-02-20","14:00:00","2026-02-23","05:00:00","2d, 15h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-010","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,9,11,"2026-02-23","05:00:00","2026-03-10","05:00:00","15d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-011","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-27","05:00:00","3d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-012","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,10,10,"2026-03-04","14:00:00","2026-03-04","21:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-013","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,10,10,"2026-03-04","14:00:00","2026-03-04","21:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-014","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,10,10,"2026-03-06","01:00:00","2026-03-06","05:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-015","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2026,2026,10,10,"2026-03-06","01:00:00","2026-03-06","05:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-016","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2026,2026,10,11,"2026-03-06","14:00:00","2026-03-09","05:00:00","2d, 15h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-017","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,11,11,"2026-03-09","16:00:00","2026-03-09","22:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6B-018","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2026,2026,11,11,"2026-03-09","23:00:00","2026-03-10","05:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6B-019","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,11,11,"2026-03-09","23:00:00","2026-03-10","05:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,24,"2026-06-01","14:00:00","2026-06-12","14:00:00","11d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-02","06:00:00","2026-06-02","22:00:00","0d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-02","06:00:00","2026-06-02","15:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-004","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2026,2026,23,23,"2026-06-02","12:00:00","2026-06-02","22:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-005","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-03","06:00:00","2026-06-03","18:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-03","10:00:00","2026-06-03","11:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,23,23,"2026-06-03","15:30:00","2026-06-03","16:30:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-008","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-09","06:00:00","2026-06-09","14:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-009","Bremen - Hannover","< >","Nienburg (Weser)","Liebenau (Han)",2026,2026,24,24,"2026-06-09","09:00:00","2026-06-09","16:00:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-010","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-09","12:00:00","2026-06-09","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-011","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-10","06:00:00","2026-06-10","15:00:00","0d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-012","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-10","09:30:00","2026-06-10","15:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-013","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-10","15:00:00","2026-06-10","16:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6C-015","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,24,24,"2026-06-10","15:00:00","2026-06-10","16:00:00","0d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,11,15,"2026-03-13","05:00:00","2026-04-12","20:00:00","30d, 14h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,12,14,"2026-03-20","18:00:00","2026-03-30","05:00:00","9d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-003","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,12,12,"2026-03-20","18:00:00","2026-03-20","22:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-004","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,12,12,"2026-03-20","20:00:00","2026-03-22","05:00:00","1d, 9h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-005","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,12,12,"2026-03-21","08:30:00","2026-03-21","12:00:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-006","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,12,12,"2026-03-22","08:00:00","2026-03-22","10:00:00","0d, 2h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-007","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,12,13,"2026-03-22","22:00:00","2026-03-27","05:00:00","4d, 7h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-008","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,13,13,"2026-03-26","11:00:00","2026-03-26","14:00:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-009","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,13,13,"2026-03-27","08:00:00","2026-03-27","10:00:00","0d, 2h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-010","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,13,13,"2026-03-27","20:00:00","2026-03-28","05:00:00","0d, 9h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-011","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,13,13,"2026-03-28","06:00:00","2026-03-28","07:30:00","0d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-012","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,13,14,"2026-03-28","22:00:00","2026-03-30","05:00:00","1d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-013","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,13,14,"2026-03-29","22:00:00","2026-03-30","05:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-014","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,13,14,"2026-03-29","22:00:00","2026-03-30","05:00:00","0d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-015","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,14,14,"2026-03-30","05:00:00","2026-03-31","14:00:00","1d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-016","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,14,14,"2026-03-31","02:00:00","2026-03-31","05:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-017","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,14,15,"2026-03-31","14:00:00","2026-04-06","05:00:00","5d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-018","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,15,15,"2026-04-06","02:00:00","2026-04-06","05:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-019","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,15,15,"2026-04-06","05:00:00","2026-04-12","20:00:00","6d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-020","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,15,15,"2026-04-12","12:00:00","2026-04-12","20:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-021","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,15,17,"2026-04-12","20:00:00","2026-04-24","18:00:00","11d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-022","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,15,16,"2026-04-12","20:00:00","2026-04-13","00:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-023","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,17,17,"2026-04-24","14:00:00","2026-04-24","18:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-024","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,17,17,"2026-04-24","14:00:00","2026-04-24","18:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-025","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,17,17,"2026-04-25","08:00:00","2026-04-25","12:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB71-026","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,17,17,"2026-04-25","12:00:00","2026-04-25","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,38,"2026-09-07","14:00:00","2026-09-18","14:00:00","11d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,37,"2026-09-10","06:00:00","2026-09-10","21:30:00","0d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-003","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,37,37,"2026-09-10","06:00:00","2026-09-10","21:30:00","0d, 15h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,37,"2026-09-11","07:00:00","2026-09-11","19:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-005","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,38,38,"2026-09-16","06:00:00","2026-09-16","19:30:00","0d, 13h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,38,38,"2026-09-16","06:00:00","2026-09-16","19:30:00","0d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,38,38,"2026-09-17","06:00:00","2026-09-17","11:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-024","Bremen - Hannover","<","Poggenhagen","Wunstorf",2026,2026,29,29,"2026-07-17","21:05:00","2026-07-18","01:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-025","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2026,2026,29,29,"2026-07-18","00:45:00","2026-07-18","03:45:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-027","Bremen - Hannover","<","Poggenhagen","Wunstorf",2026,2026,31,31,"2026-07-31","17:05:00","2026-07-31","20:55:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-028","Bremen - Hannover","< >","Poggenhagen","Wunstorf",2026,2026,31,31,"2026-07-31","18:10:00","2026-07-31","20:55:00","0d, 2h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1CAFD-002","Bremen - Hannover",">","Seelze","Seelze West",2026,2026,30,31,"2026-07-26","23:00:00","2026-07-27","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CAFD-003","Bremen - Hannover","< >","Seelze","Seelze West",2026,2026,31,32,"2026-07-27","05:00:00","2026-08-07","23:00:00","11d, 18h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-030","Bremen - Hannover","< >","Seelze","Wunstorf",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","09:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-034","Bremen - Hannover","< >","Seelze","Wunstorf",2026,2026,31,31,"2026-08-01","09:00:00","2026-08-02","09:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1B194-004","Bremen - Hannover","< >","Seelze Ost","Ahlem",2026,2026,3,3,"2026-01-13","10:00:00","2026-01-14","10:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1B1AC-003","Bremen - Hannover","< >","Seelze Ost","Ahlem",2026,2026,8,9,"2026-02-22","19:00:00","2026-02-23","05:00:00","0d, 10h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1B1AC-001","Bremen - Hannover",">","Seelze West","Ahlem",2026,2026,8,8,"2026-02-21","20:00:00","2026-02-22","06:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1CAFD-008","Bremen - Hannover","< >","Seelze West","Letter                            (Abzw)",2026,2026,32,33,"2026-08-07","23:00:00","2026-08-15","05:05:00","7d, 6h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CAFD-009","Bremen - Hannover",">","Seelze West","Wunstorf",2026,2026,32,32,"2026-08-07","23:00:00","2026-08-08","01:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CAFD-010","Bremen - Hannover",">","Seelze West","Wunstorf",2026,2026,33,33,"2026-08-15","03:00:00","2026-08-15","05:05:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CBAE-003","Bremen - Hannover","< >","Seelze West","Letter                            (Abzw)",2026,2026,41,42,"2026-10-05","23:10:00","2026-10-14","04:45:00","8d, 5h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CBAE-004","Bremen - Hannover","< >","Seelze West","Hannover-Nordstadt",2026,2026,41,42,"2026-10-07","23:10:00","2026-10-16","04:55:00","8d, 5h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-005","Bremen - Hannover","<","Seelze West","Gümmerwald",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-007","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-019","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,29,29,"2026-07-17","00:30:00","2026-07-17","04:30:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-037","Bremen - Hannover","<","Seelze West","Gümmerwald",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-038","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1B534-001","Bremen - Hannover","< >","Verden (Aller)","Walle (Kr Verden)",2026,2026,50,50,"2026-12-07","22:00:00","2026-12-12","05:00:00","4d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1D131-002","Bremen - Hannover","< >","Visselhövede","Langwedel",2026,2026,19,22,"2026-05-08","23:30:00","2026-05-25","06:00:00","16d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1D131-001","Bremen - Hannover","< >","Visselhövede","Langwedel",2026,2026,19,22,"2026-05-05","23:30:00","2026-05-28","05:10:00","22d, 5h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"5,6",1]
[null,"DB InfraGO AG","1C80D-002","Bremen - Hannover",">","Wunstorf","Haste",2026,2026,28,29,"2026-07-10","17:15:00","2026-07-15","05:15:00","4d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1C80D-004","Bremen - Hannover","< >","Wunstorf","Haste",2026,2026,29,32,"2026-07-15","05:15:00","2026-08-06","09:00:00","22d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1C80D-006","Bremen - Hannover",">","Wunstorf","Haste",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1C80D-009","Bremen - Hannover",">","Wunstorf","Haste",2026,2026,33,35,"2026-08-13","19:00:00","2026-08-30","00:30:00","16d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-012","Bremen - Hannover","< >","Wunstorf","Letter                            (Abzw)",2026,2026,32,32,"2026-08-08","01:00:00","2026-08-08","03:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-013","Bremen - Hannover","< >","Wunstorf","Letter                            (Abzw)",2026,2026,33,33,"2026-08-15","01:00:00","2026-08-15","03:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CBBC-001","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,31,"2026-07-29","08:00:00","2026-07-31","21:00:00","2d, 13h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EF-001","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,19,32,"2026-05-04","07:00:00","2026-08-07","19:00:00","95d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-002","Bremen - Hannover","< >","Wunstorf","Gümmerwald",2026,2026,27,28,"2026-07-05","23:00:00","2026-07-08","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-003","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,27,28,"2026-07-05","23:00:00","2026-07-08","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-004","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,27,32,"2026-07-05","23:00:00","2026-08-08","05:00:00","33d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-008","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,28,28,"2026-07-08","23:00:00","2026-07-10","05:00:00","1d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-009","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,28,29,"2026-07-10","23:00:00","2026-07-13","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-010","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,28,29,"2026-07-10","23:00:00","2026-07-13","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-012","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,32,"2026-07-13","00:01:00","2026-08-07","19:00:00","25d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-013","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,29,"2026-07-13","00:35:00","2026-07-15","04:35:00","2d, 4h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-014","Bremen - Hannover",">","Wunstorf","Wunstorf",2026,2026,29,29,"2026-07-16","00:35:00","2026-07-16","04:35:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-015","Bremen - Hannover",">","Wunstorf","Gümmerwald",2026,2026,29,29,"2026-07-16","00:35:00","2026-07-16","04:35:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-016","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,31,"2026-07-16","04:35:00","2026-07-31","21:00:00","15d, 16h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-017","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,31,"2026-07-16","04:35:00","2026-07-31","21:00:00","15d, 16h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-020","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","04:30:00","2026-07-31","04:30:00","14d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-021","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","21:00:00","2026-07-31","21:00:00","14d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-022","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,31,"2026-07-17","21:00:00","2026-07-31","21:00:00","14d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-023","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,29,31,"2026-07-17","21:00:00","2026-07-31","21:00:00","14d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-026","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,30,31,"2026-07-23","00:25:00","2026-07-31","04:30:00","8d, 4h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-029","Bremen - Hannover","<","Wunstorf","Gümmerwald",2026,2026,31,31,"2026-07-31","18:10:00","2026-07-31","20:55:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-031","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","09:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-032","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-033","Bremen - Hannover","< >","Wunstorf","Seelze",2026,2026,31,31,"2026-08-01","09:00:00","2026-08-02","09:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-035","Bremen - Hannover","< >","Wunstorf","Gümmerwald",2026,2026,31,32,"2026-07-31","23:00:00","2026-08-03","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-036","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,32,"2026-07-31","23:00:00","2026-08-03","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-040","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-041","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-05","23:00:00","2026-08-08","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-042","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-05","23:00:00","2026-08-08","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-001","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-002","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-003","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-004","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,40,40,"2026-10-03","00:30:00","2026-10-03","04:30:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-005","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,41,42,"2026-10-10","00:30:00","2026-10-12","04:30:00","2d, 4h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-048","Bremen - Hannover","< >","Wunstorf","Gümmerwald",2026,2026,29,29,"2026-07-18","00:45:00","2026-07-18","03:45:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","214B7-001","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,41,41,"2026-10-05","22:30:00","2026-10-10","04:30:00","4d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","214B7-004","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"3,4",1]
[null,"DB InfraGO AG","214B7-008","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-016","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-020","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-024","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"1,2",1]
[null,"DB InfraGO AG","214B7-026","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-001","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-03","06:00:00","2026-08-05","18:00:00","2d, 12h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-005","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,32,32,"2026-08-07","01:00:00","2026-08-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-006","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Rbf Abzw",2026,2026,32,34,"2026-08-07","05:00:00","2026-08-19","01:00:00","11d, 20h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-022","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,34,34,"2026-08-19","01:00:00","2026-08-19","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-002","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,41,41,"2026-10-05","23:00:00","2026-10-10","05:00:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-003","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen-Walle",2026,2026,41,41,"2026-10-05","23:00:00","2026-10-10","05:00:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-005","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-006","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-009","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-010","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-011","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-012","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-017","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-018","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-021","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-022","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-025","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-027","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen-Walle",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-028","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1E35C-004","Bremerhaven - Bremen","<","Bremen Rbf Ausfahrt","Bremen Hbf",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-05","20:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1F8D6-009","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-07","18:00:00","2026-08-07","20:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-010","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-08","04:00:00","2026-08-08","07:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-012","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,33,"2026-08-16","15:00:00","2026-08-16","16:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-013","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,33,"2026-08-16","19:00:00","2026-08-16","20:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-014","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,34,"2026-08-16","23:00:00","2026-08-17","00:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-015","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","02:00:00","2026-08-17","07:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-016","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","13:00:00","2026-08-17","15:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-018","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","21:00:00","2026-08-18","00:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-019","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-18","02:00:00","2026-08-18","05:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-004","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","10:30:00","2026-09-22","11:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-005","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","13:30:00","2026-09-22","14:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-009","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-23","10:30:00","2026-09-23","11:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1E8C2-003","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,2,3,"2026-01-09","23:00:00","2026-01-12","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-007","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,3,4,"2026-01-16","23:00:00","2026-01-19","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-011","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,4,5,"2026-01-23","23:00:00","2026-01-26","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-013","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,5,5,"2026-01-26","23:00:00","2026-01-30","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-015","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,5,6,"2026-01-30","23:00:00","2026-02-02","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-017","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,6,6,"2026-02-02","23:00:00","2026-02-06","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C3-001","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,6,7,"2026-02-06","23:00:00","2026-02-09","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C3-006","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,7,8,"2026-02-13","21:00:00","2026-02-16","05:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C3-010","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-23","05:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C3-012","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,9,9,"2026-02-23","21:00:00","2026-02-27","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C3-014","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,9,10,"2026-02-27","23:00:00","2026-03-02","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E70A-034","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,10,10,"2026-03-02","23:00:00","2026-03-04","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E70A-038","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2026,2026,10,11,"2026-03-06","23:00:00","2026-03-09","05:00:00","2d, 6h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1E70A-042","Bremerhaven - Bremen",">","Bremen-Burg","Oldenbüttel",2026,2026,11,11,"2026-03-11","23:00:00","2026-03-13","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-004","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,32,32,"2026-08-07","01:00:00","2026-08-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-023","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,34,34,"2026-08-19","01:00:00","2026-08-19","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D8-003","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","07:00:00","2026-09-22","15:30:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D8-006","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-23","07:00:00","2026-09-23","12:30:00","0d, 5h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-013","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-023","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-014","Bremerhaven - Bremen","< >","Bremen-Walle","Bremen Rbf Abzw",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-015","Bremerhaven - Bremen","< >","Bremen-Walle","Bremen Rbf Abzw",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","218BF-001","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,2,6,"2026-01-09","23:00:00","2026-02-02","05:00:00","23d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","218BF-002","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,2,2,"2026-01-09","23:00:00","2026-01-10","05:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","218BF-004","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,12,13,"2026-03-20","23:00:00","2026-03-23","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-001","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,43,44,"2026-10-23","23:00:00","2026-10-27","05:00:00","3d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-003","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,44,44,"2026-10-27","05:00:00","2026-10-30","08:00:00","3d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-004","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,45,45,"2026-11-03","05:00:00","2026-11-06","08:00:00","3d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-001","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,21,21,"2026-05-23","21:00:00","2026-05-24","13:00:00","0d, 16h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-011","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,27,28,"2026-07-03","19:00:00","2026-07-09","10:00:00","5d, 15h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-023","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,30,31,"2026-07-23","19:00:00","2026-07-30","05:00:00","6d, 10h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-001","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven Hbf",2026,2026,31,35,"2026-08-01","02:00:00","2026-08-27","15:00:00","26d, 13h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-003","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,31,31,"2026-07-31","22:00:00","2026-08-01","05:00:00","0d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-005","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven Hbf",2026,2026,31,31,"2026-08-01","22:00:00","2026-08-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-014","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,35,35,"2026-08-29","22:00:00","2026-08-30","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-015","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-08","06:00:00","3d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","218BF-003","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven Hbf",2026,2026,7,12,"2026-02-09","23:00:00","2026-03-17","05:00:00","35d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","218BF-005","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven Hbf",2026,2026,16,17,"2026-04-17","23:00:00","2026-04-20","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-002","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven Hbf",2026,2026,44,45,"2026-10-30","23:00:00","2026-11-03","05:00:00","3d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-014","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven-Wulsdorf",2026,2026,28,28,"2026-07-08","18:00:00","2026-07-09","10:00:00","0d, 16h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-016","Bremerhaven - Bremen","< >","Bremerhaven-Lehe Pbf","Bremerhaven-Wulsdorf",2026,2026,28,28,"2026-07-11","00:00:00","2026-07-11","06:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-024","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven-Wulsdorf",2026,2026,30,31,"2026-07-23","23:00:00","2026-07-27","05:00:00","3d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-026","Bremerhaven - Bremen",">","Bremerhaven-Lehe Pbf","Bremerhaven-Wulsdorf",2026,2026,31,31,"2026-07-28","16:00:00","2026-07-29","08:00:00","0d, 16h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-002","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,22,23,"2026-05-29","22:00:00","2026-06-01","06:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-003","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,23,24,"2026-06-05","23:00:00","2026-06-08","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-005","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,23,23,"2026-06-05","23:00:00","2026-06-06","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-006","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,23,24,"2026-06-07","23:00:00","2026-06-08","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-007","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,24,25,"2026-06-12","23:00:00","2026-06-15","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-008","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,24,25,"2026-06-12","23:00:00","2026-06-15","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","21EAA-009","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,24,24,"2026-06-12","23:00:00","2026-06-13","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-010","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,24,25,"2026-06-14","23:00:00","2026-06-15","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-013","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,28,28,"2026-07-09","10:00:00","2026-07-11","05:00:00","1d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-015","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,28,28,"2026-07-09","10:00:00","2026-07-11","05:00:00","1d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-017","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,28,29,"2026-07-12","22:00:00","2026-07-13","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-018","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,29,29,"2026-07-13","05:00:00","2026-07-14","05:00:00","1d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","21EAA-019","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,23,24,"2026-06-05","23:00:00","2026-06-08","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-004","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,31,32,"2026-08-01","05:00:00","2026-08-03","05:00:00","2d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-008","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,32,33,"2026-08-07","16:00:00","2026-08-11","09:00:00","3d, 17h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-010","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,33,35,"2026-08-16","22:00:00","2026-08-24","06:00:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1E8C3-004","Bremerhaven - Bremen","<","Oldenbüttel","Bremen-Burg",2026,2026,7,7,"2026-02-11","21:00:00","2026-02-13","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1E70A-040","Bremerhaven - Bremen","<","Oldenbüttel","Bremen-Burg",2026,2026,11,11,"2026-03-09","23:00:00","2026-03-11","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1E8C2-002","Bremerhaven - Bremen",">","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,2,2,"2026-01-05","23:00:00","2026-01-09","05:00:00","3d, 6h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E8C2-014","Bremerhaven - Bremen","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,5,5,"2026-01-26","23:00:00","2026-01-30","05:00:00","3d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1E8C3-013","Bremerhaven - Bremen","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,9,9,"2026-02-23","21:00:00","2026-02-27","05:00:00","3d, 8h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1E70A-043","Bremerhaven - Bremen","< >","Osterholz-Scharmbeck","Osterholz-Scharmbeck",2026,2026,11,11,"2026-03-11","23:00:00","2026-03-13","05:00:00","1d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1C34A-003","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Laufach",2026,2026,16,18,"2026-04-13","23:00:00","2026-04-27","05:00:00","13d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1C34A-006","Darmstadt - Nürnberg","< >","Aschaffenburg Hbf","Aburg-Goldbach",2026,2026,20,21,"2026-05-16","23:00:00","2026-05-24","05:00:00","7d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","202DB-002","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Wiesthal",2026,2026,46,46,"2026-11-11","22:00:00","2026-11-12","04:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","218BA-010","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Stockstadt (Main)",2026,2026,49,49,"2026-12-04","21:00:00","2026-12-06","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","1FBAC-004","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,32,32,"2026-08-08","18:00:00","2026-08-09","14:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FC34-004","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,11,12,"2026-03-15","06:00:00","2026-03-16","06:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1C058-002","Darmstadt - Nürnberg","< >","Darmstadt Gbf","Darmstadt Nord",2026,2026,10,12,"2026-03-06","21:00:00","2026-03-20","05:00:00","13d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1C058-006","Darmstadt - Nürnberg","< >","Darmstadt Gbf","Darmstadt Nord",2026,2026,26,27,"2026-06-26","21:00:00","2026-07-03","05:00:00","6d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1C08E-001","Darmstadt - Nürnberg","<","Darmstadt Gbf","Weiterstadt",2026,2026,15,16,"2026-04-11","21:00:00","2026-04-13","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1C08E-004","Darmstadt - Nürnberg","<","Darmstadt Gbf","Weiterstadt",2026,2026,23,23,"2026-06-05","21:00:00","2026-06-06","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1C882-009","Darmstadt - Nürnberg","<","Darmstadt Gbf","Weiterstadt",2026,2026,15,16,"2026-04-10","21:00:00","2026-04-17","05:00:00","6d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-06-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1C882-010","Darmstadt - Nürnberg","<","Darmstadt Hbf","Darmstadt-Arheilgen",2026,2026,15,16,"2026-04-10","21:00:00","2026-04-17","05:00:00","6d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-046","Darmstadt - Nürnberg",">","Darmstadt Hbf","Messel",2026,2026,11,12,"2026-03-15","19:00:00","2026-03-16","05:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3506-(MK26)-05","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,19,21,"14.05.2027","21:00:00","28.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK27)-01","Darmstadt - Nürnberg",">","Darmstadt Hbf","Darmstadt Nord",2027,2027,23,25,"11.06.2027","21:00:00","25.06.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-003","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt-Kranichstein",2026,2026,1,2,"2026-01-02","21:00:00","2026-01-06","05:00:00","3d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-006","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt Nord",2026,2026,1,2,"2026-01-02","21:00:00","2026-01-06","05:00:00","3d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-008","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt-Kranichstein",2026,2026,2,2,"2026-01-06","21:00:00","2026-01-09","05:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-016","Darmstadt - Nürnberg","< >","Darmstadt Nord","Darmstadt Nord",2026,2026,5,5,"2026-01-30","21:00:00","2026-01-31","09:00:00","0d, 12h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-026","Darmstadt - Nürnberg",">","Darmstadt Nord","Darmstadt Nord",2026,2026,1,2,"2026-01-02","21:00:00","2026-01-06","05:00:00","3d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,7",1]
[null,"DB InfraGO AG","20C05-049","Darmstadt - Nürnberg",">","Darmstadt Nord","Darmstadt-Kranichstein",2026,2026,5,5,"2026-01-31","21:00:00","2026-02-01","09:00:00","0d, 12h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1C08E-008","Darmstadt - Nürnberg",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,24,24,"2026-06-09","21:00:00","2026-06-10","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-001","Darmstadt - Nürnberg","< >","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,1,12,"2026-01-02","00:00:00","2026-03-17","23:59:00","74d, 23h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-020","Darmstadt - Nürnberg","<","Darmstadt-Kranichstein","Darmstadt Nord",2026,2026,5,6,"2026-02-01","17:00:00","2026-02-02","05:00:00","0d, 12h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-029","Darmstadt - Nürnberg","<","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,6,7,"2026-02-08","21:00:00","2026-02-13","05:00:00","4d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-031","Darmstadt - Nürnberg","< >","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-20","05:00:00","3d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-037","Darmstadt - Nürnberg","< >","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,10,11,"2026-03-08","17:00:00","2026-03-09","05:00:00","0d, 12h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-041","Darmstadt - Nürnberg",">","Darmstadt-Kranichstein","Darmstadt-Kranichstein",2026,2026,11,11,"2026-03-11","21:00:00","2026-03-13","07:00:00","1d, 10h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-043","Darmstadt - Nürnberg","<","Darmstadt-Kranichstein","Darmstadt Bergschneise",2026,2026,11,11,"2026-03-13","21:00:00","2026-03-14","07:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-051","Darmstadt - Nürnberg","<","Darmstadt-Kranichstein","Darmstadt Nord",2026,2026,11,11,"2026-03-14","21:00:00","2026-03-15","07:00:00","0d, 10h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1DB53-001","Darmstadt - Nürnberg","< >","Ebelsbach-Eltmann","Oberhaid",2026,2026,29,29,"2026-07-16","21:00:00","2026-07-17","05:00:00","0d, 8h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",,0",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","20130-002","Darmstadt - Nürnberg","<","Eltersdorf","Vach",2026,2026,26,27,"2026-06-28","21:00:00","2026-06-29","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","21811-018","Darmstadt - Nürnberg","<","Espenloh","Lohr Bahnhof",2026,2026,47,47,"2026-11-20","21:00:00","2026-11-22","07:00:00","1d, 10h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","22160-001","Darmstadt - Nürnberg","< >","Eußenheim","Wernfeld",2026,2026,11,12,"2026-03-15","08:00:00","2026-03-16","05:00:00","0d, 21h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-12",null,null,"5,6",1]
[null,"DB InfraGO AG","221FC-003","Darmstadt - Nürnberg",">","Gambach Üst","Gemünden (Main)",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","20029-002","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2025,2026,50,5,"2025-12-14","08:00:00","2026-01-30","20:00:00","47d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","20029-004","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2025,2026,50,5,"2025-12-14","08:00:00","2026-01-30","20:00:00","47d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","20029-009","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,2,3,"2026-01-07","08:00:00","2026-01-18","20:00:00","11d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","20029-019","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,13,27,"2026-03-28","08:00:00","2026-06-29","20:00:00","93d, 11h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,7",1]
[null,"DB InfraGO AG","20029-024","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,27,27,"2026-06-30","08:00:00","2026-07-01","20:00:00","1d, 12h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-005","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,35,"2026-08-25","23:00:00","2026-08-27","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-006","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,35,"2026-08-25","23:00:00","2026-08-27","05:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-012","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,37,38,"2026-09-11","08:00:00","2026-09-18","20:00:00","7d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-019","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,39,40,"2026-09-24","23:00:00","2026-09-28","20:00:00","3d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-022","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,41,42,"2026-10-09","23:00:00","2026-10-13","20:00:00","3d, 21h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-026","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,42,43,"2026-10-14","23:00:00","2026-10-20","05:00:00","5d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-28",null,null,"3,4",1]
[null,"DB InfraGO AG","202A2-006","Darmstadt - Nürnberg",">","Gemünden (Main)","Lohr Bahnhof",2026,2026,37,37,"2026-09-11","01:00:00","2026-09-11","05:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-031","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","221FC-002","Darmstadt - Nürnberg","< >","Gemünden (Main)","Wernfeld",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-004","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","222C2-001","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,26,34,"2026-06-26","21:00:00","2026-08-21","06:00:00","55d, 9h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1FBAC-006","Darmstadt - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2026,2026,32,32,"2026-08-08","18:00:00","2026-08-09","14:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","1FC34-003","Darmstadt - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2026,2026,11,11,"2026-03-13","22:00:00","2026-03-15","06:00:00","1d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB63-002","Darmstadt - Nürnberg","<","Haßfurt","Zeil",2026,2026,28,29,"2026-07-12","21:00:00","2026-07-16","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-08-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1FFFE-001","Darmstadt - Nürnberg",">","Langenprozelten","Lohr Bahnhof",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1C34A-004","Darmstadt - Nürnberg",">","Laufach","Aschaffenburg Hbf",2026,2026,18,20,"2026-04-27","23:00:00","2026-05-11","05:00:00","13d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1FFFE-006","Darmstadt - Nürnberg","<","Lohr Bahnhof","Rohrbach",2026,2026,41,42,"2026-10-07","21:00:00","2026-10-12","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","21811-016","Darmstadt - Nürnberg","<","Lohr Bahnhof","Nantenbach",2026,2026,42,43,"2026-10-18","21:00:00","2026-10-23","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20C05-021","Darmstadt - Nürnberg",">","Messel","Darmstadt-Kranichstein",2026,2026,5,6,"2026-02-01","17:00:00","2026-02-02","05:00:00","0d, 12h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","221C0-002","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Arnstein (Unterfr)",2026,2026,48,48,"2026-11-24","08:00:00","2026-11-24","16:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"6,7",1]
[null,"DB InfraGO AG","222C2-003","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Wernfeld",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-22","06:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"1,2",1]
[null,"DB InfraGO AG","1FFFE-003","Darmstadt - Nürnberg","< >","Nantenbach","Nantenbach",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3",1]
[null,"DB InfraGO AG","21811-024","Darmstadt - Nürnberg","< >","Nantenbach","Hohe Wart",2026,2026,47,48,"2026-11-22","19:00:00","2026-11-23","05:00:00","0d, 10h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-08-02",null,null,"5,6",1]
[null,"DB InfraGO AG","1E4C5-005","Darmstadt - Nürnberg","< >","Nürnberg Großmarkt","Fürth (Bay) Gbf",2026,2026,31,32,"2026-07-30","05:00:00","2026-08-06","21:00:00","7d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"1,7",1]
[null,"DB InfraGO AG","1FA7F-006","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Eibach",2026,2026,15,15,"2026-04-07","00:00:00","2026-04-07","05:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-007","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nür Jansenbr",2026,2026,15,15,"2026-04-07","00:00:00","2026-04-07","05:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-010","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,19,19,"2026-05-07","22:00:00","2026-05-08","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-016","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nür Jansenbr",2026,2026,19,20,"2026-05-08","22:00:00","2026-05-13","22:00:00","5d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-23",null,null,"2,3",1]
[null,"DB InfraGO AG","216FB-019","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,20,20,"2026-05-13","22:00:00","2026-05-14","04:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","216FB-024","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,20,20,"2026-05-13","22:00:00","2026-05-14","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-047","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,"6,6,6",null,null,null,"N",null,"2024-08-07",null,null,"4,5",1]
[null,"DB InfraGO AG","3247-(MK27)-02","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2027,2027,21,26,"28.05.2027","21:00:00","02.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-03","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,41,43,"15.10.2027","21:00:00","29.10.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-04","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,10,11,"12.03.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-005","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,14,16,"2026-04-05","00:00:00","2026-04-13","18:00:00","8d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-015","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,15,16,"2026-04-12","22:00:00","2026-04-13","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-20",null,null,4,1]
[null,"DB InfraGO AG","1FA7F-018","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,16,16,"2026-04-13","13:00:00","2026-04-13","18:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-01-20",null,null,4,1]
[null,"DB InfraGO AG","1FA7F-023","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,17,17,"2026-04-21","06:00:00","2026-04-26","06:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,4,1]
[null,"DB InfraGO AG","1FA7F-030","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,17,18,"2026-04-26","06:00:00","2026-04-30","00:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-034","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,17,18,"2026-04-26","22:00:00","2026-04-27","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-038","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,18,18,"2026-04-30","00:00:00","2026-04-30","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-039","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,18,18,"2026-04-30","00:00:00","2026-04-30","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-046","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,17,17,"2026-04-26","06:00:00","2026-04-26","14:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-008","Darmstadt - Nürnberg",">","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,19,19,"2026-05-07","22:00:00","2026-05-08","03:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-017","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,19,20,"2026-05-08","22:00:00","2026-05-13","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-026","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,20,20,"2026-05-15","22:00:00","2026-05-16","02:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-035","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,21,22,"2026-05-22","22:00:00","2026-05-26","16:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-039","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,22,22,"2026-05-26","22:00:00","2026-05-27","02:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-046","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,29,29,"2026-07-17","22:00:00","2026-07-19","16:00:00","1d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-04-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-047","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,29,29,"2026-07-17","22:00:00","2026-07-19","16:00:00","1d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-054","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,31,32,"2026-08-02","21:00:00","2026-08-03","02:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-20",null,null,"5,6",1]
[null,"DB InfraGO AG","2281F-001","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Eibach                 (S-Bahn)",2026,2026,31,33,"2026-08-01","23:30:00","2026-08-10","04:30:00","8d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-050","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,15,17,"2026-04-08","18:00:00","2026-04-26","06:00:00","17d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","216FB-031","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,20,21,"2026-05-16","22:00:00","2026-05-22","03:00:00","5d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1E5EA-004","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,41,42,"2026-10-08","05:00:00","2026-10-13","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA7F-044","Darmstadt - Nürnberg","<","Nürnberg-Schweinau","Nürnberg Hbf",2026,2026,18,18,"2026-05-01","22:00:00","2026-05-03","04:00:00","1d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA90-053","Darmstadt - Nürnberg","< >","Nürnberg-Schweinau","Nürnberg Hbf",2026,2026,31,31,"2026-08-02","13:00:00","2026-08-02","21:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB53-002","Darmstadt - Nürnberg","< >","Oberhaid","Ebelsbach-Eltmann",2026,2026,29,29,"2026-07-16","21:00:00","2026-07-17","05:00:00","0d, 8h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1DDD1-007","Darmstadt - Nürnberg","< >","Roth","Nürnberg Hbf",2026,2026,31,38,"2026-07-28","04:25:00","2026-09-19","04:00:00","52d, 23h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1DA02-004","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,34,"2026-08-11","23:00:00","2026-08-18","23:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-008","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-010","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-22","00:00:00","2026-08-22","05:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-030","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,41,41,"2026-10-10","00:00:00","2026-10-10","06:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-003","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,33,"2026-08-12","09:30:00","2026-08-14","10:30:00","2d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD26-001","Darmstadt - Nürnberg","<","Schweinfurt Hbf","Haßfurt",2026,2026,31,31,"2026-07-30","08:00:00","2026-07-31","15:30:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-08-01",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD2B-002","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,43,44,"2026-10-25","22:00:00","2026-10-27","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,0",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD36-001","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,48,49,"2026-11-28","22:30:00","2026-11-30","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD36-007","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-03","05:20:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-039","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-21","00:00:00","2026-08-21","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-042","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-07","23:00:00","2026-08-28","23:00:00","21d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-004","Darmstadt - Nürnberg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2026,2026,33,34,"2026-08-15","08:00:00","2026-08-18","16:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","218BA-009","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,49,49,"2026-12-04","21:00:00","2026-12-06","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20088-001","Darmstadt - Nürnberg",">","Vach","Eltersdorf",2026,2026,10,10,"2026-03-07","21:00:00","2026-03-08","01:00:00","0d, 4h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","20088-003","Darmstadt - Nürnberg",">","Vach","Eltersdorf",2026,2026,10,10,"2026-03-08","17:00:00","2026-03-08","23:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","20130-005","Darmstadt - Nürnberg","< >","Vach","Eltersdorf",2026,2026,27,27,"2026-07-01","21:00:00","2026-07-02","05:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1DBBC-002","Darmstadt - Nürnberg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,21,22,"2026-05-23","08:00:00","2026-05-29","16:30:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1DCD7-006","Darmstadt - Nürnberg","< >","Waigolshausen","Mühlhausen (Wern)",2026,2026,34,34,"2026-08-19","08:00:00","2026-08-20","16:00:00","1d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1DD08-002","Darmstadt - Nürnberg","< >","Waigolshausen","Rottendorf",2026,2026,4,5,"2026-01-19","01:30:00","2026-01-26","02:30:00","7d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","222C2-006","Darmstadt - Nürnberg","< >","Waigolshausen","Wernfeld",2026,2026,34,34,"2026-08-20","06:00:00","2026-08-21","06:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1056-(MK27)-06","Darmstadt - Nürnberg",">","Waigolshausen","Bamberg",2027,2027,36,49,"10.09.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1C08E-007","Darmstadt - Nürnberg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,24,24,"2026-06-08","21:00:00","2026-06-10","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1C08E-019","Darmstadt - Nürnberg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,28,32,"2026-07-12","21:00:00","2026-08-07","21:00:00","26d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-16",null,null,"3,4",1]
[null,"DB InfraGO AG","221D3-001","Darmstadt - Nürnberg","< >","Wernfeld","Gemünden (Main)",2026,2026,47,50,"2026-11-20","21:00:00","2026-12-11","05:00:00","20d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"4,5",1]
[null,"DB InfraGO AG","1DBAD-002","Darmstadt - Nürnberg","< >","Zeil","Gädheim",2026,2026,31,31,"2026-07-27","10:00:00","2026-07-29","11:00:00","2d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","20AD8-002","Darmstadt - Nürnberg","< >","Zollberg","Gemünden (Main)",2026,2026,28,30,"2026-07-10","21:00:00","2026-07-21","05:00:00","10d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-06",null,null,"6,7",1]
[null,"DB InfraGO AG","20AD8-007","Darmstadt - Nürnberg",">","Zollberg","Gemünden (Main)",2026,2026,29,30,"2026-07-14","21:00:00","2026-07-21","05:00:00","6d, 8h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","20535-013","Dresden - Děčín",">","Bad Schandau","Bad Schandau",2026,2026,6,9,"2026-02-02","07:00:00","2026-02-26","17:00:00","24d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","29F74-002","Dresden - Děčín","< >","Bad Schandau","Bad Schandau Gr",2026,2026,12,12,"2026-03-16","09:10:00","2026-03-16","18:50:00","0d, 9h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","20535-011","Dresden - Děčín","< >","Bad Schandau Gr","Königst (Sä) Üst",2026,2026,5,5,"2026-01-31","20:00:00","2026-02-01","04:00:00","0d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-30",null,null,"1,6,7",1]
[null,"DB InfraGO AG","20535-018","Dresden - Děčín","< >","Bad Schandau Gr","Königst (Sä) Üst",2026,2026,9,9,"2026-02-26","20:00:00","2026-02-28","04:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-30",null,null,"1,6,7",1]
[null,"DB InfraGO AG","2A2E0-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,16,21,"2026-04-13","09:10:00","2026-05-18","18:50:00","35d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"Y",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","2A3A6-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,41,41,"2026-10-06","09:10:00","2026-10-06","17:10:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2A4FD-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,46,46,"2026-11-10","09:10:00","2026-11-13","17:10:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","2A51D-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,46,50,"2026-11-09","09:10:00","2026-12-07","18:50:00","28d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"Y",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-12_N","Dresden - Děčín","< >","Bad Schandau Gr","Pirna",2027,2027,46,49,"19.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1FE81-002","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"Y",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","20535-006","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau",2026,2026,1,5,"2026-01-03","04:00:00","2026-01-31","20:00:00","28d, 16h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","20535-007","Dresden - Děčín",">","Bad Schandau Ost","Bad Schandau",2026,2026,1,5,"2026-01-03","04:00:00","2026-01-31","20:00:00","28d, 16h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","20535-015","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau",2026,2026,5,9,"2026-02-01","04:00:00","2026-02-27","20:00:00","26d, 16h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","2A4F2-003","Dresden - Děčín","< >","Bad Schandau Ost","Schöna",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","1DC42-015","Dresden - Děčín","< >","Heidenau","Dohna (Sachs)",2026,2026,3,3,"2026-01-12","00:00:00","2026-01-12","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2027B-002","Dresden - Děčín","< >","Heidenau","Dresden-Reick",2026,2026,6,6,"2026-02-02","22:10:00","2026-02-04","04:10:00","1d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","206F2-011","Dresden - Děčín","< >","Königst (Sä) Üst","Kurort Rathen (Kr Pirna)",2026,2026,16,17,"2026-04-17","04:30:00","2026-04-25","21:00:00","8d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","206F2-018","Dresden - Děčín",">","Königst (Sä) Üst","Kurort Rathen (Kr Pirna)",2026,2026,18,19,"2026-04-29","04:30:00","2026-05-08","21:00:00","9d, 16h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","206A9-002","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,8,9,"2026-02-21","20:00:00","2026-02-26","04:00:00","4d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"5,6",1]
[null,"DB InfraGO AG","206A9-003","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,8,9,"2026-02-21","20:00:00","2026-02-26","04:00:00","4d, 8h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"3,4",1]
[null,"DB InfraGO AG","206A9-011","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,9,11,"2026-02-27","00:01:00","2026-03-11","04:00:00","12d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","206A9-018","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,12,12,"2026-03-18","20:00:00","2026-03-22","04:00:00","3d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","206A9-025","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Pirna",2026,2026,15,15,"2026-04-07","20:00:00","2026-04-11","04:00:00","3d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"3,4",1]
[null,"DB InfraGO AG","206F2-007","Dresden - Děčín","<","Kurort Rathen (Kr Pirna)","Kurort Rathen (Kr Pirna)",2026,2026,16,17,"2026-04-17","04:30:00","2026-04-25","21:00:00","8d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","206F2-019","Dresden - Děčín","< >","Kurort Rathen (Kr Pirna)","Königst (Sä) Üst",2026,2026,18,19,"2026-04-29","04:30:00","2026-05-08","21:00:00","9d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-05-10",null,null,"5,6",1]
[null,"DB InfraGO AG","20005-005","Dresden - Děčín",">","Obervogelgesang","Pirna",2026,2026,24,26,"2026-06-14","21:00:00","2026-06-26","05:00:00","11d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","206A9-021","Dresden - Děčín","< >","Obervogelgesang","Pirna",2026,2026,12,14,"2026-03-22","04:00:00","2026-04-01","21:00:00","10d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","206F2-013","Dresden - Děčín","< >","Obervogelgesang","Bad Schandau",2026,2026,17,18,"2026-04-25","21:00:00","2026-04-29","04:30:00","3d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1B3FB-002","Dresden - Děčín","< >","Pirna","Pirna",2025,2026,50,14,"2025-12-14","00:00:00","2026-04-02","23:59:00","109d, 22h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-07-12",null,null,"2,3",1]
[null,"DB InfraGO AG","207CD-005","Dresden - Děčín","< >","Pirna","Heidenau",2026,2026,20,20,"2026-05-15","21:00:00","2026-05-17","05:00:00","1d, 8h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","1F543-017","Dresden - Děčín","< >","Pirna Gbf","Pirna",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","206A9-022","Dresden - Děčín","<","Pirna Gbf","Pirna",2026,2026,13,14,"2026-03-29","22:00:00","2026-04-01","04:00:00","2d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1F543-018","Dresden - Děčín","< >","Rathmannsdorf(P)","Bad Schandau",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"2,3",1]
[null,"DB InfraGO AG","2A097-001","Dresden - Děčín",">","Schmilka-Hir","Bad Schandau Ost",2026,2026,12,45,"2026-03-17","00:01:00","2026-11-05","23:59:00","233d, 23h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","2A2D1-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,12,12,"2026-03-17","09:10:00","2026-03-22","17:10:00","5d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2A2E0-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,13,14,"2026-03-23","09:10:00","2026-03-30","18:50:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2A307-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-05","22:20:00","2026-11-06","05:20:00","0d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","2A4FD-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,46,46,"2026-11-10","09:10:00","2026-11-13","17:10:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1BE30-001","Dresden - Děčín","< >","Sebnitz (Sachs)","Bad Schandau",2026,2026,34,35,"2026-08-17","22:00:00","2026-08-30","05:00:00","12d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-12",null,null,1,1]
[null,"DB InfraGO AG","1BF2F-002","Dresden - Děčín","< >","Sebnitz (Sachs)","Bad Schandau",2026,2026,24,24,"2026-06-09","07:00:00","2026-06-09","13:00:00","0d, 6h","Continuous","Tunnel","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,1,1]
[null,"DB InfraGO AG","1C092-015","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Coswig (bei Dresden)",2026,2026,40,40,"2026-09-28","04:00:00","2026-10-03","06:00:00","5d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1FB4B-010","Falkenberg - Dresden","<","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2026,2026,9,10,"2026-02-28","06:00:00","2026-03-03","18:00:00","3d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1C0FE-001","Falkenberg - Dresden","< >","Elsterwerda","Elsterwerda-Biehla",2026,2026,8,9,"2026-02-16","09:00:00","2026-02-23","15:00:00","7d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1C107-001","Falkenberg - Dresden","< >","Elsterwerda","Elsterwerda-Biehla",2026,2026,37,40,"2026-09-13","23:40:00","2026-09-28","04:20:00","14d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1C2D3-006","Falkenberg - Dresden",">","Elsterwerda","Frauenhain",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-26",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF3C-010","Falkenberg - Dresden","<","Kottewitz","Radebeul-Naundorf",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1BF59-003","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF59-007","Falkenberg - Dresden","<","Kottewitz","Weinböhla",2026,2026,41,47,"2026-10-05","04:00:00","2026-11-19","20:00:00","45d, 17h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1D405-003","Falkenberg - Dresden","< >","Leckwitz","Kottewitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1D405-012","Falkenberg - Dresden","< >","Leckwitz","Kottewitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1F543-026","Falkenberg - Dresden","< >","Leckwitz","Kottewitz",2026,2026,7,7,"2026-02-15","00:00:00","2026-02-15","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1C092-008","Falkenberg - Dresden",">","Meißen","Coswig (bei Dresden) Stw 1",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1652-(MK26)-02_N","Falkenberg - Dresden","< >","Priestewitz","Coswig Stw 1",2027,2027,19,27,"14.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CA98-004","Falkenberg - Dresden","< >","Riesa","Röderau",2026,2026,21,21,"2026-05-18","21:00:00","2026-05-19","09:00:00","0d, 12h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"5,6",1]
[null,"DB InfraGO AG","1CA98-009","Falkenberg - Dresden","< >","Riesa","Röderau Bogendreieck",2026,2026,21,30,"2026-05-19","09:00:00","2026-07-24","21:00:00","66d, 12h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-17",null,null,"2,3",1]
[null,"DB InfraGO AG","1CA98-011","Falkenberg - Dresden","< >","Riesa","Röderau Bogendreieck",2026,2026,21,30,"2026-05-19","09:00:00","2026-07-24","21:00:00","66d, 12h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-003","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,16,17,"2026-04-19","05:00:00","2026-04-20","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-006","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,16,17,"2026-04-19","05:00:00","2026-04-20","05:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-010","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1BAE4-013","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,28,29,"2026-07-10","21:00:00","2026-07-13","21:00:00","3d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1BAE4-017","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,30,50,"2026-07-22","21:00:00","2026-12-12","23:59:00","143d, 3h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-024","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,36,36,"2026-09-03","21:00:00","2026-09-04","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C91B-002","Frankfurt - Karlsruhe","<","Bickenbach (Bergstr)","Darmstadt-Eberstadt Nord",2026,2026,16,17,"2026-04-17","22:00:00","2026-04-20","04:00:00","2d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1C91B-003","Frankfurt - Karlsruhe","< >","Bickenbach Nord","Bickenbach Nord",2026,2026,16,17,"2026-04-17","22:00:00","2026-04-20","04:00:00","2d, 6h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK26)-09_WDN","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,7,11,"15.02.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP N + TSP WEN",null,null,null,"2024-04-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK27)-06","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-005","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Blankenloch",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"2,3",1]
[null,"DB InfraGO AG","1D41F-009","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-013","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-018","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1D41F-021","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1D4EB-002","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1D41F-022","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"6,7",1]
[null,"DB InfraGO AG","1D41F-026","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-029","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1896-(MK27)-21","Frankfurt - Karlsruhe","< >","Hanau Südseite","Großkrotzenburg",2027,2027,1,4,"08.01.2027","21:00:00","29.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-06-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1F485-006","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,6,6,"2026-02-02","23:00:00","2026-02-03","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1F485-025","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Hemsbach",2026,2026,6,6,"2026-02-05","23:00:00","2026-02-06","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1F485-033","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Weinheim (Bergstr) Hbf",2026,2026,7,7,"2026-02-09","23:00:00","2026-02-10","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-09",null,null,"2,3",1]
[null,"DB InfraGO AG","1F4F8-006","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,7,7,"2026-02-10","23:00:00","2026-02-11","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1F4F8-022","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,7,7,"2026-02-12","23:00:00","2026-02-13","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1F4F8-025","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,7,8,"2026-02-15","23:00:00","2026-02-17","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1F4F8-035","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,8,8,"2026-02-17","23:00:00","2026-02-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-09",null,null,7,1]
[null,"DB InfraGO AG","1F521-006","Frankfurt - Karlsruhe",">","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,8,8,"2026-02-18","23:00:00","2026-02-20","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-09",null,null,7,1]
[null,"DB InfraGO AG","1F841-008","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-06","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1F841-020","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,10,11,"2026-03-06","21:00:00","2026-03-13","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1F917-001","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,12,13,"2026-03-20","21:00:00","2026-03-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,2",1]
[null,"DB InfraGO AG","1F917-004","Frankfurt - Karlsruhe","< >","Heddesheim/Hirschberg","Heddesheim/Hirschberg",2026,2026,12,13,"2026-03-20","21:00:00","2026-03-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","1F521-019","Frankfurt - Karlsruhe","<","Heidelberg-Wieblingen","Ladenburg",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-25","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-26",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FAF2-003","Frankfurt - Karlsruhe","<","Heidelberg-Wieblingen","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,25,26,"2026-06-19","21:00:00","2026-06-22","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1F485-008","Frankfurt - Karlsruhe","< >","Hemsbach","Weinheim (Bergstr) Hbf",2026,2026,6,6,"2026-02-03","23:00:00","2026-02-04","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1F485-016","Frankfurt - Karlsruhe","< >","Hemsbach","Hemsbach",2026,2026,6,6,"2026-02-03","23:00:00","2026-02-04","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1F485-034","Frankfurt - Karlsruhe",">","Hemsbach","Ladenburg",2026,2026,7,7,"2026-02-09","23:00:00","2026-02-10","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1F485-041","Frankfurt - Karlsruhe","< >","Hemsbach","Weinheim (Bergstr) Hbf",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-022","Frankfurt - Karlsruhe","<","Heppenheim (Bergstr)","Bensheim-Auerbach",2026,2026,36,36,"2026-09-01","21:00:00","2026-09-02","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-11",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-005","Frankfurt - Karlsruhe",">","Heppenheim Nord","Heddesheim/Hirschberg",2026,2026,6,6,"2026-02-02","23:00:00","2026-02-03","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","3007-(MK27)-02","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,19,21,"15.05.2027","05:00:00","28.05.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-05","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,33,34,"20.08.2027","21:00:00","23.08.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-05-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1E550-001","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1E5BF-004","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,37,37,"2026-09-11","15:00:00","2026-09-11","21:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-011","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-017","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,37,37,"2026-09-07","22:00:00","2026-09-11","06:00:00","3d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK27)-02","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,9,10,"05.03.2027","21:00:00","12.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK27)-04","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,32,33,"13.08.2027","21:00:00","16.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1E501-009","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,21,21,"2026-05-18","23:00:00","2026-05-21","05:00:00","2d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,7,1]
[null,"DB InfraGO AG","1E501-019","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,37,"2026-08-29","18:00:00","2026-09-12","12:00:00","13d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-11-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1E501-022","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1E501-026","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-007","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-013","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-017","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-019","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-003","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-008","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,38,"2026-09-11","21:00:00","2026-09-16","08:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1F08E-009","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-11",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK26)-01","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,28,29,"16.07.2027","21:00:00","19.07.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-06_D","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,32,33,"14.08.2027","05:00:00","20.08.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1F71F-004","Frankfurt - Karlsruhe","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E709-007","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-22",null,null,3,1]
[null,"DB InfraGO AG","1E709-008","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,15,15,"2026-04-06","22:00:00","2026-04-07","06:00:00","0d, 8h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-16",null,null,4,1]
[null,"DB InfraGO AG","1F485-036","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,7,7,"2026-02-09","23:00:00","2026-02-10","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-12",null,null,"1,7",1]
[null,"DB InfraGO AG","1F4F8-015","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,7,7,"2026-02-11","23:00:00","2026-02-12","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-12",null,null,"4,5",1]
[null,"DB InfraGO AG","1F4F8-026","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,7,8,"2026-02-15","23:00:00","2026-02-17","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F4F8-037","Frankfurt - Karlsruhe","< >","Ladenburg","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,8,8,"2026-02-17","23:00:00","2026-02-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-24",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1F521-017","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-25","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1F841-013","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-06","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1F841-025","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,11,12,"2026-03-13","00:00:00","2026-03-20","05:00:00","7d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1F917-005","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,12,13,"2026-03-20","21:00:00","2026-03-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1FA57-028","Frankfurt - Karlsruhe",">","Ladenburg","Heidelberg-Wieblingen",2026,2026,24,25,"2026-06-12","21:00:00","2026-06-15","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-10-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB9B-006","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,16,17,"2026-04-17","21:00:00","2026-04-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB9B-025","Frankfurt - Karlsruhe","< >","Ladenburg","Ladenburg",2026,2026,29,30,"2026-07-17","21:00:00","2026-07-20","05:00:00","2d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1C651-004","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FBE8-006","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,20,21,"2026-05-15","01:00:00","2026-05-22","05:00:00","7d, 4h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-31",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1699-(MK27)-01","Frankfurt - Karlsruhe",">","Ludwigsburg","Bietigheim-Biss",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-11-08",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","3039-(MK27)-05","Frankfurt - Karlsruhe","< >","Ludwigsburg","Pragtunnel",2027,2027,46,47,"19.11.2027","21:00:00","26.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-11-08",null,null,"5,6",1]
[null,"DB InfraGO AG","1D7C2-011","Frankfurt - Karlsruhe","< >","Mannheim Hbf","Hockenheim",2026,2026,14,15,"2026-04-05","22:00:00","2026-04-06","06:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-08",null,null,"1,7",1]
[null,"DB InfraGO AG","1FA57-006","Frankfurt - Karlsruhe","<","M-Fr Südein/Ausf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-04",null,null,6,1]
[null,"DB InfraGO AG","1E709-010","Frankfurt - Karlsruhe","<","Neu-Edingen/Mhm-Friedrichsfeld","Heddesheim/Hirschberg",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E709-016","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,15,15,"2026-04-07","22:00:00","2026-04-08","06:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-18",null,null,7,1]
[null,"DB InfraGO AG","1F4F8-018","Frankfurt - Karlsruhe","<","Neu-Edingen/Mhm-Friedrichsfeld","Heddesheim/Hirschberg",2026,2026,7,7,"2026-02-12","23:00:00","2026-02-13","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-18",null,null,4,1]
[null,"DB InfraGO AG","1F4F8-034","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,8,8,"2026-02-17","23:00:00","2026-02-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1F521-016","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,9,9,"2026-02-23","23:00:00","2026-02-25","05:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F521-028","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,10,10,"2026-03-02","23:00:00","2026-03-05","05:00:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-30",null,null,3,1]
[null,"DB InfraGO AG","1F55A-001","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,9,9,"2026-02-25","23:00:00","2026-02-28","05:00:00","2d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-18",null,null,3,1]
[null,"DB InfraGO AG","1F55A-008","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,9,9,"2026-02-25","23:00:00","2026-02-28","05:00:00","2d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-24",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1F55A-015","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,11,11,"2026-03-10","23:00:00","2026-03-11","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-15",null,null,"6,7",1]
[null,"DB InfraGO AG","1F841-016","Frankfurt - Karlsruhe","<","Neu-Edingen/Mhm-Friedrichsfeld","Heddesheim/Hirschberg",2026,2026,10,11,"2026-03-06","21:00:00","2026-03-13","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1F917-008","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,12,13,"2026-03-20","21:00:00","2026-03-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-10",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F917-016","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,13,14,"2026-03-27","21:00:00","2026-04-03","05:00:00","6d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-18",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1F917-023","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,17,17,"2026-04-20","21:00:00","2026-04-24","05:00:00","3d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FA57-002","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,1,1]
[null,"DB InfraGO AG","1FA57-003","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-24",null,null,1,1]
[null,"DB InfraGO AG","1FA57-009","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-24",null,null,2,1]
[null,"DB InfraGO AG","1FA57-017","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA57-019","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1FA57-023","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-03",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FAF2-001","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,25,26,"2026-06-19","21:00:00","2026-06-22","05:00:00","2d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FAF2-007","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1FAF2-011","Frankfurt - Karlsruhe",">","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1FAF2-012","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-29",null,null,"3,4,5,6",1]
[null,"DB InfraGO AG","1FAF2-017","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1FAF2-022","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,28,31,"2026-07-07","21:00:00","2026-07-31","05:00:00","23d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-29",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1FA57-033","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-14",null,null,1,1]
[null,"DB InfraGO AG","1F917-027","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,12,13,"2026-03-20","21:00:00","2026-03-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,1,1]
[null,"DB InfraGO AG","1FB9B-029","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Mannheim Ziehbrunnen",2026,2026,29,30,"2026-07-17","21:00:00","2026-07-20","05:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1FB9B-034","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","M-Fr Südein/Ausf",2026,2026,29,30,"2026-07-17","21:00:00","2026-07-20","05:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1D41F-001","Frankfurt - Karlsruhe","< >","Schwetzingen","Schwetzingen",2026,2026,43,47,"2026-10-20","22:00:00","2026-11-16","22:00:00","27d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1D41F-028","Frankfurt - Karlsruhe","< >","Waghäusel Saalbach","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E550-009","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E709-002","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,15,15,"2026-04-06","00:00:00","2026-04-08","23:59:00","2d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-007","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Hemsbach",2026,2026,6,6,"2026-02-02","23:00:00","2026-02-03","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-27",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-015","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,6,6,"2026-02-03","23:00:00","2026-02-04","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-038","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Weinheim (Bergstr) Hbf",2026,2026,7,7,"2026-02-09","23:00:00","2026-02-10","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"4,5",1]
[null,"DB InfraGO AG","1F4F8-007","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Ladenburg",2026,2026,7,7,"2026-02-10","23:00:00","2026-02-11","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1F841-007","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Heddesheim/Hirschberg",2026,2026,8,9,"2026-02-20","21:00:00","2026-02-27","05:00:00","6d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2",1]
[null,"DB InfraGO AG","1F841-010","Frankfurt - Karlsruhe",">","Weinheim (Bergstr) Hbf","Ladenburg",2026,2026,9,10,"2026-02-27","21:00:00","2026-03-06","05:00:00","6d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","1F485-043","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E54-059","Hamburg - Magdeburg",">","Bardowick","Stelle",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",4,4",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FB56-007","Hamburg - Magdeburg",">","Bindfelde Abzw","Stendal Hauptbahnhof",2026,2026,30,37,"2026-07-24","21:00:00","2026-09-11","05:00:00","48d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-17",null,null,"5,6",1]
[null,"DB InfraGO AG","1D99F-001","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2026,2026,37,37,"2026-09-12","00:00:00","2026-09-13","15:00:00","1d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,7,1]
[null,"DB InfraGO AG","22E54-055","Hamburg - Magdeburg",">","Deutsch Evern","Bardowick",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","12:00:00","0d, 15h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","22C9E-012","Hamburg - Magdeburg","<","Hamburg-Harburg","Meckelfeld",2026,2026,24,25,"2026-06-11","22:00:00","2026-06-17","06:00:00","5d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-06",null,null,"5,6",1]
[null,"DB InfraGO AG","1A813-001","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,35,"2026-08-03","00:00:00","2026-08-29","00:00:00","26d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-04",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-002","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,35,"2026-08-03","00:00:00","2026-08-29","00:00:00","26d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,7",1]
[null,"DB InfraGO AG","1A813-006","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,32,"2026-08-04","07:00:00","2026-08-04","15:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-013","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-015","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,34,34,"2026-08-18","10:00:00","2026-08-22","10:00:00","4d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-020","Hamburg - Magdeburg","< >","Helmstedt","Harbke",2026,2026,34,34,"2026-08-22","00:25:00","2026-08-22","05:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1A813-026","Hamburg - Magdeburg",">","Helmstedt","Helmstedt",2026,2026,34,35,"2026-08-22","06:25:00","2026-08-28","21:00:00","6d, 14h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A852-002","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,44,45,"2026-11-01","23:00:00","2026-11-02","05:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1BE35-010","Hamburg - Magdeburg","< >","Helmstedt","Magdeburg-Sudenburg",2026,2026,29,29,"2026-07-19","00:00:00","2026-07-19","04:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","20B8B-011","Hamburg - Magdeburg","< >","Helmstedt","Magdeburg-Neustadt",2026,2026,29,29,"2026-07-19","00:00:00","2026-07-19","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-05",null,null,"1,2",1]
[null,"DB InfraGO AG","1E797-001","Hamburg - Magdeburg",">","Hoheneggelsen","Groß Gleidingen",2026,2026,25,25,"2026-06-15","23:15:00","2026-06-16","05:40:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-12-08",null,null,"5,6,7",1]
[null,"DB InfraGO AG","22E57-004","Hamburg - Magdeburg","< >","Lüneburg Gbf","Klein Süstedt",2026,2026,44,44,"2026-10-31","23:00:00","2026-11-01","05:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1B978-013","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Hbf",2026,2026,9,9,"2026-02-23","03:00:00","2026-02-23","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1B978-015","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,9,9,"2026-02-26","03:00:00","2026-02-26","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,7,1]
[null,"DB InfraGO AG","1B992-015","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,13,13,"2026-03-29","03:00:00","2026-03-29","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1BD9D-010","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,15,15,"2026-04-10","03:00:00","2026-04-10","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"6,7",1]
[null,"DB InfraGO AG","1BD9D-014","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,15,15,"2026-04-12","03:00:00","2026-04-12","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,2,1]
[null,"DB InfraGO AG","1BD9D-015","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,15,15,"2026-04-12","03:00:00","2026-04-12","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,2,1]
[null,"DB InfraGO AG","20B8B-013","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,29,29,"2026-07-19","00:00:00","2026-07-19","04:00:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1BE35-003","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1B613-010","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,3,4,"2026-01-17","03:00:00","2026-01-24","04:00:00","7d, 1h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,7",1]
[null,"DB InfraGO AG","1B613-014","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg Südseite",2026,2026,3,4,"2026-01-17","03:00:00","2026-01-24","04:00:00","7d, 1h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"2,3",1]
[null,"DB InfraGO AG","1B978-009","Hamburg - Magdeburg","< >","Magdeburg Hbf","Magdeburg-Buckau",2026,2026,9,9,"2026-02-23","03:00:00","2026-02-23","04:00:00","0d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,1,1]
[null,"DB InfraGO AG","1B613-006","Hamburg - Magdeburg","<","Magdeburg Südseite","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","18:00:00","2026-01-25","14:00:00","7d, 20h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-05-31",null,null,"2,3",1]
[null,"DB InfraGO AG","1B613-013","Hamburg - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","03:00:00","2026-01-24","04:00:00","7d, 1h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO AG","1B978-012","Hamburg - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2026,2026,9,9,"2026-02-23","03:00:00","2026-02-23","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"3,4",1]
[null,"DB InfraGO AG","1BD9D-012","Hamburg - Magdeburg","< >","Magdeburg Südseite","Magdeburg Hbf",2026,2026,15,15,"2026-04-10","03:00:00","2026-04-10","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","1B613-004","Hamburg - Magdeburg","<","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","18:00:00","2026-01-25","14:00:00","7d, 20h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-15",null,null,6,1]
[null,"DB InfraGO AG","1BD9D-004","Hamburg - Magdeburg","<","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,15,15,"2026-04-10","21:00:00","2026-04-11","17:00:00","0d, 20h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1B613-011","Hamburg - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,3,4,"2026-01-17","03:00:00","2026-01-24","04:00:00","7d, 1h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1B992-017","Hamburg - Magdeburg","< >","Magdeburg-Buckau","Magdeburg Hbf",2026,2026,13,13,"2026-03-29","03:00:00","2026-03-29","04:00:00","0d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1B3BA-001","Hamburg - Magdeburg","< >","Magdeburg-Sudenburg","Magdeburg-Sudenburg",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"6,7",1]
[null,"DB InfraGO AG","22E54-009","Hamburg - Magdeburg","< >","Maschen Pbf","Stelle",2026,2026,18,23,"2026-05-01","21:00:00","2026-06-05","18:00:00","34d, 21h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-24",null,null,5,1]
[null,"DB InfraGO AG","22E54-022","Hamburg - Magdeburg","<","Maschen Pbf","Stelle",2026,2026,23,23,"2026-06-05","20:00:00","2026-06-06","02:00:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-24",null,null,3,1]
[null,"DB InfraGO AG","1E2B5-002","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","21:00:00","2026-10-31","05:00:00","14d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","22C9E-007","Hamburg - Magdeburg",">","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,22,22,"2026-05-26","21:00:00","2026-05-29","05:00:00","2d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"5,6,7",1]
[null,"DB InfraGO AG","22C9E-011","Hamburg - Magdeburg",">","Meckelfeld","Hamburg-Harburg",2026,2026,23,24,"2026-06-05","23:00:00","2026-06-08","05:00:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","22C9E-014","Hamburg - Magdeburg","< >","Meckelfeld","Hamburg-Harburg",2026,2026,24,25,"2026-06-12","00:00:00","2026-06-17","05:00:00","5d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","22C9E-022","Hamburg - Magdeburg",">","Meckelfeld","Meckelfeld Nord",2026,2026,26,26,"2026-06-23","05:00:00","2026-06-25","05:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","22C9E-030","Hamburg - Magdeburg",">","Meckelfeld","Hamburg-Harburg Betriebsbahnhof Süd",2026,2026,28,28,"2026-07-06","21:00:00","2026-07-08","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-18",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","22C9E-004","Hamburg - Magdeburg","< >","Meckelfeld Nord","Meckelfeld",2026,2026,19,20,"2026-05-09","21:00:00","2026-05-14","05:00:00","4d, 8h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","22C9E-006","Hamburg - Magdeburg","<","Meckelfeld Nord","Meckelfeld",2026,2026,21,21,"2026-05-18","06:00:00","2026-05-22","14:00:00","4d, 8h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-05-29",null,null,"2,3,4",1]
[null,"DB InfraGO AG","22C9E-026","Hamburg - Magdeburg","< >","Meckelfeld Nord","Meckelfeld",2026,2026,26,27,"2026-06-27","21:00:00","2026-06-30","05:00:00","2d, 8h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2023-12-18",null,null,"1,2,3,4,5,7",1]
[null,"DB InfraGO AG","1FFB7-001","Hamburg - Magdeburg","< >","Oebisfelde","Lehrte",2026,2026,36,36,"2026-09-06","01:15:00","2026-09-06","06:10:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","21012-004","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,37,37,"2026-09-07","08:00:00","2026-09-08","16:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-22",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21012-006","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,38,38,"2026-09-14","00:00:00","2026-09-14","01:00:00","0d, 1h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","20EDE-001","Hamburg - Magdeburg","< >","Schnega","Veerßen",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20B8B-006","Hamburg - Magdeburg","< >","Schönebeck (Elbe)","Magdeburg Hbf",2026,2026,29,29,"2026-07-18","10:00:00","2026-07-19","04:00:00","0d, 18h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-04",null,null,"6,7",1]
[null,"DB InfraGO AG","22E54-024","Hamburg - Magdeburg","< >","Stelle","Maschen Rbf (Msof)",2026,2026,28,28,"2026-07-10","00:00:00","2026-07-10","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","22E54-026","Hamburg - Magdeburg",">","Stelle","Maschen Rbf (Msof)",2026,2026,28,29,"2026-07-10","18:00:00","2026-07-14","18:00:00","4d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-05-21",null,null,"3,4",1]
[null,"DB InfraGO AG","22E54-036","Hamburg - Magdeburg","< >","Stelle","Maschen Pbf",2026,2026,19,20,"2026-05-09","20:00:00","2026-05-11","06:00:00","1d, 10h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"3,4",1]
[null,"DB InfraGO AG","22E54-061","Hamburg - Magdeburg","<","Stelle","Bardowick",2026,2026,28,28,"2026-07-11","12:00:00","2026-07-12","12:00:00","1d, 0h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",4,4",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","206C8-002","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,40,50,"2026-10-02","05:00:00","2026-12-12","23:59:00","71d, 19h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","20B5C-001","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,4,4,"2026-01-19","08:00:00","2026-01-22","08:00:00","3d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB56-011","Hamburg - Magdeburg","<","Stendal Hauptbahnhof","Bindfelde Abzw",2026,2026,38,39,"2026-09-18","21:00:00","2026-09-25","05:00:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20185-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangermünde",2026,2026,46,46,"2026-11-15","01:00:00","2026-11-15","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"3,4",1]
[null,"DB InfraGO AG","20A85-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangermünde",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-001","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,3,4,"2026-01-17","06:30:00","2026-01-19","20:30:00","2d, 14h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-006","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-014","Hamburg - Magdeburg","<","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,37,37,"2026-09-12","12:00:00","2026-09-12","14:00:00","0d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1040-(MK27)-12","Hamburg - Magdeburg","< >","Stendal Hbf","Glindenberg",2027,2027,44,45,"05.11.2027","21:00:00","08.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-05-21",null,null,"1,2,3",1]
[null,"DB InfraGO AG","20A85-011","Hamburg - Magdeburg","< >","Tangerhütte","Stendal Hauptbahnhof",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO AG","22E54-030","Hamburg - Magdeburg","< >","Uelzen","Uelzen Gbf",2026,2026,18,28,"2026-05-01","21:00:00","2026-07-10","21:00:00","70d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-008","Hamburg - Magdeburg","< >","Uelzen","Ebstorf (Kr Uelzen)",2026,2026,48,49,"2026-11-27","05:00:00","2026-11-30","05:00:00","3d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E54-031","Hamburg - Magdeburg","< >","Uelzen Gbf","Uelzen Gbf",2026,2026,18,28,"2026-05-01","21:00:00","2026-07-10","21:00:00","70d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","22E57-003","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,42,43,"2026-10-18","22:00:00","2026-10-19","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","22E54-048","Hamburg - Magdeburg","<","Uelzen Gbf","Celle",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","12:00:00","0d, 15h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"19,19,19",null,null,null,"N",null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1031-(MK27)-94","Hamburg - Magdeburg","< >","Uelzen Gbf","Stendal Gbf",2027,2027,34,41,"27.08.2027","21:00:00","15.10.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-04-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-004","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2026,2026,34,34,"2026-08-17","23:10:00","2026-08-18","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-006","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2026,2026,34,34,"2026-08-19","23:10:00","2026-08-20","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","21340-001","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,35,39,"2026-08-29","06:30:00","2026-09-22","20:30:00","24d, 14h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-004","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,35,39,"2026-08-29","06:30:00","2026-09-22","20:30:00","24d, 14h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-010","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,40,40,"2026-10-01","20:30:00","2026-10-03","20:30:00","2d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F177-007","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,16,17,"2026-04-18","04:30:00","2026-04-20","03:35:00","1d, 23h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-017","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,37,37,"2026-09-10","08:25:00","2026-09-10","11:25:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-012","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-028","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2026,2026,35,35,"2026-08-28","15:00:00","2026-08-28","21:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A852-003","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,45,45,"2026-11-02","02:00:00","2026-11-02","05:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-003","Hannover - Magdeburg","< >","Groß Gleidingen","Groß Gleidingen",2026,2026,32,37,"2026-08-03","07:00:00","2026-09-07","19:00:00","35d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"1,7",1]
[null,"DB InfraGO AG","1A784-007","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,34,34,"2026-08-18","23:05:00","2026-08-21","05:00:00","2d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-012","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,35,35,"2026-08-25","23:05:00","2026-08-28","05:00:00","2d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A7F1-002","Hannover - Magdeburg","<","Groß Gleidingen","Vechelde",2026,2026,41,41,"2026-10-09","22:10:00","2026-10-10","00:55:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1E74B-003","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2026,2026,15,16,"2026-04-10","22:15:00","2026-04-13","05:55:00","2d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1F177-006","Hannover - Magdeburg","< >","Groß Gleidingen","Groß Gleidingen",2026,2026,16,18,"2026-04-15","20:00:00","2026-04-27","20:00:00","12d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-016","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2026,2026,37,37,"2026-09-10","06:25:00","2026-09-10","09:25:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1B42F-005","Hannover - Magdeburg","< >","Hannover-Linden","Hannover-Waldheim",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,7",1]
[null,"DB InfraGO AG","1AA87-006","Hannover - Magdeburg","< >","Hannover-Waldheim","Misburg",2026,2026,19,19,"2026-05-07","20:00:00","2026-05-08","05:00:00","0d, 9h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1B3E9-004","Hannover - Magdeburg","< >","Hannover-Wülfel","Waldhausen",2026,2026,2,2,"2026-01-10","08:00:00","2026-01-10","16:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,7",1]
[null,"DB InfraGO AG","20B78-004","Hannover - Magdeburg",">","Lehrte","Sehnde",2026,2026,27,30,"2026-07-02","01:15:00","2026-07-24","21:00:00","22d, 19h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20CFF-002","Hannover - Magdeburg",">","Lehrte","Algermissen",2026,2026,44,44,"2026-10-26","22:00:00","2026-10-29","05:50:00","2d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"22,22,22",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1AA87-009","Hannover - Magdeburg","< >","Misburg","Hannover-Waldheim",2026,2026,20,20,"2026-05-11","06:00:00","2026-05-15","17:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,6,7",1]
[null,"DB InfraGO AG","1A784-011","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,35,35,"2026-08-25","05:00:00","2026-08-28","21:00:00","3d, 16h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-02-01",null,null,"1,7",1]
[null,"DB InfraGO AG","1A7F1-006","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,42,42,"2026-10-17","00:55:00","2026-10-17","03:20:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-20",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1C0F0-001","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2026,2026,34,34,"2026-08-17","23:10:00","2026-08-18","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"4,5",1]
[null,"DB InfraGO AG","203FF-021","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,12,12,"2026-03-16","21:00:00","2026-03-17","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"1,7",1]
[null,"DB InfraGO AG","20409-024","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,18,18,"2026-04-27","21:00:00","2026-04-28","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"1,7",1]
[null,"DB InfraGO AG","20409-026","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,22,22,"2026-05-25","21:00:00","2026-05-26","05:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1A784-006","Hannover - Magdeburg","<","Vechelde","Vechelde",2026,2026,34,34,"2026-08-18","05:00:00","2026-08-21","23:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-016","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","04:00:00","2d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-006","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,34,35,"2026-08-21","23:00:00","2026-08-24","05:00:00","2d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CBF8-003","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-11","23:59:00","2d, 1h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"2,3",1]
[null,"DB InfraGO AG","1CBF8-005","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,42,"2026-10-09","23:59:00","2026-10-12","03:00:00","2d, 3h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,5,1]
[null,"DB InfraGO AG","22527-005","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,34,37,"2026-08-22","21:00:00","2026-09-07","05:00:00","15d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","22527-015","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-02-07",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","22527-020","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,35,35,"2026-08-24","23:00:00","2026-08-25","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-029","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,36,37,"2026-09-01","21:00:00","2026-09-07","05:00:00","5d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-036","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-049","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-05","23:00:00","2026-09-06","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","1D6BF-001","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D6BF-003","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2026,50,21,"2025-12-14","00:00:00","2026-05-22","04:30:00","159d, 3h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1D6BF-009","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,1,1]
[null,"DB InfraGO AG","1E029-008","Karlsruhe - München","<","Augsburg Hbf","Mering",2026,2026,35,43,"2026-08-26","21:00:00","2026-10-25","05:00:00","59d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E029-012","Karlsruhe - München","<","Augsburg Hbf","Mering",2026,2026,43,43,"2026-10-21","21:00:00","2026-10-25","05:00:00","3d, 9h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","1E176-005","Karlsruhe - München","< >","Augsburg Hbf","Augsburg-Oberhausen",2026,2026,21,21,"2026-05-18","22:00:00","2026-05-19","04:30:00","0d, 6h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,1,1]
[null,"DB InfraGO AG","1E180-001","Karlsruhe - München","<","Augsburg Rbf Mitte","Augsburg-Oberhausen",2026,2026,30,30,"2026-07-22","22:00:00","2026-07-23","04:00:00","0d, 6h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D3DB-005","Karlsruhe - München","< >","Augsburg-Hochzoll Abzweig","Mering Üst",2026,2026,9,27,"2026-03-01","21:00:00","2026-06-30","05:00:00","120d, 7h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D705-001","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg Hirblinger Straße",2026,2026,10,21,"2026-03-02","00:30:00","2026-05-19","04:30:00","78d, 3h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1D705-004","Karlsruhe - München",">","Augsburg-Oberhausen","Westheim (Schwab)",2026,2026,21,21,"2026-05-20","00:30:00","2026-05-21","04:30:00","1d, 4h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1DABD-002","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,37,"2026-08-29","22:00:00","2026-09-07","03:00:00","8d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-006","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,36,"2026-08-30","13:00:00","2026-09-03","20:00:00","4d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-008","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-05","09:00:00","2026-09-06","22:00:00","1d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"6,7",1]
[null,"DB InfraGO AG","1DABD-016","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,37,37,"2026-09-09","14:00:00","2026-09-11","04:00:00","1d, 14h","Continuous",null,null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,7",1]
[null,"DB InfraGO AG","1E17F-004","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,21,21,"2026-05-20","22:00:00","2026-05-21","04:30:00","0d, 6h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"4,5",1]
[null,"DB InfraGO AG","1E181-005","Karlsruhe - München",">","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,31,31,"2026-07-27","23:00:00","2026-07-28","03:30:00","0d, 4h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","21C52-013","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,3,4,"2026-01-17","21:00:00","2026-01-23","04:50:00","5d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-11-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","21C52-018","Karlsruhe - München","< >","Beimerstetten","Ulm-Örlingen",2026,2026,4,6,"2026-01-25","22:00:00","2026-02-06","05:00:00","11d, 7h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21CBD-012","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,14,14,"2026-03-30","21:00:00","2026-04-02","04:50:00","2d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21CC5-003","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,15,16,"2026-04-10","21:00:00","2026-04-13","05:00:00","2d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21CC5-008","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,15,18,"2026-04-11","12:00:00","2026-04-27","12:00:00","16d, 0h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","21CC5-014","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,16,18,"2026-04-13","21:00:00","2026-05-01","04:50:00","17d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-28",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21CCE-004","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-28",null,null,"6,7",1]
[null,"DB InfraGO AG","21CCE-012","Karlsruhe - München",">","Beimerstetten","Ulm-Örlingen",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","04:50:00","3d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-28",null,null,"1,2,3",1]
[null,"DB InfraGO AG","22527-024","Karlsruhe - München","<","Beimerstetten","Westerstetten",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1C651-002","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C662-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-001","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","01:00:00","2026-08-17","07:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1E12D-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","07:00:00","2026-08-21","21:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E72E-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1E622-003","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-011","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-013","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","2124F-008","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-30","05:00:00","6d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","2124F-011","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,44,44,"2026-10-30","00:10:00","2026-10-30","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","20BF3-008","Karlsruhe - München",">","Eislingen (Fils)","Süßen",2026,2026,34,34,"2026-08-22","03:00:00","2026-08-23","03:00:00","1d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20B87-009","Karlsruhe - München","< >","Eislingen (Fils)","Eislingen (Fils)",2026,2026,24,24,"2026-06-11","21:00:00","2026-06-12","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-01-03",null,null,6,1]
[null,"DB InfraGO AG","1E6B8-005","Karlsruhe - München","< >","Enzberg","Enzberg",2026,2026,9,9,"2026-02-28","07:00:00","2026-02-28","17:00:00","0d, 10h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-01-03",null,null,5,1]
[null,"DB InfraGO AG","222FB-031","Karlsruhe - München",">","Geislingen (Steige)","Westerstetten",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2023-01-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1D705-005","Karlsruhe - München","<","Gersthofen","Augsburg-Oberhausen",2026,2026,21,22,"2026-05-20","04:30:00","2026-05-28","04:30:00","8d, 0h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D705-008","Karlsruhe - München","<","Gersthofen","Augsburg-Oberhausen",2026,2026,22,22,"2026-05-27","00:30:00","2026-05-28","04:30:00","1d, 4h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-01-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1D885-010","Karlsruhe - München","<","Gessertshausen","Gessertshausen",2026,2026,23,23,"2026-06-05","05:00:00","2026-06-06","07:00:00","1d, 2h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-02-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1D885-013","Karlsruhe - München","<","Gessertshausen","Gessertshausen",2026,2026,23,24,"2026-06-06","07:00:00","2026-06-08","07:00:00","2d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-02-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1D9B7-003","Karlsruhe - München","< >","Gessertshausen","Westheim (Schwab)",2026,2026,43,46,"2026-10-23","22:30:00","2026-11-13","05:10:00","20d, 7h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-04",null,null,"2,3",1]
[null,"DB InfraGO AG","1D885-016","Karlsruhe - München","< >","Gessertshausen","Gessertshausen",2026,2026,19,23,"2026-05-09","22:00:00","2026-06-07","05:00:00","28d, 7h","Continuous","Track & Rail",null,null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-27",null,null,7,1]
[null,"DB InfraGO AG","1EEEE-018","Karlsruhe - München","<","Glems","Vaihingen (Enz)",2026,2026,27,29,"2026-07-02","22:30:00","2026-07-18","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1F188-015","Karlsruhe - München","< >","Glems","Vaihingen (Enz)",2026,2026,37,39,"2026-09-11","22:30:00","2026-09-25","05:00:00","13d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-08-16",null,null,5,1]
[null,"DB InfraGO AG","1E501-025","Karlsruhe - München","<","Grötzingen","Karlsruhe Hbf",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-02",null,null,7,1]
[null,"DB InfraGO AG","1DAD8-007","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,26,28,"2026-06-26","22:00:00","2026-07-11","05:00:00","14d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-26",null,null,7,1]
[null,"DB InfraGO AG","1DB29-005","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,30,31,"2026-07-20","22:00:00","2026-08-01","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1DB29-010","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,1,1]
[null,"DB InfraGO AG","1DB29-028","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,42,44,"2026-10-16","22:00:00","2026-10-31","05:00:00","14d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DB9A-008","Karlsruhe - München","< >","Illingen (Württ)","Mühlacker",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1E81C-012","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2026,2026,15,17,"2026-04-10","22:30:00","2026-04-22","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-19",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1EEEE-007","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,19,21,"2026-05-04","22:30:00","2026-05-23","05:00:00","18d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-10-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F6AE-012","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-29",null,null,6,1]
[null,"DB InfraGO AG","1F6AE-013","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-29",null,null,6,1]
[null,"DB InfraGO AG","1F6AE-005","Karlsruhe - München","< >","Kraichtal","Vaihingen (Enz)",2026,2026,40,41,"2026-10-03","23:00:00","2026-10-05","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1DF78-014","Karlsruhe - München","<","Lauffen (Neckar)","Bietigheim-Bissingen",2026,2026,48,49,"2026-11-29","21:00:00","2026-11-30","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1E9AE-005","Karlsruhe - München","<","Maisach","Olching",2026,2026,27,27,"2026-06-29","23:20:00","2026-07-03","05:20:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-24",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1E029-010","Karlsruhe - München","< >","Mering","Augsburg Hbf",2026,2026,35,43,"2026-08-26","21:00:00","2026-10-25","05:00:00","59d, 9h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1D3DB-020","Karlsruhe - München","<","Mering Üst","Olching",2026,2026,28,30,"2026-07-12","21:00:00","2026-07-22","05:00:00","9d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-017","Karlsruhe - München",">","Mering Üst","Augsburg-Hochzoll Abzweig",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1E81C-020","Karlsruhe - München","< >","Mettertal","Vaihingen (Enz)",2026,2026,9,11,"2026-02-23","22:30:00","2026-03-14","05:00:00","18d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-04-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1F188-014","Karlsruhe - München","< >","Mettertal","Vaihingen (Enz)",2026,2026,37,37,"2026-09-07","22:30:00","2026-09-11","05:00:00","3d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-011","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-003","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-26","20:00:00","2026-08-14","06:00:00","48d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-027","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,29,29,"2026-07-13","22:00:00","2026-07-18","05:00:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-007","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-08","05:00:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-015","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-020","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:00:00","2026-10-02","06:00:00","11d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-025","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,42,50,"2026-10-16","20:00:00","2026-12-11","06:00:00","55d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-014","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-07","Karlsruhe - München","< >","Mühlacker","Bietigheim-Biss",2027,2027,4,5,"29.01.2027","21:00:00","05.02.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-10","Karlsruhe - München","< >","Mühlacker","Bietigheim-Biss",2027,2027,2,3,"15.01.2027","21:00:00","22.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-17",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-012","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-004","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1E6B8-003","Karlsruhe - München","<","Mühlacker Em Süd","Pforzheim Hbf",2026,2026,4,12,"2026-01-25","05:00:00","2026-03-20","21:00:00","54d, 16h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-08-12",null,null,"3,4",1]
[null,"DB InfraGO AG","1DB9A-005","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1E860-002","Karlsruhe - München","<","München-Lochhausen","München-Pasing Weiche 352",2026,2026,15,15,"2026-04-07","23:35:00","2026-04-10","05:20:00","2d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1E9AE-001","Karlsruhe - München",">","München-Lochhausen","Olching",2026,2026,24,24,"2026-06-08","23:00:00","2026-06-12","05:10:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1E851-004","Karlsruhe - München",">","München-Pasing","Olching",2026,2026,13,13,"2026-03-24","00:00:00","2026-03-27","05:00:00","3d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1080-(MK27)-02","Karlsruhe - München",">","Neuoffingen","Neu-Ulm",2027,2027,5,11,"05.02.2027","21:00:00","19.03.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1F0BA-002","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,35,36,"2026-08-29","23:00:00","2026-09-04","05:00:00","5d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1F0BA-005","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,36,43,"2026-09-04","23:00:00","2026-10-19","04:00:00","44d, 5h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1D3DB-017","Karlsruhe - München",">","Olching","Mering Üst",2026,2026,28,29,"2026-07-12","21:00:00","2026-07-14","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1D3DB-024","Karlsruhe - München",">","Olching","Mering Üst",2026,2026,30,30,"2026-07-21","21:00:00","2026-07-22","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-02",null,null,"6,7",1]
[null,"DB InfraGO AG","1E9AE-004","Karlsruhe - München",">","Olching","Maisach",2026,2026,26,26,"2026-06-22","23:10:00","2026-06-26","05:10:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","1E9CB-003","Karlsruhe - München",">","Olching","Maisach",2026,2026,29,29,"2026-07-13","23:15:00","2026-07-17","04:20:00","3d, 5h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","1E6B8-006","Karlsruhe - München",">","Pforzheim Hbf","Mühlacker Em Süd",2026,2026,9,9,"2026-02-28","07:00:00","2026-02-28","17:00:00","0d, 10h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1094-(MK27)-08","Karlsruhe - München",">","Plochingen","Ulm Pbf",2027,2027,8,9,"26.02.2027","21:00:00","05.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","22494-007","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,40,43,"2026-09-28","01:00:00","2026-10-23","05:00:00","25d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-010","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-026","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","09:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-04",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-005","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,23,25,"2026-06-05","22:00:00","2026-06-15","04:00:00","9d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-010","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,23,24,"2026-06-07","22:00:00","2026-06-09","04:00:00","1d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-013","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,29,30,"2026-07-17","22:00:00","2026-07-22","04:00:00","4d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-017","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,29,30,"2026-07-19","22:00:00","2026-07-21","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-003","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-07","20:00:00","13d, 22h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-006","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,31,31,"2026-07-30","21:00:00","2026-07-31","05:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-010","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,32,32,"2026-08-05","04:00:00","2026-08-06","20:00:00","1d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-016","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,45,46,"2026-11-08","23:59:00","2026-11-09","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,1,1]
[null,"DB InfraGO AG","22ED4-021","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,7",1]
[null,"DB InfraGO AG","3042-(MK27)-01","Karlsruhe - München",">","Stuttgart-Bad Cannst","Plochingen",2027,2027,4,5,"29.01.2027","21:00:00","01.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WEN",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","3664-(MK27)-04","Karlsruhe - München","< >","Stuttgart-Bad Cannst","Plochingen",2027,2027,19,20,"14.05.2027","21:00:00","21.05.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","3040-(MK27)-02","Karlsruhe - München",">","Stuttgart-Utürkhm Pbf","Kornwestheim Pbf",2027,2027,24,26,"19.06.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-08-14",null,null,"4,5",1]
[null,"DB InfraGO AG","3756-(MK27)-03_WDN","Karlsruhe - München","< >","Stuttgart-Zazenhausen","Ludwigsburg",2027,2027,35,38,"30.08.2027","21:00:00","24.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEuN",null,null,null,"2024-07-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1FFF4-005","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-009","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,34,34,"2026-08-22","03:00:00","2026-08-23","03:00:00","1d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-010","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,37,37,"2026-09-07","00:30:00","2026-09-07","04:30:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","205A7-012","Karlsruhe - München","< >","Ulm Hbf Bft Rbf","Ulm Hbf Em Nord",2026,2026,7,15,"2026-02-13","21:00:00","2026-04-10","04:00:00","55d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,7",1]
[null,"DB InfraGO AG","21CC5-002","Karlsruhe - München","<","Ulm-Örlingen","Westerstetten",2026,2026,15,16,"2026-04-10","21:00:00","2026-04-13","05:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-09",null,null,"1,7",1]
[null,"DB InfraGO AG","21CC5-005","Karlsruhe - München","< >","Ulm-Örlingen","Beimerstetten",2026,2026,15,16,"2026-04-10","21:00:00","2026-04-13","05:00:00","2d, 8h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,7",1]
[null,"DB InfraGO AG","1DAD8-002","Karlsruhe - München","< >","Vaihingen (Enz)","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-009","Karlsruhe - München","< >","Vaihingen (Enz)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1EEEE-004","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,19,21,"2026-05-04","22:30:00","2026-05-23","05:00:00","18d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1EEEE-020","Karlsruhe - München",">","Vaihingen (Enz)","Illingen (Württ)",2026,2026,27,29,"2026-07-02","22:30:00","2026-07-18","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1E81C-004","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,10,11,"2026-03-07","23:00:00","2026-03-09","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1E81C-011","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,15,17,"2026-04-10","22:30:00","2026-04-22","05:00:00","11d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1EEEE-001","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,19,21,"2026-05-04","22:30:00","2026-05-23","05:00:00","18d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1EEEE-002","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,19,21,"2026-05-04","22:30:00","2026-05-23","05:00:00","18d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1EEEE-012","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,24,25,"2026-06-13","23:00:00","2026-06-15","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1E81C-021","Karlsruhe - München","< >","Vaihingen (Enz)","Mettertal",2026,2026,12,14,"2026-03-16","22:30:00","2026-04-04","05:00:00","18d, 5h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-003","Karlsruhe - München","< >","Vaihingen (Enz)","Langes Feld",2026,2026,31,32,"2026-08-01","23:00:00","2026-08-03","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-006","Karlsruhe - München",">","Vaihingen (Enz)","Glems",2026,2026,32,33,"2026-08-05","22:30:00","2026-08-14","05:00:00","8d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-002","Karlsruhe - München","< >","Vaihingen (Enz)","Mettertal",2026,2026,39,40,"2026-09-25","22:30:00","2026-10-02","05:00:00","6d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-017","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,44,44,"2026-10-26","22:30:00","2026-10-31","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-025","Karlsruhe - München","< >","Vaihingen (Enz)","Langes Feld",2026,2026,47,48,"2026-11-21","23:00:00","2026-11-23","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-026","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,47,48,"2026-11-21","23:00:00","2026-11-23","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"1,2",1]
[null,"DB InfraGO AG","22ED3-020","Karlsruhe - München","<","Wendlingen (Neckar)","Plochingen",2026,2026,30,30,"2026-07-22","22:00:00","2026-07-24","04:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","21CC5-018","Karlsruhe - München",">","Westerstetten","Ulm-Örlingen",2026,2026,16,18,"2026-04-13","21:00:00","2026-05-01","04:50:00","17d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-008","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,34,36,"2026-08-23","21:00:00","2026-09-01","05:00:00","8d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-012","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-022","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-042","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,36,"2026-09-02","23:00:00","2026-09-03","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-052","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,37,"2026-09-06","23:00:00","2026-09-07","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-028","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,35,36,"2026-08-25","05:00:00","2026-09-01","21:00:00","7d, 16h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1D885-014","Karlsruhe - München","< >","Westheim (Schwab)","Dinkelscherben",2026,2026,45,46,"2026-11-07","22:00:00","2026-11-09","05:00:00","1d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1DABD-010","Karlsruhe - München","<","Westheim (Schwab)","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1E2B3-009","Karlsruhe - München","< >","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-11","22:00:00","2d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1F203-019","Karlsruhe - Strasbourg","< >","Achern","Achern",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1EC96-003","Karlsruhe - Strasbourg","< >","Appenweier","Appenweier",2026,2026,29,30,"2026-07-13","23:45:00","2026-07-22","04:45:00","8d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1CDDE-001","Karlsruhe - Strasbourg","< >","Appenweier Nord","Bad Griesbach",2026,2026,31,37,"2026-07-31","23:00:00","2026-09-11","23:00:00","42d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1E768-021","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Nord",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1E768-024","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Nord",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1E199-002","Karlsruhe - Strasbourg","<","Baden-Baden","Rastatt-Süd",2026,2026,14,14,"2026-03-30","23:00:00","2026-04-03","05:00:00","3d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1E199-014","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","23:00:00","2026-04-10","05:00:00","3d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1E199-018","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-06","23:00:00","2026-04-13","07:00:00","6d, 8h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1E199-020","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,16,"2026-04-10","22:00:00","2026-04-13","05:00:00","2d, 7h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1E199-027","Karlsruhe - Strasbourg","< >","Baden-Baden","Baden-Baden",2026,2026,15,15,"2026-04-06","05:00:00","2026-04-07","07:00:00","1d, 2h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1E034-008","Karlsruhe - Strasbourg","< >","Bühl (Baden) F","Ottersweier",2026,2026,18,19,"2026-04-30","21:00:00","2026-05-04","05:00:00","3d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-009","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,3,4,"2026-01-16","22:00:00","2026-01-19","05:00:00","2d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-011","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,4,4,"2026-01-19","22:00:00","2026-01-23","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-018","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,6,6,"2026-02-03","22:00:00","2026-02-04","05:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-023","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,8,8,"2026-02-16","22:00:00","2026-02-20","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-028","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,9,9,"2026-02-23","22:00:00","2026-02-25","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-031","Karlsruhe - Strasbourg","<","Kehl","Kork",2026,2026,9,9,"2026-02-25","22:00:00","2026-02-27","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-005","Karlsruhe - Strasbourg","<","Kehl","Kork",2026,2026,10,13,"2026-03-06","22:00:00","2026-03-27","05:00:00","20d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-008","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,16,18,"2026-04-14","22:00:00","2026-05-01","05:00:00","16d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-013","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,19,19,"2026-05-04","22:00:00","2026-05-08","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-014","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,20,20,"2026-05-11","22:00:00","2026-05-15","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-018","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,23,26,"2026-06-06","22:00:00","2026-06-26","05:00:00","19d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-027","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,29,29,"2026-07-13","22:00:00","2026-07-19","05:00:00","5d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-031","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,31,31,"2026-07-27","22:00:00","2026-07-31","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-033","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,36,39,"2026-09-04","22:00:00","2026-09-25","05:00:00","20d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,43,45,"2026-10-19","22:00:00","2026-11-06","05:00:00","17d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-012","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-04","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-018","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,49,"2026-12-06","00:00:00","2026-12-06","08:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-028","Karlsruhe - Strasbourg","< >","Kehl","Kehl Grenze",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-07-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-010","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,3,4,"2026-01-16","22:00:00","2026-01-19","05:00:00","2d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-027","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,8,10,"2026-02-21","08:00:00","2026-03-08","18:00:00","15d, 10h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-003","Karlsruhe - Strasbourg","< >","Kork","Kehl",2026,2026,10,11,"2026-03-04","05:00:00","2026-03-09","08:00:00","5d, 3h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-019","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,23,26,"2026-06-06","22:00:00","2026-06-26","05:00:00","19d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-008","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,48,49,"2026-11-23","08:00:00","2026-12-05","21:00:00","12d, 13h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-017","Karlsruhe - Strasbourg","< >","Kork","Kehl",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-036","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1EC96-002","Karlsruhe - Strasbourg","<","Offenburg","Appenweier",2026,2026,29,30,"2026-07-13","23:45:00","2026-07-22","04:45:00","8d, 5h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1E034-005","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,16,17,"2026-04-18","00:30:00","2026-04-26","04:30:00","8d, 4h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1E034-012","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,19,20,"2026-05-08","21:00:00","2026-05-11","05:00:00","2d, 8h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1E034-016","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,20,21,"2026-05-15","21:00:00","2026-05-18","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1E034-018","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,20,20,"2026-05-15","21:00:00","2026-05-16","01:00:00","0d, 4h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1E15C-002","Karlsruhe - Strasbourg","< >","Ottersweier","Appenweier Nord",2026,2026,27,29,"2026-07-03","21:00:00","2026-07-13","05:00:00","9d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"5,6",1]
[null,"DB InfraGO AG","1E199-008","Karlsruhe - Strasbourg","<","Ottersweier","Rastatt-Süd",2026,2026,14,15,"2026-04-03","22:00:00","2026-04-06","05:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-033","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-034","Karlsruhe - Strasbourg","< >","Ottersweier","Appenweier Nord",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1E15C-009","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,19,19,"2026-05-05","05:00:00","2026-05-06","05:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1E15C-014","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,21,21,"2026-05-19","05:00:00","2026-05-20","05:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1E15C-017","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,22,22,"2026-05-27","05:00:00","2026-05-28","05:00:00","1d, 0h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1CE98-001","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2026,2026,17,29,"2026-04-24","06:00:00","2026-07-17","22:00:00","84d, 16h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-006","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-009","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-013","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-016","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-10","01:00:00","2026-10-12","04:00:00","2d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1E768-023","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Offenburg Ülp südl Esig",2026,2026,14,16,"2026-04-03","06:00:00","2026-04-16","21:00:00","13d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",7,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F26D-014","Magdeburg - Falkenberg",">","Coswig (Anh) Gbf","Meinsdorf",2026,2026,18,18,"2026-04-30","20:00:00","2026-05-01","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1F26D-020","Magdeburg - Falkenberg",">","Coswig (Anh) Gbf","Roßlau (Elbe)",2026,2026,19,19,"2026-05-04","20:00:00","2026-05-08","04:00:00","3d, 8h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","21916-014","Magdeburg - Falkenberg","<","Dessau Hbf","Rodleben",2026,2026,25,25,"2026-06-17","00:00:00","2026-06-17","04:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1F270-001","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,22,22,"2026-05-26","08:00:00","2026-05-29","21:00:00","3d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","2225D-005","Magdeburg - Falkenberg","< >","Falkenberg (Elster) unt Bf Stw W 26","Falkenberg (Elster) unt Bf Pbf/Stw B 20",2026,2026,16,16,"2026-04-16","21:00:00","2026-04-18","03:00:00","1d, 6h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","218FC-001","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2026,2026,39,39,"2026-09-26","20:00:00","2026-09-27","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","21D6E-001","Magdeburg - Falkenberg","< >","Herzberg (Elster)","Falkenberg (Elster) unt Bf Stw W 26",2026,2026,16,17,"2026-04-17","07:00:00","2026-04-20","15:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,2",1]
[null,"DB InfraGO AG","22420-009","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf Ostseite","Lu Wittenberg-Piesteritz Werkbf Ostseite",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1F22B-010","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Coswig (Anh) Gbf",2026,2026,31,31,"2026-07-28","22:00:00","2026-07-29","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-03",null,null,"2,3",1]
[null,"DB InfraGO AG","22420-007","Magdeburg - Falkenberg","< >","Lu Wittenberg-Piesteritz Werkbf West","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,20,20,"2026-05-15","21:30:00","2026-05-16","06:30:00","0d, 9h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1F26D-006","Magdeburg - Falkenberg","< >","Lutherstadt Wittenberg Hbf","Lutherstadt Wittenberg Hbf",2026,2026,17,17,"2026-04-25","20:00:00","2026-04-26","04:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1F26D-030","Magdeburg - Falkenberg","<","Meinsdorf","Lu Wittenberg-Piesteritz Werkbf West",2026,2026,19,19,"2026-05-07","20:00:00","2026-05-08","04:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","218A8-006","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe) Gbf",2026,2026,28,28,"2026-07-11","00:00:00","2026-07-11","05:00:00","0d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","218A8-012","Magdeburg - Falkenberg","<","Rodleben","Rodleben",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","01:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"3,4",1]
[null,"DB InfraGO AG","1F26D-018","Magdeburg - Falkenberg","<","Roßlau (Elbe)","Lutherstadt Wittenberg Hbf",2026,2026,17,19,"2026-04-25","20:00:00","2026-05-04","04:00:00","8d, 8h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","21CBB-002","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","218A8-011","Magdeburg - Falkenberg","<","Roßlau (Elbe) Gbf","Rodleben",2026,2026,28,28,"2026-07-10","21:00:00","2026-07-11","01:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1157-(MK27)-03","München - Regensburg",">","Landshut/B Hbf","München-Feldmoching",2027,2027,40,41,"08.10.2027","21:00:00","11.10.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WEN",null,null,null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1E076-011","München - Salzburg","< >","Bad Endorf (Oberbay)","Landl (Oberbay) Abzw",2026,2026,2,2,"2026-01-08","02:30:00","2026-01-09","04:00:00","1d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"4,5",1]
[null,"DB InfraGO AG","1D73C-021","München - Salzburg","< >","Grafing Bahnhof","Ostermünchen",2026,2026,3,3,"2026-01-13","22:00:00","2026-01-14","05:00:00","0d, 7h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"6,7",1]
[null,"DB InfraGO AG","1DCF0-001","München - Salzburg","< >","Gr-Karolinenf  Ü","Rosenheim",2026,2026,5,6,"2026-02-01","22:30:00","2026-02-02","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D73C-017","München - Salzburg","< >","Haar","Aßling (Oberbay)",2026,2026,3,3,"2026-01-12","22:30:00","2026-01-13","05:10:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1E076-009","München - Salzburg","<","Landl (Oberbay) Abzw","Rosenheim",2026,2026,2,2,"2026-01-07","05:00:00","2026-01-07","13:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1D73C-005","München - Salzburg","< >","München Hbf","Haar",2026,2026,2,2,"2026-01-10","22:30:00","2026-01-11","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,7",1]
[null,"DB InfraGO AG","1D341-002","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"2,3",1]
[null,"DB InfraGO AG","1D341-005","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1D3F1-005","München - Salzburg","<","München Ost Pbf","München Isartor",2026,2026,15,16,"2026-04-09","01:00:00","2026-04-13","04:30:00","4d, 3h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","1DD6A-006","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,22,22,"2026-05-28","22:30:00","2026-05-29","04:30:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD6A-009","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,23,24,"2026-06-03","14:00:00","2026-06-08","04:30:00","4d, 14h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1DD6A-011","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,23,24,"2026-06-03","14:00:00","2026-06-08","04:30:00","4d, 14h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1DD6A-016","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,29,29,"2026-07-17","22:30:00","2026-07-19","04:30:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD6A-022","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,24,25,"2026-06-12","22:30:00","2026-06-17","14:00:00","4d, 15h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1D3F1-019","München - Salzburg","<","München-Giesing","München Ost Pbf",2026,2026,15,16,"2026-04-09","04:00:00","2026-04-13","04:30:00","4d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,2",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","1DC27-003","München - Salzburg","< >","München-Trudering","München-Waldtrudering",2026,2026,4,5,"2026-01-25","22:20:00","2026-01-26","05:00:00","0d, 6h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD6A-012","München - Salzburg","<","München-Trudering","München Ost Pbf",2026,2026,24,24,"2026-06-12","18:30:00","2026-06-12","22:30:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1E132-005","München - Salzburg",">","Prien a Chiemsee","Übersee",2026,2026,6,6,"2026-02-02","07:00:00","2026-02-02","14:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-19",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1D587-006","München - Salzburg","< >","Rosenheim","Rosenheim",2026,2026,15,17,"2026-04-11","00:30:00","2026-04-20","05:00:00","9d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,"6,7",1]
[null,"DB InfraGO AG","1D8FC-003","München - Salzburg","< >","Rosenheim","Rosenheim",2026,2026,3,3,"2026-01-15","23:55:00","2026-01-16","04:50:00","0d, 4h","Continuous","Maintenance",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-28",null,null,7,1]
[null,"DB InfraGO AG","1E076-003","München - Salzburg",">","Rosenheim","Simssee",2026,2026,2,2,"2026-01-05","21:00:00","2026-01-06","05:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-24",null,null,1,1]
[null,"DB InfraGO AG","1E132-006","München - Salzburg",">","Rottau","Übersee",2026,2026,6,6,"2026-02-02","14:00:00","2026-02-02","21:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1E076-012","München - Salzburg",">","Simssee","Bad Endorf (Oberbay)",2026,2026,2,2,"2026-01-08","05:00:00","2026-01-08","12:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1E076-020","München - Salzburg",">","Simssee","Bad Endorf (Oberbay)",2026,2026,4,4,"2026-01-21","07:00:00","2026-01-22","21:00:00","1d, 14h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1E132-001","München - Salzburg","<","Übersee","Prien a Chiemsee",2026,2026,4,4,"2026-01-25","07:00:00","2026-01-25","14:00:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-15",null,null,"5,6",1]
[null,"DB InfraGO AG","1C3FA-006","Nürnberg - Passau",">","Aburg-Goldbach","Aschaffenburg Hbf",2026,2026,27,28,"2026-06-29","23:00:00","2026-07-06","05:00:00","6d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-15",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1C3FA-011","Nürnberg - Passau",">","Aburg-Goldbach","Aschaffenburg Hbf",2026,2026,28,29,"2026-07-06","23:00:00","2026-07-13","05:00:00","6d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-14",null,null,"1,2",1]
[null,"DB InfraGO AG","1E18E-002","Nürnberg - Passau","< >","Beratzhausen","Beratzhausen",2026,2026,37,40,"2026-09-07","20:00:00","2026-09-29","06:00:00","21d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"1,7",1]
[null,"DB InfraGO AG","1E72F-019","Nürnberg - Passau","<","Beratzhausen","Undorf",2026,2026,42,42,"2026-10-15","00:00:00","2026-10-15","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","1E5FD-051","Nürnberg - Passau","< >","Deining Üst","Postbauer-Heng",2026,2026,47,47,"2026-11-19","01:00:00","2026-11-19","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1E327-002","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,6,28,"2026-02-06","21:00:00","2026-07-10","20:00:00","153d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,1,1]
[null,"DB InfraGO AG","1C8BF-019","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,15,15,"2026-04-12","00:00:00","2026-04-12","05:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1C8BF-021","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,14,14,"2026-04-05","00:00:00","2026-04-05","05:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-22",null,null,5,1]
[null,"DB InfraGO AG","1E7D1-011","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","04:00:00","2d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","1DF02-019","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,6,28,"2026-02-06","00:00:00","2026-07-10","06:00:00","154d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","1E95C-011","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,45,45,"2026-11-04","10:00:00","2026-11-07","16:00:00","3d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1E95C-014","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,46,46,"2026-11-12","23:00:00","2026-11-13","04:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DDE3-001","Darmstadt - Nürnberg",">","Fürth (Bay) Hbf","Fürth-Burgfarrnbach",2026,2026,8,8,"2026-02-16","21:00:00","2026-02-20","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-07",null,null,"1,2",1]
[null,"DB InfraGO AG","1DDE3-002","Darmstadt - Nürnberg","<","Fürth-Burgfarrnbach","Fürth (Bay) Hbf",2026,2026,12,12,"2026-03-17","21:00:00","2026-03-21","05:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-21",null,null,5,1]
[null,"DB InfraGO AG","1D973-005","Nürnberg - Passau","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-14",null,null,7,1]
[null,"DB InfraGO AG","1DD7E-003","Nürnberg - Passau",">","Kirchseeon","Grafing Bahnhof",2026,2026,5,5,"2026-01-28","21:00:00","2026-01-30","05:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-11-07",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E72F-022","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,43,43,"2026-10-24","00:00:00","2026-10-24","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-09",null,null,6,1]
[null,"DB InfraGO AG","1DF02-018","Nürnberg - Passau","< >","Neumarkt (Oberpf)","Neumarkt (Oberpf)",2026,2026,6,28,"2026-02-06","00:00:00","2026-07-10","06:00:00","154d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1C8BF-004","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg Reichswald",2026,2026,6,8,"2026-02-06","01:00:00","2026-02-21","06:00:00","15d, 5h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1C8BF-010","Nürnberg - Passau",">","Nürnberg Reichswald","Allersberg (Rothsee)",2026,2026,8,8,"2026-02-21","01:00:00","2026-02-22","05:00:00","1d, 4h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",3,3",null,null,null,"N",null,"2024-12-20",null,null,"5,6",1]
[null,"DB InfraGO AG","1DF02-013","Nürnberg - Passau","< >","Nürnberg Reichswald","Regensburg Bbf",2026,2026,28,28,"2026-07-10","12:00:00","2026-07-11","12:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-01-07",null,null,1,1]
[null,"DB InfraGO AG","1DF02-017","Nürnberg - Passau","< >","Nürnberg Reichswald","Regensburg Bbf",2026,2026,24,28,"2026-06-14","21:00:00","2026-07-10","21:00:00","26d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-12-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E95C-022","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg Reichswald",2026,2026,46,46,"2026-11-13","05:00:00","2026-11-14","12:00:00","1d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1E95C-023","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg-Dutzendteich",2026,2026,50,50,"2026-12-11","05:00:00","2026-12-12","23:59:00","1d, 18h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-23",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","1E7D1-014","Nürnberg - Passau","< >","Nürnberg-Dürrenhof","Feucht",2026,2026,37,38,"2026-09-10","22:30:00","2026-09-14","04:30:00","3d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1DF02-005","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,6,28,"2026-02-03","06:00:00","2026-07-12","06:00:00","158d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D0F3-001","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,50,"2026-10-28","07:00:00","2026-12-11","23:59:00","44d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1DF02-016","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,6,28,"2026-02-03","06:00:00","2026-07-12","06:00:00","158d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C8BF-012","Nürnberg - Passau",">","Nürnberg-Langwasser","Nürnberg Reichswald",2026,2026,7,8,"2026-02-09","06:00:00","2026-02-21","06:00:00","12d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-10-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1F819-002","Nürnberg - Passau","< >","Obertraubling","Regensburg Ost",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-16","21:00:00","8d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,5,1]
[null,"DB InfraGO AG","1E72F-017","Nürnberg - Passau","<","Ochenbruck","Postbauer-Heng",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-18","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-20",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1E5FD-054","Nürnberg - Passau","< >","Ochenbruck","Postbauer-Heng",2026,2026,47,47,"2026-11-20","01:00:00","2026-11-20","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1E18E-007","Nürnberg - Passau",">","Parsberg","Deining Üst",2026,2026,48,49,"2026-11-27","01:00:00","2026-11-30","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"1,2",1]
[null,"DB InfraGO AG","1E5FD-032","Nürnberg - Passau",">","Parsberg","Seubersdorf",2026,2026,45,45,"2026-11-02","21:00:00","2026-11-06","05:00:00","3d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO AG","1CD61-001","Nürnberg - Passau","< >","Passau Gbf","Plattling",2026,2026,24,28,"2026-06-14","21:00:00","2026-07-10","21:00:00","26d, 0h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-10",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D552-001","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,39,40,"2026-09-25","05:00:00","2026-10-04","05:00:00","9d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D659-003","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,18,19,"2026-04-27","07:00:00","2026-05-04","05:00:00","6d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1D659-007","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,6,1]
[null,"DB InfraGO AG","1D710-004","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,20,21,"2026-05-15","22:00:00","2026-05-23","04:00:00","7d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,6,1]
[null,"DB InfraGO AG","1D710-005","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"5,6",1]
[null,"DB InfraGO AG","1D5C0-003","Nürnberg - Passau","< >","Passau Hbf","Passau Gbf",2026,2026,39,40,"2026-09-26","22:00:00","2026-09-28","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-006","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-08",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-008","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,40,41,"2026-10-03","22:00:00","2026-10-05","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-011","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,43,44,"2026-10-24","22:00:00","2026-10-26","05:00:00","1d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,4,1]
[null,"DB InfraGO AG","1CF23-016","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1D1F4-002","Nürnberg - Passau",">","Plattling","Straßkirchen",2026,2026,47,47,"2026-11-17","08:00:00","2026-11-18","16:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1D32E-004","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,10,10,"2026-03-02","20:00:00","2026-03-03","06:00:00","0d, 10h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"1,2,7",1]
[null,"DB InfraGO AG","1D32E-005","Nürnberg - Passau","<","Plattling","Osterhofen (Niederbay)",2026,2026,10,10,"2026-03-03","00:00:00","2026-03-03","04:00:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-08",null,null,"1,2,7",1]
[null,"DB InfraGO AG","1D32E-014","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,15,17,"2026-04-10","06:00:00","2026-04-26","22:00:00","16d, 16h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,"5,6",1]
[null,"DB InfraGO AG","1D710-001","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,20,21,"2026-05-15","07:00:00","2026-05-23","04:00:00","7d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1D495-015","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,38,45,"2026-09-15","02:00:00","2026-11-05","04:00:00","51d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1CF23-023","Nürnberg - Passau","< >","Pleinting","Mangolding",2026,2026,50,50,"2026-12-12","06:00:00","2026-12-12","23:59:00","0d, 17h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-24",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1DE17-010","Nürnberg - Passau","<","Regensburg Bbf","Regensburg Ost",2026,2026,38,38,"2026-09-15","21:00:00","2026-09-16","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-05-24",null,null,1,1]
[null,"DB InfraGO AG","1DF02-012","Nürnberg - Passau","< >","Regensburg Bbf","Nürnberg Reichswald",2026,2026,28,28,"2026-07-10","12:00:00","2026-07-11","12:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-31",null,null,1,1]
[null,"DB InfraGO AG","1E010-007","Nürnberg - Passau","< >","Regensburg Bbf","Regensburg Bbf",2026,2026,7,8,"2026-02-13","18:00:00","2026-02-19","07:00:00","5d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-03",null,null,1,1]
[null,"DB InfraGO AG","1E010-008","Nürnberg - Passau",">","Regensburg Bbf","Undorf",2026,2026,28,28,"2026-07-08","22:00:00","2026-07-09","06:00:00","0d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,1,1]
[null,"DB InfraGO AG","1DB86-003","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,11,11,"2026-03-10","00:00:00","2026-03-10","05:00:00","0d, 5h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DB86-015","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-09","21:00:00","2026-06-10","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DB86-025","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,23,24,"2026-06-07","21:00:00","2026-06-08","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1DE17-005","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Bbf",2026,2026,26,26,"2026-06-22","23:00:00","2026-06-23","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1DB86-018","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-10","19:00:00","2026-06-14","05:00:00","3d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1DE17-006","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,26,37,"2026-06-23","21:00:00","2026-09-13","04:55:00","81d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5FD-030","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,44,44,"2026-10-31","01:00:00","2026-10-31","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB86-001","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,10,10,"2026-03-06","23:00:00","2026-03-08","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB86-009","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,23,23,"2026-06-02","20:00:00","2026-06-06","06:00:00","3d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DB86-019","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,24,24,"2026-06-10","19:00:00","2026-06-14","05:00:00","3d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DB86-027","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,25,25,"2026-06-15","21:00:00","2026-06-17","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1F819-007","Nürnberg - Passau","< >","Regensburg Ost","Obertraubling",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-16","21:00:00","8d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1DA81-005","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1F819-013","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,31,34,"2026-07-29","17:00:00","2026-08-17","12:00:00","18d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1E72F-009","Nürnberg - Passau","< >","Seubersdorf","Parsberg",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","01:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO AG","1E5FD-031","Nürnberg - Passau",">","Seubersdorf","Neumarkt (Oberpf)",2026,2026,44,45,"2026-11-01","22:00:00","2026-11-02","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO AG","1CF23-005","Nürnberg - Passau","< >","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"6,7",1]
[null,"DB InfraGO AG","1EA40-002","Nürnberg - Passau","< >","Straubing","Bogen",2026,2026,31,32,"2026-07-31","06:00:00","2026-08-03","22:00:00","3d, 16h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,7,1]
[null,"DB InfraGO AG","1E18E-005","Nürnberg - Passau",">","Undorf","Parsberg",2026,2026,40,41,"2026-10-02","01:00:00","2026-10-05","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-028","Nürnberg - Passau","<","Undorf","Regensburg Dörnberg",2026,2026,44,44,"2026-10-29","21:00:00","2026-10-30","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CF23-021","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1260-(MK27)-02","Nürnberg - Plzen",">","Hersbruck (re P)","Marktredwitz",2027,2027,36,38,"10.09.2027","21:00:00","24.09.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-05-23",null,null,3,1]
[null,"DB InfraGO AG","20DE0-003","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,38,"2026-08-04","00:00:00","2026-09-16","00:00:00","43d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-007","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,34,"2026-08-09","04:45:00","2026-08-20","04:45:00","11d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-017","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","213D2-004","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,35,36,"2026-08-29","05:00:00","2026-09-01","05:00:00","3d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","213D2-006","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,35,36,"2026-08-29","22:00:00","2026-08-31","06:00:00","1d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO AG","213D2-009","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-10","23:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO AG","20DE0-008","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,32,33,"2026-08-09","00:00:00","2026-08-15","04:45:00","6d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,6,1]
[null,"DB InfraGO AG","20DE0-023","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,37,38,"2026-09-12","18:30:00","2026-09-17","11:00:00","4d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,5,1]
[null,"DB InfraGO AG","20F03-004","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,45,47,"2026-11-04","14:00:00","2026-11-17","14:00:00","13d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1550-(MK27)-01","Nürnberg - Plzen","< >","Marktredwitz","Schirnding Grenz",2027,2027,27,28,"09.07.2027","21:00:00","16.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20BFC-002","Nürnberg - Plzen","<","Neuhaus (Pegnitz)","Vorra (Pegnitz)",2026,2026,8,8,"2026-02-21","06:00:00","2026-02-22","14:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20DE0-006","Nürnberg - Plzen",">","Neunkirchen a Sand","Hersbruck (rechts Pegnitz)",2026,2026,32,34,"2026-08-09","04:45:00","2026-08-20","04:45:00","11d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,null,null,null,7,1]
[null,"DB InfraGO AG","22378-004","Nürnberg - Plzen","< >","Neusorg","Marktredwitz",2026,2026,32,32,"2026-08-06","05:00:00","2026-08-07","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-31",null,null,6]
[null,"DB InfraGO AG","2057A-011","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,41,41,"2026-10-10","21:00:00","2026-10-11","06:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2057A-004","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-05-07",null,null,"3,4,5"]
[null,"DB InfraGO AG","2057A-012","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,41,41,"2026-10-10","22:00:00","2026-10-11","06:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,null,null,null,"3,4,5,6"]
[null,"DB InfraGO AG","227DA-001","Nürnberg - Plzen","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-14","04:00:00","14d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,7"]
[null,"DB InfraGO AG","227DA-003","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,9,9,"2026-02-23","08:30:00","2026-02-26","15:30:00","3d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,null,null,null,"1,2,7"]
[null,"DB InfraGO AG","227DA-008","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,47,47,"2026-11-18","08:30:00","2026-11-19","15:30:00","1d, 7h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2057A-003","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,31,36,"2026-07-31","01:45:00","2026-08-31","04:35:00","31d, 2h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,6,7"]
[null,"DB InfraGO AG","2080A-001","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,10,10,"2026-03-04","08:00:00","2026-03-06","08:00:00","2d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-003","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,10,50,"2026-03-06","22:00:00","2026-12-12","23:59:00","281d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-011","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,32,34,"2026-08-09","06:00:00","2026-08-21","06:00:00","12d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-019","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,46,48,"2026-11-09","06:00:00","2026-11-29","06:00:00","20d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4]
[null,"DB InfraGO AG","227DA-011","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,11,12,"2026-03-13","08:30:00","2026-03-17","15:30:00","4d, 7h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"5,6"]
[null,"DB InfraGO AG","227DA-012","Nürnberg - Plzen","<","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,12,12,"2026-03-16","08:30:00","2026-03-17","15:30:00","1d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-24",null,null,5]
[null,"DB InfraGO AG","227DA-019","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,13,13,"2026-03-25","21:00:00","2026-03-26","04:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,3]
[null,"DB InfraGO AG","20BFC-001","Nürnberg - Plzen",">","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,5,7,"2026-01-31","06:00:00","2026-02-15","14:00:00","15d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-07",null,null,6]
[null,"DB InfraGO AG","21387-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","21388-003","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1053-(MK27)-02","Regensburg - Plzen","< >","Marktredwitz","Regensburg Ost & Regensburg Hbf",2027,2027,41,49,"15.10.2027","21:00:00","10.12.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1775-(MK27)-01","Regensburg - Plzen","< >","Schwandorf","Furth i W Grenze",2027,2027,5,19,"05.02.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-28",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","20EC7-021","Rostock - Berlin","< >","Bentwisch","Rostock Seehafen Süd",2026,2026,40,42,"2026-10-03","07:00:00","2026-10-16","16:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"5,6"]
[null,"DB InfraGO AG","23B3D-005","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,3]
[null,"DB InfraGO AG","23B3D-002","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4]
[null,"DB InfraGO AG","3191-(MK27)-04","Rostock - Berlin","< >","Berlin-Moabit","Berlin-Wedding Abzw",2027,2027,41,43,"16.10.2027","05:00:00","29.10.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","23B3D-004","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B5A-002","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","23B3D-006","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-23",null,null,5]
[null,"DB InfraGO AG","24036-002","Rostock - Berlin","<","Kargow","Neustrelitz Hbf",2026,2026,48,50,"2026-11-25","21:00:00","2026-12-11","21:00:00","16d, 0h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"6,7"]
[null,"DB InfraGO AG","23B3D-013","Rostock - Berlin","< >","Löwenberg (Mark)","Zehdenick (Mark)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-015","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg DB-Gr",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","24036-008","Rostock - Berlin","< >","Nassenheide","Neustrelitz Hbf",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B39-004","Rostock - Berlin","< >","Oranienburg","Oranienburg",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","21:00:00","7d, 0h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17"]
[null,"DB InfraGO AG","21E8A-012","Rostock - Berlin","< >","Rostock Seehafen Süd","Rostock Seehafen",2026,2026,21,21,"2026-05-22","16:30:00","2026-05-23","21:30:00","1d, 5h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","23B5A-007","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","24021-003","Rostock - Berlin","< >","Waren (Müritz)","Waren (Müritz)",2026,2026,32,40,"2026-08-03","08:00:00","2026-10-02","18:00:00","60d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"26.06.2024"]
[null,"DB InfraGO AG","1C130-002","Wilhelmshaven - Bremen","< >","Bookholzberg","Delmenhorst",2026,2026,19,22,"2026-05-08","22:00:00","2026-05-26","05:00:00","17d, 7h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"17.05.2024"]
[null,"DB InfraGO AG","1C054-002","Wilhelmshaven - Bremen",">","Bremen-Neustadt","Bremen-Neustadt",2026,2026,7,11,"2026-02-09","00:00:00","2026-03-14","23:59:00","33d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"07.08.2024"]
[null,"DB InfraGO AG","1C054-003","Wilhelmshaven - Bremen","<","Bremen-Neustadt","Bremen-Neustadt",2026,2026,7,11,"2026-02-09","00:00:00","2026-03-14","23:59:00","33d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"16.07.2024"]
[null,"DB InfraGO AG","1BE70-004","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bremen-Neustadt",2026,2026,13,20,"2026-03-23","00:00:00","2026-05-13","23:59:00","51d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"30.07.2024"]
[null,"DB InfraGO AG","1D066-008","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Delmenhorst Df",2026,2026,48,50,"2026-11-25","22:10:00","2026-12-11","05:00:00","15d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,null,"2024-07-30"]
[null,"DB InfraGO AG","1C130-006","Wilhelmshaven - Bremen","< >","Delmenhorst","Bookholzberg",2026,2026,22,22,"2026-05-27","05:00:00","2026-05-29","08:00:00","2d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"19.12.2023"]
[null,"DB InfraGO AG","1BE70-003","Wilhelmshaven - Bremen",">","Delmenhorst Df","Bremen Hbf ehem Bwn",2026,2026,12,12,"2026-03-21","22:00:00","2026-03-22","06:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"09.01.2025"]
[null,"DB InfraGO AG","1BA5F-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Bad Zwischenahn",2026,2026,47,48,"2026-11-16","22:00:00","2026-11-27","22:00:00","11d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"07.05.2024"]
[null,"DB InfraGO AG","1C280-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2025,2026,50,7,"2025-12-14","00:00:00","2026-02-15","23:59:00","63d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"04.06.2024"]
[null,"DB InfraGO AG","1C282-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,8,42,"2026-02-16","00:00:00","2026-10-18","23:59:00","244d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"22.01.2025"]
[null,"DB InfraGO AG","1C282-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,8,42,"2026-02-16","00:00:00","2026-10-18","23:59:00","244d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"29.08.2024"]
[null,"DB InfraGO AG","1C27A-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","23:59:00","55d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-10T07:39:21"]
[null,"DB InfraGO AG","1B659-001","Wilhelmshaven - Bremen","< >","Wilhelmshaven","Sande",2026,2026,12,15,"2026-03-20","22:00:00","2026-04-08","05:00:00","18d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:26"]
[null,"DB InfraGO AG","1D35C-002","Wilhelmshaven - Bremen","< >","Wilhelmshaven Ölweiche","Wilhelmshaven Nord",2026,2026,11,36,"2026-03-09","07:00:00","2026-08-31","17:00:00","175d, 9h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:26"]
[null,"GySEV",26529,"Sopron - Györ",null,"Győr","Csorna",2026,2026,17,17,"2026-04-20",null,"2026-04-24",null,"4 days","Continuous","Line","T",null,null,null,null,null,null,null,null,null,"Maitenance of VVF, component replacement, replacement of faulty rails, maintenance of crossings, cobblestone replacement, bush trimming along the railway and other works along the tracks",null,null,null,"2026-02-06"]
[null,"MÁV",5526001119,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,11,11,"2026-03-13","09:00:00","2026-03-13","16:00:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001122,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,12,12,"2026-03-18","09:00:00","2026-03-18","16:00:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001126,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,13,13,"2026-03-24","09:00:00","2026-03-24","16:00:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001127,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,13,13,"2026-03-25","09:00:00","2026-03-25","16:00:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001131,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,14,14,"2026-03-31","09:00:00","2026-03-31","16:00:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001136,"Hegyeshalom-Ferencváros",">","Kelenföld ","Kelenföld ",2026,2026,17,17,"2026-04-20","23:30:00","2026-04-21","04:30:00","5h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001139,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,19,19,"2026-05-05","00:30:00","2026-05-05","05:30:00","5h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001141,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,19,19,"2026-05-07","00:30:00","2026-05-07","05:30:00","5h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001147,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,21,21,"2026-05-21","09:00:00","2026-05-21","13:00:00","4h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001150,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,22,22,"2026-05-26","10:00:00","2026-05-26","11:00:00","1h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001154,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,22,22,"2026-05-27","09:00:00","2026-05-27","13:00:00","4h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001155,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,22,22,"2026-05-28","09:00:00","2026-05-28","15:00:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001159,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,26,37,"2026-06-25","18:00:00","2026-09-11","17:59:00","77d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001164,"Hegyeshalom-Ferencváros",">","Ferencváros "," Ferencváros ",2026,2026,27,27,"2026-07-04","08:00:00","2026-07-04","18:00:00","10h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001167,"Hegyeshalom-Ferencváros",">","Ferencváros "," Ferencváros ",2026,2026,28,28,"2026-07-09","08:00:00","2026-07-09","18:00:00","10h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001169,"Hegyeshalom-Ferencváros",">","Ferencváros "," Ferencváros ",2026,2026,28,28,"2026-07-11","08:00:00","2026-07-11","18:00:00","10h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001175,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,37,37,"2026-09-08","23:30:00","2026-09-09","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001178,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,37,42,"2026-09-11","18:00:00","2026-10-15","08:00:00","33d14h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001182,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-19","08:00:00","2026-10-19","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001183,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-20","08:00:00","2026-10-20","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001187,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,44,"2026-10-27","08:00:00","2026-10-27","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001192,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,44,"2026-10-27","18:00:00","2026-10-27",1,"6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001195,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-04","23:30:00","2026-11-05","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001197,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001203,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,46,46,"2026-11-12","09:30:00","2026-11-12","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001206,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-17","09:30:00","2026-11-17","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001208,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-19","09:30:00","2026-11-19","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001211,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,48,48,"2026-11-24","09:30:00","2026-11-24","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001215,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,49,49,"2026-12-04","21:30:00","2026-12-05","05:30:00","8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070005,"Štúrovo - Ferencváros",">","Szob","Szob",2026,2026,16,16,"2026-04-14","08:55:00","2026-04-14","14:10:00","5h15m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,6,7"]
[null,"MÁV",5526070008,"Štúrovo - Ferencváros",">","Rákospalota-Újpest","Dunakeszi",2026,2026,17,18,"2026-04-24","22:00:00","2026-04-27","05:00:00","2d7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070010,"Štúrovo - Ferencváros",">","Göd","Vác",2026,2026,19,20,"2026-05-10","01:00:00","2026-05-11","05:00:00","1d4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3"]
[null,"MÁV",5526070016,"Štúrovo - Ferencváros",">","Vác","Verőce",2026,2026,35,36,"2026-08-28","22:00:00","2026-08-31","05:00:00","2d7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070019,"Štúrovo - Ferencváros",">","Nagymaros","Szob",2026,2026,42,42,"2026-10-12","09:00:00","2026-10-16","22:00:00","4d13h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070021,"Štúrovo - Ferencváros",">","Szob","Szob",2026,2026,42,42,"2026-10-14","08:55:00","2026-10-14","14:10:00","5h15m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",5526100023,"Ferencváros-Szajol",">","Pestszentlőrinc","Vecsés",2026,2026,20,21,"2026-05-17","01:00:00","2026-05-18","04:00:00","1d3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5,6,7"]
[null,"MÁV",5526120001,"Ferencváros-Szajol",">","Rákoshegy","Maglód",2026,2026,9,9,"2026-02-28","08:00:00","2026-02-28","17:00:00","9h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5,7"]
[null,"MÁV",5526120008,"Ferencváros-Szajol",">","Tápiógyörgye","Újszász",2026,2026,22,23,"2026-05-29","22:00:00","2026-06-01","04:00:00","2d6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"4,5,6,7"]
[null,"MÁV",5526120026,"Ferencváros-Szajol",">","Rákoshegy","Maglód",2026,2026,41,42,"2026-10-09","20:40:00","2026-10-12","04:40:00","2d8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001007,"Hegyeshalom-Ferencváros",">","Hegyeshalom","Hegyeshalom",2026,2026,17,17,"2026-04-24","22:00:00","2026-04-26","06:00:00","32h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001040,"Hegyeshalom-Ferencváros",">","Győr személy","Győr személy",2026,2026,13,13,"2026-03-27","23:40:00","2026-03-28","04:25:00","4h45m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001047,"Hegyeshalom-Ferencváros",">","Ács","Ács",2026,2026,15,15,"2026-04-11","22:10:00","2026-04-12","04:50:00","6h40m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5,6"]
[null,"MÁV",5526001050,"Hegyeshalom-Ferencváros",">","Mosonmagyaróvár","Mosonmagyaróvár",2026,2026,17,17,"2026-04-24","23:15:00","2026-04-25","04:25:00","5h10m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001056,"Hegyeshalom-Ferencváros",">","Hegyeshalom","Hegyeshalom",2026,2026,21,21,"2026-05-22","22:40:00","2026-05-23","05:10:00","6h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5,6,7"]
[null,"MÁV",5526001060,"Hegyeshalom-Ferencváros",">","Hegyeshalom","Hegyeshalom",2026,2026,24,24,"2026-06-12","22:40:00","2026-06-13","05:10:00","6h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,5]
[null,"MÁV",5526101004,"Szajol - Biharkeresztes","< >","Báránd ","Sáp",2026,2026,37,37,"2026-09-08","20:40:00","2026-09-09","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",5526101007,"Szajol - Biharkeresztes","< >","Püspökladány","Báránd",2026,2026,37,37,"2026-09-09","20:40:00","2026-09-10","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,2]
[null,"MÁV",5526101009,"Szajol - Biharkeresztes","< >","Sáp ","Berettyóújfalu",2026,2026,37,37,"2026-09-11","20:40:00","2026-09-12","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101015,"Szajol - Biharkeresztes",">","Biharkeresztes  ","Biharkeresztes  ",2026,2026,39,39,"2026-09-22","22:00:00","2026-09-23","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101018,"Szajol - Biharkeresztes",">","Berettyóújfalu ","Berettyóújfalu ",2026,2026,40,40,"2026-09-28","22:00:00","2026-09-29","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101020,"Szajol - Biharkeresztes",">","Báránd ","Báránd ",2026,2026,40,40,"2026-10-01","07:00:00","2026-10-01","13:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120010,"Szajol-Curtici",">","Szajol","Tiszatenyő",2026,2026,36,39,"2026-08-31","00:00:00","2026-09-25","23:59:00","25d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120014,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,40,40,"2026-09-29","18:00:00","2026-09-30","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120020,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,41,41,"2026-10-05","18:00:00","2026-10-06","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120023,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,41,41,"2026-10-08","02:00:00","2026-10-08","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120025,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,41,41,"2026-10-09","19:00:00","2026-10-10","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120032,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,42,42,"2026-10-16","02:00:00","2026-10-16","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120035,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,43,43,"2026-10-20","02:00:00","2026-10-20","05:00:00","3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120037,"Szajol-Curtici",">","Gyoma","Csárdaszállás",2026,2026,43,43,"2026-10-21","19:00:00","2026-10-22","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120040,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-26","20:00:00","2026-10-27","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120045,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-29","20:00:00","2026-10-30","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120049,"Szajol-Curtici",">","Mezőberény","Murony",2026,2026,45,45,"2026-11-02","18:00:00","2026-11-03","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120052,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-04","19:00:00","2026-11-05","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120054,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-05","19:00:00","2026-11-06","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120060,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,46,46,"2026-11-11","20:00:00","2026-11-12","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120063,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,47,47,"2026-11-16","23:35:00","2026-11-17","04:00:00","4h25m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120065,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,47,47,"2026-11-17","20:00:00","2026-11-18","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120068,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,47,47,"2026-11-20","22:15:00","2026-11-21","02:45:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120073,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,48,48,"2026-11-24","20:00:00","2026-11-25","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120077,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,49,49,"2026-11-30","20:00:00","2026-12-01","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120080,"Szajol-Curtici",">","Murony","Murony",2026,2026,49,49,"2026-12-02","20:00:00","2026-12-03","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120082,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,50,50,"2026-12-07","19:00:00","2026-12-07","23:30:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100005,"Szajol - Biharkeresztes",">","Karcag","Karcag",2026,2026,16,16,"2026-04-15","21:00:00","2026-04-16","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100011,"Szajol - Biharkeresztes",">","Kisújszállás","Kisújszállás",2026,2026,17,17,"2026-04-20","21:00:00","2026-04-21","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100016,"Szajol - Biharkeresztes",">","Püspökladány","Püspökladány",2026,2026,17,17,"2026-04-22","21:00:00","2026-04-23","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100034,"Szajol - Biharkeresztes",">","Kőbánya-Kispest","Kőbánya-Kispest",2026,2026,36,40,"2026-09-04","22:00:00","2026-10-02","23:59:00","28d2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100046,"Szajol - Biharkeresztes",">","Karcag","Karcag",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100054,"Szajol - Biharkeresztes",">","Püspökladány","Püspökladány",2026,2026,42,42,"2026-10-14","21:00:00","2026-10-15","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"SNCF-R",8726164,"Karlsruhe - Strasbourg",null,"Strasbourg-Neudorf - Entrée lavage","Krimmeri-Meinau",2026,2026,21,21,"2026-05-19","00:15:00","2026-05-23","05:15:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP109+111  ",null,"Y",142000,"2024-12-17"]
[null,"SNCF-R",8726162,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Ville - Bât Voyageurs",2026,2026,21,22,"2026-05-23","23:50:00","2026-05-31","05:05:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Groupes A+B+C+D",null,"Y",142000.14499999999,"2024-12-17"]
[null,"SNCF-R",8726176,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Neudorf - Entrée lavage",2026,2026,31,32,"2026-08-02","20:20:00","2026-08-03","04:20:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP578+575+565+722+737+743+752+564+724+738+746+753",null,"Y",142000.14499999999,"2024-12-17",null,null,1]
[null,"SNCF-R",8726165,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2026,2026,45,45,"2026-11-03","00:15:00","2026-11-07","06:05:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Création de fenêtres génériques de 6h avec simultanée de 4h pour passage trains internationaux Pk début 2,500                         ",null,"Y",142000,"2024-12-17",null,null,"1,2,3,4,5,6,7"]
[null,"SNCF-R",8726168,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2025,2026,51,50,"2025-12-15","11:02:00","2026-12-11","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,"Y",142000,"2024-12-17"]
[null,"SZCZ","V-003902/24","Brno - Břeclav","< >","Brno hl.n.","Odb Brno-Židenice z",2026,2026,48,49,"2026-11-28","00:00:00","2026-11-30","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3"]
[null,"SZCZ","V-003896/24","Brno - Břeclav","< >","Odb B.-Čern.zhl.Táb.","Odb Brno-Židenice z",2026,2026,10,11,"2026-03-07","00:00:00","2026-03-09","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003898/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb Brno-Židenice z",2026,2026,10,49,"2026-03-07","00:00:00","2026-12-04","23:59:00","273 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"záhlaví 1. TK směr Odb Brno-Černovice zhl. Táborská",null,null,null,"2024-12-17"]
[null,"SZCZ","V-016319/23","Česká Třebová - Brno","< >","Adamov","Blansko",2026,2026,8,8,"2026-02-21","00:00:00","2026-02-22","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,45,46,"2026-11-06","00:00:00","2026-11-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006244/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2026,2026,11,16,"2026-03-15","00:00:00","2026-04-13","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-006249/24","Česká Třebová - Brno","< >","Odb Zádulka","Č.Třebová vjezd.sk.",2026,2026,16,47,"2026-04-14","00:00:00","2026-11-22","23:59:00","223 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003674/24","Česká Třebová - Brno","< >","Rájec-Jestřebí","Skalice nad Svitavou",2026,2026,42,43,"2026-10-16","00:00:00","2026-10-21","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003673/24","Česká Třebová - Brno","< >","Skalice nad Svitavou","Rájec-Jestřebí",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-16","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17",null,null,"3,4,5,6"]
[null,"SZCZ","V-006259/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2026,2026,7,8,"2026-02-14","00:00:00","2026-02-20","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-12-17",null,null,"2,3,4,5,6"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,48,51,"2026-11-28","00:00:00","2026-12-14","23:59:00","17 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005250/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,32,32,"2026-08-05","00:00:00","2026-08-06","23:59:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005252/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,43,43,"2026-10-19","00:00:00","2026-10-21","23:59:00","3 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005269/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2026,2026,46,46,"2026-11-11","00:00:00","2026-11-15","23:59:00","10 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003640/23","Chocen - Hranice na Morave","< >","Jistebník","Studénka",2026,2026,11,12,"2026-03-09","00:00:00","2026-03-16","23:59:00","8 days","Continuous","Signal",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ TK 1 a 2.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,26,46,"2026-06-26","00:00:00","2026-11-09","23:59:00","137 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005239/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,20,21,"2026-05-15","00:00:00","2026-05-19","23:59:00","5 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018467/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,6,7,"2026-02-02","00:00:00","2026-02-13","23:59:00","12 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006258/24","Chocen - Hranice na Morave","< >","Odb Parník","Česká Třebová",2026,2026,7,7,"2026-02-09","00:00:00","2026-02-13","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006248/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2026,2026,16,16,"2026-04-14","00:00:00","2026-04-16","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006246/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003656/23","Chocen - Hranice na Morave","< >","Studénka","Studénka",2026,2026,12,31,"2026-03-17","00:00:00","2026-07-31","23:59:00","137 days","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzhlaví jistebnické.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006244/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Odb Les",2026,2026,11,16,"2026-03-15","00:00:00","2026-04-13","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"200 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2023-11-23"]
[null,"SZCZ","V-007567/23","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,33,33,"2026-08-10","00:00:00","2026-08-15","23:59:00","6 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-11-22","2025-01-29"]
[null,"SZCZ","V-015932/23","Děčín - Kolín","< >","Libice nad Cidlinou","Poděbrady",2026,2026,18,19,"2026-05-03","00:00:00","2026-05-06","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-08-01","2025-01-29"]
[null,"SZCZ","V-015933/23","Děčín - Kolín","< >","Poděbrady","Odb Babín",2026,2026,19,19,"2026-05-07","00:00:00","2026-05-10","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018478/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018465/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-006542/24","Děčín - Praha-Libeň","< >","Povrly","Děčín hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-25","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-006539/24","Děčín - Praha-Libeň","< >","Ústí n.L.hl.n.jih","Prackovice nad Labem",2026,2026,19,20,"2026-05-10","00:00:00","2026-05-13","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013538/24","Hranice na Morave - Ostrava","< >","Ostrava-Svinov","Ostrava-Svinov",2027,2027,41,52,"2027-10-13","00:00:00","2027-12-31","23:59:00","80 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"1 jen TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-023891/19","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2026,2026,10,10,"2026-03-03","00:00:00","2026-03-04","23:59:00","2 x 2 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-003641/23","Hranice na Morave - Ostrava","< >","Studénka","Studénka",2026,2026,8,9,"2026-02-22","18:00:00","2026-02-28","06:00:00","6 x 4 hours","Periodical","Bridge",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007192/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,30,33,"2026-07-26","18:00:00","2026-08-10","06:00:00","15 x 3 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016601/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,13,16,"2027-04-02","18:00:00","2027-04-25","06:00:00","23 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2,1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-001807/22","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Vsetín-Bečva",2026,2026,8,50,"2026-02-16","00:00:00","2026-12-12","23:59:00","300 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013937/24","Hranice na Morave - Zilina","< >","Hranice na Moravě","Hranice na M. město",2027,2027,14,16,"2027-04-10","00:00:00","2027-04-25","23:59:00","16 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-017870/22","Hranice na Morave - Zilina","< >","Valašská Polanka","Vsetín-Bečva",2026,2026,18,22,"2026-05-01","00:00:00","2026-05-31","23:59:00","31 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-017869/22","Hranice na Morave - Zilina","< >","Vsetín-Bečva","Valašská Polanka",2026,2026,18,31,"2026-05-01","00:00:00","2026-07-29","23:59:00","90 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1., 2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007529/22","Kolín - Brno-Maloměřice","< >","Havlíčkův Brod","Pohled",2026,2026,30,31,"2026-07-22","00:00:00","2026-07-31","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016659/23","Kolín - Brno-Maloměřice","< >","Kutná Hora hl.n.","Kolín",2026,2026,14,28,"2026-04-02","00:00:00","2026-07-10","23:59:00","100 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005102/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,49,51,"2026-12-05","00:00:00","2026-12-18","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ 2.,1. TK.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005101/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,15,25,"2026-04-08","00:00:00","2026-06-20","23:59:00","74 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"1,3 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005065/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,31,33,"2026-08-01","18:00:00","2026-08-11","06:00:00","9 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-003951/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,7,7,"2026-02-12","00:00:00","2026-02-14","23:59:00","3 x 12 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzáhlaví a zhlaví 1. TK směr Havlíčkův Brod.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-003947/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,49,49,"2026-12-02","00:00:00","2026-12-03","23:59:00","2 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzáhlaví a zhlaví 1. TK směr Přibyslav.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016007/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,33,"2026-08-11","18:00:00","2026-08-15","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015979/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,25,30,"2026-06-21","00:00:00","2026-07-21","23:59:00","31 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"3 jen TV, 1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015921/23","Kolín - Brno-Maloměřice","< >","Velký Osek","Kolín",2026,2026,13,14,"2026-03-29","00:00:00","2026-04-01","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015901/24","Nürnberg - Plzen","< >","Cheb","Františkovy Lázně",2026,2026,27,29,"2026-07-05","00:00:00","2026-07-14","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005475/24","Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2026,2026,46,46,"2026-11-09","00:00:00","2026-11-13","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005158/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,37,38,"2026-09-11","00:00:00","2026-09-17","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-004047/23","Ostrava - Zilina","< >","Ostrava-Bartovice","Ostrava-Kunčice",2027,2027,38,39,"2027-09-21","00:00:00","2027-09-30","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016331/23","Plzen - Praha","< >","Beroun os.n.","Zdice",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-006943/24","Plzen - Praha","< >","Hořovice","Kařízek",2026,2026,15,16,"2026-04-07","18:00:00","2026-04-19","06:00:00","7 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. "]
[null,"SZCZ","V-013900/22","Plzen - Praha","< >","Odb Tunel","Praha-Radotín",2026,2026,32,42,"2026-08-09","00:00:00","2026-10-17","23:59:00","70 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. "]
[null,"SZCZ","V-015085/23","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,26,29,"2026-06-28","00:00:00","2026-07-18","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. "]
[null,"SZCZ","V-004403/24","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-11","23:59:00","8 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. bez TV. "]
[null,"SZCZ","V-010376/21","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2026,2026,30,32,"2026-07-20","00:00:00","2026-08-08","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1.,3. + TV. "]
[null,"SZCZ","V-006765/23","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2026,2026,26,26,"2026-06-27","18:00:00","2026-06-28","06:00:00","1 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,"X",null,null," ,X,X",null,null,"1.,3. jen TV. "]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Praha-Radotín",2026,2026,43,44,"2026-10-23","00:00:00","2026-10-27","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-006264/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Choceň",2026,2026,16,16,"2026-04-13","00:00:00","2026-04-17","23:59:00","5 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-005155/24","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,10,11,"2026-03-03","00:00:00","2026-03-14","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-015245/23","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,13,14,"2026-03-28","00:00:00","2026-04-03","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-006265/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Týniště nad Orlicí",2026,2026,21,21,"2026-05-18","00:00:00","2026-05-20","23:59:00","3 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-003373/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2026,2026,30,30,"2026-07-20","00:00:00","2026-07-24","23:59:00","5 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"3,5 bez TV. ",null,null,null,"2022-12-16"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-03","23:59:00","278 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006238/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,8,53,"2026-02-22","00:00:00","2026-12-31","23:59:00","313 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"17 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,32,33,"2026-08-03","00:00:00","2026-08-12","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Předměřice nad Labem",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ."]
[null,"SZCZ","V-015260/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Pardubice hl.n.",2026,2026,21,22,"2026-05-22","00:00:00","2026-05-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. "]
[null,"SZCZ","V-018463/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. "]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,41,43,"2027-10-17","00:00:00","2027-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015270/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,20,20,"2026-05-12","00:00:00","2026-05-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-020531/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,19,19,"2026-05-04","00:00:00","2026-05-09","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,3,7,"2026-01-14","00:00:00","2026-02-13","23:59:00","31 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-006263/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Choceň",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-10","23:59:00","6 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,18,19,"2027-05-07","00:00:00","2027-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice."]
[null,"SZCZ","V-015278/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2026,2026,19,20,"2026-05-08","00:00:00","2026-05-11","23:59:00","4 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-015921/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Velký Osek",2026,2026,13,14,"2026-03-29","00:00:00","2026-04-01","23:59:00","4 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"záhlaví a zhlaví 1.traťové koleje směr Kolín."]
[null,"SZCZ","V-015921/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Kolín",2026,2026,15,15,"2026-04-09","00:00:00","2026-04-12","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-015251/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,16,17,"2026-04-19","00:00:00","2026-04-23","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-005099/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 x 12 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,41,52,"2026-10-07","00:00:00","2026-12-22","23:59:00","77 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,34,42,"2026-08-17","00:00:00","2026-10-18","23:59:00","63 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-014554/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-18","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018467/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,6,7,"2026-02-02","00:00:00","2026-02-13","23:59:00","12 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015275/24","Chocen - Hranice na Morave","< >","Dlouhá Třebová","Ústí nad Orlicí",2026,2026,30,30,"2026-07-22","00:00:00","2026-07-26","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-008215/25","Chocen - Hranice na Morave","< >","Výh Dluhonice","Přerov os.n.",2026,2026,8,9,"2026-02-22","18:00:00","2026-02-25","06:00:00","3 x 8 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-007193/25","Chocen - Hranice na Morave","< >","Česká Třebová","Třebovice v Čechách",2026,2026,22,22,"2026-05-25","00:00:00","2026-05-31","23:59:00","7 x 11 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006247/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Zádulka",2026,2026,49,50,"2026-11-30","00:00:00","2026-12-12","23:59:00","13 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-017488/25","Chocen - Hranice na Morave","< >","Odb Parník","Č.Třebová náv. NS",2027,2027,35,38,"2027-09-01","00:00:00","2027-09-26","23:59:00","26 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. "]
[null,"SZCZ","V-017487/25","Chocen - Hranice na Morave","< >","Č.Třebová odj.sk.","Odb Parník",2027,2027,28,35,"2027-07-16","00:00:00","2027-08-31","23:59:00","47 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. "]
[null,"SZCZ","V-016599/25","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Odb Jezernice B",2027,2027,14,15,"2027-04-06","00:00:00","2027-04-15","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-006004/25","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2027,2027,9,9,"2027-03-01","00:00:00","2027-03-05","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-017492/25","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2028,2028,1,49,"2028-01-01","00:00:00","2028-12-09","23:59:00","344 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-016146/25","Chocen - Hranice na Morave","< >","Prosenice","Přerov os.n.",2028,2028,18,22,"2028-05-01","00:00:00","2028-05-30","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-007198/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,43,48,"2026-10-20","18:00:00","2026-11-27","06:00:00","38 x 6 hours","periodical","Miscellaneous","T","LT",null,null,"X",null,null,null,null,null,"1,2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-003640/23","Hranice na Morave - Ostrava","< >","Jistebník","Studénka",2026,2026,9,11,"2026-03-01","00:00:00","2026-03-09","23:59:00","9 days","Continuous","Signal","T","LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ TK 1 a 2.",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-016656/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,28,38,"2027-07-12","00:00:00","2027-09-26","23:59:00","77 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017480/25","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2028,2028,16,24,"2028-04-22","00:00:00","2028-06-12","23:59:00","52 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-016190/25","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2028,2028,10,25,"2028-03-08","00:00:00","2028-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017279/20","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Horní Lideč",2026,2026,17,22,"2026-04-21","00:00:00","2026-05-31","23:59:00","41 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-013646/24","Hranice na Morave - Zilina","< >","Hranice na Moravě","Odb Skalka",2026,2026,45,45,"2026-11-04","00:00:00","2026-11-08","23:59:00","10 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003470/25","Hranice na Morave - Zilina","< >","Hranice na M. město","Hustopeče nad Bečvou",2026,2026,17,18,"2026-04-21","00:00:00","2026-04-27","23:59:00","7 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-003468/25","Hranice na Morave - Zilina","< >","Hranice na M. město","Hustopeče nad Bečvou",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:20",null,null,"3,4,5,6"]
[null,"SZCZ","V-002761/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,9,50,"2026-03-01","00:00:00","2026-12-12","23:59:00","287 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-001807/22","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Vsetín-Bečva",2026,2026,8,50,"2026-02-16","00:00:00","2026-12-12","23:59:00","300 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-001315/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,1,50,"2026-01-01","00:00:00","2026-12-11","23:59:00","345 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016012/25","Hranice na Morave - Zilina","< >","Jablůnka","Valašské Meziříčí",2027,2027,20,20,"2027-05-17","00:00:00","2027-05-21","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016011/25","Hranice na Morave - Zilina","< >","Vsetín","Jablůnka",2027,2027,35,37,"2027-09-02","00:00:00","2027-09-16","23:59:00","15 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016136/25","Hranice na Morave - Zilina","< >","Hustopeče nad Bečvou","Hranice na Moravě",2028,2028,40,44,"2028-10-02","00:00:00","2028-10-31","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"2,3,4"]
[null,"SZCZ","V-016135/25","Hranice na Morave - Zilina","< >","Hranice na Moravě","Hustopeče nad Bečvou",2028,2028,35,39,"2028-09-02","00:00:00","2028-10-01","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017609/22","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,19,20,"2026-05-10","00:00:00","2026-05-15","23:59:00","6 days","Continuous","Switch","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4"]
[null,"SZCZ","V-015901/24","Nürnberg - Plzen","< >","Cheb","Františkovy Lázně",2026,2026,27,28,"2026-07-01","00:00:00","2026-07-10","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,7"]
[null,"SZCZ","V-004944/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,6,11,"2026-02-02","00:00:00","2026-03-13","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,5,6,7"]
[null,"SZCZ","V-004949/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,47,50,"2026-11-16","00:00:00","2026-12-11","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,7"]
[null,"SZCZ","V-005474/24","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005475/24","Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2026,2026,46,46,"2026-11-09","00:00:00","2026-11-13","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-004972/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2026,2026,9,9,"2026-02-24","00:00:00","2026-02-28","23:59:00","5 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005006/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2026,2026,12,49,"2026-03-16","00:00:00","2026-11-30","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,7"]
[null,"SZCZ","V-004978/25","Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2026,2026,9,10,"2026-03-01","00:00:00","2026-03-05","23:59:00","5 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005011/25","Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2026,2026,11,49,"2026-03-09","00:00:00","2026-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"3,4,5,6"]
[null,"SZCZ","V-004994/25","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2026,2026,9,10,"2026-02-24","00:00:00","2026-03-05","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005016/25","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2026,2026,48,49,"2026-11-24","00:00:00","2026-12-03","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,6,7"]
[null,"SZCZ","V-005044/25","Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2027,2027,9,48,"2027-03-01","00:00:00","2027-11-30","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"3,4,5"]
[null,"SZCZ","V-005049/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2027,2027,8,48,"2027-02-24","00:00:00","2027-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,7"]
[null,"SZCZ","V-005034/25","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2027,2027,47,48,"2027-11-26","00:00:00","2027-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,5,6,7"]
[null,"SZCZ","V-004916/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2027,2027,6,7,"2027-02-12","00:00:00","2027-02-21","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-004926/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2027,2027,46,47,"2027-11-15","00:00:00","2027-11-24","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-004938/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2028,2028,10,10,"2028-03-06","00:00:00","2028-03-10","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-018975/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,18,19,"2026-04-30","00:00:00","2026-05-04","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-018974/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,17,18,"2026-04-25","00:00:00","2026-04-29","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:26",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-005158/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,18,19,"2026-04-30","00:00:00","2026-05-06","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:26",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-005154/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,17,18,"2026-04-23","00:00:00","2026-04-29","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-017451/25","Ostrava - Zilina","< >","Český Těšín","Albrechtice u Č.T.",2027,2027,20,20,"2027-05-17","00:00:00","2027-05-21","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-017449/25","Ostrava - Zilina","< >","Albrechtice u Č.T.","Český Těšín",2027,2027,19,19,"2027-05-10","00:00:00","2027-05-16","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"2,3,4,5,6"]
[null,"SZCZ","V-006535/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,30,50,"2027-07-28","00:00:00","2027-12-17","23:59:00","143 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1a bez TV. ",null,null,null,"2025-12-09T10:06:31",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006209/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,35,49,"2027-09-01","00:00:00","2027-12-11","23:59:00","102 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-006205/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,36,38,"2027-09-08","00:00:00","2027-09-21","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-005999/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,38,49,"2027-09-22","00:00:00","2027-12-11","23:59:00","81 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-004050/23","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Bartovice",2027,2027,39,40,"2027-10-01","00:00:00","2027-10-10","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-004047/23","Ostrava - Zilina","< >","Ostrava-Bartovice","Ostrava-Kunčice",2027,2027,38,39,"2027-09-21","00:00:00","2027-09-30","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006110/25","Ostrava - Zilina","< >","Ostrava střed","Ostrava-Kunčice",2028,2028,40,41,"2028-10-08","00:00:00","2028-10-14","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006109/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava střed",2028,2028,39,40,"2028-10-01","00:00:00","2028-10-07","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006087/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Bartovice",2028,2028,41,44,"2028-10-15","00:00:00","2028-11-04","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"2,3,4"]
[null,"SZCZ","V-006031/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Vítkovice",2028,2028,28,30,"2028-07-15","00:00:00","2028-07-28","23:59:00","14 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006065/25","Ostrava - Zilina","< >","Ostrava-Vítkovice","Odb Odra",2028,2028,34,36,"2028-08-21","00:00:00","2028-09-09","23:59:00","20 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006017/25","Ostrava - Zilina","< >","Ostrava-Vítkovice","Ostrava-Kunčice",2028,2028,26,28,"2028-07-01","00:00:00","2028-07-14","23:59:00","14 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:22"]
[null,"SZCZ","V-006045/25","Ostrava - Zilina","< >","Odb Odra","Ostrava-Vítkovice",2028,2028,31,33,"2028-08-01","00:00:00","2028-08-20","23:59:00","20 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-004051/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,32,33,"2026-08-07","00:00:00","2026-08-11","23:59:00","5 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-004056/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,34,35,"2026-08-22","00:00:00","2026-08-26","23:59:00","5 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-004031/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,29,30,"2026-07-19","00:00:00","2026-07-22","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-004008/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,22,22,"2026-05-26","00:00:00","2026-05-29","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59",null,null,"1,4,5,6,7"]
[null,"SZCZ","V-003978/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,11,11,"2026-03-10","00:00:00","2026-03-13","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003982/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,11,12,"2026-03-15","00:00:00","2026-03-20","23:59:00","6 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:06:31",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003932/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,5,6,"2026-01-30","00:00:00","2026-02-06","23:59:00","8 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-003940/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,6,7,"2026-02-08","00:00:00","2026-02-11","23:59:00","4 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-003675/25","Ostrava - Zilina","< >","Karviná hl.n.","Odb Karviná-Darkov z",2026,2026,13,13,"2026-03-24","00:00:00","2026-03-28","23:59:00","10 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"1,2,5,6,7"]
[null,"SZCZ","V-003680/25","Ostrava - Zilina","< >","Karviná hl.n.","Odb Karviná-Darkov z",2026,2026,41,42,"2026-10-11","00:00:00","2026-10-13","23:59:00","6 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"1,2,3,6,7"]
[null,"SZCZ","V-003659/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2026,2026,11,12,"2026-03-15","00:00:00","2026-03-19","23:59:00","5 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"0., 2. + TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"1,2,3,7"]
[null,"SZCZ","V-003664/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2026,2026,41,41,"2026-10-08","00:00:00","2026-10-10","23:59:00","3 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"0., 2. + TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"2,3,4,5"]
[null,"SZCZ","V-003641/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2026,2026,1,39,"2026-01-01","00:00:00","2026-09-21","23:59:00","264 days","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"2,3,4,5"]
[null,"SZCZ","V-018608/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2027,2027,38,52,"2027-09-21","00:00:00","2027-12-31","23:59:00","102 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,7"]
[null,"SZCZ","V-017216/25","Ostrava - Zilina","< >","Odb Karviná-Darkov z","Louky nad Olší",2027,2027,53,38,"2027-01-01","00:00:00","2027-09-21","23:59:00","264 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017218/25","Ostrava - Zilina","< >","Odb Karviná-Darkov z","Louky nad Olší",2028,2028,1,38,"2028-01-01","00:00:00","2028-09-19","23:59:00","263 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,7"]
[null,"SZCZ","V-020685/19","Plzen - Praha","< >","Praha-Smíchov","Odb Závodiště",2026,2026,34,43,"2026-08-19","00:00:00","2026-10-19","23:59:00","62 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:05:00",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016905/24","Plzen - Praha","< >","Zdice","Lochovice",2026,2026,46,48,"2026-11-15","00:00:00","2026-11-28","23:59:00","14 days","Continuous","Signal","T","LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. ZZ.",null,null,null,"2025-12-09T10:06:31",null,null,"1,6,7"]
[null,"SZCZ","V-016333/23","Plzen - Praha","< >","Hořovice","Kařízek",2026,2026,16,16,"2026-04-15","00:00:00","2026-04-17","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:31",null,null,"1,3,4,5,6,7"]
[null,"SZCZ","V-006949/24","Plzen - Praha","< >","Zdice","Hořovice",2026,2026,15,15,"2026-04-07","18:00:00","2026-04-10","06:00:00","3 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:31",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016331/23","Plzen - Praha","< >","Beroun os.n.","Zdice",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-03","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:31"]
[null,"SZCZ","V-016329/23","Plzen - Praha","< >","Zdice","Beroun os.n.",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-06","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:31"]
[null,"SZCZ","V-006951/24","Plzen - Praha","< >","Hořovice","Zdice",2026,2026,15,16,"2026-04-11","18:00:00","2026-04-14","06:00:00","3 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:31"]
[null,"SZCZ","V-016327/23","Plzen - Praha","< >","Kařízek","Hořovice",2026,2026,16,17,"2026-04-18","00:00:00","2026-04-20","23:59:00","3 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:31"]
[null,"SZCZ","V-006585/24","Plzen - Praha","< >","Beroun os.n.","Karlštejn",2026,2026,17,17,"2026-04-22","00:00:00","2026-04-25","23:59:00","4 x 12 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-008711/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,45,45,"2026-11-03","00:00:00","2026-11-05","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006278/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,45,46,"2026-11-06","18:00:00","2026-11-12","06:00:00","6 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006658/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,28,29,"2026-07-07","18:00:00","2026-07-15","06:00:00","8 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006665/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,49,51,"2026-11-30","18:00:00","2026-12-15","06:00:00","15 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006679/25","Plzen - Praha","< >","Praha-Radotín","Odb Tunel",2026,2026,49,51,"2026-12-01","18:00:00","2026-12-15","06:00:00","14 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"3. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-007122/25","Plzen - Praha","< >","Praha-Smíchov","P.-Velká Chuchle z",2026,2026,43,46,"2026-10-20","00:00:00","2026-11-11","23:59:00","23 days","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006241/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,41,42,"2026-10-09","00:00:00","2026-10-15","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006224/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2026,2026,44,44,"2026-10-27","00:00:00","2026-10-29","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"2,3,4,5,6"]
[null,"SZCZ","V-006147/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2026,2026,40,41,"2026-10-02","00:00:00","2026-10-08","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,7"]
[null,"SZCZ","V-004402/24","Plzen - Praha","< >","Praha-Radotín","Odb Tunel",2026,2026,27,49,"2026-07-01","00:00:00","2026-12-01","23:59:00","154 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,7"]
[null,"SZCZ","V-004401/24","Plzen - Praha","< >","Odb Tunel","Praha-Radotín",2026,2026,8,27,"2026-02-16","00:00:00","2026-06-30","23:59:00","135 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"4,5,6"]
[null,"SZCZ","V-003036/25","Plzen - Praha","< >","Ejpovice","Plzeň hl.n.os.n.",2026,2026,26,27,"2026-06-22","18:00:00","2026-07-02","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-003046/25","Plzen - Praha","< >","Ejpovice","Plzeň hl.n.os.n.",2026,2026,28,29,"2026-07-06","18:00:00","2026-07-16","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-003076/25","Plzen - Praha","< >","Ejpovice","Plzeň hl.n.os.n.",2026,2026,34,35,"2026-08-17","18:00:00","2026-08-27","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-003006/25","Plzen - Praha","< >","Plzeň hl.n.os.n.","Ejpovice",2026,2026,20,21,"2026-05-11","18:00:00","2026-05-21","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003016/25","Plzen - Praha","< >","Plzeň hl.n.os.n.","Ejpovice",2026,2026,22,23,"2026-05-25","18:00:00","2026-06-04","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-06-30T10:22:35"]
[null,"SZCZ","V-003026/25","Plzen - Praha","< >","Plzeň hl.n.os.n.","Ejpovice",2026,2026,24,25,"2026-06-08","18:00:00","2026-06-18","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-003066/25","Plzen - Praha","< >","Plzeň hl.n.os.n.","Ejpovice",2026,2026,32,33,"2026-08-03","18:00:00","2026-08-13","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-015085/23","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,19,35,"2027-05-15","00:00:00","2027-09-03","23:59:00","112 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-013900/22","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,35,49,"2027-09-04","00:00:00","2027-12-10","23:59:00","98 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006796/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,21,21,"2027-05-24","18:00:00","2027-05-29","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006800/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,26,26,"2027-06-28","18:00:00","2027-07-03","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006805/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,32,32,"2027-08-09","18:00:00","2027-08-14","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006810/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,34,34,"2027-08-23","18:00:00","2027-08-28","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006815/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,39,39,"2027-09-27","18:00:00","2027-10-02","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006819/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,42,42,"2027-10-18","18:00:00","2027-10-23","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006824/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,45,45,"2027-11-08","18:00:00","2027-11-13","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006829/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,47,47,"2027-11-22","18:00:00","2027-11-27","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:20",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006230/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,46,47,"2027-11-18","18:00:00","2027-11-24","06:00:00","6 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-006834/25","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2027,2027,49,50,"2027-12-11","00:00:00","2027-12-14","23:59:00","4 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-006397/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2027,2027,39,41,"2027-09-28","00:00:00","2027-10-12","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006396/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2027,2027,37,39,"2027-09-13","00:00:00","2027-09-27","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006227/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,46,46,"2027-11-15","00:00:00","2027-11-17","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006221/25","Plzen - Praha","< >","Karlštejn","Řevnice",2027,2027,45,45,"2027-11-12","00:00:00","2027-11-14","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006136/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,42,43,"2027-10-20","00:00:00","2027-10-26","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006126/25","Plzen - Praha","< >","Karlštejn","Řevnice",2027,2027,41,42,"2027-10-13","00:00:00","2027-10-19","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006007/25","Plzen - Praha","< >","Praha-Radotín","Dobřichovice",2027,2027,30,33,"2027-07-28","00:00:00","2027-08-16","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-006006/25","Plzen - Praha","< >","Dobřichovice","Praha-Radotín",2027,2027,27,30,"2027-07-08","00:00:00","2027-07-27","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Odb Závodiště",2027,2027,49,49,"2027-12-07","00:00:00","2027-12-10","23:59:00","4 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-017964/22","Plzen - Praha","< >","Ejpovice","Chrást u Plzně",2028,2028,21,26,"2028-05-22","00:00:00","2028-06-30","23:59:00","40 days","Continuous","Bridge","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-015278/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Moravany",2026,2026,17,17,"2026-04-21","00:00:00","2026-04-25","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-015277/23","Praha - Chocen - Česká Třebová","< >","Moravany","Uhersko",2026,2026,16,17,"2026-04-16","00:00:00","2026-04-20","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015276/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,15,15,"2026-04-06","00:00:00","2026-04-10","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015274/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,15,16,"2026-04-11","00:00:00","2026-04-15","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015270/23","Praha - Chocen - Česká Třebová","< >","Moravany","Kostěnice",2026,2026,17,18,"2026-04-26","00:00:00","2026-04-30","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015266/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Moravany",2026,2026,18,19,"2026-05-01","00:00:00","2026-05-05","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015260/23","Praha - Chocen - Česká Třebová","< >","Kostěnice","Pardubice hl.n.",2026,2026,20,20,"2026-05-11","00:00:00","2026-05-15","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015256/23","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Kostěnice",2026,2026,19,19,"2026-05-06","00:00:00","2026-05-10","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015251/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Uhersko",2026,2026,14,14,"2026-04-01","00:00:00","2026-04-05","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015249/23","Praha - Chocen - Česká Třebová","< >","Uhersko","Zámrsk",2026,2026,13,14,"2026-03-27","00:00:00","2026-03-31","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015247/23","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,12,13,"2026-03-21","00:00:00","2026-03-25","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015246/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,12,12,"2026-03-16","00:00:00","2026-03-20","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015245/23","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,13,14,"2026-03-28","00:00:00","2026-04-03","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015241/23","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,12,13,"2026-03-21","00:00:00","2026-03-27","23:59:00","7 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005843/25","Praha - Chocen - Česká Třebová","< >","Velim","Kolín",2026,2026,49,50,"2026-12-05","00:00:00","2026-12-07","23:59:00","3 days","Continuous","Signal",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005830/25","Praha - Chocen - Česká Třebová","< >","Kolín","Velim",2026,2026,49,49,"2026-12-01","00:00:00","2026-12-04","23:59:00","4 days","Continuous","Signal",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-005162/24","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,8,9,"2026-02-18","00:00:00","2026-03-01","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-005155/24","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,10,11,"2026-03-02","00:00:00","2026-03-13","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005099/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,15,16,"2026-04-09","00:00:00","2026-04-13","23:59:00","5 x 12 hours","Periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003783/25","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2026,2026,46,46,"2026-11-10","00:00:00","2026-11-12","23:59:00","3 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003768/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,46,48,"2026-11-13","00:00:00","2026-11-27","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003765/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,48,49,"2026-11-28","00:00:00","2026-11-30","23:59:00","3 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003741/25","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2026,2026,42,43,"2026-10-14","18:00:00","2026-10-19","06:00:00","3 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003722/25","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2026,2026,44,46,"2026-10-26","00:00:00","2026-11-09","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003721/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,41,42,"2026-10-08","00:00:00","2026-10-13","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003720/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,40,41,"2026-10-02","00:00:00","2026-10-07","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003719/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,39,40,"2026-09-27","00:00:00","2026-10-01","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003718/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,38,39,"2026-09-17","00:00:00","2026-09-21","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003713/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,39,39,"2026-09-22","00:00:00","2026-09-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003712/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,37,38,"2026-09-12","00:00:00","2026-09-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003711/25","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2026,2026,37,37,"2026-09-07","00:00:00","2026-09-11","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003708/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2026,2026,36,36,"2026-08-31","00:00:00","2026-09-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003707/25","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2026,2026,36,36,"2026-09-05","00:00:00","2026-09-06","23:59:00","2 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003706/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2026,2026,35,35,"2026-08-29","00:00:00","2026-08-30","23:59:00","2 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003703/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín",2026,2026,34,35,"2026-08-23","00:00:00","2026-08-28","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003702/25","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2026,2026,34,34,"2026-08-17","00:00:00","2026-08-22","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-002808/24","Praha - Chocen - Česká Třebová","< >","Choceň","Zámrsk",2026,2026,21,22,"2026-05-19","18:00:00","2026-05-28","06:00:00","5 x 8 hours","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-002807/24","Praha - Chocen - Česká Třebová","< >","Zámrsk","Choceň",2026,2026,21,22,"2026-05-18","18:00:00","2026-05-27","06:00:00","5 x 8 hours","periodical","Switch",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,45,46,"2027-11-08","00:00:00","2027-11-15","23:59:00","8 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016647/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč",2027,2027,47,48,"2027-11-25","00:00:00","2027-12-04","23:59:00","10 days","Continuous","Maintenance",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016851/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Praha-Běchovice",2028,2028,33,33,"2028-08-14","00:00:00","2028-08-17","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016849/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Praha-Běchovice",2028,2028,32,32,"2028-08-10","00:00:00","2028-08-13","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016847/25","Praha - Chocen - Česká Třebová","< >","Praha-Běchovice","Úvaly",2028,2028,31,32,"2028-08-06","00:00:00","2028-08-09","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016832/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Úvaly",2028,2028,30,30,"2028-07-27","00:00:00","2028-07-30","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016831/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Úvaly",2028,2028,29,30,"2028-07-23","00:00:00","2028-07-26","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016830/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Český Brod",2028,2028,29,29,"2028-07-19","00:00:00","2028-07-22","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016824/25","Praha - Chocen - Česká Třebová","< >","Poříčany","Český Brod",2028,2028,27,28,"2028-07-09","00:00:00","2028-07-12","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016823/25","Praha - Chocen - Česká Třebová","< >","Poříčany","Český Brod",2028,2028,27,27,"2028-07-05","00:00:00","2028-07-08","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016822/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Poříčany",2028,2028,26,27,"2028-07-01","00:00:00","2028-07-04","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3"]
[null,"SZCZ","V-023240/18","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"5,6,7"]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,24,44,"2026-06-14","00:00:00","2026-10-27","23:59:00","96 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016907/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,24,53,"2026-06-14","00:00:00","2026-12-31","23:59:00","201 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015931/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,18,18,"2026-04-29","00:00:00","2026-05-02","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-015921/23","Praha - Chocen - Česká Třebová","< >","Velký Osek","Kolín-Hradišťko",2026,2026,27,28,"2026-07-05","00:00:00","2026-07-06","23:59:00","2 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-015920/23","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,16,17,"2026-04-19","00:00:00","2026-04-22","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-009151/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,15,15,"2026-04-08","00:00:00","2026-04-10","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-007394/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,27,28,"2026-07-05","00:00:00","2026-07-07","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"3,4a,4b,4c,5,6-20,17,21 jen TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-007336/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,5,7,"2026-02-01","00:00:00","2026-02-09","23:59:00","9 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-007345/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,9,9,"2026-02-25","00:00:00","2026-02-28","23:59:00","4 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-007315/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,13,14,"2026-03-25","18:00:00","2026-04-03","06:00:00","9 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-007303/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,14,15,"2026-04-04","00:00:00","2026-04-09","23:59:00","6 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-007312/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,42,42,"2026-10-14","00:00:00","2026-10-16","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-007279/25","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,20,21,"2026-05-17","18:00:00","2026-05-21","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-007287/25","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,29,30,"2026-07-17","18:00:00","2026-07-21","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-006265/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Týniště nad Orlicí",2026,2026,29,29,"2026-07-13","00:00:00","2026-07-15","23:59:00","3 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-006264/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Choceň",2026,2026,16,16,"2026-04-13","00:00:00","2026-04-17","23:59:00","5 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-006263/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Choceň",2026,2026,14,15,"2026-04-05","00:00:00","2026-04-07","23:59:00","3 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,21,23,"2026-05-23","00:00:00","2026-06-01","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019390/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,26,32,"2027-07-03","00:00:00","2027-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019389/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,14,14,"2027-04-08","00:00:00","2027-04-10","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-019382/25","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2027,2027,14,14,"2027-04-05","00:00:00","2027-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,22,23,"2027-06-02","00:00:00","2027-06-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,20,21,"2027-05-17","00:00:00","2027-05-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,15,16,"2027-04-16","00:00:00","2027-04-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-006609/24","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,13,14,"2027-04-01","00:00:00","2027-04-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-017254/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,26,32,"2027-07-03","00:00:00","2027-08-11","23:59:00","40 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016970/25","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,24,26,"2027-06-14","00:00:00","2027-07-02","23:59:00","19 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016994/25","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2027,2027,32,43,"2027-08-12","00:00:00","2027-10-27","23:59:00","77 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016989/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,24,52,"2027-06-14","00:00:00","2027-12-31","23:59:00","201 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016954/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Hradec Králové hl.n.",2027,2027,30,52,"2027-08-01","00:00:00","2027-12-31","23:59:00","153 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016536/25","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2027,2027,30,31,"2027-08-01","00:00:00","2027-08-05","23:59:00","5 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-020313/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2028,2028,43,45,"2028-10-26","00:00:00","2028-11-06","23:59:00","12 x 6 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-020309/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2028,2028,48,48,"2028-11-27","00:00:00","2028-11-30","23:59:00","4 x 6 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Převýšov",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Převýšov","Choťovice",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Choťovice","Dobšice nad Cidlinou",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Dobšice nad Cidlinou","Velký Osek-Kanín",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Velký Osek-Kanín",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail","T","LT",null,null,"X",null,null," ,X,X",null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,5,5a,5b,6,7,7a,7b bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"záhlaví a zhlaví směr Nový Bydžov.",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"záhlaví a zhlaví směr Nové Město nad Cidlinou.",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Nové Město n. Cidl.",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Nové Město n. Cidl.","Káranice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Káranice","Dobřenice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Dobřenice","Praskačka",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Praskačka","Odb Plačice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Odb Plačice","Hradec Králové hl.n.",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017175/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2028,2028,7,9,"2028-02-15","00:00:00","2028-02-28","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2028,2028,11,28,"2028-03-16","00:00:00","2028-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L..",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2028,2028,9,11,"2028-03-01","00:00:00","2028-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2028,2028,5,48,"2028-02-01","00:00:00","2028-12-03","23:59:00","307 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2028,2028,50,52,"2028-12-17","00:00:00","2028-12-31","23:59:00","15 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,19,20,"2028-05-13","00:00:00","2028-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,19,20,"2028-05-13","00:00:00","2028-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,18,19,"2028-05-07","00:00:00","2028-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice.",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017131/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2028,2028,39,41,"2028-09-27","00:00:00","2028-10-10","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019018/21","Praha - Chocen - Česká Třebová","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,27,53,"2026-06-29","00:00:00","2026-12-31","23:59:00","186 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-011641/25","Regensburg - Plzen","< >","Plzeň hl.n.os.n.","Přeštice",2026,2026,24,26,"2026-06-14","00:00:00","2026-06-28","23:59:00","15 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003056/25","Regensburg - Plzen","< >","Ejpovice","Plzeň hl.n.os.n.",2026,2026,30,31,"2026-07-20","18:00:00","2026-07-30","06:00:00","10 x 6 hours","periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002607/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Vejprnice",2026,2026,29,53,"2026-07-18","00:00:00","2026-12-31","23:59:00","167 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002586/25","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,45,45,"2026-11-07","00:00:00","2026-11-08","23:59:00","2 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2027,2027,2,13,"2027-01-15","00:00:00","2027-04-01","23:59:00","77 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017672/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Výh Chotěšov",2027,2027,43,44,"2027-10-27","18:00:00","2027-11-04","06:00:00","8 x 6 hours","periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017664/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Výh Chotěšov",2027,2027,42,43,"2027-10-19","00:00:00","2027-10-26","23:59:00","8 x 12 hours","periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2027,2027,2,25,"2027-01-15","00:00:00","2027-06-25","23:59:00","162 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002814/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2027,2027,53,2,"2027-01-01","00:00:00","2027-01-14","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002608/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Vejprnice",2027,2027,53,2,"2027-01-01","00:00:00","2027-01-14","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311013","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311009","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311007","Bratislava - Štúrovo","< >","Dvory nad Žitavou","Dvory nad Žitavou",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 ",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311012","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311010","Kúty - Bratislava","< >","Malacky","Kúty",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","56TT2311011b","Kúty - Galanta","< >","Bratislava-Rača","Trnava",2025,2026,1,9,"2025-01-01T08:00:00",45658.333333333336,"2026-02-28T17:00:00","00:00:00","371 x 23h 59min every week","Periodical","signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + zvýšenie počtu oddielov AH v úseku Rača - Trnava",null,"N",null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","56TT2311008","Kúty - Galanta","< >","Šelpice","Boleráz",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č.1",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","56TT2311011a","Kúty - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","A13225","Zilina - Cierna nad Tisou","< >","Bánovce nad Ondavou","Humenné",2025,2026,44,23,"2025-11-01","00:01:00","2026-06-01","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Elektrifikácia a modernizácia staničných koľají a výhybiek a traťovej koľaje",null,"Y",null,"2025-12-09T10:06:30",null,null,"1,2,3,6,7"]
[null,"ŽSR",5625271,"Zilina - Cierna nad Tisou","< >","Spišská Nová Ves","Vydrník",2024,2026,31,31,"2024-08-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105,null,null,null,"2025-12-09T10:02:26",null,null,"1,2,3,7"]
[null,"ŽSR",5625274,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01","08:00:00","2026-06-30","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,null,null,"2025-12-09T10:04:57",null,null,6.7]
[null,"ŽSR",5625274,"Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01","08:00:00","2026-06-30","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y",null,"2025-12-09T10:04:57",null,null,"2,3,4,5"]
[null,"ŽSR","056KE2212131","Zilina - Cierna nad Tisou","< >","Veľký Horeš","Streda nad Bodrogom",2025,2026,18,27,"2025-05-01T08:00:00",45778.333333333336,"2026-06-30T16:00:00","16:00:00",null,"Periodical","miscellaneous",null,"LT",null,null,null,null,null,null,null,null,101,null,"Y",null,"2025-12-09T10:04:57",null,null,"1,5,6,7"]
[null,"ŽSR",5625272,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,1,14,"2024-01-01","08:00:00","2026-03-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,105,null,null,null,"2025-12-09T10:05:00",null,null,6.7]
[null,"ŽSR",5625275,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad-Tatry",2024,2026,14,31,"2024-04-01","08:00:00","2026-07-31","16:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"105, TK 1/2, Modernizácia",null,null,null,"2025-12-09T10:05:00"]
[null,"ŽSR",5626156,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad Tatry",2025,2028,9,4,"2025-03-02","08:00:00","2028-01-29","17:00:00",null,"Continuous","miscellaneous",null,"x","x",null,null,null,null,null,null,null,"Modernisation",null,"Y",null,"2025-12-09T10:05:00"]

{"sheet":"Graphic Overview","index":2,"n_rows":205,"n_cols":374,"rows_kept":205,"cut":false,"hidden":false,"merged":[[0,1,1,7],[2,9,2,39],[2,282,2,312],[2,99,2,128],[2,129,2,159],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,40,2,67],[2,68,2,98],[3,355,3,361],[3,362,3,368],[3,369,3,373],[2,343,2,373],[2,313,2,342],[3,348,3,354],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,341,3,347],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,33,3,39],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[3,68,3,74],[3,103,3,109],[3,110,3,116],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,138,3,144],[3,145,3,151],[3,152,3,158],[3,159,3,165],[3,166,3,172],[3,243,3,249],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,194,3,200],[3,201,3,207],[3,208,3,214],[3,215,3,221],[3,222,3,228],[3,229,3,235],[3,236,3,242],[3,285,3,291],[3,292,3,298],[3,299,3,305],[3,306,3,312],[3,313,3,319],[3,250,3,256],[3,257,3,263],[3,264,3,270],[3,271,3,277],[3,278,3,284]]}
[null,"RFC 9 Overview"]
[]
[null,null,null,null,null,null,2027,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Frankfurt - Karlsruhe",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,null,null,null,5,5,5,5,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Karlsruhe - Strasbourg"]
[null," "]
[]
[null,"Darmstadt - Nürnberg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Nürnberg - Passau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Nürnberg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,2,2,1,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Regensburg - Plzen",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Passau - Wels"]
[null," "]
[]
[null,"Karlsruhe - München",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"München - Salzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5]
[null," "]
[]
[null,"München - Regensburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null," "]
[]
[null,"Salzburg - Wels"]
[null," "]
[]
[null,"Wels - Linz"]
[null," "]
[]
[null,"Wels - Traun - Linz"]
[null," "]
[]
[null,"Linz - Wien (NRZ)"]
[null," "]
[]
[null,"Linz - Wien (GZ)"]
[null," "]
[]
[null,"Wien - Hegyeshalom"]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron"]
[null," "]
[]
[null,"Sopron - Györ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Hegyeshalom - Rajka"]
[null," "]
[]
[null,"Hegyeshalom-Ferencváros",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros-Szajol"]
[null," "]
[]
[null,"Ferencváros-Szajol (120)"]
[null," "]
[]
[null,"Szajol-Curtici"]
[null," "]
[]
[null,"Szajol - Biharkeresztes"]
[null," "]
[]
[null,"Arad - Simeria"]
[null," "]
[]
[null,"Arad - Craiova",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Simeria -  Brasov",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Bucuresti-Constanta"]
[null," "]
[]
[null,"Coslariu - Cluj Napoca"]
[null," "]
[]
[null,"Biharkeresztes - Cluj Napoca",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Curtici - Arad"]
[null," "]
[]
[null,"Wilhelmshaven - Bremen"]
[null," "]
[]
[null,"Bremerhaven - Bremen"]
[null," "]
[]
[null,"Bremen - Hannover",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Hannover - Magdeburg"]
[null," "]
[]
[null,"Magdeburg - Falkenberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Falkenberg - Dresden",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Hamburg - Magdeburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,2,2,2,2,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Rostock - Berlin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Berlin - Dresden",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Dresden - Děčín",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Děčín - Kolín"]
[null," "]
[]
[null,"Děčín - Praha-Libeň"]
[null," "]
[]
[null,"Praha - Chocen - Česká Třebová",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Hranice na Morave - Ostrava",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Plzen - Praha",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Zilina",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ostrava - Zilina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Zilina - Cierna nad Tisou",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kolín - Brno-Maloměřice"]
[null," "]
[]
[null,"Česká Třebová - Brno"]
[null," "]
[]
[null,"Brno - Břeclav"]
[null," "]
[]
[null,"Břeclav - Wien"]
[null," "]
[]
[null,"Břeclav - Kúty"]
[null," "]
[]
[null,"Kúty - Bratislava"]
[null," "]
[]
[null,"Bratislava - Rajka"]
[null," "]
[]
[null,"Bratislava - Štúrovo"]
[null," "]
[]
[null,"Nové Zámky - Komárom"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Štúrovo - Ferencváros"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Chocen - Hranice na Morave",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros - Kelebia"]
[null," "]
[]
[]
[]
[]
[null,"Error in *All day*, *Day* or *Night*"]
[null,"| 4730 | 4731 "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":66,"n_cols":23,"rows_kept":66,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Frankfurt - Karlsruhe",1,"< >","Continuous",26536,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Karlsruhe - Strasbourg",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Darmstadt - Nürnberg",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Nürnberg - Passau",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Nürnberg - Plzen",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Regensburg - Plzen",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["SNCF-R",87,"Passau - Wels",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["CFR",53,"Karlsruhe - München",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,"München - Salzburg",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"München - Regensburg",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Salzburg - Wels",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Wels - Linz",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Wels - Traun - Linz",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Linz - Wien (NRZ)",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Linz - Wien (GZ)",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"Wien - Hegyeshalom",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"Wien - Ebenfurth - Sopron",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Sopron - Györ",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Rajka - Hegyeshalom",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Hegyeshalom - Rajka",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Hegyeshalom-Ferencváros",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Ferencváros-Szajol",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Ferencváros-Szajol (120)",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Szajol-Curtici",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Szajol - Biharkeresztes",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Arad - Simeria",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Arad - Craiova",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Simeria -  Brasov",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Bucuresti-Constanta",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Coslariu - Cluj Napoca",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Biharkeresztes - Cluj Napoca",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Curtici - Arad",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Wilhelmshaven - Bremen",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Bremerhaven - Bremen",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Bremen - Hannover",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Hannover - Magdeburg",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Magdeburg - Falkenberg",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Falkenberg - Dresden",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Hamburg - Magdeburg",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Rostock - Berlin",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Berlin - Dresden",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Dresden - Děčín",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Děčín - Kolín",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Děčín - Praha-Libeň",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Praha - Chocen - Česká Třebová",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Hranice na Morave - Ostrava",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Plzen - Praha",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,"Hranice na Morave - Zilina",48,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,"Ostrava - Zilina",49,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,"Zilina - Cierna nad Tisou",50,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,"Kolín - Brno-Maloměřice",51,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,"Česká Třebová - Brno",52,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]
[null,null,"Brno - Břeclav",53]
[null,null,"Břeclav - Wien",54]
[null,null,"Břeclav - Kúty",55]
[null,null,"Kúty - Bratislava",56]
[null,null,"Bratislava - Rajka",57]
[null,null,"Bratislava - Štúrovo",58]
[null,null,"Nové Zámky - Komárom",59]
[null,null,"Kúty - Galanta",60]
[null,null,"Rajka - Hegyeshalom",61]
[null,null,"Štúrovo - Ferencváros",62]
[null,null,"Kúty - Galanta",63]
[null,null,"Chocen - Hranice na Morave",64]
[null,null,"Ferencváros - Kelebia",65]