{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":3,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":8,"n_cols":19,"rows_kept":8,"cut":false,"hidden":false,"merged":[[1,16,1,20],[2,17,2,18]]}
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Posession Indicator Tool"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Year","Week"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2025,1]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with RED = total closure on the section"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Section marked with YELLOW = reduced capacity on the section"]

{"sheet":"Schedule","index":1,"n_rows":2367,"n_cols":37,"rows_kept":2367,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,34,2,34],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof Day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID","Date of first publication","Date of last change","Lately announced","Weekdays","Re-routing possibilities"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"CFR",5326536,"Arad - Craiova","< >","Băile Herculane","Poarta Hm.",2026,2031,30,29,"21.07.2026","00:00:00","20.07.2031","23:59:00",1826,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326537,"Arad - Craiova","< >","Poarta Hm.","Caransebeş",2026,2031,30,29,"21.07.2026","00:00:00","20.07.2031","23:59:00",1826,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326538,"Arad - Craiova","< >","Caransebeş","Zăgujeni Hm.",2027,2032,7,7,"16.02.2027","00:00:00","15.02.2032","23:59:00",1826,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326539,"Arad - Craiova","< >","Câmpuri Surduc Hm.","Ilteu Hm.",2026,2026,33,36,"15.08.2026","00:00:00","31.08. 2026","23:59:00",17,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326540,"Arad - Craiova","< >","Ilteu Hm.","Săvârşin",2026,2026,33,36,"15.08. 2026","00:00:00","31.08. 2026","23:59:00",17,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326541,"Arad - Craiova","< >",null,"Târgu Jiu",2026,2026,19,36,"2026-05-06","00:00:00","2026-08-31","23:59:00",118,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326542,"Arad - Craiova","< >","Bumbeşti Hm.","Valea Sadului Hm.",2027,2027,13,30,"2027-04-01","00:00:00","2027-07-31","23:59:00",122,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326543,"Arad - Craiova","< >","Valea Sadului Hm.","Meri",2027,2027,9,35,"2027-03-01","00:00:00","2027-08-31","23:59:00",184,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326544,"Arad - Craiova","< >","Valea Sadului Hm.","Meri",2027,2027,9,30,"2027-03-01","00:00:00","2027-07-31","23:59:00",153,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326545,"Arad - Craiova","< >","Valea Sadului Hm.","Meri",2027,2027,9,35,"2027-03-01","00:00:00","2027-08-31","23:59:00",184,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326546,"Arad - Craiova","< >","Meri","Lainici Hm.",2027,2027,9,33,"2027-03-01","00:00:00","2027-08-16","23:59:00",169,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326547,"Arad - Craiova","< >","Meri","Lainici Hm.",2027,2027,9,30,"2027-03-01","00:00:00","2027-07-31","23:59:00",153,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326548,"Arad - Craiova","< >","Corlăteşti Hm.","Zănoaga Hm.",2028,2028,20,29,"2028-05-16","00:00:00","2028-07-20","23:59:00",66,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326549,"Arad - Craiova","< >","Meri","Lainici Hm.",2027,2027,13,30,"2027-04-01","00:00:00","2027-07-31","23:59:00",122,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326550,"Arad - Craiova","< >","Meri","Lainici Hm.",2027,2027,9,39,"2027-03-01","00:00:00","2027-09-30","23:59:00",214,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326551,"Arad - Craiova","< >","Lainici Hm.","Pietrele Albe Hm.",2027,2027,13,48,"2027-04-01","00:00:00","2027-11-30","23:59:00",244,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326552,"Arad - Craiova","< >","Pietrele Albe Hm.","Strâmbuţa Hm.",2027,2027,13,35,"2027-04-01","00:00:00","2027-08-31","23:59:00",153,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326553,"Arad - Craiova","< >","Strâmbuţa Hm.","Livezeni Hm.",2027,2027,17,35,"2027-05-01","00:00:00","2027-08-31","23:59:00",123,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326554,"Arad - Craiova","< >","Strâmbuţa Hm.","Livezeni Hm.",2027,2027,17,35,"2027-05-01","00:00:00","2027-08-31","23:59:00",123,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326555,"Arad - Craiova","< >",null,"Musculeşti",2027,2027,9,52,"01.03.2027","00:00:00","2027-12-31","23:59:00",306,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326556,"Arad - Craiova","< >","Meri","Lainici Hm.",2026,2027,44,52,"2026-11-01","00:00:00","2027-12-31","23:59:00",426,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326557,"Arad - Craiova","< >","Meri","Lainici Hm.",2027,2027,13,30,"2027-04-01","00:00:00","2027-07-31","23:59:00",122,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326558,"Arad - Craiova","< >","Lainici Hm.","Pietrele Albe Hm.",2026,2027,44,52,"2026-11-01","00:00:00","2027-12-31","23:59:00",426,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326559,"Arad - Craiova","< >","Craiova","Cernele",2027,2028,19,6,"15.05.2027","00:00:00","10.02.2028","23:59:00",272,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326560,"Arad - Craiova","< >","Cernele","Işalniţa",2027,2028,20,27,"17.05.2027","00:00:00","05.07.2028","23:59:00",416,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326561,"Arad - Craiova","< >","Işalniţa","Coţofeni Hm.",2027,2028,19,44,"15.05.2027","00:00:00","05.11.2028","23:59:00",541,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326562,"Arad - Craiova","< >","Coţofeni Hm.","Răcari Hm.",2027,2028,19,52,"15.05.2027","00:00:00","28.12.2028","23:59:00",594,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326563,"Arad - Craiova","< >","Răcari Hm.","Filiaşi",2027,2028,19,41,"15.05.2027","00:00:00","12.10.2028","23:59:00",517,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326564,"Arad - Craiova","< >","Caransebeş","Zăgujeni Hm.",2026,2027,49,47,"2026-12-01","00:00:00","2027-11-27","23:59:00",362,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326565,"Arad - Craiova","< >","Jena Hm.","Găvojdia Hm.",2027,2027,28,29,"2027-07-15","00:00:00","2027-07-21","23:59:00",7,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326566,"Arad - Craiova","< >","Caransebeş","Balta Sărată Hm.",2027,2027,38,39,"2027-09-22","00:00:00","2027-09-28","23:59:00",7,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326567,"Arad - Craiova","< >",null,"Caransebeş",2027,2027,38,39,"2027-09-22","00:00:00","2027-09-28","23:59:00",7,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326568,"Arad - Craiova","< >","Caransebeş","Cornuţel Banat Hm.",2027,2027,38,39,"2027-09-22","00:00:00","2027-09-28","23:59:00",7,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326569,"Arad - Craiova","< >","Caransebeş","Caransebeş Triaj",2027,2027,38,39,"2027-09-22","00:00:00","2027-09-28","23:59:00",7,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326570,"Arad - Craiova","< >","Timişoara Nord","Ronaţ Triaj Gr. D",2026,2027,46,41,"2026-11-12","00:00:00","2027-10-15","23:59:00",338,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326571,"Arad - Craiova","< >","Timişoara Nord","Ronaţ Triaj Gr. D",2027,2027,42,43,"2027-10-22","00:00:00","2027-10-29","23:59:00",8,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326572,"Arad - Craiova","< >","Caransebeş","Caransebeş Ţiglarie Hm.",2026,2027,43,6,"2026-10-20","00:00:00","2027-02-12","23:59:00",116,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326573,"Arad - Craiova","< >","Caransebeş","Caransebeş Ţiglarie Hm.",2027,2027,9,24,"2027-03-03","00:00:00","2027-06-17","23:59:00",107,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326574,"Arad - Craiova","< >","Timişoara Est","Remetea Mică Hm",2027,2028,41,23,"2027-10-15","00:00:00","2028-06-10","23:59:00",240,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326575,"Arad - Craiova","< >","Timişoara Nord","Ronaţ Triaj Gr. D",2027,2027,40,41,"2027-10-08","00:00:00","2027-10-15","23:59:00",8,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326576,"Arad - Craiova","< >","Timişoara Nord","Ronaţ Triaj Gr. D",2027,2028,41,23,"2027-10-15","00:00:00","2028-06-10","23:59:00",240,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326577,"Arad - Craiova","< >","Timişoara Nord","Ronaţ Triaj Gr. D",2026,2027,46,41,"2026-11-12","00:00:00","2027-10-15","23:59:00",338,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326578,"Arad - Craiova","< >","Sânandrei Hm.","Aradu Nou",2027,2027,21,38,"25.05.2027","00:00:00","25.09.2027","23:59:00",124,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326579,"Arad - Craiova","< >","Aradu Nou","Zădăreni Hm.",2027,2027,21,38,"25.05.2027","00:00:00","25.09.2027","23:59:00",124,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326580,"Arad - Craiova","< >","Sânandrei Hm.","Periam Hm.",2027,2027,21,38,"25.05.2027","00:00:00","25.09.2027","23:59:00",124,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326581,"Arad - Craiova","< >","Zăgujeni Hm.","Căvăran Hm.",2027,2027,7,29,"2027-02-15","00:00:00","2027-07-21","23:59:00",157,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326582,"Arad - Craiova","< >","Zăgujeni Hm.","Căvăran Hm.",2027,2028,29,44,"2027-07-21","00:00:00","2028-10-30","23:59:00",468,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326583,"Arad - Craiova","< >","Căvăran Hm.","Găvojdia Hm.",2027,2028,47,44,"2027-11-27","00:00:00","2028-10-30","23:59:00",339,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326584,"Arad - Craiova","< >","Găvojdia Hm.","Lugoj",2027,2028,47,44,"2027-11-27","00:00:00","2028-10-30","23:59:00",339,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326585,"Arad - Craiova","< >","Zăgujeni Hm.","Căvăran Hm.",2025,2027,49,7,"2025-12-06","00:00:00","2027-02-15","23:59:00",437,"Continuous","Track & Rail",null,null,"LT","S",null,null,null,null,null,null,null,null,null,null,"2026-08-12"]
[null,"CFR",5326073,"Arad - Craiova","< >","Aradu Nou","Arad",2026,2027,43,17,"2026-10-23","00:00:00","2027-04-26","23:59:00","186d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-22"]
[null,"CFR",5326147,"Arad - Craiova","< >","Aradul Nou",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525809,"Arad - Craiova","< >","Aradul Nou","Arad",2026,2027,19,1,"2026-05-08","00:00:00","2027-01-08","23:59:00","246d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-01-10"]
[null,"CFR",5525808,"Arad - Craiova","< >","Aradul Nou ","Arad",2026,2026,31,32,"2026-08-01","00:00:00","2026-08-08","23:59:00","8d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326134,"Arad - Craiova","< >","Baile Calacea","Orțișoara",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326133,"Arad - Craiova","< >","Băile Calacea",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326039,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326102,"Arad - Craiova","< >","Belinț",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326103,"Arad - Craiova","< >","Belinț","Chizătău",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326115,"Arad - Craiova","< >","Belinț","Chizătău",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326117,"Arad - Craiova","< >","Belinț","Topolovat",2026,2027,45,22,"2026-11-03","00:00:00","2027-06-02","23:59:00","212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326080,"Arad - Craiova","< >","Caransebes",null,2026,2027,28,40,"2026-07-07","00:00:00","2027-10-04","23:59:00","455d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-13"]
[null,"CFR",5326021,"Arad - Craiova","< >","Caransebeș","Caransebeș Tiglărie",2026,2026,28,44,"2026-07-07","00:00:00","2026-11-01","23:59:00","118d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326023,"Arad - Craiova","< >","Caransebes ","Zăgujeni",2025,2026,31,36,"2025-07-30","00:00:00","2026-09-01","23:59:00","399d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-11-13"]
[null,"CFR",5326090,"Arad - Craiova","< >","Căvăran",null,2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5326092,"Arad - Craiova","< >","Căvăran","Găvojdia",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5326040,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-24"]
[null,"CFR",5326104,"Arad - Craiova","< >","Chizătău","Topolovat",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326116,"Arad - Craiova","< >","Chizătău","Topolovat",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326094,"Arad - Craiova","< >","Găvojdia",null,2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-11-08"]
[null,"CFR",5326095,"Arad - Craiova","< >","Găvojdia",null,2026,2026,12,36,"2026-03-19","00:00:00","2026-09-01","23:59:00","167d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-25"]
[null,"CFR",5326096,"Arad - Craiova","< >","Găvojdia","Lugoj",2026,2027,36,40,"2026-09-02","00:00:00","2027-10-04","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5326078,"Arad - Craiova","< >","Glogovăț","Arad",2027,2027,39,41,"2027-10-01","00:00:00","2027-10-17","23:59:00","17d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-25"]
[null,"CFR",5326148,"Arad - Craiova","< >","Glogovăț","Arad",2026,2026,4,38,"2026-01-23","00:00:00","2026-09-18","23:59:00","239d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-26"]
[null,"CFR",5326149,"Arad - Craiova","< >","Glogovăț","Arad",2026,2027,38,2,"2026-09-18","00:00:00","2027-01-17","23:59:00","122d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5525813,"Arad - Craiova","< >","Glogovăț ","Arad",2026,2026,19,32,"2026-05-08","00:00:00","2026-08-08","23:59:00","93d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5326038,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-28"]
[null,"CFR",5326101,"Arad - Craiova","< >","Jabăr","Belinț",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5326114,"Arad - Craiova","< >","Jabăr","Belinț",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-11-28"]
[null,"CFR",5326037,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-24","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-11-29"]
[null,"CFR",5326100,"Arad - Craiova","< >","Lugoj","Jabăr",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5326113,"Arad - Craiova","< >","Lugoj","Jabăr",2026,2026,35,45,"2026-08-24","00:00:00","2026-11-03","23:59:00","72d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-01"]
[null,"CFR",5326118,"Arad - Craiova","< >","Lugoj – Belint","Lugoj – Belint",2026,2027,45,14,"2026-11-03","00:00:00","2027-04-06","23:59:00","155d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-19"]
[null,"CFR",5326068,"Arad - Craiova","< >","Orțișoara",null,2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-02"]
[null,"CFR",5326076,"Arad - Craiova","< >","Orțișoara","Aradu Nou",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-19"]
[null,"CFR",5326136,"Arad - Craiova","< >","Orțișoara",null,2025,2027,43,4,"2025-10-24","00:00:00","2027-01-25","23:59:00","459d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5326137,"Arad - Craiova","< >","Orțișoara","Vinga",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-02"]
[null,"CFR",5525814,"Arad - Craiova","< >","Orțișoara","Aradul Nou",2026,2026,31,37,"2026-08-01","00:00:00","2026-09-08","23:59:00","39d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-05"]
[null,"CFR",5326108,"Arad - Craiova","< >","Recaș",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326109,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2026,39,34,"2025-09-26","00:00:00","2026-08-17","23:59:00","326d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-07-24"]
[null,"CFR",5326111,"Arad - Craiova","< >","Recaș","Remetea Mare",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326097,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2026,27,43,"2025-07-03","00:00:00","2026-10-23","23:59:00","478d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326110,"Arad - Craiova","< >","Remetea Mare",null,2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-06"]
[null,"CFR",5326112,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2025,2027,48,7,"2025-11-26","00:00:00","2027-02-17","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326119,"Arad - Craiova","< >","Remetea Mare","Timisoara Est",2027,2027,15,18,"2027-04-15","00:00:00","2027-05-04","23:59:00","20d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326069,"Arad - Craiova","< >","Ronat Triaj Gr.D","Orțișoara",2026,2026,38,39,"2026-09-18","00:00:00","2026-09-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-07"]
[null,"CFR",5326128,"Arad - Craiova","< >","Ronat Triaj Gr.D","Sânandrei",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-07"]
[null,"CFR",5326062,"Arad - Craiova","< >","Ronaț Triaj Gr.D","Ronaț Triaj Gr.D",2027,2027,1,2,"2027-01-05","00:00:00","2027-01-12","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2024-03-21"]
[null,"CFR",5326142,"Arad - Craiova","< >","Sag",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-08"]
[null,"CFR",5326143,"Arad - Craiova","< >","Șag","Valea Viilor",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-07"]
[null,"CFR",5525803,"Arad - Craiova","< >","Șag ","Valea Viilor",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-09"]
[null,"CFR",5326130,"Arad - Craiova","< >","Sânandrei",null,2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326131,"Arad - Craiova","< >","Sânandrei","Baile Calacea",2025,2026,43,38,"2025-10-24","00:00:00","2026-09-18","23:59:00","330d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326048,"Arad - Craiova","< >","Timișoara Est","Remetea Mică",2025,2026,23,36,"2025-06-02","00:00:00","2026-09-02","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-13"]
[null,"CFR",5326124,"Arad - Craiova","< >","Timișoara Est","Timișoara Est",2024,2026,35,45,"2024-09-01","00:00:00","2026-11-02","23:59:00","793d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-12"]
[null,"CFR",5326057,"Arad - Craiova","< >","Timișoara Nord","Timișoara Nord",2026,2027,18,2,"2026-05-01","00:00:00","2027-01-12","23:59:00","257d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-30"]
[null,"CFR",5326061,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2026,44,45,"2026-10-27","00:00:00","2026-11-02","23:59:00","7d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-12"]
[null,"CFR",5326126,"Arad - Craiova","< >","Timișoara Nord","Ronaț Triaj Gr.D",2026,2027,23,2,"2026-06-01","00:00:00","2027-01-12","23:59:00","226d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-16"]
[null,"CFR",5326059,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14"]
[null,"CFR",5326060,"Arad - Craiova","< >","Timișoara Nord ","Timișoara Nord ",2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-06-14"]
[null,"CFR",5326127,"Arad - Craiova","< >","Timișoara Nord ",null,2026,2027,23,35,"2026-06-01","00:00:00","2027-09-01","23:59:00","458d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-14"]
[null,"CFR",5326105,"Arad - Craiova","< >","Topolovat",null,2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326107,"Arad - Craiova","< >","Topolovat","Recas",2025,2027,39,14,"2025-09-26","00:00:00","2027-04-06","23:59:00","558d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22"]
[null,"CFR",5326075,"Arad - Craiova","< >","Valea Viilor","Arad",2027,2027,3,4,"2027-01-18","00:00:00","2027-01-25","23:59:00","8d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-14"]
[null,"CFR",5326145,"Arad - Craiova","< >","Valea Viilor","Aradul Nou",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5525806,"Arad - Craiova","< >","Valea Viilor ","Aradul Nou",2026,2026,30,32,"2026-07-25","00:00:00","2026-08-08","23:59:00","15d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326139,"Arad - Craiova","< >","Vinga",null,2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326140,"Arad - Craiova","< >","Vinga","Sag",2026,2027,4,4,"2026-01-23","00:00:00","2027-01-25","23:59:00","368d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-19"]
[null,"CFR",5326088,"Arad - Craiova","< >","Zăgujeni","Căvăran",2026,2027,18,40,"2026-05-03","00:00:00","2027-10-04","23:59:00","520d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-13"]
[null,"CFR",5326586,"Biharkeresztes - Cluj Napoca","< >","Cluj Napoca","Aghireş",2024,2026,27,53,"2024-07-01","00:00:00","2026-12-29","23:59:00",912,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326587,"Biharkeresztes - Cluj Napoca","< >","Poieni Hm.","Vadu Crişului Hm.",2026,2027,19,52,"10.05.2026","00:00:00","30.12.2027","23:59:00",600,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326588,"Biharkeresztes - Cluj Napoca","< >","Cluj Napoca","Aghireş",2026,2027,53,52,"2026-12-29","00:00:00","2027-12-30","23:59:00",367,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326589,"Biharkeresztes - Cluj Napoca","< >","Aghireş","Poieni",2026,2028,30,38,"2026-07-26","00:00:00","2028-09-19","23:59:00",787,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326590,"Biharkeresztes - Cluj Napoca","< >","Vadu Crişului Hm.","Aleşd",2024,2027,16,52,"15.04.2024","00:00:00","30.12.2027","23:59:00",1355,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326591,"Biharkeresztes - Cluj Napoca","< >","Aleşd","Episcopia Bihor Frontiera",2024,2027,24,52,"11.06.2024","00:00:00","30.12.2027","23:59:00",1298,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326592,"Biharkeresztes - Cluj Napoca","< >","Giurgiu Nord","Russe",2027,2027,14,50,"05.04.2027","00:00:00","13.12.2027",1.04097222222222,253,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5525760,"Biharkeresztes - Cluj Napoca","< >"," Baciu Triaj","Mera",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-09"]
[null,"CFR",5525728,"Biharkeresztes - Cluj Napoca","< >","Alesd","Oradea",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2022-12-15"]
[null,"CFR",5325986,"Biharkeresztes - Cluj Napoca","< >","Alesd","Telechiu",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5525742,"Biharkeresztes - Cluj Napoca","< >","Aleșd","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5525768,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-16"]
[null,"CFR",5325966,"Biharkeresztes - Cluj Napoca","< >","Braisoru",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325976,"Biharkeresztes - Cluj Napoca","< >","Bratca","Suncuius",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325975,"Biharkeresztes - Cluj Napoca","< >","Bratca ",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-16"]
[null,"CFR",5325973,"Biharkeresztes - Cluj Napoca","< >","Bulz",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5325974,"Biharkeresztes - Cluj Napoca","< >","Bulz","Bratca",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5325979,"Biharkeresztes - Cluj Napoca","< >","Ciucea",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5325980,"Biharkeresztes - Cluj Napoca","< >","Ciucea","Piatra Craiului",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-19"]
[null,"CFR",5525757,"Biharkeresztes - Cluj Napoca","< >","Cluj ","Baciu Triaj",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17"]
[null,"CFR",5525739,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Oradea Vest",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525747,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor","Frontieră Ungaria",2026,2026,40,53,"2026-10-01","00:00:00","2026-12-31","23:59:00","92d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326012,"Biharkeresztes - Cluj Napoca","< >","Episcopia Bihor",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525766,"Biharkeresztes - Cluj Napoca","< >","Gârbău","Aghireș",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525769,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325967,"Biharkeresztes - Cluj Napoca","< >","Huedin",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-20"]
[null,"CFR",5525763,"Biharkeresztes - Cluj Napoca","< >","Mera","Gârbău",2026,2026,18,36,"01.05.2026","00:00:00","31.08.2026","23:59:00","123d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5525734,"Biharkeresztes - Cluj Napoca","< >","Oradea","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-20"]
[null,"CFR",5326011,"Biharkeresztes - Cluj Napoca","< >","Oradea","Oradea",2025,2027,50,19,"2025-12-11","00:00:00","2027-05-10","23:59:00","516d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525746,"Biharkeresztes - Cluj Napoca","< >","Oradea ","Episcopia Bihor",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525745,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326004,"Biharkeresztes - Cluj Napoca","< >","Oradea Est",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326006,"Biharkeresztes - Cluj Napoca","< >","Oradea Est","Oradea",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525730,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Oradea",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525740,"Biharkeresztes - Cluj Napoca","< >","Oradea Est ","Ceica",2024,2026,5,53,"2024-02-01","00:00:00","2026-12-31","23:59:00","1065d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325999,"Biharkeresztes - Cluj Napoca","< >","Osorhei",null,2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5326001,"Biharkeresztes - Cluj Napoca","< >","Osorhei","Oradea Est",2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5525744,"Biharkeresztes - Cluj Napoca","< >","Oșorhei","Oradea Est",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325972,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului","Bulz",2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5325981,"Biharkeresztes - Cluj Napoca","< >","Piatra Craiului",null,2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5525727,"Biharkeresztes - Cluj Napoca","< >","Poieni","Alesd",2023,2026,50,50,"2023-12-12","00:00:00","2026-12-12","23:59:00","1097d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5525767,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2022-12-21"]
[null,"CFR",5325965,"Biharkeresztes - Cluj Napoca","< >","Poieni",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2022-12-21"]
[null,"CFR",5325978,"Biharkeresztes - Cluj Napoca","< >","Poieni","Ciucea",2024,2027,36,23,"2024-09-06","00:00:00","2027-06-10","23:59:00","1008d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5525770,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325968,"Biharkeresztes - Cluj Napoca","< >","Stana",null,2024,2026,1,34,"2024-01-01","00:00:00","2026-08-18","23:59:00","961d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5325969,"Biharkeresztes - Cluj Napoca","< >","Suncuius","Vadul Crisului",2024,2027,16,23,"2024-04-15","00:00:00","2027-06-10","23:59:00","1152d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5325977,"Biharkeresztes - Cluj Napoca","< >","Suncuius",null,2024,2027,34,23,"2024-08-20","00:00:00","2027-06-10","23:59:00","1025d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11"]
[null,"CFR",5525736,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2026,22,40,"2025-06-01","00:00:00","2026-10-01","23:59:00","488d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325989,"Biharkeresztes - Cluj Napoca","< >","Telechiu","Tileagd",2025,2027,41,23,"2025-10-11","00:00:00","2027-06-10","23:59:00","608d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5525743,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Oșorhei",2026,2026,12,40,"2026-03-16","00:00:00","2026-10-01","23:59:00","200d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,null,null,null,null,"2023-01-11"]
[null,"CFR",5325992,"Biharkeresztes - Cluj Napoca","< >","Tileagd",null,2025,2027,41,19,"2025-10-11","00:00:00","2027-05-10","23:59:00","577d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5325995,"Biharkeresztes - Cluj Napoca","< >","Tileagd","Osorhei",2025,2027,42,22,"2025-10-19","00:00:00","2027-06-02","23:59:00","592d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2024-08-27"]
[null,"CFR",5326593,"Simeria -  Brasov","< >","Feldioara Hm.","Apaţa",2027,2027,17,17,"26.04.2027","00:00:00","30.04.2027","23:59:00",5,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326594,"Simeria -  Brasov","< >","Feldioara Hm.","Apaţa",2027,2027,48,51,"03.12.2027","00:00:00","24.12.2027","23:59:00",22,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326595,"Simeria -  Brasov","< >","Racoş Hm.","Rupea",2022,2027,36,46,"06.09.2022","00:00:00","15.11.2027","23:59:00",1897,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326596,"Simeria -  Brasov","< >","Rupea","Caţa Hm.",2026,2027,45,46,"03.11.2026","00:00:00","17.11.2027","23:59:00",380,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure"]
[null,"CFR",5326597,"Simeria -  Brasov","< >","Braşov","Stupini Hm.",2026,2027,4,52,"20.01.2026","00:00:00","31.12.2027","23:59:00",711,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326598,"Simeria -  Brasov","< >","Stupini Hm.","Bod Hm.",2026,2026,30,43,"24.07.2026","00:00:00","21.10.2026","23:59:00",90,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326599,"Simeria -  Brasov","< >","Stupini Hm.","Bod Hm.",2026,2028,43,47,"21.10.2026","00:00:00","23.11.2028","23:59:00",765,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326600,"Simeria -  Brasov","< >","Bod Hm.","Feldioara Hm.",2026,2027,43,23,"22.10.2026","00:00:00","11.06.2027","23:59:00",233,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326601,"Simeria -  Brasov","< >","Bod Hm.","Feldioara Hm.",2027,2027,23,52,"11.06.2027","00:00:00","31.12.2027","23:59:00",204,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326602,"Simeria -  Brasov","< >","Feldioara Hm.","Apaţa",2023,2026,28,43,"10.07.2023","00:00:00","21.10.2026","23:59:00",1200,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326603,"Simeria -  Brasov","< >","Feldioara Hm.","Apaţa",2026,2027,43,17,"22.10.2026","00:00:00","30.04.2027","23:59:00",191,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326604,"Simeria -  Brasov","< >","Feldioara Hm.","Apaţa",2027,2027,17,51,"01.05.2027","00:00:00","24.12.2027","23:59:00",238,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326605,"Simeria -  Brasov","< >","Augustin Hm.","Racoş Hm.",2025,2027,51,11,"18.12.2025","00:00:00","15.03.2027","23:59:00",453,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326606,"Simeria -  Brasov","< >","Caţa Hm.","Beia Hm.",2025,2027,4,8,"20.01.2025","00:00:00","25.02.2027","23:59:00",767,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326607,"Simeria -  Brasov","< >","Caţa Hm.","Beia Hm.",2027,2028,8,12,"26.02.2027","00:00:00","20.03.2028","23:59:00",389,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326608,"Simeria -  Brasov","< >","Beia Hm.","Mureni Hm.",2025,2027,10,26,"06.03.2025","00:00:00","28.06.2027","23:59:00",845,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326609,"Simeria -  Brasov","< >","Beia Hm.","Mureni Hm.",2027,2029,26,14,"29.06.2027","00:00:00","03.04.2029","23:59:00",645,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326610,"Simeria -  Brasov","< >","Mureni Hm.","Vânători Hm.",2026,2029,35,14,"26.08.2026","00:00:00","03.04.2029","23:59:00",952,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326611,"Simeria -  Brasov","< >","Vânători Hm.","Albeşti Târnava Hm.",2026,2027,35,52,"26.08.2026","00:00:00","31.12.2027","23:59:00",493,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326612,"Simeria -  Brasov","< >","Albeşti Târnava Hm.","Sighişoara",2026,2027,53,26,"31.12.2026","00:00:00","28.06.2027","23:59:00",180,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5326613,"Simeria -  Brasov","< >","Albeşti Târnava Hm.","Sighişoara",2027,2027,26,52,"29.06.2027","00:00:00","31.12.2027","23:59:00",186,"Continuous","Track & Rail",null,null,"LT","S"]
[null,"CFR",5325917,"Simeria -  Brasov","< >","Apata","Augustin",2025,2026,46,32,"2025-11-10","00:00:00","2026-08-03","23:59:00","267d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-14"]
[null,"CFR",5325912,"Simeria -  Brasov","< >","Apața",null,2026,2026,17,33,"2026-04-20","00:00:00","2026-08-14","23:59:00","117d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5325913,"Simeria -  Brasov","< >","Apața",null,2026,2026,33,44,"2026-08-15","00:00:00","2026-10-30","23:59:00","77d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5325914,"Simeria -  Brasov","< >","Apața",null,2026,2027,44,28,"2026-10-31","00:00:00","2027-07-15","23:59:00","258d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5325915,"Simeria -  Brasov","< >","Apața",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-04"]
[null,"CFR",5525665,"Simeria -  Brasov","< >","Archita","Vînători ",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5525712,"Simeria -  Brasov","< >","Archita","Vânători ",2025,2026,51,7,"2025-12-21","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-05"]
[null,"CFR",5325938,"Simeria -  Brasov","< >","Archita ","Vînători ",2027,2028,43,8,"2027-10-26","00:00:00","2028-02-26","23:59:00","124d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-05"]
[null,"CFR",5325937,"Simeria -  Brasov","< >","Beia","Mureni",2026,2027,10,43,"2026-03-05","00:00:00","2027-10-25","23:59:00","600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5525659,"Simeria -  Brasov","< >","Beia","Mureni",2023,2026,44,40,"30.10.2023","00:00:00","30.09.2026","23:59:00","1067d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-09"]
[null,"CFR",5325892,"Simeria -  Brasov","< >","Bod",null,2025,2027,30,28,"2025-07-23","00:00:00","2027-07-15","23:59:00","723d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,2,3",1]
[null,"CFR",5325893,"Simeria -  Brasov","< >","Bod",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5325897,"Simeria -  Brasov","< >","Bod","Feldioara",2026,2027,19,48,"2026-05-06","00:00:00","2027-12-05","23:59:00","579d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"5,6,7",1]
[null,"CFR",5325898,"Simeria -  Brasov","< >","Bod","Feldioara",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"6,7",1]
[null,"CFR",5325874,"Simeria -  Brasov","< >","Brașov",null,2025,2027,46,8,"2025-11-16","00:00:00","2027-02-28","23:59:00","470d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"1,7",1]
[null,"CFR",5325875,"Simeria -  Brasov","< >","Brașov",null,2027,2027,9,28,"2027-03-01","00:00:00","2027-07-15","23:59:00","137d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-10",null,null,"4,5",1]
[null,"CFR",5325876,"Simeria -  Brasov","< >","Brașov",null,2027,2027,28,48,"2027-07-16","00:00:00","2027-12-05","23:59:00","143d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4",1]
[null,"CFR",5325879,"Simeria -  Brasov","< >","Brașov","Stupini",2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5,6,7",1]
[null,"CFR",5325880,"Simeria -  Brasov","< >","Brașov","Stupini",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325929,"Simeria -  Brasov","< >","Cata","Rupea",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"2,3",1]
[null,"CFR",5325931,"Simeria -  Brasov","< >","Cata",null,2026,2026,3,42,"2026-01-15","00:00:00","2026-10-15","23:59:00","274d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"3,4",1]
[null,"CFR",5325932,"Simeria -  Brasov","< >","Cata",null,2026,2027,42,7,"2026-10-15","00:00:00","2027-02-16","23:59:00","125d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"4,5",1]
[null,"CFR",5325934,"Simeria -  Brasov","< >","Cata","Beia",2026,2027,3,7,"2026-01-15","00:00:00","2027-02-16","23:59:00","398d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325935,"Simeria -  Brasov","< >","Cata","Beia",2027,2027,7,43,"2027-02-17","00:00:00","2027-10-25","23:59:00","251d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,5,6,7",1]
[null,"CFR",5525657,"Simeria -  Brasov","< >","Cata","Rupea",2023,2026,5,50,"02.02.2023","00:00:00","12.12.2026","23:59:00","1410d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"5,6,7",1]
[null,"CFR",5525663,"Simeria -  Brasov","< >","Cața","Archita",2026,2026,40,50,"01.10.2026","00:00:00","12.12.2026","23:59:00","73d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525703,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5525710,"Simeria -  Brasov","< >","Cața","Archita",2025,2026,51,7,"21.12.2025","00:00:00","10.02.2026","23:59:00","52d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"one track closed and the other one with speed restriction",null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325867,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,30,33,"2026-07-24","00:00:00","2026-08-14","23:59:00","22d","Continuous","Track & Rail","T",null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325902,"Simeria -  Brasov","< >","Feldioara",null,2026,2027,17,28,"2026-04-23","00:00:00","2027-07-15","23:59:00","449d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325903,"Simeria -  Brasov","< >","Feldioara",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"CFR",5325907,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2026,33,49,"2026-08-15","00:00:00","2026-11-30","23:59:00","108d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325908,"Simeria -  Brasov","< >","Feldioara","Apața",2026,2027,49,48,"2026-11-30","00:00:00","2027-12-05","23:59:00","371d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325909,"Simeria -  Brasov","< >","Feldioara","Apața",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,5,6,7",1]
[null,"CFR",5325941,"Simeria -  Brasov","< >","Mureni","Vînători",2025,2027,35,43,"2025-08-30","00:00:00","2027-10-25","23:59:00","787d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-23",null,null,"6,7",1]
[null,"CFR",5525666,"Simeria -  Brasov","< >","Mureni","Vînători",2022,2026,45,40,"09.11.2022","00:00:00","30.09.2026","23:59:00","1422d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,7",1]
[null,"CFR",5325927,"Simeria -  Brasov","< >","Rupea","Cata",2026,2026,31,38,"2026-07-28","00:00:00","2026-09-15","23:59:00","50d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"6,7",1]
[null,"CFR",5325954,"Simeria -  Brasov","< >","Sighișoara",null,2024,2027,34,50,"2024-08-21","00:00:00","2027-12-15","23:59:00","1212d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,5,7",1]
[null,"CFR",5325956,"Simeria -  Brasov","< >","Sighișoara",null,2023,2027,41,43,"2023-10-11","00:00:00","2027-10-25","23:59:00","1476d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-02",null,null,"6,7",1]
[null,"CFR",5325957,"Simeria -  Brasov","< >","Sighișoara",null,2023,2028,41,8,"2023-10-11","00:00:00","2028-02-26","23:59:00","1600d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-11",null,null,"1,2,3,7",1]
[null,"CFR",5325884,"Simeria -  Brasov","< >","Stupini",null,2025,2027,44,48,"2025-10-27","00:00:00","2027-12-05","23:59:00","770d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"3,4",1]
[null,"CFR",5325885,"Simeria -  Brasov","< >","Stupini",null,2027,2027,9,48,"2027-03-01","00:00:00","2027-12-05","23:59:00","280d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2025-01-22",null,null,"4,5",1]
[null,"CFR",5325889,"Simeria -  Brasov","< >","Stupini","Bod",2026,2027,14,48,"2026-04-01","00:00:00","2027-12-05","23:59:00","614d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-12",null,null,"1,2,3,4,6,7",1]
[null,"CFR",5325946,"Simeria -  Brasov","< >","Vînători",null,2026,2028,20,8,"2026-05-11","00:00:00","2028-02-26","23:59:00","657d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-01-17",null,null,"1,6,7",1]
[null,"CFR",5525667,"Simeria -  Brasov","< >","Vînători","Albești",2023,2026,24,20,"16.06.2023","00:00:00","12.05.2026","23:59:00","1062d","Continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,null,null,null,null,"2023-06-01",null,null,"1,4,5,6,7",1]
[null,"CFR",5326614,"Bucuresti - Giugiu","< >","Bucureşti Progresu","Giurgiu Fr.",2026,2027,36,52,"01.09.2026","00:00:00","31.12.2027","23:59:00",487,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"CFR",5326615,"Videle - Giurgiu","< >","Giurgiu Nord","Russe",2027,2027,18,50,"2027-05-04","00:00:00","13/12/2027",1.04097222222222,224,"Continuous","Track & Rail","T",null,null,null,null,null,"C,,","R,,",null,null,null,"Total closure",null,null,"2026-08-12"]
[null,"DB InfraGO AG","1FCFA-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-01-27",null,null,"1,7",1]
[null,"DB InfraGO AG","207CA-001","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,28,35,"2026-07-10","21:00:00","2026-08-24","21:00:00","45d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"6,7",1]
[null,"DB InfraGO AG","20838-002","Berlin - Dresden","< >","Berlin Eichgestell","Berlin Stadtforst",2026,2026,48,50,"2026-11-27","21:00:00","2026-12-11","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-01-27",null,null,"2,3",1]
[null,"DB InfraGO AG","1310-(MK27)-01","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,3,4,"22.01.2027","21:00:00","29.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1310-(MK27)-02","Berlin - Dresden","< >","Berlin Schönh Allee","Berlin Frankf Allee",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-01-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1CCA6-008","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-19","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,2,1]
[null,"DB InfraGO AG","1CCBC-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-02",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1CCBC-003","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,39,40,"2026-09-27","21:00:00","2026-09-28","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"2,3",1]
[null,"DB InfraGO AG","1CCC5-002","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Nord",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"4,5",1]
[null,"DB InfraGO AG","1CCC5-004","Berlin - Dresden","< >","Berlin-Grünau","Grünauer Kreuz Süd",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-27","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-02-03",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","20189-001","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","20189-002","Berlin - Dresden","<","Cossebaude","Dresden-Friedrichstadt",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","20D69-003","Berlin - Dresden","<","Cossebaude","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-07-18",null,null,1,1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3097-(MK25)-03_WDD","Berlin - Dresden",">","Dre-Friedrichst","Dresden Mitte",2027,2027,6,27,"08.02.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","3097-(MK27)-01_WDN","Berlin - Dresden","< >","Dre-Friedrichst","Dresden Mitte",2027,2027,38,46,"20.09.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1D63C-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,49,50,"2026-12-04","22:00:00","2026-12-07","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1F5FE-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO AG","1F5FE-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-11-06",null,null,7,1]
[null,"DB InfraGO AG","1F722-001","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-10-25",null,null,1,1]
[null,"DB InfraGO AG","1F722-003","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,1,1]
[null,"DB InfraGO AG","1F722-008","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,43,43,"2026-10-25","00:00:00","2026-10-25","04:00:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1F722-011","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Altstadt",2026,2026,47,47,"2026-11-16","00:00:00","2026-11-16","04:00:00","0d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1F748-002","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","1F748-004","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","20D69-006","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"7,7,7",null,null,null,"N",null,"2023-10-25",null,null,2,1]
[null,"DB InfraGO AG","20D69-007","Berlin - Dresden","< >","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-23",null,null,2,1]
[null,"DB InfraGO AG","20D69-008","Berlin - Dresden","<","Dresden Freiberger Straße","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","20:00:00","2026-10-30","07:00:00","19d, 12h","Periodical","Signal",null,null,null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-10-18",null,null,2,1]
[null,"DB InfraGO AG","3873-(MK27)-01_D","Berlin - Dresden",">","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"04.09.2027","05:00:00","12.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","3873-(MK27)-01_N","Berlin - Dresden","< >","Dresden Freibg Str","Dresden Hbf",2027,2027,35,45,"03.09.2027","21:00:00","12.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-30",null,null,3,1]
[null,"DB InfraGO AG","1F5FE-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-10-02",null,null,5,1]
[null,"DB InfraGO AG","1F5FE-007","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1F5FE-008","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-12",null,null,1,1]
[null,"DB InfraGO AG","1F6CB-001","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,36,38,"2026-08-31","18:00:00","2026-09-14","05:00:00","13d, 11h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,5,1]
[null,"DB InfraGO AG","1F722-005","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-10-16",null,null,6,1]
[null,"DB InfraGO AG","1F722-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,2,1]
[null,"DB InfraGO AG","1F722-007","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-16",null,null,2,1]
[null,"DB InfraGO AG","1F748-006","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2024-04-22",null,null,2,1]
[null,"DB InfraGO AG","1F748-007","Berlin - Dresden","< >","Dresden Hbf","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1F748-008","Berlin - Dresden","< >","Dresden Hbf","Dresden-Altstadt",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-16",null,null,1,1]
[null,"DB InfraGO AG","1655-(MK26)-02_D","Berlin - Dresden",">","Dresden Hbf","Pirna",2027,2027,15,23,"17.04.2027","05:00:00","11.06.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1655-(MK26)-02_N","Berlin - Dresden","< >","Dresden Hbf","Pirna",2027,2027,15,23,"16.04.2027","21:00:00","11.06.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1656-(MK26)-01_D","Berlin - Dresden",">","Dresden Hbf","Pirna",2027,2027,14,17,"10.04.2027","05:00:00","30.04.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1656-(MK26)-01_N","Berlin - Dresden","< >","Dresden Hbf","Pirna",2027,2027,14,17,"09.04.2027","21:00:00","30.04.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-09-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3094-(MK27)-02_WDN","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2027,2027,25,27,"21.06.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-05-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","3094-(MK27)-02_WDD","Berlin - Dresden",">","Dresden Hbf","Dresden Mitte",2027,2027,25,27,"21.06.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-09-22",null,null,6,1]
[null,"DB InfraGO AG","3094-(MK27)-03","Berlin - Dresden","< >","Dresden Hbf","Dresden Mitte",2027,2027,35,45,"03.09.2027","21:00:00","12.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2023-09-22",null,null,"6,7",1]
[null,"DB InfraGO AG","3868-(MK26)-01_D","Berlin - Dresden",">","Dresden Mitte","Dresden Hbf",2027,2027,14,15,"10.04.2027","05:00:00","16.04.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","3868-(MK26)-01_N","Berlin - Dresden","< >","Dresden Mitte","Dresden Hbf",2027,2027,14,15,"09.04.2027","21:00:00","16.04.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2023-09-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1D5D6-010","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Freiberger Straße",2026,2026,47,48,"2026-11-20","22:00:00","2026-11-23","04:00:00","2d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-24",null,null,"1,2",1]
[null,"DB InfraGO AG","1F5FE-001","Berlin - Dresden","<","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-08-05",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5FE-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-11-28",null,null,"2,3",1]
[null,"DB InfraGO AG","1F5FE-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,19,43,"2026-05-04","04:00:00","2026-10-25","04:00:00","174d, 1h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,6,1]
[null,"DB InfraGO AG","1F722-002","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"Y",null,"2023-09-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1F722-004","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,43,47,"2026-10-25","04:00:00","2026-11-16","04:00:00","22d, 0h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F748-001","Berlin - Dresden","<","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2023-09-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1F748-003","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"Y",null,"2024-07-17",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1F748-005","Berlin - Dresden","< >","Dresden-Altstadt","Dresden Hbf",2026,2026,47,50,"2026-11-16","04:00:00","2026-12-12","23:59:00","26d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-21",null,null,"2,3,4",1]
[null,"DB InfraGO AG","20189-003","Berlin - Dresden","< >","Dresden-Cotta Bft","Dresden-Kemnitz",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","3096-(MK25)-03_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Dresden Freibg Str",2026,2027,51,27,"14.12.2026","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-07-18",null,null,7,1]
[null,"DB InfraGO AG","3096-(MK25)-03_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Freibg Str",2026,2027,51,27,"14.12.2026","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-10-25",null,null,7,1]
[null,"DB InfraGO AG","3096-(MK27)-02_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Dresden Freibg Str",2027,2027,46,46,"15.11.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-10-15",null,null,3,1]
[null,"DB InfraGO AG","3096-(MK27)-02_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Freibg Str",2027,2027,46,46,"15.11.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-11-11",null,null,"3,4",1]
[null,"DB InfraGO AG","3097-(MK27)-01_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Dresden Mitte",2027,2027,38,46,"20.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-09-12",null,null,4,1]
[null,"DB InfraGO AG","3636-(MK25)-02_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,12,37,"27.03.2027","05:00:00","17.09.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-08-29",null,null,5,1]
[null,"DB InfraGO AG","3636-(MK25)-02_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,12,37,"26.03.2027","21:00:00","17.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-08-29",null,null,5,1]
[null,"DB InfraGO AG","3636-(MK26)-07_WDN","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,38,46,"20.09.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2023-10-16",null,null,6,1]
[null,"DB InfraGO AG","3636-(MK26)-07_WDD","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,38,46,"20.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2025-01-08",null,null,2,1]
[null,"DB InfraGO AG","3636-(MK26)-10_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2026,2027,50,10,"12.12.2026","05:00:00","12.03.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,2,1]
[null,"DB InfraGO AG","3636-(MK26)-10_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2026,2027,50,10,"11.12.2026","21:00:00","12.03.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3636-(MK27)-02_D","Berlin - Dresden",">","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,46,49,"20.11.2027","05:00:00","10.12.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3636-(MK27)-02_N","Berlin - Dresden","< >","Dresden-Friedrichst","Radebeul-Naundf Abz",2027,2027,46,49,"19.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2025-01-08",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1C092-003","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,38,41,"2026-09-16","07:00:00","2026-10-05","16:00:00","19d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-11-25",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1D47F-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,44,48,"2026-10-26","08:00:00","2026-11-23","18:00:00","28d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-11-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1FAD6-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1FAD6-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1FAD6-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,32,36,"2026-08-07","22:00:00","2026-09-01","04:00:00","24d, 6h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-10-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,50,"2026-03-12","04:00:00","2026-12-12","23:59:00","275d, 19h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-006","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-007","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,11,41,"2026-03-12","23:00:00","2026-10-09","04:00:00","210d, 4h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-008","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-009","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-010","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,45,50,"2026-11-02","23:00:00","2026-12-12","04:00:00","39d, 5h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-011","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-012","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20189-013","Berlin - Dresden","< >","Dresden-Friedrichstadt","Cossebaude",2026,2026,41,44,"2026-10-09","23:00:00","2026-10-31","04:00:00","21d, 6h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2023-12-06",null,null,"1,2",1]
[null,"DB InfraGO AG","20D69-001","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Cotta Bft",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-002","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden Mitte",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-004","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,"7,,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","20D69-005","Berlin - Dresden","< >","Dresden-Friedrichstadt","Dresden-Friedrichstadt",2026,2026,41,44,"2026-10-10","07:00:00","2026-10-30","20:00:00","20d, 14h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","1D050-006","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,44,44,"2026-10-26","20:50:00","2026-10-28","04:20:00","1d, 7h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1D050-007","Berlin - Dresden","< >","Dresden-Klotzsche","Dresden-Neustadt",2026,2026,44,44,"2026-10-30","20:50:00","2026-10-31","04:20:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F4C3-001","Berlin - Dresden","< >","Dresden-Pieschen                  (Abzw)","Dresden-Neustadt",2026,2026,12,50,"2026-03-16","00:00:00","2026-12-11","23:59:00","270d, 23h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-06-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1FCFA-003","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,31,31,"2026-08-01","21:00:00","2026-08-02","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","20838-003","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,48,50,"2026-11-27","21:00:00","2026-12-11","21:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","207CA-006","Berlin - Dresden","< >","Eichgestell Nord","Berlin Stadtforst",2026,2026,28,35,"2026-07-10","21:00:00","2026-08-24","21:00:00","45d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1C2D3-001","Berlin - Dresden","<","Frauenhain","Elsterwerda",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2025-01-20",null,null,"6,7",1]
[null,"DB InfraGO AG","1C573-017","Berlin - Dresden","< >","Görlitz","Dresden-Neustadt",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-10","02:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1653-(MK26)-01","Berlin - Dresden","< >","Großenh Berl Bf","Großenh Cott Bf",2027,2027,26,27,"02.07.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-10",null,null,"2,3",1]
[null,"DB InfraGO AG","1653-(MK26)-03","Berlin - Dresden","< >","Großenh Berl Bf","Großenh Cott Bf",2027,2027,31,34,"06.08.2027","21:00:00","27.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1C573-023","Berlin - Dresden","< >","Großenhain Cottb Bf","Brieske",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-10","02:00:00","0d, 4h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1CCA6-007","Berlin - Dresden","< >","Grünauer Kreuz Süd","Berlin-Grünau",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-19","04:50:00","0d, 7h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1C2D3-004","Berlin - Dresden",">","Hohenleipisch","Elsterwerda",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1E552-001","Berlin - Dresden","< >","Luckau-Uckro","Brenitz-Sonnewalde",2026,2026,48,49,"2026-11-28","22:00:00","2026-12-05","22:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1C092-009","Berlin - Dresden",">","Niederau","Coswig (bei Dresden)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-19",null,null,"5,6",1]
[null,"DB InfraGO AG","1BF3C-004","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,36,36,"2026-08-31","20:00:00","2026-09-03","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-005","Berlin - Dresden",">","Radebeul Abzw Az","Weinböhla",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-007","Berlin - Dresden","< >","Radebeul Abzw Az","Weinböhla",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-002","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,40,41,"2026-10-04","20:00:00","2026-10-05","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-004","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF59-006","Berlin - Dresden","< >","Radebeul Abzw Az","Radebeul Nord",2026,2026,50,50,"2026-12-11","20:00:00","2026-12-12","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","3648-(MK27)-01","Berlin - Dresden",">","Radebeul-Naundf Abz","Coswig (bei Dre)",2027,2027,30,33,"31.07.2027","05:00:00","20.08.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","3648-(MK27)-02","Berlin - Dresden",">","Radebeul-Naundf Abz","Coswig (bei Dre)",2027,2027,38,46,"25.09.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-07-19",null,null,"1,7",1]
[null,"DB InfraGO AG","1BF3C-003","Berlin - Dresden","< >","Radebeul-Naundorf                 (Abzw)","Kottewitz",2026,2026,36,36,"2026-08-31","20:00:00","2026-09-03","04:00:00","2d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1E552-002","Berlin - Dresden","< >","Walddrehna","Walddrehna",2026,2026,49,49,"2026-12-05","22:00:00","2026-12-06","22:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1E552-003","Berlin - Dresden","< >","Walddrehna","Walddrehna",2026,2026,49,50,"2026-12-06","22:00:00","2026-12-07","22:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-006","Berlin - Dresden","<","Weinböhla","Radebeul Abzw Az",2026,2026,13,36,"2026-03-24","04:00:00","2026-09-02","20:00:00","162d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-008","Berlin - Dresden","<","Weinböhla","Radebeul-Naundorf",2026,2026,13,33,"2026-03-26","08:00:00","2026-08-11","16:00:00","138d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-009","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,13,33,"2026-03-26","08:00:00","2026-08-11","16:00:00","138d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF3C-011","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-008","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,41,47,"2026-10-05","04:00:00","2026-11-19","20:00:00","45d, 17h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-010","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,48,50,"2026-11-27","08:00:00","2026-12-11","16:00:00","14d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1BF59-011","Berlin - Dresden","< >","Weinböhla","Weinböhla",2026,2026,41,50,"2026-10-05","04:00:00","2026-12-11","20:00:00","67d, 17h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1E1C3-001","Berlin - Dresden","< >","Zossen","Wünsdorf-Waldstadt",2026,2026,33,34,"2026-08-15","21:00:00","2026-08-17","05:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1E35C-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,36,36,"2026-09-04","22:00:00","2026-09-05","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,36,36,"2026-09-04","22:00:00","2026-09-05","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-003","Bremen - Hannover",">","Bremen Hbf","Bremen Hbf",2026,2026,36,37,"2026-09-05","10:00:00","2026-09-07","05:00:00","1d, 19h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-05","20:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-06","08:00:00","0d, 14h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-007","Bremen - Hannover",">","Bremen Hbf","Bremen Hbf",2026,2026,37,37,"2026-09-07","05:00:00","2026-09-12","14:00:00","5d, 9h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,37,38,"2026-09-12","14:00:00","2026-09-14","05:00:00","1d, 15h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,37,38,"2026-09-12","14:00:00","2026-09-14","05:00:00","1d, 15h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Rbf Ausfahrt",2026,2026,38,38,"2026-09-14","22:00:00","2026-09-15","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1E35C-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf ehem Bwn",2026,2026,38,38,"2026-09-14","22:00:00","2026-09-15","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,32,"2026-07-31","22:00:00","2026-08-03","16:30:00","2d, 18h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,31,31,"2026-08-01","05:00:00","2026-08-01","08:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-007","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,35,"2026-08-03","16:30:00","2026-08-30","18:00:00","27d, 1h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-05","04:00:00","2026-08-05","18:00:00","0d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-06","00:00:00","2026-08-06","11:00:00","0d, 11h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","22:00:00","1d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,32,32,"2026-08-09","09:00:00","2026-08-09","13:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20849-012","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,35,35,"2026-08-30","12:00:00","2026-08-30","15:00:00","0d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-001","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,38,"2026-09-14","08:00:00","2026-09-14","12:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-002","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,38,"2026-09-14","12:00:00","2026-09-14","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-003","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,38,39,"2026-09-17","07:00:00","2026-09-24","07:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-004","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","00:00:00","2026-09-24","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-005","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,40,"2026-09-24","07:00:00","2026-09-30","15:00:00","6d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-006","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","07:00:00","2026-09-24","09:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-007","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,39,39,"2026-09-24","22:00:00","2026-09-27","05:00:00","2d, 7h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-008","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,40,"2026-09-30","10:00:00","2026-09-30","12:00:00","0d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-009","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,41,"2026-09-30","15:00:00","2026-10-08","07:00:00","7d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-010","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,40,40,"2026-10-01","00:00:00","2026-10-01","03:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-011","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","00:00:00","2026-10-08","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-012","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,42,"2026-10-08","07:00:00","2026-10-13","06:00:00","4d, 23h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-013","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,42,"2026-10-08","07:00:00","2026-10-13","06:00:00","4d, 23h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-014","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","07:00:00","2026-10-08","11:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-015","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,41,41,"2026-10-08","22:00:00","2026-10-11","05:00:00","2d, 7h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-016","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","01:00:00","2026-10-13","04:00:00","0d, 3h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-017","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","01:00:00","2026-10-13","05:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-018","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","08:00:00","2026-10-13","12:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","20A9D-019","Bremen - Hannover","< >","Bremen Hbf","Bremen Hbf",2026,2026,42,42,"2026-10-13","12:00:00","2026-10-13","16:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1115-(MK27)-01_D","Bremen - Hannover",">","Bremen-Sebaldsbrück","Verden (Aller)",2027,2027,19,26,"15.05.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-19",null,null,6,1]
[null,"DB InfraGO AG","1115-(MK27)-01_N","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Verden (Aller)",2027,2027,19,26,"14.05.2027","21:00:00","02.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-01",null,null,"1,7",1]
[null,"DB InfraGO AG","3632-(MK27)-01_D","Bremen - Hannover",">","Bremen-Sebaldsbrück","Bremen Hbf",2027,2027,19,26,"15.05.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-01",null,null,"1,7",1]
[null,"DB InfraGO AG","3632-(MK27)-01_N","Bremen - Hannover","< >","Bremen-Sebaldsbrück","Bremen Hbf",2027,2027,19,26,"14.05.2027","21:00:00","02.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1CC41-039","Bremen - Hannover","<","Gümmerwald","Wunstorf",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1B42F-001","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Waldhausen",2026,2026,36,38,"2026-09-05","20:00:00","2026-09-14","06:00:00","8d, 10h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1B42F-002","Bremen - Hannover","< >","Hannover-Linden/Fischerhof","Hannover Bismarckstraße",2026,2026,37,38,"2026-09-07","23:45:00","2026-09-17","04:35:00","9d, 4h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1C80D-005","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-007","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-13","19:00:00","4d, 22h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-008","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,33,35,"2026-08-13","19:00:00","2026-08-30","00:30:00","16d, 5h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1C80D-010","Bremen - Hannover","< >","Haste","Wunstorf",2026,2026,35,36,"2026-08-30","00:30:00","2026-09-01","04:25:00","2d, 3h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-007","Bremen - Hannover",">","Letter                            (Abzw)","Seelze West",2026,2026,32,33,"2026-08-07","23:00:00","2026-08-15","05:05:00","7d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1CBAE-002","Bremen - Hannover",">","Letter                            (Abzw)","Seelze West",2026,2026,41,42,"2026-10-05","23:10:00","2026-10-14","04:45:00","8d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1E7DC-001","Bremen - Hannover","< >","Neustadt a Rübenberge","Hagen (Han)",2026,2026,42,42,"2026-10-17","23:05:00","2026-10-18","06:50:00","0d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1FB74-001","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,38,"2026-09-07","14:00:00","2026-09-18","14:00:00","11d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-002","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,37,"2026-09-10","06:00:00","2026-09-10","21:30:00","0d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-003","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,37,37,"2026-09-10","06:00:00","2026-09-10","21:30:00","0d, 15h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-004","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,37,37,"2026-09-11","07:00:00","2026-09-11","19:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-005","Bremen - Hannover","< >","Nienburg (Weser)","Estorf (Weser)",2026,2026,38,38,"2026-09-16","06:00:00","2026-09-16","19:30:00","0d, 13h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-006","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,38,38,"2026-09-16","06:00:00","2026-09-16","19:30:00","0d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB74-007","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2026,2026,38,38,"2026-09-17","06:00:00","2026-09-17","11:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1CAFD-003","Bremen - Hannover","< >","Seelze","Seelze West",2026,2026,31,32,"2026-07-27","05:00:00","2026-08-07","23:00:00","11d, 18h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-030","Bremen - Hannover","< >","Seelze","Wunstorf",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","09:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1CC41-034","Bremen - Hannover","< >","Seelze","Wunstorf",2026,2026,31,31,"2026-08-01","09:00:00","2026-08-02","09:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1CAFD-008","Bremen - Hannover","< >","Seelze West","Letter                            (Abzw)",2026,2026,32,33,"2026-08-07","23:00:00","2026-08-15","05:05:00","7d, 6h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CAFD-009","Bremen - Hannover",">","Seelze West","Wunstorf",2026,2026,32,32,"2026-08-07","23:00:00","2026-08-08","01:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CAFD-010","Bremen - Hannover",">","Seelze West","Wunstorf",2026,2026,33,33,"2026-08-15","03:00:00","2026-08-15","05:05:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"4,5",1]
[null,"DB InfraGO AG","1CBAE-003","Bremen - Hannover","< >","Seelze West","Letter                            (Abzw)",2026,2026,41,42,"2026-10-05","23:10:00","2026-10-14","04:45:00","8d, 5h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CBAE-004","Bremen - Hannover","< >","Seelze West","Hannover-Nordstadt",2026,2026,41,42,"2026-10-07","23:10:00","2026-10-16","04:55:00","8d, 5h","Periodical","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-037","Bremen - Hannover","<","Seelze West","Gümmerwald",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1CC41-038","Bremen - Hannover","<","Seelze West","Wunstorf",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1B534-001","Bremen - Hannover","< >","Verden (Aller)","Walle (Kr Verden)",2026,2026,50,50,"2026-12-07","22:00:00","2026-12-12","05:00:00","4d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1C80D-004","Bremen - Hannover","< >","Wunstorf","Haste",2026,2026,29,32,"2026-07-15","05:15:00","2026-08-06","09:00:00","22d, 3h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1C80D-006","Bremen - Hannover",">","Wunstorf","Haste",2026,2026,32,32,"2026-08-06","09:00:00","2026-08-08","21:00:00","2d, 12h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1C80D-009","Bremen - Hannover",">","Wunstorf","Haste",2026,2026,33,35,"2026-08-13","19:00:00","2026-08-30","00:30:00","16d, 5h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-012","Bremen - Hannover","< >","Wunstorf","Letter                            (Abzw)",2026,2026,32,32,"2026-08-08","01:00:00","2026-08-08","03:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CAFD-013","Bremen - Hannover","< >","Wunstorf","Letter                            (Abzw)",2026,2026,33,33,"2026-08-15","01:00:00","2026-08-15","03:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EF-001","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,19,32,"2026-05-04","07:00:00","2026-08-07","19:00:00","95d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-004","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,27,32,"2026-07-05","23:00:00","2026-08-08","05:00:00","33d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-012","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,29,32,"2026-07-13","00:01:00","2026-08-07","19:00:00","25d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-031","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","09:00:00","0d, 12h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-032","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,31,31,"2026-07-31","21:00:00","2026-08-01","21:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-033","Bremen - Hannover","< >","Wunstorf","Seelze",2026,2026,31,31,"2026-08-01","09:00:00","2026-08-02","09:00:00","1d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-035","Bremen - Hannover","< >","Wunstorf","Gümmerwald",2026,2026,31,32,"2026-07-31","23:00:00","2026-08-03","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-036","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,31,32,"2026-07-31","23:00:00","2026-08-03","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-040","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-03","23:00:00","2026-08-05","05:00:00","1d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-041","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-05","23:00:00","2026-08-08","05:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1CC41-042","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,32,32,"2026-08-05","23:00:00","2026-08-08","05:00:00","2d, 6h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-001","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-002","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-003","Bremen - Hannover","< >","Wunstorf","Seelze West",2026,2026,40,42,"2026-10-02","22:50:00","2026-10-14","04:35:00","11d, 5h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-004","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,40,40,"2026-10-03","00:30:00","2026-10-03","04:30:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D4EE-005","Bremen - Hannover","< >","Wunstorf","Wunstorf",2026,2026,41,42,"2026-10-10","00:30:00","2026-10-12","04:30:00","2d, 4h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"6,7",1]
[null,"DB InfraGO AG","214B7-001","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,41,41,"2026-10-05","22:30:00","2026-10-10","04:30:00","4d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","214B7-004","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"3,4",1]
[null,"DB InfraGO AG","214B7-008","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-016","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-020","Bremerhaven - Bremen",">","Bremen Hbf","Bremen Rbf Abzw",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","214B7-024","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"1,2",1]
[null,"DB InfraGO AG","214B7-026","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Rbf Abzw",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-001","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-03","06:00:00","2026-08-05","18:00:00","2d, 12h","Periodical","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-005","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,32,32,"2026-08-07","01:00:00","2026-08-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-006","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Rbf Abzw",2026,2026,32,34,"2026-08-07","05:00:00","2026-08-19","01:00:00","11d, 20h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-022","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,34,34,"2026-08-19","01:00:00","2026-08-19","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-002","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,41,41,"2026-10-05","23:00:00","2026-10-10","05:00:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-003","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen-Walle",2026,2026,41,41,"2026-10-05","23:00:00","2026-10-10","05:00:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-005","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-006","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,42,42,"2026-10-12","22:30:00","2026-10-17","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-009","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-010","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,46,"2026-11-06","22:30:00","2026-11-09","04:30:00","2d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-011","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-012","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-017","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-018","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,46,47,"2026-11-14","05:00:00","2026-11-16","05:00:00","2d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-021","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-022","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,48,"2026-11-24","22:30:00","2026-11-29","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-025","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-08-06",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-027","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen-Walle",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","214B7-028","Bremerhaven - Bremen","< >","Bremen Rbf Abzw","Bremen Hbf",2026,2026,49,49,"2026-11-30","22:30:00","2026-12-05","04:30:00","4d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1E35C-004","Bremerhaven - Bremen","<","Bremen Rbf Ausfahrt","Bremen Hbf",2026,2026,36,36,"2026-09-05","18:00:00","2026-09-05","20:00:00","0d, 2h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-08-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1F8D6-009","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-07","18:00:00","2026-08-07","20:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-010","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,32,32,"2026-08-08","04:00:00","2026-08-08","07:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-012","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,33,"2026-08-16","15:00:00","2026-08-16","16:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-013","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,33,"2026-08-16","19:00:00","2026-08-16","20:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-014","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,33,34,"2026-08-16","23:00:00","2026-08-17","00:00:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-015","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","02:00:00","2026-08-17","07:00:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-016","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","13:00:00","2026-08-17","15:00:00","0d, 2h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-018","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-17","21:00:00","2026-08-18","00:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-019","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,34,34,"2026-08-18","02:00:00","2026-08-18","05:00:00","0d, 3h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-004","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","10:30:00","2026-09-22","11:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-005","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","13:30:00","2026-09-22","14:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D8-009","Bremerhaven - Bremen","< >","Bremen Rbf Einfahrt","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-23","10:30:00","2026-09-23","11:30:00","0d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"1,2",1]
[null,"DB InfraGO AG","1F8D6-004","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,32,32,"2026-08-07","01:00:00","2026-08-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D6-023","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,34,34,"2026-08-19","01:00:00","2026-08-19","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D8-003","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-22","07:00:00","2026-09-22","15:30:00","0d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F8D8-006","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen Rbf Abzw",2026,2026,39,39,"2026-09-23","07:00:00","2026-09-23","12:30:00","0d, 5h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-013","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-023","Bremerhaven - Bremen","<","Bremen-Burg","Bremen Hbf",2026,2026,48,49,"2026-11-29","23:30:00","2026-11-30","04:30:00","0d, 5h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-014","Bremerhaven - Bremen","< >","Bremen-Walle","Bremen Rbf Abzw",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","214B7-015","Bremerhaven - Bremen","< >","Bremen-Walle","Bremen Rbf Abzw",2026,2026,46,46,"2026-11-09","22:30:00","2026-11-11","04:30:00","1d, 6h","Periodical","Bridge",null,null,"S",null,null,",,",",,",null,",0,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-001","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,43,44,"2026-10-23","23:00:00","2026-10-27","05:00:00","3d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-003","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,44,44,"2026-10-27","05:00:00","2026-10-30","08:00:00","3d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-004","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,45,45,"2026-11-03","05:00:00","2026-11-06","08:00:00","3d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-001","Bremerhaven - Bremen",">","Bremerhaven Hbf","Bremerhaven Hbf",2026,2026,31,35,"2026-08-01","02:00:00","2026-08-27","15:00:00","26d, 13h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-003","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Lehe Pbf",2026,2026,31,31,"2026-07-31","22:00:00","2026-08-01","05:00:00","0d, 7h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-005","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Bremerhaven Hbf",2026,2026,31,31,"2026-08-01","22:00:00","2026-08-02","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-014","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,35,35,"2026-08-29","22:00:00","2026-08-30","06:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-015","Bremerhaven - Bremen","<","Bremerhaven Hbf","Bremerhaven-Wulsdorf",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-08","06:00:00","3d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","21D6F-002","Bremerhaven - Bremen","<","Bremerhaven-Lehe Pbf","Bremerhaven Hbf",2026,2026,44,45,"2026-10-30","23:00:00","2026-11-03","05:00:00","3d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","22261-002","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,31,31,"2026-07-31","22:00:00","2026-08-01","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-004","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,31,32,"2026-08-01","05:00:00","2026-08-03","05:00:00","2d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-006","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,31,32,"2026-08-01","05:00:00","2026-08-03","05:00:00","2d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-007","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,32,33,"2026-08-07","16:00:00","2026-08-11","09:00:00","3d, 17h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-008","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,32,33,"2026-08-07","16:00:00","2026-08-11","09:00:00","3d, 17h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-009","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","06:00:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-010","Bremerhaven - Bremen","< >","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,33,35,"2026-08-16","22:00:00","2026-08-24","06:00:00","7d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-011","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,34,35,"2026-08-21","22:00:00","2026-08-25","06:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-012","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven Hbf",2026,2026,34,35,"2026-08-21","22:00:00","2026-08-25","06:00:00","3d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-08",null,null,"6,7",1]
[null,"DB InfraGO AG","22261-013","Bremerhaven - Bremen",">","Bremerhaven-Wulsdorf","Bremerhaven-Lehe Pbf",2026,2026,35,35,"2026-08-26","23:00:00","2026-08-27","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","221C0-003","Darmstadt - Nürnberg","< >","Arnstein (Unterfr)","Thüngen (Unterfr)",2026,2026,50,50,"2026-12-07","08:00:00","2026-12-09","16:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","221C0-004","Darmstadt - Nürnberg","< >","Arnstein (Unterfr)","Thüngen (Unterfr)",2026,2026,50,50,"2026-12-10","08:00:00","2026-12-10","16:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","202DB-002","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Wiesthal",2026,2026,46,46,"2026-11-11","22:00:00","2026-11-12","04:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","218BA-003","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Stockstadt (Main)",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-14","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","218BA-006","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Stockstadt (Main)",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-23","05:00:00","9d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","218BA-010","Darmstadt - Nürnberg","<","Aschaffenburg Hbf","Stockstadt (Main)",2026,2026,49,49,"2026-12-04","21:00:00","2026-12-06","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-11",null,null,"1,2",1]
[null,"DB InfraGO AG","1FBAC-001","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","18:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FBAC-004","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,32,32,"2026-08-08","18:00:00","2026-08-09","14:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1FBAC-007","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,32,33,"2026-08-09","14:00:00","2026-08-10","06:00:00","0d, 16h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1FC34-007","Darmstadt - Nürnberg","< >","Bamberg","Breitengüßbach Süd",2026,2026,31,32,"2026-08-01","14:00:00","2026-08-03","05:00:00","1d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1C08E-017","Darmstadt - Nürnberg","<","Darmstadt Gbf","Weiterstadt",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-10","05:00:00","1d, 8h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1C08E-018","Darmstadt - Nürnberg","<","Darmstadt Gbf","Weiterstadt",2026,2026,34,34,"2026-08-22","21:00:00","2026-08-23","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"18,18,18",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","3506-(MK26)-03","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2026,2027,51,53,"18.12.2026","21:00:00","01.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3506-(MK26)-04","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,9,10,"05.03.2027","21:00:00","12.03.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3506-(MK26)-05","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,19,21,"14.05.2027","21:00:00","28.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3506-(MK26)-06","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,29,30,"23.07.2027","21:00:00","26.07.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK26)-06","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2026,2026,50,52,"11.12.2026","21:00:00","25.12.2026","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK26)-09","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,21,23,"28.05.2027","21:00:00","11.06.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK26)-10","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,26,27,"02.07.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK27)-01","Darmstadt - Nürnberg",">","Darmstadt Hbf","Darmstadt Nord",2027,2027,23,25,"11.06.2027","21:00:00","25.06.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK27)-02","Darmstadt - Nürnberg","< >","Darmstadt Hbf","Darmstadt Nord",2027,2027,1,3,"08.01.2027","21:00:00","22.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","3655-(MK27)-03","Darmstadt - Nürnberg",">","Darmstadt Hbf","Darmstadt Nord",2027,2027,3,5,"22.01.2027","21:00:00","05.02.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1180-(MK27)-01","Darmstadt - Nürnberg","< >","Darmstadt Nord","Aschaffenbg Hbf & Steinerts",2026,2026,51,52,"18.12.2026","21:00:00","21.12.2026","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-07-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1C08E-010","Darmstadt - Nürnberg",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,26,32,"2026-06-26","21:00:00","2026-08-07","21:00:00","42d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1C08E-011","Darmstadt - Nürnberg",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,34,35,"2026-08-23","21:00:00","2026-08-24","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1C08E-012","Darmstadt - Nürnberg",">","Darmstadt-Arheilgen","Darmstadt Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-14","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","20780-010","Darmstadt - Nürnberg","< >","Dieburg","Babenhausen (Hess)",2026,2026,35,38,"2026-08-28","23:00:00","2026-09-14","05:00:00","16d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1834-(MK27)-01_D","Darmstadt - Nürnberg",">","Eltersdorf","Forchheim (Ofr)",2027,2027,19,27,"15.05.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1834-(MK27)-01_N","Darmstadt - Nürnberg","< >","Eltersdorf","Forchheim (Ofr)",2027,2027,19,27,"14.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","21811-018","Darmstadt - Nürnberg","<","Espenloh","Lohr Bahnhof",2026,2026,47,47,"2026-11-20","21:00:00","2026-11-22","07:00:00","1d, 10h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-16",null,null,"5,6",1]
[null,"DB InfraGO AG","1DD2B-001","Darmstadt - Nürnberg",">","Gädheim","Schweinfurt Hbf",2026,2026,43,44,"2026-10-25","22:00:00","2026-10-27","05:00:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-08-13",null,null,"6,7",1]
[null,"DB InfraGO AG","221FC-003","Darmstadt - Nürnberg",">","Gambach Üst","Gemünden (Main)",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","221FC-007","Darmstadt - Nürnberg",">","Gambach Üst","Gemünden (Main)",2026,2026,50,50,"2026-12-10","21:00:00","2026-12-11","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","20029-026","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,27,35,"2026-06-30","08:00:00","2026-08-26","20:00:00","57d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-11",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-002","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-003","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-005","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,35,"2026-08-25","23:00:00","2026-08-27","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-006","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,35,"2026-08-25","23:00:00","2026-08-27","05:00:00","1d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-007","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,36,"2026-08-28","23:00:00","2026-08-31","05:00:00","2d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-008","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,35,36,"2026-08-28","23:00:00","2026-08-31","05:00:00","2d, 6h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-009","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,36,37,"2026-09-01","23:00:00","2026-09-07","05:00:00","5d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-010","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,36,37,"2026-09-01","23:00:00","2026-09-07","05:00:00","5d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-15",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-011","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,37,38,"2026-09-11","08:00:00","2026-09-18","20:00:00","7d, 12h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-012","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,37,38,"2026-09-11","08:00:00","2026-09-18","20:00:00","7d, 12h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17",null,null,"4,5",1]
[null,"DB InfraGO AG","2037B-017","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,39,40,"2026-09-24","23:00:00","2026-09-28","20:00:00","3d, 21h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"5,6",1]
[null,"DB InfraGO AG","2037B-018","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,40,41,"2026-09-29","23:00:00","2026-10-05","05:00:00","5d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"5,6",1]
[null,"DB InfraGO AG","2037B-019","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,39,40,"2026-09-24","23:00:00","2026-09-28","20:00:00","3d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-020","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,40,41,"2026-09-29","23:00:00","2026-10-05","05:00:00","5d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-022","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,41,42,"2026-10-09","23:00:00","2026-10-13","20:00:00","3d, 21h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-024","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,41,42,"2026-10-09","23:00:00","2026-10-13","20:00:00","3d, 21h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"1,7",1]
[null,"DB InfraGO AG","2037B-025","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,42,43,"2026-10-14","23:00:00","2026-10-20","05:00:00","5d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-28",null,null,"3,4",1]
[null,"DB InfraGO AG","2037B-026","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,42,43,"2026-10-14","23:00:00","2026-10-20","05:00:00","5d, 6h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-28",null,null,"3,4",1]
[null,"DB InfraGO AG","2037B-027","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","202A2-001","Darmstadt - Nürnberg",">","Gemünden (Main)","Lohr Bahnhof",2026,2026,35,35,"2026-08-28","21:00:00","2026-08-29","01:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-23",null,null,"5,6",1]
[null,"DB InfraGO AG","202A2-006","Darmstadt - Nürnberg",">","Gemünden (Main)","Lohr Bahnhof",2026,2026,37,37,"2026-09-11","01:00:00","2026-09-11","05:00:00","0d, 4h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-031","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-17","23:00:00","2026-08-18","05:00:00","0d, 6h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"6,7",1]
[null,"DB InfraGO AG","2037B-032","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-18","05:00:00","2026-08-18","09:00:00","0d, 4h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","2037B-033","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,34,34,"2026-08-18","05:00:00","2026-08-18","09:00:00","0d, 4h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"3,4",1]
[null,"DB InfraGO AG","221FC-001","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,46,50,"2026-11-14","21:00:00","2026-12-11","05:00:00","26d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-002","Darmstadt - Nürnberg","< >","Gemünden (Main)","Wernfeld",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-004","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,46,46,"2026-11-14","21:00:00","2026-11-15","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-005","Darmstadt - Nürnberg","< >","Gemünden (Main)","Wernfeld",2026,2026,47,50,"2026-11-21","21:00:00","2026-12-10","05:00:00","18d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-006","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,50,50,"2026-12-10","21:00:00","2026-12-11","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-008","Darmstadt - Nürnberg","< >","Gemünden (Main)","Wernfeld",2026,2026,50,50,"2026-12-10","21:00:00","2026-12-11","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","221FC-009","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,47,50,"2026-11-21","21:00:00","2026-12-10","05:00:00","18d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","222AD-001","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,26,34,"2026-06-26","21:00:00","2026-08-21","06:00:00","55d, 9h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"6,7",1]
[null,"DB InfraGO AG","222C2-001","Darmstadt - Nürnberg","< >","Gemünden (Main)","Gemünden (Main)",2026,2026,26,34,"2026-06-26","21:00:00","2026-08-21","06:00:00","55d, 9h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1396-(MK27)-20","Darmstadt - Nürnberg","< >","Großkrotzenburg","Aschaffenbg Hbf",2027,2027,1,4,"08.01.2027","21:00:00","29.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1396-(MK27)-21","Darmstadt - Nürnberg","< >","Großkrotzenburg","Aschaffenbg Hbf",2027,2027,53,1,"01.01.2027","21:00:00","08.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","1FBAC-006","Darmstadt - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2026,2026,32,32,"2026-08-08","18:00:00","2026-08-09","14:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,7",1]
[null,"DB InfraGO AG","1FBAC-009","Darmstadt - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2026,2026,32,33,"2026-08-09","14:00:00","2026-08-10","06:00:00","0d, 16h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"1,7",1]
[null,"DB InfraGO AG","1FC34-008","Darmstadt - Nürnberg","< >","Hallstadt (b Bamberg)","Höflein",2026,2026,31,32,"2026-08-01","14:00:00","2026-08-03","05:00:00","1d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-20",null,null,"1,2",1]
[null,"DB InfraGO AG","1DD26-004","Darmstadt - Nürnberg",">","Haßfurt","Schweinfurt Stadt",2026,2026,31,31,"2026-08-01","08:00:00","2026-08-02","15:30:00","1d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"8,,8",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1FBAC-003","Darmstadt - Nürnberg","< >","Höflein","Hallstadt (b Bamberg)",2026,2026,32,32,"2026-08-07","22:00:00","2026-08-08","18:00:00","0d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"3,4",1]
[null,"DB InfraGO AG","21811-026","Darmstadt - Nürnberg","<","Hohe Wart","Nantenbach",2026,2026,47,47,"2026-11-20","21:00:00","2026-11-22","07:00:00","1d, 10h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1FFFE-001","Darmstadt - Nürnberg",">","Langenprozelten","Lohr Bahnhof",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","202A2-003","Darmstadt - Nürnberg",">","Langenprozelten","Langenprozelten",2026,2026,35,37,"2026-08-28","21:00:00","2026-09-11","05:00:00","13d, 8h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","202A2-004","Darmstadt - Nürnberg","< >","Langenprozelten","Langenprozelten",2026,2026,35,37,"2026-08-28","21:00:00","2026-09-11","05:00:00","13d, 8h","Periodical","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","202A2-005","Darmstadt - Nürnberg","< >","Langenprozelten","Langenprozelten",2026,2026,35,37,"2026-08-28","21:00:00","2026-09-11","05:00:00","13d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1FFFE-005","Darmstadt - Nürnberg","<","Lohr Bahnhof","Langenprozelten",2026,2026,41,42,"2026-10-07","21:00:00","2026-10-12","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-08",null,null,"3,4",1]
[null,"DB InfraGO AG","1FFFE-006","Darmstadt - Nürnberg","<","Lohr Bahnhof","Rohrbach",2026,2026,41,42,"2026-10-07","21:00:00","2026-10-12","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","21811-016","Darmstadt - Nürnberg","<","Lohr Bahnhof","Nantenbach",2026,2026,42,43,"2026-10-18","21:00:00","2026-10-23","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-06-01",null,null,"3,4",1]
[null,"DB InfraGO AG","218BA-002","Darmstadt - Nürnberg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,41,42,"2026-10-11","21:00:00","2026-10-12","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","218BA-004","Darmstadt - Nürnberg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-14","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","218BA-007","Darmstadt - Nürnberg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-23","05:00:00","9d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"4,5",1]
[null,"DB InfraGO AG","218BA-011","Darmstadt - Nürnberg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,49,49,"2026-12-04","21:00:00","2026-12-06","05:00:00","1d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-01",null,null,"2,3",1]
[null,"DB InfraGO AG","218BA-013","Darmstadt - Nürnberg","< >","Mainaschaff Abzw","Mainaschaff Abzw",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-08",null,null,"2,3",1]
[null,"DB InfraGO AG","221C0-001","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Arnstein (Unterfr)",2026,2026,48,48,"2026-11-23","08:00:00","2026-11-23","16:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"5,6",1]
[null,"DB InfraGO AG","221C0-002","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Arnstein (Unterfr)",2026,2026,48,48,"2026-11-24","08:00:00","2026-11-24","16:00:00","0d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"6,7",1]
[null,"DB InfraGO AG","222AD-003","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Wernfeld",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-22","06:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-07",null,null,"1,7",1]
[null,"DB InfraGO AG","222C2-003","Darmstadt - Nürnberg","< >","Mühlhausen (Wern)","Wernfeld",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-22","06:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"1,2",1]
[null,"DB InfraGO AG","1FFFE-003","Darmstadt - Nürnberg","< >","Nantenbach","Nantenbach",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1FFFE-004","Darmstadt - Nürnberg","< >","Nantenbach","Nantenbach",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1FFFE-007","Darmstadt - Nürnberg","< >","Nantenbach","Nantenbach",2026,2026,41,42,"2026-10-07","21:00:00","2026-10-12","05:00:00","4d, 8h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1FFFE-008","Darmstadt - Nürnberg","< >","Nantenbach","Nantenbach",2026,2026,41,42,"2026-10-07","21:00:00","2026-10-12","05:00:00","4d, 8h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"4,5",1]
[null,"DB InfraGO AG","21811-020","Darmstadt - Nürnberg","< >","Nantenbach","Hohe Wart",2026,2026,47,47,"2026-11-20","21:00:00","2026-11-22","07:00:00","1d, 10h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-08-02",null,null,"4,5",1]
[null,"DB InfraGO AG","21811-024","Darmstadt - Nürnberg","< >","Nantenbach","Hohe Wart",2026,2026,47,48,"2026-11-22","19:00:00","2026-11-23","05:00:00","0d, 10h","Continuous","Signal",null,null,"S",null,null,",,",",,",null,",2,",null,null,null,"N",null,"2024-08-02",null,null,"5,6",1]
[null,"DB InfraGO AG","21811-027","Darmstadt - Nürnberg",">","Nantenbach","Lohr Bahnhof",2026,2026,47,48,"2026-11-22","19:00:00","2026-11-23","05:00:00","0d, 10h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-02",null,null,"1,2",1]
[null,"DB InfraGO AG","21811-038","Darmstadt - Nürnberg",">","Nantenbach","Rohrbach",2026,2026,42,43,"2026-10-18","21:00:00","2026-10-23","05:00:00","4d, 8h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1E4C5-005","Darmstadt - Nürnberg","< >","Nürnberg Großmarkt","Fürth (Bay) Gbf",2026,2026,31,32,"2026-07-30","05:00:00","2026-08-06","21:00:00","7d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-26",null,null,"1,7",1]
[null,"DB InfraGO AG","1FA90-050","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Eibach",2026,2026,31,31,"2026-07-31","22:00:00","2026-08-01","03:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-051","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nür Jansenbr",2026,2026,31,31,"2026-08-01","03:00:00","2026-08-01","13:00:00","0d, 10h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3247-(MK27)-01","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2027,2027,1,2,"08.01.2027","21:00:00","15.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3247-(MK27)-02","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2027,2027,21,26,"28.05.2027","21:00:00","02.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","3247-(MK27)-03","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Fürth (Bay) Gbf",2027,2027,41,43,"15.10.2027","21:00:00","29.10.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-01","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,20,22,"21.05.2027","21:00:00","04.06.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-02","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,24,26,"18.06.2027","21:00:00","02.07.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-03","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,41,43,"15.10.2027","21:00:00","29.10.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-04","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,10,11,"12.03.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-05","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,1,2,"08.01.2027","21:00:00","15.01.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","3293-(MK27)-06","Darmstadt - Nürnberg",">","Nürnberg Hbf","Fürth (Bay) Hbf",2027,2027,11,13,"19.03.2027","21:00:00","02.04.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1DDD1-015","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Schwabach",2026,2026,31,38,"2026-07-31","21:00:00","2026-09-15","04:00:00","45d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","2057A-001","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,31,36,"2026-07-30","22:00:00","2026-09-04","06:00:00","35d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-052","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,31,31,"2026-08-01","03:00:00","2026-08-01","13:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-054","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,31,32,"2026-08-02","21:00:00","2026-08-03","02:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-20",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-055","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,33,33,"2026-08-14","22:00:00","2026-08-15","04:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-01-20",null,null,"5,6",1]
[null,"DB InfraGO AG","1FA90-056","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Ost",2026,2026,33,33,"2026-08-14","22:00:00","2026-08-15","04:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-057","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Schweinau",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","02:00:00","2d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-058","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg Hbf",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","02:00:00","2d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","2281F-001","Darmstadt - Nürnberg","< >","Nürnberg Hbf","Nürnberg-Eibach                 (S-Bahn)",2026,2026,31,33,"2026-08-01","23:30:00","2026-08-10","04:30:00","8d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1E4C5-007","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,32,32,"2026-08-07","05:00:00","2026-08-07","21:00:00","0d, 16h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1E4C5-009","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,32,34,"2026-08-08","05:00:00","2026-08-17","21:00:00","9d, 16h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"4,5",1]
[null,"DB InfraGO AG","1E5EA-002","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,40,41,"2026-10-02","05:00:00","2026-10-07","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1E5EA-004","Darmstadt - Nürnberg","< >","Nürnberg Hohe Marter","Fürth (Bay) Gbf",2026,2026,41,42,"2026-10-08","05:00:00","2026-10-13","21:00:00","5d, 16h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1FA90-053","Darmstadt - Nürnberg","< >","Nürnberg-Schweinau","Nürnberg Hbf",2026,2026,31,31,"2026-08-02","13:00:00","2026-08-02","21:00:00","0d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1FFFE-002","Darmstadt - Nürnberg","< >","Rohrbach","Nantenbach",2026,2026,40,41,"2026-10-02","21:00:00","2026-10-07","05:00:00","4d, 8h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21811-023","Darmstadt - Nürnberg","<","Rohrbach","Nantenbach",2026,2026,47,48,"2026-11-22","19:00:00","2026-11-23","05:00:00","0d, 10h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2025-01-21",null,null,"4,5",1]
[null,"DB InfraGO AG","1DDD1-007","Darmstadt - Nürnberg","< >","Roth","Nürnberg Hbf",2026,2026,31,38,"2026-07-28","04:25:00","2026-09-19","04:00:00","52d, 23h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"2,3",1]
[null,"DB InfraGO AG","1DA02-001","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-03","07:00:00","2026-08-28","17:00:00","25d, 10h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-01-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1DA02-002","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,32,"2026-08-08","00:00:00","2026-08-08","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-003","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,33,34,"2026-08-11","23:00:00","2026-08-18","23:00:00","7d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-004","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,34,"2026-08-11","23:00:00","2026-08-18","23:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-005","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","18:00:00","2026-08-22","05:00:00","3d, 11h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-006","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-008","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-009","Darmstadt - Nürnberg","<","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-21","06:00:00","2026-08-23","06:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-010","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-22","00:00:00","2026-08-22","05:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-011","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-22","00:00:00","2026-08-22","05:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-014","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,40,40,"2026-10-02","23:55:00","2026-10-03","06:45:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-025","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-027","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-030","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,41,41,"2026-10-10","00:00:00","2026-10-10","06:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DBBC-001","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,32,33,"2026-08-03","08:00:00","2026-08-10","16:00:00","7d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"6,,6",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-001","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,33,"2026-08-12","08:00:00","2026-08-14","16:00:00","2d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-003","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,33,"2026-08-12","09:30:00","2026-08-14","10:30:00","2d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-005","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Seligenstadt (b Würzburg)",2026,2026,33,34,"2026-08-15","09:30:00","2026-08-18","10:30:00","3d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD2B-002","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,43,44,"2026-10-25","22:00:00","2026-10-27","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,0",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD2B-005","Darmstadt - Nürnberg","<","Schweinfurt Hbf","Schweinfurt Stadt",2026,2026,44,44,"2026-10-27","22:30:00","2026-10-28","05:20:00","0d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-24",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD2B-006","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,44,44,"2026-10-28","22:30:00","2026-10-29","05:20:00","0d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD2B-007","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,44,44,"2026-10-28","22:30:00","2026-10-29","05:20:00","0d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD36-001","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Waigolshausen",2026,2026,48,49,"2026-11-28","22:30:00","2026-11-30","05:00:00","1d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1DD36-002","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,48,49,"2026-11-29","02:00:00","2026-11-30","03:30:00","1d, 1h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD36-003","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,48,49,"2026-11-29","02:00:00","2026-11-30","03:30:00","1d, 1h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD36-005","Darmstadt - Nürnberg",">","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-11-30","22:10:00","2026-12-01","05:20:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD36-006","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-12-01","21:30:00","2026-12-02","05:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1DD36-007","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-03","05:20:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-035","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,40,40,"2026-10-02","23:55:00","2026-10-03","06:45:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-038","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-19","23:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-039","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-21","00:00:00","2026-08-21","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1DA02-041","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Waigolshausen",2026,2026,34,34,"2026-08-21","00:00:00","2026-08-21","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-042","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-07","23:00:00","2026-08-28","23:00:00","21d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-043","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,32,35,"2026-08-07","23:00:00","2026-08-28","23:00:00","21d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-044","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,35,"2026-08-11","08:00:00","2026-08-28","23:00:00","17d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DA02-045","Darmstadt - Nürnberg","< >","Schweinfurt Hbf","Schweinfurt Hbf",2026,2026,33,35,"2026-08-13","08:00:00","2026-08-28","23:00:00","15d, 15h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1DCD7-004","Darmstadt - Nürnberg",">","Seligenstadt (b Würzburg)","Schweinfurt Hbf",2026,2026,33,34,"2026-08-15","08:00:00","2026-08-18","16:00:00","3d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","218BA-001","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,41,42,"2026-10-11","21:00:00","2026-10-12","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,6,1]
[null,"DB InfraGO AG","218BA-005","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-14","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","218BA-008","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-23","05:00:00","9d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,6,1]
[null,"DB InfraGO AG","218BA-009","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,49,49,"2026-12-04","21:00:00","2026-12-06","05:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","218BA-012","Darmstadt - Nürnberg","< >","Stockstadt (Main)","Mainaschaff",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","222C2-005","Darmstadt - Nürnberg","< >","Thüngen (Unterfr)","Wernfeld",2026,2026,31,34,"2026-07-31","06:00:00","2026-08-20","06:00:00","20d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","222AD-005","Darmstadt - Nürnberg","< >","Thüngen (Unterfr)","Wernfeld",2026,2026,31,34,"2026-07-31","06:00:00","2026-08-20","06:00:00","20d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","1DA02-007","Darmstadt - Nürnberg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,34,34,"2026-08-18","23:00:00","2026-08-21","06:00:00","2d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1DA02-026","Darmstadt - Nürnberg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,40,40,"2026-10-04","01:10:00","2026-10-04","05:15:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1DA02-029","Darmstadt - Nürnberg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,41,41,"2026-10-10","00:00:00","2026-10-10","06:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1DCD7-002","Darmstadt - Nürnberg","< >","Waigolshausen","Mühlhausen (Wern)",2026,2026,33,33,"2026-08-12","08:00:00","2026-08-14","16:00:00","2d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","1DCD7-006","Darmstadt - Nürnberg","< >","Waigolshausen","Mühlhausen (Wern)",2026,2026,34,34,"2026-08-19","08:00:00","2026-08-20","16:00:00","1d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1DD36-004","Darmstadt - Nürnberg","<","Waigolshausen","Schweinfurt Hbf",2026,2026,49,49,"2026-11-30","22:10:00","2026-12-01","05:20:00","0d, 7h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","222C2-006","Darmstadt - Nürnberg","< >","Waigolshausen","Wernfeld",2026,2026,34,34,"2026-08-20","06:00:00","2026-08-21","06:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","222AD-006","Darmstadt - Nürnberg","< >","Waigolshausen","Wernfeld",2026,2026,34,34,"2026-08-20","06:00:00","2026-08-21","06:00:00","1d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1056-(MK27)-02","Darmstadt - Nürnberg",">","Waigolshausen","Bamberg",2027,2027,27,34,"09.07.2027","21:00:00","27.08.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1056-(MK27)-04","Darmstadt - Nürnberg",">","Waigolshausen","Bamberg",2027,2027,7,13,"19.02.2027","21:00:00","02.04.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-30",null,null,7,1]
[null,"DB InfraGO AG","1056-(MK27)-06","Darmstadt - Nürnberg",">","Waigolshausen","Bamberg",2027,2027,36,49,"10.09.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1057-(MK27)-02","Darmstadt - Nürnberg","< >","Waigolshausen","Gemünden (Main)",2027,2027,31,32,"07.08.2027","05:00:00","13.08.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1C08E-019","Darmstadt - Nürnberg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,28,32,"2026-07-12","21:00:00","2026-08-07","21:00:00","26d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1C08E-020","Darmstadt - Nürnberg",">","Weiterstadt Stockschneise","Darmstadt Gbf",2026,2026,37,37,"2026-09-12","21:00:00","2026-09-13","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-10",null,null,"3,4",1]
[null,"DB InfraGO AG","221D3-001","Darmstadt - Nürnberg","< >","Wernfeld","Gemünden (Main)",2026,2026,47,50,"2026-11-20","21:00:00","2026-12-11","05:00:00","20d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"4,5",1]
[null,"DB InfraGO AG","202DB-001","Darmstadt - Nürnberg","< >","Wiesthal","Aschaffenburg Hbf",2026,2026,39,40,"2026-09-26","01:00:00","2026-09-29","07:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","202DB-003","Darmstadt - Nürnberg",">","Wiesthal","Aschaffenburg Hbf",2026,2026,46,46,"2026-11-12","22:00:00","2026-11-13","04:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-24",null,null,"4,5",1]
[null,"DB InfraGO AG","202A2-002","Darmstadt - Nürnberg","< >","Zollberg","Langenprozelten",2026,2026,35,35,"2026-08-28","21:00:00","2026-08-29","01:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"5,6",1]
[null,"DB InfraGO AG","202A2-007","Darmstadt - Nürnberg","< >","Zollberg","Langenprozelten",2026,2026,37,37,"2026-09-11","01:00:00","2026-09-11","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,7,1]
[null,"DB InfraGO AG","1FE81-001","Dresden - Děčín","< >","Bad Schandau","Bad Schandau",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"Y",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","2A2E0-006","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,23,45,"2026-06-01","09:10:00","2026-11-02","18:50:00","154d, 10h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"Y",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","2A307-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,45,45,"2026-11-05","22:20:00","2026-11-06","05:20:00","0d, 7h","Continuous","Signal",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-26",null,null,"1,2",1]
[null,"DB InfraGO AG","2A3A6-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,40,40,"2026-09-30","09:10:00","2026-10-04","17:10:00","4d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-26",null,null,"5,6",1]
[null,"DB InfraGO AG","2A3A6-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,41,41,"2026-10-06","09:10:00","2026-10-06","17:10:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2A3A6-006","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,45,45,"2026-11-03","09:10:00","2026-11-05","17:10:00","2d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2A4FD-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,45,45,"2026-11-06","09:10:00","2026-11-08","17:10:00","2d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","2A4FD-004","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,46,46,"2026-11-10","09:10:00","2026-11-13","17:10:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","2A4FD-006","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,49,49,"2026-12-01","09:10:00","2026-12-01","17:10:00","0d, 8h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"N",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","2A51D-002","Dresden - Děčín","< >","Bad Schandau Gr","Bad Schandau",2026,2026,46,50,"2026-11-09","09:10:00","2026-12-07","18:50:00","28d, 9h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,54,"Y",null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-08_D","Dresden - Děčín","< >","Bad Schandau Gr","Pirna",2026,2027,50,13,"12.12.2026","05:00:00","02.04.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP T + ESP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-08_N","Dresden - Děčín",">","Bad Schandau Gr","Pirna",2026,2027,50,13,"11.12.2026","21:00:00","02.04.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"TSP T + ESP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-10_D","Dresden - Děčín","< >","Bad Schandau Gr","Pirna",2027,2027,14,43,"10.04.2027","05:00:00","29.10.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP T + ESP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-10_N","Dresden - Děčín",">","Bad Schandau Gr","Pirna",2027,2027,14,43,"09.04.2027","21:00:00","29.10.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"TSP T + ESP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-12_D","Dresden - Děčín",">","Bad Schandau Gr","Pirna",2027,2027,46,49,"20.11.2027","05:00:00","10.12.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK26)-12_N","Dresden - Děčín","< >","Bad Schandau Gr","Pirna",2027,2027,46,49,"19.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK27)-08_WDN","Dresden - Děčín","< >","Bad Schandau Gr","Pirna",2027,2027,46,46,"15.11.2027","21:00:00","19.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-07-31",null,null,"4,5",1]
[null,"DB InfraGO AG","1162-(MK27)-08_WDD","Dresden - Děčín",">","Bad Schandau Gr","Pirna",2027,2027,46,46,"15.11.2027","05:00:00","19.11.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP VZ + TSP WEuN",null,null,null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","1FE81-002","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"0,,0",null,null,null,"Y",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","2A097-003","Dresden - Děčín","< >","Bad Schandau Ost","Schmilka-Hir",2026,2026,12,45,"2026-03-17","00:01:00","2026-11-05","23:59:00","233d, 23h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4F2-001","Dresden - Děčín","<","Bad Schandau Ost","Schmilka-Hir",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-31",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4F2-002","Dresden - Děčín","< >","Bad Schandau Ost","Bad Schandau Ost",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4F2-003","Dresden - Děčín","< >","Bad Schandau Ost","Schöna",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4F2-004","Dresden - Děčín","< >","Bad Schandau Ost","Schmilka-Hir",2026,2026,45,50,"2026-11-06","00:01:00","2026-12-12","23:59:00","36d, 23h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","1BDCA-002","Dresden - Děčín","< >","Neustadt (Sachs)","Bad Schandau",2026,2026,16,36,"2026-04-17","22:00:00","2026-09-05","04:00:00","140d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,null,null,null,"4,5",1]
[null,"DB InfraGO AG","1BF33-001","Dresden - Děčín","< >","Neustadt (Sachs)","Bad Schandau",2026,2026,45,45,"2026-11-06","22:00:00","2026-11-07","06:00:00","0d, 8h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"4,5",1]
[null,"DB InfraGO AG","2A097-001","Dresden - Děčín",">","Schmilka-Hir","Bad Schandau Ost",2026,2026,12,45,"2026-03-17","00:01:00","2026-11-05","23:59:00","233d, 23h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2024-07-31",null,null,"1,7",1]
[null,"DB InfraGO AG","2A097-002","Dresden - Děčín","< >","Schöna","Bad Schandau Ost",2026,2026,12,45,"2026-03-17","00:01:00","2026-11-05","23:59:00","233d, 23h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2A2E0-005","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,23,45,"2026-06-01","09:10:00","2026-11-02","18:50:00","154d, 10h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","2A307-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-05","22:20:00","2026-11-06","05:20:00","0d, 7h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,1,1]
[null,"DB InfraGO AG","2A3A6-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,40,40,"2026-09-30","09:10:00","2026-10-04","17:10:00","4d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","2A3A6-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,41,41,"2026-10-06","09:10:00","2026-10-06","17:10:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","2A3A6-005","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-03","09:10:00","2026-11-05","17:10:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","2A4FD-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,45,45,"2026-11-06","09:10:00","2026-11-08","17:10:00","2d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4FD-003","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,46,46,"2026-11-10","09:10:00","2026-11-13","17:10:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","2A4FD-005","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,49,49,"2026-12-01","09:10:00","2026-12-01","17:10:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"2,3",1]
[null,"DB InfraGO AG","2A51D-001","Dresden - Děčín","< >","Schöna","Bad Schandau",2026,2026,46,50,"2026-11-09","09:10:00","2026-12-07","18:50:00","28d, 9h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1BE30-001","Dresden - Děčín","< >","Sebnitz (Sachs)","Bad Schandau",2026,2026,34,35,"2026-08-17","22:00:00","2026-08-30","05:00:00","12d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-12",null,null,1,1]
[null,"DB InfraGO AG","1BF23-001","Dresden - Děčín","< >","Sebnitz (Sachs)","Bad Schandau",2026,2026,16,32,"2026-04-17","22:00:00","2026-08-05","18:00:00","109d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-24",null,null,1,1]
[null,"DB InfraGO AG","1C092-005","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Coswig (bei Dresden)",2026,2026,38,41,"2026-09-16","07:00:00","2026-10-05","16:00:00","19d, 9h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1C092-012","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Coswig (bei Dresden)",2026,2026,40,40,"2026-09-28","04:00:00","2026-10-03","06:00:00","5d, 2h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-22",null,null,"1,7",1]
[null,"DB InfraGO AG","1C092-014","Falkenberg - Dresden","<","Coswig (bei Dresden)","Radebeul-Naundorf                 (Abzw)",2026,2026,40,40,"2026-09-28","04:00:00","2026-10-03","06:00:00","5d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","1C092-015","Falkenberg - Dresden","< >","Coswig (bei Dresden)","Coswig (bei Dresden)",2026,2026,40,40,"2026-09-28","04:00:00","2026-10-03","06:00:00","5d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1C092-007","Falkenberg - Dresden","< >","Coswig (bei Dresden) Stw 1","Radebeul-Naundorf                 (Abzw)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1C092-010","Falkenberg - Dresden","< >","Coswig (bei Dresden) Stw 1","Radebeul-Naundorf                 (Abzw)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1C092-011","Falkenberg - Dresden","< >","Coswig (bei Dresden) Stw 1","Coswig (bei Dresden)",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1C107-001","Falkenberg - Dresden","< >","Elsterwerda","Elsterwerda-Biehla",2026,2026,37,40,"2026-09-13","23:40:00","2026-09-28","04:20:00","14d, 4h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1C2D3-002","Falkenberg - Dresden","<","Elsterwerda","Elsterwerda",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1C2D3-003","Falkenberg - Dresden","<","Elsterwerda","Hohenleipisch",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1C2D3-005","Falkenberg - Dresden","< >","Elsterwerda","Elsterwerda",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-01",null,null,"3,4",1]
[null,"DB InfraGO AG","1C2D3-006","Falkenberg - Dresden",">","Elsterwerda","Frauenhain",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","04:00:00","2d, 6h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-07-26",null,null,"6,7",1]
[null,"DB InfraGO AG","1C539-001","Falkenberg - Dresden","<","Elsterwerda","Gröditz (b Riesa)",2026,2026,49,49,"2026-11-30","08:00:00","2026-12-04","18:00:00","4d, 10h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-26",null,null,"6,7",1]
[null,"DB InfraGO AG","1C539-003","Falkenberg - Dresden",">","Gröditz (b Riesa)","Elsterwerda",2026,2026,50,50,"2026-12-07","08:00:00","2026-12-11","18:00:00","4d, 10h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF3C-010","Falkenberg - Dresden","<","Kottewitz","Radebeul-Naundorf",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1BF3C-012","Falkenberg - Dresden","<","Kottewitz","Radebeul Abzw Az",2026,2026,33,36,"2026-08-12","08:00:00","2026-08-31","16:00:00","19d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF59-001","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,40,41,"2026-10-04","20:00:00","2026-10-05","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF59-003","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1BF59-005","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf                 (Abzw)",2026,2026,50,50,"2026-12-11","20:00:00","2026-12-12","04:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1BF59-007","Falkenberg - Dresden","<","Kottewitz","Weinböhla",2026,2026,41,47,"2026-10-05","04:00:00","2026-11-19","20:00:00","45d, 17h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1BF59-009","Falkenberg - Dresden","<","Kottewitz","Weinböhla",2026,2026,48,50,"2026-11-27","08:00:00","2026-12-11","16:00:00","14d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-24",null,null,"3,4",1]
[null,"DB InfraGO AG","1BF59-012","Falkenberg - Dresden","< >","Kottewitz","Radebeul-Naundorf",2026,2026,41,50,"2026-10-05","04:00:00","2026-12-11","20:00:00","67d, 17h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1D405-004","Falkenberg - Dresden","< >","Kottewitz","Leckwitz",2026,2026,37,39,"2026-09-07","05:00:00","2026-09-21","05:00:00","14d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1D405-008","Falkenberg - Dresden","<","Kottewitz","Leckwitz",2026,2026,39,39,"2026-09-21","05:00:00","2026-09-22","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1D405-010","Falkenberg - Dresden","<","Kottewitz","Leckwitz",2026,2026,39,39,"2026-09-22","05:00:00","2026-09-23","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1D405-003","Falkenberg - Dresden","< >","Leckwitz","Kottewitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1D405-009","Falkenberg - Dresden",">","Leckwitz","Kottewitz",2026,2026,39,39,"2026-09-21","05:00:00","2026-09-22","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-29",null,null,"1,7",1]
[null,"DB InfraGO AG","1D405-011","Falkenberg - Dresden",">","Leckwitz","Kottewitz",2026,2026,39,39,"2026-09-22","05:00:00","2026-09-23","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1D405-012","Falkenberg - Dresden","< >","Leckwitz","Kottewitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1388-(MK26)-02_D","Falkenberg - Dresden",">","Leckwitz","Priestewitz",2027,2027,19,27,"15.05.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1388-(MK26)-02_N","Falkenberg - Dresden","< >","Leckwitz","Priestewitz",2027,2027,19,27,"14.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","1C092-008","Falkenberg - Dresden",">","Meißen","Coswig (bei Dresden) Stw 1",2026,2026,39,40,"2026-09-25","23:00:00","2026-09-28","04:00:00","2d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-30",null,null,"1,2",1]
[null,"DB InfraGO AG","1652-(MK26)-02_D","Falkenberg - Dresden",">","Priestewitz","Coswig Stw 1",2027,2027,19,27,"15.05.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-24",null,null,"2,3",1]
[null,"DB InfraGO AG","1652-(MK26)-02_N","Falkenberg - Dresden","< >","Priestewitz","Coswig Stw 1",2027,2027,19,27,"14.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1652-(MK27)-01","Falkenberg - Dresden","< >","Priestewitz","Coswig Stw 1",2027,2027,27,29,"10.07.2027","05:00:00","23.07.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1D405-001","Falkenberg - Dresden","< >","Priestewitz","Leckwitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1D405-005","Falkenberg - Dresden","<","Priestewitz","Weißig (b Großenhain)",2026,2026,37,39,"2026-09-07","05:00:00","2026-09-21","05:00:00","14d, 0h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-29",null,null,"5,6",1]
[null,"DB InfraGO AG","1D405-002","Falkenberg - Dresden","< >","Weißig (b Großenhain)","Leckwitz",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-07","05:00:00","2d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-07",null,null,"3,4",1]
[null,"DB InfraGO AG","1D405-006","Falkenberg - Dresden","<","Weißig (b Großenhain)","Weißig (b Großenhain)",2026,2026,37,39,"2026-09-07","05:00:00","2026-09-21","05:00:00","14d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-07",null,null,"3,4",1]
[null,"DB InfraGO AG","1BAE4-017","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,30,50,"2026-07-22","21:00:00","2026-12-12","23:59:00","143d, 3h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-019","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,28,50,"2026-07-10","05:00:00","2026-12-12","23:59:00","155d, 19h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","1BAE4-020","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,29,50,"2026-07-17","21:00:00","2026-12-12","23:59:00","148d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"5,6",1]
[null,"DB InfraGO AG","1BAE4-021","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,29,50,"2026-07-17","21:00:00","2026-12-12","23:59:00","148d, 3h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1BAE4-024","Frankfurt - Karlsruhe","< >","Bensheim","Bensheim",2026,2026,36,36,"2026-09-03","21:00:00","2026-09-04","05:00:00","0d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1BAE4-023","Frankfurt - Karlsruhe",">","Bensheim-Auerbach","Heppenheim (Bergstr)",2026,2026,36,36,"2026-09-02","21:00:00","2026-09-03","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-31",null,null,"3,4",1]
[null,"DB InfraGO AG","1F71F-002","Frankfurt - Karlsruhe",">","Blankenloch","Karlsruhe-Hagsfeld",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-08-09",null,null,"1,2",1]
[null,"DB InfraGO AG","1F71F-005","Frankfurt - Karlsruhe","< >","Blankenloch","Karlsruhe Hbf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-09",null,null,"1,2",1]
[null,"DB InfraGO AG","1154-(MK25)-01_WDN","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,20,27,"17.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP N + TSP WEN",null,null,null,"2024-04-29",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK25)-01_WEN","Frankfurt - Karlsruhe","< >","Bruchsal","Mühlacker",2027,2027,19,27,"14.05.2027","21:00:00","05.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP N + TSP WEN",null,null,null,"2024-07-03",null,null,4,1]
[null,"DB InfraGO AG","1154-(MK26)-09_WDN","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,7,11,"15.02.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP N + TSP WEN",null,null,null,"2024-04-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK26)-09_WEN","Frankfurt - Karlsruhe","< >","Bruchsal","Mühlacker",2027,2027,6,11,"12.02.2027","21:00:00","15.03.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP N + TSP WEN",null,null,null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK27)-02","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,1,6,"08.01.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK27)-06","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-03",null,null,"3,4",1]
[null,"DB InfraGO AG","1154-(MK27)-14","Frankfurt - Karlsruhe",">","Bruchsal","Mühlacker",2027,2027,35,49,"03.09.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-05-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-005","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Blankenloch",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"2,3",1]
[null,"DB InfraGO AG","1D41F-006","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-008","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-009","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-010","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-011","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-012","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-013","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-014","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-015","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Blankenloch",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-13",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-016","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1D41F-017","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-30","22:00:00","2026-11-02","04:00:00","2d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1D41F-018","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1D41F-019","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-020","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-021","Frankfurt - Karlsruhe","<","Graben-Neudorf","Bruchsal",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1D4EB-001","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-04","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-002","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-003","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Friedrichstal (Baden)",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-004","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-02","04:00:00","2026-11-08","04:00:00","6d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-005","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-006","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-04","04:00:00","2026-11-06","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-15",null,null,"2,3",1]
[null,"DB InfraGO AG","1D4EB-007","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,45,"2026-11-07","06:00:00","2026-11-08","22:00:00","1d, 16h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-15",null,null,"6,7",1]
[null,"DB InfraGO AG","1D41F-022","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"6,7",1]
[null,"DB InfraGO AG","1D41F-023","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-02","22:00:00","2026-11-10","06:00:00","7d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-025","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-026","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-027","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-06",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-029","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-030","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,44,"2026-10-29","22:00:00","2026-10-30","22:00:00","1d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1D41F-031","Frankfurt - Karlsruhe","< >","Graben-Neudorf","Graben-Neudorf",2026,2026,44,45,"2026-10-31","22:00:00","2026-11-02","04:00:00","1d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-20",null,null,"4,5",1]
[null,"DB InfraGO AG","1896-(MK27)-21","Frankfurt - Karlsruhe","< >","Hanau Südseite","Großkrotzenburg",2027,2027,1,4,"08.01.2027","21:00:00","29.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-06-20",null,null,"3,4",1]
[null,"DB InfraGO AG","1896-(MK27)-23","Frankfurt - Karlsruhe","< >","Hanau Südseite","Großkrotzenburg",2027,2027,53,1,"01.01.2027","21:00:00","08.01.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-25",null,null,"3,4",1]
[null,"DB InfraGO AG","1146-(MK27)-01","Frankfurt - Karlsruhe","< >","Heidelberg Hbf","Bruchsal",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-08-13",null,null,"4,5",1]
[null,"DB InfraGO AG","1F485-001","Frankfurt - Karlsruhe","< >","Hemsbach","Weinheim (Bergstr) Hbf",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"Y",null,"2024-08-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1F485-041","Frankfurt - Karlsruhe","< >","Hemsbach","Weinheim (Bergstr) Hbf",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1BAE4-022","Frankfurt - Karlsruhe","<","Heppenheim (Bergstr)","Bensheim-Auerbach",2026,2026,36,36,"2026-09-01","21:00:00","2026-09-02","05:00:00","0d, 8h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-11",null,null,"5,6",1]
[null,"DB InfraGO AG","1F71F-006","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1F71F-007","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1F71F-018","Frankfurt - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2026,2026,46,46,"2026-11-12","23:30:00","2026-11-13","04:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1F71F-020","Frankfurt - Karlsruhe",">","Karlsruhe Gbf","Karlsruhe-Hagsfeld",2026,2026,46,46,"2026-11-12","23:30:00","2026-11-13","04:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-12-13",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-01","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,10,11,"12.03.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-02","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,19,21,"15.05.2027","05:00:00","28.05.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-07-31",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-03","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,29,31,"23.07.2027","21:00:00","06.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-07-24",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-04","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,32,33,"13.08.2027","21:00:00","20.08.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-08",null,null,"1,2",1]
[null,"DB InfraGO AG","3007-(MK27)-05","Frankfurt - Karlsruhe","< >","Karlsruhe Gbf","Karlsruhe-Durlach",2027,2027,33,34,"20.08.2027","21:00:00","23.08.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-05-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1E501-017","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,35,37,"2026-08-29","00:00:00","2026-09-11","23:59:00","13d, 23h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1E550-001","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1E550-006","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Grötzingen",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1E550-020","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Grötzingen",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-21",null,null,"3,4",1]
[null,"DB InfraGO AG","1E5BF-004","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Weingarten (Baden)",2026,2026,37,37,"2026-09-11","15:00:00","2026-09-11","21:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2025-01-21",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-003","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2025-01-21",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-005","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-007","Frankfurt - Karlsruhe","<","Karlsruhe Hbf","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-008","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-011","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-012","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1F08E-013","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1F08E-015","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,37,37,"2026-09-07","22:00:00","2026-09-11","06:00:00","3d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1F08E-017","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,37,37,"2026-09-07","22:00:00","2026-09-11","06:00:00","3d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",1,1",null,null,null,"N",null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1F08E-018","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe Hbf",2026,2026,37,37,"2026-09-07","22:00:00","2026-09-11","06:00:00","3d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK26)-01","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,28,29,"16.07.2027","21:00:00","19.07.2027","05:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WE",null,null,null,"2024-07-26",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK27)-02","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,9,10,"05.03.2027","21:00:00","12.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK27)-03","Frankfurt - Karlsruhe",">","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,14,18,"10.04.2027","05:00:00","07.05.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3658-(MK27)-04","Frankfurt - Karlsruhe","< >","Karlsruhe Hbf","Karlsruhe-Durlach",2027,2027,32,33,"13.08.2027","21:00:00","16.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-08-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1E501-019","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,37,"2026-08-29","18:00:00","2026-09-12","12:00:00","13d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-11-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1E501-020","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1E501-022","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,7",1]
[null,"DB InfraGO AG","1E501-023","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"6,7",1]
[null,"DB InfraGO AG","1E501-024","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E501-026","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E501-027","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-002","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-11",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-004","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-005","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-007","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-008","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,37,"2026-09-04","21:00:00","2026-09-08","15:00:00","3d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-010","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-011","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-013","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-06",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-014","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-016","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1E550-017","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-018","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-019","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-021","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-022","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","15:00:00","2026-09-11","21:00:00","3d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-024","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1E550-025","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-002","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-003","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Gbf",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-005","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,37,"2026-09-11","15:00:00","2026-09-11","21:00:00","0d, 6h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-007","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,38,"2026-09-11","21:00:00","2026-09-16","08:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1E5BF-008","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,37,38,"2026-09-11","21:00:00","2026-09-16","08:00:00","4d, 11h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-19",null,null,"6,7",1]
[null,"DB InfraGO AG","1F08E-006","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1F08E-009","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-11",null,null,"6,7",1]
[null,"DB InfraGO AG","1F08E-010","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe-Durlach",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-11","22:00:00","5d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-09-16",null,null,"6,7",1]
[null,"DB InfraGO AG","1153-(MK27)-01","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Mühlacker",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-09-16",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK26)-01","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,28,29,"16.07.2027","21:00:00","19.07.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK26)-05","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,27,28,"09.07.2027","21:00:00","12.07.2027","05:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WE",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-02","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,10,11,"12.03.2027","21:00:00","19.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-03","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,18,21,"08.05.2027","05:00:00","28.05.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-04","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,29,31,"23.07.2027","21:00:00","06.08.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-06_D","Frankfurt - Karlsruhe",">","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,32,33,"14.08.2027","05:00:00","20.08.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","3005-(MK27)-06_N","Frankfurt - Karlsruhe","< >","Karlsruhe-Durlach","Karlsruhe Hbf",2027,2027,32,33,"13.08.2027","21:00:00","20.08.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-10-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1F71F-001","Frankfurt - Karlsruhe","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1F71F-003","Frankfurt - Karlsruhe","< >","Karlsruhe-Hagsfeld","Karlsruhe-Hagsfeld",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-11-22",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1F71F-004","Frankfurt - Karlsruhe","<","Karlsruhe-Hagsfeld","Karlsruhe Gbf",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-13","04:00:00","13d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-07",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1F71F-008","Frankfurt - Karlsruhe","< >","Karlsruhe-Hagsfeld","Karlsruhe-Hagsfeld",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","22:00:00","7d, 1h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-18",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1C651-003","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C651-004","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-12",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C651-006","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,37,37,"2026-09-07","21:00:00","2026-09-11","05:00:00","3d, 8h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C651-009","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C651-010","Frankfurt - Karlsruhe","< >","Ludwigsburg","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1699-(MK27)-01","Frankfurt - Karlsruhe",">","Ludwigsburg","Bietigheim-Biss",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-11-08",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","1699-(MK27)-02","Frankfurt - Karlsruhe",">","Ludwigsburg","Bietigheim-Biss",2027,2027,6,7,"12.02.2027","21:00:00","15.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WEN",null,null,null,"2024-11-08",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","1699-(MK27)-03","Frankfurt - Karlsruhe",">","Ludwigsburg","Bietigheim-Biss",2027,2027,20,21,"21.05.2027","21:00:00","24.05.2027","05:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WE",null,null,null,"2024-11-08",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","3039-(MK27)-04","Frankfurt - Karlsruhe",">","Ludwigsburg","Pragtunnel",2027,2027,26,27,"02.07.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-11-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3039-(MK27)-05","Frankfurt - Karlsruhe","< >","Ludwigsburg","Pragtunnel",2027,2027,46,47,"19.11.2027","21:00:00","26.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-11-08",null,null,"5,6",1]
[null,"DB InfraGO AG","1557-(MK26)-15","Frankfurt - Karlsruhe","< >","N-Edingen/F-feld","Heidelb-Wiebl",2027,2027,5,27,"05.02.2027","21:00:00","09.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-11-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F485-002","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"Y",null,"2024-11-18",null,null,7,1]
[null,"DB InfraGO AG","1F4F8-031","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,8,50,"2026-02-16","12:00:00","2026-12-12","23:59:00","299d, 11h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F485-042","Frankfurt - Karlsruhe","< >","Neu-Edingen/Mhm-Friedrichsfeld","Heidelberg-Wieblingen",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-24",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D41F-024","Frankfurt - Karlsruhe",">","Philippsburg Molzau","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-28",null,null,"3,4",1]
[null,"DB InfraGO AG","1D41F-001","Frankfurt - Karlsruhe","< >","Schwetzingen","Schwetzingen",2026,2026,43,47,"2026-10-20","22:00:00","2026-11-16","22:00:00","27d, 1h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1D41F-028","Frankfurt - Karlsruhe","< >","Waghäusel Saalbach","Graben-Neudorf",2026,2026,45,46,"2026-11-06","22:00:00","2026-11-09","06:00:00","2d, 8h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E501-021","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,35,36,"2026-08-29","21:00:00","2026-09-04","21:00:00","6d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E550-009","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E550-012","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E550-015","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-08","09:00:00","2026-09-08","15:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E550-023","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-08","22:00:00","2026-09-09","04:00:00","0d, 6h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"5,6",1]
[null,"DB InfraGO AG","1E5BF-001","Frankfurt - Karlsruhe","< >","Weingarten (Baden)","Karlsruhe Hbf",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-10","05:00:00","0d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-16",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-003","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"Y",null,"2025-01-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1F485-043","Frankfurt - Karlsruhe","< >","Weinheim (Bergstr) Hbf","Neu-Edingen/Mhm-Friedrichsfeld",2026,2026,6,50,"2026-02-02","21:00:00","2026-12-12","23:59:00","313d, 2h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1FB56-007","Hamburg - Magdeburg",">","Bindfelde Abzw","Stendal Hauptbahnhof",2026,2026,30,37,"2026-07-24","21:00:00","2026-09-11","05:00:00","48d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-17",null,null,"5,6",1]
[null,"DB InfraGO AG","1FB56-015","Hamburg - Magdeburg",">","Bindfelde Abzw","Stendal Hauptbahnhof",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-17",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1D99F-001","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2026,2026,37,37,"2026-09-12","00:00:00","2026-09-13","15:00:00","1d, 15h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,7,1]
[null,"DB InfraGO AG","1D970-008","Hamburg - Magdeburg","< >","Buchholz (Nordheide)","Hamburg-Harburg",2026,2026,48,48,"2026-11-26","23:30:00","2026-11-27","04:30:00","0d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,7,1]
[null,"DB InfraGO AG","1A813-022","Hamburg - Magdeburg",">","Harbke","Helmstedt",2026,2026,34,34,"2026-08-22","05:00:00","2026-08-22","06:25:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-22",null,null,"5,6",1]
[null,"DB InfraGO AG","1A813-001","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,35,"2026-08-03","00:00:00","2026-08-29","00:00:00","26d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-04",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-002","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,35,"2026-08-03","00:00:00","2026-08-29","00:00:00","26d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,7",1]
[null,"DB InfraGO AG","1A813-003","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,33,"2026-08-03","07:00:00","2026-08-13","17:00:00","10d, 10h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-004","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,33,"2026-08-03","07:00:00","2026-08-13","17:00:00","10d, 10h","Periodical","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-005","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,32,"2026-08-04","07:00:00","2026-08-04","15:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-006","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,32,32,"2026-08-04","07:00:00","2026-08-04","15:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-007","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,35,"2026-08-14","07:00:00","2026-08-29","07:00:00","15d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-008","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,35,"2026-08-14","07:00:00","2026-08-29","07:00:00","15d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-009","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,35,"2026-08-14","07:00:00","2026-08-29","07:00:00","15d, 0h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1A813-011","Hamburg - Magdeburg","<","Helmstedt","Harbke",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-013","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-014","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-015","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,34,34,"2026-08-18","10:00:00","2026-08-22","10:00:00","4d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-016","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,34,34,"2026-08-18","10:00:00","2026-08-22","10:00:00","4d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-018","Hamburg - Magdeburg","<","Helmstedt","Helmstedt",2026,2026,34,34,"2026-08-20","23:00:00","2026-08-22","05:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"3,4,5,6",1]
[null,"DB InfraGO AG","1A813-020","Hamburg - Magdeburg","< >","Helmstedt","Harbke",2026,2026,34,34,"2026-08-22","00:25:00","2026-08-22","05:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1A813-021","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt Grenze",2026,2026,34,34,"2026-08-22","00:25:00","2026-08-22","06:25:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-023","Hamburg - Magdeburg","<","Helmstedt","Frellstedt",2026,2026,34,34,"2026-08-22","05:00:00","2026-08-22","06:25:00","0d, 1h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-024","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt Grenze",2026,2026,34,35,"2026-08-22","06:25:00","2026-08-28","21:00:00","6d, 14h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-025","Hamburg - Magdeburg","<","Helmstedt","Helmstedt",2026,2026,34,35,"2026-08-22","06:25:00","2026-08-28","21:00:00","6d, 14h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-026","Hamburg - Magdeburg",">","Helmstedt","Helmstedt",2026,2026,34,35,"2026-08-22","06:25:00","2026-08-28","21:00:00","6d, 14h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-12-22",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-027","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,34,35,"2026-08-22","06:25:00","2026-08-28","21:00:00","6d, 14h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-029","Hamburg - Magdeburg","< >","Helmstedt","Harbke",2026,2026,35,35,"2026-08-28","15:00:00","2026-08-28","21:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,7",1]
[null,"DB InfraGO AG","1A813-030","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,35,35,"2026-08-28","21:00:00","2026-08-29","03:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1A852-002","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,44,45,"2026-11-01","23:00:00","2026-11-02","05:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1A852-005","Hamburg - Magdeburg","<","Helmstedt","Frellstedt",2026,2026,45,45,"2026-11-03","03:00:00","2026-11-04","05:00:00","1d, 2h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1A852-007","Hamburg - Magdeburg","< >","Helmstedt","Helmstedt",2026,2026,45,46,"2026-11-08","23:00:00","2026-11-09","05:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1A852-010","Hamburg - Magdeburg","<","Helmstedt","Frellstedt",2026,2026,46,46,"2026-11-10","03:00:00","2026-11-11","05:00:00","1d, 2h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"6,7",1]
[null,"DB InfraGO AG","1A852-004","Hamburg - Magdeburg","< >","Helmstedt Grenze","Helmstedt",2026,2026,45,45,"2026-11-02","23:00:00","2026-11-04","05:00:00","1d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1A852-009","Hamburg - Magdeburg","< >","Helmstedt Grenze","Helmstedt",2026,2026,46,46,"2026-11-09","23:00:00","2026-11-11","05:00:00","1d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","23082-002","Hamburg - Magdeburg","<","Lüneburg","Uelzen Gbf",2026,2026,28,50,"2026-07-10","21:00:00","2026-12-12","23:59:00","155d, 3h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-001","Hamburg - Magdeburg","< >","Lüneburg Gbf","Klein Süstedt",2026,2026,42,43,"2026-10-18","22:00:00","2026-10-19","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-004","Hamburg - Magdeburg","< >","Lüneburg Gbf","Klein Süstedt",2026,2026,44,44,"2026-10-31","23:00:00","2026-11-01","05:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-007","Hamburg - Magdeburg","< >","Lüneburg Gbf","Klein Süstedt",2026,2026,48,49,"2026-11-27","05:00:00","2026-11-30","05:00:00","3d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,7",1]
[null,"DB InfraGO AG","1B3BA-001","Hamburg - Magdeburg","< >","Magdeburg-Sudenburg","Magdeburg-Sudenburg",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1C2F9-003","Hamburg - Magdeburg","<","Marienborn","Eilsleben (b Magdeburg)",2026,2026,33,35,"2026-08-14","22:00:00","2026-08-28","22:00:00","14d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1CBF8-006","Hamburg - Magdeburg","<","Marienborn","Eilsleben (b Magdeburg)",2026,2026,41,42,"2026-10-10","03:00:00","2026-10-12","04:30:00","2d, 1h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1CBF8-009","Hamburg - Magdeburg","<","Marienborn","Eilsleben (b Magdeburg)",2026,2026,42,43,"2026-10-17","21:30:00","2026-10-19","04:30:00","1d, 7h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1E2B5-003","Hamburg - Magdeburg","<","Maschen Rbf (Mnwf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","23:00:00","2026-10-30","04:00:00","13d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E2B5-001","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","21:00:00","2026-10-31","05:00:00","14d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1E2B5-002","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Mswf)",2026,2026,42,44,"2026-10-16","21:00:00","2026-10-31","05:00:00","14d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1E2B5-004","Hamburg - Magdeburg","<","Maschen Rbf (Mswf)","Maschen Rbf (Msof)",2026,2026,44,44,"2026-10-31","02:00:00","2026-11-01","16:00:00","1d, 14h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1FFB7-001","Hamburg - Magdeburg","< >","Oebisfelde","Lehrte",2026,2026,36,36,"2026-09-06","01:15:00","2026-09-06","06:10:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","21012-002","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,36,37,"2026-08-31","08:00:00","2026-09-11","16:00:00","11d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-12-14",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","21012-003","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,36,37,"2026-08-31","08:00:00","2026-09-11","16:00:00","11d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-12-14",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21012-004","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,37,37,"2026-09-07","08:00:00","2026-09-08","16:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-10-22",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21012-005","Hamburg - Magdeburg","< >","Salzwedel","Schnega",2026,2026,38,38,"2026-09-14","00:00:00","2026-09-14","01:00:00","0d, 1h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21012-006","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,38,38,"2026-09-14","00:00:00","2026-09-14","01:00:00","0d, 1h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","21012-008","Hamburg - Magdeburg","< >","Salzwedel","Salzwedel",2026,2026,39,39,"2026-09-21","08:00:00","2026-09-22","16:00:00","1d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","21012-009","Hamburg - Magdeburg","< >","Salzwedel","Schnega",2026,2026,39,39,"2026-09-26","00:00:00","2026-09-26","01:00:00","0d, 1h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-12",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","210E1-001","Hamburg - Magdeburg","< >","Salzwedel","Wieren",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","21012-007","Hamburg - Magdeburg","< >","Salzwedel Gbf","Salzwedel",2026,2026,38,39,"2026-09-14","08:00:00","2026-09-25","16:00:00","11d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-05",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21012-010","Hamburg - Magdeburg","< >","Salzwedel Gbf","Salzwedel",2026,2026,39,39,"2026-09-26","00:00:00","2026-09-26","01:00:00","0d, 1h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-05",null,null,"5,6,7",1]
[null,"DB InfraGO AG","20EDE-001","Hamburg - Magdeburg","< >","Schnega","Veerßen",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20EDE-002","Hamburg - Magdeburg","< >","Schnega","Veerßen",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20409-019","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,35,36,"2026-08-28","21:00:00","2026-09-04","05:00:00","6d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","206C8-002","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,40,50,"2026-10-02","05:00:00","2026-12-12","23:59:00","71d, 19h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","20A85-002","Hamburg - Magdeburg","< >","Stendal Gbf","Oebisfelde",2026,2026,48,48,"2026-11-28","21:00:00","2026-11-29","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","227AF-001","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,36,36,"2026-08-31","08:00:00","2026-09-04","08:00:00","4d, 0h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3",1]
[null,"DB InfraGO AG","227AF-002","Hamburg - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,37,37,"2026-09-07","22:00:00","2026-09-09","06:00:00","1d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"3,4",1]
[null,"DB InfraGO AG","1FB6A-001","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB6A-002","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1FB56-011","Hamburg - Magdeburg","<","Stendal Hauptbahnhof","Bindfelde Abzw",2026,2026,38,39,"2026-09-18","21:00:00","2026-09-25","05:00:00","6d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20185-011","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Geestgottberg",2026,2026,46,46,"2026-11-15","01:00:00","2026-11-15","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20185-013","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal) Hp",2026,2026,46,46,"2026-11-15","01:00:00","2026-11-15","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"2,3",1]
[null,"DB InfraGO AG","20185-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangermünde",2026,2026,46,46,"2026-11-15","01:00:00","2026-11-15","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"3,4",1]
[null,"DB InfraGO AG","20A85-010","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Geestgottberg",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"3,4",1]
[null,"DB InfraGO AG","20A85-012","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Gbf",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"3,4",1]
[null,"DB InfraGO AG","20A85-013","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Kläden (Kr Stendal)",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20A85-014","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangermünde",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-005","Hamburg - Magdeburg",">","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","08:00:00","2026-09-12","10:00:00","0d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-006","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21013-007","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","21013-008","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,35,35,"2026-08-29","08:00:00","2026-08-29","18:00:00","0d, 10h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","21013-010","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","08:00:00","2026-09-12","10:00:00","0d, 2h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-20",null,null,"1,2",1]
[null,"DB InfraGO AG","21013-012","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","10:00:00","2026-09-12","12:00:00","0d, 2h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","21013-014","Hamburg - Magdeburg","<","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,37,37,"2026-09-12","12:00:00","2026-09-12","14:00:00","0d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","21013-016","Hamburg - Magdeburg","< >","Stendal Hauptbahnhof","Tangerhütte Betriebsbahnhof",2026,2026,37,37,"2026-09-12","12:00:00","2026-09-12","14:00:00","0d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1040-(MK27)-11","Hamburg - Magdeburg","< >","Stendal Hbf","Glindenberg",2027,2027,42,43,"22.10.2027","21:00:00","25.10.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-05-21",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1040-(MK27)-12","Hamburg - Magdeburg","< >","Stendal Hbf","Glindenberg",2027,2027,44,45,"05.11.2027","21:00:00","08.11.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-05-21",null,null,"1,2,3",1]
[null,"DB InfraGO AG","20185-012","Hamburg - Magdeburg","< >","Tangerhütte","Stendal Hauptbahnhof",2026,2026,46,46,"2026-11-15","01:00:00","2026-11-15","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO AG","20A85-011","Hamburg - Magdeburg","< >","Tangerhütte","Stendal Hauptbahnhof",2026,2026,48,48,"2026-11-29","01:00:00","2026-11-29","05:00:00","0d, 4h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"2,3",1]
[null,"DB InfraGO AG","21013-004","Hamburg - Magdeburg",">","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","08:00:00","2026-09-12","10:00:00","0d, 2h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","21013-011","Hamburg - Magdeburg","< >","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","10:00:00","2026-09-12","12:00:00","0d, 2h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","21013-013","Hamburg - Magdeburg","< >","Tangerhütte Betriebsbahnhof","Stendal Hauptbahnhof",2026,2026,37,37,"2026-09-12","10:00:00","2026-09-12","12:00:00","0d, 2h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","22E57-002","Hamburg - Magdeburg","< >","Uelzen","Ebstorf (Kr Uelzen)",2026,2026,42,43,"2026-10-18","22:00:00","2026-10-19","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-005","Hamburg - Magdeburg","< >","Uelzen","Ebstorf (Kr Uelzen)",2026,2026,44,44,"2026-10-31","23:00:00","2026-11-01","05:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22E57-008","Hamburg - Magdeburg","< >","Uelzen","Ebstorf (Kr Uelzen)",2026,2026,48,49,"2026-11-27","05:00:00","2026-11-30","05:00:00","3d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20EDE-003","Hamburg - Magdeburg","< >","Uelzen Gbf","Veerßen",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","20EDE-004","Hamburg - Magdeburg","< >","Uelzen Gbf","Veerßen",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","22E57-003","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,42,43,"2026-10-18","22:00:00","2026-10-19","04:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","22E57-006","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,44,44,"2026-10-31","23:00:00","2026-11-01","05:00:00","0d, 6h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","22E57-009","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2026,2026,48,49,"2026-11-27","05:00:00","2026-11-30","05:00:00","3d, 0h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","23082-001","Hamburg - Magdeburg",">","Uelzen Gbf","Lüneburg",2026,2026,28,50,"2026-07-10","21:00:00","2026-12-12","23:59:00","155d, 3h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1031-(MK27)-90","Hamburg - Magdeburg","< >","Uelzen Gbf","Stendal Gbf",2027,2027,5,8,"05.02.2027","21:00:00","26.02.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1031-(MK27)-91_WDN","Hamburg - Magdeburg","< >","Uelzen Gbf","Stendal Gbf",2027,2027,2,5,"11.01.2027","21:00:00","05.02.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEuN",null,null,null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1031-(MK27)-92","Hamburg - Magdeburg","< >","Uelzen Gbf","Stendal Gbf",2027,2027,11,27,"19.03.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-06",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1031-(MK27)-94","Hamburg - Magdeburg","< >","Uelzen Gbf","Stendal Gbf",2027,2027,34,41,"27.08.2027","21:00:00","15.10.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-04-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1B42F-003","Hamburg - Magdeburg","< >","Waldhausen","Hannover-Wülfel",2026,2026,36,38,"2026-09-05","20:00:00","2026-09-14","06:00:00","8d, 10h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-004","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2026,2026,34,34,"2026-08-17","23:10:00","2026-08-18","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-005","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2026,2026,34,34,"2026-08-18","23:10:00","2026-08-19","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1C0F0-006","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Sandbach",2026,2026,34,34,"2026-08-19","23:10:00","2026-08-20","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1FFB7-004","Hamburg - Magdeburg","< >","Weddel (Braunschw)","Fallersleben",2026,2026,36,36,"2026-09-06","01:15:00","2026-09-06","06:10:00","0d, 4h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"5,6,7",1]
[null,"DB InfraGO AG","20EDE-005","Hamburg - Magdeburg","< >","Wieren","Wieren",2026,2026,35,37,"2026-08-28","20:00:00","2026-09-11","05:00:00","13d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","20EDE-006","Hamburg - Magdeburg","< >","Wieren","Wieren",2026,2026,29,33,"2026-07-17","21:30:00","2026-08-14","05:00:00","27d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"4,5",1]
[null,"DB InfraGO AG","21340-001","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,35,39,"2026-08-29","06:30:00","2026-09-22","20:30:00","24d, 14h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-002","Hamburg - Magdeburg",">","Wolmirstedt","Zielitz Stw B2",2026,2026,35,39,"2026-08-29","06:30:00","2026-09-22","20:30:00","24d, 14h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-003","Hamburg - Magdeburg",">","Wolmirstedt","Zielitz Stw B2",2026,2026,39,40,"2026-09-22","20:30:00","2026-10-01","20:30:00","9d, 0h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-004","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,35,39,"2026-08-29","06:30:00","2026-09-22","20:30:00","24d, 14h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-005","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,39,40,"2026-09-22","20:30:00","2026-10-01","20:30:00","9d, 0h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-006","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,39,40,"2026-09-22","20:30:00","2026-10-01","20:30:00","9d, 0h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-009","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,35,35,"2026-08-27","06:30:00","2026-08-29","06:30:00","2d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","21340-010","Hamburg - Magdeburg","< >","Wolmirstedt","Wolmirstedt",2026,2026,40,40,"2026-10-01","20:30:00","2026-10-03","20:30:00","2d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-004","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,37,37,"2026-09-08","06:30:00","2026-09-08","09:30:00","0d, 3h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-006","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,37,37,"2026-09-08","08:30:00","2026-09-08","11:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1F1C2-015","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,37,37,"2026-09-10","06:25:00","2026-09-10","09:25:00","0d, 3h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-017","Hannover - Magdeburg","< >","Beddingen","Gr Gleid Ostkopf",2026,2026,37,37,"2026-09-10","08:25:00","2026-09-10","11:25:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-17",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CBF8-002","Hannover - Magdeburg",">","Eilsleben (b Magdeburg)","Marienborn",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-11","23:59:00","2d, 1h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,null,null,null,"1,2,3",1]
[null,"DB InfraGO AG","1C2F9-001","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2026,2026,33,35,"2026-08-13","08:00:00","2026-08-29","08:00:00","16d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","1CBF8-001","Hannover - Magdeburg","< >","Eilsleben (b Magdeburg) Gbf","Eilsleben (b Magdeburg) Gbf",2026,2026,41,43,"2026-10-09","08:00:00","2026-10-19","08:00:00","10d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"6,7",1]
[null,"DB InfraGO AG","1A813-010","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-25",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-012","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,33,34,"2026-08-14","21:00:00","2026-08-18","10:00:00","3d, 13h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,",,8",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-017","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,34,34,"2026-08-20","23:00:00","2026-08-22","05:00:00","1d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A813-019","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2026,2026,34,34,"2026-08-22","00:25:00","2026-08-22","05:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","1A813-028","Hannover - Magdeburg","< >","Frellstedt","Helmstedt",2026,2026,35,35,"2026-08-28","15:00:00","2026-08-28","21:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A852-001","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,44,44,"2026-11-01","00:35:00","2026-11-01","07:35:00","0d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A852-003","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,45,45,"2026-11-02","02:00:00","2026-11-02","05:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A852-006","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,45,45,"2026-11-08","00:35:00","2026-11-08","07:35:00","0d, 7h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","1A852-008","Hannover - Magdeburg",">","Frellstedt","Helmstedt",2026,2026,46,46,"2026-11-09","02:00:00","2026-11-09","05:00:00","0d, 3h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","21340-007","Hannover - Magdeburg",">","Glindenberg","Zielitz",2026,2026,40,40,"2026-10-01","12:00:00","2026-10-01","20:30:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"5,6",1]
[null,"DB InfraGO AG","21340-008","Hannover - Magdeburg",">","Glindenberg","Zielitz",2026,2026,35,35,"2026-08-29","06:30:00","2026-08-29","10:30:00","0d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-003","Hannover - Magdeburg","< >","Groß Gleidingen","Groß Gleidingen",2026,2026,32,37,"2026-08-03","07:00:00","2026-09-07","19:00:00","35d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-01",null,null,"1,7",1]
[null,"DB InfraGO AG","1A784-004","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,33,34,"2026-08-14","23:00:00","2026-08-18","05:00:00","3d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-005","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,33,34,"2026-08-14","23:00:00","2026-08-21","23:00:00","7d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1A784-007","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,34,34,"2026-08-18","23:05:00","2026-08-21","05:00:00","2d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-008","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,34,35,"2026-08-21","23:00:00","2026-08-25","05:00:00","3d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1A784-012","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,35,35,"2026-08-25","23:05:00","2026-08-28","05:00:00","2d, 5h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-013","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,35,35,"2026-08-28","15:10:00","2026-08-28","21:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1A7F1-001","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,41,43,"2026-10-09","22:10:00","2026-10-19","05:00:00","9d, 6h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1A7F1-002","Hannover - Magdeburg","<","Groß Gleidingen","Vechelde",2026,2026,41,41,"2026-10-09","22:10:00","2026-10-10","00:55:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1A7F1-007","Hannover - Magdeburg","< >","Groß Gleidingen","Peine Gbf",2026,2026,42,42,"2026-10-17","03:20:00","2026-10-17","04:20:00","0d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1A7F1-008","Hannover - Magdeburg","<","Groß Gleidingen","Peine",2026,2026,41,42,"2026-10-10","23:05:00","2026-10-12","05:00:00","1d, 5h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1F1C2-005","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2026,2026,37,37,"2026-09-08","06:30:00","2026-09-08","09:30:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,5,6,7",1]
[null,"DB InfraGO AG","1F1C2-016","Hannover - Magdeburg","< >","Groß Gleidingen","Beddingen Nordkopf",2026,2026,37,37,"2026-09-10","06:25:00","2026-09-10","09:25:00","0d, 3h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1B42F-005","Hannover - Magdeburg","< >","Hannover-Linden","Hannover-Waldheim",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,7",1]
[null,"DB InfraGO AG","1B42F-006","Hannover - Magdeburg","< >","Hannover-Wülfel","Waldhausen",2026,2026,36,36,"2026-09-05","22:00:00","2026-09-06","06:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20B78-008","Hannover - Magdeburg",">","Lehrte","Sehnde",2026,2026,32,32,"2026-08-04","00:00:00","2026-08-08","05:50:00","4d, 5h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"14,14,14",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20CFF-001","Hannover - Magdeburg",">","Lehrte","Algermissen",2026,2026,43,43,"2026-10-19","22:00:00","2026-10-22","05:50:00","2d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"22,22,22",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20CFF-002","Hannover - Magdeburg",">","Lehrte","Algermissen",2026,2026,44,44,"2026-10-26","22:00:00","2026-10-29","05:50:00","2d, 7h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"22,22,22",null,null,null,"N",null,"2024-06-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1C603-001","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2026,2026,36,50,"2026-09-01","00:00:00","2026-12-12","23:59:00","103d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"6,7",1]
[null,"DB InfraGO AG","20AD7-001","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2026,2026,26,34,"2026-06-26","00:00:00","2026-08-21","23:59:00","56d, 23h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"6,7",1]
[null,"DB InfraGO AG","1A784-010","Hannover - Magdeburg","< >","Peine Gbf","Groß Gleidingen",2026,2026,34,35,"2026-08-21","23:00:00","2026-08-28","23:00:00","7d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"6,7",1]
[null,"DB InfraGO AG","1A784-011","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,35,35,"2026-08-25","05:00:00","2026-08-28","21:00:00","3d, 16h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-02-01",null,null,"1,7",1]
[null,"DB InfraGO AG","1A7F1-003","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,41,41,"2026-10-10","00:55:00","2026-10-10","03:20:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1A7F1-004","Hannover - Magdeburg","< >","Peine Gbf","Groß Gleidingen",2026,2026,41,41,"2026-10-10","03:20:00","2026-10-10","04:20:00","0d, 1h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-20",null,null,"1,7",1]
[null,"DB InfraGO AG","1A7F1-006","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,42,42,"2026-10-17","00:55:00","2026-10-17","03:20:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-20",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1A7F1-009","Hannover - Magdeburg",">","Peine Gbf","Groß Gleidingen",2026,2026,42,43,"2026-10-17","23:05:00","2026-10-19","05:00:00","1d, 5h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-30",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1C0F0-001","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2026,2026,34,34,"2026-08-17","23:10:00","2026-08-18","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1C0F0-002","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2026,2026,34,34,"2026-08-18","23:10:00","2026-08-19","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"4,5",1]
[null,"DB InfraGO AG","1C0F0-003","Hannover - Magdeburg","< >","Schandelah","Braunschweig-Buchhorst",2026,2026,34,34,"2026-08-19","23:10:00","2026-08-20","04:50:00","0d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"3,4",1]
[null,"DB InfraGO AG","20409-032","Hannover - Magdeburg","< >","Stendal Gbf","Nahrstedt",2026,2026,38,39,"2026-09-18","21:00:00","2026-09-25","05:00:00","6d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-30",null,null,"6,7",1]
[null,"DB InfraGO AG","1A784-002","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,32,35,"2026-08-03","07:00:00","2026-08-28","23:00:00","25d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3",1]
[null,"DB InfraGO AG","1A784-006","Hannover - Magdeburg","<","Vechelde","Vechelde",2026,2026,34,34,"2026-08-18","05:00:00","2026-08-21","23:00:00","3d, 18h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-009","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,34,34,"2026-08-18","05:00:00","2026-08-21","23:00:00","3d, 18h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-014","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,35,35,"2026-08-25","05:00:00","2026-08-27","05:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-015","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,35,35,"2026-08-27","05:00:00","2026-08-28","21:00:00","1d, 16h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,",0,0",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A784-016","Hannover - Magdeburg","< >","Vechelde","Vechelde",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","04:00:00","2d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1A7F1-005","Hannover - Magdeburg","<","Vechelde","Peine",2026,2026,42,42,"2026-10-16","22:20:00","2026-10-17","00:55:00","0d, 2h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-002","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,33,35,"2026-08-14","23:00:00","2026-08-28","05:00:00","13d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-004","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-21","22:00:00","7d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-005","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,33,35,"2026-08-14","22:00:00","2026-08-28","22:00:00","14d, 0h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C2F9-006","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,34,35,"2026-08-21","23:00:00","2026-08-24","05:00:00","2d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-007","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,35,35,"2026-08-24","05:00:00","2026-08-28","22:00:00","4d, 17h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C2F9-008","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,35,36,"2026-08-28","22:00:00","2026-08-31","08:00:00","2d, 10h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1CBF8-003","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-11","23:59:00","2d, 1h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-07",null,null,"2,3",1]
[null,"DB InfraGO AG","1CBF8-004","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,41,"2026-10-09","22:00:00","2026-10-11","23:59:00","2d, 1h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,5,1]
[null,"DB InfraGO AG","1CBF8-005","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,42,"2026-10-09","23:59:00","2026-10-12","03:00:00","2d, 3h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,5,1]
[null,"DB InfraGO AG","1CBF8-007","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,42,"2026-10-10","03:00:00","2026-10-12","04:30:00","2d, 1h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1CBF8-008","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,41,42,"2026-10-10","03:00:00","2026-10-12","04:30:00","2d, 1h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-21",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1CBF8-010","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,42,43,"2026-10-17","21:30:00","2026-10-19","04:30:00","1d, 7h","Periodical","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"1,2,7",1]
[null,"DB InfraGO AG","1CBF8-011","Hannover - Magdeburg","< >","Wefensleben","Wefensleben",2026,2026,42,43,"2026-10-17","21:30:00","2026-10-19","04:30:00","1d, 7h","Periodical","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-004","Karlsruhe - München",">","Amstetten (Württ)","Westerstetten",2026,2026,34,34,"2026-08-22","21:00:00","2026-08-23","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","22527-005","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,34,37,"2026-08-22","21:00:00","2026-09-07","05:00:00","15d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","22527-006","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,34,37,"2026-08-22","21:00:00","2026-09-07","05:00:00","15d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","22527-009","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,34,36,"2026-08-23","21:00:00","2026-09-01","05:00:00","8d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"5,6,7"]
[null,"DB InfraGO AG","22527-015","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-02-07",null,null,"1,2,3,4"]
[null,"DB InfraGO AG","22527-019","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,35,35,"2026-08-24","23:00:00","2026-08-25","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"5,6,7"]
[null,"DB InfraGO AG","22527-020","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,35,35,"2026-08-24","23:00:00","2026-08-25","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","22527-023","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-028","Karlsruhe - München",">","Amstetten (Württ)","Westerstetten",2026,2026,36,37,"2026-09-01","21:00:00","2026-09-07","05:00:00","5d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-029","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,36,37,"2026-09-01","21:00:00","2026-09-07","05:00:00","5d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-030","Karlsruhe - München","< >","Amstetten (Württ)","Westerstetten",2026,2026,36,37,"2026-09-01","21:00:00","2026-09-07","05:00:00","5d, 8h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"5,6,7"]
[null,"DB InfraGO AG","222FB-034","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"5,6,7"]
[null,"DB InfraGO AG","222FB-035","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","222FB-036","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-038","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-040","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-02","05:00:00","2026-09-05","23:00:00","3d, 18h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","222FB-041","Karlsruhe - München",">","Amstetten (Württ)","Beimerstetten",2026,2026,36,36,"2026-09-02","23:00:00","2026-09-03","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-047","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-05","23:00:00","2026-09-06","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-049","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,36,36,"2026-09-05","23:00:00","2026-09-06","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","222FB-050","Karlsruhe - München",">","Amstetten (Württ)","Beimerstetten",2026,2026,36,37,"2026-09-06","23:00:00","2026-09-07","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"5,,5",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","22527-029","Karlsruhe - München","< >","Amstetten (Württ)","Amstetten (Württ)",2026,2026,35,36,"2026-08-25","05:00:00","2026-09-01","21:00:00","7d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-22"]
[null,"DB InfraGO AG","1D6BF-001","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D6BF-006","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D6BF-007","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","1D6BF-008","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-16",null,null,1,1]
[null,"DB InfraGO AG","1D6BF-009","Karlsruhe - München","< >","Augsburg Hbf","Augsburg Hbf",2026,2026,22,50,"2026-05-26","04:30:00","2026-12-12","23:59:00","200d, 20h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,1,1]
[null,"DB InfraGO AG","1E029-007","Karlsruhe - München","<","Augsburg Hbf","Mering",2026,2026,35,36,"2026-08-26","21:00:00","2026-08-31","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-008","Karlsruhe - München","<","Augsburg Hbf","Mering",2026,2026,35,43,"2026-08-26","21:00:00","2026-10-25","05:00:00","59d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E029-011","Karlsruhe - München","<","Augsburg Hbf","Kissing",2026,2026,36,43,"2026-08-31","21:00:00","2026-10-21","05:00:00","50d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024",null,null,"2,3,4",1]
[null,"DB InfraGO AG","1E029-012","Karlsruhe - München","<","Augsburg Hbf","Mering",2026,2026,43,43,"2026-10-21","21:00:00","2026-10-25","05:00:00","3d, 9h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"06.12.2024",null,null,"1,4,5,6,7",1]
[null,"DB InfraGO AG","1E029-015","Karlsruhe - München","< >","Augsburg Hbf","Mering Üst",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,6,1]
[null,"DB InfraGO AG","1E029-016","Karlsruhe - München","< >","Augsburg Hbf","Mering Üst",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"06.12.2024",null,null,6,1]
[null,"DB InfraGO AG","1E029-018","Karlsruhe - München","<","Augsburg-Hochzoll Abzweig","Mering Üst",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"06.12.2024",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DABD-001","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-29","22:00:00","2026-08-30","08:00:00","0d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,7",1]
[null,"DB InfraGO AG","1DABD-002","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,37,"2026-08-29","22:00:00","2026-09-07","03:00:00","8d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-003","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,37,"2026-08-29","22:00:00","2026-09-07","03:00:00","8d, 5h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-004","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","13:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"6,7",1]
[null,"DB InfraGO AG","1DABD-006","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,35,36,"2026-08-30","13:00:00","2026-09-03","20:00:00","4d, 7h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-007","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-03","20:00:00","2026-09-05","09:00:00","1d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"5,6",1]
[null,"DB InfraGO AG","1DABD-008","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-05","09:00:00","2026-09-06","22:00:00","1d, 13h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"6,7",1]
[null,"DB InfraGO AG","1DABD-009","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DABD-012","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"5,6",1]
[null,"DB InfraGO AG","1DABD-016","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,37,37,"2026-09-09","14:00:00","2026-09-11","04:00:00","1d, 14h","Continuous",null,null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,7",1]
[null,"DB InfraGO AG","1DABD-017","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","1DABD-021","Karlsruhe - München","< >","Augsburg-Oberhausen","Augsburg-Oberhausen",2026,2026,36,36,"2026-09-03","20:00:00","2026-09-06","22:00:00","3d, 2h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"06.12.2024",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","21CCE-002","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-28",null,null,"6,7",1]
[null,"DB InfraGO AG","21CCE-003","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-29",null,null,"1,2",1]
[null,"DB InfraGO AG","21CCE-004","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-28",null,null,"6,7",1]
[null,"DB InfraGO AG","21CCE-005","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-11-28",null,null,"6,7",1]
[null,"DB InfraGO AG","21CCE-008","Karlsruhe - München","< >","Beimerstetten","Ulm-Örlingen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-28",null,null,"6,7",1]
[null,"DB InfraGO AG","21CCE-010","Karlsruhe - München","< >","Beimerstetten","Beimerstetten",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","04:50:00","3d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-28",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","21CCE-012","Karlsruhe - München",">","Beimerstetten","Ulm-Örlingen",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","04:50:00","3d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2022-11-28",null,null,"1,2,3",1]
[null,"DB InfraGO AG","21CCE-014","Karlsruhe - München","< >","Beimerstetten","Ulm-Örlingen",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","04:50:00","3d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-11-28",null,null,"1,2,3",1]
[null,"DB InfraGO AG","22527-011","Karlsruhe - München","<","Beimerstetten","Westerstetten",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","22527-024","Karlsruhe - München","<","Beimerstetten","Westerstetten",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2024-07-17",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1C651-001","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-002","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,37,"2026-08-22","01:30:00","2026-09-07","05:00:00","16d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-005","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,37,37,"2026-09-07","21:00:00","2026-09-11","05:00:00","3d, 8h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C651-008","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,44,"2026-10-24","01:30:00","2026-10-30","21:00:00","6d, 20h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C662-001","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-28","05:00:00","6d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1C662-002","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,34,35,"2026-08-22","01:30:00","2026-08-28","05:00:00","6d, 3h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1C662-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1C662-005","Karlsruhe - München","< >","Bietigheim-Bissingen","Ludwigsburg",2026,2026,43,43,"2026-10-24","01:30:00","2026-10-24","09:30:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-001","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","01:00:00","2026-08-17","07:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1E12D-002","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","01:00:00","2026-08-17","07:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","07:00:00","2026-08-21","21:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-005","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","07:00:00","2026-08-21","21:00:00","4d, 14h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-006","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,34,"2026-08-17","09:00:00","2026-08-21","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E07D-003","Karlsruhe - München","<","Bietigheim-Bissingen","Ludwigsburg",2026,2026,35,37,"2026-08-29","05:00:00","2026-09-07","05:00:00","9d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-011","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-26","16:00:00","4d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-07",null,null,"5,6",1]
[null,"DB InfraGO AG","1E12D-012","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-26","16:00:00","4d, 19h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72E-003","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1E72E-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","05:00:00","6d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1E72E-005","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-25","22:00:00","2026-10-02","04:00:00","6d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1E72E-006","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,39,40,"2026-09-26","00:30:00","2026-10-02","05:00:00","6d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2022-12-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1E622-001","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","00:00:00","2026-08-31","06:00:00","5d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-12",null,null,"1,2",1]
[null,"DB InfraGO AG","1E622-003","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,35,36,"2026-08-26","16:00:00","2026-08-31","06:00:00","4d, 14h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,2",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-010","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-011","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-012","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-05","06:00:00","5d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-013","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2022-12-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-014","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-12-13",null,null,"2,3",1]
[null,"DB InfraGO AG","1E622-016","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,36,36,"2026-08-31","09:00:00","2026-09-04","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2124F-004","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,44,"2026-10-19","09:00:00","2026-10-30","05:00:00","10d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2023-01-09",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2124F-006","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,43,"2026-10-19","09:00:00","2026-10-23","18:00:00","4d, 9h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2022-12-15",null,null,"1,7",1]
[null,"DB InfraGO AG","2124F-007","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,43,"2026-10-19","09:00:00","2026-10-23","18:00:00","4d, 9h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","2124F-008","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-30","05:00:00","6d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","2124F-009","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-30","05:00:00","6d, 9h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","2124F-010","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,44,44,"2026-10-30","00:10:00","2026-10-30","05:00:00","0d, 4h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","2124F-011","Karlsruhe - München","< >","Bietigheim-Bissingen","Bietigheim-Bissingen",2026,2026,44,44,"2026-10-30","00:10:00","2026-10-30","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2022-12-15",null,null,"1,2,7",1]
[null,"DB InfraGO AG","20BF3-008","Karlsruhe - München",">","Eislingen (Fils)","Süßen",2026,2026,34,34,"2026-08-22","03:00:00","2026-08-23","03:00:00","1d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-06-07",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22ED4-041","Karlsruhe - München","< >","Eislingen (Fils)","Geislingen West",2026,2026,32,33,"2026-08-09","23:59:00","2026-08-10","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-19",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F188-010","Karlsruhe - München",">","Freudenstein","Vaihingen (Enz)",2026,2026,35,36,"2026-08-24","22:30:00","2026-09-05","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2023-01-11",null,null,2,1]
[null,"DB InfraGO AG","222FB-031","Karlsruhe - München",">","Geislingen (Steige)","Westerstetten",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2023-01-12",null,null,"5,6",1]
[null,"DB InfraGO AG","222FB-048","Karlsruhe - München",">","Geislingen (Steige)","Westerstetten",2026,2026,36,36,"2026-09-05","23:00:00","2026-09-06","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2023-01-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1D9B7-002","Karlsruhe - München","< >","Gessertshausen","Westheim (Schwab)",2026,2026,43,46,"2026-10-23","22:30:00","2026-11-13","05:10:00","20d, 7h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-03-04",null,null,"2,3",1]
[null,"DB InfraGO AG","1D9B7-003","Karlsruhe - München","< >","Gessertshausen","Westheim (Schwab)",2026,2026,43,46,"2026-10-23","22:30:00","2026-11-13","05:10:00","20d, 7h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-03-04",null,null,"2,3",1]
[null,"DB InfraGO AG","1D9B7-004","Karlsruhe - München","<","Gessertshausen","Westheim (Schwab)",2026,2026,46,50,"2026-11-13","22:25:00","2026-12-08","05:10:00","24d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-02-06",null,null,"2,3",1]
[null,"DB InfraGO AG","1D885-015","Karlsruhe - München","< >","Gessertshausen","Gessertshausen",2026,2026,45,46,"2026-11-07","22:00:00","2026-11-09","05:00:00","1d, 7h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-05-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1FFF4-009","Karlsruhe - München","<","Gingen Süd","Eislingen (Fils)",2026,2026,37,37,"2026-09-07","00:30:00","2026-09-07","04:30:00","0d, 4h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO AG","20BF3-012","Karlsruhe - München","<","Gingen Süd","Eislingen (Fils)",2026,2026,33,34,"2026-08-16","01:30:00","2026-08-17","04:30:00","1d, 3h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,null,null,null,1,1]
[null,"DB InfraGO AG","1F188-001","Karlsruhe - München","<","Glems","Vaihingen (Enz)",2026,2026,30,32,"2026-07-20","22:30:00","2026-08-05","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,"4,5",1]
[null,"DB InfraGO AG","1F188-005","Karlsruhe - München","< >","Glems","Vaihingen (Enz)",2026,2026,32,33,"2026-08-05","22:30:00","2026-08-14","05:00:00","8d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-24",null,null,5,1]
[null,"DB InfraGO AG","1F188-015","Karlsruhe - München","< >","Glems","Vaihingen (Enz)",2026,2026,37,39,"2026-09-11","22:30:00","2026-09-25","05:00:00","13d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-08-16",null,null,5,1]
[null,"DB InfraGO AG","1F6AE-021","Karlsruhe - München","<","Glems","Vaihingen (Enz)",2026,2026,45,45,"2026-11-02","22:30:00","2026-11-07","05:00:00","4d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-16",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E2B3-005","Karlsruhe - München","< >","Grötzingen","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-02",null,null,7,1]
[null,"DB InfraGO AG","1E501-025","Karlsruhe - München","<","Grötzingen","Karlsruhe Hbf",2026,2026,35,36,"2026-08-30","23:00:00","2026-08-31","05:00:00","0d, 6h","Continuous","Bridge",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-02",null,null,7,1]
[null,"DB InfraGO AG","1DAD8-020","Karlsruhe - München","< >","Illingen (Württ)","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","1DAD8-021","Karlsruhe - München","< >","Illingen (Württ)","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,null,null,null,"4,5",1]
[null,"DB InfraGO AG","1DAD8-025","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"4,5",1]
[null,"DB InfraGO AG","1DAD8-026","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1DB29-005","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,30,31,"2026-07-20","22:00:00","2026-08-01","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-12",null,null,"5,6",1]
[null,"DB InfraGO AG","1DB29-006","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,30,31,"2026-07-20","22:00:00","2026-08-01","05:00:00","11d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-05",null,null,"1,7",1]
[null,"DB InfraGO AG","1DB29-009","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-11-20",null,null,"1,7",1]
[null,"DB InfraGO AG","1DB29-010","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-14","05:00:00","3d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-11-20",null,null,1,1]
[null,"DB InfraGO AG","1DB29-027","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,42,44,"2026-10-16","22:00:00","2026-10-31","05:00:00","14d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-09-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1DB29-028","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,42,44,"2026-10-16","22:00:00","2026-10-31","05:00:00","14d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,7",1]
[null,"DB InfraGO AG","1DB9A-007","Karlsruhe - München","< >","Illingen (Württ)","Mühlacker",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5,6",1]
[null,"DB InfraGO AG","1DB9A-008","Karlsruhe - München","< >","Illingen (Württ)","Mühlacker",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-011","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"3,4",1]
[null,"DB InfraGO AG","1DB9A-012","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-30",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DB9A-023","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,48,50,"2026-11-23","22:00:00","2026-12-11","05:00:00","17d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-024","Karlsruhe - München",">","Illingen (Württ)","Mühlacker",2026,2026,48,50,"2026-11-23","22:00:00","2026-12-11","05:00:00","17d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-19",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-012","Karlsruhe - München","<","Illingen (Württ)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2023-09-29",null,null,6,1]
[null,"DB InfraGO AG","1F6AE-013","Karlsruhe - München","< >","Illingen (Württ)","Illingen (Württ)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-09-29",null,null,6,1]
[null,"DB InfraGO AG","1E2B3-010","Karlsruhe - München","< >","Kleinsteinbach","Kleinsteinbach",2026,2026,37,37,"2026-09-11","22:00:00","2026-09-12","22:00:00","1d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2023-10-16",null,null,7,1]
[null,"DB InfraGO AG","1F188-011","Karlsruhe - München","< >","Kraichtal","Vaihingen (Enz)",2026,2026,35,36,"2026-08-29","23:00:00","2026-08-31","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,5,1]
[null,"DB InfraGO AG","1F6AE-005","Karlsruhe - München","< >","Kraichtal","Vaihingen (Enz)",2026,2026,40,41,"2026-10-03","23:00:00","2026-10-05","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-028","Karlsruhe - München","<","Langes Feld","Vaihingen (Enz)",2026,2026,48,49,"2026-11-23","22:30:00","2026-12-05","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DF78-006","Karlsruhe - München","<","Lauffen (Neckar)","Bietigheim-Bissingen",2026,2026,41,41,"2026-10-09","21:00:00","2026-10-10","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1DF78-014","Karlsruhe - München","<","Lauffen (Neckar)","Bietigheim-Bissingen",2026,2026,48,49,"2026-11-29","21:00:00","2026-11-30","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-009","Karlsruhe - München",">","Mering","Augsburg Hbf",2026,2026,35,43,"2026-08-26","21:00:00","2026-10-25","05:00:00","59d, 9h","Periodical","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-010","Karlsruhe - München","< >","Mering","Augsburg Hbf",2026,2026,35,43,"2026-08-26","21:00:00","2026-10-25","05:00:00","59d, 9h","Periodical","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-013","Karlsruhe - München",">","Mering Üst","Augsburg Hbf",2026,2026,43,44,"2026-10-25","21:00:00","2026-10-27","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2023-11-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-014","Karlsruhe - München",">","Mering Üst","Augsburg Hbf",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-017","Karlsruhe - München",">","Mering Üst","Augsburg-Hochzoll Abzweig",2026,2026,43,47,"2026-10-25","21:00:00","2026-11-16","05:00:00","21d, 8h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-10",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-019","Karlsruhe - München",">","Mering Üst","Augsburg Hbf",2026,2026,44,46,"2026-10-27","21:00:00","2026-11-15","05:00:00","18d, 8h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-17",null,null,"1,2",1]
[null,"DB InfraGO AG","1E029-020","Karlsruhe - München",">","Mering Üst","Augsburg Hbf",2026,2026,46,47,"2026-11-15","21:00:00","2026-11-16","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-08-06",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-014","Karlsruhe - München","< >","Mettertal","Vaihingen (Enz)",2026,2026,37,37,"2026-09-07","22:30:00","2026-09-11","05:00:00","3d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-04-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1F6AE-001","Karlsruhe - München",">","Mettertal","Vaihingen (Enz)",2026,2026,39,40,"2026-09-25","22:30:00","2026-10-02","05:00:00","6d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-04-26",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-002","Karlsruhe - München","< >","Mühlacker","Maulbronn West",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-005","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-007","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-27",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-010","Karlsruhe - München","< >","Mühlacker","Maulbronn West",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-27",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-011","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1D6AE-014","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-001","Karlsruhe - München","< >","Mühlacker","Illingen (Württ)",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-003","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-26","20:00:00","2026-08-14","06:00:00","48d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-005","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-26","20:00:00","2026-08-14","06:00:00","48d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-007","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-08","05:00:00","4d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-008","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-08","05:00:00","4d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-011","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-012","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-013","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,34,35,"2026-08-21","21:00:00","2026-08-24","05:00:00","2d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-015","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-016","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-017","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,35,37,"2026-08-30","22:45:00","2026-09-11","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-019","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-18","05:00:00","4d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-020","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:00:00","2026-10-02","06:00:00","11d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-022","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:45:00","2026-10-02","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-023","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,38,40,"2026-09-20","22:45:00","2026-10-02","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-024","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,42,50,"2026-10-16","20:00:00","2026-12-11","06:00:00","55d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB29-025","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,42,50,"2026-10-16","20:00:00","2026-12-11","06:00:00","55d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-014","Karlsruhe - München","< >","Mühlacker","Mühlacker Em Nord",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-015","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-016","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,43,44,"2026-10-23","21:00:00","2026-10-26","05:00:00","2d, 9h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-21",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-018","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,45,47,"2026-11-02","22:00:00","2026-11-21","05:00:00","18d, 7h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-019","Karlsruhe - München","<","Mühlacker","Illingen (Württ)",2026,2026,45,47,"2026-11-02","22:00:00","2026-11-21","05:00:00","18d, 7h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-06","Karlsruhe - München",">","Mühlacker","Bietigheim-Biss",2027,2027,6,13,"12.02.2027","21:00:00","02.04.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-07","Karlsruhe - München","< >","Mühlacker","Bietigheim-Biss",2027,2027,4,5,"29.01.2027","21:00:00","05.02.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-08-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-08","Karlsruhe - München",">","Mühlacker","Bietigheim-Biss",2027,2027,5,6,"05.02.2027","21:00:00","12.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-09","Karlsruhe - München","< >","Mühlacker","Bietigheim-Biss",2026,2026,51,52,"18.12.2026","21:00:00","25.12.2026","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-10","Karlsruhe - München","< >","Mühlacker","Bietigheim-Biss",2027,2027,2,3,"15.01.2027","21:00:00","22.01.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-06-17",null,null,"2,3",1]
[null,"DB InfraGO AG","1327-(MK27)-14","Karlsruhe - München",">","Mühlacker","Bietigheim-Biss",2027,2027,35,42,"03.09.2027","21:00:00","22.10.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-06-17",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-012","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-016","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-20",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-004","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-020","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DB9A-025","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,48,49,"2026-11-23","22:00:00","2026-12-05","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-029","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-06-25",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-030","Karlsruhe - München","< >","Mühlacker","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-08-09",null,null,"2,3",1]
[null,"DB InfraGO AG","1DAD8-018","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-08-12",null,null,"4,5",1]
[null,"DB InfraGO AG","1DAD8-019","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1DB9A-005","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,42,47,"2026-10-17","21:00:00","2026-11-16","05:00:00","29d, 9h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1DB9A-022","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1DB9A-026","Karlsruhe - München","< >","Mühlacker Rößlesweg","Mühlacker",2026,2026,48,49,"2026-11-23","22:00:00","2026-12-05","05:00:00","11d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","1393-(MK27)-03","Karlsruhe - München","< >","München-Pasing","Olching",2027,2027,28,30,"16.07.2027","21:00:00","30.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","1393-(MK27)-05","Karlsruhe - München","< >","München-Pasing","Olching",2027,2027,30,36,"30.07.2027","21:00:00","10.09.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","1393-(MK27)-06","Karlsruhe - München","< >","München-Pasing","Olching",2027,2027,36,37,"10.09.2027","21:00:00","13.09.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","21014-005","Karlsruhe - München","< >","München-Pasing","Starnberg",2026,2026,45,47,"2026-11-06","21:00:00","2026-11-16","04:30:00","9d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1080-(MK27)-01","Karlsruhe - München",">","Neuoffingen","Neu-Ulm",2027,2027,13,19,"02.04.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1080-(MK27)-02","Karlsruhe - München",">","Neuoffingen","Neu-Ulm",2027,2027,5,11,"05.02.2027","21:00:00","19.03.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-06-24",null,null,"6,7",1]
[null,"DB InfraGO AG","1F0BA-001","Karlsruhe - München","< >","Neuoffingen","Gundelfingen (Bay)",2026,2026,35,36,"2026-08-29","23:00:00","2026-09-04","05:00:00","5d, 6h","Periodical","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1F0BA-002","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,35,36,"2026-08-29","23:00:00","2026-09-04","05:00:00","5d, 6h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"6,7",1]
[null,"DB InfraGO AG","1F0BA-003","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,35,36,"2026-08-29","23:00:00","2026-09-04","05:00:00","5d, 6h","Periodical","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1F0BA-004","Karlsruhe - München","< >","Neuoffingen","Gundelfingen (Bay)",2026,2026,36,43,"2026-09-04","23:00:00","2026-10-19","04:00:00","44d, 5h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-01",null,null,"2,3",1]
[null,"DB InfraGO AG","1F0BA-005","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,36,43,"2026-09-04","23:00:00","2026-10-19","04:00:00","44d, 5h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1F0BA-006","Karlsruhe - München","< >","Neuoffingen","Neuoffingen",2026,2026,36,43,"2026-09-04","23:00:00","2026-10-19","04:00:00","44d, 5h","Continuous","Bridge",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"2,3",1]
[null,"DB InfraGO AG","1DE53-001","Karlsruhe - München","< >","Pforzheim Hbf","Mühlacker Em Süd",2026,2026,42,43,"2026-10-16","23:00:00","2026-10-20","04:00:00","3d, 5h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1E2B3-002","Karlsruhe - München","< >","Pforzheim Hbf","Pforzheim Hbf",2026,2026,36,38,"2026-09-01","22:00:00","2026-09-14","22:00:00","13d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-07-18",null,null,"2,3",1]
[null,"DB InfraGO AG","1094-(MK27)-02","Karlsruhe - München",">","Plochingen","Ulm Pbf",2027,2027,9,11,"05.03.2027","21:00:00","19.03.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1094-(MK27)-05","Karlsruhe - München",">","Plochingen","Ulm Pbf",2027,2027,19,40,"14.05.2027","21:00:00","08.10.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1094-(MK27)-08","Karlsruhe - München",">","Plochingen","Ulm Pbf",2027,2027,8,9,"26.02.2027","21:00:00","05.03.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","22494-006","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,40,43,"2026-09-28","01:00:00","2026-10-23","05:00:00","25d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","22494-007","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,40,43,"2026-09-28","01:00:00","2026-10-23","05:00:00","25d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-21",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-008","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,40,40,"2026-09-28","01:00:00","2026-09-28","05:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-009","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,40,40,"2026-09-28","01:00:00","2026-09-28","05:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-010","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-011","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-09","21:00:00","2026-10-23","05:00:00","13d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-24",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-017","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,41,43,"2026-10-10","01:30:00","2026-10-23","04:30:00","13d, 3h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-018","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,43,43,"2026-10-22","21:00:00","2026-10-23","01:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-07",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-019","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,43,43,"2026-10-22","21:00:00","2026-10-23","01:00:00","0d, 4h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,"6,7",1]
[null,"DB InfraGO AG","22494-026","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","09:00:00","0d, 12h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-04",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-015","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,29,33,"2026-07-17","22:00:00","2026-08-10","04:00:00","23d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","22ED3-016","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,29,33,"2026-07-17","22:00:00","2026-08-10","04:00:00","23d, 6h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-001","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-07","20:00:00","13d, 22h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-003","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-07","20:00:00","13d, 22h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-008","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,32,32,"2026-08-05","04:00:00","2026-08-06","20:00:00","1d, 16h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-09-24",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-010","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,32,32,"2026-08-05","04:00:00","2026-08-06","20:00:00","1d, 16h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-011","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,32,33,"2026-08-07","20:00:00","2026-08-10","04:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-012","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,32,33,"2026-08-07","20:00:00","2026-08-10","04:00:00","2d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-013","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,33,33,"2026-08-10","04:00:00","2026-08-12","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-014","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,33,33,"2026-08-10","04:00:00","2026-08-12","04:00:00","2d, 0h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-016","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,45,46,"2026-11-08","23:59:00","2026-11-09","04:00:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,1,1]
[null,"DB InfraGO AG","22ED4-017","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,45,46,"2026-11-08","23:59:00","2026-11-09","04:00:00","0d, 4h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","22ED4-019","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","22ED4-020","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"2,3,4,5",1]
[null,"DB InfraGO AG","22ED4-021","Karlsruhe - München","< >","Plochingen","Plochingen",2026,2026,49,50,"2026-12-06","21:00:00","2026-12-07","05:00:00","0d, 8h","Continuous","Switch",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"1,7",1]
[null,"DB InfraGO AG","22ED4-043","Karlsruhe - München","< >","Plochingen","Wendlingen (Neckar)",2026,2026,32,33,"2026-08-09","23:59:00","2026-08-10","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,1,1]
[null,"DB InfraGO AG","22ED4-042","Karlsruhe - München","< >","Stuttgart Neckarpark","Plochingen",2026,2026,32,33,"2026-08-09","23:59:00","2026-08-10","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"2,3",1]
[null,"DB InfraGO AG","3042-(MK27)-01","Karlsruhe - München",">","Stuttgart-Bad Cannst","Plochingen",2027,2027,4,5,"29.01.2027","21:00:00","01.02.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WEN",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","3664-(MK27)-04","Karlsruhe - München","< >","Stuttgart-Bad Cannst","Plochingen",2027,2027,19,20,"14.05.2027","21:00:00","21.05.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","3664-(MK27)-05","Karlsruhe - München",">","Stuttgart-Bad Cannst","Plochingen",2027,2027,2,4,"15.01.2027","21:00:00","29.01.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-08-13",null,null,"2,3",1]
[null,"DB InfraGO AG","22ED4-040","Karlsruhe - München","< >","Stuttgart-Untertürkheim Pbf","Göppingen",2026,2026,32,33,"2026-08-09","23:59:00","2026-08-10","04:00:00","0d, 4h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"3,4",1]
[null,"DB InfraGO AG","3040-(MK27)-01","Karlsruhe - München",">","Stuttgart-Utürkhm Pbf","Kornwestheim Pbf",2027,2027,30,34,"31.07.2027","05:00:00","27.08.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-08-12",null,null,"4,5",1]
[null,"DB InfraGO AG","3040-(MK27)-02","Karlsruhe - München",">","Stuttgart-Utürkhm Pbf","Kornwestheim Pbf",2027,2027,24,26,"19.06.2027","05:00:00","02.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, T",null,null,null,"2024-08-14",null,null,"4,5",1]
[null,"DB InfraGO AG","3041-(MK27)-01","Karlsruhe - München","< >","Stuttgart-Utürkhm Pbf","Stuttgart Hafen",2027,2027,48,49,"03.12.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-08-14",null,null,"4,5",1]
[null,"DB InfraGO AG","3756-(MK27)-01","Karlsruhe - München","< >","Stuttgart-Zazenhausen","Ludwigsburg",2027,2027,19,22,"14.05.2027","21:00:00","31.05.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","3756-(MK27)-02","Karlsruhe - München",">","Stuttgart-Zazenhausen","Ludwigsburg",2027,2027,41,47,"15.10.2027","21:00:00","26.11.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-06-26",null,null,"4,5",1]
[null,"DB InfraGO AG","3756-(MK27)-03_WE","Karlsruhe - München","< >","Stuttgart-Zazenhausen","Ludwigsburg",2027,2027,34,38,"27.08.2027","21:00:00","20.09.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEuN",null,null,null,"2024-07-01",null,null,"4,5",1]
[null,"DB InfraGO AG","3756-(MK27)-03_WDN","Karlsruhe - München","< >","Stuttgart-Zazenhausen","Ludwigsburg",2027,2027,35,38,"30.08.2027","21:00:00","24.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEuN",null,null,null,"2024-07-01",null,null,"4,5",1]
[null,"DB InfraGO AG","1FFF4-004","Karlsruhe - München",">","Süßen","Gingen Süd",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-005","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-006","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,34,35,"2026-08-22","03:00:00","2026-08-24","05:00:00","2d, 2h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-007","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,34,35,"2026-08-22","03:00:00","2026-08-24","05:00:00","2d, 2h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-25",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-009","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,34,34,"2026-08-22","03:00:00","2026-08-23","03:00:00","1d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-010","Karlsruhe - München",">","Süßen","Gingen Süd",2026,2026,34,35,"2026-08-23","03:00:00","2026-08-24","04:30:00","1d, 1h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-27",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-011","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,34,35,"2026-08-23","03:00:00","2026-08-24","04:30:00","1d, 1h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-007","Karlsruhe - München",">","Süßen","Gingen Süd",2026,2026,36,36,"2026-08-31","23:00:00","2026-09-03","05:00:00","2d, 6h","Periodical","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-28",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-008","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,36,36,"2026-08-31","23:00:00","2026-09-03","05:00:00","2d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-010","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,37,37,"2026-09-07","00:30:00","2026-09-07","04:30:00","0d, 4h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-01",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-011","Karlsruhe - München",">","Süßen","Gingen Süd",2026,2026,43,43,"2026-10-20","23:00:00","2026-10-21","05:00:00","0d, 6h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1FFF4-012","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,43,43,"2026-10-20","23:00:00","2026-10-21","05:00:00","0d, 6h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","20BF3-013","Karlsruhe - München","< >","Süßen","Süßen",2026,2026,33,34,"2026-08-16","01:30:00","2026-08-17","04:30:00","1d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-21",null,null,"5,6",1]
[null,"DB InfraGO AG","21CCE-011","Karlsruhe - München","< >","Ulm-Örlingen","Beimerstetten",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","05:00:00","3d, 8h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","21CCE-013","Karlsruhe - München","< >","Ulm-Örlingen","Beimerstetten",2026,2026,36,36,"2026-08-31","21:00:00","2026-09-04","05:00:00","3d, 8h","Continuous","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"1,7",1]
[null,"DB InfraGO AG","1DAD8-002","Karlsruhe - München","< >","Vaihingen (Enz)","Mühlacker",2026,2026,26,50,"2026-06-22","09:00:00","2026-12-12","23:59:00","173d, 15h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"Y",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1DAD8-010","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,26,33,"2026-06-27","20:00:00","2026-08-10","06:00:00","43d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DAD8-022","Karlsruhe - München","< >","Vaihingen (Enz)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DAD8-024","Karlsruhe - München","< >","Vaihingen (Enz)","Illingen (Württ)",2026,2026,26,33,"2026-06-27","21:00:00","2026-08-10","05:00:00","43d, 8h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-06-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-002","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,42,50,"2026-10-17","20:00:00","2026-12-07","06:00:00","50d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-009","Karlsruhe - München","< >","Vaihingen (Enz)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1DB9A-010","Karlsruhe - München","< >","Vaihingen (Enz)","Illingen (Württ)",2026,2026,42,50,"2026-10-17","21:00:00","2026-12-07","05:00:00","50d, 9h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-009","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-019","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,44,44,"2026-10-26","22:30:00","2026-10-31","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-26",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-002","Karlsruhe - München","< >","Vaihingen (Enz)","Glems",2026,2026,30,32,"2026-07-20","22:30:00","2026-08-05","05:00:00","15d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-003","Karlsruhe - München","< >","Vaihingen (Enz)","Langes Feld",2026,2026,31,32,"2026-08-01","23:00:00","2026-08-03","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-004","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,31,32,"2026-08-01","23:00:00","2026-08-03","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-006","Karlsruhe - München",">","Vaihingen (Enz)","Glems",2026,2026,32,33,"2026-08-05","22:30:00","2026-08-14","05:00:00","8d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-008","Karlsruhe - München","<","Vaihingen (Enz)","Freudenstein",2026,2026,33,34,"2026-08-14","22:30:00","2026-08-21","05:00:00","6d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-012","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,35,36,"2026-08-29","23:00:00","2026-08-31","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-013","Karlsruhe - München","<","Vaihingen (Enz)","Mettertal",2026,2026,37,37,"2026-09-07","22:30:00","2026-09-11","05:00:00","3d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F188-016","Karlsruhe - München",">","Vaihingen (Enz)","Glems",2026,2026,37,39,"2026-09-11","22:30:00","2026-09-25","05:00:00","13d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-002","Karlsruhe - München","< >","Vaihingen (Enz)","Mettertal",2026,2026,39,40,"2026-09-25","22:30:00","2026-10-02","05:00:00","6d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-006","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,40,41,"2026-10-03","23:00:00","2026-10-05","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-011","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-014","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,43,43,"2026-10-19","22:30:00","2026-10-24","05:00:00","4d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-017","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,44,44,"2026-10-26","22:30:00","2026-10-31","05:00:00","4d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"2,2,",null,null,null,"N",null,"2024-07-05",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-020","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,44,44,"2026-10-26","22:30:00","2026-10-31","05:00:00","4d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-022","Karlsruhe - München","< >","Vaihingen (Enz)","Glems",2026,2026,45,45,"2026-11-02","22:30:00","2026-11-07","05:00:00","4d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-07-25",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-024","Karlsruhe - München",">","Vaihingen (Enz)","Langes Feld",2026,2026,46,47,"2026-11-09","22:30:00","2026-11-21","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-025","Karlsruhe - München","< >","Vaihingen (Enz)","Langes Feld",2026,2026,47,48,"2026-11-21","23:00:00","2026-11-23","05:00:00","1d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-29",null,null,"1,2",1]
[null,"DB InfraGO AG","1F6AE-026","Karlsruhe - München","< >","Vaihingen (Enz)","Vaihingen (Enz)",2026,2026,47,48,"2026-11-21","23:00:00","2026-11-23","05:00:00","1d, 6h","Periodical","Signal",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-02",null,null,"1,2",1]
[null,"DB InfraGO AG","21CCE-007","Karlsruhe - München",">","Westerstetten","Ulm-Örlingen",2026,2026,35,36,"2026-08-28","21:00:00","2026-08-31","05:00:00","2d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-007","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,34,34,"2026-08-22","21:00:00","2026-08-23","05:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-008","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,34,36,"2026-08-23","21:00:00","2026-09-01","05:00:00","8d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-010","Karlsruhe - München","< >","Westerstetten","Amstetten (Württ)",2026,2026,34,36,"2026-08-23","21:00:00","2026-09-01","05:00:00","8d, 8h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-012","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"9,9,9",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-014","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-016","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,35,36,"2026-08-24","05:00:00","2026-08-31","23:00:00","7d, 18h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-017","Karlsruhe - München","<","Westerstetten","Geislingen (Steige)",2026,2026,35,35,"2026-08-24","23:00:00","2026-08-25","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-021","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,34,35,"2026-08-23","23:00:00","2026-08-24","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-022","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-026","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-027","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,37,38,"2026-09-13","23:00:00","2026-09-14","05:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"9,,9",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-039","Karlsruhe - München","<","Westerstetten","Geislingen (Steige)",2026,2026,36,36,"2026-09-01","23:00:00","2026-09-02","05:00:00","0d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-042","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,36,"2026-09-02","23:00:00","2026-09-03","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-043","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,36,"2026-09-02","23:00:00","2026-09-03","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-044","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,36,"2026-09-03","05:00:00","2026-09-06","23:00:00","3d, 18h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-051","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,37,"2026-09-06","23:00:00","2026-09-07","05:00:00","0d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","222FB-052","Karlsruhe - München","< >","Westerstetten","Westerstetten",2026,2026,36,37,"2026-09-06","23:00:00","2026-09-07","05:00:00","0d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","22527-028","Karlsruhe - München","<","Westerstetten","Amstetten (Württ)",2026,2026,35,36,"2026-08-25","05:00:00","2026-09-01","21:00:00","7d, 16h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1D885-014","Karlsruhe - München","< >","Westheim (Schwab)","Dinkelscherben",2026,2026,45,46,"2026-11-07","22:00:00","2026-11-09","05:00:00","1d, 7h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"3,4",1]
[null,"DB InfraGO AG","1D9B7-001","Karlsruhe - München",">","Westheim (Schwab)","Gessertshausen",2026,2026,43,46,"2026-10-23","22:30:00","2026-11-13","05:10:00","20d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1D9B7-005","Karlsruhe - München","< >","Westheim (Schwab)","Gessertshausen",2026,2026,46,50,"2026-11-13","22:25:00","2026-12-08","05:10:00","24d, 6h","Periodical","Catenary",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1D9B7-006","Karlsruhe - München","< >","Westheim (Schwab)","Gessertshausen",2026,2026,46,50,"2026-11-13","22:25:00","2026-12-08","05:10:00","24d, 6h","Periodical","Catenary",null,null,"S",null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1DABD-005","Karlsruhe - München","<","Westheim (Schwab)","Augsburg-Oberhausen",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","13:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1DABD-010","Karlsruhe - München","<","Westheim (Schwab)","Augsburg-Oberhausen",2026,2026,36,37,"2026-09-06","22:00:00","2026-09-07","03:00:00","0d, 5h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-16",null,null,"3,4",1]
[null,"DB InfraGO AG","1E2B3-003","Karlsruhe - München","< >","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,36,38,"2026-09-01","22:00:00","2026-09-14","22:00:00","13d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1E2B3-007","Karlsruhe - München","< >","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,1",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1E2B3-009","Karlsruhe - München","< >","Wilferdingen-Singen","Wilferdingen-Singen",2026,2026,37,37,"2026-09-09","22:00:00","2026-09-11","22:00:00","2d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1F203-019","Karlsruhe - Strasbourg","< >","Achern","Achern",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"2,3",1]
[null,"DB InfraGO AG","1F203-020","Karlsruhe - Strasbourg","< >","Achern","Appenweier Nord",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"2,3",1]
[null,"DB InfraGO AG","1D5C3-018","Karlsruhe - Strasbourg","< >","Appenweier","Offenburg",2026,2026,40,41,"2026-10-04","03:00:00","2026-10-07","04:30:00","3d, 1h","Continuous","Switch",null,null,null,null,null,",,",",,",null,",3,",null,null,null,"N",null,"2024-07-16",null,null,"2,3",1]
[null,"DB InfraGO AG","1F203-011","Karlsruhe - Strasbourg",">","Appenweier Kurve","Kehl",2026,2026,49,49,"2026-12-01","21:00:00","2026-12-05","21:00:00","4d, 0h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-026","Karlsruhe - Strasbourg","< >","Appenweier Kurve","Kork",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"4,5",1]
[null,"DB InfraGO AG","1CDDE-001","Karlsruhe - Strasbourg","< >","Appenweier Nord","Bad Griesbach",2026,2026,31,37,"2026-07-31","23:00:00","2026-09-11","23:00:00","42d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-021","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier-Muhrhaag",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-022","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier-Muhrhaag",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-027","Karlsruhe - Strasbourg","< >","Appenweier Nord","Appenweier Kurve",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-023","Karlsruhe - Strasbourg","< >","Baden-Baden","Ottersweier",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F43D-003","Karlsruhe - Strasbourg","< >","Baden-Baden","Rastatt-Süd",2026,2026,41,41,"2026-10-06","00:01:00","2026-10-09","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F43D-012","Karlsruhe - Strasbourg","< >","Baden-Baden","Rastatt-Süd",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-001","Karlsruhe - Strasbourg","< >","Kehl","Kork",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-007","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,3,50,"2026-01-16","21:00:00","2026-12-12","23:59:00","330d, 2h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-001","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,10,50,"2026-03-04","05:00:00","2026-12-09","05:00:00","280d, 0h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-22",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-030","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,30,32,"2026-07-24","22:00:00","2026-08-03","05:00:00","9d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-032","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,32,32,"2026-08-03","22:00:00","2026-08-07","05:00:00","3d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-033","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,36,39,"2026-09-04","22:00:00","2026-09-25","05:00:00","20d, 7h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-034","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,36,39,"2026-09-04","22:00:00","2026-09-24","05:00:00","19d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F0E7-035","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,39,39,"2026-09-24","22:00:00","2026-09-25","05:00:00","0d, 7h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-001","Karlsruhe - Strasbourg","< >","Kehl","Kehl Grenze",2026,2026,39,40,"2026-09-25","22:00:00","2026-09-29","22:00:00","4d, 0h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,87,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-003","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,40,43,"2026-09-30","22:00:00","2026-10-19","05:00:00","18d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-004","Karlsruhe - Strasbourg","<","Kehl","Kork",2026,2026,40,43,"2026-09-30","22:00:00","2026-10-19","05:00:00","18d, 7h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-005","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,43,45,"2026-10-19","22:00:00","2026-11-06","05:00:00","17d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-007","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,46,50,"2026-11-12","21:00:00","2026-12-09","05:00:00","26d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-009","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,49,"2026-12-01","21:00:00","2026-12-05","21:00:00","4d, 0h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-012","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-04","05:00:00","1d, 7h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-013","Karlsruhe - Strasbourg","< >","Kehl","Kehl Grenze",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-04","05:00:00","1d, 7h","Periodical","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-07-05",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-015","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-016","Karlsruhe - Strasbourg","< >","Kehl","Kehl Grenze",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary",null,null,null,null,"X",",,",",,",null,",,",null,null,87,"N",null,"2024-07-11",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-018","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,49,49,"2026-12-06","00:00:00","2026-12-06","08:00:00","0d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-028","Karlsruhe - Strasbourg","< >","Kehl","Kehl Grenze",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,87,"N",null,"2024-07-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1F79E-030","Karlsruhe - Strasbourg","< >","Kehl","Kehl",2026,2026,50,50,"2026-12-09","05:00:00","2026-12-12","23:59:00","3d, 18h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-002","Karlsruhe - Strasbourg","<","Kehl Grenze","Kehl",2026,2026,39,40,"2026-09-25","22:00:00","2026-09-29","22:00:00","4d, 0h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,87,"N",null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1F00D-002","Karlsruhe - Strasbourg","< >","Kork","Kehl",2025,2026,50,50,"2025-12-14","00:00:00","2026-12-12","23:59:00","363d, 23h","Continuous","Catenary",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-29",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-006","Karlsruhe - Strasbourg",">","Kork","Kehl",2026,2026,43,45,"2026-10-19","22:00:00","2026-11-06","05:00:00","17d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-008","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,48,49,"2026-11-23","08:00:00","2026-12-05","21:00:00","12d, 13h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-010","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,49,50,"2026-12-01","21:00:00","2026-12-09","05:00:00","7d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-014","Karlsruhe - Strasbourg","< >","Kork","Kehl",2026,2026,49,49,"2026-12-02","22:00:00","2026-12-04","05:00:00","1d, 7h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-017","Karlsruhe - Strasbourg","< >","Kork","Kehl",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-029","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-030","Karlsruhe - Strasbourg","< >","Kork","Kehl",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-035","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,49,49,"2026-12-01","21:00:00","2026-12-05","05:00:00","3d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"4,5",1]
[null,"DB InfraGO AG","1F203-036","Karlsruhe - Strasbourg","< >","Kork","Kork",2026,2026,49,50,"2026-12-05","21:00:00","2026-12-09","05:00:00","3d, 8h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-025","Karlsruhe - Strasbourg","< >","Ottersweier","Achern",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-04",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-032","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-04",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-033","Karlsruhe - Strasbourg","< >","Ottersweier","Ottersweier",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary",null,"ST",null,null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1F203-034","Karlsruhe - Strasbourg","< >","Ottersweier","Appenweier Nord",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","1F79E-001","Karlsruhe - Strasbourg","< >","Ottersweier","Baden-Baden",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-07","05:00:00","0d, 5h","Continuous","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1F43D-002","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2026,2026,41,41,"2026-10-06","00:01:00","2026-10-09","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-004","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,41,41,"2026-10-06","00:01:00","2026-10-09","04:00:00","3d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-005","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2026,2026,41,41,"2026-10-06","00:01:00","2026-10-09","04:00:00","3d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-006","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-007","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-008","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-009","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,,",null,null,null,"N",null,"2024-07-18",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-011","Karlsruhe - Strasbourg","< >","Rastatt","Baden-Baden",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-013","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-014","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,42,42,"2026-10-13","00:01:00","2026-10-16","04:00:00","3d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-015","Karlsruhe - Strasbourg",">","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-10","01:00:00","2026-10-12","04:00:00","2d, 3h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-016","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt-Süd",2026,2026,41,42,"2026-10-10","01:00:00","2026-10-12","04:00:00","2d, 3h","Periodical","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-017","Karlsruhe - Strasbourg","< >","Rastatt","Rastatt",2026,2026,41,42,"2026-10-10","01:00:00","2026-10-12","04:00:00","2d, 3h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-07-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1F43D-010","Karlsruhe - Strasbourg","< >","Rastatt-Süd","Rastatt",2026,2026,41,42,"2026-10-09","22:00:00","2026-10-12","04:00:00","2d, 6h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-07-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1E2B3-008","Karlsruhe - Strasbourg","< >","Söllingen (b Karlsruhe) Abzw","Wilferdingen-Singen",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-11","22:00:00","7d, 0h","Continuous","Track & Rail",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"1,7",1]
[null,"DB InfraGO AG","1D3FE-001","Magdeburg - Falkenberg","< >","Dannenberg Ost","Lüneburg",2026,2026,15,50,"2026-04-06","22:00:00","2026-12-12","06:00:00","249d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10",null,null,"5,6",1]
[null,"DB InfraGO AG","218FC-001","Magdeburg - Falkenberg","< >","Güterglück Stw Gkn","Güterglück",2026,2026,39,39,"2026-09-26","20:00:00","2026-09-27","04:00:00","0d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-16",null,null,"1,2",1]
[null,"DB InfraGO AG","1446-(MK27)-02","Magdeburg - Falkenberg","< >","Lu Wittenberg","Meinsdorf",2027,2027,23,24,"11.06.2027","21:00:00","14.06.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-07-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1446-(MK27)-03","Magdeburg - Falkenberg","< >","Lu Wittenberg","Meinsdorf",2027,2027,36,37,"10.09.2027","21:00:00","13.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WEN",null,null,null,"2024-07-15",null,null,"1,2",1]
[null,"DB InfraGO AG","21CBB-001","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-17",null,null,"3,4",1]
[null,"DB InfraGO AG","21CBB-003","Magdeburg - Falkenberg","< >","Rodleben","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-23",null,null,"3,4",1]
[null,"DB InfraGO AG","21CBB-002","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","21CBB-004","Magdeburg - Falkenberg","< >","Roßlau (Elbe)","Roßlau (Elbe)",2026,2026,39,39,"2026-09-26","08:00:00","2026-09-26","18:00:00","0d, 10h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-15",null,null,"3,4",1]
[null,"DB InfraGO AG","1EDB0-002","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2026,2026,18,50,"2026-05-01","00:00:00","2026-12-12","23:59:00","226d, 0h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-08-12",null,null,"3,4",1]
[null,"DB InfraGO AG","1EDB0-003","Magdeburg - Falkenberg","< >","Roßlau (Elbe) Gbf","Roßlau (Elbe) Gbf",2026,2026,18,50,"2026-05-01","00:00:00","2026-12-12","23:59:00","226d, 0h","Continuous",null,null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-08-14",null,null,"3,4",1]
[null,"DB InfraGO AG","1157-(MK27)-02","München - Regensburg",">","Landshut/B Hbf","München-Feldmoching",2027,2027,27,28,"09.07.2027","21:00:00","16.07.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","1157-(MK27)-03","München - Regensburg",">","Landshut/B Hbf","München-Feldmoching",2027,2027,40,41,"08.10.2027","21:00:00","11.10.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, WEN",null,null,null,"2024-07-18",null,null,"4,5",1]
[null,"DB InfraGO AG","3148-(MK27)-01","München - Salzburg","< >","München Leuchtenberg","München-Daglfing",2027,2027,33,34,"20.08.2027","21:00:00","23.08.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-08-12",null,null,"2,3",1]
[null,"DB InfraGO AG","1D341-002","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"2,3",1]
[null,"DB InfraGO AG","1D341-003","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"5,6",1]
[null,"DB InfraGO AG","1D341-004","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1D341-005","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2025,2026,50,50,"2025-12-14","00:01:00","2026-12-12","23:59:00","363d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-09",null,null,"3,4",1]
[null,"DB InfraGO AG","1DD6A-001","München - Salzburg",">","München Ost Pbf","München Ost Pbf",2026,2026,24,50,"2026-06-08","04:30:00","2026-12-12","23:59:00","187d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-18",null,null,"5,6",1]
[null,"DB InfraGO AG","1DD6A-013","München - Salzburg","< >","München Ost Pbf","München Ost Pbf",2026,2026,25,50,"2026-06-17","04:30:00","2026-12-12","23:59:00","178d, 20h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-08-22",null,null,"1,2",1]
[null,"DB InfraGO AG","1DFAD-001","München - Salzburg",">","München Ost Pbf","Haar",2026,2026,50,50,"2026-12-07","23:00:00","2026-12-11","05:00:00","3d, 6h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-07-22",null,null,"6,7",1]
[null,"DB InfraGO AG","1071-(MK27)-01","München - Salzburg","< >","Rosenheim","Freilassing",2027,2027,5,27,"05.02.2027","21:00:00","09.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-08-28",null,null,"1,2,4",1]
[null,"DB InfraGO AG","1E18E-001","Nürnberg - Passau","< >","Beratzhausen","Seubersdorf",2026,2026,35,36,"2026-08-28","01:00:00","2026-08-31","04:00:00","3d, 3h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,7,1]
[null,"DB InfraGO AG","1E18E-002","Nürnberg - Passau","< >","Beratzhausen","Beratzhausen",2026,2026,37,40,"2026-09-07","20:00:00","2026-09-29","06:00:00","21d, 10h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"1,7",1]
[null,"DB InfraGO AG","1E18E-006","Nürnberg - Passau",">","Beratzhausen","Seubersdorf",2026,2026,44,45,"2026-10-30","01:00:00","2026-11-02","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,"1,7",1]
[null,"DB InfraGO AG","1E72F-016","Nürnberg - Passau",">","Beratzhausen","Parsberg",2026,2026,41,41,"2026-10-08","01:00:00","2026-10-08","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","1E72F-019","Nürnberg - Passau","<","Beratzhausen","Undorf",2026,2026,42,42,"2026-10-15","00:00:00","2026-10-15","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","1E5FD-046","Nürnberg - Passau","< >","Beratzhausen","Deining Üst",2026,2026,47,47,"2026-11-18","01:00:00","2026-11-18","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-09-25",null,null,1,1]
[null,"DB InfraGO AG","1E72F-023","Nürnberg - Passau",">","Deining Üst","Postbauer-Heng",2026,2026,44,44,"2026-10-27","19:00:00","2026-10-28","05:00:00","0d, 10h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-02",null,null,"1,2",1]
[null,"DB InfraGO AG","1E5FD-033","Nürnberg - Passau",">","Deining Üst","Neumarkt (Oberpf)",2026,2026,45,45,"2026-11-02","21:00:00","2026-11-05","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-09-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1E5FD-035","Nürnberg - Passau","<","Deining Üst","Seubersdorf",2026,2026,46,46,"2026-11-09","21:00:00","2026-11-14","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-10-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1E5FD-051","Nürnberg - Passau","< >","Deining Üst","Postbauer-Heng",2026,2026,47,47,"2026-11-19","01:00:00","2026-11-19","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-08",null,null,"2,3",1]
[null,"DB InfraGO AG","1E72F-003","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"3,4",1]
[null,"DB InfraGO AG","1E72F-011","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","01:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1E7D1-002","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,31,31,"2026-08-01","23:30:00","2026-08-02","04:30:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-02",null,null,"4,5",1]
[null,"DB InfraGO AG","1E7D1-003","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,38,38,"2026-09-19","23:30:00","2026-09-20","04:30:00","0d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","1E7D1-011","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","04:00:00","2d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","1E7D1-013","Nürnberg - Passau","< >","Feucht","Altdorf (b Nürnberg)",2026,2026,37,38,"2026-09-10","22:30:00","2026-09-14","04:30:00","3d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,5,1]
[null,"DB InfraGO AG","1E7D1-015","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,33,37,"2026-08-10","20:30:00","2026-09-07","04:30:00","27d, 8h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-07-30",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1E95C-010","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,44,44,"2026-10-30","23:00:00","2026-10-31","05:00:00","0d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"4,5",1]
[null,"DB InfraGO AG","1E95C-011","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,45,45,"2026-11-04","10:00:00","2026-11-07","16:00:00","3d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,7",1]
[null,"DB InfraGO AG","1E95C-012","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,45,46,"2026-11-08","06:00:00","2026-11-09","12:00:00","1d, 6h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","1E95C-013","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,46,46,"2026-11-10","10:00:00","2026-11-12","16:00:00","2d, 6h","Periodical","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-30",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","1E95C-014","Nürnberg - Passau","< >","Feucht","Nürnberg-Langwasser",2026,2026,46,46,"2026-11-12","23:00:00","2026-11-13","04:00:00","0d, 5h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E7D1-016","Nürnberg - Passau","< >","Feucht","Feucht",2026,2026,32,38,"2026-08-06","18:00:00","2026-09-14","18:00:00","39d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-29",null,null,2,1]
[null,"DB InfraGO AG","1067-(MK27)-01","Nürnberg - Passau",">","Feucht","Regensburg Bbf",2027,2027,47,49,"26.11.2027","21:00:00","10.12.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-10-29",null,null,"2,3",1]
[null,"DB InfraGO AG","1E4C5-008","Darmstadt - Nürnberg","<","Fürth (Bay) Gbf","Nürnberg Hohe Marter",2026,2026,32,34,"2026-08-08","05:00:00","2026-08-17","21:00:00","9d, 16h","Periodical","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-08-08",null,null,"5,6",1]
[null,"DB InfraGO AG","1E5EA-001","Darmstadt - Nürnberg","<","Fürth (Bay) Gbf","Nürnberg Hohe Marter",2026,2026,40,41,"2026-10-02","05:00:00","2026-10-07","21:00:00","5d, 16h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-08-08",null,null,"6,7",1]
[null,"DB InfraGO AG","1058-(MK27)-01_D","Darmstadt - Nürnberg",">","Fürth (Bay) Hbf","Bamberg",2027,2027,19,27,"15.05.2027","05:00:00","09.07.2027","21:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-11-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1058-(MK27)-01_N","Darmstadt - Nürnberg","< >","Fürth (Bay) Hbf","Bamberg",2027,2027,19,27,"14.05.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"ESP T + TSP N",null,null,null,"2024-11-15",null,null,"1,2",1]
[null,"DB InfraGO AG","1D973-001","Nürnberg - Passau","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,34,34,"2026-08-21","21:00:00","2026-08-23","21:00:00","2d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-02",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1D973-004","Nürnberg - Passau","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,34,39,"2026-08-23","21:00:00","2026-09-23","21:00:00","31d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-11-18",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1D973-005","Nürnberg - Passau","< >","Geiselhöring","Radldorf (Niederbay)",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-10-14",null,null,7,1]
[null,"DB InfraGO AG","1D0F3-003","Nürnberg - Passau","< >","Ingolstadt Nord","Nürnberg Reichswald",2026,2026,44,50,"2026-10-30","23:50:00","2026-12-11","04:50:00","41d, 5h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-10-17",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1CF23-014","Nürnberg - Passau","< >","Mangolding","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2024-11-25",null,null,7,1]
[null,"DB InfraGO AG","1CF23-022","Nürnberg - Passau","< >","Mangolding","Pleinting",2026,2026,50,50,"2026-12-12","06:00:00","2026-12-12","23:59:00","0d, 17h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-12-04",null,null,7,1]
[null,"DB InfraGO AG","1E72F-001","Nürnberg - Passau","< >","Neumarkt (Oberpf)","Neumarkt (Oberpf)",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1E72F-021","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,43,43,"2026-10-20","21:00:00","2026-10-23","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-09",null,null,"6,7",1]
[null,"DB InfraGO AG","1E72F-022","Nürnberg - Passau",">","Neumarkt (Oberpf)","Postbauer-Heng",2026,2026,43,43,"2026-10-24","00:00:00","2026-10-24","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-09",null,null,6,1]
[null,"DB InfraGO AG","1E5FD-034","Nürnberg - Passau","<","Neumarkt (Oberpf)","Deining (Oberpf)",2026,2026,46,46,"2026-11-09","21:00:00","2026-11-12","05:00:00","2d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-10",null,null,6,1]
[null,"DB InfraGO AG","1E5FD-036","Nürnberg - Passau","<","Neumarkt (Oberpf)","Seubersdorf",2026,2026,46,46,"2026-11-12","21:00:00","2026-11-13","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-29",null,null,"6,7",1]
[null,"DB InfraGO AG","1E72F-004","Nürnberg - Passau","<","Nürnberg Reichswald","Feucht",2026,2026,40,41,"2026-10-04","21:00:00","2026-10-05","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-07",null,null,"4,5",1]
[null,"DB InfraGO AG","1E72F-014","Nürnberg - Passau","<","Nürnberg Reichswald","Feucht",2026,2026,41,41,"2026-10-08","21:00:00","2026-10-10","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-07",null,null,4,1]
[null,"DB InfraGO AG","1E95C-007","Nürnberg - Passau","<","Nürnberg Reichswald","Feucht",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-12-23",null,null,2,1]
[null,"DB InfraGO AG","1E95C-008","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg-Dutzendteich",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-23",null,null,2,1]
[null,"DB InfraGO AG","1E95C-009","Nürnberg - Passau","< >","Nürnberg Reichswald","Allersberg (Rothsee)",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-23",null,null,"2,3",1]
[null,"DB InfraGO AG","1E95C-022","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg Reichswald",2026,2026,46,46,"2026-11-13","05:00:00","2026-11-14","12:00:00","1d, 7h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-23",null,null,"5,6",1]
[null,"DB InfraGO AG","1E95C-023","Nürnberg - Passau","< >","Nürnberg Reichswald","Nürnberg-Dutzendteich",2026,2026,50,50,"2026-12-11","05:00:00","2026-12-12","23:59:00","1d, 18h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-12-23",null,null,"1,2,6,7",1]
[null,"DB InfraGO AG","1E7D1-001","Nürnberg - Passau",">","Nürnberg-Dürrenhof","Feucht",2026,2026,31,31,"2026-08-01","23:30:00","2026-08-02","04:30:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,null,"N",null,"2025-01-08",null,null,"5,6",1]
[null,"DB InfraGO AG","1E7D1-004","Nürnberg - Passau",">","Nürnberg-Dürrenhof","Feucht",2026,2026,38,38,"2026-09-19","23:30:00","2026-09-20","04:30:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"15,,15",null,null,null,"N",null,"2025-01-09",null,null,"5,6",1]
[null,"DB InfraGO AG","1E7D1-012","Nürnberg - Passau","< >","Nürnberg-Dürrenhof","Feucht",2026,2026,32,33,"2026-08-07","22:00:00","2026-08-10","04:00:00","2d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-08",null,null,"1,7",1]
[null,"DB InfraGO AG","1E7D1-014","Nürnberg - Passau","< >","Nürnberg-Dürrenhof","Feucht",2026,2026,37,38,"2026-09-10","22:30:00","2026-09-14","04:30:00","3d, 6h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3498-(MK27)-01","Nürnberg - Passau","< >","Nürnberg-Dürrenhof","Feucht",2027,2027,30,36,"30.07.2027","21:00:00","10.09.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2025-01-08",null,null,"3,4",1]
[null,"DB InfraGO AG","3498-(MK27)-02","Nürnberg - Passau","< >","Nürnberg-Dürrenhof","Feucht",2027,2027,36,37,"10.09.2027","21:00:00","13.09.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2025-01-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D0F3-001","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,50,"2026-10-28","07:00:00","2026-12-11","23:59:00","44d, 16h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-12-10",null,null,"6,7",1]
[null,"DB InfraGO AG","1E95C-002","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,47,"2026-10-29","08:00:00","2026-11-16","08:00:00","18d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E95C-003","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,47,"2026-10-29","08:00:00","2026-11-16","08:00:00","18d, 0h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E95C-005","Nürnberg - Passau","< >","Nürnberg-Dutzendteich","Nürnberg-Dutzendteich",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-10",null,null,2,1]
[null,"DB InfraGO AG","1DDD1-025","Nürnberg - Passau","< >","Nürnberg-Eibach","Nürnberg Hbf",2026,2026,31,38,"2026-07-31","21:00:00","2026-09-15","04:00:00","45d, 7h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-10",null,null,2,1]
[null,"DB InfraGO AG","1E72F-005","Nürnberg - Passau",">","Nürnberg-Langwasser","Nürnberg Reichswald",2026,2026,40,41,"2026-10-04","21:00:00","2026-10-05","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2024-06-21",null,null,6,1]
[null,"DB InfraGO AG","1E95C-006","Nürnberg - Passau",">","Nürnberg-Langwasser","Nürnberg Reichswald",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-13","05:00:00","13d, 8h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,,",null,null,null,"N",null,"2025-01-14",null,null,6,1]
[null,"DB InfraGO AG","1F819-001","Nürnberg - Passau","< >","Obertraubling","Regensburg Ost",2026,2026,31,32,"2026-08-01","21:00:00","2026-08-08","21:00:00","7d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1F819-002","Nürnberg - Passau","< >","Obertraubling","Regensburg Ost",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-16","21:00:00","8d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-14",null,null,5,1]
[null,"DB InfraGO AG","1F819-010","Nürnberg - Passau","< >","Obertraubling","Regensburg Ost",2026,2026,31,32,"2026-08-01","21:00:00","2026-08-08","21:00:00","7d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2025-01-14",null,null,5,1]
[null,"DB InfraGO AG","1E72F-006","Nürnberg - Passau",">","Ochenbruck","Nürnberg Reichswald",2026,2026,41,41,"2026-10-05","21:00:00","2026-10-07","05:00:00","1d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-20",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-017","Nürnberg - Passau","<","Ochenbruck","Postbauer-Heng",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-18","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2025-01-20",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1E5FD-054","Nürnberg - Passau","< >","Ochenbruck","Postbauer-Heng",2026,2026,47,47,"2026-11-20","01:00:00","2026-11-20","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17",null,null,"6,7",1]
[null,"DB InfraGO AG","1D1F4-001","Nürnberg - Passau",">","Osterhofen (Niederbay)","Plattling",2026,2026,47,47,"2026-11-16","08:00:00","2026-11-16","16:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-04-12",null,null,"6,7",1]
[null,"DB InfraGO AG","1E18E-003","Nürnberg - Passau","< >","Parsberg","Parsberg",2026,2026,41,44,"2026-10-05","20:00:00","2026-10-26","06:00:00","20d, 11h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO AG","1E18E-007","Nürnberg - Passau",">","Parsberg","Deining Üst",2026,2026,48,49,"2026-11-27","01:00:00","2026-11-30","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"1,2",1]
[null,"DB InfraGO AG","1E72F-010","Nürnberg - Passau",">","Parsberg","Seubersdorf",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","01:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1E72F-013","Nürnberg - Passau","<","Parsberg","Beratzhausen",2026,2026,41,42,"2026-10-08","21:00:00","2026-10-13","05:00:00","4d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"2,3",1]
[null,"DB InfraGO AG","1E5FD-032","Nürnberg - Passau",">","Parsberg","Seubersdorf",2026,2026,45,45,"2026-11-02","21:00:00","2026-11-06","05:00:00","3d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-11",null,null,"3,4",1]
[null,"DB InfraGO AG","1E72F-029","Nürnberg - Passau","< >","Parsberg","Parsberg",2026,2026,41,41,"2026-10-07","01:00:00","2026-10-07","05:00:00","0d, 4h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-01-11",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CD61-002","Nürnberg - Passau","< >","Passau Gbf","Plattling",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CF23-010","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D552-001","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,39,40,"2026-09-25","05:00:00","2026-10-04","05:00:00","9d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D552-003","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,42,43,"2026-10-13","05:00:00","2026-10-22","05:00:00","9d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-08",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D552-004","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,43,44,"2026-10-23","05:00:00","2026-11-01","05:00:00","9d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D552-005","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,43,44,"2026-10-23","05:00:00","2026-11-01","05:00:00","9d, 1h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D659-007","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,6,1]
[null,"DB InfraGO AG","1D659-008","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,6,1]
[null,"DB InfraGO AG","1D710-005","Nürnberg - Passau","< >","Passau Gbf","Passau Gbf",2026,2026,38,38,"2026-09-18","22:00:00","2026-09-20","04:00:00","1d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"5,6",1]
[null,"DB InfraGO AG","1CF23-009","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CF23-015","Nürnberg - Passau","< >","Passau Hbf","Vilshofen (Niederbay)",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"11,11,11",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D552-002","Nürnberg - Passau","< >","Passau Hbf","Passau Gbf",2026,2026,41,42,"2026-10-05","05:00:00","2026-10-12","05:00:00","7d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-08",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-001","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,38,39,"2026-09-19","22:00:00","2026-09-21","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-002","Nürnberg - Passau","< >","Passau Hbf","Passau Grenze",2026,2026,39,40,"2026-09-26","22:00:00","2026-09-28","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-003","Nürnberg - Passau","< >","Passau Hbf","Passau Gbf",2026,2026,39,40,"2026-09-26","22:00:00","2026-09-28","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-004","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,40,41,"2026-10-03","22:00:00","2026-10-05","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-005","Nürnberg - Passau","< >","Passau Hbf","Passau Grenze",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-006","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,41,42,"2026-10-10","22:00:00","2026-10-12","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-08",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-007","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,38,39,"2026-09-19","22:00:00","2026-09-21","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-008","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,40,41,"2026-10-03","22:00:00","2026-10-05","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,1,1]
[null,"DB InfraGO AG","1D5C0-009","Nürnberg - Passau","< >","Passau Hbf","Passau Grenze",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","05:00:00","1d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,4,1]
[null,"DB InfraGO AG","1D5C0-010","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","05:00:00","1d, 7h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-27",null,null,4,1]
[null,"DB InfraGO AG","1D5C0-011","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,43,44,"2026-10-24","22:00:00","2026-10-26","05:00:00","1d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-14",null,null,4,1]
[null,"DB InfraGO AG","1D5C0-012","Nürnberg - Passau","< >","Passau Hbf","Passau Hbf",2026,2026,43,44,"2026-10-24","22:00:00","2026-10-26","05:00:00","1d, 8h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-12-13",null,null,4,1]
[null,"DB InfraGO AG","1CD61-005","Nürnberg - Passau","< >","Plattling","Obertraubling",2026,2026,28,38,"2026-07-10","21:00:00","2026-09-20","21:00:00","72d, 0h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-04-05",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1CF23-003","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-05",null,null,"1,2,5,6,7",1]
[null,"DB InfraGO AG","1CF23-004","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,"6,7",1]
[null,"DB InfraGO AG","1CF23-016","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CF23-017","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-04-05",null,null,"6,7",1]
[null,"DB InfraGO AG","1CF23-018","Nürnberg - Passau","< >","Plattling","Mangolding",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"16,16,16",null,null,null,"N",null,"2024-05-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1CF23-019","Nürnberg - Passau","< >","Plattling","Vilshofen (Niederbay)",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-27",null,null,"1,2",1]
[null,"DB InfraGO AG","1D1F4-002","Nürnberg - Passau",">","Plattling","Straßkirchen",2026,2026,47,47,"2026-11-17","08:00:00","2026-11-18","16:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-30",null,null,"3,4",1]
[null,"DB InfraGO AG","1D1F4-003","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,47,47,"2026-11-19","08:00:00","2026-11-20","16:00:00","1d, 8h","Periodical","Catenary",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"3,4,5",1]
[null,"DB InfraGO AG","1D1F4-005","Nürnberg - Passau","<","Plattling","Osterhofen (Niederbay)",2026,2026,48,48,"2026-11-25","08:00:00","2026-11-25","16:00:00","0d, 8h","Continuous","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-30",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1D495-015","Nürnberg - Passau","< >","Plattling","Plattling",2026,2026,38,45,"2026-09-15","02:00:00","2026-11-05","04:00:00","51d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-15",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1CD61-009","Nürnberg - Passau","< >","Plattling","Obertraubling",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Container","T",null,null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-05-24",null,null,"5,6,7",1]
[null,"DB InfraGO AG","2AF29-001","Nürnberg - Passau","<","Plattling","Passau Gbf",2026,2026,28,38,"2026-07-10","21:00:00","2026-09-20","21:00:00","72d, 0h","Continuous","Container",null,"LT",null,null,null,",,",",,",null,"5,5,5",null,null,null,"N",null,"2024-05-24",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1CF23-023","Nürnberg - Passau","< >","Pleinting","Mangolding",2026,2026,50,50,"2026-12-12","06:00:00","2026-12-12","23:59:00","0d, 17h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"2024-05-24",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1E72F-015","Nürnberg - Passau",">","Postbauer-Heng","Feucht",2026,2026,42,42,"2026-10-12","01:00:00","2026-10-12","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-025","Nürnberg - Passau","<","Postbauer-Heng","Neumarkt (Oberpf)",2026,2026,44,44,"2026-10-28","21:00:00","2026-10-29","02:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-14",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CF23-011","Nürnberg - Passau","< >","Regensburg Bbf","Regensburg Bbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,1,1]
[null,"DB InfraGO AG","1DE17-010","Nürnberg - Passau","<","Regensburg Bbf","Regensburg Ost",2026,2026,38,38,"2026-09-15","21:00:00","2026-09-16","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"12,12,12",null,null,null,"N",null,"2024-05-24",null,null,1,1]
[null,"DB InfraGO AG","1DE17-011","Nürnberg - Passau","<","Regensburg Bbf","Regensburg Hbf",2026,2026,38,38,"2026-09-18","21:00:00","2026-09-20","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-24",null,null,1,1]
[null,"DB InfraGO AG","1E72F-002","Nürnberg - Passau","< >","Regensburg Bbf","Regensburg Bbf",2026,2026,40,47,"2026-10-02","18:00:00","2026-11-17","20:00:00","46d, 3h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,1,1]
[null,"DB InfraGO AG","1E72F-024","Nürnberg - Passau",">","Regensburg Bbf","Beratzhausen",2026,2026,44,44,"2026-10-28","00:00:00","2026-10-28","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,1,1]
[null,"DB InfraGO AG","1DE17-008","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-15","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-06-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1DE17-012","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Bbf",2026,2026,38,39,"2026-09-20","21:00:00","2026-09-21","05:00:00","0d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-06-14",null,null,"4,5",1]
[null,"DB InfraGO AG","1CF23-012","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1DA81-001","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,33,34,"2026-08-14","07:00:00","2026-08-23","04:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"6,7",1]
[null,"DB InfraGO AG","1DE17-006","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,26,37,"2026-06-23","21:00:00","2026-09-13","04:55:00","81d, 7h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"6,7",1]
[null,"DB InfraGO AG","1DE17-009","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Hbf",2026,2026,37,38,"2026-09-13","21:00:00","2026-09-15","05:00:00","1d, 8h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2023-11-24",null,null,"1,2,3,4,5,6",1]
[null,"DB InfraGO AG","1DE17-013","Nürnberg - Passau","< >","Regensburg Hbf","Regensburg Bbf",2026,2026,38,38,"2026-09-16","23:00:00","2026-09-18","05:00:00","1d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"2,2,2",null,null,null,"N",null,"2024-05-13",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1E72F-026","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,44,44,"2026-10-28","21:00:00","2026-10-29","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,6,7",1]
[null,"DB InfraGO AG","1E5FD-030","Nürnberg - Passau",">","Regensburg Hbf","Undorf",2026,2026,44,44,"2026-10-31","01:00:00","2026-10-31","05:00:00","0d, 4h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-31",null,null,"1,2",1]
[null,"DB InfraGO AG","1CF23-006","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,"1,2,3,4",1]
[null,"DB InfraGO AG","1F819-007","Nürnberg - Passau","< >","Regensburg Ost","Obertraubling",2026,2026,32,33,"2026-08-08","21:00:00","2026-08-16","21:00:00","8d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-31",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1CF23-013","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1DA81-002","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","07:00:00","2026-08-23","04:00:00","8d, 21h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-21",null,null,"1,2",1]
[null,"DB InfraGO AG","1DA81-003","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2023-11-29",null,null,"1,2",1]
[null,"DB InfraGO AG","1DA81-004","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-19",null,null,"3,4",1]
[null,"DB InfraGO AG","1DA81-005","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","22:00:00","2026-08-23","04:00:00","8d, 6h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1DA81-006","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,33,34,"2026-08-14","23:00:00","2026-08-23","03:00:00","8d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"5,6,7",1]
[null,"DB InfraGO AG","1DA81-007","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,42,43,"2026-10-17","22:00:00","2026-10-19","04:00:00","1d, 6h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2",1]
[null,"DB InfraGO AG","1F819-013","Nürnberg - Passau","< >","Regensburg Ost","Regensburg Ost",2026,2026,31,34,"2026-07-29","17:00:00","2026-08-17","12:00:00","18d, 19h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"3,4",1]
[null,"DB InfraGO AG","1E5FD-041","Nürnberg - Passau","< >","Regensburg-Prüfening               (NRH)","Beratzhausen",2026,2026,47,47,"2026-11-17","01:00:00","2026-11-17","05:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,4,1]
[null,"DB InfraGO AG","3321-(MK27)-01","Nürnberg - Passau",">","Reichswald","Nürnberg Hbf",2027,2027,15,16,"16.04.2027","21:00:00","23.04.2027","21:00:00",null,"Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, VZ",null,null,null,"2024-05-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1E18E-004","Nürnberg - Passau","< >","Seubersdorf","Seubersdorf",2026,2026,45,48,"2026-11-03","00:00:00","2026-11-23","06:00:00","20d, 6h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO AG","1E72F-009","Nürnberg - Passau","< >","Seubersdorf","Parsberg",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","01:00:00","0d, 4h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO AG","1E5FD-031","Nürnberg - Passau",">","Seubersdorf","Neumarkt (Oberpf)",2026,2026,44,45,"2026-11-01","22:00:00","2026-11-02","05:00:00","0d, 7h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-07",null,null,6,1]
[null,"DB InfraGO AG","1D1F4-004","Nürnberg - Passau","<","Straßkirchen","Plattling",2026,2026,48,48,"2026-11-23","08:00:00","2026-11-24","16:00:00","1d, 8h","Periodical","Catenary",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-01-04",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CF23-005","Nürnberg - Passau","< >","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"6,7",1]
[null,"DB InfraGO AG","1CF23-007","Nürnberg - Passau","< >","Straubing","Straubing",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-01",null,null,7,1]
[null,"DB InfraGO AG","1D973-002","Nürnberg - Passau","< >","Straubing","Bogen",2026,2026,34,38,"2026-08-21","21:00:00","2026-09-20","20:59:00","29d, 23h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","1D973-003","Nürnberg - Passau","< >","Straubing","Bogen",2026,2026,42,47,"2026-10-14","00:00:00","2026-11-19","00:00:00","36d, 1h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","1EA40-002","Nürnberg - Passau","< >","Straubing","Bogen",2026,2026,31,32,"2026-07-31","06:00:00","2026-08-03","22:00:00","3d, 16h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,7,1]
[null,"DB InfraGO AG","1EA40-003","Nürnberg - Passau","< >","Straubing","Bogen",2026,2026,33,34,"2026-08-14","06:00:00","2026-08-17","22:00:00","3d, 16h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,7,1]
[null,"DB InfraGO AG","1E18E-005","Nürnberg - Passau",">","Undorf","Parsberg",2026,2026,40,41,"2026-10-02","01:00:00","2026-10-05","05:00:00","3d, 4h","Continuous","Miscellaneous",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-018","Nürnberg - Passau",">","Undorf","Parsberg",2026,2026,42,42,"2026-10-14","00:00:00","2026-10-14","05:00:00","0d, 5h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-020","Nürnberg - Passau",">","Undorf","Beratzhausen",2026,2026,42,43,"2026-10-18","21:00:00","2026-10-24","05:00:00","5d, 8h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1E72F-028","Nürnberg - Passau","<","Undorf","Regensburg Dörnberg",2026,2026,44,44,"2026-10-29","21:00:00","2026-10-30","05:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1CD61-004","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2026,2026,38,50,"2026-09-20","21:00:00","2026-12-11","21:00:00","82d, 1h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,3,1]
[null,"DB InfraGO AG","1CF23-008","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Vilshofen (Niederbay)",2026,2026,23,50,"2026-06-01","06:00:00","2026-12-12","23:59:00","194d, 18h","Continuous","Container",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,5,1]
[null,"DB InfraGO AG","1CF23-020","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Passau Hbf",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"11,11,11",null,null,null,"N",null,"2024-05-23",null,null,5,1]
[null,"DB InfraGO AG","1CF23-021","Nürnberg - Passau","< >","Vilshofen (Niederbay)","Plattling",2026,2026,50,50,"2026-12-11","21:00:00","2026-12-12","06:00:00","0d, 9h","Continuous","Container",null,null,"S",null,null,",,",",,",null,"10,10,10",null,null,null,"N",null,"2024-05-23",null,null,"1,5,6,7",1]
[null,"DB InfraGO AG","1D1F4-006","Nürnberg - Passau","< >","Wallersdorf","Plattling",2026,2026,48,48,"2026-11-26","08:00:00","2026-11-27","16:00:00","1d, 8h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,2,1]
[null,"DB InfraGO AG","1260-(MK27)-01","Nürnberg - Plzen","< >","Hersbruck (re P)","Marktredwitz",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","1260-(MK27)-02","Nürnberg - Plzen",">","Hersbruck (re P)","Marktredwitz",2027,2027,36,38,"10.09.2027","21:00:00","24.09.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-05-23",null,null,3,1]
[null,"DB InfraGO AG","20DE0-001","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,32,"2026-08-04","00:00:00","2026-08-05","04:35:00","1d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-23",null,null,3,1]
[null,"DB InfraGO AG","20DE0-002","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,38,"2026-08-04","00:00:00","2026-09-16","00:00:00","43d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","20DE0-003","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,38,"2026-08-04","00:00:00","2026-09-16","00:00:00","43d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-007","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,34,"2026-08-09","04:45:00","2026-08-20","04:45:00","11d, 0h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-014","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Pommelsbrunn",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","20DE0-015","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-016","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","20DE0-017","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"4,,4",null,null,null,"N",null,"2024-05-23",null,null,7,1]
[null,"DB InfraGO AG","20DE0-018","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,34,37,"2026-08-20","04:45:00","2026-09-11","05:00:00","22d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"3,,3",null,null,null,"N",null,"2024-05-23",null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-020","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,33,37,"2026-08-15","04:45:00","2026-09-12","18:30:00","28d, 13h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-021","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,34,38,"2026-08-20","04:45:00","2026-09-14","08:00:00","25d, 3h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"2,,2",null,null,null,"N",null,null,null,null,"1,2,3,4,5",1]
[null,"DB InfraGO AG","20DE0-022","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz) Ost",2026,2026,37,38,"2026-09-12","18:30:00","2026-09-17","11:00:00","4d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","213D2-004","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,35,36,"2026-08-29","05:00:00","2026-09-01","05:00:00","3d, 0h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","213D2-005","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,36,36,"2026-08-31","01:10:00","2026-09-01","05:00:00","1d, 3h","Continuous","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,2,1]
[null,"DB InfraGO AG","213D2-006","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,35,36,"2026-08-29","22:00:00","2026-08-31","06:00:00","1d, 8h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO AG","213D2-008","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,37,37,"2026-09-08","05:00:00","2026-09-10","05:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO AG","213D2-009","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-10","23:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,3,1]
[null,"DB InfraGO AG","213D2-010","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Pommelsbrunn",2026,2026,37,37,"2026-09-08","23:00:00","2026-09-10","23:00:00","2d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-13",null,null,"1,2",1]
[null,"DB InfraGO AG","213D2-011","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,37,38,"2026-09-10","23:00:00","2026-09-15","23:00:00","5d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","213D2-012","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz)","Vorra (Pegnitz)",2026,2026,37,38,"2026-09-10","23:00:00","2026-09-15","23:00:00","5d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","20DE0-005","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,32,33,"2026-08-09","04:45:00","2026-08-15","04:45:00","6d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,"5,6",1]
[null,"DB InfraGO AG","20DE0-008","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,32,33,"2026-08-09","00:00:00","2026-08-15","04:45:00","6d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,6,1]
[null,"DB InfraGO AG","20DE0-011","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,33,34,"2026-08-15","04:45:00","2026-08-20","04:45:00","5d, 0h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,7,1]
[null,"DB InfraGO AG","20DE0-012","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,33,34,"2026-08-15","00:00:00","2026-08-20","04:45:00","5d, 4h","Periodical","Track & Rail",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,7",1]
[null,"DB InfraGO AG","20DE0-019","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,37,37,"2026-09-11","05:00:00","2026-09-12","18:30:00","1d, 13h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,4,1]
[null,"DB InfraGO AG","20DE0-023","Nürnberg - Plzen","< >","Hersbruck (rechts Pegnitz) Ost","Hersbruck (rechts Pegnitz)",2026,2026,37,38,"2026-09-12","18:30:00","2026-09-17","11:00:00","4d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,5,1]
[null,"DB InfraGO AG","20ED5-002","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,44,45,"2026-10-30","14:00:00","2026-11-04","14:00:00","5d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-24",null,null,"1,7",1]
[null,"DB InfraGO AG","20ED5-004","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,45,47,"2026-11-04","14:00:00","2026-11-17","14:00:00","13d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-05-24",null,null,"1,7",1]
[null,"DB InfraGO AG","20F03-003","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,44,45,"2026-10-30","14:00:00","2026-11-04","14:00:00","5d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-11-21",null,null,"1,2",1]
[null,"DB InfraGO AG","20F03-004","Nürnberg - Plzen","< >","Kirchenlaibach","Schnabelwaid",2026,2026,45,47,"2026-11-04","14:00:00","2026-11-17","14:00:00","13d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"0,0,0",null,null,null,"N",null,"2024-11-21",null,null,"5,6",1]
[null,"DB InfraGO AG","1550-(MK27)-01","Nürnberg - Plzen","< >","Marktredwitz","Schirnding Grenz",2027,2027,27,28,"09.07.2027","21:00:00","16.07.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-24",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1550-(MK27)-02","Nürnberg - Plzen","< >","Marktredwitz","Schirnding Grenz",2027,2027,28,29,"16.07.2027","21:00:00","19.07.2027","05:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, WE",null,null,null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","1848-(MK27)-01","Nürnberg - Plzen","< >","Marktredwitz","Oberkotzau",2027,2027,11,19,"19.03.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","22378-003","Nürnberg - Plzen","< >","Marktredwitz","Neusorg",2026,2026,32,32,"2026-08-06","05:00:00","2026-08-07","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-01-18",null,null,"1,2,3,4,5,6,7",1]
[null,"DB InfraGO AG","2138C-002","Nürnberg - Plzen","< >","Neuhaus (Pegnitz)","Pegnitz",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"4,5",1]
[null,"DB InfraGO AG","20DE0-006","Nürnberg - Plzen",">","Neunkirchen a Sand","Hersbruck (rechts Pegnitz)",2026,2026,32,34,"2026-08-09","04:45:00","2026-08-20","04:45:00","11d, 0h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,null,null,null,7,1]
[null,"DB InfraGO AG","22378-002","Nürnberg - Plzen","< >","Neusorg","Marktredwitz",2026,2026,31,32,"2026-07-31","21:00:00","2026-08-06","05:00:00","5d, 8h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,5]
[null,"DB InfraGO AG","22378-004","Nürnberg - Plzen","< >","Neusorg","Marktredwitz",2026,2026,32,32,"2026-08-06","05:00:00","2026-08-07","05:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-31",null,null,6]
[null,"DB InfraGO AG","2057A-005","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-31",null,null,6]
[null,"DB InfraGO AG","2057A-011","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,41,41,"2026-10-10","21:00:00","2026-10-11","06:00:00","0d, 9h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2057A-014","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,41,42,"2026-10-11","22:00:00","2026-10-12","06:00:00","0d, 8h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-30",null,null,"1,2,3,6,7"]
[null,"DB InfraGO AG","227DA-002","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg-Dutzendteich",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-14","04:00:00","14d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,6,7"]
[null,"DB InfraGO AG","2057A-004","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,"2024-05-07",null,null,"3,4,5"]
[null,"DB InfraGO AG","2057A-006","Nürnberg - Plzen","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-16",null,null,"3,4,5"]
[null,"DB InfraGO AG","2057A-009","Nürnberg - Plzen",">","Nürnberg Ost","Nürnberg-Erlenstegen",2026,2026,36,36,"2026-08-31","06:00:00","2026-09-02","12:00:00","2d, 6h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,6]
[null,"DB InfraGO AG","2057A-010","Nürnberg - Plzen",">","Nürnberg Ost","Nürnberg-Erlenstegen",2026,2026,36,36,"2026-09-02","12:00:00","2026-09-06","04:00:00","3d, 16h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2057A-012","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,41,41,"2026-10-10","22:00:00","2026-10-11","06:00:00","0d, 8h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,null,null,null,"3,4,5,6"]
[null,"DB InfraGO AG","2057A-013","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,41,42,"2026-10-11","23:40:00","2026-10-12","06:00:00","0d, 6h","Continuous","Track & Rail",null,"LT",null,null,null,",,",",,",null,"3,3,",null,null,null,"N",null,null,null,null,"3,4,5,6"]
[null,"DB InfraGO AG","2080A-018","Nürnberg - Plzen","< >","Nürnberg Ost","Lauf (rechts Pegnitz)",2026,2026,44,46,"2026-10-30","22:00:00","2026-11-09","06:00:00","9d, 8h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-023","Nürnberg - Plzen","< >","Nürnberg Ost","Lauf (rechts Pegnitz)",2026,2026,12,50,"2026-03-19","01:55:00","2026-12-12","04:00:00","268d, 2h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","227DA-001","Nürnberg - Plzen","< >","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,44,46,"2026-10-30","21:00:00","2026-11-14","04:00:00","14d, 7h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,null,null,null,"1,2,7"]
[null,"DB InfraGO AG","227DA-005","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,46,46,"2026-11-14","04:00:00","2026-11-15","04:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"3,4"]
[null,"DB InfraGO AG","227DA-006","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,46,46,"2026-11-14","04:00:00","2026-11-15","04:00:00","1d, 0h","Continuous","Bridge",null,null,"S",null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"2,3,4,5"]
[null,"DB InfraGO AG","227DA-007","Nürnberg - Plzen",">","Nürnberg Ost","Rückersdorf (Mittelfr)",2026,2026,47,47,"2026-11-16","08:30:00","2026-11-17","15:30:00","1d, 7h","Periodical","Bridge",null,"LT",null,null,null,",,",",,",null,"3,,3",null,null,null,"N",null,null,null,null,"2,3,4,5"]
[null,"DB InfraGO AG","227DA-008","Nürnberg - Plzen","< >","Nürnberg Ost","Nürnberg Ost",2026,2026,47,47,"2026-11-18","08:30:00","2026-11-19","15:30:00","1d, 7h","Periodical","Bridge",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,null,null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","213D2-003","Nürnberg - Plzen","< >","Pommelsbrunn","Hersbruck (rechts Pegnitz)",2026,2026,36,37,"2026-09-01","05:00:00","2026-09-08","23:00:00","7d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2057A-003","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,31,36,"2026-07-31","01:45:00","2026-08-31","04:35:00","31d, 2h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,6,7"]
[null,"DB InfraGO AG","2057A-007","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,31,36,"2026-07-31","22:00:00","2026-08-31","06:00:00","30d, 8h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"2024-05-07",null,null,"1,2,6,7"]
[null,"DB InfraGO AG","2057A-008","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Nürnberg Ost",2026,2026,31,36,"2026-07-31","23:40:00","2026-08-31","04:40:00","30d, 5h","Periodical","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-003","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,10,50,"2026-03-06","22:00:00","2026-12-12","23:59:00","281d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-004","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,10,50,"2026-03-06","22:00:00","2026-12-12","23:59:00","281d, 1h","Continuous","Miscellaneous",null,null,"S",null,null,",,",",,",null,"0,,0",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-005","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,11,50,"2026-03-10","22:00:00","2026-12-12","23:59:00","277d, 1h","Continuous","Miscellaneous",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"5,6,7"]
[null,"DB InfraGO AG","2080A-008","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,12,32,"2026-03-18","06:00:00","2026-08-09","06:00:00","143d, 23h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-011","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,32,34,"2026-08-09","06:00:00","2026-08-21","06:00:00","12d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,"1,,1",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-012","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,34,44,"2026-08-21","06:00:00","2026-10-30","22:00:00","70d, 17h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","2080A-017","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,48,50,"2026-11-29","06:00:00","2026-12-12","23:59:00","13d, 17h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-24",null,null,4]
[null,"DB InfraGO AG","2080A-019","Nürnberg - Plzen","< >","Rückersdorf (Mittelfr)","Rückersdorf (Mittelfr)",2026,2026,46,48,"2026-11-09","06:00:00","2026-11-29","06:00:00","20d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4]
[null,"DB InfraGO AG","20ED5-001","Nürnberg - Plzen","< >","Schnabelwaid","Kirchenlaibach",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","14:00:00","6d, 17h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"2,3,4,5"]
[null,"DB InfraGO AG","20F03-002","Nürnberg - Plzen","< >","Schnabelwaid","Kirchenlaibach",2026,2026,43,44,"2026-10-23","22:00:00","2026-10-30","14:00:00","6d, 17h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","20BFC-003","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","21387-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","21388-003","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","2138A-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG",21.38,"Nürnberg - Plzen","< >","Vorra (Pegnitz)","Neuhaus (Pegnitz)",2026,2026,34,37,"2026-08-21","21:00:00","2026-09-11","04:50:00","20d, 7h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,1]
[null,"DB InfraGO AG","20DE0-004","Nürnberg - Plzen","<","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,32,32,"2026-08-06","00:00:00","2026-08-07","04:35:00","1d, 4h","Periodical","Track & Rail",null,"LT",null,null,null,",,",",,",null,"10,,10",null,null,null,"N",null,"2024-05-07",null,null,1]
[null,"DB InfraGO AG","213D2-002","Nürnberg - Plzen","< >","Vorra (Pegnitz)","Hersbruck (rechts Pegnitz)",2026,2026,36,37,"2026-09-01","05:00:00","2026-09-08","23:00:00","7d, 18h","Continuous","Bridge","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1053-(MK27)-02","Regensburg - Plzen","< >","Marktredwitz","Regensburg Ost & Regensburg Hbf",2027,2027,41,49,"15.10.2027","21:00:00","10.12.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1053-(MK27)-03","Regensburg - Plzen",">","Marktredwitz","Regensburg Ost & Regensburg Hbf",2027,2027,22,25,"04.06.2027","21:00:00","25.06.2027","05:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"ESP, N",null,null,null,"2024-05-07",null,null,1]
[null,"DB InfraGO AG","1053-(MK27)-04","Regensburg - Plzen","< >","Marktredwitz","Regensburg Ost & Regensburg Hbf",2027,2027,25,27,"25.06.2027","21:00:00","09.07.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-05-07",null,null,1]
[null,"DB InfraGO AG","1053-(MK27)-05","Regensburg - Plzen","< >","Marktredwitz","Regensburg Ost & Regensburg Hbf",2027,2027,33,35,"20.08.2027","21:00:00","03.09.2027","05:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, N",null,null,null,"2024-05-07",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","1775-(MK27)-01","Regensburg - Plzen","< >","Schwandorf","Furth i W Grenze",2027,2027,5,19,"05.02.2027","21:00:00","14.05.2027","21:00:00",null,"Continuous","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, VZ",null,null,null,"2024-05-28",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","20EC7-021","Rostock - Berlin","< >","Bentwisch","Rostock Seehafen Süd",2026,2026,40,42,"2026-10-03","07:00:00","2026-10-16","16:00:00","13d, 9h","Periodical","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-28",null,null,"5,6"]
[null,"DB InfraGO AG","23B3D-005","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,3]
[null,"DB InfraGO AG","23B5A-005","Rostock - Berlin","< >","Bergfelde Ost","Hohen Neuend Sw",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-06",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-003","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B5A-011","Rostock - Berlin","< >","Berlin-Blankenburg","Berlin-Karow West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","23B3D-002","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-07",null,null,4]
[null,"DB InfraGO AG","23B5A-012","Rostock - Berlin","< >","Berlin-Karow","Berlin-Karow West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-06-07",null,null,5]
[null,"DB InfraGO AG","23B3D-001","Rostock - Berlin","< >","Berlin-Karow Ost","Hohen Neuendorf West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14",null,null,6]
[null,"DB InfraGO AG","3191-(MK27)-01","Rostock - Berlin","< >","Berlin-Moabit","Berlin-Wedding Abzw",2027,2027,1,5,"09.01.2027","05:00:00","05.02.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-05-21",null,null,4]
[null,"DB InfraGO AG","3191-(MK27)-02","Rostock - Berlin","< >","Berlin-Moabit","Berlin-Wedding Abzw",2027,2027,9,13,"06.03.2027","05:00:00","02.04.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-05-21",null,null,6]
[null,"DB InfraGO AG","3191-(MK27)-04","Rostock - Berlin","< >","Berlin-Moabit","Berlin-Wedding Abzw",2027,2027,41,43,"16.10.2027","05:00:00","29.10.2027","21:00:00",null,"Periodical","Miscellaneous","T",null,null,null,null,null,null,null,null,null,"TSP, T",null,null,null,"2024-05-21",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","21793-002","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Birkenwerder (b Berlin)",2026,2026,36,37,"2026-09-06","06:00:00","2026-09-13","18:00:00","7d, 12h","Continuous","Track & Rail",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"5,6"]
[null,"DB InfraGO AG","23B3D-004","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-007","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Hohen Neuendorf West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B5A-002","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"4,5,6,7"]
[null,"DB InfraGO AG","23B5A-004","Rostock - Berlin","< >","Birkenwerder (b Berlin)","Birkenwerder (b Berlin)",2026,2026,46,50,"2026-11-13","21:00:00","2026-12-11","21:00:00","28d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-29",null,null,"1,5,6,7"]
[null,"DB InfraGO AG","23B3E-001","Rostock - Berlin","< >","Birkenwerder Nord","Nassenheide",2026,2026,46,50,"2026-11-13","21:00:00","2026-12-11","21:00:00","28d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-16",null,null,"5,6"]
[null,"DB InfraGO AG","23B3F-001","Rostock - Berlin","< >","Birkenwerder Nord","Nassenheide",2026,2026,44,45,"2026-10-30","21:00:00","2026-11-06","21:00:00","7d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-16",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B39-003","Rostock - Berlin","< >","Birkenwerder Nord","Nassenheide",2026,2026,40,42,"2026-10-02","21:00:00","2026-10-16","21:00:00","14d, 0h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-18",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-006","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-01-23",null,null,5]
[null,"DB InfraGO AG","23B3D-008","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder Nord",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,5]
[null,"DB InfraGO AG","23B5A-003","Rostock - Berlin","< >","Hohen Neuend Sw","Schönfließ West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,2,5,6,7"]
[null,"DB InfraGO AG","23B5A-006","Rostock - Berlin","< >","Hohen Neuend Sw","Birkenwerder (b Berlin)",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-13",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","24036-002","Rostock - Berlin","<","Kargow","Neustrelitz Hbf",2026,2026,48,50,"2026-11-25","21:00:00","2026-12-11","21:00:00","16d, 0h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"6,7"]
[null,"DB InfraGO AG","24036-003","Rostock - Berlin","< >","Kargow","Vollrathsruhe",2026,2026,46,50,"2026-11-13","23:00:00","2026-12-11","05:00:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-08",null,null,"5,6"]
[null,"DB InfraGO AG","23B5A-001","Rostock - Berlin","< >","Karower Kr Strw","Hohen Neuendorf West",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"1,2"]
[null,"DB InfraGO AG","23B5A-010","Rostock - Berlin","< >","Karower Kr Strw","Berlin-Karow Ost",2026,2026,47,49,"2026-11-20","21:00:00","2026-12-04","21:00:00","14d, 0h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-04-18",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-013","Rostock - Berlin","< >","Löwenberg (Mark)","Zehdenick (Mark)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-015","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg DB-Gr",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-03",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","24036-009","Rostock - Berlin","< >","Löwenberg (Mark)","Löwenberg DB-Gr",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","24036-010","Rostock - Berlin","< >","Löwenberg (Mark)","Zehdenick (Mark)",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-02-07",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-009","Rostock - Berlin","< >","Nassenheide","Neustrelitz Hbf",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5"]
[null,"DB InfraGO AG","24036-008","Rostock - Berlin","< >","Nassenheide","Neustrelitz Hbf",2026,2026,46,50,"2026-11-13","22:45:00","2026-12-11","04:45:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-22",null,null,"1,2,3,4,5,6,7"]
[null,"DB InfraGO AG","23B3D-010","Rostock - Berlin","< >","Neustrelitz Hbf","Blankensee (Meckl)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14"]
[null,"DB InfraGO AG","23B3D-011","Rostock - Berlin","< >","Neustrelitz Hbf","Vollrathsruhe",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14"]
[null,"DB InfraGO AG","23B3D-014","Rostock - Berlin","< >","Neustrelitz Hbf","Neustrelitz Gr",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14"]
[null,"DB InfraGO AG","24036-001","Rostock - Berlin",">","Neustrelitz Hbf","Kargow",2026,2026,46,48,"2026-11-13","21:00:00","2026-11-25","21:00:00","12d, 0h","Continuous","Signal",null,"LT",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-05-14"]
[null,"DB InfraGO AG","23B39-004","Rostock - Berlin","< >","Oranienburg","Oranienburg",2026,2026,39,40,"2026-09-25","21:00:00","2026-10-02","21:00:00","7d, 0h","Continuous","Signal",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2025-01-17"]
[null,"DB InfraGO AG","20EC7-015","Rostock - Berlin","< >","Rostock Seehafen Süd","Bentwisch",2026,2026,40,42,"2026-10-02","23:15:00","2026-10-16","21:00:00","13d, 21h","Continuous","Miscellaneous","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","23B5A-007","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","23B5A-008","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","23B5A-009","Rostock - Berlin","< >","Schönfließ West","Schönfließ West",2026,2026,49,50,"2026-12-04","21:00:00","2026-12-08","14:00:00","3d, 17h","Continuous","Track & Rail",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"06.12.2024"]
[null,"DB InfraGO AG","24021-001","Rostock - Berlin","< >","Waren (Müritz)","Waren (Müritz)",2026,2026,32,40,"2026-08-03","08:00:00","2026-10-02","18:00:00","60d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"13.05.2024"]
[null,"DB InfraGO AG","24021-002","Rostock - Berlin","< >","Waren (Müritz)","Waren (Müritz)",2026,2026,32,40,"2026-08-03","08:00:00","2026-10-02","18:00:00","60d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"13.05.2024"]
[null,"DB InfraGO AG","24021-003","Rostock - Berlin","< >","Waren (Müritz)","Waren (Müritz)",2026,2026,32,40,"2026-08-03","08:00:00","2026-10-02","18:00:00","60d, 10h","Continuous","Switch",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"26.06.2024"]
[null,"DB InfraGO AG","24036-006","Rostock - Berlin","< >","Waren (Müritz)","Neustrelitz Hbf",2026,2026,46,50,"2026-11-13","22:00:00","2026-12-11","06:00:00","27d, 8h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"13.05.2024"]
[null,"DB InfraGO AG","23B3D-012","Rostock - Berlin","< >","Waren DB-Gr","Waren (Müritz)",2026,2026,48,48,"2026-11-27","21:00:00","2026-11-28","05:00:00","0d, 8h","Continuous","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"28.05.2024"]
[null,"DB InfraGO AG","24036-004","Rostock - Berlin","< >","Waren DB-Gr","Waren (Müritz)",2026,2026,46,50,"2026-11-13","23:00:00","2026-12-11","05:00:00","27d, 6h","Periodical","Signal","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"19.12.2023"]
[null,"DB InfraGO AG","1D066-001","Wilhelmshaven - Bremen","<","Bremen-Neustadt","Delmenhorst Df",2026,2026,46,48,"2026-11-13","22:10:00","2026-11-25","05:00:00","11d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"26.03.2024"]
[null,"DB InfraGO AG","1D066-004","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Delmenhorst Df",2026,2026,46,48,"2026-11-13","22:10:00","2026-11-25","05:00:00","11d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",,2",null,null,null,"N",null,"19.07.2024"]
[null,"DB InfraGO AG","1D066-007","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Delmenhorst Df",2026,2026,48,50,"2026-11-25","22:10:00","2026-12-11","05:00:00","15d, 6h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"19.12.2023"]
[null,"DB InfraGO AG","1D066-008","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Delmenhorst Df",2026,2026,48,50,"2026-11-25","22:10:00","2026-12-11","05:00:00","15d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,",1,",null,null,null,"N",null,null,"2024-07-30"]
[null,"DB InfraGO AG","1D066-002","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Bremen-Neustadt",2026,2026,46,48,"2026-11-13","22:10:00","2026-11-25","05:00:00","11d, 6h","Periodical","Signal",null,null,null,"P",null,",,",",,",null,",,",null,null,null,"N",null,"25.11.2024"]
[null,"DB InfraGO AG","1D066-005","Wilhelmshaven - Bremen",">","Delmenhorst Df","Bremen-Neustadt",2026,2026,48,50,"2026-11-25","22:10:00","2026-12-11","05:00:00","15d, 6h","Periodical","Signal",null,"LT",null,null,null,",,",",,",null,"4,4,4",null,null,null,"N",null,"28.10.2024"]
[null,"DB InfraGO AG","1D066-003","Wilhelmshaven - Bremen","< >","Delmenhorst Heidkrug","Bremen-Neustadt",2026,2026,46,48,"2026-11-13","22:10:00","2026-11-25","05:00:00","11d, 6h","Periodical","Signal",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"04.06.2024"]
[null,"DB InfraGO AG","1B7E0-001","Wilhelmshaven - Bremen","< >","Kayhauserfeld","Oldenburg (Oldb) Hbf",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","22:00:00","3d, 0h","Continuous","Switch","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"20.01.2025"]
[null,"DB InfraGO AG","1B7E0-002","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldenburg (Oldb) Hbf",2026,2026,46,47,"2026-11-13","22:00:00","2026-11-16","22:00:00","3d, 0h","Continuous","Switch",null,"LT",null,null,null,",,",",,",null,"3,3,3",null,null,null,"N",null,"28.11.2024"]
[null,"DB InfraGO AG","1BA5F-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Bad Zwischenahn",2026,2026,47,48,"2026-11-16","22:00:00","2026-11-27","22:00:00","11d, 0h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"07.05.2024"]
[null,"DB InfraGO AG","1B7E0-003","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,47,50,"2026-11-16","22:00:00","2026-12-12","23:59:00","26d, 1h","Continuous","Switch",null,null,"S",null,null,",,",",,",null,"1,1,1",null,null,null,"N",null,"05.12.2024"]
[null,"DB InfraGO AG","1C282-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,8,42,"2026-02-16","00:00:00","2026-10-18","23:59:00","244d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"22.01.2025"]
[null,"DB InfraGO AG","1C282-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,8,42,"2026-02-16","00:00:00","2026-10-18","23:59:00","244d, 22h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"29.08.2024"]
[null,"DB InfraGO AG","1C27A-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","23:59:00","55d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"01.10.2024"]
[null,"DB InfraGO AG","1C27A-002","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","23:59:00","55d, 0h","Continuous","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"Y",null,"2024-07-10T07:39:21"]
[null,"DB InfraGO AG","1C27A-003","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","04:30:00","54d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:21"]
[null,"DB InfraGO AG","1C27A-005","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","04:30:00","54d, 5h","Periodical","Miscellaneous",null,"ST",null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:21"]
[null,"DB InfraGO AG","1C27A-006","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Oldenburg (Oldb) Hbf",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-12","04:30:00","54d, 5h","Periodical","Miscellaneous",null,null,null,null,"X",",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:22"]
[null,"DB InfraGO AG","1D626-001","Wilhelmshaven - Bremen","< >","Oldenburg (Oldb) Hbf","Kayhauserfeld",2026,2026,49,49,"2026-11-30","07:00:00","2026-12-05","16:00:00","5d, 9h","Continuous","Track & Rail","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:22"]
[null,"DB InfraGO AG","1D35C-002","Wilhelmshaven - Bremen","< >","Wilhelmshaven Ölweiche","Wilhelmshaven Nord",2026,2026,11,36,"2026-03-09","07:00:00","2026-08-31","17:00:00","175d, 9h","Periodical","Catenary","T",null,null,null,null,",,",",,",null,",,",null,null,null,"N",null,"2024-07-10T07:39:26"]
[null,"GySEV",26530,"Sopron - Györ",null,"Csorna","Csorna",2026,2026,35,42,"2026-08-24",null,"2026-10-16",null,"8 weeks","Continuous","Line","T",null,null,null,null,null,null,null,null,null,"sk+55cm platform construction",null,null,null,"2026-02-06"]
[null,"GySEV",26531,"Sopron - Györ",null,"Győr","Csorna",2026,2026,37,39,"2026-09-11",null,"2026-09-22",null,"12 days","Continuous","Line","T",null,null,null,null,null,null,null,null,null,"PFT, VVF maintenance works, works done on other lines, Framebridge insulation at Kóny 215+31, bridge insulation at KO-EN 228+68, replacement of SK 30 platform elements alongside the main rail line going through Ikrény ",null,null,null,"2026-02-06"]
[null,"GySEV",26532,"Sopron - Györ",null,"Csorna","Sopron",2027,2027,14,17,"2027-04-07",null,"2027-04-30",null,"24 days","Continuous","Line","T",null,null,null,null,null,null,null,null,null,"Rail replacement, bush trimming ect.",null,null,null,"2025-12-14"]
[null,"GySEV",26533,"Sopron - Györ",null,"Győr","Csorna",2027,2027,38,39,"2027-09-20",null,"2027-10-02",null,"13 days","Continuous","Line","T",null,null,null,null,null,null,null,null,null,"Rail replacement, railroad crossing maintenance, replacement of missing cobblestone ect.",null,null,null,"2025-12-14"]
[null,"MÁV",5526001159,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,26,37,"2026-06-25","18:00:00","2026-09-11","17:59:00","77d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001171,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,36,36,"2026-08-31","09:00:00","2026-08-31","13:00:00","4h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001172,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,36,36,"2026-09-01","23:30:00","2026-09-02","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001173,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,36,36,"2026-09-02","23:30:00","2026-09-03","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001174,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,36,36,"2026-09-03","23:30:00","2026-09-04","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001175,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,37,37,"2026-09-08","23:30:00","2026-09-09","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001176,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,37,37,"2026-09-09","23:30:00","2026-09-10","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001177,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,37,37,"2026-09-10","23:30:00","2026-09-11","05:30:00","6h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001178,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,37,42,"2026-09-11","18:00:00","2026-10-15","08:00:00","33d14h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001179,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,35,35,"2026-08-30","08:00:00","2026-08-30","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001180,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,38,44,"2026-09-14","08:00:00","2026-10-27","17:59:00","43d9h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001181,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,39,39,"2026-09-27","08:00:00","2026-09-27","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001182,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-19","08:00:00","2026-10-19","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001183,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-20","08:00:00","2026-10-20","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001184,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-21","08:00:00","2026-10-21","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001185,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,43,43,"2026-10-22","08:00:00","2026-10-22","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001186,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,44,"2026-10-26","08:00:00","2026-10-26","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001187,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,44,"2026-10-27","08:00:00","2026-10-27","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001188,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,42,44,"2026-10-15","08:00:00","2026-10-27","17:59:00","12d9h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001189,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,42,42,"2026-10-15","08:00:00","2026-10-15","14:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001190,"Hegyeshalom-Ferencváros",">","Ferencváros ","Ferencváros ",2026,2026,43,43,"2026-10-21","22:00:00","2026-10-22","06:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001191,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,46,"2026-10-27","18:00:00","2026-11-09","17:59:00","12d23h559m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001192,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,44,44,"2026-10-27","18:00:00","2026-10-27",1,"6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001193,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-02","23:30:00","2026-11-03","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001194,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-03","23:30:00","2026-11-04","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001195,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-04","23:30:00","2026-11-05","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001196,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-06","23:30:00","2026-11-07","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001197,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,45,"2026-11-07","23:30:00","2026-11-08","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001198,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,45,46,"2026-11-08","23:30:00","2026-11-09","05:30:00","6h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001199,"Hegyeshalom-Ferencváros",">","Ferencváros ","Kelenföld ",2026,2026,46,46,"2026-11-09","23:30:00","2026-11-10","03:00:00","3h30m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001200,"Hegyeshalom-Ferencváros","< >","Ferencváros ","Kelenföld ",2026,2026,46,46,"2026-11-10","03:00:00","2026-11-10","05:00:00","2h","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001201,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2027,46,35,"2026-11-09","18:00:00","2027-09-05","17:59:00","299d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001202,"Hegyeshalom-Ferencváros",">","Ferencváros","Kelenföld",2026,2026,46,46,"2026-11-11","09:30:00","2026-11-11","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001203,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,46,46,"2026-11-12","09:30:00","2026-11-12","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001204,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,46,46,"2026-11-13","09:30:00","2026-11-13","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001205,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-16","09:30:00","2026-11-16","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001206,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-17","09:30:00","2026-11-17","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001207,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-18","09:30:00","2026-11-18","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001208,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-19","09:30:00","2026-11-19","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001209,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,47,47,"2026-11-20","09:30:00","2026-11-20","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001210,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,48,48,"2026-11-23","09:30:00","2026-11-23","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001211,"Hegyeshalom-Ferencváros",">","Kelenföld","Kelenföld",2026,2026,48,48,"2026-11-24","09:30:00","2026-11-24","16:30:00","7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001212,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,49,49,"2026-12-01","09:00:00","2026-12-01","13:00:00","4h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001213,"Hegyeshalom-Ferencváros","< >","Ferencváros","Kelenföld",2026,2026,49,49,"2026-12-02","09:00:00","2026-12-02","13:00:00","4h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526001214,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,49,49,"2026-12-03","21:30:00","2026-12-04","05:30:00","8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526001215,"Hegyeshalom-Ferencváros",">","Ferencváros","Ferencváros",2026,2026,49,49,"2026-12-04","21:30:00","2026-12-05","05:30:00","8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070015,"Štúrovo - Ferencváros",">","Nagymaros","Szob",2026,2026,33,33,"2026-08-10","09:00:00","2026-08-14","22:00:00","4d13h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5,6,7"]
[null,"MÁV",5526070016,"Štúrovo - Ferencváros",">","Vác","Verőce",2026,2026,35,36,"2026-08-28","22:00:00","2026-08-31","05:00:00","2d7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070017,"Štúrovo - Ferencváros",">","Verőce","Nagymaros",2026,2026,38,39,"2026-09-18","22:00:00","2026-09-21","05:00:00","2d7h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070018,"Štúrovo - Ferencváros",">","Vác","Vác",2026,2026,40,40,"2026-10-03","23:35:00","2026-10-04","05:25:00","5h50m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070019,"Štúrovo - Ferencváros",">","Nagymaros","Szob",2026,2026,42,42,"2026-10-12","09:00:00","2026-10-16","22:00:00","4d13h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526070020,"Štúrovo - Ferencváros",">","Szob","Szob",2026,2026,42,42,"2026-10-13","08:55:00","2026-10-13","14:10:00","5h15m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",5526070021,"Štúrovo - Ferencváros",">","Szob","Szob",2026,2026,42,42,"2026-10-14","08:55:00","2026-10-14","14:10:00","5h15m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",55011150001,"Ferencváros - Kelebia",">","Ferencváros ","Soroksári út",2026,2026,36,37,"2026-09-04","22:00:00","2026-09-07","05:00:00","2d7h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",5526100025,"Ferencváros-Szajol",">","Városligeti elágazás","Kőbánya-Kispest",2026,2026,25,35,"2026-06-20","00:00:00","2026-08-28","23:59:00","69d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100056,"Ferencváros-Szajol",">","Kőbánya-Kispest","Kőbánya-Kispest",2026,2026,45,48,"2026-11-03","00:00:00","2026-11-29","23:59:00","26d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15",null,null,"5,6"]
[null,"MÁV",5526120019,"Ferencváros-Szajol",">","Tápiószele","Tápiószele",2026,2026,40,41,"2026-10-02","22:00:00","2026-10-05","04:00:00","2d6h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120026,"Ferencváros-Szajol",">","Rákoshegy","Maglód",2026,2026,41,42,"2026-10-09","20:40:00","2026-10-12","04:40:00","2d8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101002,"Szajol - Biharkeresztes","< >","Berettyóújfalu","Mezőpeterd",2026,2026,31,32,"2026-07-31","19:00:00","2026-08-03","06:00:00","2d11h","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,7]
[null,"MÁV",5526101003,"Szajol - Biharkeresztes","< >","Püspökladány","Báránd",2026,2026,37,37,"2026-09-07","20:40:00","2026-09-08","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,"2,3"]
[null,"MÁV",5526101004,"Szajol - Biharkeresztes","< >","Báránd ","Sáp",2026,2026,37,37,"2026-09-08","20:40:00","2026-09-09","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,"1,2,3,4,5"]
[null,"MÁV",5526101005,"Szajol - Biharkeresztes","< >","Püspökladány","Báránd",2026,2026,37,37,"2026-09-08","20:40:00","2026-09-09","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101006,"Szajol - Biharkeresztes","< >","Báránd ","Sáp",2026,2026,37,37,"2026-09-09","20:40:00","2026-09-10","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,5]
[null,"MÁV",5526101007,"Szajol - Biharkeresztes","< >","Püspökladány","Báránd",2026,2026,37,37,"2026-09-09","20:40:00","2026-09-10","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15",null,null,2]
[null,"MÁV",5526101008,"Szajol - Biharkeresztes","< >","Sáp ","Berettyóújfalu",2026,2026,37,37,"2026-09-10","20:40:00","2026-09-11","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101009,"Szajol - Biharkeresztes","< >","Sáp ","Berettyóújfalu",2026,2026,37,37,"2026-09-11","20:40:00","2026-09-12","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101010,"Szajol - Biharkeresztes","< >","Sáp ","Berettyóújfalu",2026,2026,38,38,"2026-09-14","20:40:00","2026-09-15","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101011,"Szajol - Biharkeresztes","< >","Berettyóújfalu","Mezőpeterd",2026,2026,38,38,"2026-09-15","20:40:00","2026-09-16","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101012,"Szajol - Biharkeresztes","< >","Mezőpeterd","Biharkeresztes",2026,2026,38,38,"2026-09-16","20:40:00","2026-09-17","04:20:00","7h40m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101013,"Szajol - Biharkeresztes","< >","Biharkeresztes","Biharkeresztes oh.",2026,2026,38,38,"2026-09-17","22:00:00","2026-09-18","04:20:00","6h20m","Continuous","other","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526101014,"Szajol - Biharkeresztes",">","Biharkeresztes  ","Biharkeresztes  ",2026,2026,39,39,"2026-09-21","22:00:00","2026-09-22","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101015,"Szajol - Biharkeresztes",">","Biharkeresztes  ","Biharkeresztes  ",2026,2026,39,39,"2026-09-22","22:00:00","2026-09-23","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101016,"Szajol - Biharkeresztes",">","Biharkeresztes  ","Biharkeresztes  ",2026,2026,39,39,"2026-09-23","22:00:00","2026-09-24","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101017,"Szajol - Biharkeresztes",">","Mezőpeterd ","Mezőpeterd ",2026,2026,39,39,"2026-09-24","22:00:00","2026-09-25","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101018,"Szajol - Biharkeresztes",">","Berettyóújfalu ","Berettyóújfalu ",2026,2026,40,40,"2026-09-28","22:00:00","2026-09-29","04:20:00","6h20m","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101019,"Szajol - Biharkeresztes",">","Sáp ","Sáp ",2026,2026,40,40,"2026-09-30","07:00:00","2026-09-30","13:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526101020,"Szajol - Biharkeresztes",">","Báránd ","Báránd ",2026,2026,40,40,"2026-10-01","07:00:00","2026-10-01","13:00:00","6h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120010,"Szajol-Curtici",">","Szajol","Tiszatenyő",2026,2026,36,39,"2026-08-31","00:00:00","2026-09-25","23:59:00","25d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120011,"Szajol-Curtici",">","Szajol","Tiszatenyő",2026,2026,40,40,"2026-09-28","19:00:00","2026-09-29","02:45:00","7h45m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120012,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,40,40,"2026-09-29","00:30:00","2026-09-29","02:45:00","2h15m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120013,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,40,40,"2026-09-29","03:00:00","2026-09-29","04:50:00","1h50m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120014,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,40,40,"2026-09-29","18:00:00","2026-09-30","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120015,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,40,40,"2026-09-30","18:00:00","2026-10-01","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120016,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,40,40,"2026-10-01","18:00:00","2026-10-02","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120017,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,40,40,"2026-10-02","02:00:00","2026-10-02","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120018,"Szajol-Curtici",">","Szajol","Tiszatenyő",2026,2026,40,40,"2026-10-02","21:05:00","2026-10-03","04:00:00","6h55m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120020,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,41,41,"2026-10-05","18:00:00","2026-10-06","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120021,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,41,41,"2026-10-06","18:00:00","2026-10-07","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120022,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,41,41,"2026-10-07","18:00:00","2026-10-08","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120023,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,41,41,"2026-10-08","02:00:00","2026-10-08","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120024,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,41,41,"2026-10-08","19:00:00","2026-10-09","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120025,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,41,41,"2026-10-09","19:00:00","2026-10-10","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120027,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,42,42,"2026-10-12","19:00:00","2026-10-13","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120028,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,42,42,"2026-10-13","02:00:00","2026-10-13","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120029,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,42,42,"2026-10-13","19:00:00","2026-10-14","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120030,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,42,42,"2026-10-14","19:00:00","2026-10-15","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120031,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,42,42,"2026-10-15","19:00:00","2026-10-16","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120032,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,42,42,"2026-10-16","02:00:00","2026-10-16","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120033,"Szajol-Curtici",">","Gyoma","Csárdaszállás",2026,2026,42,42,"2026-10-16","19:00:00","2026-10-17","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120034,"Szajol-Curtici",">","Gyoma","Csárdaszállás",2026,2026,43,43,"2026-10-19","19:00:00","2026-10-20","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120035,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,43,43,"2026-10-20","02:00:00","2026-10-20","05:00:00","3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120036,"Szajol-Curtici",">","Gyoma","Csárdaszállás",2026,2026,43,43,"2026-10-20","19:00:00","2026-10-21","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120037,"Szajol-Curtici",">","Gyoma","Csárdaszállás",2026,2026,43,43,"2026-10-21","19:00:00","2026-10-22","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120038,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,43,43,"2026-10-22","01:30:00","2026-10-22","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120039,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,43,43,"2026-10-22","01:30:00","2026-10-22","05:00:00","3h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120040,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-26","20:00:00","2026-10-27","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120041,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-27","20:00:00","2026-10-28","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120042,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,44,44,"2026-10-28","01:00:00","2026-10-28","05:00:00","4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120043,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,44,44,"2026-10-28","01:00:00","2026-10-28","05:00:00","4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120044,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-28","20:00:00","2026-10-29","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120045,"Szajol-Curtici",">","Csárdaszállás","Mezőberény",2026,2026,44,44,"2026-10-29","20:00:00","2026-10-30","05:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120046,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,44,44,"2026-10-30","01:00:00","2026-10-30","05:00:00","4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120047,"Szajol-Curtici",">","Mezőberény","Murony",2026,2026,44,44,"2026-10-30","18:00:00","2026-10-31","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120048,"Szajol-Curtici",">","Murony","Murony",2026,2026,44,44,"2026-10-31","02:00:00","2026-10-31","05:00:00","3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120049,"Szajol-Curtici",">","Mezőberény","Murony",2026,2026,45,45,"2026-11-02","18:00:00","2026-11-03","05:00:00","11h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120050,"Szajol-Curtici",">","Murony","Murony",2026,2026,45,45,"2026-11-03","02:00:00","2026-11-03","05:00:00","3h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120051,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-03","19:00:00","2026-11-04","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120052,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-04","19:00:00","2026-11-05","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120053,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,45,45,"2026-11-05","01:00:00","2026-11-05","05:00:00","4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120054,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-05","19:00:00","2026-11-06","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120055,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,45,45,"2026-11-06","19:00:00","2026-11-07","05:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120056,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,45,45,"2026-11-07","01:00:00","2026-11-07","05:00:00","4hh","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120057,"Szajol-Curtici",">","Békéscsaba","Szabadkígyós",2026,2026,45,45,"2026-11-07","03:00:00","2026-11-07","05:00:00","2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120058,"Szajol-Curtici",">","Szajol","Tiszatenyő",2026,2026,46,46,"2026-11-09","21:05:00","2026-11-10","04:00:00","6h55m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120059,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,46,46,"2026-11-10","20:00:00","2026-11-11","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120060,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,46,46,"2026-11-11","20:00:00","2026-11-12","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120061,"Szajol-Curtici",">","Tiszatenyő","Tiszatenyő",2026,2026,46,46,"2026-11-12","20:00:00","2026-11-13","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120062,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,47,47,"2026-11-16","21:20:00","2026-11-17","00:40:00","3h20m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120063,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,47,47,"2026-11-16","23:35:00","2026-11-17","04:00:00","4h25m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120064,"Szajol-Curtici",">","Tiszatenyő","Mezőtúr",2026,2026,47,47,"2026-11-17","01:10:00","2026-11-17","02:30:00","1h20m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120065,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,47,47,"2026-11-17","20:00:00","2026-11-18","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120066,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,47,47,"2026-11-18","20:00:00","2026-11-19","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120067,"Szajol-Curtici",">","Mezőtúr","Mezőtúr",2026,2026,47,47,"2026-11-19","20:00:00","2026-11-20","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120068,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,47,47,"2026-11-20","22:15:00","2026-11-21","02:45:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120069,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,47,47,"2026-11-21","01:15:00","2026-11-21","05:20:00","4h5m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120070,"Szajol-Curtici",">","Mezőtúr","Gyoma",2026,2026,47,47,"2026-11-21","03:10:00","2026-11-21","04:20:00","1h10m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120071,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,48,48,"2026-11-23","20:00:00","2026-11-24","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120072,"Szajol-Curtici",">","Nagylapos forg. kit.","Gyoma",2026,2026,48,48,"2026-11-23","23:00:00","2026-11-24","03:00:00","4h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120073,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,48,48,"2026-11-24","20:00:00","2026-11-25","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120074,"Szajol-Curtici",">","Gyoma","Gyoma",2026,2026,48,48,"2026-11-25","20:00:00","2026-11-26","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120075,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,48,48,"2026-11-26","20:00:00","2026-11-27","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120076,"Szajol-Curtici",">","Csárdaszállás","Csárdaszállás",2026,2026,48,48,"2026-11-27","20:00:00","2026-11-28","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120077,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,49,49,"2026-11-30","20:00:00","2026-12-01","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120078,"Szajol-Curtici",">","Mezőberény","Mezőberény",2026,2026,49,49,"2026-12-01","20:00:00","2026-12-02","01:00:00","5h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120079,"Szajol-Curtici",">","Murony","Murony",2026,2026,49,49,"2026-12-02","01:30:00","2026-12-02","06:00:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120080,"Szajol-Curtici",">","Murony","Murony",2026,2026,49,49,"2026-12-02","20:00:00","2026-12-03","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120081,"Szajol-Curtici",">","Murony","Murony",2026,2026,49,49,"2026-12-03","20:00:00","2026-12-04","04:00:00","8h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120082,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,50,50,"2026-12-07","19:00:00","2026-12-07","23:30:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120083,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,50,50,"2026-12-07","21:00:00","2026-12-08","06:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120084,"Szajol-Curtici",">","Murony","Békéscsaba",2026,2026,50,50,"2026-12-08","19:00:00","2026-12-08","23:30:00","4h30m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120085,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,50,50,"2026-12-08","21:00:00","2026-12-09","06:00:00","9h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120086,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,50,50,"2026-12-09","20:00:00","2026-12-10","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526120087,"Szajol-Curtici",">","Békéscsaba","Békéscsaba",2026,2026,50,50,"2026-12-10","20:00:00","2026-12-11","06:00:00","10h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100032,"Szajol - Biharkeresztes","< >","Rákosrendező","Városliget elágazás",2026,2026,35,35,"2026-08-24","07:00:00","2026-08-28","23:59:00","4d17h59m","Continuous","Track & Rail","T",null,null,null,null,null,null,null,null,null,"Total closure",null,null,null,"2025-12-15"]
[null,"MÁV",5526100034,"Szajol - Biharkeresztes",">","Kőbánya-Kispest","Kőbánya-Kispest",2026,2026,36,40,"2026-09-04","22:00:00","2026-10-02","23:59:00","28d2h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100038,"Szajol - Biharkeresztes",">","Szolnok-Rendező","Szolnok-Rendező",2026,2026,38,39,"2026-09-15","07:00:00","2026-09-21","04:00:00","5d21h","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100041,"Szajol - Biharkeresztes",">","Kőbánya-Kispest","Kőbánya-Kispest",2026,2026,40,45,"2026-10-03","00:00:00","2026-11-02","23:59:00","30d23h59m","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100042,"Szajol - Biharkeresztes",">","Kaba","Kaba",2026,2026,41,41,"2026-10-05","21:00:00","2026-10-06","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100044,"Szajol - Biharkeresztes",">","Kaba","Kaba",2026,2026,41,41,"2026-10-06","21:00:00","2026-10-07","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100046,"Szajol - Biharkeresztes",">","Karcag","Karcag",2026,2026,41,41,"2026-10-07","21:00:00","2026-10-08","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100048,"Szajol - Biharkeresztes",">","Karcag","Karcag",2026,2026,41,41,"2026-10-08","21:00:00","2026-10-09","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100051,"Szajol - Biharkeresztes",">","Kisújszállás","Kisújszállás",2026,2026,42,42,"2026-10-12","21:00:00","2026-10-13","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100053,"Szajol - Biharkeresztes",">","Kisújszállás","Kisújszállás",2026,2026,42,42,"2026-10-13","21:00:00","2026-10-14","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100054,"Szajol - Biharkeresztes",">","Püspökladány","Püspökladány",2026,2026,42,42,"2026-10-14","21:00:00","2026-10-15","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"MÁV",5526100055,"Szajol - Biharkeresztes",">","Püspökladány","Püspökladány",2026,2026,42,42,"2026-10-15","21:00:00","2026-10-16","05:00:00","8h","Continuous","other",null,"LT",null,null,null,null,null,null,null,null,"Single line operation\n(closure of one track of a double track line)",null,null,null,"2025-12-15"]
[null,"SNCF-R",8726175,"Karlsruhe - Strasbourg",null,"Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2026,2026,40,40,"2026-10-04","00:15:00","2026-10-04","05:15:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y",142000,"2024-12-17"]
[null,"SNCF-R",8726163,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Neudorf - Entrée lavage",2026,2026,32,32,"2026-08-03","20:20:00","2026-08-06","04:20:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP578+575+565+722+737+743+752+564+724+738+746+753",null,"Y",142000.14499999999,"2024-12-17"]
[null,"SNCF-R",8726167,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Neudorf - Entrée lavage",2026,2026,33,33,"2026-08-10","22:00:00","2026-08-12","04:00:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP578+575+565+722+737+743+752+564+724+738+746+753",null,"Y",142000.14499999999,"2024-12-17",null,null,"3,4,5"]
[null,"SNCF-R",8726174,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Neudorf - Entrée lavage",2026,2026,32,33,"2026-08-09","22:00:00","2026-08-10","04:00:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP578+575+565+722+737+743+752+564+724+738+746+753",null,"Y",142000.14499999999,"2024-12-17"]
[null,"SNCF-R",8726176,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Bât Voyageurs","Strasbourg-Neudorf - Entrée lavage",2026,2026,31,32,"2026-08-02","20:20:00","2026-08-03","04:20:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"ZEP578+575+565+722+737+743+752+564+724+738+746+753",null,"Y",142000.14499999999,"2024-12-17",null,null,1]
[null,"SNCF-R",8726160,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2025,2026,51,50,"2025-12-15","09:54:00","2026-12-11","11:02:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main courante n°15 SA2023)  SA2024 Main Courante 18 : vibration de + 10 minutes des horaires  SA2026 : Modification des horaires suite à Concertation sur le Système Capacitaire (14/11/2023 XSE",null,"Y",142000,"2024-12-17",null,null,"1,2,3,4,5,6,7"]
[null,"SNCF-R",8726161,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2026,2026,45,45,"2026-11-02","22:40:00","2026-11-07","04:40:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Recommandation de non activation entre avril et octobre Modification de fenêtre : 6h dont 4 de simultanée pour passage trains internationaux      ",null,"Y",142000,"2024-12-17"]
[null,"SNCF-R",8726165,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2026,2026,45,45,"2026-11-03","00:15:00","2026-11-07","06:05:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Création de fenêtres génériques de 6h avec simultanée de 4h pour passage trains internationaux Pk début 2,500                         ",null,"Y",142000,"2024-12-17",null,null,"1,2,3,4,5,6,7"]
[null,"SNCF-R",8726168,"Karlsruhe - Strasbourg",null,"Strasbourg-Ville - Jonction 1","Strasbourg-Port-du-Rhin - Frontière Fr-Al",2025,2026,51,50,"2025-12-15","11:02:00","2026-12-11","11:56:00",null,"Periodical","Miscellanous",null,"LT",null,null,null,null,null,null,null,null,"Vibration des horaires suite à la Main Courante du 17/08/2021 (Main Courante n°16 du SA2023)  SA2025 - Main courante 82 : vibration des horaires de +2 minutes",null,"Y",142000,"2024-12-17"]
[null,"SZCZ","V-003902/24","Brno - Břeclav","< >","Brno hl.n.","Odb Brno-Židenice z",2026,2026,48,49,"2026-11-28","00:00:00","2026-11-30","23:59:00","3 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3"]
[null,"SZCZ","V-016312/23","Brno - Břeclav","< >","Brno jih","Brno jih",2026,2026,38,42,"2026-09-14","00:00:00","2026-10-13","23:59:00","30 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"108a bez TV, 104.,106.,108.,110a jen TV, 110b,110c + TV. ",null,null,null,"2024-12-17",null,null,"1,2,5,6,7"]
[null,"SZCZ","V-016313/23","Brno - Břeclav","< >","Brno-Horní Heršpice","Brno-Horní Heršpice",2026,2026,27,33,"2026-07-01","00:00:00","2026-08-14","23:59:00","45 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null,null,null,null,"5.,707.,709.,709b,711.,713.,717. bez TV, 3.,3a,3b,5.,7.,9.,90.,603.,707.,709. jen TV. ",null,null,null,"2024-12-17",null,null,"1,2,3,5,6,7"]
[null,"SZCZ","V-015894/23","Brno - Břeclav","< >","Odb B.-Čern.zhl.Táb.","Odb Brno-Židenice z",2026,2026,47,47,"2026-11-21","00:00:00","2026-11-22","23:59:00","2 x 12 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003903/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb Brno-Židenice z",2026,2026,11,47,"2026-03-10","00:00:00","2026-11-20","23:59:00","256 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 1. TK směr Odb Brno-Černovice zhl. Táborská od hrotu výh. č. 2 po nám. výh. č.6b, od nám. výh. č. 3 po nám. výh. č. 8 a 13\n\nzhlaví 2. TK směr Odb Brno-Černovice zhl. Táborská od hrotu výh. č. 4 po výh. č. 7 (mimo).",null,null,null,"2024-12-17",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-003899/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Brno-Maloměřice",2026,2026,47,48,"2026-11-21","00:00:00","2026-11-23","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,null,null,null,null,"2024-12-17"]
[null,"SZCZ","V-003898/24","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb Brno-Židenice z",2026,2026,10,49,"2026-03-07","00:00:00","2026-12-04","23:59:00","273 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"záhlaví 1. TK směr Odb Brno-Černovice zhl. Táborská",null,null,null,"2024-12-17"]
[null,"SZCZ","V-015893/23","Brno - Břeclav","< >","Odb Brno-Židenice z","Odb B.-Čern.zhl.Táb.",2026,2026,9,49,"2026-02-28","00:00:00","2026-12-04","23:59:00","280 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-016322/23","Česká Třebová - Brno","< >","Blansko","Rájec-Jestřebí",2026,2026,45,46,"2026-11-06","00:00:00","2026-11-10","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006247/24","Česká Třebová - Brno","< >","Česká Třebová","Opatov",2026,2026,49,49,"2026-11-30","00:00:00","2026-12-04","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006246/24","Česká Třebová - Brno","< >","Česká Třebová","Odb Zádulka",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006260/24","Česká Třebová - Brno","< >","Odb Les","Odb Zádulka",2026,2026,49,53,"2026-12-05","00:00:00","2026-12-31","23:59:00","27 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-006249/24","Česká Třebová - Brno","< >","Odb Zádulka","Č.Třebová vjezd.sk.",2026,2026,16,47,"2026-04-14","00:00:00","2026-11-22","23:59:00","223 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003674/24","Česká Třebová - Brno","< >","Rájec-Jestřebí","Skalice nad Svitavou",2026,2026,42,43,"2026-10-16","00:00:00","2026-10-21","23:59:00","6 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016321/23","Česká Třebová - Brno","< >","Rájec-Jestřebí","Blansko",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003673/24","Česká Třebová - Brno","< >","Skalice nad Svitavou","Rájec-Jestřebí",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-16","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17",null,null,"3,4,5,6"]
[null,"SZCZ","V-006247/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Zádulka",2026,2026,49,49,"2026-11-30","00:00:00","2026-12-04","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006247/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Zádulka",2026,2026,49,49,"2026-11-30","00:00:00","2026-12-04","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-17",null,null,"1,4,5,6,7"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,48,51,"2026-11-28","00:00:00","2026-12-14","23:59:00","17 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005250/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,32,32,"2026-08-05","00:00:00","2026-08-06","23:59:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005252/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,43,43,"2026-10-19","00:00:00","2026-10-21","23:59:00","3 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005255/24","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2026,2026,45,45,"2026-11-03","00:00:00","2026-11-08","23:59:00","6 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005269/24","Chocen - Hranice na Morave","< >","Drahotuše","Odb Jezernice A",2026,2026,46,46,"2026-11-11","00:00:00","2026-11-15","23:59:00","10 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-004092/24","Chocen - Hranice na Morave","< >","Hoštejn z","Hoštejn z",2026,2026,38,39,"2026-09-14","00:00:00","2026-09-23","23:59:00","10 days","Continuous","Signal",null,"ST",null,null,null,null,null,null,null,null,"zab. zař. staniční.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018472/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,46,48,"2026-11-10","00:00:00","2026-11-27","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,26,46,"2026-06-26","00:00:00","2026-11-09","23:59:00","137 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,35,38,"2026-08-30","00:00:00","2026-09-16","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,28,49,"2026-07-10","00:00:00","2026-12-03","23:59:00","147 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-005274/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Odb Jezernice A",2026,2026,49,50,"2026-12-01","00:00:00","2026-12-08","23:59:00","16 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-015331/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Prosenice",2027,2027,19,22,"2027-05-14","00:00:00","2027-05-31","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006246/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006246/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-015330/24","Chocen - Hranice na Morave","< >","Prosenice","Lipník nad Bečvou",2027,2027,17,19,"2027-04-26","00:00:00","2027-05-13","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003980/23","Chocen - Hranice na Morave","< >","Studénka","Studénka",2026,2026,31,36,"2026-08-01","00:00:00","2026-08-31","23:59:00","31 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"2,4 jen TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-003657/23","Chocen - Hranice na Morave","< >","Studénka","Studénka",2026,2026,31,49,"2026-08-01","00:00:00","2026-11-30","23:59:00","122 days","Continuous","Bridge",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. \nzhlaví jistebnické.",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006243/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Č.Třebová vjezd.sk.",2026,2026,16,47,"2026-04-14","00:00:00","2026-11-22","23:59:00","223 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2024-12-17"]
[null,"SZCZ","V-006243/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Č.Třebová vjezd.sk.",2026,2026,16,47,"2026-04-14","00:00:00","2026-11-22","23:59:00","223 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2023-11-23"]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2023-11-23"]
[null,"SZCZ","V-017126/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Odb Les",2027,2027,22,49,"2027-06-03","00:00:00","2027-12-11","23:59:00","192 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"200 + TV. ",null,null,null,"2023-11-23"]
[null,"SZCZ","V-007567/23","Děčín - Kolín","< >","Dřísy","Všetaty",2026,2026,33,33,"2026-08-10","00:00:00","2026-08-15","23:59:00","6 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2023-11-22","2025-01-29"]
[null,"SZCZ","V-018467/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-04","2025-01-29"]
[null,"SZCZ","V-018463/22","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-04","2025-01-29"]
[null,"SZCZ","V-006609/24","Děčín - Kolín","< >","Libice nad Cidlinou","Velký Osek",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-20","2025-01-29"]
[null,"SZCZ","V-018491/22","Děčín - Kolín","< >","Nymburk hl.n.","Velký Osek",2026,2026,47,47,"2026-11-18","00:00:00","2026-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015888/23","Děčín - Kolín","< >","Polepy","Hoštka",2026,2026,32,34,"2026-08-03","00:00:00","2026-08-22","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-010088/19","Děčín - Kolín","< >","Velké Březno","Boletice nad Labem",2026,2026,38,41,"2026-09-17","00:00:00","2026-10-06","23:59:00","20 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018478/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018465/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-018453/22","Děčín - Kolín","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013311/24","Hranice na Morave - Ostrava","< >","Ostrava-Svinov","Ostrava-Svinov",2027,2027,9,26,"2027-03-01","00:00:00","2027-06-30","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"3,5,5b,7,9,11 jen TV, 5a + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013538/24","Hranice na Morave - Ostrava","< >","Ostrava-Svinov","Ostrava-Svinov",2027,2027,41,52,"2027-10-13","00:00:00","2027-12-31","23:59:00","80 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"1 jen TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013529/24","Hranice na Morave - Ostrava","< >","Ostrava-Svinov","Ostrava-Svinov",2027,2027,32,52,"2027-08-12","00:00:00","2027-12-31","23:59:00","142 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"3,5,5a,7,9,11 jen TV, 5b + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013385/24","Hranice na Morave - Ostrava","< >","Ostrava-Svinov","Ostrava-Svinov",2027,2027,26,29,"2027-07-01","00:00:00","2027-07-21","23:59:00","21 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"1,3,5,5b,7,9,11 jen TV, 5a + TV. \nzhlaví od nám. výh. 18 po nám. výh. 23 a nám. výh. 24.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016885/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,48,49,"2027-12-05","18:00:00","2027-12-07","06:00:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016599/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,43,46,"2027-10-27","00:00:00","2027-11-16","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015925/24","Hranice na Morave - Ostrava","< >","Studénka","Suchdol nad Odrou",2027,2027,14,16,"2027-04-08","00:00:00","2027-04-25","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007198/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,43,48,"2026-10-20","18:00:00","2026-11-27","06:00:00","38 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,"X",null,null,null,null,null,"1,2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007192/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,30,33,"2026-07-26","18:00:00","2026-08-10","06:00:00","15 x 3 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016654/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,45,45,"2027-11-12","18:00:00","2027-11-14","06:00:00","2 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016624/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,39,43,"2027-09-27","18:00:00","2027-10-27","06:00:00","30 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2,1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016601/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,13,16,"2027-04-02","18:00:00","2027-04-25","06:00:00","23 x 4 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"2,1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015924/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Studénka",2027,2027,11,14,"2027-03-21","00:00:00","2027-04-07","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-002761/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,9,50,"2026-03-01","00:00:00","2026-12-12","23:59:00","287 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-001315/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,1,50,"2026-01-01","00:00:00","2026-12-11","23:59:00","345 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-001807/22","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Vsetín-Bečva",2026,2026,8,50,"2026-02-16","00:00:00","2026-12-12","23:59:00","300 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013938/24","Hranice na Morave - Zilina","< >","Hranice na M. město","Hranice na Moravě",2027,2027,17,17,"2027-04-27","00:00:00","2027-05-01","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013853/24","Hranice na Morave - Zilina","< >","Hranice na M. město","Hranice na Moravě",2027,2027,10,11,"2027-03-08","00:00:00","2027-03-21","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013937/24","Hranice na Morave - Zilina","< >","Hranice na Moravě","Hranice na M. město",2027,2027,14,16,"2027-04-10","00:00:00","2027-04-25","23:59:00","16 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-012359/24","Kolín - Brno-Maloměřice","< >","Golčův Jeníkov","Vlkaneč",2026,2026,27,32,"2026-07-01","00:00:00","2026-08-05","23:59:00","36 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. \nzab. zař. TZZ v 1.TK.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016660/23","Kolín - Brno-Maloměřice","< >","Kolín","Kutná Hora hl.n.",2026,2026,28,43,"2026-07-11","00:00:00","2026-10-19","23:59:00","101 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005102/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,49,51,"2026-12-05","00:00:00","2026-12-18","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ 2.,1. TK.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005065/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,31,33,"2026-08-01","18:00:00","2026-08-11","06:00:00","9 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005074/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,36,37,"2026-09-01","18:00:00","2026-09-13","06:00:00","12 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015961/23","Kolín - Brno-Maloměřice","< >","Pohled","Přibyslav",2026,2026,40,42,"2026-10-01","18:00:00","2026-10-18","06:00:00","17 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-003947/24","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,49,49,"2026-12-02","00:00:00","2026-12-03","23:59:00","2 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. \nzáhlaví a zhlaví 1. TK směr Přibyslav.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016016/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,48,"2026-08-15","00:00:00","2026-11-23","23:59:00","101 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"zhlaví 2. TK směr Havl. Brod, jeho část.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016015/23","Kolín - Brno-Maloměřice","< >","Pohled","Havlíčkův Brod",2026,2026,31,33,"2026-08-01","00:00:00","2026-08-14","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-016007/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,33,33,"2026-08-11","18:00:00","2026-08-15","06:00:00","4 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015982/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,48,49,"2026-11-24","00:00:00","2026-11-30","23:59:00","7 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"lichá jen TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-015981/23","Kolín - Brno-Maloměřice","< >","Pohled","Pohled",2026,2026,31,48,"2026-08-01","00:00:00","2026-11-23","23:59:00","115 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"sudá + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005087/23","Kolín - Brno-Maloměřice","< >","Přibyslav","Pohled",2026,2026,9,46,"2026-03-01","00:00:00","2026-11-14","23:59:00","259 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-012360/24","Kolín - Brno-Maloměřice","< >","Vlkaneč","Golčův Jeníkov",2026,2026,32,37,"2026-08-06","00:00:00","2026-09-10","23:59:00","36 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. \nzab. zař. TZZ v 2.TK.",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007171/24","Nürnberg - Plzen","< >","Cheb","Schirnding",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-007171/24","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005474/24","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005475/24","Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2026,2026,46,46,"2026-11-09","00:00:00","2026-11-13","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005154/24","Ostrava - Zilina","< >","Albrechtice u Č.T.","Havířov",2026,2026,36,37,"2026-09-04","00:00:00","2026-09-10","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-005158/24","Ostrava - Zilina","< >","Havířov","Albrechtice u Č.T.",2026,2026,37,38,"2026-09-11","00:00:00","2026-09-17","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-004047/23","Ostrava - Zilina","< >","Ostrava-Bartovice","Ostrava-Kunčice",2027,2027,38,39,"2027-09-21","00:00:00","2027-09-30","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-004050/23","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Bartovice",2027,2027,39,40,"2027-10-01","00:00:00","2027-10-10","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2024-12-27"]
[null,"SZCZ","V-013900/22","Plzen - Praha","< >","Odb Tunel","Praha-Radotín",2026,2026,32,42,"2026-08-09","00:00:00","2026-10-17","23:59:00","70 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. "]
[null,"SZCZ","V-010376/21","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2026,2026,30,32,"2026-07-20","00:00:00","2026-08-08","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1.,3. + TV. "]
[null,"SZCZ","V-010367/21","Plzen - Praha","< >","Praha-Radotín","Praha-Smíchov",2026,2026,42,43,"2026-10-18","00:00:00","2026-10-22","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Praha-Radotín",2026,2026,43,44,"2026-10-23","00:00:00","2026-10-27","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Praha-Radotín",2026,2026,43,44,"2026-10-23","00:00:00","2026-10-27","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-017131/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2027,2027,39,40,"2027-09-27","00:00:00","2027-10-10","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2024-01-05"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,9,48,"2027-03-01","00:00:00","2027-12-03","23:59:00","278 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006240/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,14,53,"2026-04-01","00:00:00","2026-12-31","23:59:00","275 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"25 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006238/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2026,2026,8,53,"2026-02-22","00:00:00","2026-12-31","23:59:00","313 days","Continuous","Miscellaneous",null,"ST",null,null,null,null,null,null,null,null,"17 bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,32,33,"2026-08-03","00:00:00","2026-08-12","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-003401/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2026,2026,34,35,"2026-08-17","00:00:00","2026-08-26","23:59:00","10 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2027,2027,11,28,"2027-03-16","00:00:00","2027-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L.."]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Předměřice nad Labem",2027,2027,9,11,"2027-03-01","00:00:00","2027-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ."]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,10,12,"2027-03-08","00:00:00","2027-03-24","23:59:00","17 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-002786/24","Praha - Chocen - Česká Třebová","< >","Kostěnice","Kostěnice",2026,2026,43,43,"2026-10-19","00:00:00","2026-10-23","23:59:00","5 days","Continuous","Track & Rail",null,"ST",null,null,null,null,null,null,null,null,"5.,7. jen TV. "]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,42,44,"2026-10-17","00:00:00","2026-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018463/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-06","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-006609/24","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2026,2026,36,37,"2026-09-01","00:00:00","2026-09-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","5 x 4 hours","Periodical","Catenary","T","LT",null,null,null,null,null,null,null,null,"1.,2. + TV. "]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,41,43,"2027-10-17","00:00:00","2027-10-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. "]
[null,"SZCZ","V-012789/21","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Pardubice-Ros.n.Lab.",2026,2026,48,50,"2026-11-28","00:00:00","2026-12-09","23:59:00","12 days","Continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,"zab. zař. TZZ."]
[null,"SZCZ","V-017141/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2027,2027,34,35,"2027-08-26","00:00:00","2027-08-31","23:59:00","6 x 5 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. "]
[null,"SZCZ","V-016925/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,3,53,"2026-01-14","00:00:00","2026-12-31","23:59:00","352 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. "]
[null,"SZCZ","V-006263/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Choceň",2026,2026,41,41,"2026-10-05","00:00:00","2026-10-10","23:59:00","6 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. "]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,53,52,"2027-01-01","00:00:00","2027-12-31","23:59:00","365 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. "]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2027,2027,48,52,"2027-12-01","00:00:00","2027-12-31","23:59:00","31 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. "]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,19,19,"2027-05-13","00:00:00","2027-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. "]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2027,2027,18,19,"2027-05-07","00:00:00","2027-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice."]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,45,46,"2026-11-02","00:00:00","2026-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-018465/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,41,41,"2026-10-07","00:00:00","2026-10-08","23:59:00","2 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2026,2026,38,39,"2026-09-16","00:00:00","2026-09-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-018491/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Nymburk hl.n.",2027,2027,46,47,"2027-11-18","00:00:00","2027-11-22","23:59:00","15 x 4 hours","Periodical","Catenary","T","LT"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,44,45,"2027-11-02","00:00:00","2027-11-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. "]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,41,52,"2026-10-07","00:00:00","2026-12-22","23:59:00","77 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,34,42,"2026-08-17","00:00:00","2026-10-18","23:59:00","63 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,43,50,"2026-10-19","00:00:00","2026-12-13","23:59:00","56 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. "]
[null,"SZCZ","V-019018/21","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,8,33,"2026-02-16","00:00:00","2026-08-16","23:59:00","182 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-014555/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,50,50,"2026-12-07","00:00:00","2026-12-13","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-014554/24","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,42,42,"2026-10-12","00:00:00","2026-10-18","23:59:00","7 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018473/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,35,39,"2026-08-27","00:00:00","2026-09-21","23:59:00","26 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-018471/23","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2026,2026,28,49,"2026-07-10","00:00:00","2026-12-03","23:59:00","147 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-015712/24","Chocen - Hranice na Morave","< >","Dlouhá Třebová","Ústí nad Orlicí",2026,2026,30,33,"2026-07-22","00:00:00","2026-08-10","23:59:00","20 days","Continuous","Bridge",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-007206/25","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2026,2026,33,33,"2026-08-10","00:00:00","2026-08-15","23:59:00","6 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-007200/25","Chocen - Hranice na Morave","< >","Česká Třebová","Třebovice v Čechách",2026,2026,32,32,"2026-08-03","00:00:00","2026-08-08","23:59:00","6 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006247/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Zádulka",2026,2026,49,50,"2026-11-30","00:00:00","2026-12-12","23:59:00","13 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2024-01-05"]
[null,"SZCZ","V-006246/24","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2026,2026,48,48,"2026-11-25","00:00:00","2026-11-29","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. "]
[null,"SZCZ","V-006243/24","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Č.Třebová vjezd.sk.",2026,2026,16,48,"2026-04-14","00:00:00","2026-11-23","23:59:00","224 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. "]
[null,"SZCZ","V-017488/25","Chocen - Hranice na Morave","< >","Odb Parník","Č.Třebová náv. NS",2027,2027,35,38,"2027-09-01","00:00:00","2027-09-26","23:59:00","26 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. "]
[null,"SZCZ","V-017487/25","Chocen - Hranice na Morave","< >","Č.Třebová odj.sk.","Odb Parník",2027,2027,28,35,"2027-07-16","00:00:00","2027-08-31","23:59:00","47 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. "]
[null,"SZCZ","V-017129/24","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2027,2027,49,52,"2027-12-12","00:00:00","2027-12-31","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. "]
[null,"SZCZ","V-017126/24","Chocen - Hranice na Morave","< >","Odb Les","Třebovice v Čechách",2027,2027,22,49,"2027-06-03","00:00:00","2027-12-11","23:59:00","192 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3 + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016601/25","Chocen - Hranice na Morave","< >","Odb Jezernice B","Lipník nad Bečvou",2027,2027,20,22,"2027-05-22","00:00:00","2027-05-31","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016599/25","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Odb Jezernice B",2027,2027,14,15,"2027-04-06","00:00:00","2027-04-15","23:59:00","10 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-015486/25","Chocen - Hranice na Morave","< >","Svitavy","Česká Třebová",2027,2027,26,35,"2027-07-01","00:00:00","2027-08-31","23:59:00","62 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,null,null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-015331/24","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Prosenice",2027,2027,18,20,"2027-05-04","00:00:00","2027-05-21","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-015330/24","Chocen - Hranice na Morave","< >","Prosenice","Lipník nad Bečvou",2027,2027,15,18,"2027-04-16","00:00:00","2027-05-03","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-006005/25","Chocen - Hranice na Morave","< >","Drahotuše","Lipník nad Bečvou",2027,2027,9,10,"2027-03-06","00:00:00","2027-03-10","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-006004/25","Chocen - Hranice na Morave","< >","Lipník nad Bečvou","Drahotuše",2027,2027,9,9,"2027-03-01","00:00:00","2027-03-05","23:59:00","5 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-017493/25","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Č.Třebová vjezd.sk.",2028,2028,49,52,"2028-12-10","00:00:00","2028-12-31","23:59:00","22 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4 + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017492/25","Chocen - Hranice na Morave","< >","Třebovice v Čechách","Česká Třebová",2028,2028,1,49,"2028-01-01","00:00:00","2028-12-09","23:59:00","344 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017492/25","Chocen - Hranice na Morave","< >","Odb Zádulka","Česká Třebová",2028,2028,1,49,"2028-01-01","00:00:00","2028-12-09","23:59:00","344 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017492/25","Chocen - Hranice na Morave","< >","Česká Třebová","Odb Parník",2028,2028,1,49,"2028-01-01","00:00:00","2028-12-09","23:59:00","344 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2,1 + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-016146/25","Chocen - Hranice na Morave","< >","Prosenice","Přerov os.n.",2028,2028,18,22,"2028-05-01","00:00:00","2028-05-30","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-016146/25","Chocen - Hranice na Morave","< >","Prosenice","Výh Dluhonice",2028,2028,18,22,"2028-05-01","00:00:00","2028-05-30","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1S + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-016144/25","Chocen - Hranice na Morave","< >","Přerov os.n.","Prosenice",2028,2028,13,17,"2028-04-01","00:00:00","2028-04-30","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016144/25","Chocen - Hranice na Morave","< >","Výh Dluhonice","Prosenice",2028,2028,13,17,"2028-04-01","00:00:00","2028-04-30","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2S + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-013562/24","Chocen - Hranice na Morave","< >","Hranice na Moravě","Drahotuše",2028,2028,46,52,"2028-11-16","00:00:00","2028-12-31","23:59:00","46 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"4. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-007198/20","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2026,2026,43,48,"2026-10-20","18:00:00","2026-11-27","06:00:00","38 x 6 hours","periodical","Miscellaneous","T","LT",null,null,"X",null,null,null,null,null,"1,2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-016808/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,17,27,"2027-04-26","00:00:00","2027-07-11","23:59:00","77 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"1,2,6,7"]
[null,"SZCZ","V-016733/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,28,37,"2027-07-12","00:00:00","2027-09-17","23:59:00","68 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-016801/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,38,38,"2027-09-20","00:00:00","2027-09-26","23:59:00","7 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-016656/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,28,38,"2027-07-12","00:00:00","2027-09-26","23:59:00","77 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-016600/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2027,2027,46,49,"2027-11-17","00:00:00","2027-12-07","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016599/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2027,2027,43,46,"2027-10-27","00:00:00","2027-11-16","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-015925/24","Hranice na Morave - Ostrava","< >","Studénka","Suchdol nad Odrou",2027,2027,11,13,"2027-03-16","00:00:00","2027-04-02","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-015924/24","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Studénka",2027,2027,8,11,"2027-02-26","00:00:00","2027-03-15","23:59:00","18 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-017480/25","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2028,2028,16,24,"2028-04-22","00:00:00","2028-06-12","23:59:00","52 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-017479/25","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2028,2028,9,16,"2028-03-01","00:00:00","2028-04-21","23:59:00","52 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-016903/25","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2028,2028,9,10,"2028-03-01","00:00:00","2028-03-07","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-016598/24","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2028,2028,40,42,"2028-10-04","00:00:00","2028-10-19","23:59:00","16 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-016191/25","Hranice na Morave - Ostrava","< >","Suchdol nad Odrou","Polom",2028,2028,25,40,"2028-06-21","00:00:00","2028-10-03","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-016190/25","Hranice na Morave - Ostrava","< >","Polom","Suchdol nad Odrou",2028,2028,10,25,"2028-03-08","00:00:00","2028-06-20","23:59:00","105 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-013651/24","Hranice na Morave - Zilina","< >","Hranice na Moravě","Odb Skalka",2026,2026,46,46,"2026-11-09","00:00:00","2026-11-13","23:59:00","10 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-013646/24","Hranice na Morave - Zilina","< >","Hranice na Moravě","Odb Skalka",2026,2026,45,45,"2026-11-04","00:00:00","2026-11-08","23:59:00","10 x 8 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002761/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,9,50,"2026-03-01","00:00:00","2026-12-12","23:59:00","287 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-001807/22","Hranice na Morave - Zilina","< >","Horní Lideč st.hr.","Vsetín-Bečva",2026,2026,8,50,"2026-02-16","00:00:00","2026-12-12","23:59:00","300 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-001315/24","Hranice na Morave - Zilina","< >","Horní Lideč","Valašská Polanka",2026,2026,1,50,"2026-01-01","00:00:00","2026-12-11","23:59:00","345 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016012/25","Hranice na Morave - Zilina","< >","Jablůnka","Valašské Meziříčí",2027,2027,20,20,"2027-05-17","00:00:00","2027-05-21","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016011/25","Hranice na Morave - Zilina","< >","Vsetín","Jablůnka",2027,2027,35,37,"2027-09-02","00:00:00","2027-09-16","23:59:00","15 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-016136/25","Hranice na Morave - Zilina","< >","Hustopeče nad Bečvou","Hranice na Moravě",2028,2028,40,44,"2028-10-02","00:00:00","2028-10-31","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"2,3,4"]
[null,"SZCZ","V-016135/25","Hranice na Morave - Zilina","< >","Hranice na Moravě","Hustopeče nad Bečvou",2028,2028,35,39,"2028-09-02","00:00:00","2028-10-01","23:59:00","30 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:58",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-004949/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,47,50,"2026-11-16","00:00:00","2026-12-11","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,7"]
[null,"SZCZ","V-005474/24","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2026,2026,45,45,"2026-11-02","00:00:00","2026-11-06","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005475/24","Nürnberg - Plzen","< >","Dolní Žandov","Lipová u Chebu",2026,2026,46,46,"2026-11-09","00:00:00","2026-11-13","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005006/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2026,2026,12,49,"2026-03-16","00:00:00","2026-11-30","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,7"]
[null,"SZCZ","V-005011/25","Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2026,2026,11,49,"2026-03-09","00:00:00","2026-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"3,4,5,6"]
[null,"SZCZ","V-005016/25","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2026,2026,48,49,"2026-11-24","00:00:00","2026-12-03","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,6,7"]
[null,"SZCZ","V-005044/25","Nürnberg - Plzen","< >","Cheb","Lipová u Chebu",2027,2027,9,48,"2027-03-01","00:00:00","2027-11-30","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"3,4,5"]
[null,"SZCZ","V-005049/25","Nürnberg - Plzen","< >","Lipová u Chebu","Cheb",2027,2027,8,48,"2027-02-24","00:00:00","2027-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,7"]
[null,"SZCZ","V-005034/25","Nürnberg - Plzen","< >","Mariánské Lázně","Lipová u Chebu",2027,2027,47,48,"2027-11-26","00:00:00","2027-12-05","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,5,6,7"]
[null,"SZCZ","V-004916/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2027,2027,6,7,"2027-02-12","00:00:00","2027-02-21","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-004926/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2027,2027,46,47,"2027-11-15","00:00:00","2027-11-24","23:59:00","10 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-004938/25","Nürnberg - Plzen","< >","Cheb","Cheb st.hr.",2028,2028,10,10,"2028-03-06","00:00:00","2028-03-10","23:59:00","5 x 8 hours","Periodical","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-017451/25","Ostrava - Zilina","< >","Český Těšín","Albrechtice u Č.T.",2027,2027,20,20,"2027-05-17","00:00:00","2027-05-21","23:59:00","5 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-017449/25","Ostrava - Zilina","< >","Albrechtice u Č.T.","Český Těšín",2027,2027,19,19,"2027-05-10","00:00:00","2027-05-16","23:59:00","7 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"2,3,4,5,6"]
[null,"SZCZ","V-006535/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,30,50,"2027-07-28","00:00:00","2027-12-17","23:59:00","143 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1a bez TV. ",null,null,null,"2025-12-09T10:06:31",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006209/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,35,49,"2027-09-01","00:00:00","2027-12-11","23:59:00","102 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-006205/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,36,38,"2027-09-08","00:00:00","2027-09-21","23:59:00","14 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-005999/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Vratimov",2027,2027,38,49,"2027-09-22","00:00:00","2027-12-11","23:59:00","81 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 bez TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-004050/23","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Bartovice",2027,2027,39,40,"2027-10-01","00:00:00","2027-10-10","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-004047/23","Ostrava - Zilina","< >","Ostrava-Bartovice","Ostrava-Kunčice",2027,2027,38,39,"2027-09-21","00:00:00","2027-09-30","23:59:00","10 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006110/25","Ostrava - Zilina","< >","Ostrava střed","Ostrava-Kunčice",2028,2028,40,41,"2028-10-08","00:00:00","2028-10-14","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006109/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava střed",2028,2028,39,40,"2028-10-01","00:00:00","2028-10-07","23:59:00","7 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006087/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Bartovice",2028,2028,41,44,"2028-10-15","00:00:00","2028-11-04","23:59:00","21 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"2,3,4"]
[null,"SZCZ","V-006031/25","Ostrava - Zilina","< >","Ostrava-Kunčice","Ostrava-Vítkovice",2028,2028,28,30,"2028-07-15","00:00:00","2028-07-28","23:59:00","14 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006065/25","Ostrava - Zilina","< >","Ostrava-Vítkovice","Odb Odra",2028,2028,34,36,"2028-08-21","00:00:00","2028-09-09","23:59:00","20 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006017/25","Ostrava - Zilina","< >","Ostrava-Vítkovice","Ostrava-Kunčice",2028,2028,26,28,"2028-07-01","00:00:00","2028-07-14","23:59:00","14 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:22"]
[null,"SZCZ","V-006045/25","Ostrava - Zilina","< >","Odb Odra","Ostrava-Vítkovice",2028,2028,31,33,"2028-08-01","00:00:00","2028-08-20","23:59:00","20 x 10 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1 + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"3,4,5,6,7"]
[null,"SZCZ","V-004051/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,32,33,"2026-08-07","00:00:00","2026-08-11","23:59:00","5 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5"]
[null,"SZCZ","V-004056/25","Ostrava - Zilina","< >","Bohumín os.n.","Bohumín os.n.",2026,2026,34,35,"2026-08-22","00:00:00","2026-08-26","23:59:00","5 x 8 hours","Periodical","Others",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1.,3.,2. bez TV, celá jen TV. \nzhlaví ze směru Ostrava od nám. výh.52 po náv.L2, od nám. výh.50 po náv.L1, L3.",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003680/25","Ostrava - Zilina","< >","Karviná hl.n.","Odb Karviná-Darkov z",2026,2026,41,42,"2026-10-11","00:00:00","2026-10-13","23:59:00","6 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"1,2,3,6,7"]
[null,"SZCZ","V-003664/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2026,2026,41,41,"2026-10-08","00:00:00","2026-10-10","23:59:00","3 x 10 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"0., 2. + TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"2,3,4,5"]
[null,"SZCZ","V-003641/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2026,2026,1,39,"2026-01-01","00:00:00","2026-09-21","23:59:00","264 days","Continuous","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"2,3,4,5"]
[null,"SZCZ","V-018608/25","Ostrava - Zilina","< >","Louky nad Olší","Odb Karviná-Darkov z",2027,2027,38,52,"2027-09-21","00:00:00","2027-12-31","23:59:00","102 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,7"]
[null,"SZCZ","V-017216/25","Ostrava - Zilina","< >","Odb Karviná-Darkov z","Louky nad Olší",2027,2027,53,38,"2027-01-01","00:00:00","2027-09-21","23:59:00","264 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-017218/25","Ostrava - Zilina","< >","Odb Karviná-Darkov z","Louky nad Olší",2028,2028,1,38,"2028-01-01","00:00:00","2028-09-19","23:59:00","263 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. bez TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,7"]
[null,"SZCZ","V-020685/19","Plzen - Praha","< >","Praha-Smíchov","Odb Závodiště",2026,2026,34,43,"2026-08-19","00:00:00","2026-10-19","23:59:00","62 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:05:00",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016905/24","Plzen - Praha","< >","Zdice","Lochovice",2026,2026,46,48,"2026-11-15","00:00:00","2026-11-28","23:59:00","14 days","Continuous","Signal","T","LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. ZZ.",null,null,null,"2025-12-09T10:06:31",null,null,"1,6,7"]
[null,"SZCZ","V-008711/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,45,45,"2026-11-03","00:00:00","2026-11-05","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006278/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,45,46,"2026-11-06","18:00:00","2026-11-12","06:00:00","6 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006665/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2026,2026,49,51,"2026-11-30","18:00:00","2026-12-15","06:00:00","15 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006679/25","Plzen - Praha","< >","Praha-Radotín","Odb Tunel",2026,2026,49,51,"2026-12-01","18:00:00","2026-12-15","06:00:00","14 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"3. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-007122/25","Plzen - Praha","< >","Praha-Smíchov","P.-Velká Chuchle z",2026,2026,43,46,"2026-10-20","00:00:00","2026-11-11","23:59:00","23 days","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006241/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2026,2026,41,42,"2026-10-09","00:00:00","2026-10-15","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-006224/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2026,2026,44,44,"2026-10-27","00:00:00","2026-10-29","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"2,3,4,5,6"]
[null,"SZCZ","V-006147/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2026,2026,40,41,"2026-10-02","00:00:00","2026-10-08","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,7"]
[null,"SZCZ","V-004402/24","Plzen - Praha","< >","Praha-Radotín","Odb Tunel",2026,2026,27,49,"2026-07-01","00:00:00","2026-12-01","23:59:00","154 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"3. + TV. ",null,null,null,"2025-12-09T10:02:25",null,null,"1,2,3,4,7"]
[null,"SZCZ","V-003076/25","Plzen - Praha","< >","Ejpovice","Plzeň hl.n.os.n.",2026,2026,34,35,"2026-08-17","18:00:00","2026-08-27","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-003066/25","Plzen - Praha","< >","Plzeň hl.n.os.n.","Ejpovice",2026,2026,32,33,"2026-08-03","18:00:00","2026-08-13","06:00:00","10 x 6 hours","Periodical","Others",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-015085/23","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,19,35,"2027-05-15","00:00:00","2027-09-03","23:59:00","112 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-013900/22","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,35,49,"2027-09-04","00:00:00","2027-12-10","23:59:00","98 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006796/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,21,21,"2027-05-24","18:00:00","2027-05-29","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006800/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,26,26,"2027-06-28","18:00:00","2027-07-03","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006805/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,32,32,"2027-08-09","18:00:00","2027-08-14","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006810/25","Plzen - Praha","< >","Odb Závodiště","Praha-Radotín",2027,2027,34,34,"2027-08-23","18:00:00","2027-08-28","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006815/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,39,39,"2027-09-27","18:00:00","2027-10-02","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006819/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,42,42,"2027-10-18","18:00:00","2027-10-23","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006824/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,45,45,"2027-11-08","18:00:00","2027-11-13","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006829/25","Plzen - Praha","< >","Praha-Radotín","Odb Závodiště",2027,2027,47,47,"2027-11-22","18:00:00","2027-11-27","06:00:00","5 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:20",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-006230/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,46,47,"2027-11-18","18:00:00","2027-11-24","06:00:00","6 x 6 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"1.,2. + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-006834/25","Plzen - Praha","< >","Odb Závodiště","Praha-Smíchov",2027,2027,49,50,"2027-12-11","00:00:00","2027-12-14","23:59:00","4 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-006397/25","Plzen - Praha","< >","Karlštejn","Odb Lom",2027,2027,39,41,"2027-09-28","00:00:00","2027-10-12","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006396/25","Plzen - Praha","< >","Odb Lom","Karlštejn",2027,2027,37,39,"2027-09-13","00:00:00","2027-09-27","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006227/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,46,46,"2027-11-15","00:00:00","2027-11-17","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006221/25","Plzen - Praha","< >","Karlštejn","Řevnice",2027,2027,45,45,"2027-11-12","00:00:00","2027-11-14","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-006136/25","Plzen - Praha","< >","Řevnice","Karlštejn",2027,2027,42,43,"2027-10-20","00:00:00","2027-10-26","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006126/25","Plzen - Praha","< >","Karlštejn","Řevnice",2027,2027,41,42,"2027-10-13","00:00:00","2027-10-19","23:59:00","7 x 6 hours","Periodical","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:23"]
[null,"SZCZ","V-006007/25","Plzen - Praha","< >","Praha-Radotín","Dobřichovice",2027,2027,30,33,"2027-07-28","00:00:00","2027-08-16","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-006006/25","Plzen - Praha","< >","Dobřichovice","Praha-Radotín",2027,2027,27,30,"2027-07-08","00:00:00","2027-07-27","23:59:00","20 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-004464/24","Plzen - Praha","< >","Praha-Smíchov","Odb Závodiště",2027,2027,49,49,"2027-12-07","00:00:00","2027-12-10","23:59:00","4 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-017964/22","Plzen - Praha","< >","Ejpovice","Chrást u Plzně",2028,2028,21,26,"2028-05-22","00:00:00","2028-06-30","23:59:00","40 days","Continuous","Bridge","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-005843/25","Praha - Chocen - Česká Třebová","< >","Velim","Kolín",2026,2026,49,50,"2026-12-05","00:00:00","2026-12-07","23:59:00","3 days","Continuous","Signal",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-005830/25","Praha - Chocen - Česká Třebová","< >","Kolín","Velim",2026,2026,49,49,"2026-12-01","00:00:00","2026-12-04","23:59:00","4 days","Continuous","Signal",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003783/25","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2026,2026,46,46,"2026-11-10","00:00:00","2026-11-12","23:59:00","3 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003768/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,46,48,"2026-11-13","00:00:00","2026-11-27","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-003765/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,48,49,"2026-11-28","00:00:00","2026-11-30","23:59:00","3 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003741/25","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2026,2026,42,43,"2026-10-14","18:00:00","2026-10-19","06:00:00","3 x 8 hours","Periodical","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003722/25","Praha - Chocen - Česká Třebová","< >","Přelouč nákl. n.","Pardubice hl.n.",2026,2026,44,46,"2026-10-26","00:00:00","2026-11-09","23:59:00","15 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-003721/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,41,42,"2026-10-08","00:00:00","2026-10-13","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003720/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč nákl. n.",2026,2026,40,41,"2026-10-02","00:00:00","2026-10-07","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003719/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,39,40,"2026-09-27","00:00:00","2026-10-01","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003718/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,38,39,"2026-09-17","00:00:00","2026-09-21","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003713/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,39,39,"2026-09-22","00:00:00","2026-09-26","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003712/25","Praha - Chocen - Česká Třebová","< >","Přelouč","Řečany nad Labem",2026,2026,37,38,"2026-09-12","00:00:00","2026-09-16","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003711/25","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2026,2026,37,37,"2026-09-07","00:00:00","2026-09-11","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003708/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2026,2026,36,36,"2026-08-31","00:00:00","2026-09-04","23:59:00","5 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003707/25","Praha - Chocen - Česká Třebová","< >","Řečany nad Labem","Záboří nad Labem",2026,2026,36,36,"2026-09-05","00:00:00","2026-09-06","23:59:00","2 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003706/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Řečany nad Labem",2026,2026,35,35,"2026-08-29","00:00:00","2026-08-30","23:59:00","2 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003703/25","Praha - Chocen - Česká Třebová","< >","Záboří nad Labem","Kolín",2026,2026,34,35,"2026-08-23","00:00:00","2026-08-28","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"2 + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-003702/25","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2026,2026,34,34,"2026-08-17","00:00:00","2026-08-22","23:59:00","6 days","Continuous","Switch",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-020979/21","Praha - Chocen - Česká Třebová","< >","Kolín","Záboří nad Labem",2027,2027,45,46,"2027-11-08","00:00:00","2027-11-15","23:59:00","8 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:19",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016647/25","Praha - Chocen - Česká Třebová","< >","Pardubice hl.n.","Přelouč",2027,2027,47,48,"2027-11-25","00:00:00","2027-12-04","23:59:00","10 days","Continuous","Maintenance",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016851/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Praha-Běchovice",2028,2028,33,33,"2028-08-14","00:00:00","2028-08-17","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016849/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Praha-Běchovice",2028,2028,32,32,"2028-08-10","00:00:00","2028-08-13","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016847/25","Praha - Chocen - Česká Třebová","< >","Praha-Běchovice","Úvaly",2028,2028,31,32,"2028-08-06","00:00:00","2028-08-09","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:21",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016832/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Úvaly",2028,2028,30,30,"2028-07-27","00:00:00","2028-07-30","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:22",null,null,"1,2,3,4,5,6"]
[null,"SZCZ","V-016831/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Úvaly",2028,2028,29,30,"2028-07-23","00:00:00","2028-07-26","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-016830/25","Praha - Chocen - Česká Třebová","< >","Úvaly","Český Brod",2028,2028,29,29,"2028-07-19","00:00:00","2028-07-22","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null," ,X,X",null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016824/25","Praha - Chocen - Česká Třebová","< >","Poříčany","Český Brod",2028,2028,27,28,"2028-07-09","00:00:00","2028-07-12","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"0. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016823/25","Praha - Chocen - Česká Třebová","< >","Poříčany","Český Brod",2028,2028,27,27,"2028-07-05","00:00:00","2028-07-08","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016822/25","Praha - Chocen - Česká Třebová","< >","Český Brod","Poříčany",2028,2028,26,27,"2028-07-01","00:00:00","2028-07-04","23:59:00","4 days","Continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-023254/18","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3"]
[null,"SZCZ","V-016966/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2026,2026,24,44,"2026-06-14","00:00:00","2026-10-27","23:59:00","96 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016907/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2026,2026,27,33,"2026-07-03","00:00:00","2026-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:24"]
[null,"SZCZ","V-016906/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2026,2026,24,53,"2026-06-14","00:00:00","2026-12-31","23:59:00","201 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:24",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-007312/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2026,2026,42,42,"2026-10-14","00:00:00","2026-10-16","23:59:00","3 x 6 hours","Periodical","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:57",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-019390/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,26,32,"2027-07-03","00:00:00","2027-08-11","23:59:00","40 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019389/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,14,14,"2027-04-08","00:00:00","2027-04-10","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"SZCZ","V-019382/25","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2027,2027,14,14,"2027-04-05","00:00:00","2027-04-07","23:59:00","3 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4"]
[null,"SZCZ","V-018478/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,22,23,"2027-06-02","00:00:00","2027-06-11","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-018467/22","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,20,21,"2027-05-17","00:00:00","2027-05-26","23:59:00","10 days","Continuous","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-018453/22","Praha - Chocen - Česká Třebová","< >","Velký Osek","Libice nad Cidlinou",2027,2027,15,16,"2027-04-16","00:00:00","2027-04-25","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"2. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-006609/24","Praha - Chocen - Česká Třebová","< >","Libice nad Cidlinou","Velký Osek",2027,2027,13,14,"2027-04-01","00:00:00","2027-04-10","23:59:00","10 x 10 hours","Periodical","Catenary",null,"LT",null,null,null,null,null,null,null,null,"1. + TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-017254/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2027,2027,26,32,"2027-07-03","00:00:00","2027-08-11","23:59:00","40 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016970/25","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2027,2027,24,26,"2027-06-14","00:00:00","2027-07-02","23:59:00","19 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:18"]
[null,"SZCZ","V-016994/25","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Hr.Králové-Sl.Př.",2027,2027,32,43,"2027-08-12","00:00:00","2027-10-27","23:59:00","77 x 8 hours","Periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016989/25","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2027,2027,24,52,"2027-06-14","00:00:00","2027-12-31","23:59:00","201 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016954/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Hradec Králové hl.n.",2027,2027,30,52,"2027-08-01","00:00:00","2027-12-31","23:59:00","153 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-016536/25","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Velký Osek",2027,2027,30,31,"2027-08-01","00:00:00","2027-08-05","23:59:00","5 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:19"]
[null,"SZCZ","V-020313/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2028,2028,43,45,"2028-10-26","00:00:00","2028-11-06","23:59:00","12 x 6 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-020309/21","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Třebechovice p.Or.",2028,2028,48,48,"2028-11-27","00:00:00","2028-11-30","23:59:00","4 x 6 hours","Periodical","Catenary","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Převýšov",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Převýšov","Choťovice",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Choťovice","Dobšice nad Cidlinou",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017336/25","Praha - Chocen - Česká Třebová","< >","Dobšice nad Cidlinou","Velký Osek-Kanín",2028,2028,50,52,"2028-12-16","00:00:00","2028-12-31","23:59:00","16 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Velký Osek-Kanín",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail","T","LT",null,null,"X",null,null," ,X,X",null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:02:20"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,5,5a,5b,6,7,7a,7b bez TV. ",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"záhlaví a zhlaví směr Nový Bydžov.",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017332/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Chlumec nad Cidlinou",2028,2028,2,50,"2028-01-10","00:00:00","2028-12-15","23:59:00","341 days","Continuous","Track & Rail",null,"ST",null,null,"X",null,null," ,X,X",null,null,"záhlaví a zhlaví směr Nové Město nad Cidlinou.",null,null,null,"2025-12-09T10:02:21"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Chlumec nad Cidlinou","Nové Město n. Cidl.",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:02:25"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Nové Město n. Cidl.","Káranice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Káranice","Dobřenice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Dobřenice","Praskačka",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Praskačka","Odb Plačice",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017204/25","Praha - Chocen - Česká Třebová","< >","Odb Plačice","Hradec Králové hl.n.",2028,2028,1,51,"2028-01-01","00:00:00","2028-12-18","23:59:00","353 days","Continuous","Track & Rail","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017175/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Odb Plačice",2028,2028,7,9,"2028-02-15","00:00:00","2028-02-28","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017160/24","Praha - Chocen - Česká Třebová","< >","Hradec Králové hl.n.","Hradec Králové hl.n.",2028,2028,11,28,"2028-03-16","00:00:00","2028-07-15","23:59:00","122 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"zhlaví SK1-9,2-6 směr HK-Slezské P. a Předměřice n. L..",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017151/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2028,2028,9,11,"2028-03-01","00:00:00","2028-03-15","23:59:00","15 days","Continuous","Miscellaneous",null,"LT",null,null,null,null,null," ,X,X",null,null,"zab. zař. TZZ.",null,null,null,"2025-12-09T10:04:57"]
[null,"SZCZ","V-017150/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hradec Králové hl.n.",2028,2028,5,48,"2028-02-01","00:00:00","2028-12-03","23:59:00","307 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hradec Králové hl.n.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"LT",null,null,"X",null,null,null,null,null,"traťová jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Třebechovice p.Or.","Třebechovice p.Or.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017140/24","Praha - Chocen - Česká Třebová","< >","Hr.Králové-Sl.Př.","Hr.Králové-Sl.Př.",2028,2028,1,52,"2028-01-01","00:00:00","2028-12-31","23:59:00","366 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null,null,null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:04:58"]
[null,"SZCZ","V-017139/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Hr.Králové-Sl.Př.",2028,2028,50,52,"2028-12-17","00:00:00","2028-12-31","23:59:00","15 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:04:59"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,19,20,"2028-05-13","00:00:00","2028-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"1,2,3,4,8 bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017135/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,19,20,"2028-05-13","00:00:00","2028-05-15","23:59:00","3 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017134/24","Praha - Chocen - Česká Třebová","< >","Týniště nad Orlicí","Týniště nad Orlicí",2028,2028,18,19,"2028-05-07","00:00:00","2028-05-12","23:59:00","6 days","Continuous","Miscellaneous",null,"ST",null,null,"X",null,null," ,X,X",null,null,"celá jen TV. \nzáhlaví a zhlaví směr Borohrádek a Častolovice.",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017131/24","Praha - Chocen - Česká Třebová","< >","Borohrádek","Týniště nad Orlicí",2028,2028,39,41,"2028-09-27","00:00:00","2028-10-10","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová + TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019018/21","Praha - Chocen - Česká Třebová","< >","Plzeň hl.n.N.Hospoda","Nýřany",2026,2026,27,53,"2026-06-29","00:00:00","2026-12-31","23:59:00","186 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002607/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Vejprnice",2026,2026,29,53,"2026-07-18","00:00:00","2026-12-31","23:59:00","167 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002586/25","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2026,2026,45,45,"2026-11-07","00:00:00","2026-11-08","23:59:00","2 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-019022/21","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2027,2027,2,13,"2027-01-15","00:00:00","2027-04-01","23:59:00","77 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017672/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Výh Chotěšov",2027,2027,43,44,"2027-10-27","18:00:00","2027-11-04","06:00:00","8 x 6 hours","periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-017664/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Výh Chotěšov",2027,2027,42,43,"2027-10-19","00:00:00","2027-10-26","23:59:00","8 x 12 hours","periodical","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-003831/24","Regensburg - Plzen","< >","Nýřany","Výh Chotěšov",2027,2027,2,25,"2027-01-15","00:00:00","2027-06-25","23:59:00","162 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002814/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Nýřany",2027,2027,53,2,"2027-01-01","00:00:00","2027-01-14","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"SZCZ","V-002608/25","Regensburg - Plzen","< >","Plzeň hl.n.N.Hospoda","Vejprnice",2027,2027,53,2,"2027-01-01","00:00:00","2027-01-14","23:59:00","14 days","Continuous","Miscellaneous","T","LT",null,null,null,null,null," ,X,X",null,null,"traťová bez TV. ",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311013","Bratislava - Rajka","< >","Bratislava ÚNS","Bratislava-Petržalka",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"Rekonštrukcia koľají č. 1, 2 (mimo DŽM)",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311009","Bratislava - Rajka","< >","Bratislava-Nové Mesto","Bratislava ÚNS",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č. 1, 2",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311007","Bratislava - Štúrovo","< >","Dvory nad Žitavou","Dvory nad Žitavou",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Switch",null,"ST",null,null,null,null,null,null,null,null,"Rekonštrukcia výhybiek č. 1,2,3,4,5,6,7,8 ",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311012","Kúty - Bratislava","< >","Kúty št. hr.","Devínska Nová Ves",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia dvoch úsekov železničnej trate štátna hranica ČR/SR - Devínska Nová Ves",null,null,null,"2025-12-09T10:06:30"]
[null,"ŽSR","56TT2311010","Kúty - Bratislava","< >","Malacky","Kúty",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,"Modernizácia železničnej trate Devínska Nová Ves - štátna hranica SR/ČR + DOZZ, ETCS",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","56TT2311008","Kúty - Galanta","< >","Šelpice","Boleráz",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"KRŽZ koľ. č.1",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR","56TT2311011a","Kúty - Galanta","< >","Trnava","Križovany nad Dudváhom",2026,2026,1,53,"2026-01-01","08:00:00","2026-12-31","17:00:00",null,"Periodical","Signal",null,"LT",null,null,null,null,null,null,null,null,"CRD Trnava + dispečerizácia Trnava - Križovany",null,null,null,"2025-12-09T10:06:30",null,null,"1,2,3,4,5,6,7"]
[null,"ŽSR",5626156,"Zilina - Cierna nad Tisou","< >","Vydrník","Poprad Tatry",2025,2028,9,4,"2025-03-02","08:00:00","2028-01-29","17:00:00",null,"Continuous","miscellaneous",null,"x","x",null,null,null,null,null,null,null,"Modernisation",null,"Y",null,"2025-12-09T10:05:00"]

{"sheet":"Graphic Overview","index":2,"n_rows":211,"n_cols":374,"rows_kept":211,"cut":false,"hidden":false,"merged":[[3,250,3,256],[3,257,3,263],[3,264,3,270],[3,271,3,277],[3,278,3,284],[3,285,3,291],[3,292,3,298],[3,299,3,305],[3,306,3,312],[3,313,3,319],[3,243,3,249],[3,173,3,179],[3,180,3,186],[3,187,3,193],[3,194,3,200],[3,201,3,207],[3,208,3,214],[3,215,3,221],[3,222,3,228],[3,229,3,235],[3,236,3,242],[3,138,3,144],[3,145,3,151],[3,152,3,158],[3,159,3,165],[3,166,3,172],[3,103,3,109],[3,110,3,116],[3,117,3,123],[3,124,3,130],[3,131,3,137],[3,75,3,81],[3,82,3,88],[3,89,3,95],[3,96,3,102],[3,9,3,11],[3,12,3,18],[3,19,3,25],[3,26,3,32],[3,33,3,39],[3,40,3,46],[3,47,3,53],[3,54,3,60],[3,61,3,67],[3,68,3,74],[3,355,3,361],[3,362,3,368],[3,369,3,373],[2,343,2,373],[2,313,2,342],[3,348,3,354],[3,320,3,326],[3,327,3,333],[3,334,3,340],[3,341,3,347],[0,1,1,7],[2,9,2,39],[2,282,2,312],[2,99,2,128],[2,129,2,159],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,40,2,67],[2,68,2,98]]}
[null,"RFC 9 Overview"]
[]
[null,null,null,null,null,null,2027,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Frankfurt - Karlsruhe",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,null,null,null,5,5,5,5,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Karlsruhe - Strasbourg"]
[null," "]
[]
[null,"Darmstadt - Nürnberg",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Nürnberg - Passau",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null," "]
[]
[null,"Nürnberg - Plzen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,2,2,1,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Regensburg - Plzen",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Passau - Wels"]
[null," "]
[]
[null,"Karlsruhe - München",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,2,2,2,2,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,null,null,null,null,null,null,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"München - Salzburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5]
[null," "]
[]
[null,"München - Regensburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null," "]
[]
[null,"Salzburg - Wels"]
[null," "]
[]
[null,"Wels - Linz"]
[null," "]
[]
[null,"Wels - Traun - Linz"]
[null," "]
[]
[null,"Linz - Wien (NRZ)"]
[null," "]
[]
[null,"Linz - Wien (GZ)"]
[null," "]
[]
[null,"Wien - Hegyeshalom"]
[null," "]
[]
[null,"Wien - Ebenfurth - Sopron"]
[null," "]
[]
[null,"Sopron - Györ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Hegyeshalom - Rajka"]
[null," "]
[]
[null,"Hegyeshalom-Ferencváros",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros-Szajol"]
[null," "]
[]
[null,"Ferencváros-Szajol (120)"]
[null," "]
[]
[null,"Szajol-Curtici"]
[null," "]
[]
[null,"Szajol - Biharkeresztes"]
[null," "]
[]
[null,"Arad - Simeria"]
[null," "]
[]
[null,"Arad - Craiova",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Simeria -  Brasov",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Bucuresti-Constanta"]
[null," "]
[]
[null,"Coslariu - Cluj Napoca"]
[null," "]
[]
[null,"Biharkeresztes - Cluj Napoca",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,3]
[null," "]
[]
[null,"Curtici - Arad"]
[null," "]
[]
[null,"Wilhelmshaven - Bremen"]
[null," "]
[]
[null,"Bremerhaven - Bremen"]
[null," "]
[]
[null,"Bremen - Hannover",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Hannover - Magdeburg"]
[null," "]
[]
[null,"Magdeburg - Falkenberg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Falkenberg - Dresden",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Hamburg - Magdeburg",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,2,2,2,2,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null," "]
[]
[null,"Rostock - Berlin",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Berlin - Dresden",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Dresden - Děčín",null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null," "]
[]
[null,"Děčín - Kolín"]
[null," "]
[]
[null,"Děčín - Praha-Libeň"]
[null," "]
[]
[null,"Praha - Chocen - Česká Třebová",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Hranice na Morave - Ostrava",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Plzen - Praha",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Hranice na Morave - Zilina",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ostrava - Zilina",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Zilina - Cierna nad Tisou",null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Kolín - Brno-Maloměřice"]
[null," "]
[]
[null,"Česká Třebová - Brno"]
[null," "]
[]
[null,"Brno - Břeclav"]
[null," "]
[]
[null,"Břeclav - Wien"]
[null," "]
[]
[null,"Břeclav - Kúty"]
[null," "]
[]
[null,"Kúty - Bratislava"]
[null," "]
[]
[null,"Bratislava - Rajka"]
[null," "]
[]
[null,"Bratislava - Štúrovo"]
[null," "]
[]
[null,"Nové Zámky - Komárom"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Rajka - Hegyeshalom"]
[null," "]
[]
[null,"Štúrovo - Ferencváros"]
[null," "]
[]
[null,"Kúty - Galanta"]
[null," "]
[]
[null,"Chocen - Hranice na Morave",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,null,null,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3]
[null," "]
[]
[null,"Ferencváros - Kelebia"]
[null," "]
[]
[null,"Bucuresti - Giugiu",null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[null,"Videle - Giurgiu",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5]
[null," "]
[]
[]
[]
[]
[null,"Error in *All day*, *Day* or *Night*"]
[null,"| 2355 | 2356 "]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":68,"n_cols":23,"rows_kept":68,"cut":false,"hidden":true,"merged":[[0,0,0,1],[0,2,0,3]]}
["IM",null,"Section",null,"Direction","Duration","ID value","Reason for restriction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Other","In yearly timetable","Classification","Status","Automatic process","Year","Week"]
["DB InfraGO AG",80,"Frankfurt - Karlsruhe",1,"< >","Continuous",26616,"Signal","T","LT","S","W","Do","C,,","R,,",",B,","O,,","Y","Major","Planned","Y",2024,1]
["SZCZ",54,"Karlsruhe - Strasbourg",2,">","Periodical",null,"Switch",null,"ST",null,"L",null,",C,",",R,",",,B",",O,","N","High","Coordination","N",2025,2]
["ŽSR",56,"Darmstadt - Nürnberg",3,"<",null,null,"Catenary",null,"LT+ST",null,"P",null,",,C",",,R",",B,B",",,O",null,"Medium","Consultation",null,2026,3]
["ÖBB Infra",81,"Nürnberg - Passau",4,null,null,null,"Track & Rail",null,null,null,"W+L",null,"C,C,","R,R,",null,"O,O,",null,"Minor","Published",null,2027,4]
["MÁV",55,"Nürnberg - Plzen",5,null,null,null,"Tunnel",null,null,null,"W+P",null,"C,,C","R,,R",null,"O,,O",null,null,"Canceled",null,null,5]
["GYSEV",55,"Regensburg - Plzen",6,null,null,null,"Bridge",null,null,null,"L+P",null,",C,C",",R,R",null,",O,O",null,null,null,null,null,6]
["SNCF-R",87,"Passau - Wels",7,null,null,null,"Miscellaneous",null,null,null,"W+L+P",null,"C,C,C","R,R,R",null,"O,O,O",null,null,null,null,null,7]
["CFR",53,"Karlsruhe - München",8,null,null,null,"Maintenance",null,null,null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,"München - Salzburg",9,null,null,null,"Others",null,null,null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,"München - Regensburg",10,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,"Salzburg - Wels",11,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,"Wels - Linz",12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,"Wels - Traun - Linz",13,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,"Linz - Wien (NRZ)",14,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,"Linz - Wien (GZ)",15,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,"Wien - Hegyeshalom",16,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,"Wien - Ebenfurth - Sopron",17,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,"Sopron - Györ",18,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,"Rajka - Hegyeshalom",19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,"Hegyeshalom - Rajka",20,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20]
[null,null,"Hegyeshalom-Ferencváros",21,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,21]
[null,null,"Ferencváros-Szajol",22,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22]
[null,null,"Ferencváros-Szajol (120)",23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,23]
[null,null,"Szajol-Curtici",24,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,24]
[null,null,"Szajol - Biharkeresztes",25,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25]
[null,null,"Arad - Simeria",26,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,26]
[null,null,"Arad - Craiova",27,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,27]
[null,null,"Simeria -  Brasov",28,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,28]
[null,null,"Bucuresti-Constanta",29,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,29]
[null,null,"Coslariu - Cluj Napoca",30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30]
[null,null,"Biharkeresztes - Cluj Napoca",31,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,31]
[null,null,"Curtici - Arad",32,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,32]
[null,null,"Wilhelmshaven - Bremen",33,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,33]
[null,null,"Bremerhaven - Bremen",34,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,34]
[null,null,"Bremen - Hannover",35,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,35]
[null,null,"Hannover - Magdeburg",36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36]
[null,null,"Magdeburg - Falkenberg",37,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,37]
[null,null,"Falkenberg - Dresden",38,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,38]
[null,null,"Hamburg - Magdeburg",39,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,39]
[null,null,"Rostock - Berlin",40,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40]
[null,null,"Berlin - Dresden",41,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,41]
[null,null,"Dresden - Děčín",42,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,42]
[null,null,"Děčín - Kolín",43,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43]
[null,null,"Děčín - Praha-Libeň",44,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,44]
[null,null,"Praha - Chocen - Česká Třebová",45,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,45]
[null,null,"Hranice na Morave - Ostrava",46,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,46]
[null,null,"Plzen - Praha",47,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,47]
[null,null,"Hranice na Morave - Zilina",48,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48]
[null,null,"Ostrava - Zilina",49,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,49]
[null,null,"Zilina - Cierna nad Tisou",50,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50]
[null,null,"Kolín - Brno-Maloměřice",51,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,51]
[null,null,"Česká Třebová - Brno",52,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,52]
[null,null,"Brno - Břeclav",53]
[null,null,"Břeclav - Wien",54]
[null,null,"Břeclav - Kúty",55]
[null,null,"Kúty - Bratislava",56]
[null,null,"Bratislava - Rajka",57]
[null,null,"Bratislava - Štúrovo",58]
[null,null,"Nové Zámky - Komárom",59]
[null,null,"Kúty - Galanta",60]
[null,null,"Rajka - Hegyeshalom",61]
[null,null,"Štúrovo - Ferencváros",62]
[null,null,"Kúty - Galanta",63]
[null,null,"Chocen - Hranice na Morave",64]
[null,null,"Ferencváros - Kelebia",65]
[null,null,"Bucuresti - Giugiu",66]
[null,null,"Videle - Giurgiu",67]